## PROG PRI
# | JOB | DAY TURN | LINES | THT | REQUEST DATE | PROGRAMMER | PROG STARTED | NEED BY / PROG NOTES | NOTES | NEW / REPEAT | STATUS | NOTES
| 128842 | 10 | 55 | 5 | 2024-10-16 |  | DONE |  |  | NEW | NOT CLEAR
| 128838 | 10 | 75 | 9 | 2024-10-16 |  | DONE |  |  | NEW | NOT CLEAR
| 129014 | 2 | 45 | 22 |  |  | DONE |  | KIT BOX/PCB HERE | NEW | NOT CLEAR
| 129068 | 10 | 80 | 18 | 2024-10-21 |  | DONE |  | 10/21 - KIT CLEAR | NEW | NOT CLEAR
| 129188 | 5 | 82 | 0 | 2024-10-22 |  | DONE |  | 10/24 - PCB DUE | NEW | NOT CLEAR
| 128690 | 10 | 105 | 1 |  |  | DONE |  | 10/22 - KIT CLEAR | NEW | NOT CLEAR
| 128573 | 20 | 99 | 12 |  |  | Y |  | 10/21 - KIT CLEAR | NEW | NOT CLEAR
| 128910 | 5 | 146 | 52 |  |  |  |  | 10/30 - PCB DUE | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
[10 empty] | NEW | NOT CLEAR
NOT CLEAR
NOT CLEAR
| COMPLETED | [9 empty] | NOT CLEAR
| 119713 | 5 | 33 |  |  | RAY | DONE | SUBMITTING SETUP SHEETS 9/15@6 AM | high THT count | NEW | NOT CLEAR
| 120492 | 5 | 34 |  |  | RAY | DONE | SUBMITTING SETUP SHEETS 9/15@6 AM |  | NEW
| 120153 | 5 | 49 |  |  | RAY | DONE | 9/15 12:00 PM | SMT CLEAR, but HAS SHIP DATE | RONC
| 120561 | 5 | 63 |  |  | RAY | DONE | SUBMITTING SETUP SHEETS 9/15@12 PM |  | NEW
| 119676 | 15 | 49 |  |  | RAY | DONE | 9/18 6:00 AM |  | NEW | KIT CLEAR
| 118820 | 3 | 68 |  |  | RAY | DONE | 9/18 (ASAP) | 2ND ARTICLE | RONC | KIT CLEAR
| 120559 | 10 | 65 |  |  | RAY | DONE 9/20 | 9/18 (EOD) |  | ROWC | NOT CLEAR
| 120614 | 5 | 99 |  |  | NAM | DONE 9/16 | 9/18 6:00 AM |  | NEW | KIT CLEAR
| 118916 | 5 | 48 |  |  | NAM | DONE 9/17 | 9/18 6:00 AM | SHORT 1 SMT PART | NEW | KIT CLEAR
| 119431 | 20 | 96 |  |  | NAM | DONE 9/17 | 9/18 |  | NEW | KIT CLEAR
1 | 120152 | 5 | 31 |  |  | RAY | DONE 9/18 | 9/18 6:00 AM |  | NEW | KIT CLEAR 9/18
2 | 120432 | 10 | 43 |  |  | RAY | DONE 9/18 | 9/18 (EOD) | WILL CLEAR SOON | ROWC | KIT CLEAR
3 | 120636 | 5 | 1 |  |  | SMT | DONE 9/19 | 9/18 (EOD) | PCB DUE 9/19 | NEW | NOT CLEAR
4 | 120638 | 5 | 123 |  |  | NAM | DONE 9/20 | 9/19 |  | NEW | KIT CLEAR
6 | 120883 | 3 | 3 |  |  | SMT | DONE 9/20 | 9/20 | PROGRAM ON SMT LINE | NEW | NOT CLEAR
4 | 120686 | 3 | 2 |  |  | SMT | DONE 9/20 | 9/20 | PROGRAM ON SMT LINE | NEW | NOT CLEAR
4 | 120092 | 3 | 1 |  |  | SMT | DONE 9/20 | 9/20 | PROGRAM ON SMT LINE | NEW | NOT CLEAR
3 | 120474 | 10 | 3 |  |  | SMT | DONE 9/20 | 9/19 (EOD) 9/20 |  | NEW | KIT CLEAR 9/19
1 | 120745 | 5 | 65 |  |  | RAY | DONE | SUBMITTED | KIT CLEAR 9/15 | NEW | NOT CLEAR
2 | 119829 | 20 | 27 |  |  | RAY | DONE | SUBMITTED | KIT CLEAR 9/15 | RONC | NOT CLEAR
5 | 120387 | 5 | 106 |  |  | NAM | DONE 9/20 | 9/19 |  | NEW | NOT CLEAR
1 | 120532 | 5 | 22 |  |  | RAY | DONE 9/21 | SUBMITTED |  | NEW | KIT CLEAR 9/18
5 | 120702 | 5 | 79 |  | 2023-09-20 | RAY | DONE 9/21 | SUBMITTED | WILL CLEAR 9/20 | ROWC 117480 | KIT CLEAR 9/19
4 | 120529 | 5 | 10 |  | 2023-09-20 | RAY | DONE 9/21 | 9/21 6am | WILL CLEAR 9/20 | NEW | KIT CLEAR
3 | 120664 | 10 | 110 |  |  | NAM | DONE 9/22 | 9/20 |  | NEW | KIT CLEAR 9/19
3 | 119290 | 10 | 106 |  |  | NAM | DONE 9/23 | 9/20 |  | NEW | NOT CLEAR
5 | 119568 | 9 | 118 |  |  | NAM | DONE 9/24 | 9/20 |  | NEW | KIT CLEAR
2 | 120528 | 5 | 25 |  | 2023-09-20 | RAY | DONE 9/25 | 9/21 6 am |  | NEW | KIT CLEAR
6 | 120284 | 10 | 58 |  |  | RAY | DONE 9/25 | 9/21 |  | ROWC | KIT CLEAR 9/18
3 | 119577 | 10 | 13 |  |  | RAY | DONE 9/26 | 9/21 |  | NEW | NOT CLEAR
2 | 119291 | 10 | 99 |  | 2023-09-25 | NAM | DONE 9/26 | 9/25 |  | NEW | NOT CLEAR
| 119346-3 | 5 | 1 |  |  | SMT |  |  |  | RONC-DR | NOT CLEAR
| 117822 | 20 | 1 |  |  | SMT |  |  |  | RONC-DR | NOT CLEAR
4 | 118067-2 | 5 | 93 |  | 2023-09-22 | NATION | DONE 9/27 | 9/25 | Gerber changed/New program complete | ROWC 2ND | KIT CLEAR
6 | 120864 | 5 | 37 |  | 2023-09-25 | NAM | DONE 9/27 | 9/26 |  | NEW | KIT CLEAR
3 | 120701 | 5 | 54 |  |  | RAY | DONE 9/27 | 9/25 6:00 AM |  | NEW | NOT CLEAR
| 119431-2 | 5 | 222 |  |  | ROBERT | DONE 9/26 |  |  | ROWC-DR | NOT CLEAR
3 | 120423 | 5 | 75 |  | 2023-09-26 | NAM | DONE 9/28 | 9/26 |  | NEW | NOT CLEAR
8 | 120825 | 10 | 53 |  |  | ROBERT | DONE 9/28 | 10/2 |  | RONC | NOT CLEAR
| 120287 | 10 | 6 |  |  | SMT |  |  |  | NEW | NOT CLEAR
| 120758 | 10 | 89 |  |  | ROBERT |  |  |  | ROWC-DR 9/25 | NOT CLEAR
| 120284 | 10 | 58 |  |  | ROBERT |  |  |  | ROWC-DR 9/13 | NOT CLEAR
| 120688 | 15 | 68 |  | 2023-09-27 | ROBERT |  | 10/7 |  | ROWC-DR 9/25 | NOT CLEAR
3 | 120276 | 5 | 72 |  | 2023-09-26 | NAM | DONE 9/29 | 9/27 |  | NEW
1 | 121017 | 3 | 84 |  | 9/29 9/26 | NAM | DONE 9/29 | 9/29 | KIT CLEAR | NEW | NOT CLEAR
| 120284 | 100 | 58 |  | 2023-10-03 | ROBERT |  |  | KIT CLEAR 10/2 | ROWC | NOT CLEAR
| 117366 | 10 | 7 |  |  | SMT |  |  | KIT CLEAR 10/3 | NEW | NOT CLEAR
3 | 119322 | 5 | 252 |  |  | NAM | DONE 10/2 | 9/19 |  | NEW | NOT CLEAR
4 | 120730 | 5 | 105 |  | 2023-09-26 | NAM | DONE 10/2 | 9/28 |  | NEW | NOT CLEAR
1 | 118595 | 7 | 53 |  | 2023-09-30 | NAM | DONE 10/3 | ASAP 10/5 | KIT CLEAR | NEW
8 | 120932 | 5 | 54 |  | 2023-10-03 | NATION | DONE 10/4 | 10/5 |  | NEW-DR 9/29
1 | 120297 | 10 | 148 |  | 2023-09-15 | NAM | DONE 10/4 | 10/3 9/22 | PCB DUE 9/28 | NEW | NOT CLEAR
2 | 120758 | 10 |  |  |  |  | DONE 10/4 |  |  | ROWC | NOT CLEAR
1 | 121088 | 3 | 99 |  | 2023-10-02 | NAM | DONE 10/5 | 10/3 |  | NEW
5 | 119594 | 10 | 98 |  | 2023-09-26 | NAM | DONE 10/6 | 9/29 |  | NEW
2 | 120533 | 10 | 128 |  |  |  | DONE 10/9 | WILL CLEAR 10/10 |  | NEW | NOT CLEAR
8 | 120970 | 10 | 52 |  | 2023-09-26 | NAM | DONE 10/9 | 10/3 |  | NEW-DR 9/26
7 | 119432-1 | 5 | 148 |  | 2023-09-26 | NAM | DONE 10/9 | 10/2 |  | NEW | NOT CLEAR
2 | 121252 | 5 |  |  |  | RAY | DONE 10/9 | WILL CLEAR WEEK OF 10/9 | NO DOCS | NEW | NOT CLEAR
1 | 121051 | 5 | 32 |  | 2023-10-11 | NAM | DONE 10/12 | 10/11 |  | NEW | NOT CLEAR
1 | 120938 | 10 | 74 |  | 2023-10-11 | NAM | DONE 10/13 | 10/12 |  | NEW | NOT CLEAR
1 | 120110 | 10 | 131 |  | 2023-10-11 | NAM | DONE 10/16 | 10/13 |  | NEW-DR 10/2 | NOT CLEAR
2 | 120927 | 5 | 71 |  | 2023-10-11 | NAM | DONE 10/16 | 10/16 |  | NEW-DR 10/10 | NOT CLEAR
| 121006 | 10 | 66 |  | 2023-10-11 | NAM | DONE 10/16 | 10/16 |  | NEW-DR 10/10 | KIT CLEAR
1 | 121007 | 5 | 66 |  | 2023-10-16 | NAM |  | 2023-10-17 | SHARES PROGRAM W/ B121006 | ROWC-DR | NOT CLEAR
1 | 120886 | 5 | 78 |  | 2023-10-16 | ROBERT | DONE | 2023-10-17 |  | RONC-DR | NOT CLEAR
1 | 120927 | 5 | 71 |  | 2023-10-16 | NATION | DONE | 2023-10-18 |  | NEW-DR | NOT CLEAR
2 | 120790 | 10 | 26 |  | 2023-10-16 | NATION | DONE | oct 19 10/23/2023 | WILL CLEAR 10/19 | NEW-DR | NOT CLEAR
1 | 120762 | 5 | 81 |  | 2023-10-16 | NATION | DONE | 2023-10-18 | ETA ON LINE 10/23 | NEW-DR | NOT CLEAR
1 | 119482-2 | 10 | 9 |  | 2023-10-19 | NATION | DONE | 2023-10-20 | SMT CLEAR | 2ND ARTICLE | NOT CLEAR
2 | 119480-2 | 10 | 43 |  | 2023-10-19 | NATION | DONE | 2023-10-20 | 394 OF 395 CLEAR | 2ND ARTICLE | NOT CLEAR
6 | 117944 | 10 | 106 |  | 2023-10-18 | NATION | DONE | 2023-10-26 |  | RONC | NOT CLEAR
1 | 120130-1 | 5 | 100 | 0 | 2023-10-16 | NATION | DONE 10/23 | 2023-10-24 |  | NEW | NOT CLEAR
3 | 121408 | 5 | 47 | 15 | 1902-10-16 | NATION | DONE 10/23 | 2023-10-24 |  | NEW | NOT CLEAR
4 | 121521 | 5 | 44 | 1 | 2023-10-20 | NATION | DONE 10/24 | 2023-10-24 |  | NEW | NOT CLEAR
| 120096 | 5 | 56 | 4 | 2023-10-24 | ROBERT/NATION | DONE 10/25 |  |  | RONC 1ST ARTICLE
1 | 121504 | 3 | 108 | 0 | 2023-10-20 | NAM | done 10/25 | OCT 25 8 am 10/23/2023 |  | NEW | NOT CLEAR
2 | 117812 | 10 | 119 | 1 | 2023-10-16 | NAM | done 10/25 | 2023-10-25 |  | NEW | NOT CLEAR
3 | 121432 | 5 | 29 | 35 | 2023-10-24 | NATION / ROBERT | DONE 10/24 | 2023-10-25 |  | ROWC | NOT CLEAR
4 | 120807 | 10 | 40 | 0 | 2023-10-24 | NATION / ROBERT | DONE 10/26 | 2023-10-25 |  | RONC
5 | 121232 | 5 | 43 | 0 | 2023-10-20 | NATION | DONE 10/25 | 2023-10-26 | KIT CLEAR 10/24 - Feeder list in kit box | NEW | NOT CLEAR
6 | 121284 | 5 | 72 | 0 | 2023-10-25 | NATION | DONE 10/26 | 2023-10-26 | Should clear 10/26 - Feeder list in kit box | NEW | NOT CLEAR
8 | 108434 | 20 | 60 | 0 | 2023-10-24 | NATION / ROBERT | DONE 10/25 | 2023-10-27 |  | RONC | NOT CLEAR
1 | 121062 | 15 | 11 | 1 | 2023-10-18 | NATION | DONE 10/26 | 2023-10-27 | PCBS DUE 10/31 | NEW-DR | NOT CLEAR
1 | 121472 | 5 | 75 | 11 | 2023-10-25 | NATION | DONE 10/27 | 2023-10-27 | EXPECTED CLEAR DATES 10/26 OR 10/27 CUSTOMER ASKING FOR JOB | NEW | kit clear
1 | 121032 | 10 | 48 | 28 | 2023-10-24 | NATION | DONE | oct 27 10/30/2023 | KIT CLEAR - QTY 25 DUE 11/17 | NEW | kit clear
1 | 121693 | 3 | 71 | 1 | 2023-10-26 | NATION | DONE | 2023-10-30 | PCBs DUE 11/2 | NEW | NOT CLEAR
2 | 121364 | 5 | 101 | 61 | 2023-10-30 | NATION | DONE | 10/31/2023 noon | KIT CLEAR: SHIP DATE 11/6 - Feeder list in kit box AWT PART CONF THAN SMT CLEAR | NEW | NOT CLEAR
1 | 121658 | 5 | 80 | 8 | 2023-10-31 | NATION | DONE | 11/1/2023 noon | PCBS DUE 11/1 - Feeder setup list in Gerry's area. | NEW | NOT CLEAR
2 | 121705 | 10 | 1 | 47 | 2023-10-31 | NATION / ROBERT | DONE | 2023-11-01 | PCBS DUE 11/8 | RONC | KIT CLEAR
5 | 120324-2ND | 10 | 46 | 4 |  | NATION / ROBERT | DONE |  |  | ROWC | NOT CLEAR
1 | 120897 | 10 | 58 | 2 | 2023-10-26 | NATION | DONE | NOV 1 10/31/2023 | PCBS DUE 11/3 - Feeder list in kit box at stockroom. | NEW | KIT CLEAR
2 | 121155 | 10 | 86 | 8 | 2023-10-26 | NATION | DONE | NOV 2 10/31/2023 | PCBS DUE 11/3 | NEW | NOT CLEAR
1 | 121557 | 5 | 96 | 11 | 2023-11-01 | NATION | DONE | 2023-11-03 | 11/6 - Expected clear date | NEW | NOT CLEAR
1 | 116950 | 3 | 6 | 5 | 2023-11-02 | NATION | DONE | 2023-11-03 | 11/10 - PCB DUE - Can't find B116860. Did B116950 instead (a 6 Line 3 Day Turn job) | NEW
1 | 116964 | 3 | 63 | 9 | 2023-11-03 | NATION | DONE | 2023-11-06 | 11/7 - pcb due | NEW | NOT CLEAR
2 | 121617 | 5 | 124 | 7 | 2023-11-03 | NATION | DONE | 2023-11-06 | 11/7 - Expected clear date | NEW | NOT CLEAR | THOMAS (11/1): CHANGED DUE DATE FROM NOV 1 TO NOV 2, BECAUSE OF OTHER JOBS CLEARING THAT WE NEED PROGRAMS FOR FIRST
1 | 121671 | 5 | 89 | 43 | 2023-11-01 | NATION | DONE | 2023-11-07 | 11/7 - Expected clear date - Feeder list in Gerry's | NEW | NOT CLEAR
2 | 116956 | 10 | 28 | 3 | 2023-11-03 | NATION | DONE | 2023-11-07 | 11/6 - SHORT ATTRITION 11/3 - PCB DUE TODAY | NEW
5 | 116954 | 10 | 24 | 1 | 2023-11-03 | NATION | DONE | 2023-11-08 | 11/6 - pcb due | NEW | NOT CLEAR
6 | 116970 | 15 | 29 | 11 | 2023-11-03 | NATION | DONE | 2023-11-08 | AWT 1 PART CONF | NEW | NOT CLEAR
3 | 121788 | 5 | 104 | 4 | 2023-11-03 | NATION | DONE | 2023-11-08 | 11/9 - PCB DUE | NEW | NOT CLEAR
1 | 120925 | 5 | 161 | 35 | 2023-11-06 | NATION | DONE | 2023-11-08 | AWT PART CONF THAN SMT CLEAR | NEW | NOT CLEAR
1 | 121416 | 5 | 113 | 11 | 2023-11-02 | NATION | DONE | 2023-11-09 | 11/10 - PCB DUE | NEW | NOT CLEAR
1 | 121870 | 3 | 114 | 2 | 2023-11-08 | NATION | DONE | 2023-11-13 | 11/20 - PCB DUE | NEW | NOT CLEAR
1 | 121413 | 5 | 131 | 10 | 2023-11-09 | NATION | DONE | 11/13/2023 MORNING | 11/13 - PCB DUE | NEW
4 | 121008 | 5 | 127 | 4 | 2023-11-10 | NAM | DONE | nov 14 morning | 11/21 - PCB DUE | NEW
2 | 121854 | 5 | 51 | 3 | 2023-11-08 | NATION | DONE | NOV 14 11/13/2023 | 11/15 - PCB DUE | NEW | NOT CLEAR
1 | 121581 | 10 | 88 | 12 | 2023-11-09 | NATION | DONE | 2023-11-15 | 11/17 - PCB DUE | NEW | NOT CLEAR
1 | 121829 | 5 | 34 | 0 | 2023-11-13 | NAM | DONE | 2023-11-15 | N/A | NEW | NOT CLEAR
1 | 121959 | 5 | 114 | 5 | 2023-11-15 | NATION | DONE | 2023-11-16 | POSSIBLY CLEAR TODAY |  | NOT CLEAR
3 | 122608 | 5 | 86 | 8 | 2023-12-20 | NATION | DONE | 2023-12-27 |  | ROWC B121155 | NOT CLEAR
1 | 121008 | 20* | 127 | 4 | 2023-12-20 | NATION/NAM | Update done/Original Program Nam | 2023-12-22 | SCHEDULED SPLIT SHIPMENT - WAITING FOR PROGRAM FROM MACHINE | ROWC 1st Article | NOT CLEAR
1 | 122635 | 5 | 64 | 35 | 2023-12-21 | NATION | DONE | 2023-12-22 | WILL CLEAR TODAY 12/22 | NEW | NOT CLEAR
1 | 122507 | 5 | 58 | 10 | 2023-12-21 | NATION | DONE | 2023-12-26 | SMT CLEAR 12/22 | NEW | NOT CLEAR
2 | 122472 | 10 | 71 | 42 | 2023-12-20 | NATION | DONE | 2023-12-27 |  | NEW | NOT CLEAR
| 122836 | 5 | 128 | 0 | 2024-01-02 | NATION | DONE | 2024-01-03 | DAY 1 IS 1/3 | NEW | NOT CLEAR
| 122846 | 10 | 127 | 34 | 2024-01-02 | NATION | DONE | 2024-01-04 | SHORTAGE DUE 1/4 | NEW | NOT CLEAR
| 122397 | 10 | 57 | 27 | 2024-01-04 | NATION | DONE | 2024-01-09 | 1/11 - PCB DUE | NEW | NOT CLEAR
| 122618 | 5 | 60 | 90 | 2024-01-05 | NATION | DONE | 2024-01-09 | 1/8 - PCB DUE; NO ETA ON BGA | NEW | NOT CLEAR
| 122850 | 10 | 86 | 4 | 2024-01-08 | NATION | DONE | 2024-01-09 | MAY NEED TO EXPEDITE | NEW | NOT CLEAR
| 123058 | 5 | 65 | 11 | 2024-01-11 | NATION | DONE | 2024-01-15 | 1/16 - PCB DUE | NEW | NOT CLEAR
| 123123 | 10 | 34 | 13 | 2024-01-19 | NATION | DONE | 2024-01-22 | AWT PART CONF |  | NOT CLEAR
| 123193 | 5 | 84 | 59 | 2024-01-23 | NATION | DONE |  | 1/25 - PCB DUE | NEW | NOT CLEAR
| 119889 | 15 | 48 | 8 | 2024-01-25 | NATION | DONE |  | PRE-EMPTIVE FOR DAY OFFS | ROWC | NOT CLEAR
| 120828 | 10 | 120 | 18 |  |  | DONE |  | KIT NOT RELEASED | RONC | NOT CLEAR
1 | 123335 | 3 | 105 | 11 | 2024-02-01 | NATION | DONE | 2024-02-02 | MOSTLY CLEAR | NEW | NOT CLEAR
2 | 123214 | 3 | 90 | 40 | 2024-01-30 | NATION | DONE | 2024-02-02 | Feeder list at Gerry's | ROWC | NOT CLEAR
1 | 123248 | 5 | 29 | 0 | 2024-02-21 | NATION | DONE | 2024-02-22 | NO ETA FOR PCB | NEW | NOT CLEAR
1 | 123648 | 5 | 39 | 8 | 2024-02-21 | NATION | DONE | 2024-02-22 | SHORT J12 - Setup Sheet at Gerry's | NEW | NOT CLEAR
2 | 123291 | 10 | 40 | 0 | 2024-02-22 | NATION | DONE | 2024-02-22 | SHORT PARTS DUE 2/23- Setup Sheet at Gerry's | RONC | NOT CLEAR
3 | 122735 | 15 | 14 | 7 | 2024-02-21 | NATION | DONE | 2024-02-26 | SHORT PCB- Setup Sheet at Gerry's | NEW | NOT CLEAR
4 | 122774 | 3 | 41 | 12 | 2024-02-22 | NATION | DONE | 2024-02-26 | SHORT PCB- Setup Sheet at Gerry's | NEW | NOT CLEAR
2 | 122381 | 5 | 137 | 55 | 2024-02-28 | NATION | DONE | 2024-03-29 | EXPECT CLEAR 2/29 | NEW | NOT CLEAR
1 | 123201 | 15 | 164 | 26 | 2024-02-28 | NATION | DONE | 2024-03-01 | EXPECT CLEAR NEXT WEEK | NEW | NOT CLEAR
1 | 123806 | 5 | 66 | 4 | 2024-02-29 | NAM | DONE | 2024-03-04 | EXPECT CLEAR 3/4 | NEW | NOT CLEAR
2 | 123954 | 3 | 84 | 32 | 2024-03-01 | NATION | DONE | 2024-03-04 | ALMOST CLEAR | NEW | NOT CLEAR
1 | 124026 | 5 | 138 | 116 | 2024-03-01 | NATION | DONE | 2024-03-04 | PCB DUE 3/5 - Feeder list at Gerry's | NEW | NOT CLEAR
1 | 124144 | 3 | 180 | 6 | 2024-03-01 | NATION | DONE | 2024-03-05 | ALMOST CLEAR - Feeder list at Gerry's | NEW | NOT CLEAR
2 | 123759 | 5 | 13 | 70 | 2024-03-04 | NATION | DONE | 2024-03-06 | PCB DUE 3/7 - Feeder list at Gerry's | NEW | NOT CLEAR
3 | 124091 | 10 | 100 | 60 | 2024-03-04 | NATION | DONE | 2024-03-06 | Y2 DUE 3/5 OR 3/6 - Feeder list at Gerry's | NEW | NOT CLEAR
1 | 123565 | 10 | 136 | 19 | 2024-03-01 | NATION | DONE | 2024-03-07 | PCB DUE 3/11 - Feeder list at Gerry's | NEW | NOT CLEAR
2 | 123907 | 5 | 71 | 16 | 2024-03-05 | NATION | DONE | 2024-03-07 | PCB DUE 3/11 - Feeder list at Gerry's | NEW
1 | 123794 | 10 | 51 | 8 | 2024-03-06 | NATION | DONE | 2024-03-08 | PCB DUE 3/14 | RONC | NOT CLEAR
1 | 124033 | 15 | 20 | 3 | 2024-03-06 | NATION | DONE | 2024-03-08 | PCB DUE 3/11 | RONC | NOT CLEAR
1 | 124325 | 1 | 3 | 0 | 2024-03-11 | NATION | DONE | 2024-03-12 | 3/12 - PCB DUE | NEW | NOT CLEAR
2 | 124326 | 1 | 5 | 0 | 2024-03-11 | NATION | DONE | 2024-03-12 | 3/12 - PCB DUE | NEW | NOT CLEAR
3 | 124240 | 5 | 80 | 25 | 2024-03-11 | NATION | DONE | 2024-03-11 | 3/12 - PCB DUE | NEW | NOT CLEAR
4 | 123920 | 10 | 36 | 8 | 2024-03-11 | NATION | DONE | 2024-03-12 | 3/11 - PCB DUE | NEW | NOT CLEAR
5 | 123787 | 5 | 153 | 19 | 2024-03-06 | NATION | DONE | 2024-03-08 | 3/20 - shortages due | NEW | NOT CLEAR
6 | 122657 | 5 | 44 | 5 | 2024-03-11 | NATION | DONE | 2024-03-13 | 3/14 - PCB DUE | NEW | NOT CLEAR
7 | 124259 | 10 | 91 | 6 | 2024-03-11 | NATION | DONE | 2024-03-15 | 3/19 - PCB DUE | NEW | NOT CLEAR
1 | 123545 | 5 | 50 | 14 | 2024-03-12 | NATION | DONE | 2024-03-14 | PCB DUE 3/14 | NEW | NOT CLEAR
1 | 122618-2 | 7 | 56 | 86 | 2024-03-13 | NATION | DONE | 2024-03-15 | SETUP JOB SOON (TAD) | ROWC 1st Article | NOT CLEAR
1 | 124388 | 5 | 73 | 7 | 2024-03-19 | NATION | DONE | 2024-03-22 | PCB DUE 3/25 | NEW | NOT CLEAR
1 | 124484 | 10 | 136 | 28 | 2024-03-21 | NATION | DONE | 3/26/2024 3/28/2024 | KIT CLEAR - Feeder list at Gerry's 3/29 - PCB DUE | NEW | NOT CLEAR
1 | 124607 | 5 | 82 | 8 | 2024-03-25 | NATION | DONE | 3/26 (IF POSSIBLE) | SHORT 1 SKIPPABLE SMT PART - Feeder list at Gerry's | NEW | NOT CLEAR
1 | 124449 | 5 | 37 | 37 | 2024-03-25 | NATION | DONE | 2024-03-26 | SHORT PCB - Feeder list at Gerry's 3/26 - PCB DUE | NEW | NOT CLEAR
1 | 124505 | 5 | 68 | 3 | 2024-03-27 | NATION | DONE | 2024-03-28 | we want to run this ASAP - Feeder list in kitbox | NEW | NOT CLEAR
1 | 124720 | 2 | 87 | 14 | 2024-03-27 | NATION | DONE | 2024-03-28 | 4/1 - PCB DUE - Feeder list at Gerry's COULD CLEAR THIS WEEK | NEW | NOT CLEAR
2 | 124656 | 5 | 194 | 2 | 2024-03-26 | NATION | DONE | 2024-03-29 | SHORT PCB - Feeder list at Gerry's | NEW | NOT CLEAR
3 | 124685 | 5 | 57 | 29 | 2024-03-28 | NATION | DONE | 2024-04-01 | 4/1 - PCB DUE - Feeder list at Gerry's | NEW | NOT CLEAR
4 | 124583 | 5 | 43 | 47 | 2024-03-27 | NATION | DONE |  | SHORT PCB - Feeder list at Gerry's | NEW | NOT CLEAR
1 | 124635 | 3 | 49 | 55 |  | NATION | DONE | ASAP | PCB/KIT HERE | NEW
1 | 123504 | 10 | 92 | 12 | 2024-04-01 | NATION | DONE | 4/3/2024 4/4/2024 | 4/3 - WILL CLEAR DATE - Feeder list at Gerry's 4/5 PCB DUE | NEW | NOT CLEAR
2 | 124290 | 5 | 82 | 23 | 2024-03-28 | NATION | DONE | 2024-04-02 | AWT PART CONF SHORT PARTS | NEW | NOT CLEAR
1 | 124475 | 5 | 43 | 6 | 2024-04-03 | NATION | DONE | 4/4/2024 4/8/2024 | 4/3 - KIT CLEAR - Feeder list at Gerry's 4/8 - PCB DUE | NEW | NOT CLEAR
2 | 124737 | 10 | 17 | 55 | 2024-03-28 | NATION | DONE | 4/4/2024 4/10/2024 | 4/3 - KIT CLEAR - Feeder list at Gerry's 4/10 - PCB DUE | NEW | NOT CLEAR
1 | 124615 | 5 | 92 | 33 | 2024-03-27 | NATION | DONE |  | SHORT PCB - Feeder list at Gerry's | NEW | NOT CLEAR
3 | 123722 | 10 | 106 | 83 | 2024-04-02 | NATION | DONE | 2024-04-04 | SHORT PCB - Feeder list at Gerry's | NEW | NOT CLEAR
1 | 124582 | 5 | 129 | 73 | 2024-03-21 | NATION | DONE | 4/3/2024 3/29/2024 3/25/2024 | 4/4 - PCB DUE SHORTAGES DUE 3/25 | NEW | NOT CLEAR
1 | 124488 | 10 | 57 | 55 | 2024-04-09 | NATION | DONE | 2024-04-10 | SMT CLEAR - Feeder list at Gerry's | NEW | NOT CLEAR
2 | 124556 | 5 | 93 | 7 | 2024-04-09 | NATION | DONE | 2024-04-10 | 4/9 - MAY CLEAR DATE | NEW | NOT CLEAR
5 | 121964 (HF) | 10 | 12 | 0 | 2024-04-08 | NATION | DONE | APR 12 4/10/2024 | KIT CLEAR 4/10 | NEW
6 | 121980 (HF) | 10 | 33 | 6 | 2024-04-08 | NATION | DONE | APR 12 4/10/2024 | SHORT PCB | NEW | NOT CLEAR
8 | 121968 (HF) | 10 | 15 | 0 |  | NATION | DONE |  | KIT CLEAR 4/10 | NEW | NOT CLEAR
9 | 121973 (HF) | 10 | 1 | 1 |  | NATION | DONE |  | KIT CLEAR 4/10 | NEW | NOT CLEAR
10 | 121978 (HF) | 10 | 8 | 1 |  | NATION | DONE |  | KIT CLEAR 4/10 | NEW | NOT CLEAR
11 | 124126 (HF) | 10 | 35 | 6 |  | NATION | DONE |  | KIT CLEAR 4/10 | NEW | NOT CLEAR
1 | 121966 (HF) | 10 | 16 | 0 |  | NATION | DONE |  | KIT CLEAR 4/10 | NEW | NOT CLEAR
2 | 124745 | 5 | 73 | 10 | 2024-04-10 | NATION | DONE | 2024-04-11 | 4/10 - MAY CLEAR TODAY - Feeder list at Gerry's | NEW | NOT CLEAR
5 | 124334 | 5 | 106 | 38 | 2024-04-04 | NATION/ROBERT | DONE | 2024-04-05 | 4/11 - SMT CLEAR - Feeder list at Gerry's 4/5 - SHORTAGES MAYBE DUE | ROWC 120730 | NOT CLEAR
3 | 121281 | 5 | 45 | 26 | 2024-04-09 | NATION | DONE | 2024-04-11 | PART SHORTAGES - Feeder list at Gerry's | NEW | NOT CLEAR
1 | 124494 (HF) | 10 | 57 | 24 |  | NATION | DONE |  | 4/12 - KIT CLEAR - Feeder list at Gerry's 4/17 - PCB DUE | NEW | NOT CLEAR
2 | 121960(HF) | 10 | 10 | 2 | 2024-04-11 | NATION | DONE |  | 4/11 - KIT CLEAR - Feeder list at Gerry's | NEW | NOT CLEAR
3 | 125010(HF) | 10 | 23 | 0 | 2024-04-11 | NATION | DONE |  | 4/11 - KIT CLEAR - Feeder list at Gerry's | NEW | NOT CLEAR
1 | 124498(HF) | 10 | 46 | 28 | 2024-04-11 | NATION | DONE |  | 4/11 - KIT CLEAR - Feeder list at Gerry's | NEW | NOT CLEAR
1 | 121961 (HF) | 10 | 16 | 0 |  | NATION | DONE |  | 4/11 - KIT CLEAR - Feeder list at Gerry's | NEW | NOT CLEAR
1 | 121969 (HF) | 10 | 8 | 0 |  | NATION | DONE |  | 4/11 - KIT CLEAR - Feeder list at Gerry's | NEW
2 | 121979 (HF) | 10 | 28 | 8 |  | NATION | DONE |  | 4/11 - KIT CLEAR - Feeder list at Gerry's | NEW
3 | 121282 | 5 | 42 | 14 | 2024-04-09 | NATION | DONE | 2024-04-11 | SHORT 1 PART - Feeder list at Gerry's PART SHORTAGES | NEW
4 | 120425 | 5 | 45 | 15 | 2024-04-11 | NATION | DONE | 2024-04-15 | SHORT 1 PART - Feeder list at Gerry's | NEW | NOT CLEAR
5 | 125073 | 3 | 37 | 8 | 2024-04-12 | NATION | DONE | 2024-04-15 | 4/16 - PCB DUE - Feeder list at Gerry's | NEW | NOT CLEAR
6 | 124949 | 3 | 78 | 10 |  | NATION | DONE |  | 4/15 - PCB/KIT BOX HERE | NEW | NOT CLEAR
7 | 124492 (HF) | 10 | 8 | 0 |  | NATION | DONE |  | 4/16 - PCB DUE | NEW | NOT CLEAR
1 | 124791 | 15 | 11 | 0 |  | NATION | DONE |  | 4/15 - KIT CLEAR - Feeder list in kit box | NEW
14 | 125000 | 10 | 53 | 2 |  | NATION | DONE |  | 4/25 - EXPECT CLEAR DATE | RONC
10 | 125078 | 8 | 41 | 12 |  | NATION | DONE |  | 4/22 - EXPECT CLEAR DATE | ROWC | NOT CLEAR
1 | 121972 (HF) | 10 | 1 | 1 |  | NATION | DONE |  | 4/16 - KIT CLEAR 4/23 - PCB DUE | NEW | NOT CLEAR
2 | 121965(HF) | 10 | 29 | 1 |  | NATION | DONE |  | 4/16 - KIT CLEAR 4/23 - PCB DUE | NEW
1 | 124129 (HF) | 10 | 17 | 0 |  | NATION | DONE |  | 4/16 - SHORTAGES DUE - Feeder list at Gerry's | NEW
2 | 125036 | 5 | 54 | 11 |  | NATION | DONE | 2024-04-17 | 4/17 - PCB DUE - Feeder list at Gerry's | NEW
3 | 121971(HF) | 10 | 8 | 0 |  | NATION | DONE |  | 4/18 - PCB DUE - Feeder list at Gerry's | NEW | NOT CLEAR
4 | 121977 (HF) | 10 | 14 | 0 |  | NATION | DONE |  | 4/17 - KIT CLEAR - Feeder list at Gerry's 4/18 - PCB DUE | NEW
7 | 124128 (HF) | 10 | 12 | 4 |  | NATION | DONE |  | 4/17 - SMT CLEAR - Feeder list at Gerry's 4/18 - PCB DUE | NEW
1 | 121981 (HF) | 10 | 38 | 0 |  | NATION | DONE |  | 4/18 - PCB DUE - Feeder list at Gerry's | NEW
2 | 121984 (HF) | 10 | 5 | 0 |  | NATION | DONE |  | 4/18 - PCB DUE - Feeder list at Gerry's | NEW
1 | 124493(HF) | 10 | 31 | 7 | 2024-04-18 | NATION | DONE |  | 4/18 - KIT CLEAR - Feeder list at Gerry's 4/23 - PCB DUE | NEW | NOT CLEAR
2 | 124917 | 10 | 37 | 451 |  | NATION | DONE |  | 4/18 - KIT CLEAR - Feeder list at Gerry's 4/23 - PCB DUE | NEW
3 | 125103 | 3 | 82 | 3 |  | NATION | DONE |  | 4/22 - PCB DUE - Feeder list at Gerry's | NEW | NOT CLEAR
14 | 125007 | 5 | 37 | 0 | 2024-04-18 | NAM | done | 2024-04-22 | 4/18 - KIT CLEAR long ref numbers | NEW | NOT CLEAR
1 | 124503 | 10 | 150 | 0 |  | NATION | DONE |  | 4/19 - SHORT 1 ITEM (ETA 4/20) - Feeder list at Gerry's 4/18 - KIT BOX/PCB IN STOCKROOM | NEW
2 | 121967(HF) | 10 | 29 | 1 |  | NATION | DONE |  | 4/19 - KIT CLEAR - Feeder list at Gerry's 4/23 - PCB DUE | NEW
3 | 86602484 | ASAP | 199 | 81 | 2024-04-10 | NATION | DONE | 2024-04-22 | HII (CUI) DIGITAL TRAVELER | NEW
7 | 124496 (HF) | 10 | 9 | 1 |  | NATION | DONE | 2024-04-25 | 4/29 - PCB DUE - Feeder list at Gerry's 4/17 - PCB DUE | NEW | NOT CLEAR
8 | 124497 (HF) | 10 | 42 | 0 |  | NATION | DONE | 2024-04-25 | 4/18 - PCB RECEIVED - Feeder list at Gerry's 4/11 - SHORT PCB + 1 ITEM | NEW
4 | 125211 | 3 | 21 | 37 |  | NATION | DONE |  | 4/25 - KIT BOX/PCB HERE | RONC 118965
1 | 124290 | 3 | 82 | 23 |  | NATION | DONE | 2024-04-25 | skipping short #28(U2_5) - Feeder list at Gerry's | ROWC 1st Article | NOT CLEAR
2 | 124495(HF) | 10 | 86 | 0 |  | NATION | DONE | 2024-04-25 | 4/25 - KIT CLEAR 4/25 - PCB DUE | NEW | NOT CLEAR
| 125456 | 5 | 3 | 0 |  | NATION | DONE |  | 4/25 - KIT BOX/PCB HERE | NEW | NOT CLEAR
1 | 124627 | 10 | 126 | 31 |  | NATION | DONE | 2024-04-25 | 4/25 - KIT CLEAR | NEW | NOT CLEAR
2 | 124815 | 3 | 103 | 27 |  | NATION | DONE | 2024-04-26 | 4/29 - PCB DUE | NEW | NOT CLEAR
1 | 125496 | 1 | 89 | 12 |  | NATION | DONE |  | 4/26 - KIT BOX HERE - PCB ETA 4/29 6:30 AM | NEW
3 | 125083 | 10 | 32 | 55 |  | NATION | DONE | 2024-04-25 | 4/26 - KIT CLEAR - Feeder list at Gerry's | NEW | NOT CLEAR
2 | 124125(HF) | 10 | 103 | 22 |  | NATION | DONE | 2024-04-25 | 4/26 - KIT CLEAR - Feeder list at Gerry's 4/25 - PCB DUE | NEW | NOT CLEAR
1 | 123853 | 5 | 88 | 1 |  | NATION | DONE |  | 4/26 - KIT CLEAR - Feeder list at Gerry's | NEW | NOT CLEAR
1 | 125017 | 5 | 93 | 34 |  | NATION | DONE | 2024-04-25 | 4/29 - KIT CLEAR - Feeder list at Gerrys' 5/1 - PCB DUE | NEW | NOT CLEAR
2 | 125273 | 5 | 7 | 2 |  | NATION | DONE |  | 4/29 - kit clear - Feeder list at Gerrys' 4/29 - AWT PART CONF #10 (T1) 4/26 - SHORTAGES DUE | NEW | NOT CLEAR
3 | 125274 | 5 | 79 | 3 |  | NATION | DONE |  | 4/29 - KIT CLEAR - Feeder list at Gerry's 4/29 - SHORTAGES DUE DATE | NEW
4 | 124342 | 10 | 102 | 0 |  | NATION | DONE |  | 4/26 - KIT CLEAR - Feeder list at Gerry's | NEW
6 | 124151 | 10 | 29 | 4 |  | NATION | DONE |  | 5/1 KIT CLEAR Tad wants to run this job immediately once it clears 4/30 - PCB DUE | NEW | NOT CLEAR
1 | 125253 | 5 | 76 | 7 |  | NATION | DONE |  | 5/2 - KIT CLEAR - Feeder list at Gerry's | NEW
2 | 124127(HF) | 10 | 156 | 12 |  | NATION | DONE | apr 29 4/25 | 5/2 - KIT CLEAR - Feeder list at Gerry's 5/1 - Updated BOM - Short 1 part 4/29 - KIT CLEAR 4/30 - PCB DUE 4/25 - PCB DUE | NEW
3 | 125344 | 3 | 124 | 32 |  | NATION | DONE | 2024-05-07 | 5/10 - PCB DUE - Feeder list at Gerry's | NEW
4 | 125312 | 5 | 65 | 11 |  | NATION | DONE | 2024-05-07 | 5/10 - PCB DUE - Feeder list at Gerry's | NEW | NOT CLEAR
5 | 125612 | 5 | 145 | 51 | 2024-05-07 | NATION | DONE | 2024-05-10 | 5/15 - PCB DUE | NEW | NOT CLEAR
1 | 125652 | 1 | 178 | 18 | 2024-05-07 | NATION | DONE | 2024-05-08 | 5/8 - may clear date | NEW | NOT CLEAR
3 | 125153 | 5 | 4 | 2 | 2024-05-08 | NATION | DONE | 2024-05-08 | 5/10 - PCB DUE | NEW | NOT CLEAR
1 | 124979 | 3 | 41 | 27 | 2024-05-07 | ROBERT/RAY | done | 2024-05-08 | 5/10 - EXPECT CLEAR DATE | RONC | NOT CLEAR
1 | 124923 | 10 | 113 | 57 | 2024-05-07 | NATION | DONE | 2024-05-08 | 5/9 - KIT CLEAR (may expedite job) 5/10 - PCB DUE | NEW | NOT CLEAR
3 | 124988 | 15 | 159 | 47 | 2024-05-08 | NATION | DONE | 2024-05-13 | 5/9 - KIT CLEAR | NEW | NOT CLEAR
| 125716 | 5 | 83 | 10 | 2024-05-09 | NATION | DONE | 2024-05-10 | 5/9 - KIT CLEAR | NEW | NOT CLEAR
| 125148 | 10 | 37 | 4 | 2024-05-09 | NATION | DONE | 2024-05-13 |  | NEW | NOT CLEAR
2 | 125776 | 2 | 18 | 0 | 2024-05-10 | NATION | DONE | 2024-05-13 | may clear soon | NEW | NOT CLEAR
3 | 119411 | 10 | 22 | 10 | 2024-05-13 | NATION | DONE | 2024-05-13 | 5/13 - KIT CLEAR | RONC | NOT CLEAR
6 | 125339 | 5 | 36 | 9 | 2024-05-13 | NATION | DONE | 2024-05-14 | 5/14 - SHORT PARTS 5/16 - pcb due | RONC | NOT CLEAR
4 | 125795 | 3 | 52 | 4 | 2024-05-14 | NATION | DONE | 2024-05-15 | 5/17 - CLEAR BY DATE | RONC | NOT CLEAR
2 | 125449 | 5 | 58 | 8 | 2024-05-13 | NATION | DONE | 2024-05-13 | 5/16 - KIT CLEAR - XY missing angle column - requesting new XY - New XY received 5/13 - PCB DUE | NEW | NOT CLEAR
3 | 124857 | 5 | 116 | 23 | 2024-05-13 | NATION | DONE | 2024-05-15 | 5/15 - PCB DUE & 4-DAY TURN 5/16 - pcb due | NEW | NOT CLEAR
6 | 125711 | 10 | 25 | 3 | 2024-05-10 | NATION | DONE | 2024-05-14 |  | NEW | NOT CLEAR
2 | 124835 | 5 | 17 | 0 | 2024-05-14 | NATION | DONE | 2024-05-17 | Requesting XY XY RECEIVED | NEW | NOT CLEAR
3 | 125146 | 10 | 53 | 3 | 2024-05-13 | NATION | DONE | 2024-05-17 |  | NEW | NOT CLEAR
4 | 125344 | 5 | 125 | 22 | 2024-05-15 | NATION | DONE | 2024-05-16 | SMT CLEAR - "U35" OK TO SKIP | ROWC | NOT CLEAR
2 | 125398 | 15 | 110 | 2 | 2024-05-15 | NATION | DONE | 2024-05-17 | 5/16 - KIT CLEAR | NEW | NOT CLEAR
4 | 125560 | 10 | 63 | 5 | 2024-05-16 | NATION/ROBERT | DONE | 2024-05-17 | 5/17 - PCB DUE | ROWC | NOT CLEAR
5 | 123547 | 20 | 48 | 8 | 2024-05-16 | NATION/ROBERT | DONE | 2024-05-17 | 5/21 - EXPECT CLEAR DATE | RONC | NOT CLEAR
7 | 125805 | 10 | 84 | 0 | 2024-05-16 | NATION/ROBERT | DONE | 2024-05-17 | 5/22 - PCB DUE | ROWC | NOT CLEAR
2 | 125697 | 10 | 112 | 2 | 2024-05-09 | NATION | DONE | MAY 17 5/13/2024 |  | NEW | NOT CLEAR
3 | 125536 | 10 | 50 | 14 | 2024-05-16 | NATION | DONE | 2024-05-17 |  | NEW | NOT CLEAR
| 126006 | 1 | 63 | 3 | 2024-05-17 | NAM | DONE | 2024-05-20 | 1-DAY TURN | NEW | NOT CLEAR
1 | 125418 | 5 | 94 | 2 | 2024-05-17 | NAM | DONE | 2024-05-20 |  | NEW | NOT CLEAR
1 | 123155 | 10 | 36 | 7 | 2024-05-17 | NAM | DONE | 2024-05-21 |  | NEW | NOT CLEAR
2 | 125998 | 3 | 18 | 2 | 2024-05-20 | NAM | DONE | 2024-05-21 | 3-DAY TURN | NEW | NOT CLEAR
3 | 125999 | 3 | 16 | 5 | 2024-05-20 | NAM | DONE | 2024-05-21 | 3-DAY TURN | NEW | NOT CLEAR
| 125996 | 3 | 89 | 12 | 2024-05-20 | ROBERT | DONE |  |  | ROWC | NOT CLEAR
| 125581 | 5 | 106 | 83 | 2024-05-20 | ROBERT | DONE |  |  | ROWC | NOT CLEAR
| 126002 | 1 | 106 | 6 | 2024-05-21 | NAM |  | 2024-05-22 | 1-DAY | NEW | NOT CLEAR
| 125726 | 5 | 113 | 3 | 2024-05-21 | NAM | DONE | 2024-05-23 | EMAIL ROBERT - B125727 | NEW | NOT CLEAR
| 125611 | 3 | 24 | 4 | 2024-05-22 | NAM | DONE | 2024-05-23 | 3-DAY TURN | NEW | NOT CLEAR
| 125951 | 5 | 37 | 6 | 2024-05-21 | ROBERT | DONE |  |  | ROWC | NOT CLEAR
| 125498 | 5 | 41 | 3 | 2024-05-23 | NAM | DONE | 2024-05-28 | URGENT | NEW | NOT CLEAR
| 126001 | 2 | 14 | 2 | 2024-05-24 | NAM | DONE | 2024-05-28 | 2-DAY TURN | NEW | NOT CLEAR
| 125719 | 10 | 43 | 8 | 2024-05-28 | NAM | DONE | 2024-05-30 |  | NEW | NOT CLEAR
1 | 126168 | 1 | 62 | 3 | 2024-05-29 | NAM | DONE | 2024-05-30 | 1-DAY | NEW | NOT CLEAR
| 125293 | 5 | 73 | 7 | 2024-05-29 | ROBERT | DONE |  | SMT CLEAR | ROWC | NOT CLEAR
| 126086 | 5 | 82 | 8 | 2024-05-29 | ROBERT | DONE |  |  | RONC | NOT CLEAR
2 | 126196 | 1 | 57 | 2 | 2024-05-29 | NAM | DONE | 2024-05-30 | 1-DAY | NEW | NOT CLEAR
2 | 126042 | 3 | 20 | 6 | 2024-05-29 | NAM | DONE | 2024-05-30 | 3-DAY | NEW | NOT CLEAR
1 | 125900 | 2 | 27 | 8 | 2024-05-29 | NAM | DONE | 2024-05-30 | 2-DAY (KIT CLEAR) | NEW | NOT CLEAR
3 | 126163 | 5 | 20 | 9 | 2024-05-29 | NAM | DONE | 2024-05-31 |  | NEW | NOT CLEAR
1 | 126055 | 10 | 15 | 8 | 2024-05-29 | NAM | DONE | 2024-05-31 | KIT CLEAR | NEW | NOT CLEAR
1 | 125275 | 10 | 71 | 7 | 2024-05-30 | NAM | DONE | 2024-06-03 | CUI - DOD | NEW | NOT CLEAR
3 | 126015 | 5 | 104 | 10 | 2024-05-30 | NAM | DONE | 2024-06-03 |  | NEW | NOT CLEAR
| 107957 | 10 | 114 | 44 |  | NATION | DONE |  |  | NEW | NOT CLEAR
| 126074 | 5 | 75 | 5 | 2024-05-30 | NAM | DONE | 2024-06-03 |  | NEW | NOT CLEAR
| 126212 | 5 | 30 | 2 | 2024-06-03 | NATION | DONE | 2024-06-04 | 6/3 - kit clear | NEW | NOT CLEAR
| 126085 | 2 | 10 | 8 | 2024-06-03 | NATION | DONE | 2024-06-04 |  | NEW | NOT CLEAR
| 124940 | 10 | 60 | 0 | 2024-05-30 | ROBERT |  | 2024-06-03 |  | RONC | NOT CLEAR
| 124941 | 10 | 106 | 11 | 2024-05-30 | ROBERT |  | 2024-06-03 |  | RONC | NOT CLEAR
| 126100 | 5 | 6 | 16 | 2024-06-04 | NATION/ROBERT | DONE |  | Feeder list at Gerry's | RONC | NOT CLEAR
| 126272 | 10 | 17 | 8 | 2024-06-04 | NATION | DONE |  | Feeder list at Gerry's | NEW | NOT CLEAR
| 125727 | 5 | 110 | 2 | 2024-06-04 | NATION/ROBERT | DONE |  |  | ROWC | NOT CLEAR
| 126151 | 5 | 75 | 16 | 2024-06-04 | NATION | DONE |  | Feeder list at Gerry's | NEW | NOT CLEAR
| 125202 | 10 | 9 | 15 | 2024-06-04 | NATION | DONE |  | Feeder list at Gerry's | NEW | NOT CLEAR
3 | 126664 | 10 | 87 | 20 | 2024-07-02 | NATION | DONE |  | Feeder list at Gerry's | NEW | NOT CLEAR
1 | 126578 | 5 | 28 | 16 | 2024-07-01 | NATION | DONE |  | Feeder list at Gerry's | NEW | NOT CLEAR
1 | 126194-2 | 5 | 54 | 45 | 2024-07-08 | NATION | DONE |  | ON FEEDERS ¦¦ WILL SKIP PARTS SHORT - Feeder list at Gerry's | ROWC | NOT CLEAR
2 | 126269 | 3 | 40 | 0 | 2024-07-08 | NATION | DONE |  | 7/8 - Potentially 1 change - Feeder list in kit box at stockroom | NEW | NOT CLEAR
1 | 126530 | 10 | 175 | 11 | 2024-07-09 | NATION | DONE |  | 7/12 - PCB DUE ¦ OTHER SHORT SKIPPABLE - Feeder list at Gerry's | NEW | NOT CLEAR
1 | 126350 | 10 | 96 | 11 | 2024-07-11 | NATION | DONE | 2024-07-12 | 7/12 - SHORTAGES DUE - Feeder list in kitbox | NEW | NOT CLEAR
2 | 126908 | 5 | 82 | 13 | 2024-07-10 | NATION | DONE | 2024-07-12 | 7/15 - PCB DUE - Feeder list at Gerry's | NEW | NOT CLEAR
1 | 126817 | 3 | 62 | 23 | 2024-07-11 | NATION | DONE | 2024-07-12 | 7/12 - PCB DUE DATE - Feeder list at Gerry's | NEW | NOT CLEAR
3 | 126629 | 5 | 39 | 4 | 2024-07-11 | NATION | DONE | 2024-07-16 | 7/17 - PCB DUE | NEW | NOT CLEAR
6 | 126815 | 5 | 6 | 11 | 2024-07-15 | NATION | DONE | 2024-07-19 | 7/19 - PCB DUE | RONC | NOT CLEAR
1 | 126425 | 5 | 148 | 29 | 2024-07-02 | NATION | DONE | 2024-07-15 | KIT CLEAR - Feeder list at Gerry's 7/16 - PCB DUE | NEW | NOT CLEAR
1 | 126532 | 5 | 64 | 38 | 2024-07-11 | NATION | DONE | 2024-07-16 | 7/15 - KIT CLEAR - Feeder list at Gerry's 7/18 - PCB DUE | NEW | NOT CLEAR
2 | 125578 | 15 | 85 | 1 | 2024-07-11 | NATION | DONE | 7/16 7/17/2024 | 7/16 - EXPECTED TO CLEAR 7/15 - SMT CLEAR 7/17 - PCB DUE | NEW | NOT CLEAR
1 | 125704 | 15 | 102 | 8 | 2024-07-12 | NATION | DONE | 2024-07-16 | 7/16 - KIT CLEAR - Feeder list at Gerry's 7/15 - SMT CLEAR 7/15 - EXPECTED SMT CLEAR DATE | NEW | NOT CLEAR
1 | 127012 | 3 | 139 | 36 | 2024-07-15 | NATION | DONE | 2024-07-16 | 7/17 - PCB DUE - Feeder list at Gerry's | NEW | NOT CLEAR
1 | 126631 | 3 | 154 | 80 | 2024-07-16 | NATION | DONE | 2024-07-17 | 7/23 (OR SOONER) - PCB DUE - Feeder list at Gerry's | NEW | NOT CLEAR
1 | 126982 | 8 | 123 | 68 | 2024-07-15 | NATION | DONE |  | 7/25 - PCB DUE - Feeder list at Gerry's | NEW | NOT CLEAR
1 | 125391 | 10 | 161 | 18 | 2024-07-19 | NATION | DONE | 2024-07-22 | 7/22 - PCB DUE - Feeder list in Kit box | NEW | NOT CLEAR
1 | 127160 | 3 | 42 | 86 | 2024-07-22 | NATION | DONE | 2024-07-23 | SHORT PCB -- NO ETA - Feeder list at Gerry's | NEW | NOT CLEAR
1 | 125349 | 5 | 164 | 21 | 2024-07-22 | NATION | DONE | 2024-07-24 | 7/23 - J4 & ATTRITION DUE - Feeder list in kit box SHORT PCB (NO ETA) | NEW | NOT CLEAR
1 | 126673 | 10 | 170 | 61 | 2024-07-19 | NATION | DONE | 2024-07-25 | KIT CLEAR - Feeder list at Gerry's SHORT 1 SMT PART -- NO ETA | NEW | NOT CLEAR
2 | 126794 | 5 | 72 | 10 | 2024-07-22 | NATION | DONE | 2024-07-25 | NEED TO START 1-2 DAYS BEFORE CLEAR - Feeder list in kit box 7/29 - PCB DUE | NEW | NOT CLEAR
4 | 126359 | 4 | 1 | 0 | 2024-07-25 | NATION | DONE | 2024-07-27 | SAME DAY TURN 7/31 - PCB DUE & SHIP SAME DAY | NEW | NOT CLEAR
5 | 126358 | 4 | 1 | 0 | 2024-07-25 | NATION | DONE | 2024-07-27 | SAME DAY TURN 7/31 - PCB DUE & SHIP SAME DAY | NEW | NOT CLEAR
1 | 127145 | 3 | 41 | 31 | 2024-07-25 | NATION | DONE | 2024-07-27 | ETA START BUILD 7/29 | NEW | NOT CLEAR
2 | 127107 | 4 | 35 | 6 | 2024-07-25 | NATION | DONE | 2024-07-27 | ETA START BUILD 7/30 | NEW | NOT CLEAR
3 | 126510 | 4 | 71 | 1 | 2024-07-25 | NATION | DONE | 2024-07-27 | ETA START BUILD 7/30 | NEW | NOT CLEAR
3 | 127246 | 5 | 29 | 5 | 2024-07-31 | NATION | DONE | 2024-08-02 | KIT CLEAR - Feeder list at Gerrys | NEW | NOT CLEAR
1 | RBE-SYNC1.2.C.X | 10 | 86 | 12 | 2024-07-30 | NATION | DONE | 2024-07-31 | KIT CLEAR - Feeder list at Gerrys | NEW | NOT CLEAR
1 | 127034 | 5 | 150 | 40 | 2024-07-30 | NATION | DONE | 2024-08-01 | 8/1 - pcb due date - Feeder list at Gerry's | NEW | NOT CLEAR
| 126947 | 10 | 73 | 14 | 2024-08-01 | NATION | DONE | 2024-08-02 | KIT CLEAR - Feeder list in kit box | NEW | NOT CLEAR
7 | 127196 | 10 | 24 | 7 | 2024-08-01 | NATION | DONE | 2024-08-07 | PREV BUILD ON LINE 3 | RONC | NOT CLEAR
1 | 127450 | 1 | 14 | 3 | 2024-08-01 | NATION | DONE | 2024-08-02 | NO PCB - NO ETA | NEW | NOT CLEAR
3 | 127451 | 5 | 14 | 3 | 2024-08-01 | NATION | DONE | 2024-08-05 | 8/7 - PCB ETA (BUT RONC B127450) - Can use same program/setup as B127450 | RONC | NOT CLEAR
1 | 127385 | 2 | 173 | 22 | 2024-07-31 | NATION | DONE | 2024-08-02 | 8/6 - PCB DUE | NEW | NOT CLEAR
2 | 127342 | 1 | 60 | 5 | 2024-08-01 | NATION | DONE | 2024-08-06 | TAD WANTS THIS SETUP BY EOD 8/7 8/8 - PCB DUE | NEW | NOT CLEAR
1 | 127445 | 1 | 58 | 4 | 2024-08-01 | NATION | DONE | 2024-08-03 | 8/5 - PCB DUE NO PCB - NO ETA | NEW | NOT CLEAR
2 | 127474 | 1 | 18 | 9 | 2024-08-02 | NATION | DONE | 2024-08-05 | 8/5 - PCB DUE | NEW | NOT CLEAR
3 | 127452 | 1 | 105 | 9 | 2024-08-02 | NATION | DONE | 2024-08-05 | NO PCB - NO ETA | NEW | NOT CLEAR
1 | 127187 | 5 | 100 | 35 | 2024-08-05 | NATION | DONE | 2024-08-06 | AWT PART CONF THEN CLEAR | NEW | NOT CLEAR
1 | 127333 | 5 | 112 | 34 | 2024-08-01 | NATION | DONE | 2024-08-07 | 8/8 - PCB DUE | NEW | NOT CLEAR
1 | 127480 | 5 | 43 | 72 | 2024-08-08 | NATION | DONE | 2024-08-09 | kit clear | NEW | NOT CLEAR
2 | 127475 | 5 | 18 | 2 | 2024-08-08 | NATION | DONE | 2024-08-09 | line 3 | RONC | NOT CLEAR
2 | 127473 | 5 | 1 | 1 | 2024-08-08 | NATION | DONE | 2024-08-09 | line 3 | RONC | NOT CLEAR
1 | 127471 | 5 | 27 | 6 | 2024-08-08 | NATION | DONE | 2024-08-09 | LINE 1 Waiting for B127470 to finish | RONC | NOT CLEAR
2 | 127395 | 5 | 202 | 14 | 2024-08-09 | NATION | DONE | 2024-08-12 | KIT CLEAR | NEW | NOT CLEAR
2 | 127283 | 5 | 56 | 7 | 2024-08-08 | NATION | DONE | 2024-08-13 | KIT CLEAR 8/12 - PCB DUE | NEW | NOT CLEAR
4 | 127180 | 3 | 32 | 1 | 2024-08-07 | NATION | DONE |  | SHORT PCB WITH NO ETA | NEW | NOT CLEAR
1 | 126733 | 10 | 255 | 22 | 2024-07-19 | NATION | DONE | 2024-08-12 | SHORT 4 SMT PARTS - ETA 8/13 | NEW | NOT CLEAR
1 | 127629 | 3 | 66 | 3 | 2024-08-12 | NATION | DONE | 2024-08-14 | 8/15 - PCB DUE | NEW | NOT CLEAR
1 | 127248 | 5 | 104 | 33 | 2024-08-06 | NATION | DONE |  | 8/19 - PCB DUE | NEW | NOT CLEAR
| 127581 | 5 | 77 | 72 | 2024-08-19 | NATION | DONE | 2024-08-20 | KIT CLEAR | NEW | NOT CLEAR
| 127065 | 5 | 32 | 25 | 2024-08-19 | NATION | DONE | 2024-08-20 | SMT CLEAR | NEW | NOT CLEAR
| 127383 | 5 | 182 | 38 | 2024-08-21 | NATION | DONE | ASAP | 3 Machine Job Priority Rating: DO-A7 | NEW | NOT CLEAR
| 127298 | 5 | 82 | 1 | 2024-08-20 | NATION | DONE | 2024-08-29 | 9/3 - PCB DUE | NEW | NOT CLEAR
| 127552 | 10 | 150 | 36 | 2024-08-22 | NATION | DONE | 2024-08-29 | 8/26 - CONFIRM PART THAN CLEAR SHORT PCB + 6 ITEMS (8/30 - PCB DUE) | NEW | NOT CLEAR
| SUPER-CTL1-3.C.X | 20 | 199 | 1 | 2024-08-28 | NATION | DONE | 2024-08-29 | SHORT #54 (EQ1 & EQ2) (TOP SIDE) want to start bottom side 9/3 | NEW | NOT CLEAR
1 | 127843 | 5 | 85 | 14 | 2024-08-27 | NATION | DONE | SEP 3 9/5/2024 | KIT CLEAR 9/6 - PCB DUE may skip C64 if PCB arrives before part | NEW | NOT CLEAR
1 | 127830 | 15 | 150 | 38 | 2024-08-28 | NATION | DONE | 2024-09-03 | KIT CLEAR 8/28 - SHOULD CLEAR TODAY | NEW | NOT CLEAR
1 | 128050 | 2 | 105 | 9 | 2024-08-29 | NATION | DONE | 2024-09-04 | 9/6 - PCB DUE OR SOONER | NEW | NOT CLEAR
2 | 127250 | 15 | 53 | 1 | 2024-09-03 | NATION | DONE | 2024-09-04 | 9/3 OR 9/4 - LAST PART #37 (BL1) DUE | NEW | NOT CLEAR
5 | 128023 | 5 | 25 | 60 | 2024-08-29 | NATION | DONE | 2024-09-05 | 9/5 - PCB DUE | NEW | NOT CLEAR
1 | 127130 | 5 | 30 | 8 | 2024-09-04 | NATION | DONE | 2024-09-04 | KIT CLEAR | NEW | NOT CLEAR
1 | 127635 | 10 | 266 | 17 | 2024-08-27 | NATION | DONE | 2024-09-05 | KIT CLEAR 9/4 - PCB DUE | NEW | NOT CLEAR
2 | 128238 | 3 | 32 | 1 | 2024-09-05 | NATION/ROBERT | DONE | 2024-09-06 | 9/11 - SHIP DATE | RONC | NOT CLEAR
1 | 127832 | 15 | 166 | 33 | 2024-08-29 | NATION | DONE | 2024-09-06 | KIT CLEAR WILL CLEAR SOON | NEW | NOT CLEAR
3 | 127831 | 15 | 189 | 50 | 2024-09-04 | NATION | DONE | 2024-09-06 | KIT CLEAR | NEW | NOT CLEAR
1 | 127216 | 10 | 103 | 10 | 2024-09-05 | NATION | DONE | 2024-09-06 | KIT CLEAR | NEW | NOT CLEAR
2 | 127981 | 5 | 89 | 0 | 2024-09-04 | NATION | DONE | 2024-09-06 | KIT CLEAR 9/6 - LAST PART DUE TO ARRIVE DATE SHOULD CLEAR SOON | NEW | NOT CLEAR
1 | 127842 | 5 | 62 | 14 | 2024-09-04 | NATION | DONE | 9/9 9/10 | KIT CLEAR 9/11 - PCB DUE | NEW | NOT CLEAR
2 | 128276 | 1 | 37 | 7 | 2024-09-09 | NATION | DONE | 2024-09-10 |  | NEW | NOT CLEAR
3 | 127780 | 3 | 77 | 3 | 2024-09-06 | NATION | DONE | 2024-09-09 | 9/10 - pcb due | NEW | NOT CLEAR
4 | 127841 | 5 | 58 | 11 | 2024-09-05 | NATION | DONE | 2024-09-10 | 9/12 - PCB DUE | NEW | NOT CLEAR
2 | 128008 | 5 | 27 | 19 | 2024-09-05 | NATION | DONE | 2024-09-11 | KIT CLEAR | NEW | NOT CLEAR
1 | 128170 | 2 | 159 | 18 | 2024-09-10 | NATION | DONE | 2024-09-11 | 9/11 - PCB DUE | NEW | NOT CLEAR
3 | QUAD-H1-TEST3 | 5 | 19 | 1 | 2024-09-06 | NATION | DONE | 2024-09-11 | WILL CLEAR SOON | NEW | NOT CLEAR
4 | 127654 | 10 | 105 | 30 | 2024-08-23 | NATION | DONE | 11-SEP 9/9/2024 | 9/6 - PCB DUE | NEW | NOT CLEAR
5 | 128122 | 10 | 36 | 8 | 2024-09-10 | NATION/ROBERT | DONE |  | 9/19 - PCB DUE | RONC | NOT CLEAR
1 | 128116 | 2 | 88 | 3 | 2024-09-11 | NATION | DONE | 2024-09-12 | 9/13 - PCB DUE | NEW | NOT CLEAR
2 | 128025 | 1 | 107 | 0 | 2024-09-11 | NATION | DONE |  |  | NEW | NOT CLEAR
1 | 128129 | 3 | 91 | 28 | 2024-09-06 | NATION | DONE | 2024-09-13 | 9/16 - PCB DUE | NEW | NOT CLEAR
2 | 128084 | 3 | 84 | 1 | 2024-09-09 | NATION | DONE | 2024-09-16 | 9/17 - PCB DUE | NEW | NOT CLEAR
| 128164 | 5 | 46 | 25 | 2024-09-13 | NATION | DONE | 2024-09-16 | KIT CLEAR | NEW | NOT CLEAR
| 126961 | 15 | 38 | 0 | 2024-09-13 | NATION | DONE | 2024-09-16 | KIT CLEAR | NEW | NOT CLEAR
| 126809 | 10 | 77 | 45 | 2024-09-10 | NATION | DONE |  |  | NEW | NOT CLEAR
| 126794 | 5 | 73 | 10 | 2024-09-17 | NATION | DONE |  |  | ROWC
| 128379 | 3 | 77 | 99 | 2024-09-17 | NATION | DONE | 2024-09-18 | KIT CLEAR 9/18 - PCB DUE | NEW
1 | 128136 | 3 | 154 | 12 |  | NATION | DONE |  | SHORT PCB | NEW
2 | 126574 | 5 | 110 | 64 |  | NATION | DONE |  | KIT BOX/PCB HERE | NEW
| 127912 | 9 | 36 | 18 |  | NATION | DONE |  | 9/20 - KIT CLEAR | NEW | NOT CLEAR
1 | 126660 | 5 | 80 | 54 |  | NATION | DONE | 2024-09-22 | 9/20 - KIT CLEAR | NEW | NOT CLEAR
2 | 128183 | 10 | 65 | 44 |  | NATION | DONE |  | 9/20 - SMT CLEAR | NEW
3 | 128594 | 3 | 17 | 113 |  | NATION | DONE |  | 9/20 - SHORT PCB + 1 ITEM | NEW
4 | 332-0034 revC | 7 | 82 | 19 | 2024-09-13 | NATION | DONE | SEP 23 9/19/2024 | 9/24 - PCB DUE | NEW | NOT CLEAR
1 | 127951 | 10 | 151 | 41 | 2024-09-23 | NATION | DONE | 2024-09-24 | 9/24 - SHORT 2 ITEMS ETA TODAY 9/24 | NEW | NOT CLEAR
2 | 128433 | 10 | 154 | 39 | 2024-09-19 | NATION | DONE | SEP 24 9/23/2024 | 9/24 - KIT CLEAR | NEW | NOT CLEAR
1 | 128696 | 1 | 17 | 23 | 2024-09-24 | NATION | DONE | 2024-09-24 | 9/25 - PCB DUE | NEW | NOT CLEAR
2 | 128663 | 1 | 64 | 2 | 2024-09-24 | NATION | DONE | 2024-09-25 | 9/26 - PCB DUE | NEW | NOT CLEAR
3 | 128662 | 2 | 22 | 9 | 2024-09-24 | NATION | DONE | 2024-09-25 |  | NEW | NOT CLEAR
6 | 128613 | 3 | 18 | 220 | 2024-09-24 | NATION | DONE | 2024-09-27 | 9/30 - PCB DUE | NEW | NOT CLEAR
7 | 127976 | 3 | 48 | 1 |  | NATION | DONE |  | KIT BOX HERE | NEW
1 | OCTO-FPGA-A1-3.C.1 | 10 | 209 | 4 | 2024-09-11 | NATION | DONE | 2024-09-25 | 9/27 - PCB DUE | NEW | NOT CLEAR
1 | OCTO-QUAD-D2-1.B.1 | 10 | 238 | 22 | 2024-09-11 | NATION | DONE | 2024-09-25 | 9/27 - PCB DUE | NEW | NOT CLEAR
2 | 126847 | 10 | 78 | 22 | 2024-09-25 | NATION | DONE | 2024-10-02 | 9/26 - KIT CLEAR 10/3 - PCB DUE | NEW | NOT CLEAR
3 | 127321 | 10 | 57 | 19 | 2024-09-26 |  | DONE |  | 9/26 - KIT CLEAR | NEW | NOT CLEAR
4 | 127752 | 10 | 38 | 1 | 2024-09-25 | NATION | DONE | 2024-09-27 | 9/30 - PC DUE | NEW | NOT CLEAR
7 | 127138 | 10 | 34 | 0 | 2024-09-25 | NATION | DONE | 2024-10-03 | 10/3 - PCB DUE | NEW | NOT CLEAR
1 | 128344 | 5 | 80 | 27 | 10/1 9/30 | NATION | DONE | 2024-10-01 | KIT CLEAR 10/1 - PCB DUE | NEW | NOT CLEAR
3 | 128611 | 5 | 110 | 50 | 2024-09-30 | NATION | DONE | 2024-10-02 | 10/2 - KIT CLEAR 10/2 - PCB DUE | NEW | NOT CLEAR
1 | 128342 | 3 | 97 | 28 | 2024-09-24 | NATION | DONE | 1-OCT 10/9/2024 | 10/11 - PCB DUE | NEW | NOT CLEAR
2 | 128480 | 5 | 35 | 0 | 2024-09-30 | NATION | DONE | 2024-10-02 | 10/2 - KIT CLEAR 10/3 - PCB DUE | NEW | NOT CLEAR
3 | 125916 | 10 | 61 | 11 | 2024-09-30 | NATION | DONE | 2024-10-02 | 10/1 - KIT CLEAR | NEW | NOT CLEAR
1 | 125915 | 10 | 58 | 18 | 2024-09-30 | NATION | DONE | 2024-10-03 | 10/2 - KIT CLEAR SMT CLEAR 9/30 - SHORTAGES DUE | NEW | NOT CLEAR
2 | 128348 | 10 | 42 | 6 | 2024-09-30 | NATION | DONE |  | 10/4 - KIT CLEAR 10/9 - PCB DUE | NEW | NOT CLEAR
2 | 128490 | 3 | 155 | 9 | 2024-10-04 | NATION | DONE |  | 10/7 - PCB POSSIBLE CLEAR DATE (TAD) | NEW | NOT CLEAR
1 | 128561 | 3 | 21 | 25 | 2024-09-30 | NATION | DONE | 2024-10-08 | 10/10 - PCB DUE | NEW | NOT CLEAR
1 | 125020 | 10 | 80 | 10 | 2024-10-04 | NATION | DONE |  | 10/7 - KIT CLEAR | NEW | NOT CLEAR
2 | 128615 | 5 | 70 | 29 | 2024-09-30 | NATION | DONE |  | 10/8 - PCB DUE | NEW | NOT CLEAR
1 | 128297 | 5 | 25 | 27 | 2024-10-04 | NATION | DONE |  | 10/8 - PCB DUE | NEW | NOT CLEAR
2 | 125153 | 10 | 4 | 2 | 2024-10-07 | NATION | DONE | 2024-10-08 | 10/8 - last part due (CAN'T FIND PROGRAM FOR 1ST RUN) | NEW | NOT CLEAR
3 | 128642 | 2 | 42 | 86 |  | NATION | DONE |  | SHORT PCB + 1 ITEM | NEW | NOT CLEAR
1 | 128753 | 10 | 78 | 0 | 2024-10-07 | NATION | DONE | 2024-10-10 | 10/10 - pcb due | NEW | NOT CLEAR
2 | 128669 | 5 | 106 | 42 | 2024-10-02 | NATION | DONE |  | 10/23 - PCB DUE | NEW | NOT CLEAR
| 128282 | 5 | 124 | 32 | 2024-10-08 | NATION | DONE |  | SHORT PCB - NO ETA | NEW | NOT CLEAR

## UNREL
[8 empty] | 2023-09-20 17:06 | [21 empty] | ESTIMATE TIME
SHIPPED | LINE 1 | LINE 2 | LINE 3 | JOB | QTY | LT | STATUS | MFG NOTES | TYPE | PROG | SMT LINES | SMT PLCMNTS | MACH | T/H | T/H EXT | STENCIL | KIT NOTES | SMT COMP DATE | SHIP METHOD | CUST | HISTORY | DOC REL | KIT REL | CODE | RELEASE NOTES | SHIP DATE | MACH SIDES | DATE SMT START | ACTUAL SMT TIME | SETUP TIME (HRS)
|  |  |  | 114025 | 20 | 1 | FSU | *** 1 DAY TURN *** ICs & PCBs REQ BAKING BEFORE RUN | RONC 113426 | NL | 72 | 254 | 1B 1T | 22 | 440 |  |  |  | FEDEX P |  |  | SHORT PCB + 2 ITEMS |  | 12395.8 | 1-DAY TURN; L3 ALREADY PROG; BOT 1ST; LF |  | 2 |  |  | 3
|  |  |  | 121433 | 6 | 3 | FSU |  | REWORK 118749 | X |  |  |  |  | 0 |  |  |  | FEDEX GRD | Thermon Heating Systems, Inc |  | NO DOC. |  | 2340 | [5 empty] | 1
|  |  |  | 114124-3 | 16 | 5 | FSU |  |  | - |  |  |  |  | 0 | [6 empty] | NO DOC. |  | 11073.92 | [5 empty] | 1
|  |  |  | 114307-3 | 16 | 10 | FSU |  |  | - |  |  |  |  | 0 | [6 empty] | NO DOC. |  | 9622.74 | [5 empty] | 1
|  |  |  | 118993-2 | 30 | 5 | FSU | JOB CLOSED (10/17) PARTS MOVE TO B121521 |  | - |  |  |  |  | 0 |  |  |  | UPS RED |  |  | NO DOC. |  | 2172 | [5 empty] | 1
|  |  |  | 119432-3 | 10 | 5 | FSU |  |  | - |  |  |  |  | 0 |  |  |  | FEDEX P | Phoenix Contact, Inc. |  | NO DOC. |  | 9997 | [5 empty] | 1
|  |  |  | 119788-2 | 105 | 5 | FSU |  |  | - |  |  |  |  | 0 |  |  |  | FEDEX P | Industrialex Manufacturing |  | NO DOC. |  | 4984.35 | [5 empty] | 1
|  |  |  | 120465-2 | 90 | 3 | FSU |  |  | - |  |  |  |  | 0 |  |  |  | FEDEX P | Industrialex Manufacturing |  | NO DOC. |  | 4257 | [5 empty] | 1
|  |  |  | 120633-1 | 2 | 5 | FSU |  | REWORK 116048 | X |  |  |  |  | 0 |  |  |  | FEDEX GRD | HRL Laboratories |  | NO DOC. |  | 1812 | Already completed per PCMRP SO#013511 |  |  |  |  | 1
|  |  |  | 120633-2 | 10 | 5 | FSU |  | REWORK 116048 | X |  |  |  |  | 0 |  |  |  | FEDEX GRD | HRL Laboratories |  | NO DOC. |  | 1023 | Already completed per PCMRP SO#013511 |  |  |  |  | 1
|  |  |  | 121339 | 109 | ??? 10D | FSU | THT Assembly Only DEPANEL MECH ASSY REQ - SEE DWG NOTES 13 & 14 LABEL PER ECO #5 TRIM LEADS 0.030 MAX PER ECO #6 INCLUDE S/N'S ON CofC |  | X | 0 | 0 | 0 | 44 | 4796 |  |  |  | FEDEX P | Boeing - Argon ST |  | DOC REL 11/30 |  | 1469.92 | THT ONLY |  |  |  |  | 1
|  |  |  | 122309 | 91 | 5 | FSU |  | REWORK 118686 | X |  |  |  |  | 0 |  |  |  | UPS 2ND DAY | Graph-Tech USA, LLC |  | NO DOC. |  | 2548 | [5 empty] | 1
|  |  |  | 121807 | 1 | 5 | FSU |  | REWORK 111657 | X |  |  |  |  | 0 |  |  |  | UPS 3DAY | Coastal Designs, LLC |  | NO DOC. |  | 400 | [5 empty] | 1
|  |  |  | 123871-2 | 10 | 10 | FSU |  |  | - |  |  |  |  | 0 |  |  |  | FEDEX P | Design Solutions Inc. |  | NO DOC. |  | 2298 | [5 empty] | 1
|  |  |  | 124685 | 25 | 5 | FSU | Component lead extension to be 0.140" max PER ECO #2 SPECIAL LABEL FORMAT REQ PER ECO #6 *READ - DEPANEL PER ECO #1 | NEW | NL | 57 | 218 | 1T | 29 | 725 |  |  |  | FEDEX P | Friedrich Air Conditioning LLC |  | DOC REL 3/27 |  | 2970.5 | [5 empty] | 2
|  |  |  | 121281-2 | 3 | 10 | FSU |  |  | - |  |  |  |  | 0 |  |  |  | UPS RED | Nottingham Spirk Design Associates, Inc. |  | NO DOC. |  | 5818.71 | [5 empty] | 1
|  |  |  | 121282-2 | 3 | 5 | FSU |  |  | - |  |  |  |  | 0 |  |  |  | UPS RED | Nottingham Spirk Design Associates, Inc. |  | NO DOC. |  | 2714.4 | [5 empty] | 1
|  |  |  | 122789-2ND | 98 | 5 | FSU |  |  | - |  |  |  |  | 0 |  |  |  | FEDEX GRD | Duotech Services Inc |  | NO DOC. |  | 36597.12 | [5 empty] | 1
|  |  |  | RBE-SYNC1-2.C.X-2 | 10 | 10 | FSU | *** (CUI) *** CLASS 3 SEE BUILD NOTES SEE READ ME PRIOR TO RUNNING |  | - |  |  |  |  | 0 |  |  |  | Vendor's Standard Shipping | "OK-UNO" |  | NO DOC. |  | 14564 | [5 empty] | 1
|  |  |  | 126277 | 6 | 2 | FSU |  | NEW | NL | 80 | 473 | 1B 1T | 9 | 54 |  |  |  | FEDEX P | Plexus Engineering Solutions |  | DOC REL 7/9 |  | 2000 | [5 empty] | 3
|  |  |  | 126891 | 3 | 10 | FSU | *** DoD DO-C9 RATING *** on hold | NEW | - | 119 | 839 |  | 55 | 165 |  |  |  | FEDEX P | Scientific Research Corporation |  | DOC REL 7/17 |  | 5122.8 | [5 empty] | 4
|  |  |  | 127250-2ND | 998 | 15 | FSU | TRUE NO CLEAN BUILD DEPANEL | NEW | - | 53 | 90 |  | 1 | 998 |  |  |  | FEDEX P | Hip Science, LLC |  | DOC REL 7/29 |  | 13395 | [5 empty] | 2
|  |  |  | 123007 | 162 | 10 | FSU |  |  | - |  |  |  |  | 0 |  |  |  | FEDEX P | Biomeme, Inc. |  | NO DOC. |  | 2901.02 | [5 empty] | 1
|  |  |  | 127321-2ND | 95 | 10 | FSU |  |  | - |  |  |  |  | 0 |  |  |  | FEDEX GRD | LMA Technologies LLC |  | NO DOC. |  | 6881 | [5 empty] | 1
|  |  |  | 123154 | 50 | 10 | FSU | Cancelled 08-22-2024 |  | X |  |  |  |  | 0 |  |  |  | FEDEX P | TEST COACH |  | NO DOC. |  | 6736.5 | [5 empty] | 1
|  |  |  | 127818 | 14 | 5 | FSU |  | REWORK 126223 | X |  |  |  |  | 0 |  |  |  | FEDEX P | L3 |  | NO DOC. |  | 1855 | [5 empty] | 1
|  |  |  | 127434 | 6 | 3 | FSU | SNA BUILD - DISREGARD |  | - |  |  |  |  | 0 |  |  |  | FEDE 2 DAY | Honeywell International Inc |  | NO DOC. |  | 6773.28 | [5 empty] | 1
|  |  |  | 127433 | 6 | 3 | FSU | SNA BUILD - DISREGARD |  | - |  |  |  |  | 0 |  |  |  | FEDE 2 DAY | Honeywell International Inc |  | NO DOC. |  | 7674.32 | [5 empty] | 1
|  |  |  | 127554 | 30 | 5 | FSU | T/H ONLY NO ECO SPACERS, WASHERS, NUTS & RED THREAD SEALANT REQUIRED... *** PLEASE READ THE "S&B Supplemental Work Instructions" PDF FROM CUSTOMER | NEW | X | 0 | 0 |  | 106 | 3180 |  |  |  | FEDEX P | GatesAir, Inc. |  | DOC REL 8/29 |  | 9324 | [5 empty] | 1
|  |  |  | 128280 | 1 | 3 | FSU |  |  | - |  |  |  |  | 0 |  |  |  | UPS RED | Innerspec Technologies, Inc |  | NO DOC. |  | 1850 | [5 empty] | 1
|  |  |  | 128297-2 | 23 | 10 | FSU |  |  | - |  |  |  |  | 0 |  |  |  | UPS GRD | Science & Engineering Services |  | NO DOC. |  | 3920.58 | [5 empty] | 1
|  |  |  | 128669-2 | 23 | 10 | FSU |  |  | - |  |  |  |  | 0 |  |  |  | UPS RED | Science & Engineering Services |  | NO DOC. |  | 5459.05 | [5 empty] | 1
|  |  |  | 127349 | 400 | 5 | FSU | CLASS 3 | NEW | NL | 25 | 42 | 2B 1T | 2 | 800 |  |  |  | FEDEX P | Industrialex Manufacturing |  | DOC REL 10/1 |  | 9424 | [5 empty] | 2
|  |  |  | 128574 | 75 | 20 | FSU | "LS1, LS2' U13" AFTER WASH DEPANEL & SAND PER ECO - BURRS NOT TO EXCEED 0.015" | NEW | - | 105 | 295 |  | 6 | 450 |  |  |  | FEDEX P | Nextern Inc. |  | DOC REL 10/14 |  | 9641.75 | [5 empty] | 4
|  |  |  | 128739 | 15 | 10 | FSU | "J2 & J10" MISSING PIN, PLACE PER ECO | NEW | - | 220 | 1749 |  | 35 | 525 |  |  |  | FEDEX P | Integrated Consultants |  | DOC REL 10/16 |  | 28152 | [5 empty] | 7
|  |  |  | 128713 | 250 | 10 | FSU |  |  | - |  |  |  |  | 0 |  |  |  | UPS GRD | Cogmedix, Inc. |  | NO DOC. |  | 7985 | [5 empty] | 1
|  |  |  | 129019 | 50 | 15 | FSU | LEAD FREE PROCESS ALPHA WS820 SOLDER PASTE REQ BOARDS TO BE FREE & CLEAN OF DEBRIS | NEW | NL | 5 | 49 | 1B 1T | 0 | 0 |  |  |  | FEDEX P | Ultracomm, Inc. |  | DOC REL 10/17 |  | 2860 | [5 empty] | 1
|  |  |  | 128917 | 200 | 10 | FSU | "LS1, IC1, SW_1" AFTER WASH LED'S W/ WIRES REQ SOLDERING PER ECO DEPANEL | RONC 107492 | NL | 16 | 25 | 1B 1T | 10 | 2000 |  |  |  | FEDEX P | ILC Dover |  | DOC REL 10/17 |  | 3876 | [5 empty] | 1
|  |  |  | 129046 | 215 | 5 | FSU | ***START ON DAY 1 OR SOONER |  | - |  |  |  |  | 0 |  |  |  | FEDEX P | Nextern Inc. |  | NO DOC. |  | 19798 | [5 empty] | 1
|  |  |  | 128821-2 | 35 | 3 | FSU |  |  | - |  |  |  |  | 0 |  |  |  | UPS RED | Reprieve Cardiovascular, Inc. |  | NO DOC. |  | 17422.3 | [5 empty] | 1
|  |  |  | 128513 | 45 | 10 | FSU |  |  | - |  |  |  |  | 0 |  |  |  | FEDEX GRD | Sea Land Aire |  | NO DOC. |  | 7889.2 | [5 empty] | 1
|  |  |  | 126996 | 2 | 10 | FSU |  |  | - |  |  |  |  | 0 |  |  |  | FEDEX 2DAY | Ideas-Tek |  | NO DOC. |  | 2767 | [5 empty] | 1
|  |  |  | 129087 | 175 | 5 | FSU |  |  | - |  |  |  |  | 0 |  |  |  | FEDEX P | Industrialex Manufacturing |  | NO DOC. |  | 2978.5 | [5 empty] | 1
|  |  |  | 128899 | 10 | 10 | FSU |  |  | - |  |  |  |  | 0 |  |  |  | FEDEX P | Advanced Acoustic Concepts, LLC |  | NO DOC. |  | 2579 | [5 empty] | 1
|  |  |  | 129171 | 50 | 3 | FSU |  |  | - |  |  |  |  | 0 |  |  |  | FEDEX P | Hoverfly Technologies Inc |  | NO DOC. |  | 15562.5 | [5 empty] | 1
|  |  |  | 128353 | 17 | 3 | FSU | "T1" DO NOT WASH PER ECO DEPANEL |  | - |  |  |  |  | 0 |  |  |  | FEDEX P | Plexus Engineering Solutions |  | NO DOC. |  | 5730.17 | [5 empty] | 1
|  |  |  | 128661 | 6 | 5 | FSU |  |  | - |  |  |  |  | 0 |  |  |  | FEDEX P | Augustus Aero |  | NO DOC. |  | 7791.62 | [5 empty] | 1
|  |  |  | 129147 | 25 | 3 | FSU |  |  | - |  |  |  |  | 0 |  |  |  | FEDEX P | Nordson Corporation |  | NO DOC. |  | 2675 | [5 empty] | 1
|  |  |  | 129275 | 50 | 10 | FSU |  |  | - |  |  |  |  | 0 |  |  |  | UPS GRD | Technical Marine Service, Inc. |  | NO DOC. |  | 3500 | [5 empty] | 1
|  |  |  | 128758 | 15 | 10 | FSU |  |  | - |  |  |  |  | 0 |  |  |  | FEDEX P | IonQ, Inc. |  | NO DOC. |  | 5614 | [5 empty] | 1
|  |  |  | 129215 | 110 | 5 | FSU | *** SHIP EARLY *** |  | - |  |  |  |  | 0 |  |  |  | FEDEX P | X-Microwave - A Quantic Company |  | NO DOC. |  | 18344.7 | [5 empty] | 1
|  |  |  | 129271 | 10 | 3 | FSU | *** SHIP EARLY *** |  | - |  |  |  |  | 0 |  |  |  | FEDEX P | Diligent Robotics |  | NO DOC. |  | 5288.5 | [5 empty] | 1
|  |  |  | 129150 | 50 | 3 | FSU | UPS RED - EARLY AM 830 |  | - |  |  |  |  | 0 |  |  |  | UPS RED | Blur Product Development |  | NO DOC. |  | 10191 | [5 empty] | 1
[7 empty] | FSU |  |  | - |  |  |  |  | 0 | [6 empty] | NO DOC. | [7 empty] | 1
[7 empty] | FSU |  |  | - |  |  |  |  | 0 | [6 empty] | NO DOC. | [7 empty] | 1
[7 empty] | FSU |  |  | - |  |  |  |  | 0 | [6 empty] | NO DOC. | [7 empty] | 1
[7 empty] | FSU |  |  | - |  |  |  |  | 0 | [6 empty] | NO DOC. | [7 empty] | 1
[7 empty] | FSU |  |  | - |  |  |  |  | 0 | [6 empty] | NO DOC. | [7 empty] | 1
[7 empty] | FSU |  |  | - |  |  |  |  | 0 | [6 empty] | NO DOC. | [7 empty] | 1
[7 empty] | FSU |  |  | - |  |  |  |  | 0 | [6 empty] | NO DOC. | [7 empty] | 1
[7 empty] | FSU |  |  | - |  |  |  |  | 0 | [6 empty] | NO DOC. | [7 empty] | 1
[7 empty] | FSU |  |  | - |  |  |  |  | 0 | [6 empty] | NO DOC. | [7 empty] | 1
Formulas:
SMT COMP DATE = IF(ISBLANK([DATE SMT START]),"",WORKDAY([DATE SMT START],#REF!,#REF!))

## SCHD
|  |  |  | S C H E D U L E |  |  |  | 2026-04-19 22:37
SHIPPED | LINE 1 | LINE 2 | LINE 3 | JOB | QTY | SHIP DATE | STATUS | MFG NOTES | TYPE | PROG | SMT LINES | SMT PLCMNTS | MACH | T/H | T/H EXT | STENCIL | KIT NOTES | SMT EST COMP DATE | SHIP METHOD | CUST | HISTORY | DOC REL | KIT REL | CODE | RELEASE NOTES | SHIP DATE | MACH SIDES | DATE SMT START | ACTUAL SMT TIME
|  |  | 3 | 127621-2 PAR | 120 | 10/30 10D 15D | RTR | CLASS 3 *** DEPANEL - CHECK W/ TAD BEFORE DEPANELING - MOUSE BITES WILL CAUSE DAMAGE *** MAKE SURE BOARDS ARE CLEAN | NEW | NL | 38 | 71 | 1B 2T | 0 | 0 | X | 9/27 - PCB DUE DATE 10/15 - PARTIAL CLEAR QTY 120 |  | FEDEX P | Integra Life Sciences | FLEX BOARD | DOC REL 8/13 | 8/19 | 4434 | BOT 1ST |  | 2
|  | 1 |  | 128786 | 345 | 10/30 10D | 10/21 - TOP 1:00 QTY 30 DONE 10/22 - QTY 142 10:00 10/22 - QTY 315 2:00 | LEAD PROCESS | RONC 124151 | NL | 29 | 56 | 2T | 4 | 1380 |  | 10/11 - U5 ETA BETWEEN 10/17 AND 10/21 SHORT 1 PCB - DUE 10/16 10/16 - KIT CLEAR |  | UPS RED | Technical Maintenance & Electronics Inc. |  | DOC REL 10/10 | 10/11 | 6703.35
|  |  | 1 | 128842 | 200 | 10/30 10D | 10/22 - BOT 10:00 10/22 - TOP 12:00 | LEAD PROCESS TRUE NO CLEAN DEPANEL | NEW | NL | 55 | 156 | 1B 2T | 5 | 1000 | X | 10/16 - KIT CLEAR |  | FEDEX GRD | Urban Sky Theory LLC |  | DOC REL 10/11 | 10/16 | 10268
| 1 |  |  | 128838 | 200 | 10/30 10D | 10/22 - BOT 1:30 | LEAD PROCESS "C38" AFTER WASH DEPANEL | NEW | NL | 75 | 304 | 2B 1T | 9 | 1800 | X | 10/9 - SHORT PCB, MP3, and U14, WAITING FOR TR# 10/16 - KIT CLEAR |  | FEDEX GRD | Urban Sky Theory LLC |  | DOC REL 10/8 | 10/9 | 17076
|  |  |  | 129008 SMT CLEAR | 200 | 10/30 5D | FSU | "U2, U4, U6, U8" MASK OFF PADS PER ECO *** KEEP GRIS HOLES FREE OF SOLDER PER ECO #3 FINAL QA BEFORE INSTALLING "S1" SHIELD INSTALL SHIELD COVERS PRIOR TO SHIPPING DEPANEL | RONC 127540 | NL | 33 | 167 | 1T | 9 | 1800 |  | 10/29 - PCB DUE DATE I SHORT S1 COVER (T/H) WITH NO ETA. 10/18 - SMT CLEAR 10/23 - KIT CLEAR |  | FEDEX P | TMC / Technical Manufacturing Corp. |  | DOC REL 10/17 | 10/18 | 9802
|  |  | 2 | 125151 | 2 | 10/31 10D | RTR | *** RUN ON LINE 3 ONLY (ALL LED'S)*** DEPANEL | NEW | NL | 5 | 648 | 1T | 336 | 672 | X | 10/17 - WAITING FOR 1 ITEM (DC1_1..) TO CONFIRM KIT CLEAR |  | FEDEX P | MPR Associates, Inc. |  | DOC REL 10/15 | 11/17 | 4316.8
|  | 2 |  | 129068 | 70 | 11/4 10D | FSU 1 | NO CLEAN PROCESS DEPANEL | NEW | NL | 80 | 132 | 1B 1T | 18 | 1260 | X | 10/17 - PCB & C4 ETA 10/26 10/21 - KIT CLEAR |  | FEDEX GRD | HunterLab |  | DOC REL 10/15 | 10/17 | 5760
| 2 |  |  | 127440-2 | 990 | 11/4 15D | FSU 3 | TRUE NO CLEAN ALL COMPONENTS FLUSH TO BOARD DEPANEL | RONC 1st Article | NL | 40 | 69 | 1B 2T | 0 | 0 |  | 10/14 - PCB DUE KIT CLEAR |  | FEDEX P | United Mesh Solutions, LLC | 9/30 - U6 PLACEMENT ISSUE PREVIOUSLY (NOT FLAT) ROBERT IS AWARE AND HAS ADJUSTED STENCIL | DOC REL 10/9 | 10/10 | 11068.2
|  |  | 3 | 129014 *NEED ITEM 34 TO START BOT SIDE 10/22 - RECV QTY 150 (75 BOARDS) | 125 | ??? 2D | FSU 2 | *** 2 DAY TURN *** LEAD PROCESS DEPANEL & SAND TO REMOVE ALL BURRS 0.015" MAX PER ECO #1 MAKE SURE BOARDS ARE FREE OF DEBRIS | NEW | NL | 45 | 129 | 1B 2T | 22 | 2750 |  | 10/21 - SHORT 4 ITEMS (D100, P206, R200 =SMT) & (P102 = T/H) |  | FEDEX P | Atlas Devices |  | DOC REL 10/21 | 10/21 | 13956.25
|  |  |  | 128690 | 70 | 11/05 10D | FSU 4 | DEPANEL & SAND | NEW | NL | 105 | 290 | 1B 2T | 1 | 70 | X | 10/22- PCB DUE / KIT CLEAR |  | FEDEX GRD | Fast Enterprises, LLC |  | DOC REL 10/10 | 10/14 | 8498
|  |  |  | 129188 | 10 | ??? 5D | FSU 5 | LEAD PROCESS DEPANEL | NEW | NL | 82 | 283 | 2T | 0 | 0 |  | 10/24 - PCB DUE |  | FEDEX P | Atomic Semiconductor |  | DOC REL 10/21 | 10/22 | 2802.2
|  |  |  | 128997 SMT CLEAR | 20 | ??? 5D | FSU | *** READ ECO #12 & 13 BEFORE RELEASING/RUNNING *** LEAD PROCESS - DISREGARD ROHS NOTE ON DWG "L1" AFTER WASH 10/17 - CUST MOVED C40 TO ITEM #18 INSTALL FUSES PRIOR TO SHIPPING *** ***TRIM LEADS TO 0.140" MAX HEIGHT*** *** "U1 & U2" HAVE MOUNTING TORERANCES - READ ECO #12 & #13 BEFORE INSTALING SHIPPING BOXES REQUIRE LABELS PER ECO #15 DEPANEL & SAND | NEW | NL | 113 | 363 | 2B | 65 | 1300 | X | 10/18 - 10/21 PCB DUE 10/15 - SHORT 4 SMT ITEMS & 5 THT ITEMS PENDING ON ETA 10/18 - SHORT L2, J6, and T1 & CONFIRM K1 (ALL T/H PARTS) 10/21 - SMT CLEAR, SHORT L2 & T1 (THT PARTS) - POSSIBLE NEXT WEEK |  | FEDEX P | Industrialex Manufacturing |  | DOC REL 10/14 | 10/15 | 9254
|  |  |  | 127752 *ORD NEW STENCIL | 100 | 11/05 10/14 10D 5D | FSU | ON HOLD DUE TO TOO MANY VIA HOLES LEAD PROCESS DEPANEL | NEW | NL | 38 | 110 | 1B 1T | 1 | 100 | X | 9/30 - PCB DUE 9/30 - KIT CLEAR 9/30 - RECEIVED PCB'S WITH VIAS CONNECTED TO PADS (16 LOCATIONS) 10/8 - CUSTOMER WILL RE-MAKE PCB'S 10/21 - NEW PCB DUE -RECEVIED BOARDS BUT NEED INSPECT & NEED NEW STENCIL RECEIVED 10/22 10/22 - KIT CLEAR |  | FEDEX GRD | Cardinal Peak, LLC |  | DOC REL 9/23 | 9/25 | 4140 | BOT 1ST |  | 2
|  |  |  | 126651 *HABD SOLDER SMT PARTS | 19 | 11/05 10D | FSU | CLASS 3 "XA1, XA2" HANDLE W/ CARE - HAND TIGHTEN ONLY "DO NOT USE ANY TOOLS" REMOVE ANY HARDWARE PRIOR TO SOLDERING AND WASHING - RE-INSTALL PRIOR TO SHIPPING *** *** DO NOT MIX HARDWARE PER ECO #6 TAG BOARDS W/ ANY BTD/DNI PARTS & NOTE ON PAPERWORK PER ECO | NEW | NL | 2 | 4 | 1T | 30 | 570 |  | 10/22 - KIT CLEAR BUT PENDING ON PCB REV.C TO BE CONFIRMED. PCB REV.C OK TO USED. |  | UPS RED | Coastal Designs, LLC |  | DOC REL 10/21 | 10/22 | 4714
|  |  |  | 129045 | 225 | 11/06 10D | FSU | CLASS 3 DEPANEL | NEW | NL | 2 | 2 | 1B 1T | 0 | 0 |  | 10/30 - PCB DUE 10/23 - KIT CLEAR |  | FEDEX P | Nextern Inc. |  | DOC REL 10/21 | 10/21 | 3947.5
|  |  |  | 128573 | 75 | 11/18 20D | FSU | DEPANEL & SAND PER ECO - BURRS NOT TO EXCEED 0.015" "R47 & RELATED x10" TRIM LEADS TO 0.045" MAX | NEW | - | 99 | 361 |  | 12 | 900 | X | 10/21 - KIT CLEAR |  | FEDEX P | Nextern Inc. |  | DOC REL 10/14 | 10/21 | 8718.75
|  |  | ??? | 128688 | 100 | ??? 10D | FSU | *** RUN ON LINE 3 ONLY (ALL LED'S) | NEW | NL | 9 | 211 | 1B 1T | 0 | 0 | X | 10/22 - SHORT LED105 WITH ETA 10/31 |  | FEDEX GRD | Fast Enterprises, LLC |  | DOC REL 10/11 | 10/22 | 6225
|  |  |  | 128821-1 *SET UPP BOT ONLY | 5 | ??? 5D | FSU | "LED1, 9, 10, 11, 12, 14" CHECK ECO FOR PLACEMENT "SW1, SW2, U5, L1" AFTER WASH "J41, J42, J43" MECH REQ PER ECO DEPANEL | NEW | NL | 146 | 565 | 2B 2T | 52 | 260 |  | 10/18 - SHORT PCB WTIH NO ETA. SHORT U29 (SMT) and A1 (T/H) ETA 10/22 |  | UPS RED | Reprieve Cardiovascular, Inc. |  | DOC REL 10/17 | 10/18 | 5331
|  |  |  | 126718 | 50 | 20D | FSU | UPON DOC RELEASE CHECK EMAIL FOR ADDITIONAL FILES PROVIDED BY CUST *** DO NOT DEPANEL UNTIL ASSY'S COME BACK FROM TEST COACH *** "SW11000" AFTER WASH "P22000" PRESS FIT INSTALL SHIELD FENCE PRIOR TO SHIPPING TO TEST COACH | RONC 125336 | NL | 127 | 895 | 1B 2T | 4 | 200 |  | 10/9 - PCB DUE ¦ SHORT FL3002 & FL3003 WITH NO ETA. 10/11, 10/17 OR LATER - SHORT PCB - NO ETA |  | FEDEX P | TEST COACH |  | DOC REL 8/8 | 10/8 | 12457.5
|  |  |  | 128454 | 5 | 10D | FSU | T/H ONLY INSTALL FUSES PER ECO DEPANEL | NEW | X | 0 | 0 |  | 130 | 650 |  | 10/9 - SHORT PCB WITH NO ETA |  | FEDEX GRD | Bruker Nano, RMR (FKA RAVE LLC) |  | DOC REL 10/8 | 10/8 | 4225
|  |  |  | 127321-1ST | 5 | ??? 10/10 10D | FSU | ON HOLD - TOO MANY VIA HOLES LEAD PROCESS "S1" AFTER WASH DEPANEL | NEW | NL | 57 | 233 | 1B 1T | 19 | 95 | X | 9/26- KIT CLEAR 9/27 - NOT CLEAR |  | FEDEX GRD | LMA Technologies LLC |  | DOC REL 7/29 | 9/26 | 6881 | BOT 1ST |  | 2
|  |  |  | 125202 | 25 | ??? 10D | RTR | ROSE TESTING MECH ASSY REQUIRED NO SPACER UNDER J1 (ECO) PCA CLEANING REQUIRED DEPANEL USING ROUTER METHOD ONLY LABEL @ LOC ON DRAWING | NEW | NL | 9 | 90 | 1B 1T | 15 | 375 | X | 5/16 - SHORT PCB THAN SMT CLEAR |  | FEDEX P | SUMMIT HOLLISTER |  | DOC REL 5/13 | 5/16 | 5625 | TOP 1ST |  | 2
|  |  |  | 128976 | 4 | ??? 3D | FSU | ***3 DAY TURN*** DEPANEL & SAND - SEE ECO FOR SPECIFIC CALLOUT TOLERANCE | NEW | NL | 19 | 170 | 1B 1T | 30 | 120 | X | 10/16 - SHORT PCB and J20A WITH NO ETA YET. |  | FEDEX P | Anduril |  | DOC REL 10/15 | 10/16 | 4546
|  |  |  | 128910 | 10 | ??? 5D | FSU | TRIM LEADS 0.130" MAX *** PACKAGE AND BOX TO PREVENT ANY DAMAGE - USE HEAVY BUBBLE AND MULTIPLE BOXES DEPANEL | NEW | - | 146 | 521 |  | 52 | 520 |  | 10/30 - PCB DUE DATE |  | FEDEX P | Engenious Design |  | DOC REL 10/16 | 10/18 | 8003.6
|  |  | 100 | 127621-3 BAL | 8 | ??? 15D | FSU | CLASS 3 *** DEPANEL - CHECK W/ TAD BEFORE DEPANELING - MOUSE BITES WILL CAUSE DAMAGE *** MAKE SURE BOARDS ARE CLEAN | NEW | NL | 38 | 71 | 1B 2T | 0 | 0 | X | 9/27 - PCB DUE DATE |  | FEDEX P | Integra Life Sciences | FLEX BOARD | DOC REL 8/13 | 8/19 | 11602.3 | BOT 1ST |  | 2
| LINE 1 | LINE 2 | LINE 3 | JOB/REL | QTY | SHIP DATE | STATUS | MFG NOTES | TYPE | PROG | SMT LINES | SMT PLCMNTS |  | T/H | T/H EXT | STENCIL | KIT NOTES | SMT COMP DATE | SHIP METHOD | CUST | HISTORY | DOC REL | KIT REL | CODE
|  |  |  | 107703-1 | 1 | ??? 5D | FSU |  |  |  | 124 | 326 | 41 | 124 | 124 | X | *SHORT PARTS - OK TO SKIP |  | FEDEX P | CROW ENG |  |  | 2/24 | 1572.4 |  | ???
|  |  |  | 110428 | 350 | ??? 10D | 5/15 - TOP 5/16 - BACK | DEPANEL THIS BOARD IS DAUGHTER BOARD TO B110198 *DO NOT SHIP THIS BOARD WITHOUT B110198* | NEW | NL | 2 | 1 | 1T | 2 | 700 | X | 6/8 - SMT CLEAR |  | OTHER | WALKMED |  |  | 6/8 | 3361 |  | ???
|  |  |  | 114334-4 | 344 | ??? 10D |  | R&R 2 LOCATIONS | PAID RWK |  | 7 | 35 | 19 | 2 | 688 | X |  |  | UPS RED | PARTICLE MEASURING SYSTEMS |  |  | 11/21 | 2050.24 |  | ???
|  |  |  | 114618-2 BAL | 15 | ??? 10D | 5/15 - BOT 5:00 5/15 - TOP 9:00 | 3 | NEW |  | 10 | 768 | 78 | 10 | 150 | X | 5/9 - OK TO SKIP #78 "T1-T6" |  | FEDEX GND | MAGNIX | 7/26 - SMT CLEAR |  | 5/9 | 3727.8 |  | ???
| 2 |  |  | 128090-2 BAL | 29 | ??? 5D | 9/13 - BOT 7:00 9/13 - PAUSE 1:00 9/16 - TOP 8:30 9/16 - AOI 10:30 | J7, J8, J2, J1, J3 ORIENTATION (ECO) CofC REQUIRES S/N FOR SMT, ASSEMBLE ALL BOARDS THAN PARTIAL SHIPMENT 51 OF 80 UNTIL BAL OF #19 (J3) ARRIVES | RONC 126369 | NL | 32 | 131 | 1B 1T | 7 | 203 | RONC | 9/11 - PCB DUE THAN CLEAR FOR 51 ¦ RUN ALL BOARDS IN SMT 9/12 - SMT CLEAR TO RUN ALL ¦ KIT CLEARED FOR 51 OF 80 BOARDS | #REF! | UPS GRD | Churchill Navigation dba Shotover Systems, Inc. |  | DOC REL 9/4 | 9/5 | 3180 | BOT 1ST | 2024-09-19 | 2 | 2024-09-12 | 8
|  |  | 1 | 127138-3 BAL | 40 | 1/4 10D | 10/17 - BOT 6:00 10/18 - AOI 6:00 | 30 10/22/2024 30 12/2/2024 40 1/4/2024 NO CLEAN PROCESS - DO NOT WASH DEPANEL | NEW | NL | 34 | 64 | 1B | 0 | 0 | X | 10/3 - PCB DUE ¦ SHORT #19 (U4) NO ETA 10/1 - KIT CLEAR |  | FEDEX GRD | McQ |  | DOC REL 9/23 | 9/25 | 2865 | top 1st | 2024-10-22 | 2
|  |  | 1 | 127138-2 PAR | 30 | 12/2 10D | 10/17 - BOT 6:00 10/18 - AOI 6:00 | 30 10/22/2024 30 12/2/2024 40 1/4/2024 NO CLEAN PROCESS - DO NOT WASH DEPANEL | NEW | NL | 34 | 64 | 1B | 0 | 0 | X | 10/3 - PCB DUE ¦ SHORT #19 (U4) NO ETA 10/1 - KIT CLEAR |  | FEDEX GRD | McQ |  | DOC REL 9/23 | 9/25 | 2865 | top 1st | 2024-10-22 | 2
|  |  |  | 129016 | 100 | 10/30 10D | FSU | T/H ONLY "IC3" COMPONENT REQUIRES LABEL W/ MFG DATE PER ECO *** "IC3 & C1" ARE BTD *** | NEW | X | 0 | 0 |  | 46 | 4600 |  | PCB & parts ETA 10/16 10/16 - KIT CLEAR |  | UPS GRD | Technical Marine Service, Inc. | *IF THERE IS SHORTAGE OF IC3 and C1 , PLEASE BUILD TO DEPLETION ON on IC3 and C1. | DOC REL 10/11 | 10/15 | 6946
| 1 |  |  | 128669-1st | 2 | 10/28 5D | 10/22 - BOT 10:00 10/22 - TOP 12:30 10/22 - AOI 1:30 | CUI "U41" MANDATORY NO CLEAN PER ECO "FX1, FX2" DNI - SHIP pARTS WITH 1ST ARTICLE PCBA'S | NEW | NL | 106 | 509 | 1B 2T | 42 | 84 | X | 10/16 - 10/23 PCB DUE 10/21 - KIT CLEAR |  | UPS RED | Science & Engineering Services |  | DOC REL 9/27 | 10/3 | 3421 | BOT 1ST |  | 2
| 1 |  |  | 124348 | 500 | 10/25 20D | 9/24 - BOT 8:30 9/25 - PAUSE 6:00 9/25 - BOT 12:00 9/26 - PAUSE 11:00 9/27 - BOT 6:00 9/27 - TOP 12:00 9/28 - PAUSE 2:30 10/8 - TOP 9:00 10/10 - PAUSE 10/15 - TOP 2:00 10/16 - AOI 11:00 | CLASS 3 *PLEASE IDENTIFY ANY "DNI" LOCATIONS WITH YELLOW ARROWS. SEGREGATE AND IDENTIFY ESD BAGS (DNI) PRIOR TO SHIPPING | RONC 120828 | NL | 120 | 400 | 2B 2T | 18 | 9000 | RONC | 8/30 - PCB DUE 9/23 - EXPECTED CLEAR BY DATE 9/27 - KIT CLEAR | 2024-10-14 | UPS GRD | Coastal Designs, LLC | 9/25 - 100 BOARDS BOT COMP (6 AM) 9/27 - BOT COMP (19.5 HRS) 9/28 - 109 BOARDS TOP COMP (2PM) | DOC REL 7/10 | 8/15 | 39220 | BOT 1ST | 2024-10-25 | 2 | 2024-09-24
| 1 |  |  | 128640 | 50 | 10/25 10D | 10/15 - BOT 6:00 10/15 - TOP 10:00 10/18 - AOI 1:30 | ***QUALITY ALERT - PREVIOUS BUILD B96858 - "J21 J11 J15 J22 J20 J18 J12 J25 J9 J6 J2 J8" WERE INSTALLED BACKWARDS. *** SEE "ARC_BOARD_CONNECTOR_ORIENTATION.PDF FOR REFERENCE "BUZ1, LCD1" AFTER WASH INSTALL MATING PARTS TO THE "J" CONNECTORS | ROWC 96858 | NL | 71 | 451 | 1B 1T | 48 | 2400 |  | 10/9 - SHORT PCB WITH NO ETA 10/17 - PCB DUE 10/11 - KIT CLEAR |  | FEDEX P | Rheem Manufacturing Company |  | DOC REL 10/8 | 10/8 | 11943.5
| 1 |  |  | 128764 | 35 | 10/24 5D | 10/21 - BOT 1:00 10/22 - TOP 6:00 10/22 - AOI 9:00 | ***(CUI) DPAS RATING DO-A7*** LEAD FREE PROCESS NO ADDITIONAL VENDOR MARKS ALLLWED "U30" USE MARKING AED/BAC+ "U29" IS BTD DEPANEL & SAND | NEW | NL | 93 | 657 | 2B 1T | 15 | 525 | X | 10/11 - SHORT C3, U7, U29 WITH NO ETA ¦ CONFIRM IF U30 OKAY TO USE. 10/17 - KIT CLEAR WITH PENDING ON U30 TO BE CONFIRM. *BUILD TO DEPLETION ON U29. |  | FEDEX P | John Hopkins University Applied Physics Lab |  | DOC REL 10/10 | 10/11 | 13545.15
|  |  | 1 | 122789-1ST | 2 | 10/23 3D | 10/18 - BOT 1:00 10/18 - TOP 1:30 10/18 - AOI 2:30 | *** 3 DAY TURN *** CLASS 3 CUI ***NO SOLDER SPLASH ON PLATED EDGE CONTACTS PER ECO #3 MAX COMPONENT HEIGHT PER ECO #5 "XU1A, XU1B, XU2A, XU2B" REQUIRES FIXTURE TO INSTALL PER ECO #6 DEPANEL | NEW | NL | 43 | 347 | 1B 1T | 5 | 10 |  | 10/17 - 1 ITEM (F5,F6) WAITING FOR CONFIRM. WE MAY START THIS JOB 10/21 10/23 - SHORT PARTS |  | FEDEX GRD | Duotech Services Inc |  | DOC REL 10/16 | 10/17 | 2977
|  |  |  | 114812-7 | 50 |  |  | BAKE BOARDS BEFORE SHIPPING CLASS 3 DEPANEL | RONC 1ST |  | 16 | 554 | 92 | 16 | 800 | X |  |  | UPS RED | Precision Graphics Inc |  |  |  | 5642 |  | 2023-02-28
Formulas:
SMT EST COMP DATE = IF(ISBLANK([DATE SMT START]),"",WORKDAY([DATE SMT START],#REF!,#REF!))

## NC LOG
SHIPPING NON-CONFORMANCE LOG
B NUMBER | DATE | TOT QTY | QTY REJ |  | NON CONFORMANCE | REF | QA INSP | PHOTO | note
119614 | 2023-08-03 | 40 | 0 | 0% | NO FINDINGS
119456 | 2023-08-03 | 10 | 0 | 0% | NO FINDINGS
118036 | 2023-08-03 | 8 | 0 | 0% | NO FINDINGS
119616 | 2023-08-03 | 48 | 0 | 0% | NO FINDINGS
119317 | 2023-08-03 | 60 | 2 | 3.333% | BENT LEADS | J1 |  | Y
119543 | 2023-08-03 | 165 | 48 | 29.09% | NOT TRIMMED LOW ENOUGH |  |  | Y
114318 | 2023-08-04 | 102 | 5 | 4.902% | 1 DAMAGED CAP, 4 IMPROPER TRIMMING | C2, U1, U4 |  | Y
119318 | 2023-08-04 | 102 | 0 | 0% | NO FINDINGS
117371 | 2023-08-04 | 12 | 0 | 0% | NO FINDINGS
118222 | 2023-08-07 | 80 | 0 | 0% | NO FINDINGS
119534 | 2023-08-07 | 35 | 0 | 0% | NO FINDINGS
118860 | 2023-08-07 | 8 | 0 | 0% | NO FINDINGS
118699 | 2023-08-07 | 2 | 2 | 100% | BENT LEADS | JP |  | Y
119534 | 2023-08-07 | 35 | 0 | 0% |  |  |  |  | NO AOI
119051 | 2023-08-07 | 20 | 0 | 0% |  |  |  |  | XRAY
119660 | 2023-08-08 | 15 | 0 | 0%
118651 | 2023-08-08 | 3 | 0 | 0%
118943 | 2023-08-08 | 45 | 0 | 0% |  |  |  |  | CUST IS ABB - J66 & RELATED - ECO SHOWS CONFLICTING PIN 1 DIAGRAMS
119672 | 2023-08-08 | 30 | 0 | 0% |  |  |  |  | TILT @ Y2 - CONNECTION IS OK
119677 | 2023-08-08 | 100 | 0 | 0% |  |  |  | Y | DEPANEL ISSUE - THICK BOARD - CANNOT DEPANEL DUE TO DESIGN
119433 | 2023-08-08 | 5 | 2 | 40% | SOLDER BALL | C9, C10, C13 |  | Y
119659 | 2023-08-09 | 15 | 1 | 6.667% | MISSING HARDWARE |  |  | Y
119403 | 2023-08-09 | 9 | 0 | 0%
118974 | 2023-08-09 | 15 | 1 | 6.667% | DAMAGED INDUCTOR | L22 |  | Y | *SEVERAL INDUCTORS TILTED/MISALIGNED - TOO MUCH SOLDER
119565 | 2023-08-09 | 50 | 0 | 0%
119468 | 2023-08-10 | 96 | 1 | 1.042% | BENT LEADS | J1 |  | Y
119071 | 2023-08-10 | 40 | 0 | 0%
119754 | 2023-08-10 | 30 | 0 | 0% |  |  |  | Y | *SEVERAL DIODESS TILTED/MISALIGNED - TOO MUCH SOLDER
115809 | 2023-08-11 | 10 | 0 | 0%
119067 | 2023-08-11 | 50 | 0 | 0%
117522 | 2023-08-11 | 105 |  | 0%
118705 | 2023-08-11 | 100 | 7 | 7% | BENT TABS, 1 RED ARROW & TOMBSTONES, MP | RJ1, RJ159, R44, D15 |  | Y
118087 | 2023-08-17 | 50 | 6 | 12% | INSUFICIENT SOLDER | J5, J9, J12, 13 |  | Y
119499 | 2023-08-17 | 6 | 0 | 0%
120057 | 2023-08-17 | 5 | 0 | 0%
119812 | 2023-08-17 | 250 | 0 | 0%
119437 | 2023-08-18 | 5 | 1 | 20% | CAPS TOUCHING/BRIDGE | C10, C93 |  | Y
118691 | 2023-08-18 | 60 | 6 | 10% | CONN MISALIGNED | J1, J2 |  | Y
120057 | 2023-08-21 | 5 | 0 | 0%
119962 | 2023-08-22 | 5 | 0 | 0%
117522 | 2023-08-22 | 20 | 0 | 0% |  |  |  |  | ICC MED
119998 | 2023-08-22 | 100 | 0 | 0%
119384 | 2023-08-22 | 50 | 0 | 0%
119747 | 2023-08-24 | 25 | 0 | 0%
119826 | 2023-08-24 | 20 | 0 | 0%
118109 | 2023-08-24 | 375 | 2 | 0.5333% | DAMAGED LED & MISSING LED |  |  | Y
119480 | 2023-08-25 | 5 | 0 | 0%
119492 | 2023-08-25 | 75 | 0 | 0%
118109 | 2023-08-25 | 375 | 0 | 0%
114615 | 2023-08-25 | 20 | 16 | 80% | IMPROPER TRIMMING, 3 DAMAGED FROM DEPANEL |  |  | Y
119272 | 2023-08-25 | 45 | 1 | 2.222% | BURNED CONN & RED ARROW (MISSING PART) |  |  | Y
116086 | 2023-08-25 | 175 | 0 | 0%
119913 | 2023-08-30 | 69 | 0 | 0% | POSS INSUF. SOLDER @ U17 |  |  |  | POSS INSUF. SOLDER @ U17 - SOME TOUCHED UP, SOME NOT
120150 | 2023-08-31 | 20 | 0 | 0%
119849 | 2023-08-31 | 80 | 1 | 1.25% | EXPOSED COPPER |  |  | Y | QA LET GO - TAD REJECTED
118969 | 2023-08-31 | 250 | 12 | 4.8% | OPEN SOLDER | Y1, Y2 |  | N
119071 | 2023-09-08 | 50 | 1 | 2% | J2 PIN NOT SOLDERED PER ECO/CUSTOMER ALERT | J2 | QA12 | N
120218 | 2023-09-08 | 70 | 0 | 0% |  |  | QA13
119276 | 2023-09-11 | 140 | 0 | 0% |  |  | QA12 | Y | POSS INSUF. SOLDER @J2 - TRINH SAID OK, 50%MIN SOLDER FILL REQ
116508 | 2023-09-11 | 120 | 0 | 0% |  |  | QA13
119296 | 2023-09-13 | 64 | 0 | 0% |  |  | QA13
120450 | 2023-09-13 | 135 | 0 | 0% |  |  | QA13
119924 | 2023-09-13 | 30 | 0 | 0% |  |  | QA12
120465 | 2023-09-15 | 10 | 0 | 0% |  |  | QA13
119275 | 2023-09-15 | 45 | 0 | 0% |  |  | QA13 |  | NOTE: RECOMMEND DOING AWAY WITH MOUSE BITE @ "LED1"
119188 | 2023-09-20 | 40 | 3 | 7.5% | MISSING QA STAMP |  | QA12 |  | SENT BACK TO QA
120492 | 2023-09-20 | 80 | 0 | 0% |  |  | QA12
120561 | 2023-09-20 | 2 | 1 | 50% | MISSING QA STAMP |  | QA12 |  | SENT BACK TO QA
118860 | 2023-09-20 | 12 | 0 | 0% |  |  | QA12
119925 | 2023-09-20 | 20 | 0 | 0% |  |  | QA13
120556 | 2023-09-22 | 6 | 0 | 0% |  |  | QA12
119346 | 2023-09-22 | 2 | 0 | 0% |  |  |  |  | QA DONE - NO STAMP REQ
119574 | 2023-09-22 | 70 | 0 | 0% |  |  | QA8 |  | NOTE: DEPANEL/SAND NOT GOOD
119343 | 2023-09-22 | 248 | 0 | 0% |  |  | QA13 |  | NOTE: SAND NOT GOOD. Qty 2 u17 btd
116819 | 2023-09-26 | 5 | 0 | 0% |  |  | QA13
118702 | 2023-09-27 | 100 | 0 | 0% |  |  | QA8
119676 | 2023-09-27 | 50 | 0 | 0% |  |  | QA13
120889 | 2023-09-27 | 100 | 0 | 0% |  |  | QA13
120474 | 2023-09-29 | 5 | 0 | 0% |  |  | QA13
120532 | 2023-09-29 | 150 | 0 | 0% |  |  | QA13
118397 | 2023-10-02 | 90 |  | 0% |  |  | QA12
119344 | 2023-10-02 | 248 | 6 | 2.419% |  |  | TAD |  | QTY 4 BRIDGING/FLUX & QTY 2 NO SOLDER ON T/H CONN
120702 | 2023-10-02 | 20 | 1 | 5% |  |  | QA13 |  | QTY 1 W/ RED ARROW - NEEDED TOUCH UP
| 2023-10-02 | 20 | 1 | 5% |  |  | QA13 |  | QTY 1 D33 SIDEWAYS - ANDERSON
120701 | 2023-10-03 | 6 | 0 | 0% |  |  | QA13
120636 | 2023-10-03 | 40 | 0 | 0% |  |  | QA13
120499 | 2023-10-05 | 50 | 0 | 0% |  |  | QA12
120259 | 2023-10-05 | 1200 | 1 | 0.08333%
120528 | 2023-10-06 | 98 |  | 0% |  |  | QA13
119291 | 2023-10-06 | 50 | 0 | 0% |  |  | QA12
117094 | 2023-10-06 | 400 |  | 0% |  |  | QA12
120864 | 2023-10-06 | 80 | 0 | 0% |  |  | QA13
118628 | 2023-10-10 | 1550 | 4 | 0.2581% |  |  | QA12 |  | QTY 1 - CN4 INSUF. SOLDER, QTY 1 X1 NO SOLDER, QTY 1 X2 BRIDGE, QTY 1 X2 BENT LEAD
120288 | 2023-10-11 | 50 | 0 | 0% |  |  | QA13 |  | INSP BY HAI
120287 | 2023-10-13 | 50 | 0 | 0% |  |  | QA13 |  | QTY 6 HAD FLUX FROM T/U, QTY 2 SLIGHT BURN ON LOCK13 & LOCK14 - LET GO
119829 | 2023-10-13 | 200 | 0 | 0% |  |  | QA12 |  | DID NOT SAND - PHOTOS IN FILE SHOWED NO SANDING
119849 | 2023-10-16 | 49 | 0 | 0% |  |  |  |  | REWORK
120284 | 2023-10-16 | 20 | 0 | 0% |  |  | QA12 |  | QTY 3 - SOME LOCATIONS NOT TRIMMED
117366 | 2023-10-17 | 100 | 0 | 0% |  |  | QA8 |  | INCONSISTANT TRIMMING, 1 WITH LEADS TOUCHING
114862 | 2023-10-18 | 450 | 5 | 1.111% |  | L4, L5 | QA8, QA12, QA13 |  | QTY 5 DAMAGED, QTY 48 MISSING LABELS, QTY8 NOT SANDED
119594 | 2023-10-20 | 25 | 0 | 0% |  |  | QA13
121252 | 2023-10-20 | 5 | 0 | 0% |  |  | QA12
116310 | 2023-10-20 | 200 | 0 | 0% |  |  | QA13 |  | SPLIT SHIPMENT
120820 | 2023-10-25 | 50 | 10 | 20% |  |  | QA12 |  | QTY 10 NOT TRIMMED @ "PS1"
121408 | 2023-10-31 | 50 | 0 | 0% |  |  |  |  | INSP BY THOMAS; SOME SOLDER NEEDED TO BE CHIPPED OFF LEAD (TOO MUCH SOLDER)
121504 | 2023-11-01 | 21 | 0 | 0% |  |  | QA13
120633 | 2023-11-03 | 2 | 0 | 0% |  |  |  |  | RWK
121284 | 2023-11-03 | 30 | 0 | 0%
120927 | 2023-11-03 | 10 | 0 | 0% |  |  |  |  | no stamps allowed - P1-P6 DNI due to press fit too loose & RXlocations btd
121472 | 2023-11-03 | 70 | 0 | 0% |  |  | QA12
119482 | 2023-11-06 | 395 | 0 | 0% |  |  |  |  | missed trim leads
121364 | 2023-11-06 | 20 | 0 | 0% |  |  | QA12
120284 | 2023-11-09 | 50 | 0 | 0% |  |  | QA12 |  | QTY 33 MISSED TRIM LEADS
121693 | 2023-11-09 | 105 | 0 | 0% |  |  | QA12
121658 | 2023-11-09 | 21 | 0 | 0% |  |  | QA12
121559 | 2023-11-09 | 5 | 0 | 0% |  |  | QA13
119432 | 2023-11-09 | 2 | 0 | 0% |  |  | QA12
121417 | 2023-11-13 | 121 | 0 | 0% |  |  |  |  | SPLIT SHIPMENT - QTY 17 TO AA, BAL TO CUST
120807 | 2023-11-13 | 150 |  | 0%
121671 | 2023-11-13 | 5 | 0 | 0% |  |  | QA13
116970 | 2023-11-17 | 60 | 0 | 0% |  |  | QA12 |  | QTY MISSING HARDWARE, QTY 1 EDGE NOT SANDED
116956 | 2023-11-17 | 60 | 0 | 0% |  |  | QA13
120886 | 2023-11-17 | 5 | 0 | 0% |  |  | QA12
116955 | 2023-11-17 | 2 | 0 | 0% |  |  | QA13 |  | QTY 2 MISSING HARDWARE
116967 | 2023-11-17 | 60 | 0 | 0% |  |  | QA13 |  | QTY 3 MISSING HARDWARE
116954 | 2023-11-17 | 60 | 0 | 0% |  |  | QA13
116957 | 2023-11-20 | 2 | 0 | 0% |  |  | QA13
119023 | 2023-12-14 | 8 | 3 | 37.5% |  |  | QA13 | Y | "J10" BENT LEADS
122444 | 2023-12-14 | 350 | [6 empty] | MISSING JUMPERS, MISSED TRIM LEADS, MISSING "JP" CONN

## SHIPPED (AA)
SHIPPED | PCB NOTES | KIT NOTES | SCHEDULING NOTES | FEEDER S/U | LINE 1 | LINE 2 | LINE 3 | JOB | QTY | SHIP DATE | PROG | STENCIL | MFG NOTES | BOTTOM | TOP | AOI | SMT LINES | SMT PLCMNTS | MACH | T/H | T/H EXT | SHIP METHOD | CUSTOMER | SALES P | HISTORY | DOC REL | KIT REL | CODE
2024-10-23 |  | 10/10 - PCB DUE ¦ MANY TAPE & REEL REQUIRED 10-24 - PCB DUE 10/18 - KIT CLEAR |  |  |  |  | 1 | 128561 NEW | 3 | 10/23 3D | NL | X | *** 3 DAY TURN *** DoD (CUI) MAKE SURE BOARDS ARE PRE-BAKED CLASS 3 NO ECO |  |  | 10/21 - BOT 1:00 10/22 - TOP 6:00 10/22 - AOI 10:00 | 21 | 596 | 1B 1T | 25 | 75 | FEDEX P | Moog Space & Defense |  |  | DOC REL 9/27 | 9/30 | 4695.3 | BOT 1ST |  | 2 |  |  | 2
2024-10-23 |  | 10/10 - PCB DUE ¦ SHORT MANY PARTS WITH NO CURRENT ETA 10/10 - KIT CLEAR 10/18 - PCB ISSUE - NOT MATCHING STENCIL (WILL REMOVE "Q2" MASKING) |  |  |  |  | 1 | 128753 NEW | 48 | 10/23 10D | NL | X | *** DO NOT DEPANEL *** NO CLEAN PROCESS |  |  | 10/17 - TOP 1:45 10/21 - AOI 12:00 | 78 | 165 | 2T | 0 | 0 | FEDEX P | Gentex Corporation (MI) |  |  | DOC REL 10/1 | 10/7 | 5356 | TOP 1ST |  | 1 |  |  | 3
2024-10-22 |  | 10/3 - PCB DUE ¦ SHORT #19 (U4) NO ETA 10/1 - KIT CLEAR |  |  |  |  | 1 | 127138 NEW | 30 | 10/22 10/15 10D | NL | X | 30 10/22/2024 30 12/2/2024 40 1/4/2024 NO CLEAN PROCESS - DO NOT WASH DEPANEL |  |  | 10/17 - BOT 6:00 10/18 - AOI 6:00 | 34 | 64 | 1B | 0 | 0 | FEDEX GRD | McQ |  |  | DOC REL 9/23 | 9/25 | 2865 | top 1st | 2024-10-22 | 2 |  |  | 2
2024-10-22 |  | 10/11 - SHORT PCB WITH NO ETA PCB DUE 10/18 10/18 - KIT CLEAR |  |  |  | 1 |  | 128929 NEW | 10 | 10/22 2D | NL | X | *** 2 DAY TURN *** "PZ1, U28" AFTER WASH SPLIT SHIPMENT: QTY TO ERGOTRON 1181 TRAPP RD & QTY 2 TO ENOVATE 1152 PARK AVE |  |  | 10/18 - BOT 10:00 10/21 - TOP 6:00 12/21 - AOI 11:30 | 95 | 364 | 1B 2T | 12 | 120 | FEDEX P | Ergotron, Inc. |  |  | DOC REL 10/11 | 10/11 | 12973.6 | [5 empty] | 3
2024-10-22 |  | 10/11 - PCB DUE ¦ AWT PART CONF #26 (CR42..) 10/17 - PCB DUE 10/17 KIT CLEAR |  |  | 1 |  |  | 128342 NEW | 30 | 10/22 3D | NL | X | *** 3 DAY TURN *** ***10/3 - PCB REV LEVEL UPDATED TO REV 002 FROM 001 - PLEASE MAKE SURE WE RECEIVE REV 002 PCB'S NO CLEAN PROCESS "C159, C192, C173" REQUIRES EPOXY DOW 3145 (1 HR WORK TIME ¦ 48 HR CURE) 9/23 - customer provide epoxy |  |  | 10/17 - BOT 1:30 10/18 - TOP 9:30 10/18 - 20 LEFT 2:30 10/21 - AOI 9:30 | 97 | 633 | 1B 1T | 28 | 840 | FEDEX P | Saronic Technologies |  |  | DOC REL 9/23 | 9/24 | 13986 | bot 1st |  | 2 |  |  | 3
2024-10-21 |  | 10/9 - SHORT #17 (U1..) QTY.55, ETA 10/11. 11/14 - KIT CLEAR |  |  |  | 1 |  | 127438-2 RONC 1st Article | 180 | 10/21 5D | NL |  | TRUE NO CLEAN XRAY & SAVE IMAGES ALL COMPONENTS FLUSH TO BOARD DEPANEL |  |  | 10/16 - BOT 12:00 10/17 - TOP 8:30 10/17 - AOI 1:30 | 34 | 59 | 1B 1T | 0 | 0 | FEDEX P | United Mesh Solutions, LLC |  |  | DOC REL 10/9 | 10/9 | 4361.4 | [5 empty] | 2
2024-10-21 |  | 10/8 - short pcb & #37 (U1) no ETA 10/15 - PCB DUE 10/14 - KIT CLEAR |  |  | 1 |  |  | 128282 NEW | 20 | 10/21 5D | NL |  | "S1-4" AFTER WASH DEPANEL |  |  | 10/16 - BOT 12:00 10/17 - TOP 8:30 10/17 - AOI 11:00 | 124 | 1125 | 1B 2T | 32 | 640 | FEDEX P | Nordson Corporation |  |  | DOC REL 10/7 | 10/8 | 16462.6 | bot 1st |  | 2 |  |  | 4
2024-10-21 |  | 10/7 - KIT CLEAR |  |  |  | 1 |  | 125020 NEW | 50 | 10/21 10D | NL | X | *** PRE=PCB INSPECTION FOR INK & COPPER STAMPS - IF FOUND NOTIFY CUSTOMER - NO MARKINGS ALLOWED WATER COLUABLE PASTE & FLUX REQ *** REMOVE ALL FLUX RESIDUE DEPANEL |  |  | 10/15 - BOT 6:00 10/15 - TOP 1:30 10/16 - AOI 11:30 | 80 | 263 | 1B 1T | 10 | 500 | UPS GRND | Moxtek |  |  | DOC REL 10/4 | 10/7 | 5733 | BOT 1ST | 2024-10-21 | 2 |  |  | 3
2024-10-18 |  | 9/10 – PCB due date ¦ AWT PART CONF: #18 (D19) & #31 (U6) 10/14 - PCB DUE 10/15 - KIT CLEAR (HOLD - FAB ISSUE) |  |  |  |  | 1 | 127780 NEW | 4 | 10/21 10/18 3D | NL | X | *** 3 DAY TURN *** *** 10/15 KIT CLEAR BUT NOW NEED FIXTURE TO PRINT FLEX END DEPANEL & SAND PACKAGE WITH EXTRA CARE |  |  | 10/15 - FSU-HOLD 10/17 - IS DAY ONE 10/16 - BOT 12:30 10/17 - TOP 6:00 10/17 - AOI 9:30 | 77 | 266 | 1B 1T | 3 | 12 | FEDEX P | National Geographic |  |  | DOC REL 8/22 | 9/6 | 4332 | bot 1st |  | 2 |  |  | 3
2024-10-18 |  | 9/30 - SHORT PCB WITH NO ETA 10/9 - PCB DUE 10/4 - KIT CLEAR |  |  |  |  | 2 | 128348 NEW | 10 | 10/18 10D | NL | X | DEPANEL & SAND - REMOVE ALL BURRS/SHARP EDGES 0.15 MAX "J1, J4" SPECIFIC HEIGHT REQUIREMENTS PER ECO #3 |  |  | 10/15 - BOT 6:00 10/16 TOP 7:30 10/16 - AOI 10:00 | 42 | 124 | 1B 1T | 6 | 60 | FEDEX P | Nor-Cal Products dba Pfeiffer Vacuum, Inc. |  |  | DOC REL 9/24 | 9/30 | 3097 | BOT 1ST | 2024-10-18 | 2 |  |  | 2
2024-10-18 |  | 10/4 - KIT CLEAR | [5 empty] | 128731 NEW | 50 | 10/18 10D | X |  | T/H ONLY JUMPERS REQ PER ECO |  |  | FSU | 0 | 0 |  | 51 | 2550 | UPS GRD | Technical Marine Service, Inc. |  |  | DOC REL 10/1 | 10/3 | 3500 | [5 empty] | 1
2024-10-17 |  | 10/9 - KIT CLEAR (USE 10/11 AS DAY 1) |  |  |  |  | 1 | 127439-2 RONC 1st Article | 180 | 10/17 5D | NL |  | XRAY & SAVE IMAGES ALL COMPONENTS FLUSH TO BOARD DEPANEL |  |  | 10/15 - BOT 9:00 10/15 - TOP 11:00 10/15 - AOI 1:30 | 6 | 6 | 1B 1T | 0 | 0 | FEDEX P | United Mesh Solutions, LLC |  |  | DOC REL 10/9 | 10/9 | 2592 | [5 empty] | 1
2024-10-16 |  | 10/8 - PCB DUE 10/9 - KIT CLEAR |  |  |  | 1 |  | 128297-1ST NEW | 2 | 10/16 5D | NL | X | "C1,C2,C23,D5" STAKING REQ PER ECO (DOW CORNING 3140 IS APPROVED TO USE) T/H TEST POINTS TO BE POPULATED IN ORIENTATIONS SHOWN +/- 30 DEG (SEE DWG SHEET 3 OF 7) DEPANEL & SAND |  |  | 10/11 - BOT 12:00 10/14 - TOP 6:00 10/14 - AOI 10:30 | 25 | 158 | 1B 1T | 27 | 54 | UPS GRD | Science & Engineering Services |  |  | DOC REL 9/24 | 10/4 | 2510 | BOT 1ST |  | 2 |  |  | 2
2024-10-16 |  | 9/30 - SMT CLEAR 10-2 - KIT CLEAR |  |  |  |  | 1 | 125915 NEW | 25 | 10/16 10D | NL | X | *** PRE=PCB INSPECTION FOR INK & COPPER STAMPS - IF FOUND NOTIFY CUSTOMER - NO MARKINGS ALLOWED REMOVE ALL FLUX RESIDUE!!! *** "J2 & J3" PROTECT WITH FOAM BLOCK TO PREVENT SHIPPING DAMAGE "J7" TRIM WELD TABS PRIOR TO SOLDERING PER ECO DEPANEL & SAND |  |  | 10/14 - TOP 6:00 10/14 - AOI | 58 | 210 | 1T | 18 | 450 | UPS GRND | Moxtek |  |  | DOC REL 9/18 | 9/30 | 2952.5 | TOP ONLY | 2024-10-16 | 1 |  |  | 2
2024-10-16 |  | 9/30 - SHORT PCB THEN SMT CLEAR 10/8 - PCB DUE 10/9 - KIT CLEAR |  |  | 1 |  |  | 128615 NEW | 50 | 10/16 5D | NL | X | LEAD PROCESS MOUNT ALL T/H FLUSH DEPANEL |  |  | 10/11 - BOT 12:00 10/14 - TOP 6:00 10/14 - AOI 12:00 | 70 | 313 | 1B 1T | 29 | 1450 | FEDEX P | Flock Safety |  |  | DOC REL 9/27 | 9/30 | 8480 | BOT 1ST U1000 REQUIRE DEPANEL BEFORE SMT? |  | 2 |  |  | 3
2024-10-16 |  | 10/10 - KIT CLEAR 10/10 - RECVD REV 1 & 2 PCBS - CHECKING W/ CUST - ADD ONE DAY 10/11 - KIT CLEAR 10/11 - BOT SIDE 8:00 10/11 - TOP 10:00 |  |  | 1 |  |  | 128960 NEW | 10 | 10/16 3D | NL |  | *** 3 DAY TURN *** LEAD PROCESS "J10" REMOVE SOLDER PASTE PER ECO #2 "U14, Y2" AFTER WASH 10/10 - OK TO USE PCB QTY 5 REV OO1 & QTY 5 REV 002 |  |  | 10/11 - BOT 8:00 10/11 - TOP 10:00 10/11 - AOI 12:00 | 66 | 438 | 1B 2T | 52 | 520 | FEDEX P | Avtron Power Solutions |  |  | DOC REL 10/7 |  | 6004.2 | [5 empty] | 3
2024-10-16 |  | 10/3 - PCB DUE 9/25 - KIT CLEAR |  |  |  |  | 1 | 128382 ROWC 120259 | 1100 | 10/16 15D | NL | ROWC | "J1" T/H - REMOVE MIDDLE PIN" DEPANEL |  |  | 10/3 - BOT 11:30 10/3 - PAUSE 2:00 10/7 - BOT 11:00 10/9 - TOP 10/10 - TOP 12:00 - 150 PANELS LEFT 10/11 - TOP LINE 3 10/11 - AOI | 17 | 96 | 1B 1T | 1 | 1100 | FEDEX GRD | Radiation Detection Technologies, Inc. |  | 9/23 - J1 = T/H PART | DOC REL 9/17 | 9/23 | 19745 | BOT 1ST | 2024-10-16 | 2 | 2024-10-04 |  | 1
2024-10-15 |  | 8/19 - SHORT PCB WITH NO ETA 9/10 - PCB DUE 9/23 - AWT FIXTURE THEN CLEAR 9/25 - KIT CLEAR |  |  |  |  | 2 | 127621-1 PAR NEW | 186 | 10/16 15D | NL | X | CLASS 3 *** DEPANEL - CHECK W/ TAD BEFORE DEPANELING - MOUSE BITES WILL CAUSE DAMAGE *** MAKE SURE BOARDS ARE CLEAN |  |  | 10/1 - BOT 8:00 10/2 - PAUSE 9:00 10/14 - DONE 10:00 | 38 | 2 | 1B 2T | 0 | 0 | FEDEX P | Integra Life Sciences |  | FLEX BOARD 9/23 - robert borrowed a bare FAB to make a fixture 10/1 - BOARD / FIXTURE ISSUE | DOC REL 8/13 | 8/19 | 14222.7 | BOT 1ST | 2024-10-16 | 5 | 2024-08-10 |  | 2
2024-10-15 |  | 10/8 - #3 (J2) DUE DATE 10/8 - KIT CLEAR |  |  | 1 |  |  | 125153-2 BAL NEW | 75 | 10/15 5D | NL | X | ORDER IS FOR APPLE - PLEASE ENSURE GOOD QUALITY THROUGHOUT JUMPERS REQUIRED PER ECO DEPANEL & SAND |  |  | 10/14 - TOP 12:30 10/14 - AOI 2:00 | 4 | 4 | 1T | 2 | 150 | FEDEX P | Summit Santa Clara-Streamline Circuits |  |  | NO DOC. | 10/7 | 6668 | TOP ONLY | 2024-10-15 | 1 |  |  | 1
2024-10-15 |  | 9/30 - PCB DUE 10/1 - KIT CLEAR |  |  | 1 |  |  | 125916 NEW | 25 | 10/15 10D | NL | X | LEAD-FREE WASH *** PRE=PCB INSPECTION FOR INK & COPPER STAMPS - IF FOUND NOTIFY CUSTOMER - NO MARKINGS ALLOWED REMOVE ALL FLUX RESIDUE!!! *** "J2 & J3" PROTECT WITH FOAM BLOCK TO PREVENT SHIPPING DAMAGE "J7" TRIM WELD TABS PRIOR TO SOLDERING PER ECO DEPANEL & SAND |  |  | 10/10 - BOT 12:00 10/11 - TOP 6:00 10/11 - AOI 7:30 | 61 | 229 | 1B 1T | 11 | 275 | UPS GRND | Moxtek |  |  | DOC REL 9/18 | 9/30 | 2896.25 | BOT 1ST | 2024-10-15 | 2 |  |  | 3
2024-10-15 |  | 10/8 - PCB DUE 10/1 - KIT CLEAR | [5 empty] | 128451 NEW | 10 | 10/15 10D | X |  | T/H ONLY DEPANEL |  |  | FSU | 0 | 0 |  | 53 | 530 | FEDEX GRD | Bruker Nano, RMR (FKA RAVE LLC) |  |  | DOC REL 9/24 | 9/30 | 2650 | [5 empty] | 1
2024-10-14 |  | 9/25 - SHORT ATTRITION 9/30 - KIT CLEAR |  |  |  | 1 |  | 120425-2ND RONC 1st Article | 3 | 10/14 10D 5D | NL | RONC | DEPANEL |  |  | 10/11 - TOP SIDE 6:00 10/11 - AOI | 45 | 2807 | 2T | 15 | 45 | UPS RED | Nottingham Spirk Design Associates, Inc. |  |  | DOC REL 9/24 | 9/25 | 2406.6 | TOP ONLY | 2024-10-14 | 1 | 2024-10-09 |  | 2
2024-10-14 |  | 10/10 - KIT CLEAR |  |  |  |  | 1 | 128642 NEW | 3 | 10/14 2D | NL |  | CLASS 3 *** 2 DAY TURN *** FAIR REQUIRED "J1" MECH REQ BEFORE SOLDERING PER ECO STAKING REQ X13 |  |  | 10/10 - BOT 12:00 10/10 - TOP 2:30 10/10 - AOI | 42 | 210 | 1B 1T | 86 | 258 | FEDEX P | QinetiQ |  |  | DOC REL 10/2 | 10/10 | 6154 | [5 empty] | 2
2024-10-14 |  | 10/2 - PCB DUE ¦ SHORT #14 (D1..) NO ETA 9/30 - KIT CLEAR |  |  | 2 |  |  | 128532 RONC 123657 | 50 | 10/14 10D 5D | NL | RONC | CLASS 3 NO CLEAN PROCESS ECO NOTE 4: With the clients parts kit they will provide ESD bags that they want us to use for the boards to be individually packed and shipped in |  |  | 10/9 - BOT 10/10 - TOP 10/10 - AOI | 40 | 150 | 1B 1T | 1 | 50 | UPS GRND | Ultra Motion LLC |  | 9/24 - USE CUSTOMER SUPPLIED ESD BAGS | DOC REL 9/20 | 9/25 | 3062.5 | BOT 1ST Pat has a special note : with the customers parts are ESD bags that they want us to use when packaging and shipping back the populated boards. | 2024-10-14 | 2 |  |  | 2
2024-10-14 |  | 9/30 - KIT CLEAR | [5 empty] | 128452 NEW | 5 | 10/14 10D | X |  | T/H ONLY CLASS 3 "KA2" AFTER WASH "LED1-6" MOUNT FLUSH |  |  | FSU | 0 | 0 |  | 133 | 665 | FEDEX GRD | Bruker Nano, RMR (FKA RAVE LLC) |  |  | DOC REL 9/26 | 9/30 | 4322.5 | [5 empty] | 1
2024-10-10 |  | 9/30 - SHORT PCB WITH NO ETA 10/8 - PCB DUE 10/7 - KIT CLEAR |  |  | 2 |  |  | 127976 NEW | 2 | 10/10 3D | NL | X | *** 3 DAY TURN *** DEPANEL |  |  | 10/8 - TOP 7:30 10/8 - AOI 9:00 | 48 | 773 | 1T | 1 | 2 | FEDEX P | MIT Lincoln Laboratory |  |  | DOC REL 9/24 | 9/30 | 4197.92 | TOP ONLY | 2024-10-10 | 1 |  | 1.5 | 2
2024-10-10 |  | 10/7 - MAY CLEAR DATE 10/7 - KIT CLEAR |  |  |  |  | 1 | 128490 NEW | 15 | 10/10 3D | NL | X | *** 3 DAY TURN *** DoD (CUI) DO-A7 RATING *** NO ADDITIONAL VENDOR MARKS ALLOWED *** COMPLETE REMOVAL OF FLUX RESIDUE REQUIRED *** |  |  | 10/7 - BOT 11:00 10/7 - PAUSE 12:00 10/8 - BOT 6:00 10/8 - TOP 9:00 10/8 - AOI 12:00 | 155 | 829 | 2B 2T | 9 | 135 | FEDEX P | John Hopkins University Applied Physics Lab |  |  | DOC REL 9/26 | 10/4 | 18407.25 | bot 1st | 2024-10-10 | 2 |  | 7 | 5
2024-10-10 |  | 10/3 - PCB DUE 9/26 - KIT CLEAR |  |  | 1 |  |  | 126847 NEW | 25 | 10/10 10D | NL | X | "SP1, D5" AFTER WASH DEPANEL |  |  | 10/7 - BOT 10:30 10/7 - TOP 12:00 10/8 - AOI 8:00 | 78 | 192 | 1B 2T | 22 | 550 | FEDEX P | Applied Radar, Inc. |  |  | DOC REL 9/23 | 9/25 | 3385 | BOT 1ST | 2024-10-10 | 2 | 2024-10-08 | 6 | 3
2024-10-10 |  | 9/19 - RUN BOT COMP (TAD) 9/24 - BOT COMPLETE 10/3 - KIT CLEAR |  |  | 1 |  |  | 126794-2nd ROWC 1st Article | 57 | 10/10 5D | NL | ROWC | EXTRA TIME NEEDED TO RUN THIS JOB - RUN BOT SIDE AHEAD IF POSSIBLE 2ND ARTICLE HAS 36 BOM CHANGES - SEE EMAIL/BOM COMPARE "L49, 50, 51" AFTER WASH DEPANEL |  |  | 9/21 - BOT 9/24 - PAUSE 8:30 10/3 - TOP 3:30 10/7 - AOI 10:30 | 73 | 2240 | 2B 2T | 10 | 570 | FEDEX GRD | Alpheus Medical, Inc. |  | 9/24 - BOT COMP (10+ HRS) 10/4 - ETA TOP TIME = 15.5 HRS | DOC REL 9/16 | 9/19 | 27834.24 | BOT 1ST | 2024-10-10 | 2 | 2024-09-27 | 28 | 3
|  | 10/3 - PCB DUE 10/1 - KIT CLEAR 10/8 - ITEM 11, QTY 2 FELL OFF IN REFLOW |  |  |  | 1 |  | 128480 NEW | 125 | 10/8 5D | NL | X | XRAY ^ SAVE IMAGES PER ECO DEPANEL |  |  | 10/4 - BOT 8:00 10/4 - TOP 10/7 - AOI 11:30 | 35 | 84 | 1B 1T | 0 | 0 | FEDEX GRD | Medtronic Inc. |  |  | DOC REL 9/26 | 9/30 | 5096.25 | BOT 1ST | 2024-10-08 | 2 | 2024-10-04 | 9.5
2024-10-08 |  | 9/10 - SHORT PCB WITH NO ETA 9/25 - PCB DUE 9/24 - KIT CLEAR |  |  | 1 |  |  | 126809 NEW | 2 | 10/8 10D | NL | X | "C10" Do not populate C10, package separately and send w/ assembled boards. Note: C10 has the same P/N as C9 |  |  | 10/2 - TOP 8:30 10/2 - BOT 10/2 - AOI 2:30 | 77 | 854 | 2B 1T | 45 | 90 | FEDEX P | Advanced Acoustic Concepts, LLC |  |  | DOC REL 9/9 | 9/10 | 5637.5 | TOP 1ST | 2024-10-08 | 2 | 2024-10-02 | 6
2024-10-08 |  | 9/17 - AWT PART CONF: #1 (C6...) & #15 (D6, D7) 9/17 - KIT CLEAR |  |  | 1 |  |  | 128162 RONC 116612 | 54 | 10/8 15D | NL | RONC | "J3, J4" REQUIRE SOLDER ON THRU HOLE MOUNTING PADS PER ECO |  |  | 10/1 - BOT 6:00 10/1 - TOP 9:00 10/2 - AOI 9:00 | 66 | 370 | 1B 1T | 2 | 108 | FEDEX P | Protocol Insight, LLC |  |  | DOC REL 9/9 | 9/17 | 6376 | BOT 1ST | 2024-10-08 | 2 | 2024-10-01 | 13.5
2024-10-08 |  | 9/24 - SHORT MANY ¦ EXPECTED CLEAR DATE 9/24 - KIT CLEAR |  |  |  |  | 1 | 127951 NEW | 3 | 10/8 10D | NL | X | CLASS 3 "SW1, SW6, IC57, IC671, IC672" AFTER WASH TRIM LEADS TO 1.5MM MAX PER CLASS 3 "CN2, CN3" PLACE PER EMAIL (NATION) |  |  | 9/27 - BOT 5:00 9/27 - TOP 8:30 9/27 - AOI 11:00 | 151 | 1904 | 1B 3T | 41 | 123 | FEDEX P | Toshiba International Corp. |  | 3-machine | DOC REL 9/17 | 9/23 | 10752.5 | BOT 1ST | 2024-10-08 | 5 | 2024-09-26 | 6
2024-10-08 |  | 10/2 - PCB DUE ¦ SHORT #59 (U22..) WITH NO ETA 10/1 - KIT CLEAR |  |  | 1 |  |  | 128611 NEW | 5 | 10/8 5D | NL | X | "L5" AFTER WASH "T1, T2" DO NOT TRIM LEADS "U56" HEATSINK & HARDWARE REQ "L20" INDUCTOR HARDWARE REQ DEPANEL BARCODE LABEL REQ *** EXTRA PACKING AND USE MULTIPLE BOXES TO PREVENT DAMAGE |  |  | 10/3 - BOT 12:30 10/3 - TOP 1:30 10/3 - AOI 4:00 | 110 | 484 | 1B 2T | 50 | 250 | FEDEX P | Bausch & Lomb |  |  | DOC REL 9/26 | 9/30 | 5467.8 | BOT 1ST | 2024-10-08 | 2 | 2024-10-03 | 3.5
2024-10-08 |  | 10/1 - PCB DUE 10/1 - KIT CLEAR |  |  | 1 |  |  | 128344 NEW | 15 | 10/8 5D | NL | X | "SW1, SW2, U38, U50" AFTER WASH |  |  | 10/2 - BOT 2:00 10/2 - TOP 7:00 10/2 - AOI 1:30 | 80 | 339 | 1B 1T | 27 | 405 | FEDEX P | IEQmax |  |  | DOC REL 9/26 | 9/30 | 6502.3 | BOT 1ST | 2024-10-08 | 2 | 2024-10-02 | 8
2024-10-08 |  | 9/24 - KIT CLEAR |  |  |  | 1 |  | 128159 RONC 116452 | 15 | 10/8 10D | NL | RONC | DEPANEL 9/24 - CHANGED ITEM #6 TO SMT |  |  | 10/1 - BOT 8:00 10/1 - TOP 10:30 10/1 - AOI 2:00 | 6 | 71 | 1B 1T | 55 | 825 | FEDEX P | IonQ, Inc. |  |  | DOC REL 9/20 | 9/24 | 5490 | BOT 1ST | 2024-10-08 | 2 | 2024-10-01 | 6
2024-10-07 |  | 9/16 - PCB DUE 9/16 - KIT CLEAR |  |  |  | 1 |  | 126961 NEW | 1750 | 10/7 15D | NL | X | *** MULTIPLE CUT STRIPS, WILL TAKE LONGER TO RUN - START EARLY *** LEAD PROCESS DEPANEL |  |  | 9/18 - BOT 11:00 9/24 - PAUSE 10:00 9/24 - BOT 1:00 9/24 - PAUSE 2:00 9/25 - BOT 11:00 9/25 - TOP 1:00 9/27 - PAUSE 8:00 9/28 - TOP 8:00 9/30 - AOI 2:00 | 38 | 77 | 2B 1T | 0 | 0 | FEDEX P | Kustom Komponents |  | 9/25 - 26 HOURS TO COMP BOT 9/30 - 19 HOURS TO COMP TOP | DOC REL 9/9 | 9/16 | 22305 | BOT 1ST | 2024-10-07 | 2 | 2024-09-23 | 45
2024-10-07 |  | 9/3 - PCB DUE 9/11 - PCB DUE & SHRT 4 PCS OF U11 9/20 - PCB'S DUE & "U11" IS BTD 9/30 - KIT CLEAR |  |  |  | 1 |  | 127298-2BAL NEW | 39 | 10/7 5D | NL | X | "U11" - HANDLE W/ CARE!!! - DO NOT LOSE OR DAMAGE PARTS "BT1" LEAVE PASTE ON CENTER PADS "U22, SW2" AFTER WASH DEPANEL DO NOT SHIP EXCESS MATL |  |  | 10/1 - BOT 2:00 10/2 - TOP 1:00 10/3 - AOI 11:00 | 82 | 275 | 1B 2T | 1 | 39 | FEDEX P | Nextern, Inc. |  |  | DOC REL 8/12 | 8/20 | 2351.7 | BOT 1ST | 2024-10-07 | 2 | 2024-10-01 | 9
2024-10-07 |  | 9/23 - PCB & SHORTAGES DUE 9/24 - KIT CLEAR 9/24 - DAY 1 (PHUONG) |  |  |  |  | 1 | 128433 NEW | 6 | 10/7 10D | NL | X | "J1" LEAVE PASTE ON CENTER PAD "S1-3, BZ1, J43, U45, U22" AFTER WASH DEPANEL |  |  | 9/30 - BOT 8:00 9/30 - TOP 10:30 9/30 - pause 12:00 10/1 - TOP 5:00 10/1 - AOI 8:00 | 154 | 525 | 1B 3T | 39 | 234 | FEDEX P | MPR Associates Inc |  | 3-machine | DOC REL 9/17 | 9/20 | 8086.4 | BOT 1ST | 2024-10-07 | 5 | 2024-09-30 | 7
2024-10-07 |  | 10/2 - PCB DUE OR SOONER 10/2 - KIT COMPLETED |  |  |  |  | 1 | 128136 NEW | 25 | 10/7 3D | NL | X | *** 3 DAY TURN *** CLASS 3 "K1, K2, K3, RL4, U3, L2" AFTER WASH XRAY & SAVE IMAGES ALL T/H MOUNT FLUSH TO PCB LIST S/Ns ON THE CofC |  |  | 10/3 - BOT 9:00 10/3 - TOP 1:30 10/4 - AOI 11:30 | 154 | 693 | 2B 2T | 12 | 300 | FEDEX P | Anduril |  |  | DOC REL 9/17 | 9/20 | 17275 | BOT 1ST | 2024-10-07 | 2 | 2024-10-03 | 11
2024-10-07 |  | 9/20 - SMT CLEAR 9/23 - KIT CLEAR |  |  |  |  | 1 | 128183 NEW | 20 | 10/7 10D | NL | X | DNI MP1 - MP4 "L3" AFTER WASH SOLDER BUILD UP ON GND PADS NOT TO EXCEED 0.006" IN HEIGHT ***TRIM LEADS TO 0.140" MAX "J33" JUMPER AND "J33" FUSE INSTALL PRIOR TO SHIPPING SCREW TERMINALS MUST BE SHIPPED W/ CAGES FULLY OPENED |  |  | 9/25 - TOP 1:00 9/25 - PAUSE 2:30 9/27 - TOP 11:30 9/27 - AOI 2:30 | 65 | 229 | 1T | 44 | 880 | FEDEX P | Rheem Manufacturing Company |  |  | DOC REL 9/18 | 9/20 | 3953 | TOP ONLY | 2024-10-07 | 1 | 2024-09-26 | 4.5
2024-10-04 |  | 9/24 - PCB DUE 9/30 - KIT CLEAR | [5 empty] | 121246 NEW | 80 | 10/7 5D | X |  | T/H ONLY DEPANEL AS9100 FAIR REQ MAKE SURE BOARDS ARE CLEAN - NO DUST ETC SHIPPING INSPECTION - MAKE SURE HEADER PINS ARE NOT BENT PRIOR TO SHIPPING EXTRA CARE WHEN PACKAGING - PREVENT DAMAGE |  |  | BACK | 0 | 0 |  | 4 | 320 | FEDEX P | Aptiv Services 3 US, LLC |  |  | DOC REL 8/15 | 9/20 | 2640 | T/H ONLY
2024-10-04 |  | 9/24 - PCB DUE 9/20 - KIT CLEAR |  |  |  |  | 1 | 128277 NEW | 750 | 10/4 10D | NL | X | LEAD-FREE, NO CLEAN "U1" SEE ECO DEPANEL |  |  | 9/25 - BOT 11:00 9/25 - PAUSE 1:00 9/26 - BOT 6:00 9/26 - PAUSE 7:00 9/26 - TOP 10:00 9/26 - AOI 2:00 | 6 | 14 | 1B 1T | 0 | 0 | UPS RED | Reprieve Cardiovascular, Inc. |  | 9/25 - AWT FIXTURE | DOC REL 9/12 | 9/16 | 6925 | BOT 1ST | 2024-10-04 | 2 | 2024-09-25 | 7
2024-10-03 |  | 9/20 - PCB DUE 9/23 - PCB DUE 9/20 - KIT CLEAR |  |  |  | 1 |  | 128290 RONC 104778 | 500 | 10/4 10D | NL | RONC | DEPANEL |  |  | 9/24 - TOP 12:00 9/24 - PAUSE 1:00 9/25 - TOP 8:00 9/25 - AOI 11:00 | 17 | 21 | 2T | 3 | 1500 | FEDEX P | Hose Monster |  |  | DOC REL 9/9 | 9/12 | 8490 | TOP ONLY | 2024-10-04 | 1 | 2024-09-25 | 4
2024-10-03 |  | 8/30 - PCB DUE DATE 9/6 - KIT CLEAR |  |  | 2 |  |  | 127900 RONC 126262 | 1000 | 10/4 20D | NL | RONC | NO ECO |  |  | 9/9 - BOT 10:00 9/10 - AOI 11:00 | 16 | 31 | 2B | 5 | 5000 | FEDEX GRD | Respond Systems, Inc. |  |  | DOC REL 8/23 | 8/26 | 10890 | BOT ONLY | 2024-10-04 | 1 | 2024-09-09 | 9
2024-10-03 |  | 9/20 - KIT CLEAR |  |  | 1 |  |  | 127912 NEW | 40 | 10/3 9D | NL | X | *** (CUI) *** 9/17 - J3A, J3B, J3C (PN R161419020) – IS NOW DNI AND U16 (PN LT5570IDD#TRPBF) – Use part LTC5582IDD#TRPBF instead DEPANEL AND SAND |  |  | 9/25 - TOP 6:00 9/25 - AOI 12:00 | 36 | 158 | 1T | 18 | 720 | FEDEX P | Jefferson Labs |  |  | DOC REL 9/12 | 9/20 | 2753.6 | top only | 2024-10-03 | 1 | 2024-09-25 | 6
2024-10-02 |  | 9/24 - PCB DUE 9/25 - KIT CLEAR |  |  | 1 |  |  | 127440-1ST NEW | 60 | 10/2 5D | NL | X | SHIP BY 9/30 (PHUONG) TRUE NO CLEAN ALL COMPONENTS FLUSH TO BOARD DEPANEL |  |  | 9/26 - BOT 12:00 9/26 - PAUSE 2:30 9/30 - BOT 6:00 9/30 - TOP 7:00 9/30 - AOI 10:00 | 40 | 69 | 1B 2T | 0 | 0 | FEDEX P | United Mesh Solutions, LLC |  | 9/30 - U6 TILTED | DOC REL 9/11 | 9/20 | 2837 | BOT 1ST | 2024-10-02 | 2 | 2024-09-27 | 6.5
2024-10-02 |  | 9/6 - SHORT #32 (U7..), #71 (H5) & #89 (R8..) 9/11 - EXPECT CLEAR DATE 9/11 - KIT CLEAR |  |  | 1 |  |  | 127725 RONC 119747 | 200 | 10/2 15D | NL | RONC | NO CLEAN PROCESS "D1" INSTALL PER ECO "J3" READ ECO PRIOR TO INSTALLATION |  |  | 9/19 - TOP 9:30 9/19 - PAUSE 12:00 9/20 - TOP 10:30 9/21 - AOI | 101 | 173 | 2T | 0 | 0 | FEDEX 2DAY | Marshall Radio Telemetry Inc |  | 9/19 - DREMIL PCB BEFORE SMT ASSY REQUIRED 10/2 - J3 RWK REQUIRED AFTER DEPANEL | DOC REL 8/23 | 9/6 | 6612 | TOP ONLY | 2024-10-02 | 2 | 2024-09-18
2024-10-02 |  | 9/26 - SHORT PCB WITH ETA 9/30 9/30 - KIT CLEAR |  |  |  |  | 1 | 128662 NEW | 10 | 10/2 2D | NL | X | *** 2 DAY TURN *** DEPANEL & SAND |  |  | 9/30 - TOP 12:00 9/30 - AOI 2:30 | 22 | 66 | 1T | 9 | 90 | FEDEX P | Ergotron, Inc. |  |  | DOC REL 9/23 | 9/26 | 7116 | TOP ONLY | 2024-10-02 | 1 |  | 2.5
2024-10-02 |  | 9/23 - PCB DUE 9/20 - KIT CLEAR 9/26 - DAY 1 (ANNE) |  |  |  | 1 |  | 126660 NEW | 60 | 10/2 9/27 5D | NL | X | rtv LOCTITE SI 5699 REQ SPECIFIC ECO INSTRUCTIONS FOR RTV ON "C2, C3, L1, L2, L3, R8" TRIM LEADS TO 0.140" MAX READ ECO NOTE #1 FOR DEPANELING SCREW TERMINALS MUST SHIP W/ ALL CAGES FULLY OPEN LABEL EACH BOX WITH DATE CODE & QTY IN BOX ON TOP AND SIDE PANEL |  |  | 9/23 - TOP 10:00 9/24 - AOI 12:00 | 80 | 288 | 2T | 54 | 3240 | FEDEX P | Industrialex Manufacturing |  | 9/23 - skip #40 (U3, U5) | DOC REL 9/17 | 9/18 | 8341.6 | BOT 1ST | 2024-09-30 | 2 | 2024-09-23 | 8
2024-10-01 |  | 9/26 - PCB DUE 9/27 - PCB DUE 9/30 - KIT CLEAR |  |  | 1 |  |  | 128663 NEW | 30 | 10/1 1D | NL | X | *** 1 DAY TURN *** DEPANEL & SAND |  |  | 9/30 - BOT 10:00 9/30 - TOP 12:00 9/30 - AOI 2:30 | 64 | 168 | 1B 1T | 2 | 60 | FEDEX P | Ergotron, Inc. |  |  | DOC REL 9/23 | 9/24 | 23794 | BOT 1ST | 2024-10-01 | 2 |  | 4.5
2024-10-01 |  | 9/30 - PCB DUE 09/26 - KIT CLEAR |  |  |  | 1 |  | 128613 NEW | 5 | 10/1 3D | NL | X | *** 3 DAY TURN *** ok to skip & ship with boards #17 (TP1...) "U1, U10, K1 x10" AFTER WASH DEPANEL SHIP #17 (TP1...) WITH BOARDS |  |  | 9/27 - BOT 8:00 9/27 - TOP 10:00 9/27 - AOI 12:00 | 18 | 302 | 1B 1T | 220 | 1100 | UPS RED | Hermeus |  |  | DOC REL 9/23 | 9/24 | 9395.85 | BOT 1ST | 2024-10-01 | 2 | 2024-09-27 | 4
2024-09-30 |  | 9/27 - EXPECT CLEAR BY DATE 9/25 - KIT CLEAR |  |  |  |  | 3 | 128594 NEW | 5 | 9/30 3D | NL | X | *** 3 DAY TURN *** DEPANEL SHIP #18 (TP1...) WITH BOARDS |  |  | 9/26 - TOP 7:00 9/26 - BOT 8:30 9/26 - AOI 10:00 | 17 | 515 | 1B 1T | 113 | 565 | UPS RED | Hermeus |  |  | DOC REL 9/20 | 9/23 | 7109 | TOP 1ST | 2024-09-30 | 2 |  | 3
2024-09-30 |  | 9/23 - KIT CLEAR |  |  |  |  | 1 | 126574 NEW | 10 | 9/30 5D | NL | X | *** CANNOT BE LATE *** "L1" AFTER WASH SOLDER BUILD UP ON GND PADS NOT TO EXCEED 0.006" IN HEIGHT ***TRIM LEADS TO 0.140" MAX INSTALL FUSES PRIOR TO SHIPPING SCREW TERMINALS MUST BE SHIPPING W/ CAGES FULLY OPENED |  |  | 9/24 - BOT 1:00 9/25 - AOI 8:30 | 110 | 363 | 2B | 64 | 640 | FEDEX P | Rheem Manufacturing Company |  |  | DOC REL 9/18 | 9/23 | 7322.5 | BOT ONLY | 2024-09-30 | 1 | 2024-09-25 | 4
2024-09-27 |  | 9/5 - KIT CLEAR |  |  | 1 |  |  | 127711 RONC 111910 | 15 | 10/3 20D | NL | RONC | LEAD PROCESS TP701- TP704, TP706- TP716 SEE ECO FOR INSTALLATION *** "J701" DO NOT CUT PINS/TRIM LEADS *** |  |  | 9/18 - BOT 6:00 9/18 - TOP 8:00 9/18 - AOI 12:00 | 93 | 353 | 1B 2T | 29 | 435 | FEDEX GRD | Case Western APT |  |  | DOC REL 8/28 | 9/5 | 2658.84 | BOT 1ST | 2024-10-03 | 2 | 2024-09-18 | 6
2024-09-27 |  | 9/16 - SHORT PCB & PARTS 9/20 - KIT CLEAR | [5 empty] | 128465 RWK | 7 | 9/27 5D | - | X | SEE PDF Add SH1, SH2, SH3, J71, J72 (qty.5) Remove and rotate 180 deg - U22, U39.1-U39.4, U39.9, U39.10-U39.12 (qty.9) |  |  | BACK | - | - | - | 3 | 21 | FEDEX P | John Hopkins |  |  |  | 9/18 | 6860 |  |  |  |  | 16.5
2024-09-26 |  | 9/25 - PCB & SHORTAGES DUE 9/26 - KIT CLEAR |  |  | 1 |  |  | 128696 NEW | 10 | 9/27 1D | NL | X | *** 1 DAY TURN *** SPLIT QTY SHIPMENT - QTY 8 W/ CONN MATES & FUSES TO 1181 TRAP RD / QTY 2 TO 1152 PARK AVE (SEE EMAIL) |  |  | 9/26 - TOP 10:30 9/26 - AOI 12:00 | 17 | 36 | 1T | 23 | 230 | FEDEX P | Ergotron, Inc. |  |  | DOC REL 9/23 | 9/24 | 11750 | top only | 2024-09-27 | 1 | 2024-09-26 | 1.5
2024-09-26 |  | 9/19 - PCB DUE 9/16 - KIT CLEAR |  |  |  |  | 3 | 128122 RONC 123920 | 5 | 9/30 10D | NL | X | NO ECO |  |  | 9/23 - BOT 10:00 9/23 - TOP 9/23 - AOI 2:30 | 36 | 101 | 1B 1T | 8 | 40 | UPS 2ND DAY | Rocky Research |  |  | DOC REL 9/9 | 9/10 | 1777 | BOT 1ST | 2024-09-30 | 2 | 2024-09-24 | 4.5
2024-09-26 |  | 8/19 - short #20 (c122), #42 (u22..) and #56 (j2) WITH NO ETA 9/11 - NOT RELEASED 9/19 - KIT CLEAR |  |  |  |  | 1 | 126752-2 BAL NEW | 114 | 9/26 5D | NL | X | "L17, 18, 19, 22" AFTER WASH DEPANEL |  |  | 9/20 - BOT 8:30 9/21 - TOP 7:00 9/21 - AOI | 91 | 312 | 2B 2T | 0 | 0 | FEDEX P | Summit Santa Clara-Streamline Circuits |  | VERIFY SIDE TO RUN | DOC REL 8/12 | 8/19 | 8133.9 | BOT 1ST | 2024-09-26 | 2 | 2024-09-20
2024-09-25 |  | 9/23 - PCB DUE 9/19 - KIT CLEAR |  |  |  |  | 1 | 127438-1ST NEW | 20 | 9/26 5D | NL | X | TRUE NO CLEAN XRAY & SAVE IMAGES ALL COMPONENTS FLUSH TO BOARD DEPANEL |  |  | 9/23 - BOT 9/23 - TOP 9/23 - AOI | 34 | 59 | 1B 1T | 0 | 0 | FEDEX P | United Mesh Solutions, LLC |  |  | DOC REL 9/11 | 9/16 | 1482 | BOT 1ST | 2024-09-26 | 2 | 2024-09-23
2024-09-25 |  | 9/4 - KIT CLEAR |  |  |  |  | 1 | 127831 NEW | 4 | 9/25 15D | NL | X | Please tag the boards with BTD or DNI’ed parts and note these on the paperwork. |  |  | 9/19 - BOT 12:00 9/20 - TOP 9/20 - AOI 12:00 | 189 | 620 | 1B 3T | 50 | 200 | UPS 3DAY | Coastal Designs, LLC |  |  | DOC REL 8/26 | 9/4 | 9675.2 | bot 1st | 2024-09-25 | 5 | 2024-09-19 | 8
2024-09-25 |  | 9/18 - PCB DUE THN SMT CLEAR 9/18 - KIT CLEAR |  |  | 3 |  |  | 128251 NEW | 3 | 9/25 5D | NL | X | HEAVY THRU HOLE |  |  | 9/19 - BOT 8:00 9/19 - TOP 9/19 - AOI 11:30 | 2 | 160 | 1B 1T | 405 | 1215 | UPS RED | Hermeus |  |  | DOC REL 9/12 | 9/16 | 8776.25 | BOT 1ST | 2024-09-25 | 2 | 2024-09-19 | 3.5
2024-09-24 |  | 9/23 - PCB DUE 9/19 - KIT CLEAR |  |  |  |  | 2 | 127650 NEW | 3 | 9/26 5D | NL | X | CLASS 3 DEPANEL & SAND |  |  | 9/23 - AOI | 17 | 85 | 1T | 86 | 258 | UPS RED | ECLARO International Inc |  |  | DOC REL 9/11 | 9/12 | 3592.5 | TOP ONLY | 2024-09-26 | 1 | 2024-09-23
2024-09-24 |  | 9/17 - KIT CLEAR |  |  | 1 |  |  | 128235 RONC 119272 | 20 | 9/24 5D | NL | RONC | "H1 H2 H3 H4 " Per Customer, these parts are solder on nuts. Customer cannot if the paste added to the paste file. Please do what is needed at your shop to solder these standoffs. Either modify the paste file or hand solder. “The nuts should be placed on the "TOP" side of the board (side with the majority of the components.” |  |  | 9/19 - BOT 12:30 9/19 - TOP 2:30 9/20 - AOI 12:00 | 75 | 207 | 1B 1T | 3 | 60 | FEDEX GRD | H3D, Inc. |  |  | DOC REL 9/9 | 9/17 | 1798.8 | BOT 1ST | 2024-09-24 | 2 | 2024-09-20 | 7.5
2024-09-24 |  | 8/29 - AWT PART CONF THEN CLEAR 9/3 - KIT CLEAR |  |  |  |  | 1 | 127832 NEW | 4 | 9/24 15D | NL | X | Please tag the boards with BTD or DNI’ed parts and note these on the paperwork. |  |  | 9/9 - BOT 1:00 9/10 - TOP 9/10 - AOI 9:30 | 166 | 486 | 1B 2T | 33 | 132 | UPS 3DAY | Coastal Designs, LLC |  |  | DOC REL 8/26 | 8/29 | 4244 | BOT 1ST | 2024-09-24 | 2 | 2024-09-10 | 5
2024-09-23 |  | 9/23 - PCB DUE ¦ NO ETA FOR #3(U1) 9/18 - #3 (U1) DUE DATE 9/16 - KIT CLEAR |  |  |  |  | 1 | 127439-1st NEW | 20 | 9/23 5D | NL | X | XRAY & SAVE IMAGES ALL COMPONENTS FLUSH TO BOARD DEPANEL |  |  | 9/18 - BOT 11:00 9/18 - TOP 9/18 - AOI 2:30 | 6 | 6 | 1B 1T | 0 | 0 | FEDEX P | United Mesh Solutions, LLC |  |  | DOC REL 9/11 | 9/12 | 1810 | BOT 1ST | 2024-09-23 | 2 | 2024-09-18 | 3.5
2024-09-23 |  | 9/13 - SMT CLEAR 9/16 - KIT CLEAR |  |  | 1 |  |  | 128164 NEW | 1 | 9/23 5D | NL | X | *** DO:A7 RATING *** LEAD PROCESS PER ECO - All repairs require customer approval in writing -Q42 |  |  | 9/18 - BOT 11:00 9/18 - TOP 1:30 9/19 - AOI 7:00 | 46 | 933 | 1B 1T | 25 | 25 | FEDEX P | Southwest Research Institute |  | 9/19 - TOUCH UP OK W/O NOTIFY CUSTOMER (TAD) | DOC REL 9/9 | 9/16 | 3455.95 | TOP 1ST? BOT 1ST | 2024-09-23 | 2 | 2024-09-19 | 4.5
2024-09-23 |  | 8/28 - AWT PART CONF #63 (U128) & #165 (Q1...) 8/29 - KIT CLEAR |  |  | 1 |  |  | 127830 NEW | 4 | 9/23 15D | NL | X | Please tag the boards with BTD or DNI’ed parts and note these on the paperwork |  |  | 9/9 - BOT 6:00 9/9 - TOP 9/9 - AOI 10:30 | 150 | 478 | 1B 2T | 38 | 152 | UPS 3DAY | Coastal Designs, LLC |  |  | DOC REL 8/23 | 8/28 | 7830 | BOT 1ST | 2024-09-23 | 2 | 2024-09-09 | 4.5
2024-09-23 |  | 9/18 - PCB DUE ¦ AWT PART CONF #71 (R48...) 9/18 - KIT CLEAR |  |  | 2 |  |  | 128379 NEW | 4 | 9/23 3D | NL | X | *** 3 DAY TURN *** "LS1" AFTER WASH *** TRIM LEADS 0.5MM MIN TO 1MM MAX *** DEPANEL |  |  | 9/19 - TOP 6:30 9/19 - AOI 10:30 | 77 | 284 | 2T | 99 | 396 | UPS RED | Veranex |  |  | DOC REL 9/16 | 9/17 | 5696 | TOP ONLY | 2024-09-23 | 1 | 2024-09-19 | 4
2024-09-23 |  | 9/6 - PCB DUE 9/11 - KIT CLEAR |  |  | 1 |  |  | 127654 NEW | 25 | 9/23 9/25 10D | NL | X | DEPANEL |  |  | 9/16 - BOT 10:30 9/16 - TOP 1:00 9/17 - AOI 10:00 | 105 | 496 | 1B 2T | 30 | 750 | FEDEX P | Beckman Coulter |  |  | DOC REL 8/12 | 8/23 | 6028.75 | BOT 1ST | 2024-09-23 | 2 | 2024-09-13 | 7.5
2024-09-20 |  | 9/9 - PCB DUE 9/6 - KIT CLEAR |  |  |  | 1 |  | 127989 RONC 126442 | 200 | 9/20 10D | NL | RONC | DEPANEL |  |  | 9/12 - TOP 9:00 9/12 - PAUSE 10:00 9/13 - TOP 8:00 9/16 - AOI 12:00 | 3 | 6 | 1T | 0 | 0 | UPS GRD | Sick, Inc. |  |  | DOC REL 8/26 | 9/3 | 3180 | TOP ONLY | 2024-09-20 | 8 | 2024-09-12 | 15
2024-09-20 |  | 9/3 - PCB DUE 9/11 - PCB DUE & SHRT 4 PCS OF U11 9/13 - KIT CLEAR |  |  |  | 1 |  | 127298-1PAR NEW | 26 | 9/20 5D | NL | X | "U11" - HANDLE W/ CARE!!! - DO NOT LOSE OR DAMAGE PARTS "BT1" LEAVE PASTE ON CENTER PADS "U22, SW2" AFTER WASH DEPANEL |  |  | 9/16 - BOT 11:30 9/17 - TOP 8:30 9/18 - AOI 11:00 | 82 | 275 | 1B 2T | 1 | 26 | FEDEX P | Nextern, Inc. |  |  | DOC REL 8/12 | 8/20 | 3997.8 | BOT 1ST | 2024-09-20 | 2 | 2024-09-16 | 11.5
2024-09-19 |  | 9/17 - PCB DUE 9/18 - KIT CLEAR |  |  |  |  | 1 | 128025 NEW | 5 | 9/19 1D | NL | X | *** 1 DAY TURN *** BOM/GERBERS/XY CHANGED - PLEASE MAKE SURE CORRECT DOCS ARE USED AND ALL CHANGES ARE CAPTURED LEAD NO CLEAN PROCESS "U801" MOISTURE SENSITIVE - READ ECO |  |  | 9/19 - BOT 6:00 9/19 - TOP 9:00 9/19 - AOI 11:30 | 107 | 434 | 1B 2T | 0 | 0 | FEDEX P | Ocean Aero, Inc. |  |  | DOC REL 9/6 | 9/12 | 10640 | BOT 1ST | 2024-09-19 | 2 | 2024-09-19 | 5.5
2024-09-19 |  | 9/17 - PCB DUE 9/16 - KIT CLEAR |  |  | 1 |  |  | 128084 NEW | 40 | 9/19 3D | NL | X | *** 3 DAY TURN *** RTV REQ C58 & C59 AFTER SOLDERING - AROUND EDGES ONLY AND DO NOT GET RTV ON SURROUNDING PARTS "THERE ARE .4MM PITCH DEVICES THAT MAY REQUIRE A SPECIAL PASTE STENCIL" (ECO) |  |  | 9/17 - BOT 8:30 9/17 - TOP 12:00 9/17 - AOI 5:30 | 84 | 391 | 1B 1T | 1 | 40 | FEDEX P | L3 |  |  | DOC REL 9/6 | 9/10 | 11652 | BOT 1ST | 2024-09-19 | 2 | 2024-09-17 | 9
2024-09-19 |  | 9/5 - KIT CLEAR |  |  | 2 |  |  | 127216 NEW | 25 | 9/19 10D | NL | X | XRAY & SAVE "M1-4" SWAGING REQ DEPANEL |  |  | 9/12 - BOT 10:30 9/12 - TOP 12:00 9/13 - AOI 8:00 | 103 | 327 | 1B 2T | 10 | 250 | UPS RED | Blur Product Development |  |  | DOC REL 9/4 | 9/5 | 6577 | BOT 1ST | 2024-09-19 | 2 | 2024-09-11 | 5.5
2024-09-19 |  | 9/16 - PCB DUE (SHORT 1 PCB) 9/16 - KIT CLEAR |  |  |  |  | 1 | 128129 NEW | 10 | 9/19 3D | NL | X | *** SAC305 SOLDER ONLY *** "U13, SW1" MOISTURE SENSITIVE/AFTER WASH |  |  | 9/18 - BOT 6:00 9/18 - TOP 8:30 9/18 - AOI 12:30 | 91 | 748 | 1B 1T | 28 | 280 | FEDEX P | Anduril |  |  | DOC REL 9/5 | 9/10 | 6976 | bot 1st | 2024-09-19 | 2 | 2024-09-17 | 6.5
2024-09-19 |  | 9/11 - PCB DUE THAN CLEAR FOR 51 ¦ RUN ALL BOARDS IN SMT 9/12 - SMT CLEAR TO RUN ALL ¦ KIT CLEARED FOR 51 OF 80 BOARDS |  |  | 2 |  |  | 128090-1 PAR RONC 126369 | 51 | 9/19 5D | NL | RONC | J7, J8, J2, J1, J3 ORIENTATION (ECO) CofC REQUIRES S/N FOR SMT, ASSEMBLE ALL BOARDS THAN PARTIAL SHIPMENT 51 OF 80 UNTIL BAL OF #19 (J3) ARRIVES |  |  | 9/13 - BOT 7:00 9/13 - PAUSE 1:00 9/16 - TOP 8:30 9/16 - AOI 10:30 | 32 | 131 | 1B 1T | 7 | 357 | UPS GRD | Churchill Navigation dba Shotover Systems, Inc. |  |  | DOC REL 9/4 | 9/5 | 2027.25 | BOT 1ST | 2024-09-19 | 2 | 2024-09-12 | 8
cancelled | [7 empty] | 121592 NEW | 40 | 3 | NL |  | Cancelled - Transfer to B124008. Same BOM/GERBR/XY |  |  | FSU | 227 | 987 | 3B 2T | 0 | 0 | UPS RED | ICUMedical |  |  | DOC REL 2/5 |  | 30920 | TEMPURATURE QUESTIONS TOP 1ST SOME SIZE 201
cancelled | [7 empty] | 123104-2 | 31 | 15 | X |  | 2nd Article Cancelled 4-25-2024 |  |  | FSU |  |  |  |  | 0 | FEDEX P | Farsounder Inc |  |  | NO DOC. |  | 7630.85
cancelled | [7 empty] | 124748 | 200 | 10 | X |  | Cancelled 04-01-2024 |  |  | FSU |  |  |  |  | 0 | FEDEX P | Open Source Instruments, Inc. |  |  | NO DOC. |  | 1878
cancelled | [7 empty] | 127034-2 | 6 | 5 | - |  | 2nd Article Cancelled 9-16-2024 |  |  | FSU |  |  |  |  | 0 | FEDEX P | MPR Associates Inc |  |  | NO DOC. |  | 6836.4
2024-09-18 |  | 9/4 - PCB DUE ¦ AWT PART CONF 9/4 - KIT CLEAR |  |  |  |  | 1 | 127635 NEW | 25 | 9/18 10D | NL | X | "U38, U31" AFTER WASH *** MAKE SURE BOARDS ARE CLEAN PER ECO NOTE 3 *** DEPANEL ***MAKE SURE RoHS IS STATED ON THE CofC *** WAIVED PER JOE |  |  | 9/10 - BOT 9:00 9/10 - TOP 2:30 9/11 - AOI 4:00 | 266 | 1473 | 2B 3T | 17 | 425 | FEDEX P | Beckman Coulter |  |  | DOC REL 8/20 | 8/28 | 42225 | bot 1st | 2024-09-18 | 5 | 2024-09-09 | 15
2024-09-18 |  | 8/26 - KIT CLEAR |  |  | 1 | 0 |  | 127187-2nd RONC 1st Article | 90 | 9/18 15D | NL | RONC | XRAY & SAVE IMAGES |  |  | 8/29 - BOT 11:00 9/3 - PAUSE 11:00 9/4 - TOP 6:00 9/5 - AOI 11:00 | 110 | 767 | 1B 2T | 35 | 3150 | FEDEX P | GL Communications |  | 8/29 - L2 RUNS BOT ¦ L1 RUNS TOP | DOC REL 8/23 | 8/26 | 15501.6 | BOT 1ST | 2024-09-18 | 2 | 2024-08-29 | 27
2024-09-17 |  | 9/12 - PCB DUE 9/10 - KIT CLEAR |  |  | 1 |  |  | 127841 NEW | 5 | 9/17 5D | NL | X | "L1" ECO STATES AFTER WASH DUE TO PART MARKING COMMING OFF DURING WASH - PLEASE DISCUSS WITH TAD PRIOR TO RUNNING "R89 ^ C39" SILKSCREEN ARE SWAPPED, PLEASE REFER TO ECO DE[ANEL |  |  | 9/12 - BOT 7:00 9/12 - TOP 8:30 9/12 - AOI 11:00 | 58 | 244 | 1B 1T | 11 | 55 | FEDEX P | Bausch & Lomb |  |  | DOC REL 8/23 | 9/5 | 2691.5 | BOT 1ST | 2024-09-17 | 2 | 2024-09-12 | 4
2024-09-17 |  | 9/13 - PCB DUE 9/13 - KIT CLEAR |  |  | 1 |  |  | 128116 NEW | 35 | 9/17 2D | NL |  | *** 2 DAY TURN *** "U13" Customer will provide Qty. 10 of P/N M2MSIM-HD-D. Please use P/N GL1-MFF2-250 for the remainder. "LS1, U1" AFTER WASH |  |  | 9/13 - BOT 1:00 9/16 - TOP 9/16 - AOI 9:30 | 88 | 222 | 1B 1T | 3 | 105 | FEDEX P | Aspinity |  |  | DOC REL 9/6 | 9/12 | 10837.5 | BOT 1ST | 2024-09-17 | 2 |  | 7
2024-09-17 |  | 8/30 - PCB DUE ¦ many shortages with no ETA 8/27 - KIT SHORT ATTRITION 9/3 - KIT CLEAR |  |  |  | 0 | 3 | 127552 NEW | 3 | 9/17 10D | NL | X | DEPANEL AND SAND |  |  | 9/5 - BOT 10:30 9/5 - PAUSE 12:30 9/5 - TOP 1:00 9/6 - AOI 9:00 | 150 | 1183 | 1B 3T | 36 | 108 | UPS GRD | Droplet Measurement Technologies |  |  | DOC REL 8/21 | 8/22 | 8182.6 | BOT 1ST | 2024-09-17 | 5 | 2024-09-06 | 6.5
2024-09-17 |  | 9/6 - SHORT PCB WITH NO ETA 9/10 - KIT CLEAR |  |  | 1 |  |  | 128008 NEW | 32 | 9/17 5D | NL | X | DEPANEL |  |  | 9/11 - BOT 1:00 9/11 - TOP 2:30 9/12 - AOI 8:00 | 27 | 124 | 1B 1T | 19 | 608 | FEDEX P | Cognex |  |  | DOC REL 9/4 | 9/6 | 4589.6 | TOP 1ST | 2024-09-17 | 2 | 2024-09-10 | 3.5
2024-09-13 |  | 9/4 - EXPECTED CLEAR DATE 9/4 - KIT CLEAR |  |  |  |  | 2 | 127792 RONC 118922 | 164 | 9/18 10D | NL | RONC | *** DO NOT DEPANEL!!! *** LEADFREE NO CLEAN XRAY AND SAVE IMAGES MUST BE TRACEABLE BY SERIAL NUMBER AND LOCATION SEE ECO FOR PACKAGING |  |  | 9/5 - BOT 11:00 9/6 - PAUSE 2:30 9/6 - TOP 11:00 9/6 - AOI 2:00 | 4 | 9 | 1B 1T | 0 | 0 | DHL | Person-Aiz AS - fomerly Listen AS |  |  | DOC REL 8/28 | 9/3 | 1968 | BOT 1ST | 2024-09-18 | 3 | 2024-09-09 | 6.5
2024-09-13 |  | 9/4 - SHORT #28 (U5..) & SHOULD CLEAR SOON 9/6 - AWT PART CONF #28 (U5) 9/6 - KIT CLEAR |  |  |  | 1 |  | 127981 NEW | 32 | 9/13 5D | NL | X | SMT HAND-LOAD #2 (C269) DEPANEL |  |  | 9/10 - BOT 11:30 9/11 - TOP 10:00 9/12 - AOI 2:00 | 89 | 471 | 1B 1T | 0 | 0 | FEDEX P | AIRS - American Infrared Solutions |  | 9/11 - J1 DOES NOT MATCH FOOTPRINT 9/12 - new J1 received | DOC REL 8/28 | 9/4 | 5706 | BOT 1ST | 2024-09-13 | 2 | 2024-09-10 | 14.5
2024-09-13 |  | 9/11 - PCB DUE 9/6 - KIT CLEAR |  |  | 1 |  |  | 127842 NEW | 5 | 9/13 5D | NL | X | PLEASE SEE ECO #3 FOR SPECIFIC BAR CODE INSTRUCTIONS PACKAGE WITH EXTRA CARE - USE MULTIPLE SHIPPING BOXES TO PREVENT DAMAGE PER ECO #4 DEPANEL PACKAGING LABEL REQUIRED PER ECO #4 |  |  | 9/10 - BOT 10:00 9/10 - TOP 1:30 9/10 - AOI 10:30 | 62 | 318 | 1B 1T | 14 | 70 | FEDEX P | Bausch & Lomb |  |  | DOC REL 8/28 | 9/4 | 2918.5 | BOT 1ST | 2024-09-13 | 2 | 2024-09-11 | 8.5
2024-09-13 |  | 9/11 - PCB DUE ¦ AWT PART CONF 9/11 - KIT CLEAR |  |  |  |  | 1 | 128170 NEW | 9 | 9/13 2D | NL | X | *** 2 DAY TURN *** DEPANEL & SAND |  |  | 9/12 - TOP 3:00 9/13 - AOI 10:00 | 159 | 705 | 3T | 18 | 162 | FEDEX P | Ergotron, Inc. |  |  | DOC REL 9/6 | 9/10 | 21772 | TOP ONLY | 2024-09-13 | 4 | 2024-09-12 | 7
2024-09-13 |  | 8/20 - SHORT PCB WITH NO ETA 9/3 - PCB DUE 9/10 - KIT CLEAR |  |  | 1 |  |  | 127779 NEW | 10 | 9/13 3D | NL | X | *** 3 DAY TURN *** LEAD PROCESS MECH REQ *8/27 - UPDATED ECO NOTE 3 FOR "U4, U5" MECH ASSY REQ BEFORE SOLDERING DEPANEL |  |  | 9/11 - BOT 7:00 9/11 - TOP 10:00 9/11 - AOI 12:00 | 46 | 126 | 1B 1T | 43 | 430 | FEDEX P | Hoverfly Technologies Inc |  |  | DOC REL 8/19 | 8/20 | 4713.5 | TOP 1ST | 2024-09-13 | 2 | 2024-09-11 | 5
2024-09-12 |  | 9/3 OR 9/4 - #37 (BL1) DUE 9/5 - KIT CLEAR |  |  | 1 |  |  | 127250-1ST NEW | 52 | 9/12 5D | NL | X | TRUE NO CLEAN BUILD DEPANEL |  |  | 9/6 - BOT 9:00 9/6 - PAUSE 2:30 9/10 - TOP 6:00 9/10 - AOI 10:00 | 53 | 90 | 1B 2T | 1 | 52 | FEDEX P | Hip Science, LLC |  | 9/6 - REQ FIXTURE DUE TO HOW THIN THE BOARDS ARE | DOC REL 7/29 | 9/3 | 2491 | BOT 1ST | 2024-09-12 | 2 | 2024-09-09 | 9.5
2024-09-12 |  | 9/11 - PCB DUE DATE 9/11 - KIT CLEAR |  |  | 1 |  |  | 128276 NEW | 10 | 9/12 1D | NL | X | *** 1 DAY TURN *** DEPANEL |  |  | 9/11 - TOP 11:00 9/11 - AOI 2:30 | 37 | 126 | 1T | 7 | 70 | FEDEX P | Ergotron, Inc. |  |  | DOC REL 9/6 | 9/10 | 9125 | TOP ONLY | 2024-09-12 | 1 | 2024-09-12
2024-09-11 |  | 9/9 - DAY 1 (PHUONG) 9/6 - KIT CLEAR |  |  |  | 1 |  | 128238 RONC 127180 | 140 | 9/11 3D | NL | RONC | *** 3 DAY TURN *** DEPANEL & SAND PACKAGE WITH EXTRA CARE |  |  | 9/9 - BOT 8:00 9/9 - TOP 11:30 9/10 - AOI 1:00 | 32 | 90 | 1B 1T | 1 | 140 | UPS GRD | ERI Group |  |  | DOC REL 9/5 | 9/5 | 5696.6 | BOT 1ST | 2024-09-11 | 2 | 2024-09-09 | 11
2024-09-11 |  | 9/4 - KIT CLEAR |  |  |  | 1 |  | 127130 NEW | 48 | 9/11 5D | NL | X | BOARDS TO BE FREE AND CLEAN OF DEBRIS |  |  | 9/5 - TOP 1:00 9/6 - AOI 3:00 | 30 | 197 | 1T | 8 | 384 | FEDEX P | Samtec |  | 9/6 - COAXIL PARTS TOO CLUSTERED CAUSING XTRA TIME NEEDED DURING H/L FOR SMT | DOC REL 9/3 | 9/4 | 4671.04 | TOP ONLY | 2024-09-11 | 1 | 2024-09-06 | 8
2024-09-11 |  | 8/26 - SHORT PCB WITH NO ETA 9/4 - PCB DUE 9/4 - KIT CLEAR |  |  | 1 |  |  | 127598 NEW | 10 | 9/11 5D | NL | X | "SW1" AFTER WASH DEPANEL |  |  | 9/5 - BOT 2:00 9/6 - TOP 8:00 9/6 - AOI 11:00 | 39 | 302 | 1B 1T | 42 | 420 | FEDEX 2DAY | Monaco Enterprises, Inc. |  |  | DOC REL 8/21 | 8/26 | 4128 | BOT 1ST | 2024-09-11 | 2 | 2024-09-05 | 5.5
2024-09-11 |  | 9/5 - PCB DUE 9/4 - KIT CLEAR |  |  | 1 |  |  | 128023 NEW | 10 | 9/11 5D | NL | X | DEPANEL |  |  | 9/5 - BOT 11:00 9/5 - AOI 2:30 | 25 | 176 | 1B | 60 | 600 | FEDEX GRD | Alpheus Medical Inc |  |  | DOC REL 8/28 | 8/29 | 3546 | BOT ONLY | 2024-09-11 | 1 | 2024-09-05 | 3.5
2024-09-10 |  | 9/6 - PCB DUE 9/6 - KIT CLEAR |  |  | 2 |  |  | 128050 NEW | 25 | 9/10 2D | NL | X | *** 2 DAY TURN *** "L3. L4" AFTER WASH INSTALL "F1" BLADE FUSE PRIOR TO SHIPPING DEPANEL & SAND SPLIT SHIPMENT - SHIP QTY 10 TO: Enovate Medical SHIP QTY 15 TO: Ergotron, Inc. ADDRESS SPECIFIED ON ECO |  |  | 9/6 - BOT 1:30 9/7 - TOP 9/7 - AOI | 105 | 358 | 1B 2T | 9 | 225 | FEDEX P | Enovate Medical / Ergotron, Inc. |  |  | DOC REL 8/28 | 8/29 | 25290 | bot 1st | 2024-09-10 | 2 | 2024-09-07
2024-09-09 |  | 8/22 - SHORT 3 ITMS: #21 (C480..), #30 (U57..) AND #43 (U5) 8/29 - EXPECT CLEAR DATE 8/28 - KIT CLEAR |  |  | 1 |  |  | 123731 ROWC 120387 | 14 | 9/13 10D | NL | ROWC | DEPANEL |  |  | 9/3 - TOP 7:00 9/3 - TOP 9:00 9/3 - AOI 2:30 | 106 | 1204 | 2B 2T | 23 | 322 | FEDEX P | Southwest Research Institute |  |  | DOC REL 8/5 | 8/22 | 10392.76 | BOT 1ST | 2024-09-13 | 2 | 2024-08-30 | 7.5
2024-09-09 |  | 9/6 - PCB DUE ¦ C64 DUE NXT WEEK 8/29 - KIT CLEAR |  |  |  | 1 |  | 127843 NEW | 5 | 9/9 5D | NL | X | DEPANEL SHIP IN MULTIPLE BOXES TO PREVENT SHIPPING DAMAGE - DO NOT OVERPACK BOXES |  |  | 9/3 - BOT 11:00 9/3 - TOP 2:00 9/3 - PAUSE 10:00 9/5 - TOP 8:00 9/5 - AOI 11:00 | 85 | 352 | 1B 1T | 14 | 70 | FEDEX P | Bausch & Lomb |  | 9/4 - LINE 2 JUUKI ISSUES | DOC REL 8/23 | 8/27 | 2724 | BOT 1ST | 2024-09-09 | 2 | 2024-09-04 | 8
2024-09-09 |  | 8/21 - KIT CLEAR 8/23 - ON HOLD 8/27 - DAY 1 8/29 (TAD) |  |  | 1 |  |  | 127383 NEW | 11 | 9/9 8/28 5D | NL | X | ON HOLD - FAB DOESN'T MATCH FILES *** DO-A7 RATING *** MAKE SURE FIL14-FIL17 IS INSTALLED MOD1-MOD4, DEV2 ARE DNI NO ALTA VENDOR MARKINGS/STAMPS BOARDS MUST BE CLEAN - REMOVE ALL FLUX PACKAGE WITH EXTRA CARE |  |  | 8/28 - BOT 11:30 8/29 - TOP 9:00 9/3 - AOI 8:00 | 182 | 644 | 2B 3T | 37 | 407 | FEDEX P | John Hopkins University Applied Physics La |  |  | DOC REL 8/8 | 8/21 | 10846.8 | BOT 1ST | 2024-09-09 | 5 | 2024-08-28 | 13.5
2024-09-06 |  | 8/19 - SHORT PCB WITH NO ETA 8/29 - PCB DUE 8/27 - KIT CLEAR |  |  |  | 1 |  | 127559 NEW | 150 | 9/12 10D | NL | X | DEPANEL MAKE SURE BOARDS ARE CLEAN |  |  | 8/28 - TOP 9:30 8/29 - BOT 8:30 8/29 - AOI 11:00 | 32 | 46 | 1B 1T | 0 | 0 | FEDEX P | Industrialex Manufacturing |  |  | DOC REL 8/13 | 8/19 | 3177 | TOP 1ST | 2024-09-12 | 2 | 2024-08-28 | 7.5
2024-09-06 |  | 9/3 - PCB DUE ¦ short U11 9/4 - KIT CLEAR |  |  |  | 2 |  | 127823 RONC 123794 | 6 | 9/9 3D | NL | RONC | *** 3 DAY TURN *** "L1" AFTER WASH DEPANEL |  |  | 9/4 - BOT 10:00 9/4 - TOP 12:00 9/4 - AOI 3:30 | 51 | 556 | 1B 1T | 8 | 48 | FEDEX P | Genuen, LLC |  |  | DOC REL 8/23 | 8/28 | 3384 | BOT 1ST | 2024-09-09 | 2 |  | 5.5
2024-09-06 |  | 8/21 - KIT CLEAR |  |  | 1 |  |  | 127078 RONC 122165 | 40 | 9/6 10D | NL | RONC | U15 BTD PRE-BAKE PCB'S 24 HRS XRAY & SAVE IMAGES DEPANEL AND SAND |  |  | 8/27 - TOP 8:30 8/27 - AOI 2:30 | 73 | 306 | 2T | 9 | 360 | UPS GRD | Jefferson Labs |  |  | DOC REL 7/26 | 8/22 | 2763.2 | TOP ONLY | 2024-09-06 | 1 | 2024-08-26 | 6
2024-09-05 |  | 7/12 - PCB DUE ¦¦ SHORT #100 (U6) & #36 (C333) BOTH TOP SIDE 7/15 - PCB DUE 7/16 - short #100 (U3) -- SKIP 8/22 - KIT CLEAR |  |  | 1 |  |  | 126530 NEW | 10 | 9/9 10D | NL | X | #36 (C333) DNI LEAD FREE PROCESS RTV REQ PER ECO #3 *** TEST & RTV PER ECO #5 WAIVED, DO NOT INSTALL SHIELDS SHIP SHIELDS W/ ASSYS DEPANEL AND SAND |  |  | 7/17 - BOT 1:30 7/17 - PAUSE 2:30 7/18 - BOT 11:00 7/18 - TOP 2:00 7/19 - AOI 12:00 | 175 | 710 | 1B 2T | 11 | 110 | FEDEX GRD | L3 |  | 7/17 - AWT ARRAY FILE | DOC REL 7/8 | 7/9 | 13747.5 | BOT 1ST | 2024-07-31 | 2 | 2024-07-18
2024-09-05 |  | 8/19 - short #20 (c122), #42 (u22..) and #56 (j2) WITH NO ETA 8/27 - PARTIAL CLEAR (136 OF 250) |  |  |  |  | 1 | 126752-1 PAR NEW | 136 | 9/5 5D | NL | X | "L17, 18, 19, 22" AFTER WASH DEPANEL |  |  | 8/28 - BOT 6:00 8/29 - TOP 9:00 9/3 - AOI 10:00 | 91 | 312 | 2B 2T | 0 | 0 | FEDEX P | Summit Santa Clara-Streamline Circuits |  | VERIFY SIDE TO RUN | DOC REL 8/12 | 8/19 | 13503.6 | BOT 1ST | 2024-09-05 | 2 | 2024-08-28 | 29
2024-09-04 |  | 7/1 - SHORT PCB W/ NO ETA 7/29 - KIT CLEAR 8/14 - PCB due 8/14 - KIT CLEAR |  |  |  | 1 | 1 | 126664 NEW | 4 | 8/28 8/12 10D | NL | X | ***READ ECO BEFORE RUNNING*** ***DO NOT DEPANEL - BOARDS NEED TO GET SENT TO TESTING BEFORE DEPANEL!!! CLASS 3 "J3 & J4" MAKE SURE CONNECTORS ARE ALIGNED AND MOUNTING HARDWARE IS ALIGNED AND WILL FIT "L1A & L1B" REQUIRE FIXTURES MECH ASSY REQ press fit |  |  | 8/23 - BOT 2:00 8/26 - TOP 11:00 8/27 - AOI 10:00 | 87 | 497 | 1B 1T | 20 | 80 | FEDEX P | Test Coach Company |  |  | DOC REL 7/1 | 7/2 | 3780 | BOT 1ST SCREW INSTALLATION REQUIRED AFTER TOP HAS GONE THROUGH REFLOW | 2024-08-28 | 2 | 2024-08-27 | 10
2024-09-04 |  | 8/26 - KIT CLEAR | [5 empty] | 127818 RWK 126223 | 14 | 9/4 5D | X |  | 1, The correct placement of U10 we will need to remove and rotate the part 90 deg counterclockwise (SEE TRAVELER) 2, U34 remove MAX20360BEWZ and replace with MAX20360CEWZ. QA Inspection: IPC –610 is used to check rework requirements |  |  | BACK | 136 | 849 | 2B 2T | 3 | 42 | FEDEX P | L3 |  |  | NO DOC. |  | 1855
2024-09-04 |  | 8/23 - PCB DUE ¦ many shortages with no ETA 8/23 - short #63 (J3) 8/26 - KIT CLEAR |  |  | 1 |  |  | 127377 NEW | 20 | 9/4 5D | NL | X | LEAD PROCESS "U59, L30" AFTER WASH DEPANEL |  |  | 8/28 - TOP 6:00 8/28 - AOI 12:00 | 92 | 459 | 2T | 8 | 160 | FEDEX 2DAY | Oak Ridge National Labs |  |  | DOC REL 8/13 | 8/22 | 4940 | TOP ONLY | 2024-09-04 | 1 | 2024-08-27 | 6
2024-09-04 |  | 8/29 - PCB DUE 8/21 - KIT CLEAR | [5 empty] | 127804 RONC 100892 | 3 | 9/4 9/6 10D | X |  |  |  |  | BACK | 0 | 0 |  | 112 | 336 | UPS GRD | Prima Power Laserdyne LLC |  |  | DOC REL 8/15 |  | 2856
2024-09-04 |  | 8/21 - PCB DUE 8/19 - OTHER SHORTAGES DUE 8/20 - SMT CLEAR 8/26 - KIT CLEAR |  |  |  | 1 |  | 127046 ROWC 112479 | 20 | 9/4 5D | NL | ROWC | T1-T8 SPECIFIC INSTALL INSTRUCTIONS (SEE ECO) E0-E12 FLUSH TO BOARD CofC AND PACKING SLIP REQUIREMENTS DEPANEL |  |  | 8/27 - BOT 10:00 8/27 - PAUSE 11:00 8/27 - BOT 1:00 8/27 - TOP 2:00 8/28 - AOI 10:00 | 32 | 139 | 1B 1T | 24 | 480 | UPS GRD | LKC Technologies |  |  | DOC REL 8/15 | 8/16 | 2685 | BOT 1ST | 2024-09-04 | 2 | 2024-08-28 | 4
2024-09-03 |  | 8/19 - SMT CLEAR 8/23 - KIT CLEAR |  |  | 1 |  |  | 127065 NEW | 6 | 9/3 5D | NL | X | LEAD PROCESS "C20_X1 x12" SEE ECO FOR SOLDERING DEPANEL |  |  | 8/27 - BOT 6:00 8/27 - TOP 8/27 - AOI 9:00 | 32 | 473 | 1B 1T | 25 | 150 | FEDEX P | Naval Research Laboratory |  |  | DOC REL 8/16 | 8/19 | 4077.84 | BOT 1ST | 2024-09-03 | 2 | 2024-08-27
2024-09-03 |  | 8/8 OR 8/9 - PCB DUE 8/12 - KIT CLEAR |  |  |  | 1 |  | 126657 ROWC 119296 | 43 | 9/3 15D | NL | ROWC | NOTE – all PWB’s for PO 24-029 should have P/N “13068_ _ _ REV –“ etched in copper markings and REV – is acceptable. TRIM LEADS PER ECO #2 DEPANEL |  |  | 8/26 - TOP 12:00 8/27 - BOT 9:00 8/27 - AOI 2:00 | 26 | 85 | 1B 1T | 11 | 473 | FEDEX P | Plasma Ruggedized Solutions |  |  | DOC REL 7/15 | 8/5 | 1423.3 | TOP 1ST | 2024-09-03 | 2 | 2024-08-27 | 8
2024-08-29 |  | 7/19 - SHORT 4 SMT ITMS - NO ETA 8/13 - AWT PAT CONF #92 (U47) 8/14 - SMT CLEAR 8/15 - KIT CLEAR |  |  |  |  | 1 | 126733 NEW | 5 | 8/29 10D | NL | X | LEAD PROCESS ORIENT "J24" PER ECO #5 RTV REQ PER ECO #2 |  |  | 8/21 - TOP 6:00 8/21 - PAUSE 11:00 8/23 - BOT 1:30 8/24 - AOI | 255 | 1531 | 3B 3T | 22 | 110 | FEDEX GRD | L3 |  |  | DOC REL 7/12 | 7/19 | 11986.2 | TOP 1ST | 2024-08-29 | 5 | 2024-08-22
2024-08-29 |  | 8/12 - PCB DUE DATE 8/27 - KIT CLEAR | [5 empty] | 126955 NEW | 20 | 8/29 8/21 10D | X |  | PART SHORTAGES T/H ONLY DEPANEL |  |  | back | 0 | 0 |  | 49 | 980 | FEDEX GRD | United Therapeutics |  |  | DOC REL 8/5 |  | 2555
2024-08-29 |  | 8/19 - KIT CLEAR |  |  | 1 |  |  | 127581 NEW | 15 | 8/29 8/26 5D | NL | X | DEPANEL |  |  | 8/22 - BOT 8:30 8/22 - PAUSE 9:30 8/23 - BOT 7:00 8/23 - PAUSE 9:00 8/23 - TOP 11:30 8/23 - AOI 12:30 | 77 | 416 | 1B 1T | 72 | 1080 | FEDEX 2DAY | Applied Radar, Inc. |  | 8/21 - SHORT U40 (TOP SIDE) | DOC REL 8/13 | 8/19 | 5581.2 | BOT 1ST | 2024-08-26 | 2 | 2024-08-23 | 4
2024-08-29 |  | 8/5 - SHORT #1 (C10_1..) & #27 (Y3) 8/7 - AWT PART CONF 8/7 - KIT CLEAR |  |  | 1 |  |  | 127038 ROWC 117812 | 20 | 8/28 8/12 10D | NL | X | "S1" AFTER WASH 8/7 - CUST ADDED "J1012 & J1013" TO BE INSTALLED - "J8, J12" DNI MAKE SURE BOARDS ARE WASHED AND CLEAN DEPANEL |  |  | 8/26 - BOT 6:00 8/26 - PAUSE 8:00 8/26 - TOP 11:00 8/26 - AOI 2:30 | 119 | 431 | 2B 2T | 1 | 20 | FEDEX GND | PERATON |  | F1 & F2 MARKING DOESN'T MATCH | DOC REL 8/1 | AUG 5 | 2476.8 | BOT 1ST SCREW INSTALLATION REQUIRED AFTER TOP HAS GONE THROUGH REFLOW | 2024-08-28 | 2 | 2024-08-26 | 10
2024-08-29 |  | 8/19 - PCB DUE 8/9 - SHORT PCB & #1 (C1002) NO ETA 8/21 - PCB DUE 8/21 - KIT CLEAR |  |  | 1 |  |  | 127248-2 BAL NEW | 38 | 8/28 5D | NL | X | ***ALL DNI PADS MUST BE FREE OF SOLDER ALPHA WS-820 PASTE REQ "C266" MIX POP - Qty 732 (TCJD477M004R0025) DigiKey - Qty 706 (T520D477M004ATE025) Mouser - Qty 734 (T520D477M004ATE025) DigiKey AWT shortages from customer DNI C527, C537, C547 and C577 DEPANEL |  |  | 8/23 - BOT 10:30 8/23 - PAUSE 11:30 8/23 - BOT 1:30 8/24 - AOI | 104 | 568 | 1B 2T | 30 | 1140 | FEDEX INTL | Alphawave IP Inc. |  |  | DOC REL 8/5 | 8/6 | 6486 | BOT 1ST | 2024-08-28 | 2
2024-08-28 |  | 8/8 - SHORT PCB WITH NO ETA 8/22 - KIT CLEAR |  |  |  |  | cancelled | 127180 NEW | 140 | 8/27 3D | NL | X | ON HOLD - J2 DOESN'T FIT PROPERLY *** 3 DAY TURN *** DEPANEL AND SAND EXTRA PACKAGING CARE REQ |  |  | 8/23 - BOT 6:00 8/23 - pause 11:00 | 32 | 90 | 1B 1T | 1 | 140 | FEDEX GRD | ERI Group |  | 8/23 - J2 DOES NOT FIT PROPERLY | DOC REL 8/7 | 8/8 | 5696.8 | BOT 1ST | 2024-08-27 | 2
2024-08-28 |  | 8/16 - PCB DUE 8/21 - KIT CLEAR |  |  |  |  | 1 | 126986 ROWC 121008 | 42 | 8/28 5D | NL | ROWC | *** MASK OUTER PADS OF "SW1" PER ECO "U31" AFER WASH "J1" PRESS FIT DEPANEL |  |  | 8/24 - BOT 8/26 - TOP 11:00 8/26 - AOI 1:00 | 128 | 800 | 2B 2T | 4 | 168 | UPS RED | Farsounder, Inc. |  |  | DOC REL 8/9 | 8/15 | 8019.66 | BOT 1ST | 2024-08-28 | 2 | 2024-08-23
2024-08-28 |  | 8/1 - SHORT PCB W/ NO ETA 8/14 - PCB DUE 8/15 - PCB DUE 8/22 - PCB DUE 8/23 - KIT CLEAR |  |  | 1 |  |  | 127196 RONC 125611 | 6 | 8/28 10D | NL | RONC | *** EXPEDITE. SHIP BY DUE DATE *** LEAD PROCESS DEPANEL |  |  | 8/26 - TOP 8:00 8/26 - AOI 12:00 | 24 | 137 | 2T | 7 | 42 | FEDEX P | Ocean Aero, Inc. |  | PREV BUILD = L3 | DOC REL 7/31 | 8/1 | 1755 | TOP ONLY | 2024-08-28 | 1 | 2024-08-26 | 4
2024-08-28 |  | 8/8 - SHORT PCB WITH NO ETA 8/21 - pcb due 8/28 - KIT CLEAR |  |  |  | 1 |  | 127471 RONC 127470 | 90 | 8/28 5D | NL | RO | "SW1, SW2" AFTER WASH TRIM LEADS - MAX LEAD HIEGHT 2.0 DEPANEL & SAND DO NOT SHIP EXCESS MATL |  |  | 8/23 - TOP 8:00 8/23 - AOI 1:00 | 27 | 81 | 1T | 6 | 540 | FEDEX P | Ergotron, Inc. |  |  | DOC REL 8/8 | 8/8 | 12604 | TOP ONLY | 2024-08-28 | 1 | 2024-08-22 | 5
2024-08-27 |  | 8/19 - PCB DUE 8/9 - SHORT PCB & #1 (C1002) NO ETA 8/21 - PCB DUE 8/21 - KIT CLEAR |  |  | 1 |  |  | 127248-1 PAR NEW | 2 | 8/28 5D | NL | X | ***ALL DNI PADS MUST BE FREE OF SOLDER ALPHA WS-820 PASTE REQ "C266" MIX POP - Qty 732 (TCJD477M004R0025) DigiKey - Qty 706 (T520D477M004ATE025) Mouser - Qty 734 (T520D477M004ATE025) DigiKey AWT shortages from customer DNI C527, C537, C547 and C577 DEPANEL |  |  | 8/23 - BOT 10:30 8/23 - PAUSE 11:30 8/23 - BOT 1:30 8/24 - AOI | 104 | 568 | 1B 2T | 30 | 60 | FEDEX INTL | Alphawave IP Inc. |  |  | DOC REL 8/5 | 8/6 | 6486 | BOT 1ST | 2024-08-28 | 2
2024-08-27 |  | 8/2 - KIT CLEAR | [5 empty] | 127573-2 BAL RWK 126350 | 33 | 8/28 8/16 10D | - |  | 1. Remove qty 11 T/H per board 2. Place missing connectors onto J11, J12, J18 & J19, cover with foil to protect certain areas and reflow 3. Re-solder qty 11 T/H per board 4. Wash 5. Re-inspect 6. Photos of rework area required before shipping |  |  | BACK |  |  |  |  | 0 | FEDEX P | Integrated Consultants |  |  | NO DOC. | 8/2 | 4125
2024-08-27 |  | 5/22 - PCB DUE 5/21 - KIT CLEAR |  |  | 1 |  |  | 125711-2 BAL NEW | 60 | 8/27 10D | NL | X | DO NOT SHIP EARLY QTY 60 7/25/2024 QTY 60 8/27/2024 TRIM LEADS TO 0.98 PER ECO DEPANEL |  |  | 5/31 - TOP 11:00 6/1 - AOI 7:00 | 25 | 51 | 1T | 3 | 180 | FEDEX GRD | Frencken America Inc. |  |  | NO DOC. | 5/10 | 1156.8 | TOP ONLY | 2024-07-25 | 1 |  | 5.5
2024-08-26 |  | 8/15 - PCB DUE ¦ SHORT #23 (S1) 8/19 - KIT CLEAR |  |  | 1 |  |  | 127540 RONC 111683 | 100 | 8/26 5D | NL | RONC | *** VERIFY "U2, U4, U6, U8" IS MASKED OFF PER ECO *** KEEP GRID HOLES FREE OF SOLDER QA BEFORE INSTALLING SHIELD AND COVER DEPANEL |  |  | 8/22 - TOP 9:30 8/23 - AOI 8:00 | 33 | 167 | 1T | 9 | 900 | FEDEX P | Technical Manufacturing Corp (TMC) |  |  | DOC REL 8/9 | 8/14 | 5316 | TOP ONLY | 2024-08-26 | 1 | 2024-08-22 | 9
2024-08-23 |  | 8/15 - PCB DUE & SHORT #39 (L3) 8/19 - KIT CLEAR |  |  |  |  | 2 | 127179-2 BAL NEW | 1 | 8/22 3D | NL | X | *** 3 DAY TURN *** LOT TRACKING REQ PER ECO DEPANEL & SAND |  |  | 8/20 - BOT 12:00 8/21 - TOP 10:00 8/22 - AOI 10:00 | 105 | 290 | 1B 2T | 1 | 1 | UPS GRD | ERI Group |  |  | DOC REL 8/5 | 8/12 | 12812.2 | BOT 1ST | 2024-08-22 | 2 |  | 16
2024-08-23 |  | 8/22 - KIT CLEAR |  |  | 1 |  |  | 127728 NEW | 10 | 8/23 1D | NL |  | *** 1 DAY TURN *** DEPANEL AND SAND |  |  | 8/22 - TOP 9:30 8/22 - AOI 11:30 | 8 | 23 | 1T | 22 | 220 | FEDEX P | Ergotron, Inc. |  |  | DOC REL 8/20 | 8/22 | 6550 | TOP ONLY | 2024-08-23 | 1 | 2024-08-22 | 2
2024-08-23 |  | 8/5 - KIT CLEAR (DAY 1 8/8/2024 PHUONG) |  |  | 1 |  |  | 126757 RONC 124745 | 200 | 8/23 8/21 10D | NL | RONC | LEAD PROCESS DEPANEL |  |  | 8/17 - BOT 7:00 8/19 - TOP 1:00 8/20 - AOI 4:30 | 73 | 270 | 1B 1T | 10 | 2000 | UPS GRD | Safe Foods |  |  | DOC REL 6/28 | 8/5 | 12260 | BOT 1ST | 2024-08-21 | 2 | 2024-08-12 | 18
2024-08-22 |  | 8/15 - KIT CLEAR | [5 empty] | 125843-1 BAL NEW | 135 | 8/22 5D | X |  | THT ONLY DEPANEL |  |  | BACK | 0 | 0 | 0 | 1 | 135 | FEDEX P | Summit Santa Clara-Streamline Circuits |  |  | DOC REL 5/28 |  | 4275
2024-08-22 |  | 8/15 - PCB DUE & SHORT #39 (L3) 8/19 - KIT CLEAR |  |  |  |  | 2 | 127179-1 PAR NEW | 139 | 8/22 3D | NL | X | *** 3 DAY TURN *** LOT TRACKING REQ PER ECO DEPANEL & SAND |  |  | 8/20 - BOT 12:00 8/21 - TOP 10:00 8/22 - AOI 10:00 | 105 | 290 | 1B 2T | 1 | 139 | UPS GRD | ERI Group |  |  | DOC REL 8/5 | 8/12 | 12812.2 | BOT 1ST | 2024-08-22 | 2 |  | 16
2024-08-22 |  | 8/8 - SHORT PCB & #20 (R4) WITH NO ETA 8/15 - PCB DUE 8/15 - KIT CLEAR |  |  |  |  | 1 | 127475 RONC 127474 | 80 | 8/22 5D | NL | RONC | DEPANEL & SAND DO NOT SHIP EXCESS MATL |  |  | 8/19 - TOP 9:00 8/19 - AOI 12:00 | 18 | 26 | 1T | 2 | 160 | FEDEX P | Ergotron, Inc. |  |  | DOC REL 8/8 | 8/8 | 12570 | TOP ONLY | 2024-08-22 | 1 | 2024-08-20 | 3
2024-08-22 |  | 8/13 - SHORT #7 (D1_1...) QTY 50 PCS ¦ AWT PART CONF #29 (P5_1...) 8/14 - KIT CLEAR |  |  |  | 1 |  | 127332 RONC 124409 | 110 | 8/22 8/21 5D | NL | RONC | ***NO VENDOR MARKING ALLOWED PER ECO |  |  | 8/19 - TOP 6:00 8/20 - AOI 12:00 | 36 | 315 | 1T | 16 | 1760 | FEDEX P | John Hopkins University Applied Physics Lab |  | 8/20 - SHORT 300 PCS OF #2 | DOC REL 7/26 | 8/13 | 14258.2 | top only | 2024-08-21 | 1 |  | 15
2024-08-22 |  | 8/12 - SHORT PCB with NO ETA 8/15 - pcb due 8/16 - PCB DUE 8/19 - PCB DUE 8/19 - KIT CLEAR |  |  |  |  | 1 | 127629 NEW | 20 | 8/22 3D | NL | X | *** 3 DAY TURN *** U5 Orientation (SEE ECO) L1 & L2 PLACE AFTER WASH TWO DATA MATRIX LABELS REQUIRED: ONE S/N AND ONE ASSY |  |  | 8/21 - BOT 2:00 8/22 - TOP 11:00 8/22 - AOI 3:00 | 66 | 730 | 1B 1T | 2 | 40 | FEDEX P | OXOS Medical, Inc. |  |  | DOC REL 8/9 | 8/12 | 8530 | BOT 1ST | 2024-08-22 | 2 |  | 10
2024-08-21 |  | 8/20 - KIT CLEAR |  |  | 2 |  |  | 127729 NEW | 50 | 8/21 1D | NL | X | *** 1 DAY TURN *** DEPANEL & SAND |  |  | 8/21 - BOT 6:00 8/21 - AOI 10:30 | 1 | 3 | 1B | 11 | 550 | FEDEX P | Ergotron, Inc. |  |  | DOC REL 8/20 | 8/20 | 9600 | bot only | 2024-08-21 | 1 |  | 5.5
2024-08-21 |  | 8/19 - PCB DUE 8/16 - KIT CLEAR |  |  | 1 |  |  | 127723 NEW | 80 | 8/21 3D | NL | X | *** 3 DAY TURN *** DEPANEL 2 DIFFERENT LABELS PER BOARD REQ |  |  | 8/21 - BOT 10:00 8/21 - TOP 8/21 - AOI 1:30 | 15 | 68 | 1B 1T | 0 | 0 | FEDEX P | OXOS Medical, Inc. |  |  | DOC REL 8/13 | 8/14 | 5080 | TOP 1ST | 2024-08-21 | 2 | 2024-08-20 | 3.5
2024-08-21 |  | 8/9 - PCB DUE 8/8 - KIT CLEAR 8/14 - KIT CLEAR |  |  | 2 |  |  | 127480 NEW | 10 | 8/21 8/15 5D | NL | X | ON HOLD "SW1, SW2" AFTER WASH "PS201" AFTERWASH & NEEDS TO GET ASSEMBLED TOGETHER POST BAKE 30 MIN IF BOARDS ARE WASHED DEPANEL |  |  | 8/16 - TOP 2:30 8/16 - AOI 3:30 | 43 | 174 | 1T | 72 | 720 | FEDEX P | Rasirc |  | 8/8 - PCBA MISSING V-SCORES | DOC REL 8/7 | 8/8 | 5833 | TOP ONLY | 2024-08-21 | 1 | 2024-08-20
2024-08-21 |  | 8/8 - PCB DUE THEN SMT CLEAR 8/13 - qty 22 pcbs due; ship partial 8/14 - KIT CLEAR |  |  |  |  | 1 | 127333-2 BAL NEW | 21 | 8/21 5D | NL | X | CLASS 3 ***ALPHA CVP-390V SOLDER PASTE REQUIRED (COMPATABLE FLUX REQUIRED) "U14" NO SOLDER ON CENTER PAD "L5" AFTER WASH ***USE LEAD SOLDER ON T/H PARTS*** MECH ASSY REQ DEPANEL SHIP 1 BOARD ON 3-DAY TURN AOI BEFORE SHIP DNI (ON THE 1 BOARD) J1, J2, J3, J4, J5_1, J5_2, J5_3, J5_4, J5_5 BTD J1 & J3 |  |  | 8/16 - BOT 7:00 8/16 - TOP 2:30 8/19 - AOI 8:00 | 111 | 2530 | 1B 2T | 34 | 714 | FEDEX STD | Varda Space-El Segundo, CA |  | CUST CHANGED BOM 8/2 - D4 moved to item #31. Item #30 (previously used for D4 only) is no longer needed and moved to the DNI section | DOC REL 7/29 | 8/1 | 16360.89 | BOT 1ST | 2024-08-15 | 2 |  | 19
2024-08-20 |  | 8/8 - PCB DUE THEN SMT CLEAR 8/13 - qty 22 pcbs due; ship partial 8/14 - KIT CLEAR |  |  |  |  | 1 | 127333-1 PAR NEW | 5 | 8/21 5D | NL | X | CLASS 3 ***ALPHA CVP-390V SOLDER PASTE REQUIRED (COMPATABLE FLUX REQUIRED) "U14" NO SOLDER ON CENTER PAD "L5" AFTER WASH ***USE LEAD SOLDER ON T/H PARTS*** MECH ASSY REQ DEPANEL SHIP 1 BOARD ON 3-DAY TURN AOI BEFORE SHIP DNI (ON THE 1 BOARD) J1, J2, J3, J4, J5_1, J5_2, J5_3, J5_4, J5_5 BTD J1 & J3 |  |  | 8/16 - BOT 7:00 8/16 - TOP 2:30 8/19 - AOI 8:00 | 111 | 2530 | 1B 2T | 34 | 170 | FEDEX STD | Varda Space-El Segundo, CA |  |  | DOC REL 7/29 | 8/1 | 6295.45 | BOT 1ST | 2024-08-15 | 2 |  | 19
2024-08-20 |  | 8/13 - PCB DUE & SHORT #20 (U205) & #35 (J102) 8/13 - KIT CLEAR |  |  | 2 |  |  | 127483 RONC 127482 | 20 | 8/20 5D | NL | RONC | DEPANEL & SAND DO NOT SHIP EXCESS MATL |  |  | 8/19 - TOP 12:30 8/19 - AOI 3:30 | 66 | 334 | 1T | 4 | 80 | FEDEX P | Ergotron, Inc. |  |  | DOC REL 8/8 | 8/12 | 22360.2 | TOP ONLY | 2024-08-20 | 1 | 2024-08-19
2024-08-20 |  | 8/13 - PCB DUE 8/13 - KIT CLEAR |  |  | 1 |  |  | 127469 RONC 127468 | 80 | 8/20 5D | NL | RONC | "PZ1, SW2" AFTER WASH "J10" JUMPER REQ DEPANEL & SAND DO NOT SHIP EXCESS MATL |  |  | 8/16 - BOT 6:00 8/16 - TOP 10:30 8/17 - AOI 8:00 | 88 | 340 | 1B 1T | 14 | 1120 | FEDEX P | Ergotron, Inc. |  |  | DOC REL 8/7 | 8/12 | 41673.2 | BOT 1ST | 2024-08-20 | 2 | 2024-08-15 | 11
2024-08-20 |  | 8/6 TO 8/8 - SHORT #13 (U5) 8/6 - KIT CLEAR |  |  | 2 |  |  | 127212 RONC 124151 | 300 | 8/20 10D | NL | RONC | LEAD PROCESS |  |  | 8/13 - TOP 4:00 8/14 - AOI 10:30 | 29 | 56 | 2T | 4 | 1200 | UPS RED | Technical Maintenance & Electronics, Inc. |  |  | DOC REL 8/1 | 8/5 | 5275 | TOP ONLY | 2024-08-20 | 1 | 2024-08-13 | 7
2024-08-19 |  | 8/12 - PCB DUE 8/12 - KIT CLEAR |  |  | 2 |  |  | 127283 NEW | 3 | 8/19 5D | NL | X | XRAY & SAVE IMAGES DEPANEL |  |  | 8/15 - BOT 5:00 8/15 - TOP 8/15 - AOI 10:00 | 56 | 548 | 1B 1T | 7 | 21 | FEDEX P | View Point Medical |  |  | DOC REL 8/8 | 8/8 | 3404.4 | BOT 1ST | 2024-08-19 | 2 | 2024-08-16 | 5
2024-08-19 |  | 8/8 - SHORT PCB WITH NO ETA 8/13 - PCB DUE |  |  |  |  | 2 | 127473 RONC 127472 | 80 | 8/19 5D | NL | RONC | DEPANEL & SAND DO NOT SHIP EXCESS MATL |  |  | 8/16 - TOP 6:00 8/16 - AOI 7:00 | 1 | 3 | 1T | 1 | 80 | FEDEX P | Ergotron, Inc. |  |  | DOC REL 8/8 | 8/8 | 7760 | TOP ONLY | 2024-08-19 | 1 | 2024-08-15 | 1
2024-08-19 |  | 8/8 - SHORT PCB, #13(J1) & #19(R2..) 8/13 - PCB DUE 8/12 - KIT CLEAR |  |  |  |  | 1 | 127477 RONC 127476 | 80 | 8/19 5D | NL | RONC | TRIM LEADS TO 2.0 MAX HIEGHT PER ECO DEPANEL & SAND DO NOT SHIP EXCESS MATL |  |  | 8/16 - TOP 5:00 8/16 - AOI 6:00 | 16 | 33 | 1T | 8 | 640 | FEDEX P | Ergotron, Inc. |  |  | DOC REL 8/8 | 8/8 | 18530 | top only | 2024-08-19 | 1 | 2024-08-15 | 1
2024-08-19 |  | 8/7 - PCB DUE 8/5 - KIT CLEAR |  |  | 2 |  |  | 127314 NEW | 750 | 8/19 10D | NL | X | DEPANEL |  |  | 8/13 - BOT 11:00 8/13 - PAUSE 4:30 8/14 - TOP 10:00 8/15 - AOI 6:00 PM | 17 | 31 | 1B 2T | 2 | 1500 | UPS GRD | S & A Systems |  |  | DOC REL 7/26 | 7/29 | 10300 | BOT 1ST | 2024-08-19 | 2 | 2024-08-13 | 23
2024-08-16 |  | 8/15 - SHORT U4 ¦ SKIP (ANNE) |  |  | 1 |  |  | 127617 RONC 125418 | 2 | 8/16 2D | NL |  | *** 2 DAY TURN *** DEPANEL |  |  | 8/15 - BOT 12:00 8/15 - TOP 2:00 8/15 - AOI 4:00 | 92 | 267 | 2B 2T | 3 | 6 | FEDEX P | Saturn PCB Design, Inc. |  |  | DOC REL 8/9 |  | 4894.8 |  | 2024-08-16 | 1 |  | 4
2024-08-16 |  | 8/9 - KIT CLEAR |  |  |  |  | 1 | 127395 NEW | 10 | 8/16 5D | NL | X | 3M adhesive S-22863, Adhesive required in final assembly. "LS1, S1, S2, U42, MP1x8" AFTER WASH "BT1" AFTER REFLOW DEPANEL |  |  | 8/14 - BOT 10:00 8/14 - TOP 1:30 8/15 - AOI 4:00 | 202 | 1001 | 2B 3T | 14 | 140 | FEDEX P | OXOS Medical, Inc. |  |  | DOC REL 8/3 | 8/9 | 16370 | BOT 1ST | 2024-08-16 | 5 | 2024-08-14 | 15
2024-08-16 |  | 7/12 - WILL CLEAR AFTER CUSTOMER OKAY ON SOLDER SAMPLE 7/17 - KIT CLEAR |  |  |  |  | 4 | 123005 ROWC 110514 | 67 | 8/16 8/14 20D | NL | ROWC | DEPANEL |  |  | 8/6 - TOP 7:00 8/6 - PAUSE 8:30 8/8 - TOP 5:00 8/8 - AOI 8:00 | 11 | 34 | 1T | 0 | 0 | FEDEX P | Biomeme, Inc. |  | RIGID FLEX BOARD (XFER TO TRI TO RUN) 8/13 - NOTIFY CUSTOMER ABOUT BOARD BLISTERS 8/15 - label board blistered (customer) | DOC REL 7/3 | 7/12 | 2572.4 | TOP ONLY | 2024-08-14 | 1 | 2024-08-08 | 4.5
2024-08-15 |  | 8/1 - KIT CLEAR |  |  |  |  | 1 | 126947 NEW | 10 | 8/15 10D | NL | X | ***PLEASE READ ECO PRIOR TO RUNNING*** LEAD FREE NO CLEAN PROCESS ***LABEL BOARDS W/ "TAD DEPANEL - ECO 7" CUST UPDATED BOM TO FOR ITEM #44 TO DNI 16 OF 18 LOCATIONS WASH BOARDS WITH "KYZEN AQUANOX" TO REMOVE NO CLEAN FLUX NO VENDOR MARKINGS ALLOWED DEPANEL ***MUST SAND EDGES EXTRA PACKAGING FOR SAFE HANDLING |  |  | 8/12 - BOT 10:00 8/12 - pause 1:30 8/13 - TOP 1:00 8/13 - AOI 3:30 | 73 | 1099 | 1B 1T | 14 | 140 | FEDEX P | John Hopkins University Applied Physics Lab |  | XTRA TIME IN BACK NEEDED TO CLEAN BOARDS 8/7 - TAD WANTS TO REVIEW FEEDERS AFTER SETUP BY THIS DATE AT THE LATEST | DOC REL 7/29 | 8/1 | 7137.7 | BOT 1ST | 2024-08-15 | 2 | 2024-08-13 | 6
2024-08-15 |  | 8/7 - ALMOST CLEAR 8/8 - KIT CLEAR |  |  |  |  | 1 | 123289 NEW | 2 | 8/15 5D | NL | X | "K1x10" AFTER WASH DEPANEL |  |  | 8/13 - TOP 3:00 8/14 - AOI | 27 | 525 | 1T | 108 | 216 | DHL INTL | ICU Medical |  |  | DOC REL 8/7 | 8/7 | 2814.5 | TOP ONLY | 2024-08-15 | 1 | 2024-08-14
2024-08-15 |  | 8/14 - PCB DUE 8/8 - KIT CLEAR |  |  | 1 |  |  | 127453 RONC 127452 | 80 | 8/15 5D | NL | RONC | "SW2, SW3" AFTER WASH INSTALL "F1 & FH1" TOGETHER DEPANEL & SAND DO NOT SHIP EXCESS MATL |  |  | 8/12 - BOT 6:00 8/12 - PAUSE 8:30 8/12 - TOP 1:00 8/13 - AOI 11:00 | 105 | 358 | 1B 2T | 9 | 720 | FEDEX P | Ergotron, Inc. |  |  | DOC REL 8/1 | 8/6 | 49049.6 | BOT 1ST | 2024-08-15 | 2 | 2024-08-09 | 11
2024-08-14 |  | 8/7 - PCB DUE |  |  |  |  | 1 | 127451 RONC 127450 | 80 | 8/14 5D | NL | RONC | POST BAKE 30 MIN IF BOARDS ARE WASHED DEPANEL & SAND DO NOT SHIP EXCESS MATL |  |  | 8/8 - TOP 9:00 8/8 - AOI 2:00 | 14 | 56 | 1T | 3 | 240 | FEDEX P | Ergotron, Inc. |  |  | DOC REL 8/1 | 8/1 | 15810 | TOP ONLY | 2024-08-14 | 1 | 2024-08-09 | 5
2024-08-14 |  | 8/7 - PCB DUE DATE ¦ SHORT #18 (10) WITH NO ETA 8/7 - KIT CLEAR |  |  | 2 |  |  | 127447 RONC 127445 | 80 | 8/14 5D | NL | RONC | ***REPORT SERIAL NUMBERS TO THE CUSTOMER PRIOR TO SHIPPING "U31" AFTER WASH DEPANEL & SAND DO NOT SHIP EXCESS MATL |  |  | 8/10 - AOI | 58 | 187 | 1B 1T | 4 | 320 | FEDEX P | Ergotron, Inc. |  |  | DOC REL 8/1 | 8/5 | 23072 | BOT 1ST | 2024-08-14 | 2 | 2024-08-10
2024-08-13 |  | Short #23 (C190), #47 (47) U31 & #103 (R527) AWT PART CONF the rest 7/22 – PCB due date 7/29 - KIT CLEAR |  |  | 3 |  |  | 125391-2 BAL NEW | 2 | 8/12 10D | NL | X | MIXED POP - "U31, U32" U31 U32 9 of 20 boards - Install U31 U32 part number BU-64863H8-102 (SN: 0001 – 0009). 1 of 20 boards - Install U31 U32 part number HI-62203PBT (SN: 0010) DNI FOR SN 0011 - 0020 For U13: 19 of 20 boards – Install U13 part number AS4C256M16D3LB-12BAN (SN: 0001 – 0009 and 0011 – 0020) 1of 20 boards – Install U13 part number MT41K256M16TW-107 AAT:P TR (SN: 0010) |  |  | 8/5 - BOT 8:00 8/5 - PAUSE 12:30 8/7 - TOP 8:30 8/7 - PAUSE 10:00 8/8 - TOP 6:00 8/8 - AOI 10:00 | 161 | 1233 | 2B 2T | 19 | 38 | FEDEX P | Integrated Consultants |  | 8/5 - BOT COMP IN 4.5 HRS | DOC REL 7/17 | 7/22 | 16938 | BOT 1ST | 2024-08-12 | 3 | 2024-08-07 | 10
2024-08-13 |  | 8/5 - SMT CLEAR 8/12 - J14 DUE THEN CLEAR 8/9 - KIT CLEAR |  |  | 1 |  |  | 127515 RONC 125211 | 30 | 8/14 3D | NL |  | *** 3 DAY TURN *** DEPANEL & SAND SHIP EXCESS MATERIAL W/ BOARDS |  |  | 8/5 - TOP 1:30 8/5 - AOI 4:30 | 21 | 229 | 1T | 37 | 1110 | FEDEX P | RollPros, LLC |  |  | DOC REL 8/3 | 8/5 | 4410.3 | TOP ONLY | 2024-08-09 | 1 |  | 3
2024-08-13 |  | 8/5 - SHORT PCB & #2 (C2..) NO ETA 8/8 - PCB DUE 8/9 - KIT CLEAR |  |  | 1 |  |  | 127466 NEW | 3 | 8/13 2D | NL | X | *** 2 DAY TURN *** "S1, S2, S3, S4" AFTER WASH DEPANEL DO NOT SHIP EXCESS MATL |  |  | 8/9 - BOT 1:00 8/9 - AOI 2:30 | 16 | 411 | 1B | 48 | 144 | UPS RED | Hermeus |  |  | DOC REL 8/5 | 8/5 | 6292 | BOT ONLY | 2024-08-13 | 1 | 2024-08-10 | 1.5
2024-08-13 |  | 8/5 - AWT PART CONF 8/6 - KIT CLEAR |  |  |  |  | 1 | 127187-1ST NEW | 10 | 8/13 5D | NL | X | XRAY & SAVE IMAGES |  |  | 8/9 - BOT 7:00 8/9 - PAUSE 10:00 8/10 - TOP 5:00 8/10 - AOI | 110 | 767 | 1B 2T | 35 | 350 | FEDEX P | GL Communications |  |  | DOC REL 8/1 | 8/5 | 4847 | BOT 1ST | 2024-08-13 | 2 | 2024-08-08
2024-08-13 |  | 8/8 - PCB DUE ¦ #63 (Q1..) DUE TODAY 8/7 - FEEDER SETUP READY DUE DATE 8/9 - PCB DUE 8/9 - KIT CLEAR |  |  | 1 |  |  | 127342 NEW | 93 | 8/13 8/12 1D | NL | X | ON HOLD *** 1 DAY TURN *** ***SEE TAD AFTER RELEASING & BEFORE FEEDER SET UP - PART BAGS/ITEM NUMBERS NEED TO BE CHECKED AGAINST AUDIT BOM AND SET UP SHEETS "SW1, LS1" AFTER WASH DO NOT SHIP EXCESS MATL |  |  | 8/9 - TOP 10:00 8/9 - PAUSE 11:00 8/12 - TOP 8:00 8/12 - AOI 2:00 | 60 | 162 | 2T | 5 | 465 | FEDEX P | Ergotron, Inc. |  | 8/9 - NT LOCATIONS HAVE PASTE LAYER, BUT NO PADS 8/12 - OKAY TO RUN | DOC REL 7/30 | 8/1 | 59564.62 | TOP ONLY |  | 1 |  | 7
2024-08-12 |  | 8/7 - KIT CLEAR |  |  | 1 |  |  | 126796 NEW | 500 | 8/12 3D | NL | X | *** 3 DAY TURN *** XRAY & SAVE IMAGES DEPANEL |  |  | 8/8 - TOP 2:00 8/8 - BOT 4:00 8/9 - AOI 7:00 | 6 | 8 | 1B 1T | 0 | 0 | FEDEX P | Procter & Gamble Company |  |  | DOC REL 8/7 | 8/7 | 5275 | bot 1st TOP 1ST | 2024-08-12 | 2 | 2024-08-07 | 3
2024-08-12 |  | 8/5, 8/7,, 8/9 - PCB'S DUE 8/9 - KIT CLEAR |  |  |  |  | 1 | 127476 NEW | 20 | 8/12 1D | NL | X | *** 1 DAY TURN *** TRIM LEADS TO 2.0 MAX HEIGHT PER ECO DEPANEL & SAND DO NOT SHIP EXCESS MATL ***SPLIT SHIPMENT - QTY 10 TO ERGOTRON - QTY 10 TO ENOVATE |  |  | 8/9 - TOP 9:30 8/9 - AOI 12:00 | 16 | 33 | 1T | 8 | 160 | FEDEX P | Ergotron, Inc. |  |  | DOC REL 8/2 | 8/5 | 8790 | TOP ONLY | 2024-08-12 | 1 | 2024-08-09 | 2.5
2024-08-12 |  | Short #23 (C190), #47 (47) U31 & #103 (R527) AWT PART CONF the rest 7/22 – PCB due date 7/29 - KIT CLEAR |  |  | 3 |  |  | 125391-1 PAR NEW | 18 | 8/12 10D | NL | X | MIXED POP - "U31, U32" U31 U32 9 of 20 boards - Install U31 U32 part number BU-64863H8-102 (SN: 0001 – 0009). 1 of 20 boards - Install U31 U32 part number HI-62203PBT (SN: 0010) DNI FOR SN 0011 - 0020 For U13: 19 of 20 boards – Install U13 part number AS4C256M16D3LB-12BAN (SN: 0001 – 0009 and 0011 – 0020) 1of 20 boards – Install U13 part number MT41K256M16TW-107 AAT:P TR (SN: 0010) |  |  | 8/5 - BOT 8:00 8/5 - PAUSE 12:30 8/7 - TOP 8:30 8/7 - PAUSE 10:00 8/8 - TOP 6:00 8/8 - AOI 10:00 | 161 | 1233 | 2B 2T | 19 | 342 | FEDEX P | Integrated Consultants |  | 8/5 - BOT COMP IN 4.5 HRS | DOC REL 7/17 | 7/22 | 16938 | BOT 1ST | 2024-08-12 | 3 | 2024-08-07 | 10
2024-08-12 |  | 8/8 - KIT CLEAR |  |  |  |  | 1 | 125902-RMA RMA | 2 | ASAP | NL | X | CUI CLASS 3 SN21: REFLOW AND XRAY U76's A27 & A28 (REMOVE AND RE-BALL IF NEEDED) SN22: XRAY U1, U2 & U3 P/N LTM4638IY#PBF AND REFLOW/REPLACE PARTS AS NEEDED |  |  | BACK | 151 | 1632 | 1B 2T | 45 | 90 | FEDEX P | Aeronix Inc |  |  | DOC REL 6/11 | 6/13 | 63214.2 | BOT 1ST | 2024-06-27 | 2 | 2024-06-21 | 19
2024-08-09 |  | 8/8 - KIT CLEAR |  |  | 2 |  |  | 127470 NEW | 10 | 8/9 1D | NL | X | *** 1 DAY TURN *** ON HOLD "SW1, SW2" AFTER WASH TRIM LEADS TO 2.0 MAX HEIGHT PER ECO DEPANEL & SAND |  |  | 8/9 - TOP 9:00 8/9 - AOI 10:30 | 27 | 81 | 1T | 6 | 60 | FEDEX P | Ergotron, Inc. |  |  | DOC REL 8/8 | 8/8 | 8316 | TOP ONLY | 2024-08-09 | 1 |  | 1.5
2024-08-09 |  | 8/5 - SHORT PCB, #20 (U205) & #35 (J102) WITH NO ETA 8/7 - PCB DUE 8/8 - KIT CLEAR |  |  | 1 |  |  | 127482 NEW | 20 | 8/9 1D | NL | X | *** 1 DAY TURN *** DEPANEL & SAND DO NOT SHIP EXCESS MATL ***SPLIT SHIPMENT - QTY 10 TO ERGOTRON - QTY 10 TO ENOVATE |  |  | 8/8 - TOP 10:00 8/8 - AOI 2:00 | 66 | 334 | 1T | 4 | 80 | FEDEX P | Ergotron, Inc. |  |  | DOC REL 8/2 | 8/5 | 29360 | TOP ONLY | 2024-08-09 | 1 | 2024-08-07 | 4
2024-08-09 |  | 7/10 - SMT CLEAR 7/12 - CUSTOMER SENDING REPLACEMENT FOR "U11" - ORIG SENT BY CUST WAS WRONG PART NUMBER 7/16- MISSING VSCORE PCB'S SEND BACK TO ROYAL 7/17 - ROYAL NEEDS PARTS REMOVED IN ORDER TO ADD THE VSCORE. SENDING PCB'S BACK TO ALTA 8/2 - KIT CLEAR |  |  | 1 |  |  | 126289-2 BAL NEW | 246 | 8/9 8/29 20D | NL | X | QTY 28 PANELS MISSING VSCORE - 7/16 SENT TO ROYAL TO ADD VSCORE AFTER ROYAL DEPANEL ONLY 2 PANELS, INSPECT ALL COMPONENTS AROUND TOP SIDE AND BOT SIDE EDGES FOR CRACKING/DAMAGE - SHIP THE 4 DEPANELED BOARDS TO: Sparx Engineering ATTN: Nathan Christensen 3110 Southfork Pkwy Manvel, TX 77578 LEAD PROCESS "S4" ADHESIVE REQUIRED PER ECO NO SOLDER ALLOWED ON TEST POINTS "L2, P3, BR3" ARE BI-DIRECTIONAL "S2, U11, L2" AFTER WASH DEPANEL |  |  | 7/11 - BOT 8:30 7/12 - TOP 9:00 7/15 - AOI 8:30 | 69 | 211 | 2B 2T | 14 | 3444 | FEDEX GRD | Allthenticate |  | 54 BOARDS (28 PANELS) W/O V-SCORE | DOC REL 6/21 | 7/10 | 12595.2 | BOT 1ST | 2024-07-31 | 2 | 2024-07-10 | 16
2024-08-09 |  | 8/7 - KIT CLEAR |  |  |  |  | 1 | 127495 NEW | 5 | 8/9 1D 3 | NL | X | ON HOLD - AWT PART CONF *** HOT! EXPEDITE! LEAD PROCESS DEPANEL |  |  | 8/8 - TOP 1:30 8/8 - AOI 3:30 | 29 | 309 | 1T | 43 | 215 | FEDEX P | Hubble Network |  |  | DOC REL 8/7 | 8/7 | 4805.3 | TOP ONLY | 2024-08-08 | 1 | 2024-08-07 | 2
2024-08-08 |  | 7/12 - WILL CLEAR AFTER CUSTOMER OKAY ON SOLDER SAMPLE 7/16 - KIT CLEAR |  |  | 1 |  |  | 123003 NEW | 79 | 8/13 20D | NL | X | "U3, U4, U5" AFTER WASH DEPANEL |  |  | 8/1 - TOP 10:00 8/1 - AOI 12:00 | 19 | 51 | 1T | 3 | 237 | FEDEX P | Biomeme, Inc. |  |  | DOC REL 6/26 | 7/12 | 2627.04 | TOP ONLY | 2024-08-13 | 1 | 2024-08-01
2024-08-08 |  | 8/1 - SHORT PCB & #18 (D10...) WITH NO DUE DATE 8/5 - PCB DUE 8/6 - PCB DUE 8/7 - PCB DUE |  |  | 1 |  |  | 127445 NEW | 20 | 8/8 1D | NL | X | *** 1 DAY TURN *** "U31" AFTER WASH DEPANEL & SAND DO NOT SHIP EXCESS MATL ***SPLIT SHIPMENT - QTY 10 TO ERGOTRON - QTY 10 TO ENOVATE |  |  | 8/7 - BOT 10:00 8/7 - TOP 1:00 8/7 - AOI 4:00 | 58 | 187 | 1B 1T | 4 | 80 | FEDEX P | Ergotron, Inc. |  |  | DOC REL 8/1 | 8/1 | 11719 | BOT 1ST | 2024-08-09 | 2 | 2024-08-08 | 6
2024-08-08 |  | 8/6 - PCB DUE 8/6 - KIT CLEAR |  |  |  |  | 1 | 127385 NEW | 30 | 8/8 2D | NL | X | *** 2 DAY TURN *** "U43" AFTER WASH POST BAKE 30 MIN IF BOARDS ARE WASHED DEPANEL & ***SAND DO NOT SHIP EXCESS MATL |  |  | 8/6 - BOT 11:30 8/6 - TOP 2:00 8/7 - AOI 1:00 | 173 | 600 | 1B 3T | 22 | 660 | FEDEX P | Ergotron, Inc. |  |  | DOC REL 7/30 | 7/31 | 47120 | BOT 1ST | 2024-08-08 | 5 |  | 11
2024-08-07 |  | 7/31 - PCB DUE (PCB'S LATE - 4D TURN IS OK) 8/1 - KIT CLEAR |  |  | 1 |  |  | 126510 NEW | 15 | 8/7 4D | NL | X | ***AS9100 FAIR REQ*** TRIM LEADS - MAX LEAD PROTRUSION TO BE .03 |  |  | 8/3 - BOT 9:00 8/3 - TOP 8/5 - AOI | 71 | 376 | 1B 1T | 1 | 15 | FEDEX P | Chelton Avionics, Inc. |  |  | DOC REL 7/25 | 7/25 | 4400 | BOT SIDE 1ST | 2024-08-07 | 2 | 2024-08-01
2024-08-07 |  | 8/2 - SHORT PCB W/ NO ETA 8/5 or 8/6 - PCB DUE DATE 8/6 - KIT CLEAR |  |  | 1 |  |  | 127452 NEW | 20 | 8/7 1D | NL | X | *** 1 DAY TURN *** "SW2, SW3" AFTER WASH INSTALL "F1 & FH1" TOGETHER DEPANEL & SAND DO NOT SHIP EXCESS MATL ***SPLIT SHIPMENT - QTY 10 TO ERGOTRON - QTY 10 TO ENOVATE |  |  | 8/6 - BOT 8:30 8/6 - TOP 10:00 8/6 - AOI 2:30 | 105 | 358 | 1B 2T | 9 | 180 | FEDEX P | Ergotron, Inc. |  |  | DOC REL 8/1 | 8/2 | 21304 | BOT 1ST | 2024-08-07 | 2 | 2024-08-05 | 6
2024-08-07 |  | 8/5 - PCB DUE 8/6 - PCB DUE |  |  | 1 |  |  | 127468 NEW | 20 | 8/7 1D | NL | X | *** 1 DAY TURN *** "PZ1, SW2" AFTER WASH JUMPER REQ @ "J10" DEPANEL & SAND DO NOT SHIP EXCESS MATL ***SPLIT SHIPMENT - QTY 10 TO ERGOTRON - QTY 10 TO ENOVATE |  |  | 8/6 - BOT 3:00 8/7 - TOP 6:00 8/7 - AOI 9:00 | 88 | 340 | 1B 1T | 14 | 280 | FEDEX P | Ergotron, Inc. |  |  | DOC REL 8/2 | 8/5 | 16273 | BOT 1S | 2024-08-07 | 2 | 2024-08-07 | 4.5
2024-08-07 |  | 8/1 - PCB DUE DATE ¦ SHORT #52(U26..) WITH NO ETA 7/31 - KIT CLEAR |  |  | 1 |  |  | 127034-1st NEW | 4 | 8/7 5D | NL | X | "J1" LEAVE PASTE ON CENTER PAD "SW1, SW2, SW3, BZ1, J43, U22, U45" AFTER WASH MOUNT ALL COMPONENTS FLUSH TO PCB DEPANEL |  |  | 8/1 - BOT 1:30 8/2 - TOP 8:30 8/2 - PAUSE 9:30 8/2 - TOP 10:30 8/2 - AOI 4:30 | 150 | 520 | 1B 3T | 40 | 160 | FEDEX P | MPR Associates Inc |  |  | DOC REL 7/29 | 7/30 | 6227 | BOT 1ST | 2024-08-07 | 5 | 2024-08-02 | 10
2024-08-07 |  | 7/31 - KIT CLEAR |  |  | 1 |  |  | 127246 NEW | 66 | 8/7 5D | NL | X | NO VENDOR MARKINGS OR in-house LABELS LABELS REQ PER ECO #2 |  |  | 8/1 - TOP 12:30 8/1 - PAUSE 1:30 8/3 - TOP 6:00 8/3 - AOI 9:00 | 29 | 126 | 1T | 5 | 330 | FEDEX P | John Hopkins University Applied Physics Lab |  | 8/1 - AWT ARRAY FILE | DOC REL 7/30 | 7/31 | 3674.14 | TOP ONLY | 2024-08-07 | 1 | 2024-08-05 | 4
2024-08-06 |  | 8/2 - KIT CLEAR | [5 empty] | 127573-1 PAR RWK 126350 | 10 | ASAP | - |  | 1. Remove qty 11 T/H per board 2. Place missing connectors onto J11, J12, J18 & J19, cover with foil to protect certain areas and reflow 3. Re-solder qty 11 T/H per board 4. Wash 5. Re-inspect 6. Photos of rework area required before shipping |  |  | BACK |  |  |  |  | 0 | FEDEX P | Integrated Consultants |  |  | NO DOC. | 8/2 | 1250
2024-08-06 |  | 8/5 - PCB'S DUE 8/6 - PCB DUE 8/6 - KIT CLEAR |  |  |  |  | 1 | 127472 NEW | 20 | 8/7 1D | NL | X | *** 1 DAY TURN *** DEPANEL & SAND DO NOT SHIP EXCESS MATL ***SPLIT SHIPMENT - QTY 10 TO ERGOTRON - QTY 10 TO ENOVATE |  |  | 8/6 - TOP 8:30 8/6 - AOI 10:30 | 1 | 3 | 1T | 1 | 20 | FEDEX P | Ergotron, Inc. |  |  | DOC REL 8/2 | 8/5 | 7540 | TOP ONLY | 2024-08-07 | 1 |  | 2
2024-08-06 |  | 8/5 - PCB'S DUE 8/6 - PCB DUE 8/6 - KIT CLEAR |  |  |  |  | 1 | 127474 NEW | 20 | 8/7 1D | NL | X | *** 1 DAY TURN *** DEPANEL & SAND DO NOT SHIP EXCESS MATL ***SPLIT SHIPMENT - QTY 10 TO ERGOTRON - QTY 10 TO ENOVATE |  |  | 8/6 - TOP 10:00 8/6 - AOI 12:00 | 18 | 26 | 1T | 2 | 40 | FEDEX P | Ergotron, Inc. |  |  | DOC REL 8/2 | 8/5 | 10370 | TOP ONLY | 2024-08-07 | 1 |  | 2
2024-08-06 |  | 8/1 - SHORT PCB W/ NO ETA 8/5 - PCB DUE 8/5 - KIT CLEAR |  |  |  |  | 1 | 127450 NEW | 20 | 8/6 1D | NL | X | *** 1 DAY TURN *** HAND-PLACE J1 & J2 (SMT) POST BAKE 30 MIN IF BOARDS ARE WASHED DEPANEL & SAND DO NOT SHIP EXCESS MATL ***SPLIT SHIPMENT - QTY 10 TO ERGOTRON - QTY 10 TO ENOVATE |  |  | 8/5 - TOP 1:30 8/5 - AOI 3:30 | 14 | 56 | 1T | 3 | 60 | FEDEX P | Ergotron, Inc. |  |  | DOC REL 8/1 | 8/1 | 10610 | TOP ONLY | 2024-08-06 | 1 |  | 2
2024-08-06 |  | 7/16 - KIT CLEAR |  |  | 2 |  |  | 123006 ROWC 110512 | 84 | 8/13 20D | NL | ROWC | ON HOLD - 7/26 WTG FOR ARRAY FILES ON MON 7/29 FAIR REQUIRED DO NOT SKIP AOI DEPANEL |  |  | 7/25 - TOP 8:30 7/25 - PAUSE 9:00 8/1 - TOP 8:00 8/1 - AOI 11:00 | 11 | 21 | 1T | 2 | 168 | FEDEX P | Biomeme, Inc. |  | 7/25 - STENCIL DOESN'T MATCH PANEL | DOC REL 7/3 | 7/16 | 1854.2 | TOP ONLY | 2024-08-13 | 1 | 2024-08-01 | 3
2024-08-05 |  | 7/19 - SHORT #93 (J28) -- NO ETA 7/24 - #93(J28) & #107(J5) due 7/24 - KIT CLEAR |  |  |  |  | 2 | 126673 NEW | 3 | 8/7 10D | NL | X | ECO #7 waived LEAD-FREE NO CLEAN (SAC 305) PER ECO #3 "B1, BUZ1, LS1, U33, REL1, REL2" AFTER WASH SPECIAL PACKAGING REQ PER ECO #13 DEPANEL |  |  | 7/29 - BOT 6:00 7/29 - TOP 9:00 7/30 - AOI 12:00 | 170 | 1043 | 1B 3T | 61 | 183 | FEDEX P | DePuy Synthes Products, LLC |  |  | DOC REL 7/18 | 7/19 | 8920.6 | bot 1st | 2024-08-07 | 3 | 2024-07-29 | 14
2024-08-05 |  | 7/26 - KIT CLEAR (7/30 DAY 1 -ANNE) |  |  |  |  | 1 | 123853-2ND ROWC 1st Article | 9 | 8/5 5D | NL | ROWC | XRAY & SAVE IMAGES OF ALL BGA'S ***DEPANEL & SAND KO LABELS REQUIRED |  |  | 8/1 - TOP 12:30 8/2 - AOI 10:00 | 88 | 350 | 2T | 0 | 0 | FEDEX P | X-Microwave (A Quantic Company) |  |  | DOC REL 7/26 | 7/29 | 3048.84 | TOP ONLY | 2024-08-05 | 1 | 2024-08-01 | 7
2024-08-05 |  | 7/30 - SHORT PCB W/NO ETA 8/1 - PCB DUE 8/1 - KIT CLEAR |  |  | 2 |  |  | 127428 NEW | 68 | 8/5 2D | X | X | *** 2 DAY TURN *** #3 (P2, P6) & #4 (P3-P5) SMT INSTALL T/H ONLY |  |  | 8/2 - TOP 9:30 8/2 - AOI 12:00 | 0 | 0 | - | 7 | 476 | FEDEX P | Ergotron, Inc. |  |  | DOC REL 7/30 | 7/30 | 13328 | TOP ONLY | 2024-08-05 | 1
2024-08-05 |  | 7/25 - PCB DUE THEN SMT CLEAR 7/24 - KIT CLEAR |  |  |  |  | 1 | 126982 NEW | 15 | 8/5 8D | NL | X | INSTALL FUSES |  |  | 7/27 - BOT 6:00 7/27 - TOP 12:00 7/29 - AOI 2:30 | 123 | 1959 | 1B 2T | 68 | 1020 | FEDEX 2D | Plexus Engineering Solutions |  |  | DOC REL 7/12 | 7/15 | 17482.35 | BOT 1ST BIG BOARD | 2024-07-31 | 2 | 2024-07-24 | 16
2024-08-02 |  | 7/10 - SMT CLEAR 7/12 - CUSTOMER SENDING REPLACEMENT FOR "U11" - ORIG SENT BY CUST WAS WRONG PART NUMBER 7/16- MISSING VSCORE PCB'S SEND BACK TO ROYAL 7/17 - ROYAL NEEDS PARTS REMOVED IN ORDER TO ADD THE VSCORE. SENDING PCB'S BACK TO ALTA 8/2 - KIT CLEAR |  |  | 1 |  |  | 126289-1 PAR NEW | 4 | 8/29 20D | NL | X | QTY 28 PANELS MISSING VSCORE - 7/16 SENT TO ROYAL TO ADD VSCORE AFTER ROYAL DEPANEL ONLY 2 PANELS, INSPECT ALL COMPONENTS AROUND TOP SIDE AND BOT SIDE EDGES FOR CRACKING/DAMAGE - SHIP THE 4 DEPANELED BOARDS TO: Sparx Engineering ATTN: Nathan Christensen 3110 Southfork Pkwy Manvel, TX 77578 LEAD PROCESS "S4" ADHESIVE REQUIRED PER ECO NO SOLDER ALLOWED ON TEST POINTS "L2, P3, BR3" ARE BI-DIRECTIONAL "S2, U11, L2" AFTER WASH DEPANEL |  |  | 7/11 - BOT 8:30 7/12 - TOP 9:00 7/15 - AOI 8:30 | 69 | 211 | 2B 2T | 14 | 56 | FEDEX GRD | Allthenticate |  | 54 BOARDS (28 PANELS) W/O V-SCORE | DOC REL 6/21 | 7/10 | 2048 | BOT 1ST | 2024-07-31 | 2 | 2024-07-10 | 16
2024-08-02 |  | 7/29 - PCB DUE 7/29 - KIT CLEAR |  |  | 1 |  |  | 126794-1 PAR NEW | 18 | 8/2 8/5 5D | NL | X | *** EXPEDITE *** EXTRA TIME NEEDED TO RUN THIS JOB (JOE) "L49, 50, 51" AFTER WASH DEPANEL |  |  | 7/30 - BOT 1:30 7/31 - TOP 11:30 8/1 - AOI 9:30 | 72 | 2241 | 2B 1T | 10 | 180 | FEDEX GRD | Alpheus Medical, Inc. |  |  | DOC REL 7/1 | 7/24 | 18879 | top or bot 1st bot 1st | 2024-08-05 | 2 | 2024-07-29 | 11
2024-08-02 |  | 7/12 - WILL CLEAR AFTER CUSTOMER OKAY ON SOLDER SAMPLE 7/16 - KIT CLEAR |  |  |  |  | 2 | 123004 NEW | 133 | ASAP 7/31 7/30 10D | NL | X | VERIFY STENCIL REQUIREMENTS PER ECO #2 WIRE ASSY REQUIRED PER ECO #4 - KAPTON TAPE REQUIRED ON BACK SIDE OF SOLDERED WIRES MAKE SURE BOARDS ARE FREE OF OIL, DUST & DEBRIS |  |  | 7/22 - BOT 9:30 7/22 - TOP 11:00 7/22 - AOI 1:30 | 12 | 15 | 1B 1T | 8 | 1064 | FEDEX P | Biomeme, Inc. |  | 7/25 - REQ EXTERNAL COMP TO BUILD WIRES -- DUE 7/29 - 7/30 | DOC REL 7/3 | 7/12 | 5006 | bot 1st | 2024-07-30 | 2 | 2024-07-23 | 4
2024-08-01 |  | 7/30 - KIT CLEAR |  |  | 1 |  |  | 126194-RWK RWK | 18 | ASAP | NL | ROWC | J2 P/N IS ASP-236298-02 J5 P/N IS SSM-130-F-DV R&R INCORRECT PARTS AND INSTALL CORRECT PARTS |  |  | BACK | 54 | 575 | 1B 1T | 45 | 810 | FEDEX P | NASA - John F Kennedy Space Center |  |  | DOC REL 7/8 | [5 empty] | 2024-07-10 | 6.5
2024-08-01 |  | 7/26 - SHORT PCB 7/30 - PCB DUE 7/29 - KIT CLEAR |  |  |  |  | 1 | 127145 (AA XFER) NEW | 5 | (8/1) 3D | NL | X | *** 3 DAY TURN *** NO CLEAN PROCESS "U2" - PIN 5 NOT USED DEPANEL ***SHIP TO ADVANCED ON 8/1 |  |  | 7/30 - TOP 5:00 7/30 - AOI 11:00 | 41 | 75 | 1T | 31 | 155 | FEDEX P | Lake Shore Cryotronics, Inc. |  |  | DOC REL 7/25 | 7/25 | 1500 | TOP ONLY | 2024-08-01 | 2 | 2024-07-30 | 6
2024-08-01 |  | 7/22 - SHORT PCB (NO ETA) 7/23 - OTHER SHORTAGES DUE 7/25 - KIT CLEAR |  |  | 1 |  |  | 125349 NEW | 20 | 8/1 5D | NL | X | ***PLEASE SEE TAD BEFORE RELEASING*** ***REBALL "U12,U19,U30,U32" PRIOR TO SMT*** ***ALL MUST WEAR GLOVES*** ANY RWK MUST BE APPROVED BY THE CUSTOMER ANY CHANGES/SUBSTITUTIONS MUST BE APPROVED BY THE CUSTOMER DNI J4 |  |  | 7/29 - BOT 8:00 7/29 - PAUSE 10:30 7/29 - BOT 6:00 7/29 - TOP 9:30 7/30 - AOI 3:30 | 164 | 946 | 2B 2T | 21 | 420 | FEDEX P | Test Range Systems |  |  | DOC REL 7/19 | 7/22 | 18312 | TOP OR BOTTOM? top 1st | 2024-08-01 | 2 | 2024-07-29
2024-08-01 |  | 7/24 - SHORT PCB (NO ETA) ¦ AWT PART CONFIRM #22 (L200..) 7/30 - PCB DUE 7/30 - KIT CLEAR |  |  |  |  | 1 | 127206 NEW | 61 | 8/1 2D | NL | X | *** 2 DAY TURN *** DEPANEL & SAND - REMOVE BURRS & SHARP EDGES |  |  | 7/31 - BOT 8:00 7/31 - TOP 2:00 7/31 - AOI 12:00 | 41 | 212 | 1B 1T | 26 | 1586 | FEDEX P | Ergotron, Inc. |  | 7/29 - VERIFY NEW #22 (P/N PA4344.562NLT): NEED ROBERT TO VERIFY IF IT FITS | DOC REL 7/22 | 7/24 | 20733.5 | BOT 1ST | 2024-08-01 | 2 | 2024-07-30 | 14
2024-07-31 |  | 7/29 - PCB'S DUE 7/26 - KIT CLEAR |  |  | 1 |  |  | 126358 NEW | 50 | 7/31 4D | NL | X | NO CLEAN PROCESS DEPANEL |  |  | 7/29 - BOT 7/29 - AOI | 1 | 1 | 1B | 0 | 0 | FEDEX P | Daxsonics Ultrasound Inc. |  |  | DOC REL 7/25 | 7/25 | 3600 | top only | 2024-07-31 | 1 | 2024-07-30
2024-07-31 |  | 7/29 - PCB'S DUE 7/26 - KIT CLEAR |  |  | 2 |  |  | 126359 NEW | 50 | 7/31 4D | NL | X | NO CLEAN PROCESS DEPANEL |  |  | 7/29 - TOP 7/29 - AOI | 1 | 1 | 1T | 0 | 0 | FEDEX P | Daxsonics Ultrasound Inc. |  |  | DOC REL 7/25 | 7/25 | 2900 | top only | 2024-07-31 | 1 | 2024-07-30
2024-07-31 |  | 7/16 - CLOSING SHORT ¦ KIT CLEAR |  |  | 2 |  |  | 125336-2 BAL NEW | 22 | 7/31 8/7 15D | NL | X | NO DEPANEL - TEST COACH ON HOLD (board REV req TAD review) - run 22 & mark with correct REV w/ marker send waiver w/ shipment ***AS9100 (CUI)*** print attachment and ship w/ boards Build QTY 48 5-day turn: qty 25 ship to customer 15-day turn: qty 22 ship to Test Coach SMT install shield AS9100 FAIR REQUIRED "SW11000" AFTER WASH "P22000" PRESS FIT |  |  | 7/26 - BOT 12:30 7/27 - TOP 7/27 - AOI | 128 | 896 | 1B 2T | 3 | 66 | FEDEX P | Chelton Avionics, Inc. |  |  | DOC REL 5/3 | 7/16 | 6410.8 | TOP OR BOTTOM? BOT 1ST | 2024-07-31 | 2 | 2024-07-29
2024-07-31 |  | 7/30 - PCB DUE 7/30 - KIT CLEAR |  |  |  |  | 1 | 127339 NEW | 45 | 7/31 1D | NL | X | *** 1 DAY TURN *** DEPANEL & SAND |  |  | 7/30 - BOT 10:00 7/30 - TOP 2:30 7/31 - AOI 8:00 | 65 | 172 | 1B 1T | 2 | 90 | FEDEX P | Ergotron, Inc. |  |  | DOC REL 7/26 | 7/29 | 32170 | BOT 1ST | 2024-07-31 | 2 | 2024-07-30 | 6
2024-07-31 |  | 7/19 - KIT CLEAR |  |  | 3 |  |  | 126917 NEW | 96 | 7/31 8/2 10D | NL | X | on hold share parts w/ B126918 (pcb look the same) XRAY, SAVE & SEND TO CUSTOMER PER ECO #2 "M200" AFTER WASH DEPANEL & SAND (RIGID FLEX) |  |  | 7/24 - BOT 11:00 7/24 - TOP 1:00 7/24 - PAUSE 3:30 7/27 - TOP 7/27 - AOI | 7 | 8 | 1B 1T | 1 | 96 | DHL INTERNTIONAL | Person-Aiz AS - fomerly Listen AS |  | 7/24 - PART (M200) ISSUE | DOC REL 7/12 | 7/19 | 4284 | BOT 1ST | 2024-07-31 | 2 | 2024-07-29
2024-07-31 |  | 7/19 - KIT CLEAR |  |  | 4 |  |  | 126918 NEW | 96 | 7/31 8/2 10D | NL | X | on hold share parts w/ B126917 (pcb look the same) XRAY, SAVE & SEND TO CUSTOMER PER ECO #2 "M200" AFTER WASH DEPANEL & SAND (RIGID FLEX) |  |  | 7/24 - BOT 1:30 7/24 - PAUSE 2:30 7/27 - TOP 7/27 - AOI | 7 | 8 | 1B 1T | 1 | 96 | DHL INTERNTIONAL | Person-Aiz AS - fomerly Listen AS |  |  | DOC REL 7/12 | 7/19 | 4284 | BOT 1ST | 2024-07-31 | 2 | 2024-07-29
2024-07-31 |  | 7/16 - KIT CLEAR |  |  | 1 |  |  | 123007 ROWC 110511 | 162 | 7/31 10D | NL | ROWC | DEPANEL |  |  | 7/29 - TOP 10:30 7/29 - AOI 4:30 | 13 | 28 | 1T | 2 | 324 | FEDEX P | Biomeme, Inc. |  |  | DOC REL 7/3 | 7/17 | 2901.02 | TOP ONLY | 2024-07-31 | 1 | 2024-07-25 | 2.5
2024-07-31 |  | 7/13 - EXPECTED SMT CLEAR DATE 7/15 - SMT CLEAR 7/16 - KIT CLEAR |  |  | 1 |  |  | 125704 NEW | 54 | 7/31 8/6 15D | NL | X | ***ADD SOLDER PASTE PER ECO #2 HARDWARE AND TORQING REQUIRED DEPANEL ***SHIP QTY 3 OF 54 DIRECT TO THE CUSTOMER: Allocortech, Inc. 440 N Commerce Ave Waynesboro, VA 22980-4029 |  |  | 7/24 - BOT 6:00 7/24 - pause 10:00 7/25 - BOT 6:00 7/25 - TOP 1:30 7/26 - AOI 11:00 | 102 | 612 | 2B 2T | 8 | 432 | FEDEX P | Industrialex Manufacturing |  | 7/22 - MANY SMT STRIPS & LOOSE PARTS (EXTRA TIME NEEDED FOR SETUPD AND RUN 7/25 - SOLDER QUALITY ISSUES | DOC REL 6/27 | 7/12 | 8852.56 | BOT 1ST | 2024-07-31 | 2 | 2024-07-24
2024-07-30 |  | 7/29 - PCB DUE 7/26 - KIT CLEAR |  |  | 1 |  |  | 127107 (AA XFER) NEW | 5 | (7/31) 4D | NL | X | DEPANEL PACKAGE TO PREVENT DAMAGE |  |  | 7/29 - TOP 7/29 - AOI 3:00 | 35 | 85 | 1T | 6 | 30 | FEDEX P | Fresenius Kabi |  |  | DOC REL 7/25 | 7/25 | 1100 | top only | 2024-07-31 | 1 | 2024-07-30
2024-07-30 |  | 7/22 - PCB DUE 7/22 - KIT CLEAR |  |  | 1 |  |  | 126048 NEW | 45 | 7/31 8/5 10D | NL | X | DEPANEL |  |  | 7/24 - TOP 10:00 7/24 - AOI 12:00 | 10 | 23 | 1T | 31 | 1395 | FEDEX P | Tennessee Valley Authority |  |  | DOC REL 7/15 | 7/17 | 5379.3 | TOP ONLY | 2024-07-30 | 1 | 2024-07-24 | 2
2024-07-30 |  | 7/22 - SHORT PCB (NO ETA) 7/24 - PCB DUE 7/25 - PCB DUE 7/25 - KIT CLEAR |  |  |  |  | 1 | 127160 NEW | 15 | 7/30 3D | NL | X | *** 3 DAY TURN *** "SW3,SW4" AFTER WASH DEPANEL *EXTRA CARE/PACKAGING REQUIRED PER ECO |  |  | 7/25 - TOP 12:30 7/26 - AOI 8:00 | 42 | 316 | 1T | 86 | 1290 | FEDEX P | Biolog Inc. |  |  | DOC REL 7/19 | 7/22 | 5905 | TOP ONLY | 2024-07-30 | 1 | 2024-07-25
2024-07-30 |  | 7/16 - KIT CLEAR |  |  |  |  | 1 | 126563-2nd RONC 1st Article | 149 | 7/30 10D | NL | RONC | LEAD PROCESS "S1" AFTER WASH DEPANEL |  |  | 7/18 - TOP 8:00 7/18 - AOI 1:00 | 13 | 37 | 1T | 54 | 8046 | UPS GRD | Hamilton Mfg. Corp |  |  | DOC REL 7/16 | 7/16 | 7019.39 | TOP ONLY | 2024-07-30 | 1 | 2024-07-18 | 5
2024-07-29 |  | 7/17 - PCB DUE SHORT #39 (U2) -- due 7/15 (THEN SMT CLEAR) 7/15 - SMT CLEAR 7/16 - KIT CLEAR |  |  | 1 |  |  | 125578 NEW | 54 | 7/31 8/6 15D | NL | X | LEAD FREE NO CLEAN PROCESS ***SEE ECO #6 - NO SOLDER IN VIA'S ALLOWED*** "J1" INSTALL & TORQUE PRIOR TO SOLDERING PER ECO #5 DEPANEL OK TO USE THE FOLLOW ALT PARTS: (C20) C0402C104K8RACTU (U16) TL431LIAEDBZRQ1 (U32) XCL206C333CR-G |  |  | 7/19 - TOP 12:30 7/19 - BOT 2:30 7/22 - AOI 2:30 | 85 | 337 | 2B 1T | 1 | 54 | FEDEX P | Industrialex Manufacturing |  | 7/18 - A LOT OF SMT STRIPS | DOC REL 6/28 | 7/11 | 5351.54 | TOP 1ST - STANDOFFS | 2024-08-06 | 2 | 2024-07-19 | 10
2024-07-29 |  | 7/11 - PCB DUE DATE ¦ SHORT #18 (U200..) & #19 (L201..) NO ETA 7/19 - PCB DUE 7/24 - KIT CLEAR |  |  |  |  | 2 | 126269 NEW | 15 | 7/29 3D | NL | X | *** 3 DAY TURN *** CUI CLASS 3 TRIM LEADS TO 0.06 MAX AS9100 FAIR REQUIRED |  |  | 7/26 - BOT 6:00 7/26 - TOP 12:30 7/26 - AOI 1:45 | 40 | 378 | 1B 1T | 0 | 0 | FEDEX P | Chelton Avionics, Inc. |  |  | DOC REL 7/2 | 7/8 | 5057 | BOT 1ST | 2024-07-29 | 2 | 2024-07-25
2024-07-29 |  | 7/26 - PCB DUE 7/26 - KIT CLEAR |  |  |  |  | 1 | 127181 NEW | 100 | 7/29 1D | NL |  | *** 1 DAY TURN *** CLASS 3 QTY 65 LOAD "U1" QTY 35 "U1" IS NO LOAD DEPANEL & SAND |  |  | 7/26 - TOP 12:00 7/26 - AOI 1:30 | 4 | 5 | 1T | 0 | 0 | UPS RED | Diversified Supply |  |  | DOC REL 7/24 | 7/25 | 5930 | TOP ONLY |  | 1
2024-07-29 |  | 7/19 - PCB DUE 7/16 - KIT CLEAR 7/16 - PCB'S SENT BACK TO ROYAL TO RE-DRILL MOUSE BITES |  |  |  |  | 1 | 126815 RONC 119012 | 25 | 7/29 7/23 5D | NL | RONC | ON HOLD DUE TO MOUSEBITE ISSUE BEFORE INSTALLING "NANO" FINAL QA INSPECT PARTS BELOW PER ECO #3 IF BOARDS WASHED, POST BAKE 30 MIN DEPANEL "FEM_HEAD" TRIM LEADS |  |  | 7/24 - TOP 9:30 7/24 - AOI 12:30 | 6 | 12 | 1T | 11 | 275 | FEDEX P | Industrialex Manufacturing |  | 7/17 - mousebites insufficient sized for proper breakage 7/22 - REC'D BOARDS FROM ROYAL | DOC REL 7/12 | 7/15 | 823.75 | TOP ONLY | 2024-07-29 | 1 | 2024-07-24 | 3
2024-07-29 |  | 7/12 - PCB & #43 (U3) DUE 7/12 - ONLY SHORT ONE "U3" - OK TO SKIP 7/15 - KIT CLEAR 7/18 - "U1" & "Q2 x12" WRONG PART RECEIVED. |  |  | 1 |  |  | 126350 NEW | 43 | 7/29 10D | NL | X | ON HOLD (WRONG PARTS) SHORT 1 PART #43 (U3) -- OK TO SKIP DEPANEL |  |  | 7/18 - BOT 8:30 7/18 - pause 11:00 7/23 - BOT 6:00 7/23 - TOP 9:00 7/24 - AOI 9:30 | 96 | 523 | 1B 1T | 11 | 473 | FEDEX P | Integrated Consultants |  | 7/18 - PARTS DOESN'T FIT: #99 (Q2,Q3..), #49 (U1) 7/22 - correct parts received 7/22 - VIA HOLES ON PADS, EXTRA SOLDER APPLIED BEFORE REFLOW | DOC REL 7/10 | 7/11 | 11067.2 | BOT 1ST | 2024-07-29 | 2 | 2024-07-19 | 14.5
2024-07-26 |  | 7/23 OR SOONER - PCB DUE 7/23 - KIT CLEAR |  |  |  |  | 1 | 126631 NEW | 2 | 7/26 3D | NL | X | *** 3 DAY TURN *** ITAR DEPANEL J3 MIX POP: 1 BOARD W/ P/N DCCM37SBSP 1 BOARD W/ P/N DCCM37SBSPN |  |  | 7/24 - BOT 11:30 7/24 - TOP 1:00 7/25 - AOI 10:30 | 154 | 1484 | 1B 3T | 80 | 160 | FEDEX P | Scientific Research Corporation |  |  | DOC REL 7/10 | 7/16 | 9930 | BOT 1ST | 2024-07-26 | 4 | 2024-07-24 | 8
2024-07-25 |  | 7/24 - KIT CLEAR | [5 empty] | 125612-RWK RWK | 7 | 7/25 1D | - |  | Remove U29 from board and hand-solder new part (AT17F040-30JU) onto U29 |  |  | BACK |  |  |  |  | 0 |  |  |  |  | NO DOC.
2024-07-25 |  | 5/22 - PCB DUE 5/21 - KIT CLEAR |  |  | 1 |  |  | 125711-1 PAR NEW | 60 | 7/25 10D | NL | X | DO NOT SHIP EARLY QTY 60 7/25/2024 QTY 60 8/27/2024 TRIM LEADS TO 0.98 PER ECO DEPANEL |  |  | 5/31 - TOP 11:00 6/1 - AOI 7:00 | 25 | 51 | 1T | 3 | 180 | FEDEX GRD | Frencken America Inc. |  |  | NO DOC. | 5/10 | 3113.6 | TOP ONLY | 2024-07-25 | 1 |  | 5.5
2024-07-24 |  | 7/24 - KIT CLEAR | [5 empty] | 125822 RWK | 15 | 7/24 1D | - |  | QTY OF BOARDS NEED RWK = 2 CLASS 3 We received 15 boards returning from Test coach, but only S/N: 042 & 045 need to be reworked. 1, S/N 042, R82 Nonwetting or De-wetting, please rework/touch-up. 2, S/N 045, Q20 Nonwetting or Defective, please rework/touch-up. After S/N 042 & 045 finished reworked, de-panel all 15 boards. Ship all 15 boards directly to Customer. |  |  | BACK |  |  |  |  | 0 |  |  |  |  | NO DOC.
2024-07-24 |  | 7/1 - SHORT PCB W/ NO ETA 7/17 - KIT CLEAR |  |  |  |  | 1 | 126578 NEW | 15 | 7/24 5D | NL | X | ***PRIOR TO SMT, RUN SOLDER SAMPLE THROUGH REFLOW TO CHECK FOR WARPAGE PER ECO #1 waived (joe) SEE eco #4 FOR "JMP1 & JMP2" ALL T/H COMPONENTS SHOULD BE MOUNTED FLUSH TO THE BOARD |  |  | 7/22 - BOT 6:00 7/22 - TOP 7/22 - AOI 10:00 | 28 | 56 | 1B 1T | 16 | 240 | FEDEX P | CACI |  | 7/18 - hold until Monday (Robert) PCB requires further testing | DOC REL 6/28 | 7/1 | 2946.5 | BOT 1ST | 2024-07-24 | 2 | 2024-07-22 | 4
2024-07-24 |  | 7/23 - PCB DUE 7/23 - KIT CLEAR |  |  |  |  | 1 | 127191 NEW | 25 | 7/24 1D | NL | X | *** 1 DAY TURN *** "PZ1, SW1" AFTER WASH CRITICAL PLACEMENT OF "D23, D27" PER ECO |  |  | 7/23 - BOT 12:00 7/24 - TOP 2:00 7/25 - AOI 9:30 | 85 | 342 | 1B 1T | 14 | 350 | FEDEX P | Ergotron, Inc. |  |  | DOC REL 7/18 | 7/22 | 20670 | BOT 1ST | 2024-07-24 | 2 | 2024-07-23 | 6
2024-07-24 |  | 7/17 - PCB DUE ¦ #82 (LTC400) ALSO DUE 7/19 - KIT CLEAR |  |  |  |  | 1 | 127012 NEW | 10 | 7/24 3D | NL | X | *** 3 DAY TURN *** WASH BOARDS WITHIN 8 HOURS OF SOLDERING OPERATIONS L101, L103 PLACE ORIENTATION (ECO) PLACE AFTER WASH: SW100,SW101,SW500,SW501,SW200, SW300,SW400,SW401,SW701,SW702, SW704,SW101,SW700,SW703 DEPANEL |  |  | 7/22 - TOP 9:30 7/23 - AOI 1:00 | 139 | 1004 | 3T | 36 | 360 | FEDEX P | Engenious Design |  |  | DOC REL 7/12 | 7/15 | 24036 | TOP ONLY BIG BOARD | 2024-07-24 | 3 | 2024-07-22 | 10
2024-07-23 |  | 7/25 - PCB DUE 7/19 - KIT CLEAR |  |  | 1 |  |  | 126280 ROWC 110896 | 200 | 7/26 5D | NL | ROWC | DEPANEL |  |  | 7/22 - TOP 1:00 7/23 - AOI 2:30 | 19 | 32 | 2T | 0 | 0 | FEDEX P | TMC / Technical Manufacturing Corp. |  |  | DOC REL 7/12 | 7/17 | 2640 | TOP ONLY | 2024-07-26 | 1 | 2024-07-22 | 1.5
2024-07-22 |  | 7/17 - PCB DUE 7/16 - KIT CLEAR |  |  | 1 |  |  | 126629 NEW | 75 | 7/23 5D | NL | X | *READ DWG NOTES & ECO PRIOR UPON RELEASING PER DRAWING - COMPONENT LEAD EXTENSION TO BE 0.140" MAX DISREGARD DWG NOTES 8 & 9, NO LABELS REQ PACKAGE REQUIRES 2 LABELS: DATE CODE & QTY #9 (Y1) & #21 (U12) OK TO USE USE ESD STICKERS PER ESD BAG |  |  | 7/17 - TOP 12:30 7/18 - AOI 10:00 | 39 | 115 | 1T | 4 | 300 | FEDEX P | Rheem Manufacturing Company |  |  | DOC REL 7/9 | 7/11 | 3628.75 | TOP ONLY | 2024-07-23 | 1 | 2024-07-17 | 6
2024-07-19 |  | 7/2 - SHORT PCB W/ NO ETA 7/11 - KIT CLEAR |  |  | 1 |  |  | 126814 ROWC 121693 | 20 | 7/25 10D | NL | ROWC | ***SMT TO ADD EXTRA SOLDER TO PADS W/ VIA HOLES LEAD PROCESS DEPANEL |  |  | 7/16 - TOP 9:30 7/16 - BOT 11:30 7/17 - AOI 9:30 | 71 | 199 | 1B 2T | 1 | 20 | FEDEX P | Ocean Aero, Inc. |  | VIA HOLES IN PCB -- (STILL HAVE INSUFFICIENT SOLDER FOR 1 LOCATION (R124) 7/16 - REFLOW ISSUE | DOC REL 7/1 | 7/2 | 3204 | TOP 1ST | 2024-07-25 | 2 | 2024-07-15 | 8
2024-07-19 |  | 7/16 - #2 (CONN1) DUE DATE 7/15 - KIT CLEAR |  |  |  |  | 1 | 126768 NEW | 400 | 7/22 5D | NL | X | *NO SOLDER ON DNI PADS - CHECK STENCIL PRIOR TO RUNNING XRAY & SAVE DEPANEL |  |  | 7/17 - TOP 10:00 7/17 - BOT 2:30 7/18 - AOI 10:00 | 3 | 4 | 1B 1T | 0 | 0 | FEDEX P | Procter & Gamble Company |  |  | DOC REL 7/1 | 7/9 | 4980 | TOP 1ST | 2024-07-22 | 2 | 2024-07-17 | 8
2024-07-19 |  | 7/18 - PCB DUE 7/15 - KIT CLEAR |  |  | 1 |  |  | 126532 NEW | 10 | 7/22 5D | NL | X | CLASS 3 DEPANEL & SAND AWT PART CONF #14 (C25..) EGPD101ELL361MK35H |  |  | 7/16 - BOT 12:30 7/17 - TOP 8:30 7/17 - AOI 2:30 | 64 | 448 | 1B 1T | 38 | 380 | FEDEX P | Parker Hannifin Corp |  |  | DOC REL 7/10 | 7/12 | 2998 | bot 1st | 2024-07-22 | 2 | 2024-07-16 | 10
2024-07-19 |  | 7/16 - PCB DUE 7/12 - KIT CLEAR |  |  |  |  | 1 | 126425 NEW | 15 | 7/19 5D | NL | X | DEPANEL J1 - OK TO PLACE AS IS |  |  | 7/16 - BOT 7:30 7/16 - TOP 9:00 7/16 - PAUSE 11:30 7/17 - TOP 6:00 7/17 - AOI 2:30 | 148 | 878 | 1B 3T | 29 | 435 | FEDEX P | Plexus Engineering Solutions |  | 7/16 - J1 MISSING PADS TO MATCH CONNECTOR LEGS (ok to place as is) | DOC REL 6/28 | 7/2 | 13342.15 | bot 1st | 2024-07-19 | 2 | 2024-07-15 | 14.5
2024-07-19 |  | 7/12 - KIT CLEAR |  |  |  |  | 2 | 124835-RMA RONC 124835 | 18 | 7/19 5D | NL | RONC | TREAT AS CLASS 3 REMAKE TO REPLACE DAMAGED BOARDS ***DO NOT DEPANEL - GIVE TO TAD ROTATE L2 LOCATIONS 90 DEGREES |  |  | 7/16 - BOT 2:00 7/17 - TOP 9:30 7/17 - AOI 2:30 | 17 | 79 | 1B 1T | 0 | 0 | FEDEX | SRI |  |  | DOC REL 7/10 | 7/12 |  | BOT OR TOP | 2024-07-19 | 2 | 2024-07-17 | 8
2024-07-18 |  | 7/15 - PCB DUE DATE ¦¦ SHORT #59 (LED3..) NO ETA 7/12 - KIT CLEAR |  |  | 1 |  |  | 126908 NEW | 30 | 7/19 5D | NL | X | NO CLEAN PROCESS "L3" AFTER WASH DEPANEL |  |  | 7/15 - BOT 8:30 7/15 - TOP 12:00 7/15 - PAUSE 2:00 7/16 - TOP 6:00 7/16 - AOI 10:00 | 82 | 327 | 1B 2T | 13 | 390 | UPS RED | Tintometer, Inc. |  | 7/15 - HAD TO MODIFY TOP SIDE OF STENCIL TO INCLUDE MISSING STANDOFF LOCATIONS | DOC REL 7/9 | 7/10 | 3654.7 | BOT 1ST | 2024-07-19 | 2 | 2024-07-12
2024-07-17 |  | 7/12 - PCB DUE THEN SMT CLEAR 7/12 - KIT CLEAR |  |  |  |  | 1 | 126817 NEW | 50 | 7/17 3D | NL | X | *** 3 DAY TURN *** J5 BTD MECH ASSY REQ OK TO USE: #19 (D2) SM4007PL-TP #22 (D1) SS1060FL_R1_00001 #28 (U6) R5F51305ADFL#10 #31 (L1) 0630CDMCCDS-100MC #34 (J5) PVP06-5,08 LABELS WAIVED |  |  | 7/15 - BOT 6:00 7/15 - TOP 8:00 7/15 - AOI 12:00 | 62 | 149 | 1B 1T | 23 | 1150 | FEDEX P | Rheem Manufacturing Company |  |  | DOC REL 7/10 | 7/11 | 4715 | BOT 1ST | 2024-07-18 | 2 | 2024-07-12 | 5
2024-07-16 |  | 7/8 - KIT MAYBE CLEAR; CUST SEND TWO NEW PARTS TO ADD 7/10 - KIT CLEAR |  |  | 1 |  |  | 126194-2nd ROWC 1st Article | 18 | 7/17 5D | NL | ROWC | ok to SMT SKIP J2 & J5 NO ECO NOTES ***CUSTOMER NOW WANTS TO LOAD "J2 & J5" AND NO LOAD "R52C" |  |  | 7/10 - BOT 11:30 7/11 - TOP 6:30 7/11 - AOI 9:30 | 54 | 575 | 1B 1T | 45 | 810 | FEDEX P | NASA - John F Kennedy Space Center |  | PREVIOUS BUILD USED BLUE LED (D2..) | DOC REL 7/8 | 7/8 | 5406.66 | BOT 1ST | 2024-07-15 | 2 | 2024-07-10 | 6.5
2024-07-16 |  | 7/1 - KIT CLEAR | [5 empty] | 125293-RMA BAL RWK | 50 | 7/11 7D | - |  | PAID RWK QTY 8 - R&R X11 o Replace components R5, R13, R18, R20, R32, R33, R48, R51, R61, R64, R65 with BOM MFRPN ERJ-2RKF1502X o Inspect R15, R18, R24 and R27 for component damage QTY 59 - R&R X11 o Repair/replace L1 in the correct orientation. o Replace components R5, R13, R18, R20, R32, R33, R48, R51, R61, R64, R65 with BOM MFRPN ERJ-2RKF1502X. o Inspect R15, R18, R24 and R27 for component damage. |  |  | BACK |  |  |  | 21 | 1050 | FEDEX P | Protedyne Corporation - 3274-CTL062 |  |  | NO DOC. | 7/1 | 2500
2024-07-15 |  | 7/10 - KIT CLEAR |  |  |  |  | 1 | 126879 RONC 123846 | 50 | 7/15 3D | NL | RONC | *** 3 DAY TURN *** LEAD PROCESS DEPANEL CoC/PACK SLIP PER ECO SHIP EXCESS MATL W/ ASSY'S |  |  | 7/12 - BOT 6:00 7/12 - TOP 8:30 7/12 - AOI 2:30 | 75 | 143 | 1B 1T | 11 | 550 | UPS RED | Royal Circuit Solutions, Inc. |  | VIA HOLES issues previous build | DOC REL 7/10 | 7/10 | 3767.5 | BOT 1ST MANY VIA HOLES | 2024-07-15 | 2 | 2024-07-11 | 8
2024-07-12 |  | 7/10 - SHORTAGES DUE DATE 7/11 - #67 (R1..) DUE |  |  |  |  | 1 | 126277 NEW | 6 | 7/12 2D | NL | X | *** 2 DAY TURN *** PCB BAKE WAIVE (TAD) LEAVE PROTECTIVE FILM ON CMOS SENSOR D89 ORIENTATION (SEE ECO) PLACE AFTER ASSY: BATT DEPANEL |  |  | 7/11 - BOT 6:00 7/11 - TOP 9:00 7/11 - AOI 2:30 | 80 | 849 | 1b 1t | 8 | 48 | FEDEX P | Plexus Engineering Solutions |  | - U21 FOLLOW SILKSCREEN - CMOS SENSOR IS OK TO WASH | NO DOC. | 7/9 | 2000 | bot 1st | 2024-07-12 | 2 | 2024-07-10 | 8.5
2024-07-12 |  | 6/28 - PCB DUE ¦ AWT part conf #76 (J9, J11, J12) PCB DUE 7/2, 7/8 7/8 - KIT CLEAR |  |  | 1 |  |  | 126223 NEW | 24 | 7/12 5D | NL | X | J3 : MISSING 1 GROUND PAD FOR LEG -- OK TO INSTALL AND THEN RTV PART AFTER CONTINUITY TEST WAIVED |  |  | 7/8 - BOT 2:00 7/10 - TOP 8:00 7/10 - AOI 2:00 | 136 | 849 | 2B 2T | 3 | 72 | FEDEX P | L3 |  | 7/8 - #73 (J8) skip & hand soldered - VR1 IS BI-DIRECTIONAL, BUT PLACE ORIENTATION ACCORDING TO CUSTOMER DRAWING | DOC REL 6/25 | 6/26 | 10816.8 | BOT 1ST | 2024-07-12 | 2 | 2024-07-09 | 16
2024-07-11 |  | 7/8 - PCB DUE ¦ SHORTAGES NO ETA 7/8 - SHORT #24 (U6..) & #40 (FB2..) 7/8 - KIT CLEAR |  |  |  |  | 1 | 126727 NEW | 52 | 7/22 10D | NL | X | NO VENDOR MARKINGS ALLOWED DEPANEL |  |  | 7/9 - BOT 6:00 7/9 - TOP 9:00 7/9 - AOI 2:30 | 74 | 346 | 1B 1T | 0 | 0 | FEDEX P | Allocortech Inc. |  |  | DOC REL 6/26 | 6/28 | 4329.2 | BOT 1ST | 2024-07-22 | 2 | 2024-07-09 | 8.5
2024-07-11 |  | 5/30 - not released 6/28 - WILL CLEAR SOON 7/1 - KIT CLEAR |  |  | 1 |  |  | 125275 NEW | 15 | 7/16 10D | NN | X | DO:A7 (CANNOT BE LATE) CUI "FL1-10" MAKE SURE LOCATIONS HAVE NO SOLDER PER ECO #1 |  |  | 7/8 - BOT 6:00 7/8 - TOP 12:00 7/8 - AOI 2:30 | 71 | 255 | 2B 2T | 7 | 105 | FEDEX P | Southwest Research Institute |  | 7/3 - UNABLE TO RUN SMT FOR ALL OF SMA JACK THT PARTS, WILL RUN ONE SIDE ONLY AND THT WILL COMPLETE OTHER SIDE 7/8 - NEED TO SKIP #41 (J1X5) & #44 (J6X11) NEXT TIME INSTEAD OF THE OTHER SIDE - SMT PROGRAM: RESISTORS PLACED ON TOP OF ONE ANOTHER (R1-R12 & R13-R24) - NEED TO SKIP J1X5 & J6X11 OR HAVE A FIXTURE MADE FOR THESE LOCATIONS - J69 PIN 1 SILKSCREEN (SEE PHOTOS) | DOC REL 5/29 | 5/9 | 3836.25 | BOT 1ST | 2024-07-16 | 2 | 2024-07-02 | 8
2024-07-10 |  | 7/1 - PCB DUE 7/8 - PCB DUE 7/8 - KIT CLEAR |  |  |  |  | 1 | 126563-1st NEW | 1 | 7/16 5D | NL | X | LEAD PROCESS "S1" AFTER WASH DEPANEL |  |  | 7/10 - AOI | 13 | 37 | 1T | 54 | 54 | UPS GRD | Hamilton Mfg. Corp |  |  | DOC REL 6/21 | 6/26 | 1400 | TOP ONLY | 2024-07-16 | 1
2024-07-10 |  | 6/25 - KIT CLEAR |  |  | 1 |  |  | 125498-2nd ROWC 1st Article | 25 | 7/24 20D | NL | ROWC | *** DOD DO-C9 *** (CUI/ITAR) "D1-D5" INSTALL REVERSE OF SILKSCREEN PER ECO #1 |  |  | 6/28 - TOP 12:00 6/28 - BOT 2:30 6/28 - PAUSE 7/2 - BOT 6:00 7/2 - AOI 10:00 | 39 | 330 | 2B 2T | 43 | 1075 | FEDEX P | Technology Service Corporation |  | 7/1 - LINEMAN DAY OFF | DOC REL 6/12 | 6/25 | 3966.5 | BOT 1ST top 1st | 2024-07-24 | 2 | 2024-07-01 | 6.5
2024-07-10 |  | 6/25 - SMT CLEAR 7/9 - #21 (X2) due date |  |  | 1 |  |  | 126368 ROWC 118628 | 115 | 7/18 10D | NL | ROWC | CLASS 3 ***QUALITY ALERT - BAG LOOSE - PREVIOUSLY BAGGED TOO TIGHT & DAMAGED PINS *NEED ALL NON COMFORMANCES RECORDED PER ECO #3 DEPANEL |  |  | 6/27 - BOT 2:00 6/28 - TOP 10:00 6/28 - AOI 1:00 | 30 | 155 | 1B 1T | 3 | 345 | UPS GRD | ICC, Inc. |  |  | DOC REL 6/24 | 6/25 | 5514.25 | BOT 1ST | 2024-07-23 | 2 | 2024-06-27 | 7
2024-07-09 |  | 6/26 - PCB DUE 6/27 - KIT CLEAR |  |  |  |  | 1 | 126442 RONC 125375 | 200 | 7/12 10D | NL | RONC | SMT LONGER RUNTIME DUE TO HAND-PLACED PARTS & NUMBER OF FIXTURES AVAILABLE DEPANEL |  |  | 6/27 - TOP 1:00 6/28 - PAUSE 6:00 7/1 - TOP 6:00 7/8 - AOI | 3 | 6 | 1T | 0 | 0 | UPS GRD | Sick, Inc. |  | 6/28 - LINEMAN DAY OFF | DOC REL 6/20 | 6/20 | 2940 | TOP ONLY | 2024-07-12 | 10 | 2024-07-02
2024-07-09 |  | 6/24 - #70 (U72) OK TO SKIP ¦ AWT PART CONF #73 (U27....) 6/25 - KIT CLEAR |  |  |  |  | 1 | 126465 NEW | 8 | 7/10 10D | NL | X | ***PLEASE CHECK "T" DRIVE "B126465" FOLDER FOR XDDITIONAL DOCS ON ORIENTATION & POLARITY ENSURE BOARDS ARE "THOUROGHLY" WASHED AND CLEANED PER ECO ALT U27 PART CONFIRMED DEPANEL |  |  | 6/27 - BOT 9:00 6/27 - TOP 12:00 6/27 - PAUSE 7/1 - TOP 6:00 7/1 - AOI 1:30 | 157 | 1118 | 1B 3T | 147 | 1176 | FEDEX P | Lake Shore Cryotronics, Inc. |  | 6/27 - AWT SETUP & 6/28 - LINEMAN DAY OFF 7/2 - #105 (L5) bi-directional | DOC REL 6/13 | 6/24 | 10635.68 | BOT 1ST | 2024-07-10 | 2 | 2024-06-27 | 10.5
2024-07-08 |  | 2/9 - SMT CLEAR; BUILT AND SHIPPED 60 ON 2/23 |  |  |  |  | 1 | 116970-2ND BAL RONC | 60 | 7/8 6/21 20D | NL | RONC | SCHEDULED SHIPMENT: BAL 60 L1 – P/N MSS5131-393MLC U2 – P/N LTC2864MPS-2#PBF DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/13 - TOP 9:00 2/13 - BOT 1:30 2/14 - AOI 12:00 | 29 | 54 | 2B 1T | 11 | 660 | UPS GRD | Anderson Connectivity |  |  | DOC REL 2/2 | 2/8 | 1316.64 | L1 IS P/N MSS5131-393MLC BOT 1ST | 2024-03-19 | 2 | 2024-02-13 | 12
2024-07-08 |  | 2/7 - CLEARED FOR 190 BOARDS (60 BOARDS SHIPPED 2/14/24) 2/22 - SHORT U2 3/1 - KIT CLEAR |  |  |  |  | 2 | 116967-2ND BAL RONC | 60 | 7/8 6/21 20D | NL | RONC | SCHEDULED SHIPMENT: BAL 60 30119-102 00500+ J1 – p/n approved M80-5402042 DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 3/4 - TOP 7:30 | 37 | 89 | 1T | 2 | 120 | UPS GRD | Anderson Connectivity |  |  | DOC REL 2/2 | 2/7 | 1182.67 | TOP ONLY | 2024-04-19 | 1 | 2024-02-14
2024-07-08 |  | 2/9 - #15 (IC2) DUE DATE 2/9 - KIT CLEAR |  |  |  | 1 |  | 116966-3RD BAL RONC | 60 | 7/8 6/21 20D | NL | RONC | SCHEDULED SHIPMENT: BAL 60 J1 – P/N M80-5402042 2 LABEL TYPES & LOCS TEXT LABEL & QR CODE ENSURE S/N MATCH LABELS SPECIFIED LOCATIONS DEPANEL XRAY & SVE |  |  | 2/13 - BOT 12:00 2/13 - TOP 2:00 2/15 - AOI 2:00 | 34 | 154 | 2B 2T | 1 | 60 | UPS GRD | Anderson Connectivity |  |  | DOC REL 2/2 | 2/8 | 1680.63 | BOT 1ST | 2024-03-19 | 2 | 2024-02-13 | 14
2024-07-08 |  | 2/8 - SHORT #27A (U10) NO ETA 2/9 - KIT CLEAR |  |  | 1 |  |  | 116964-3RD BAL RONC | 60 | 7/8 6/21 20D | NL | RONC | SCHEDULED SHIPMENT: BAL 60 U8, U9 – LTC2864MPS-2#PBF U10 – LTC2864MPS-1#PBF DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/13 - BOT 8:30 2/13 - TOP 12:30 2/15 - AOI 9:00 | 68 | 264 | 2B 2T | 5 | 300 | UPS GRD | Anderson Connectivity |  |  | DOC REL 2/2 | 2024-02-08 | 3156.95 | Customer wants to use a different part number for U8, U9 only, PN LTC2864MPS-2#PBF. U10, PN LTC2864MPS-1#PBF, will remain the same. BOT 1ST | 2024-03-19 | 2 | 2024-02-13 | 16.5
2024-07-08 |  | 2/5 - SMT CLEAR |  |  | 1 |  |  | 116957-3RD BAL RONC | 60 | 7/8 6/21 20D | NL | RONC | SCHEDULED SHIPMENT: BAL 60 #3 (C4) ALT P/N UBT2A221MHD8TN DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/7 - BOT 11:00 2/7 - AOI 1:30 | 1 | 1 | 1B | 12 | 720 | UPS GRD | Anderson Connectivity |  |  | DOC REL 2/2 | 2024-02-05 | 897.63 |  |  | 1 | 2024-02-07 | 2.5
2024-07-08 |  | 2/7 - KIT CLEAR |  |  | 1 |  |  | 116956-2ND BAL RONC | 60 | 7/8 6/21 20D | NL | RONC | DNI #20 (FB8) SCHEDULED SHIPMENT: BAL 60 L1 – P/N 1264EY-330M=P3 J1 – P/N M80-5402042 DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/8 - BOT 10:00 2/9 - TOP 5:00 2/9 - STOP 2:30 2/15 - TOP 9:00 2/15 - AOI 1:00 | 28 | 121 | 1B 1T | 3 | 180 | UPS GRD | Anderson Connectivity |  |  | DOC REL 2/2 | 2024-02-07 | 1641.16 | BOT 1ST | 2024-03-19 | 2 | 2024-02-15 | 20
2024-07-08 |  | 2/5 - SMT CLEAR |  |  | 1 |  |  | 116955-3RD BAL RONC | 60 | 7/8 6/21 20D | NL | RONC | SCHEDULED SHIPMENT: BAL 60 SHORT #10 (J1,J2) P/N M80-5000000M2-02-331-00-000 DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/7 - TOP 9:00 2/7 - AOI 12:00 | 7 | 8 | 1T | 12 | 720 | UPS GRD | Anderson Connectivity |  |  | DOC REL 2/2 | 2024-02-05 | 816 |  |  | 1 |  | 3
2024-07-08 |  | 2/8 - SHORT #10 (U1) & #7 (D10, D11...) NO ETA 2/9 - KIT CLEAR |  |  | 1 |  |  | 116954-2ND BAL RONC | 60 | 7/8 6/21 20D | NL | RONC | SCHEDULED SHIPMENT: BAL 60 no 0 OHM rework required U1 – P/N LTC2864MPS-1#PBF L1 – P/N MSS5131-393MLC J1 – P/N M80-5402042 DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/15 - TOP 1:00 2/16 - AOI 11:30 | 24 | 87 | 1T | 1 | 60 | UPS GRD | Anderson Connectivity |  |  | DOC REL 2/2 | 2024-02-08 | 1104 | L1 IS P/N MSS5131-393MLC TOP ONLY | 2024-03-19 | 1 | 2024-02-15 | 6.5
2024-07-08 |  | 2/5 - SMT CLEAR 2/7 - 60 PCBAS OF 360 CLEAR TO SHIP 2/19 2/14 - KIT CLEAR |  |  | 1 |  |  | 116950-3RD BAL RONC | 60 | 7/8 6/21 20D | NL | RONC | SCHEDULED SHIPMENT: BAL 60 LEAD PROCESS DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/7 - BOT 1:30 2/8 - AOI 11:00 | 6 | 16 | 1B 1T | 5 | 300 | UPS GRD | Anderson Connectivity |  |  | DOC REL 2/2 | 2/5 | 781.58 |  |  | 2 | 2024-02-07 | 6.5
2024-07-08 |  | 6/27 - KIT CLEAR |  |  | 2 |  |  | 126459 RONC 123578 | 6 | 7/12 10D | NL | RONC | DEPANEL |  |  | 7/2 - TOP 8:00 7/2 - AOI 9:00 | 1 | 40 | 1T | 47 | 282 | FEDEX P | Innomotics, LLC |  |  | DOC REL 6/26 | 6/27 | 2154 | TOP ONLY | 2024-07-12 | 1 | 2024-07-02 | 1
2024-07-08 |  | 6/19 - SHORTAGES (#91 - U12.., #186 - R310 & #208 - Q9) DUE SOON 6/21 - KIT CLEAR |  |  | 1 |  |  | 125822 NEW | 15 | 7/8 10D | NL | X | BTD Q9 *MAKE SURE TO BAKE PCB'S 12HR MIN CLASS 3 ***DO NOT DEPANEL UNTIL AFTER FLYING PROBE TESTING - AFTER ASSY SEND TO TEST COACH FOR TESTING. AFTER TESTING ALTA TO FINISH ASSY'S XRAY & SAVE IMAGES "J16 & J17" ARE PRESS FIT - DO NOT SOLDER "MECH1-6" SEE ECO FOR PLACEMENT |  |  | 6/25 - BOT 2:00 6/26 - TOP 9:30 6/26 - PAUSE 2:30 6/27 - TOP 9:00 6/27 - AOI 1:30 | 207 | 1336 | 2B 2T | 8 | 120 | FEDEX P | Test Coach Company |  | 6/26 - PAUSE TO START TOP TO ALLOW TRINH TIME TO FIX OS & MA ISSUES WITH BOTTOM SIDE | DOC REL 6/18 | 6/19 | 20169.45 | BOT 1ST | 2024-07-08 | 2 | 2024-06-26 | 8.5
2024-07-08 |  | 7/8 - PCB DUE 7/1 - KIT CLEAR |  |  | 1 |  |  | 126644 RONC 125697 | 20 | 7/8 3D | NL | RONC | *** 3 DAY TURN *** LEAD PROCESS DEPANEL |  |  | 7/2 - BOT 9:00 7/2 - TOP 1:00 | 112 | 512 | 2B 2T | 3 | 60 | FEDEX P | Ocean Aero, Inc. |  |  | DOC REL 6/20 | 6/21 | 7518.4 | BOT 1ST | 2024-07-08 | 2 | 2024-07-02
2024-07-03 |  | 6/24 - KIT CLEAR |  |  | 1 |  |  | 125746 NEW | 5 | 7/9 10D | NL | X | SOLDER PASTE MUST BE • SAC 305 (Sn 96.5 Ag 3.0Cu 0.5) PER ECO |  |  | 6/27 - BOT 6:00 6/27 - TOP 9:00 6/27 - PAUSE 9:00 6/27 - TOP 12:30 6/27 - AOI 3:30 | 73 | 635 | 1B 1T | 41 | 205 | FEDEX P | Innomotics LLC |  |  | DOC REL 6/11 | 6/24 | 4891.75 | BOT 1ST | 2024-07-09 | 2 | 2024-06-27
2024-07-03 |  | 6/18 - PCB DUE ¦ SHORT OTHER PARTS AS WELL 6/19 - PCB DUE 6/19 - KIT CLEAR |  |  |  |  | 1 | 125259 NEW | 10 | 7/3 10D | NL | X | DNI J9 J21 & J30 SHOULD MATCH SILKSCREEN INSTALL J13: SHORT EDGE W/ SMALL SILK "D53, D54" PARTS WILL OVERHANG ON LAND PADS PER ECO |  |  | 6/19 - BOT 12:00 6/21 - TOP 6:00 6/21 - PAUSE 6:00 6/26 - TOP 6:00 6/26 - AOI 4:00 | 260 | 2120 | 3B 3T | 38 | 380 | FEDEX P | Integrated Consultants |  | 6/20 - J10 PLACEMENT ORIENTATION 6/26 - MANY OPEN SOLDER, MISSING PARTS AND SOLDER QUALITY ISSUES | DOC REL 6/5 | 6/12 | 31863 | BOT OR TOP | 2024-07-03 | 3 | 2024-06-25 | 21.5
2024-07-03 |  | 6/20 - KIT CLEAR |  |  | 1 |  |  | 126237 NEW | 25 | 7/3 6/27 5D | NL | X | *** SENT TO ROYAL - DRILL J4 HOLES LEAD FREE PROCESS DEPANEL |  |  | 6/25 - BOT 2:00 6/25 - TOP 10:00 6/25 - AOI 2:30 | 75 | 629 | 1B 1T | 3 | 75 | FEDEX P | Flir |  | 6/25 - J4 missing drill holes | DOC REL 6/20 | 6/20 | 8569 | BOT 1ST | 2024-06-27 | 2 | 2024-06-24 | 8.5
2024-07-03 |  | 7/1 - KIT CLEAR | [5 empty] | 125293-RMA PAR RWK | 17 | 7/11 7D | - |  | PAID RWK QTY 8 - R&R X11 o Replace components R5, R13, R18, R20, R32, R33, R48, R51, R61, R64, R65 with BOM MFRPN ERJ-2RKF1502X o Inspect R15, R18, R24 and R27 for component damage QTY 59 - R&R X11 o Repair/replace L1 in the correct orientation. o Replace components R5, R13, R18, R20, R32, R33, R48, R51, R61, R64, R65 with BOM MFRPN ERJ-2RKF1502X. o Inspect R15, R18, R24 and R27 for component damage. |  |  | BACK |  |  |  | 21 | 357 | FEDEX P | Protedyne Corporation - 3274-CTL062 |  |  | NO DOC. | 7/1 | 2500
2024-07-01 |  | 6/21 - KIT CLEAR | [5 empty] | 126155 RWK | 18 | 7/8 10D | - |  | remove & replace SW1_FT with EXBS8V220J |  |  | FSU | - | - | - | 1 | 18 | UPS 2 DAY | Farsounder, Inc. |  |  | NO DOC. | 6/21 | 540
2024-06-28 |  | 6/18 - KIT CLEAR |  |  | 1 |  |  | 126262 NEW | 500 | 6/28 7/17 20D | NL | X | NO ECO |  |  | 6/19 - BOT 1:30 6/19 - AOI 10:00 | 16 | 31 | 2B | 5 | 2500 | UPS GND | Respond Systems, Inc. |  |  | DOC REL 6/18 | 6/18 | 6810 | TOP 1ST | 2024-07-17 | 2 |  | 5
2024-06-27 |  | 6/3 - PCB SHORT ¦ NO ETA 6/13 - PCB DUE 6/17 - PCB DUE 6/18 - KIT CLEAR |  |  | 1 |  |  | 107957 NEW | 10 | 7/2 10D | NL | X | DNI J25/J26 & ship with boards NO ECO |  |  | 6/18 - BOT 1:00 6/19 - TOP 8:00 6/19 - AOI 2:30 | 114 | 891 | 1B 2T | 44 | 440 | UPS 2ND DAY | Rocky Research |  | 6/19 - J25 & J26 PARTS DO NOT FIT 6/19 - FIXTURE REQUIRED; CANNOT PLACE BOARD ON STANDARD FIXTURE BECAUSE BOT DIODES (TVSD51 & TVSDS52) | DOC REL 5/30 | 6/3 | 3902.5 | BOT 1ST | 2024-07-02 | 2 |  | 9.5
2024-06-27 |  | 6/27 - PCB DUE ¦ SHORT #8 (U7) 6/24 - KIT CLEAR |  |  |  |  | 1 | 126189 NEW | 200 | 6/27 3D | NL | X | *** 3 DAY TURN *** NO CLEAN PROCESS *NO SOLDER ON DNI & TEST POINT PADS XRAY & SAVE IMAGES |  |  | 6/25 - BOT 6:00 6/25 - TOP 12:00 6/25 - AOI 3:00 | 22 | 34 | 1B 1T | 1 | 200 | FEDEX P | Procter & Gamble Company |  |  | DOC REL 6/18 | 6/18 | 6660 | BOT 1ST | 2024-06-27 | 2 | 2024-06-24 | 9
2024-06-27 |  | 6/19 - PCB & #39 (U5) DUE 6/20 - PCB DUE 6/20 - KIT CLEAR |  |  | 1 |  |  | 126440 NEW | 30 | 6/27 5D | NL | X | "U5" CHECK ORIENTATION PER ECO #2 BEFORE PLACING "L1,2,3,5,7" AFTER WASH XRAY & SAVE IMAGES DEPANEL |  |  | 6/24 - BOT 8:00 6/24 - TOP 11:00 6/24 - AOI 3:30 | 123 | 433 | 2B 2T | 20 | 600 | UPS INTL | BinSentry |  | 6/24 - BOT 1ST DUE TO CONN SMA JACK | DOC REL 6/13 | 6/14 | 5975.1 | TOP 1ST BOT 1ST | 2024-06-27 | 2 | 2024-06-24 | 7.5
2024-06-27 |  | 6/17 - PCB DUE 6/13 - #64 (U108, U109) DUE 6/20 - PCB DUE 6/20 - KIT CLEAR |  |  |  |  | 1 | 125902 NEW | 27 | 6/27 5D | NL | X | CUI CLASS 3 "SW1" AFTER WASH "H1-H9" REFER TO "AE103540-002_PCBA_GPC-4_VPX_CARD_REV-" PDF PER ECO #2 ORLO, ORMO, ORHO, ROLO, ROMO, ROHO (Halide Free) ***BOM UPDATED 6/12 - "P2B DNI FOR THIS BUILD ONLY "RCVR1 & RELATED, XMTR1, L1. L3" AFTER WASH DEPANEL BAR CODES REQUIRED |  |  | 6/21 - BOT 6:00 6/21 - TOP 11:30 6/24 - AOI 4:00 | 151 | 1632 | 1B 2T | 45 | 1215 | FEDEX P | Aeronix Inc |  |  | DOC REL 6/11 | 6/13 | 63214.2 | BOT 1ST | 2024-06-27 | 2 | 2024-06-21 | 19
2024-06-26 |  | 6/17 - KIT CLEAR |  |  |  |  | 1 | 125529 RONC 122927 | 10 | 6/26 7/1 10D | NL | RONC | LEAD PROCESS "IC10" IS MOISTURE SENSITIVE PER ECO #4 - DO NOT WASH!!! DEPANEL |  |  | 6/18 - BOT 9:00 6/19 - TOP 6/19 - AOI | 97 | 339 | 1B 1T | 6 | 60 | FEDEX P | Ocean Aero, Inc. |  |  | DOC REL 6/14 | 6/17 | 2951.5 | BOT 1ST | 2024-07-01 | 2
2024-06-26 |  | 6/19 - KIT CLEAR FOR 25 OF 50 |  |  | 1 |  |  | 125336-1 PAR NEW | 25 | 6/26 5D | NL | X | ON HOLD (board REV req TAD review) - run 25 & mark with correct REV w/ marker send waiver w/ shipment ***AS9100 (CUI)*** print attachment and ship w/ boards Build QTY 50 (no FA) 5-day turn: qty 25 ship to customer 15-day turn: qty 25 ship to Test Coach SMT install shield AS9100 FAIR REQUIRED "SW11000" AFTER WASH "P22000" PRESS FIT |  |  | 6/20 - BOT 10:30 6/20 - TOP 1:00 6/20 - PAUSE 2:30 6/21 - TOP 7:30 6/21 - AOI 2:30 | 128 | 896 | 1B 2T | 3 | 75 | FEDEX P | Chelton Avionics, Inc. |  |  | DOC REL 5/3 | 6/19 | 8861.85 | TOP OR BOTTOM? bot | 2024-06-26 | 2 | 2024-06-20 | 11.5
2024-06-25 |  | 6/20 - PCB DUE DATE 6/14 - AWT PART CONF #27 (J8) 6/20 - KIT CLEAR |  |  | 1 |  |  | 126194-1st NEW | 2 | 6/25 3D | NL | X | *** 3 DAY TURN *** ok to use APT2012SGC for D2 NO ECO NOTES |  |  | 6/21 - BOT 12:30 6/21 - TOP 1:30 6/24 - AOI 9:00 | 52 | 574 | 1B 1T | 45 | 90 | FEDEX P | NASA - John F Kennedy Space Center |  |  | DOC REL 6/11 | 6/14 | 2991 | BOT 1ST | 2024-06-25 | 2 | 2024-06-24 | 5
2024-06-24 |  | 6/6 - KIT CLEAR |  |  |  |  | 1 | 125581 RONC 123722 | 2 | 6/27 10D | NL | RONC | ON HOLD DNI #65 (J2...) & X1 DO NOT RUN ON LINE 1 VERIFY IF THERE ARE X1 COPPER RING PAD LEAD PROCESS NO LABELS REQUIRED XRAY & SAVE IMAGES DEPANEL |  |  | 6/12 - TOP 11:30 6/12 - HOLD 12:00 6/14 - TOP 8:00 6/14 - AOI 12:00 | 106 | 540 | 2T | 83 | 166 | FEDEX P | X-Microwave (A Quantic Company) |  | 6/12 - WRONG FAB 6/13 - NEW FABS RECEIVED | DOC REL 5/9 | 6/6 | 1785.3 | TOP ONLY | 2024-06-27 | 2 |  | 4
2024-06-24 |  | 6/18 - PCB DUE 6/12 - KIT CLEAR |  |  |  |  | 1 | 126272 NEW | 2 | 6/26 10D | NL | X | SPACERS FOR "D1" x17 REQUIRED PER ECO DEPANEL |  |  | 6/14 - AOI | 17 | 165 | 1T | 8 | 16 | FEDEX GRD | Bruker Nano, RMR (FKA RAVE LLC) |  |  | DOC REL 6/3 | 6/4 | 2641 | TOP ONLY | 2024-06-26 | 1
2024-06-24 |  | 5/24 - PCB DUE 6/6 - SHORT #38 (U4) 6/17 - KIT CLEAR |  |  | 1 |  |  | 125418 NEW | 2 | 6/24 5D | NN | X | ok to skip #38 (U4) DEPANEL |  |  | 6/18 - BOT 9:00 6/18 - TOP 6/18 - AOI 2:00 | 94 | 271 | 2B 2T | 2 | 4 | FEDEX P | Saturn PCB Design, Inc. |  |  | DOC REL 5/17 | 5/17 | 2798.16 | BOT 1ST | 2024-06-24 | 2 |  | 5
2024-06-24 |  | 6/10 - KIT CLEAR |  |  | 1 |  |  | 125719 NEW | 2 | 6/24 10D | NN | X | NO ECO "J22" CBD3W3F37S000 and "P1, P4" CBD8W8F37S0T20\AA ARE NOW "INSTALL" ***SHIPPING METHOD CHANGED TO "RYDER (DTMS)" - CHECK 2 DAYS BEFORE SHIPPING TO MAKE SURE RYDER ACCT WAS SET UP |  |  | 6/12 - TOP 1:30 6/13 - AOI | 43 | 577 | 2T | 8 | 16 | RYDER (DTMS) | Northrop Grumman Systems Corporation |  |  | DOC REL 5/28 | 6/10 | 2989 | TOP ONLY | 2024-06-24 | 1
2024-06-24 |  | 5/20 - SHORT PCB ¦ NO ETA 6/3 - PCB DUE 6/10 - KIT CLEAR |  |  | 1 |  |  | 123155 NEW | 50 | 6/24 10D | NN | X | ***DO NOT DEPANEL*** BOARDS SHIP TO FLYING PROBE TESTING AND NEED THE RAILS FOR TESTING. (DEPANEL WHEN THEY COME BACK FROM TESTING) |  |  | 6/12 - TOP 9:30 6/12 - AOI 12:30 | 36 | 117 | 2T | 7 | 350 | FEDEX P | TEST COACH |  |  | DOC REL 5/17 | 5/20 | 2402 | TOP ONLY | 2024-06-24 | 1 |  | 3
2024-06-24 |  | 5/21 - EXPECTED CLEAR DATE 5/23 - short 7 pieces of #33 (U20) 5/24 - KIT CLEAR |  |  | 1 |  |  | 123547 ROWC 119889 | 11 | 6/24 20D | NL | RONC | changed to ROWC (instead of RONC) PP0 (1410147-1) PRESS FIT - SEE ECO #7 PN#XCF32PVO48C (UPG2) priority 1: ~10 pieces xcf32pvo48c, new priority 2: ~20 pieces xcf32pvo48c, used (pulled out from old PCBs) priority 3: 48 pieces xcf16pvo48c, new (use this after the priority 1 and 2 depleted). XRAY & SAVE DEPANEL EXTRA PACKAGING REQUIRED FOR PROTECTION PER ECO #10 |  |  | 6/6 - BOT 12:00 6/6 - TOP 2:00 6/7 - AOI 10:00 | 48 | 936 | 1B 1T | 8 | 88 | UPS GRD | Jefferson Labs |  |  | DOC REL 5/16 | 5/16 | 5162.64 | BOT 1ST FIBER OPTIC PLUG | 2024-06-24 | 2 | 2024-06-07 | 6
2024-06-21 |  | 6/5 - Short #48 (U28..) & #52 (U26) 6/14 - KIT CLEAR |  |  | 1 |  |  | 125727 ROWC 125726 | 10 | 6/21 5D | NL | ROWC | ok skip #52 (U28) CLASS 3 ENSURE BOARDS ARE CLEAN "MP1, 2, 3 ,4" SHIP BACK TO CUSTOMER WITH THE BOARDS |  |  | 6/17 - TOP 6:00 6/17 - BOT 12:00 6/18 - AOI 9:00 | 110 | 1085 | 2B 2T | 2 | 20 | FEDEX GRD | Anduril |  |  | DOC REL 5/21 | 5/30 | 12050 | TOP OR BOTTOM? top 1st | 2024-06-21 | 2 |  | 11
2024-06-21 |  | 6/19 - PCB DUE 6/20 - KIT CLEAR |  |  | 2 |  |  | 126591 NEW | 8 | 6/21 1D | NL | X | *** 1 DAY TURN *** DISREGARD DWG NOTE #17 & #18 (LABEL/SER #) PER ECO #3 DEPANEL & SAND |  |  | 6/21 - TOP 6:00 6/21 - AOI 10:00 | 65 | 337 | 1T | 4 | 32 | FEDEX P | Ergotron, Inc. |  |  | DOC REL 6/17 | 6/18 | 14084 | TOP ONLY | 2024-06-21 | 1 | 2024-06-21 | 4
2024-06-21 |  | 6/13 - PCB DUE 6/14 - SHORTAGES DUE 6/14 - KIT CLEAR |  |  |  |  | 1 | 126369 RONC 122435 | 50 | 6/21 5D | NL | RONC | SEVERAL ORIENTATION REQUIREMENTS - SEE ECO DEPANEL *BOARDS GET CONFORMAL COATING SO MAKE SURE BOARDS ARE FREE OF DUST/DEBRIS CoC REQUIRES SER NUMBERS |  |  | 6/17 - BOT 6:00 6/17 - TOP 9:00 6/17 - AOI 11:30 | 32 | 131 | 1B 1T | 7 | 350 | UPS GRD | Churchill Navigation dba Shotover Systems Inc |  |  | DOC REL 6/11 | 6/12 | 2118.5 | BOT 1ST | 2024-06-21 | 2 |  | 5.5
2024-06-20 |  | 5/16 - SHORT #27(X1) 6/10 - SMT CLEAR 6/13 - KIT CLEAR |  |  |  |  | 1 | 125339 RONC 110180 | 10 | 6/20 5D | NL | RONC | short X1 (is this skippable?) than SMT clear MECH ASSY CABLE1 & PS1 SHIP W/ BOARDS IC1 BAKE PRIOR TO ASSY DEPANEL |  |  | 6/12 - TOP 6:00 6/12 - BOT 10:30 6/12 - AOI 12:30 | 36 | 283 | 1B 1T | 9 | 90 | FEDEX P | Analog Devices Inc. |  | 6/12 - BOT 1ST | DOC REL 5/10 | 5/13 | 4487 | top 1st | 2024-06-20 | 2 |  | 6.5
2024-06-20 |  | 6/13 - KIT CLEAR |  |  | 1 |  |  | 126106 NEW | 35 | 6/20 5D | NL | X | "S1" AFTER WASH "D1-D10, D23-D27" INSTALL FLUSH PER ECO #3 DEPANEL |  |  | 6/14 - BOT 7:00 6/14 - TOP 6/14 - AOI 3:00 | 37 | 162 | 1B 1T | 22 | 770 | FEDEX P | Becton, Dickinson and Company |  | 6/13 - SHORT ARRAY FILE | DOC REL 6/13 | 6/13 | 3905 | BOT 1ST | 2024-06-20 | 2 |  | 8
2024-06-20 |  | 5/9 - KIT CLEAR | [5 empty] | 123601-6 BAL RWK | 295 | 6/20 |  | X | RWK - 0 BAL REMAINING SCHEDULED SHIPMENT 50-100 / WEEK |  |  | BACK |  |  |  | 0 | 0 | FEDEX | NAL Research Corp
2024-06-19 |  | 5/30 - KIT CLEAR |  |  | 2 |  |  | 124791-2 BAL NEW | 51 | 6/20 15D | NL | X | balance remaining OF 150 DEPANEL & SAND PER ECO LABEL EACH ESD BAG PER ECO #3 |  |  | 5/31 - AOI | 11 | 17 | 1B 1T | 0 | 0 | UPS RED | Onward Robotics |  |  | DOC REL 4/8 | 4/15 | 867 | BOT 1ST | 2024-06-20 | 1 |  | 4.5
2024-06-19 |  | 6/5 - KIT CLEAR |  |  | 1 |  |  | 125312-2nd RONC 1ST | 39 | 6/19 10D | NL | RONC | "SW1 & RELATED" AFTER WASH DEPANEL |  |  | 6/10 - BOT 9:30 6/10 - TOP 1:00 6/11 - AOI 10:00 | 65 | 508 | 1B 1T | 11 | 429 | FEDEX P | Nordson Corporation |  |  | DOC REL 6/5 | 6/5 | 5216.64 | BOT 1ST | 2024-06-19 | 2 |  | 8.5
2024-06-18 |  | 5/17 - CLEAR BY DATE 5/20 - KIT CLEAR | [5 empty] | 125795 RONC 125637 | 73 | 5/23 3D | NL | RONC | Cancelled 06-18-2024 |  |  | RTR | 52 | 136 | 1T | 4 | 292 | FEDEX P | Ergotron, Inc. |  |  | DOC REL 5/14 | 5/14 | 16060 | TOP ONLY |  | 1
2024-06-18 |  | 6/13 - PCB DUE 6/11 - KIT CLEAR |  |  | 2 |  | 1 | 126038 RONC 123320 | 53 | 6/18 5D | NL | RONC | NO CLEAN *NO SOLDER ON DNI PADS XRAY & SAVE DEPANEL |  |  | 6/12 - BOT 8:30 6/12 - TOP 1:30 6/13 - AOI | 22 | 36 | 1B 1T | 0 | 0 | UPS RED | Kinetic Vision |  |  | DOC REL 6/7 | 6/10 | 2361.15 | bot 1st | 2024-06-18 | 2
2024-06-18 |  | 5/30 - SHORT PCB ¦ NO ETA 6/10 - WILL CLEAR THIS WEEK 6/11 - KIT CLEAR |  |  | 1 |  |  | 126015 NEW | 10 | 6/18 5D | NN | X | NO SOLDER ON DNI LOCATIONS SW2 AFTER WASH CLEAN BOARDS DEPANEL & SAND |  |  | 6/13 - BOT 10:00 6/13 - TOP 12:30 6/14 - AOI 7:00 | 104 | 795 | 2B 2T | 10 | 100 | FEDEX 2DAY | Alphawave IP, Inc. |  |  | DOC REL 5/30 | 5/30 | 5634.5 | BOT 1ST | 2024-06-18 | 2 |  | 5
2024-06-18 |  | 5/28 - PCB & MATs DUE 5/28 - KIT CLEAR |  |  | 1 |  |  | 123956 NEW | 85 | 6/18 15D | NL | X | CLASS 3 DEPANEL |  |  | 6/7 - BOT 10:00 6/10 - AOI | 34 | 175 | 1B 1T | 7 | 595 | FEDEX P | Jet Propulsion Lab |  |  | DOC REL 4/8 | 5/24 | 4122.5 | BOT 1ST | 2024-06-18 | 2 | 2024-06-10
2024-06-17 |  | 6/11 - ALMOST CLEAR 6/14 - KIT CLEAR |  |  |  |  | 1 | 126452 NEW | 35 | 6/17 1D | NL | X | ok to SKIP F1 & R48 *** 1 DAY TURN *** "SW1, LS1" AFTER WASH "P1" REFER TO ECO #3 & SPECIFIED DATASHEET |  |  | 6/14 - TOP 10:00 6/14 - AOI 2:00 | 60 | 156 | 1T | 5 | 175 | FEDEX P | Ergotron, Inc. |  |  | DOC REL 6/10 | 6/11 | 17040 | TOP ONLY | 2024-06-17 | 1 |  | 4
2024-06-17 |  | 6/10 - SHORT #2 PCS OF #19 (U4) & ATTRITION OF #11 (D8) - OK TO SKIP SHORTAGES 6/10 - KIT CLEAR |  |  |  | 1 |  | 125121-2ND RONC 1st Article | 198 | 6/17 5D | NL | RONC | Skipped short #11 (D8) & #19 (U4) BTD #11 (D8) & #19 (U4) "U15" AFTER WASH *NO SOLDER FLUX LEFT ON BOARDS PER ECO #4 DEPANEL |  |  | 6/11 - TOP 8:00 6/12 - BOT 9:30 6/12 - AOI 2:00 | 44 | 98 | 1B 1T | 5 | 990 | FEDEX P | Industrialex Manufacturing |  | 6/11 - TOP 1ST DUE TO MODULE | DOC REL 6/6 | 6/10 | 6229.08 | bot 1st | 2024-06-17 | 2 |  | 12
2024-06-14 |  | 5/9 - KIT CLEAR | [5 empty] | 123601-5 PAR RWK | 60 | 6/14 |  | X | RWK - 295 BAL REMAINING SCHEDULED SHIPMENT 50-100 / WEEK |  |  | BACK |  |  |  | 0 | 0 | FEDEX P | NAL Research Corp
2024-06-14 |  | 6/10 - SHORT PCB & D14 THAN SMT CLEAR (ok to skip D14) 6/11 - KIT CLEAR |  |  |  |  | 1 | 126181 NEW | 1 | 6/14 3D | NL | X | *** 3 DAY TURN *** LEAD PROCESS "K25" AFTER WASH DEPANEL |  |  | 6/10 - BOT 12:30 6/10 - TOP 2:30 6/11 - AOI 7:00 | 35 | 130 | 1B 1T | 79 | 79 | FEDEX GRD | Duotech Services Inc |  |  | DOC REL 6/6 | 6/6 | 4127 | BOT 1ST | 2024-06-14 | 2 |  | 3
2024-06-14 |  | 6/7 - KIT CLEAR |  |  | 1 |  |  | 126209 NEW | 50 | 6/14 5D | NL | X | LEAD PROCESS FULLY INSPECT "MP1, MP2" PRIOR TO INSTALLING SHIELD "U11, U12" AFTER WASH DEPANEL |  |  | 6/11 - BOT 9:30 6/11 - TOP 2:00 6/12 - AOI 10:00 | 86 | 298 | 1B 1T | 3 | 150 | FEDEX P | Urban Sky Theory LLC |  |  | DOC REL 6/6 | 6/7 | 7117.5 | BOT 1ST | 2024-06-14 | 2 |  | 8.5
2024-06-14 |  | 5/16 - PCB DUE ¦ AWT PART CONF 5/20 - KIT CLEAR |  |  | 1 |  |  | 125413 RONC 125273 | 800 | 6/14 10D | NL | RONC | ADDED 8-DAYS TO PLACE L1 AFTER WASH NO IN-HOUSE LABELS "SW!, PS1, U5, SW2" AFTER WASH DEPANEL MECH ASSY AND HARDWARE INSTALLED PER ECO #2 NO LEFT OVER FLUX ALLOWED - MUST BE REMOVED |  |  | 5/24 - TOP 7:00 5/28 - BOT 7:00 5/28 - PAUSE 1:30 5/29 - TOP 9:00 5/29 - AOI 11:30 | 7 | 59 | 1B 1T | 2 | 1600 | UPS RED | Moxtek |  | TOP 1ST DUE TO LARGE PART | DOC REL 5/3 | 5/15 | 11760 | BOT 1ST TOP 1ST | 2024-06-12 | 2 |  | 17
2024-06-13 |  | 6/7 - PCB DUE 6/6 - KIT CLEAR |  |  |  |  | 1 | 126151 NEW | 10 | 6/13 5D | NL | X | INSTALL SHUNTS DEPANEL |  |  | 6/10 - TOP 9:00 6/10 - AOI 12:00 | 75 | 273 | 2T | 16 | 160 | FEDEX P | HunterLab |  |  | DOC REL 6/3 | 6/4 | 4047.5 | TOP ONLY | 2024-06-13 | 1 | 2024-06-10
2024-06-13 |  | 6/4 - PCB DUE 5/30 - KIT CLEAR |  |  |  |  | 1 | 126012 NEW | 5 | 6/13 10D | OL | X | *** NO BOARD HOUSE STAMPS *** DEPANEL |  |  | 5/31 - BOT 12:00 6/1 - AOI | 10 | 145 |  | 4 | 20 | UPS GRD | Moxtek |  |  | DOC REL 5/24 | 5/29 | 3695 | TOP 1ST | 2024-06-13 | 2
2024-06-13 |  | 6/5 - PCB & SHORTAGES DUE 6/6 - KIT CLEAR |  |  | 2 |  |  | 126163 NEW | 6 | 6/13 5D | NN | X | LEAD PROCESS *6/3 UPDATED TO NO CLEAN PROCESS "SW1-29 & SW23" AFTER WASH DEPANEL |  |  | 6/10 - AOI | 20 | 102 | 1T | 9 | 54 | UPS RED | Pacific Northwest National Laboratory |  |  | DOC REL 5/29 | 5/30 | 3607 | TOP ONLY | 2024-06-13 | 1
2024-06-12 |  | 5/29 - KIT CLEAR |  |  |  |  | 2 | 124940 RONC 123511 | 120 | 6/12 10D | RT | RONC | CLASS 3 DEPANEL AND SAND |  |  | 6/6 - BOT 1:00 6/10 - AOI | 60 | 188 | 2B 2T | 0 | 0 | UPS 3D | Coastal Designs, LLC |  |  | DOC REL 5/22 | 5/30 | 9024 | BOT 1ST | 2024-06-12 | 2 | 2024-06-07
2024-06-12 |  | 6/5 - PCB DUE 6/5 - KIT CLEAR |  |  |  | 1 |  | 126074 NEW | 9 | 6/12 5D | NN | X | DNI T35 DEPANEL |  |  | 6/7 - BOT 10:00 6/10 - AOI | 75 | 320 | 2B 2T | 5 | 45 | FEDEX P | Ocean Aero, Inc. |  | 6/10 - side w/o CON2 & CON3 runs first | DOC REL 5/29 | 5/30 | 2821.73 | BOT 1ST | 2024-06-12 | 2 | 2024-06-10
2024-06-12 |  | 5/30 - KIT CLEAR |  |  | 1 |  |  | 124941 RONC 123510 | 20 | 6/12 10D | RT | RONC | *** QUALITY ALERT - PREVIOUS RUNS HAD EXCESS SOLDER INSIDE "P5" COMPONENT |  |  | 6/5 - BOT 12:00 6/6 - TOP 8:00 6/6 - AOI 11:00 | 106 | 341 | 1B 2T | 11 | 220 | UPS 3D | Coastal Designs, LLC |  |  | DOC REL 5/22 | 5/30 | 3650 | BOT 1ST | 2024-06-12 | 2 | 2024-06-05 | 9
2024-06-12 |  | 5/29 - KIT CLEAR |  |  |  | 1 |  | 126055 NEW | 40 | 6/12 10D | NN | X | USE LAYOUT FOR B120255 PER ECO "PS1" AFTER WASH DEPANEL |  |  | 6/3 - TOP 12:30 6/3 - AOI 3:30 | 15 | 44 | 1T | 8 | 320 | FEDEX P | Industrialex Manufacturing |  |  | DOC REL 5/22 | 5/29 | 2936 | TOP ONLY | 2024-06-12 | 1 |  | 3
2024-06-12 |  | 5/29 - SMT CLEAR 6/5 - KIT CLEAR |  |  | 1 |  |  | 125293 ROWC 124388 | 72 | 6/12 5D | RT | ROWC | for L1, use all of P/N SPDL485025-250-2P-T than ALT P/N WCM5555FASV-301-LM ***QUALITY ALERT FROM PREVIOUS BUILD - "U9" NOT MOUNTED FLAT AND SOLDER BRIDGE & "R27" HAD SURFACE DAMAGE CAUSING WRONG RESISTANCE INSTALL BATTERY MAX LEAD LENGTH "0.080 DEPANEL |  |  | 6/4 - BOT 9:00 6/4 - TOP 1:30 6/5 - AOI 11:00 | 73 | 292 | 1B 2T | 7 | 504 | FEDEX P | Protedyne Corporation - 3274-CTL062 |  |  | DOC REL 5/24 | 5/29 | 6449.76 | BOT 1ST | 2024-06-12 | 2 |  | 10
2024-06-12 |  | 5/30 - PCB DUE 5/29 - KIT CLEAR |  |  |  | 1 |  | 125146 NEW | 210 | 6/12 10D | NL | X | "U8" AFTER WASH DEPANEL |  |  | 5/31 - TOP 8:00 6/3 - AOI 3:30 | 53 | 124 | 2T | 3 | 630 | FEDEX GRD | Pivot International |  |  | DOC REL 5/9 | 5/13 | 6417.5 | TOP ONLY | 2024-06-12 | 1
2024-06-12 |  | 6/3 - SHORT #4 (C5) 6/5 - KIT CLEAR |  |  | 1 |  |  | 126085 NEW | 105 | 6/12 6/11 6/7 2D | NL | X | *** 2 DAY TURN *** SHIP QTY 10 T0: Solar Stik, Inc. 13 N Leonardi St Saint Augustine, FL 32084-3425 USA SHIP QTY 95 TO: Industrialex Manufacturing 6250 Joyce Dr Arvada, CO 80403 USA LEAD PROCESS DEPANEL |  |  | 6/6 - TOP 10:00 6/6 - AOI 12:00 | 10 | 15 | 1T | 8 | 840 | FEDEX P | Solar Stik, Inc. 10pcs / Industrialex Manufacturing 95pcs |  |  | DOC REL 6/3 | 6/3 | 9961.25 | TOP ONLY | 2024-06-07 | 1 | 2024-06-06 | 2
2024-06-12 |  | 2/8 - SHORT #10 (U1) & #7 (D10, D11...) NO ETA 2/9 - KIT CLEAR |  |  | 1 |  |  | 116954-2ND PAR RONC | 60 | 6/10 20D | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 120 no 0 OHM rework required U1 – P/N LTC2864MPS-1#PBF L1 – P/N MSS5131-393MLC J1 – P/N M80-5402042 DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/15 - TOP 1:00 2/16 - AOI 11:30 | 24 | 87 | 1T | 1 | 60 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2024-02-08 | 1104 | L1 IS P/N MSS5131-393MLC TOP ONLY | 2024-03-19 | 1 | 2024-02-15 | 6.5
2024-06-12 |  | 2/5 - SMT CLEAR |  |  | 1 |  |  | 116957-3RD PAR RONC | 60 | 6/10 20D | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 120 #3 (C4) ALT P/N UBT2A221MHD8TN DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/7 - BOT 11:00 2/7 - AOI 1:30 | 1 | 1 | 1B | 12 | 720 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2024-02-05 | 897.63 |  |  | 1 | 2024-02-07 | 2.5
2024-06-12 |  | 2/8 - SHORT #27A (U10) NO ETA 2/9 - KIT CLEAR |  |  | 1 |  |  | 116964-3RD PAR RONC | 60 | 6/10 20D | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 120 U8, U9 – LTC2864MPS-2#PBF U10 – LTC2864MPS-1#PBF DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/13 - BOT 8:30 2/13 - TOP 12:30 2/15 - AOI 9:00 | 68 | 264 | 2B 2T | 5 | 300 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2024-02-08 | 3156.95 | Customer wants to use a different part number for U8, U9 only, PN LTC2864MPS-2#PBF. U10, PN LTC2864MPS-1#PBF, will remain the same. BOT 1ST | 2024-03-19 | 2 | 2024-02-13 | 16.5
2024-06-12 |  | 2/7 - CLEARED FOR 190 BOARDS (60 BOARDS SHIPPED 2/14/24) 2/22 - SHORT U2 3/1 - KIT CLEAR |  |  |  |  | 2 | 116967-2ND PAR RONC | 60 | 6/10 20D | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 120 30119-102 00500+ J1 – p/n approved M80-5402042 DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 3/4 - TOP 7:30 | 37 | 89 | 1T | 2 | 120 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2/7 | 1182.67 | TOP ONLY | 2024-04-19 | 1 | 2024-02-14
2024-06-11 |  | 5/28 - KIT CLEAR | [5 empty] | 125865 NEW | 25 | 6/11 10D | X |  | THT ONLY *** NO BOARDHOUSE STAMPS *** |  |  | FSU | 0 | 0 | 0 | 1 | 25 | UPS GRD | Moxtek |  |  | DOC REL 5/24 | 5/28 | 1470 | THT ONLY | 2024-06-11
2024-06-11 |  | 6/6 - PCB DUE THAN SMT CLEAR 6/7 - KIT CLEAR | [5 empty] | 126183 NEW | 75 | 6/11 2D | NL | X | *** 2 DAY TURN *** DEPANEL |  |  | 6/10 - AOI | 14 | 29 | 1T | 7 | 525 | FEDEX P | Solar Stik, Inc. |  |  | DOC REL 6/4 | 6/4 | 6481.25 | top only | 2024-06-11 | 1
2024-06-11 |  | 2/7 - KIT CLEAR |  |  | 1 |  |  | 116956-2ND PAR RONC | 60 | 6/10 20D | NL | RONC | DNI #20 (FB8) SCHEDULED SHIPMENT: SHIP 60 OF 120 L1 – P/N 1264EY-330M=P3 J1 – P/N M80-5402042 DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/8 - BOT 10:00 2/9 - TOP 5:00 2/9 - STOP 2:30 2/15 - TOP 9:00 2/15 - AOI 1:00 | 28 | 121 | 1B 1T | 3 | 180 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2024-02-07 | 1641.16 | BOT 1ST | 2024-03-19 | 2 | 2024-02-15 | 20
2024-06-11 |  | 2/9 - #15 (IC2) DUE DATE 2/9 - KIT CLEAR |  |  |  | 1 |  | 116966-3RD PAR RONC | 60 | 6/10 20D | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 120 J1 – P/N M80-5402042 2 LABEL TYPES & LOCS TEXT LABEL & QR CODE ENSURE S/N MATCH LABELS SPECIFIED LOCATIONS DEPANEL XRAY & SVE |  |  | 2/13 - BOT 12:00 2/13 - TOP 2:00 2/15 - AOI 2:00 | 34 | 154 | 2B 2T | 1 | 60 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2/8 | 1680.63 | BOT 1ST | 2024-03-19 | 2 | 2024-02-13 | 14
2024-06-11 |  | 2/9 - SMT CLEAR; BUILT AND SHIPPED 60 ON 2/23 |  |  |  |  | 1 | 116970-2ND PAR RONC | 60 | 6/10 20D | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 120 L1 – P/N MSS5131-393MLC U2 – P/N LTC2864MPS-2#PBF DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/13 - TOP 9:00 2/13 - BOT 1:30 2/14 - AOI 12:00 | 29 | 54 | 2B 1T | 11 | 660 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2/8 | 1316.64 | L1 IS P/N MSS5131-393MLC BOT 1ST | 2024-03-19 | 2 | 2024-02-13 | 12
2024-06-11 |  | 2/5 - SMT CLEAR |  |  | 1 |  |  | 116955-3RD PAR RONC | 60 | 6/10 20D | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 120 SHORT #10 (J1,J2) P/N M80-5000000M2-02-331-00-000 DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/7 - TOP 9:00 2/7 - AOI 12:00 | 7 | 8 | 1T | 12 | 720 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2024-02-05 | 816 |  |  | 1 |  | 3
2024-06-11 |  | 2/5 - SMT CLEAR 2/7 - 60 PCBAS OF 360 CLEAR TO SHIP 2/19 2/14 - KIT CLEAR |  |  | 1 |  |  | 116950-3RD PAR RONC | 60 | 6/10 20D | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 120 LEAD PROCESS DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/7 - BOT 1:30 2/8 - AOI 11:00 | 6 | 16 | 1B 1T | 5 | 300 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2/5 | 781.58 |  |  | 2 | 2024-02-07 | 6.5
2024-06-10 |  | 6/4 - KIT CLEAR |  |  |  | 1 |  | 126100 RONC 123454 | 50 | 6/10 5D | NL | RONC | DEPANEL |  |  | 6/6 - BOT 12:00 6/7 - TOP 8:00 6/7 - AOI 10:00 | 6 | 36 | 1B 1T | 16 | 800 | FEDEX P | Diligent Robotics |  |  | DOC REL 6/3 | 6/4 | 1592 | BOT 1ST | 2024-06-10 | 2 | 2024-06-07 | 4
2024-06-10 |  | 5/31 - PCB DUE 5/24 - KIT CLEAR | [5 empty] | 125922 RONC 125313 | 32 | 6/10 10D | X |  | "SW1,2.3" AFTER WASH DEPANEL |  |  | FSU | 0 | 0 |  | 29 | 928 | FEDEX P | NSI-MI Technologies |  |  | DOC REL 5/16 |  | 3248
2024-06-10 |  | 6/3 - KIT CLEAR |  |  |  |  | 1 | 126212 NEW | 180 | 6/10 5D | NL | X | LEAD PROCESS DEPANEL |  |  | 6/6 - TOP 11:00 6/10 - AOI | 30 | 124 | 2T | 2 | 360 | FEDEX P | RX Monitoring Service, Inc. |  | 6/6 - AWT STENCIL | DOC REL 5/30 | 6/3 | 7509.6 | TOP ONLY | 2024-06-10 | 1 | 2024-06-06
2024-06-07 |  | 5/9 - KIT CLEAR | [5 empty] | 123601-4 PAR RWK | 60 | 6/7 20D |  | X | RWK - 355 BAL REMAINING SCHEDULED SHIPMENT 50-100 / WEEK |  |  | BACK |  |  |  | 0 | 0 | FEDEX P | NAL Research Corp
2024-06-07 |  | 5/23 - KIT CLEAR |  |  |  |  | 1 | 125805-2S BAL ROWC 122050 | 200 | 6/7 10D | NL | ROWC | SPLIT SHIPMENT: 2 O F 2 "U401" ADD EXTRA FLUX PER ECO XRAY & SAVE IMAGES DEPANEL |  |  | 5/28 - BOT 10:00 5/28 - TOP 1:00 5/29 - PAUSE 11:00 5/30 - TOP 10:00 5/31 - AOI 12:00 | 84 | 373 | 2B 2T | 0 | 0 | FEDEX GRD | Sea Land Aire |  |  | NO DOC. | 5/16 | 27602 | BOT 1ST | 2024-06-07 | 2 | 2024-05-24
2024-06-07 |  | 5/15 - SHORT PCB ¦ NO ETA 5/16 - KIT CLEAR | [5 empty] | 125278 NEW | 300 | 6/7 15D | X |  | THT ONLY REFER TO ECO/PHOTOS FOR INSTALLATION |  |  | BACK | 0 | 0 |  | 3 | 900 | UPS RED | PCM of NC, Inc. |  |  | DOC REL 5/15 |  | 1980
2024-06-07 |  | 5/29 - WILL CLEAR THIS WEEK 5/30 - KIT CLEAR |  |  | 1 |  |  | 126086-2 BAL RONC 124607 | 35 | 6/6 5D | RT | RONC | LEAD PROCESS DEPANEL |  |  | 6/1 - BOT 7:00 6/3 - TOP 6/3 - PAUSE 11:00 6/4 - TOP 7:00 6/4 - AOI 9:00 | 82 | 247 | 1B 2T | 8 | 280 | FEDEX P | RX Monitoring Service, Inc. |  | PEM DOES NOT FIT in 29 boards | NO DOC. | 5/29 | 8410 | BOT 1ST | 2024-06-06 | 2 |  | 13
2024-06-07 |  | 5/9 - SHORT PCB W/ NO ETA 5/24 - PCB DUE 5/23 - KIT CLEAR |  |  | 1 |  |  | 125697 NEW | 15 | 6/7 10D | NL | X | ***INSPECT PCB'S FOR VIA'S IN PAD BEFORE RUNNING*** |  |  | 5/30 - BOT 11:00 5/30 - TOP 2:30 5/31 - AOI 9:30 | 112 | 512 | 2B 2T | 2 | 30 | FEDEX P | Ocean Aero, Inc. |  |  | DOC REL 5/9 | 5/9 | 5022.5 | BOT 1ST | 2024-06-07 | 2
2024-06-07 |  | 5/15 - SHORT PCB ¦ NO ETA 5/16 - KIT CLEAR |  |  |  |  | 1 | 125398 NEW | 50 | 6/7 15D | NL | X | NO CLEAN PROCESS "U5" CHECK ROTATION PER ECO #1 |  |  | 5/21 - TOP 9:00 5/21 - BOT 2:00 5/21 - PAUSE 2:00 5/24 - BOT 8:30 5/24 - AOI 2:30 | 110 | 408 | 2B 1T | 2 | 100 | FEDEX GRD | McQ |  |  | DOC REL 5/13 | 5/15 | 7928.5 | TOP 1ST | 2024-06-07 | 2 | 2024-05-20 | 11
2024-06-07 |  | 6/6 - PCB DUE 6/4 - KIT CLEAR |  |  | 1 |  |  | 126042 NEW | 40 | 6/7 3D | NN | X | *** 3 DAY TURN *** "SW1" AFTER WASH MAKE SURE "J1 & J2" ARE INSTALLED - PREVIOUS BUILD ONLY REQ "J1" DEPANEL |  |  | 6/5 - TOP 11:00 6/5 - AOI 1:30 | 20 | 42 | 1T | 6 | 240 | FEDEX P | Draper Laboratory |  |  | DOC REL 5/29 | 5/30 | 4660 | TOP ONLY | 2024-06-07 | 1 |  | 2.5
2024-06-06 |  | 5/22 - KIT CLEAR |  |  |  | 1 |  | 125866 RONC 96659 | 20 | 6/6 10D | RT | RONC | *** "J601" DO NOT TRIM LEADS DEPANEL |  |  | 5/30 - BOT 9:00 5/30 - TOP 12:00 5/30 - AOI 4:30 | 72 | 285 | 1B 1T | 6 | 120 | FEDEX GRD | Case Western APT |  |  | NO DOC. | 5/22 | 2780 | BOT 1ST | 2024-06-06 | 2 |  | 7.5
2024-06-06 |  | 5/30 - KIT CLEAR |  |  |  | 1 | 1 | 125726 NEW | 40 | 6/6 5D | NN | X | CLASS 3 ENSURE BOARDS ARE CLEAN "MP1, 2, 3 ,4" SHIP BACK TO CUSTOMER WITH THE BOARDS |  |  | 6/4 - TOP 8:00 6/5 - BOT 11:00 6/6 - AOI 11:30 | 113 | 1051 | 2B 2T | 3 | 120 | FEDEX GRD | Anduril |  |  | NO DOC. | 5/30 | 21302 | TOP OR BOTTOM? top 1st | 2024-06-06 | 2 |  | 17.5
2024-06-06 |  | 5/17 - PCB DUE 5/21 - SMT CLEAR 5/22 - KIT CLEAR |  |  | 1 |  |  | 125536 NEW | 30 | 6/6 10D | NL | X | ITEM #39 (GND1...) BTD "K1, K2, MODE, ADH_SW" AFTER WASH DEPANEL |  |  | 5/29 - TOP 12:00 5/30 - AOI 8:00 | 50 | 138 | 1T | 14 | 420 | UPS RED | Daikin Applied |  |  | NO DOC. | 5/16 | 2340.6 | TOP 1ST | 2024-06-06 | 1 | 2024-05-28 | 4.5
2024-06-06 |  | 5/28 - will clear this week 5/30 - KIT CLEAR |  |  |  |  | 2 | 125951-2 BAL ROWC 125073 | 70 | 6/6 5D | RT | ROWC | SPLIT SHIPMENT: BAL OF 80 LEAD PROCESS DEPANEL |  |  | 6/1 - BOT 6/1 - TOP 6/3 - AOI | 37 | 213 | 1B 1T | 6 | 420 | FEDEX P | OnLogic |  |  | NO DOC. | 5/24 | 3446.1 | BOT 1ST | 2024-06-06 | 2
2024-06-06 |  | 5/21 - SHORT R277 5/22 - KIT CLEAR |  |  | 1 |  |  | 123722-2ND ROWC 1ST | 6 | 6/6 10D | RT | ROWC | DNI J2 ¦ R277 P/N CRCW0402100KFKTD LEAD PROCESS U1, U6, U24, U28, U30, J3 - XRAY & SAVE IMAGES DEPANEL AND SAND PER ECO #1 DO NOT LABEL PER ECO #4 |  |  | 5/30 - TOP 8:30 5/30 - AOI 11:00 | 106 | 540 | 2T | 83 | 498 | FEDEX P | X-Microwave - A Quantic Company |  | DO NOT RUN ON LINE 1 AGAIN to check for Open Solder and Misalignment issues | NO DOC. | 5/21 | 2435 | TOP ONLY | 2024-06-06 | 1 | 2024-05-31 | 2.5
2024-06-06 |  | 5/29 - WILL CLEAR THIS WEEK 5/30 - KIT CLEAR |  |  | 1 |  |  | 126086-1 PAR RONC 124607 | 110 | 6/6 5D | RT | RONC | LEAD PROCESS DEPANEL |  |  | 6/1 - BOT 7:00 6/3 - TOP 6/3 - PAUSE 11:00 6/4 - TOP 7:00 6/4 - AOI 9:00 | 82 | 247 | 1B 2T | 8 | 880 | FEDEX P | RX Monitoring Service, Inc. |  | PEM DOES NOT FIT in 29 boards | NO DOC. | 5/29 | 8410 | BOT 1ST | 2024-06-06 | 2 |  | 13
2024-06-05 |  | 5/29 - KIT CLEAR | [5 empty] | 125843-1 PAR NEW | 165 | 6/5 5D |  |  | THT ONLY DEPANEL |  |  | BACK |  |  |  | 1 | 165 | FEDEX P | Summit Santa Clara-Streamline Circuits |  |  | NO DOC. | 5/29 | 4275
2024-06-05 |  | 5/16 - MAY BE SMT CLEAR DATE 5/16 - SMT CLEAR 5/21 - KIT CLEAR |  |  | 1 |  |  | 125412 ROWC 125274 | 800 | 6/5 10D | NL | ROWC | ***FAB INSPECTION REQUIRED UPON RECEIVING INSPECTION - NO VENDORMAR KINGS/STAMPS ALLOWED. REPORT ASAP IF FOUND!!! NO IN HOUSE LABELS ALLOWED ***ADD SOLDER (CREATE SOLDER DOME) TO "J1" THRU-HOLE PER ECO #7 "L1" AFTER WASH TRIM THT PARTS TO SOLDER ROUNDING |  |  | 5/17 - TOP 10:00 5/21 - PAUSE 11:00 5/22 - TOP 8:00 5/22 - AOI 2:30 | 79 | 190 | 2T | 3 | 2400 | UPS RED | Moxtek |  |  | DOC REL 5/3 | 5/15 | 43440 | TOP ONLY | 2024-06-05 | 1 | 2024-05-16 | 23.5
2024-06-05 |  | 5/17 - PCB DUE 5/17 - SMT CLEAR 5/20 - KIT CLEAR |  |  |  | 1 |  | 125560 ROWC 118430 | 100 | 6/5 6/4 10D | NL | ROWC | CLASS 3 *NO QUALITY STAMPS ALLOWED ***SEE ECO NOTE #1 BEFORE RUNNING "U13 & U15" AFTER WASH "BATT1" REQ ADHISIVE PAD PRIOR TO SOLDERING PER ECO #4 "JP2 & JP3" REQ EPOXY PER ECO #6 "BATT1" ALSO REQ EPOXY PER ECO #4 "U16" INSTALL PER ECO #9 DEPANEL AND SAND |  |  | 5/28 - BOT 11:00 5/29 - TOP 9:00 5/29 - AOI 2:00 | 63 | 171 | 1B 1T | 6 | 600 | FEDEX GRD | Trendsetter Vulcan Offshore, Inc. |  |  | NO DOC. | 5/16 | 7267 | BOT 1ST | 2024-06-04 | 2 | 2024-05-24 | 9
2024-06-04 |  | 5/10 - PCB DUE 5/9 - KIT CLEAR |  |  |  | 1 |  | 124923 NEW | 20 | 5/23 10D | NL | X | EXPEDITE (FASTER THAN 10D) "J17 & J18" SEE ECO FOR PLACEMENT |  |  | 5/10 - BOT 2:00 5/13 - TOP 1:00 5/14 - AOI 8:00 | 113 | 254 | 1B 2T | 57 | 1140 | FEDEX P | HII Unmanned Systems, Inc |  |  | DOC REL 5/1 | 5/7 | 7950 | BOT 1ST | 2024-05-23 | 2 | 2024-05-13 | 9
2024-06-04 |  | 5/29 - SHORT #14(D1..) & #16(F1) THEN SMT CLEAR 6/3 - KIT CLEAR |  |  | 2 |  |  | 126168 NEW | 16 | 6/4 1D | NN | X | *** 1 DAY TURN *** DEPANEL & SAND |  |  | 6/3 - BOT 11:00 6/3 - TOP 1:30 6/4 - AOI 10:00 | 62 | 171 | 2B 2T | 3 | 48 | FEDEX P | Ergotron, Inc. |  |  | NO DOC. | 5/29 | 14110.8 | BOT 1ST | 2024-06-04 | 2
2024-06-04 |  | 5/28 - will clear this week 5/30 - KIT CLEAR |  |  |  |  | 2 | 125951-1 PAR ROWC 125073 | 10 | 6/4 3D | RT | ROWC | *** 3 day turn *** SPLIT SHIPMENT: 10 OF 80 ON 6/4 EXPEDITE LEAD PROCESS DEPANEL |  |  | 6/3 - AOI | 37 | 213 |  | 6 | 60 | FEDEX P | OnLogic |  |  | NO DOC. | 5/24 | 2862.3 | BOT 1ST | 2024-06-04 | 2
2024-06-04 |  | 5/14 - PCB DUE 5/9 - KIT CLEAR |  |  | 1 |  |  | 124988-2 BAL NEW | 1 | 5/31 15D | NL | X | "Z3-Z7" VERIFY PADS ARE MASKED OFF PER ECO #2 "T4, SW1, SW4" AFTER WASH SERIALIZE PER ECO #11 |  |  | 5/13 - BOT 1:30 5/14 - TOP 8:00 5/15 - AOI | 159 | 561 | 1B 3T | 47 | 47 | UPS RED | Farsounder, Inc. |  |  | DOC REL 5/1 | 5/8 | 9392.9 | BOT 1ST | 2024-05-31 | 3 | 2024-05-14
2024-06-04 |  | 5/23 - KIT CLEAR | [5 empty] | 123547-RWK RWK | 55 | 6/4 7D |  |  | QTY 1 : 7-DAY TURN (REMOVE & REPLACE 10 REF.DES W/ 0OHM) |  |  | BACK |  |  |  | 10 | 550 | UPS GRD | Jefferson Labs |  |  | NO DOC. | 5/23 | 5162.64 | BOT 1ST |  | 2
2024-06-04 |  | 5/20 - KIT CLEAR |  |  |  | 1 |  | 125863 RONC 122481 | 200 | 6/4 10D | RT | RONC | DEPANEL |  |  | 5/23 - BOT 8:00 5/24 - AOI 9:00 | 26 | 38 | 1B 1T | 4 | 800 | FEDEX P | Open Source Instruments Inc |  |  | NO DOC. | 5/20 | 1878 | bot 1st | 2024-06-04 | 2 | 2024-05-23
2024-06-04 |  | 5/29 - SHORT #25 (R22..) THEN SMT CLEAR 5/30 - KIT CLEAR |  |  |  |  | 2 | 125900 NEW | 10 | 6/4 6/3 2D | NN | X | *** 2 DAY TURN *** DEPANEL |  |  | 5/31 - AOI | 27 | 109 | 1B 1T | 8 | 80 | FEDEX P | Ergotron, Inc. |  |  | NO DOC. | 5/29 | 7532.5 | BOT 1ST | 2024-06-03 | 2
2024-06-03 |  | 5/29 - SHORT PCB ¦ ON HOLD 6/3 - PCB DUE 6/3 - KIT CLEAR |  |  |  |  | 1 | 126196 NEW | 10 | 6/3 1D | NN | X | *** 1-DAY TURN *** DEPANEL |  |  | RTR | 57 | 313 | 2T | 2 | 20 | FEDEX P | Ergotron, Inc. |  |  | NO DOC. | 5/29 | 16280 | TOP ONLY | 2024-06-03 | 1
2024-06-03 |  | 5/28 - SHORT PCB ¦ NO ETA 5/30 - KIT CLEAR |  |  |  |  | 1 | 126001 NEW | 23 | 6/3 2D | NN | X | *** 2 DAY TURN *** POST-WASH BAKE REQ J2 PLACE AS IS USE K3 & K4 FOOTPRINT (SEE ECO) DEPANEL |  |  | 5/31 - AOI | 14 | 56 | 1T | 2 | 46 | FEDEX P | Ergotron, Inc. |  |  | NO DOC. | 5/28 | 8819.5 | TOP ONLY | 2024-06-03 | 1
2024-05-31 |  | 5/9 - KIT CLEAR | [5 empty] | 123601-3 PAR RWK | 60 | 5/31 20D |  | X | RWK - 415 BAL REMAINING SCHEDULED SHIPMENT 50-100 / WEEK |  |  | BACK |  |  |  | 0 | 0 | FEDEX P | NAL Research Corp
2024-05-31 |  | 5/22 - PCB DUE 5/23 - PCB DUE 5/23 - KIT CLEAR |  |  |  |  | 1 | 125805-1S PAR ROWC 122050 | 50 | 5/31 5D | NL | ROWC | SPLIT SHIPMENT: 1 OF 2 "U401" ADD EXTRA FLUX PER ECO XRAY & SAVE IMAGES DEPANEL |  |  | 5/28 - BOT 10:00 5/28 - TOP 1:00 5/29 - AOI 11:00 | 84 | 373 | 2B 2T | 0 | 0 | FEDEX GRD | Sea Land Aire |  |  | NO DOC. | 5/16 | 6900.5 | BOT 1ST | 2024-05-31 | 2 | 2024-05-29 | 9
2024-05-31 |  | 5/23 - KIT CLEAR |  |  | 1 |  |  | 125498-1st NEW | 1 | 5/31 5D | NN | X | *** DOD DO-C9 *** (CUI/ITAR) |  |  | 5/28 - BOT 1:30 5/29 - TOP 7:00 5/29 - AOI 9:00 | 39 | 345 | 1B 1T | 5 | 5 | FEDEX P | Technology Service Corporation |  |  | NO DOC. | 5/23 | 5075.16 | BOT 1ST | 2024-05-31 | 2 | 2024-05-29 | 4
2024-05-31 |  | 5/6 - PCB DUE 5/1 - #2 (C3) DUE 5/10 - KIT CLEAR |  |  | 2 |  |  | 125315 ROWC 118184 | 100 | 5/31 15D | NL | ROWC | DEPANEL INSTALL FUSE HOLDER ACCORDING TO PICTURE (ECO) |  |  | 5/13 - TOP 11:30 5/13 - AOI 2:00 | 6 | 10 | 1T | 3 | 300 | FEDEX GRD | Boise State University |  |  | DOC REL 4/23 | 4/24 | 1380 | TOP ONLY | 2024-05-31 | 1 |  | 5
2024-05-31 |  | 5/14 - PCB DUE 5/9 - KIT CLEAR |  |  | 1 |  |  | 124988-1 PAR NEW | 30 | 5/31 15D | NL | X | "Z3-Z7" VERIFY PADS ARE MASKED OFF PER ECO #2 "T4, SW1, SW4" AFTER WASH SERIALIZE PER ECO #11 |  |  | 5/13 - BOT 1:30 5/14 - TOP 8:00 5/15 - AOI | 159 | 561 | 1B 3T | 47 | 1410 | UPS RED | Farsounder, Inc. |  |  | DOC REL 5/1 | 5/8 | 9392.9 | BOT 1ST | 2024-05-31 | 3 | 2024-05-14
2024-05-30 |  | 5/24 - PCB DUE 5/24 - KIT CLEAR |  |  |  |  | 1 | 125611 NEW | 17 | 5/30 3D | NN | X | *** 3 DAY TURN *** LEAD PROCESS DEPANEL |  |  | 5/28 - AOI | 26 | 137 | 2T | 4 | 68 | FEDEX P | Ocean Aero, Inc. |  |  | NO DOC. | 5/23 | 2755 | TOP ONLY | 2024-05-30 | 1 | 2024-05-28
2024-05-30 |  | 5/10 - SHORT 2 PCS OF #30 (U57..) 5/15 - KIT CLEAR 5/16 - ON HOLD DUE TO VIA HOLES |  |  |  |  | 1 | 125489 RONC 117696 | 10 | 5/30 10D | NL | RONC | "J1131 & U25" ENSURE VIA IN PAD HOLES ARE FILLED ***DO NOT LOSE ANY "J1131" SEE ECO #3 FOR PLACEMENT "SW3, SW521 SW152" AFTER WASH DEPANEL |  |  | 5/20 - BOT 9:00 5/20 - TOP 2:30 5/21 - AOI 11:30 | 80 | 410 | 1B 1T | 11 | 110 | FEDEX GRD | Protocol Insight, LLC |  |  | DOC REL 5/1 | 5/10 | 1600.4 | bot 1st | 2024-05-30 | 1 | 2024-05-20 | 11
2024-05-30 |  | 5/22 - SHORT PCB W/ NO ETA 5/29 - KIT CLEAR |  |  |  |  | 1 | 126002 NEW | 23 | 5/30 1D | NN | X | *** 1 DAY TURN *** FUSE INSTALL REQUIRED DEPANEL & SAND |  |  | 5/29 - BOT 11:30 5/29 - TOP 12:30 5/30 - AOI 10:00 | 106 | 365 | 1B 2T | 6 | 138 | FEDEX P | Ergotron, Inc. |  | Ergotron, Inc. | NO DOC. | 5/22 | 19900.06 | BOT 1ST | 2024-05-30 | 2 |  | 6.5
2024-05-29 |  | 4/30 - PCB DUE 4/22 - #6(U5,U6) & #8(AC1,AC2) 4/24 - SMT CLEAR 4/25 - KIT CLEAR |  |  | 1 |  |  | 125092-2 BAL RONC 113097 | 24 | 5/9 10D | NL | RONC | ***QUALITY ALERT - ALL LEADS MUST BE TRIMMED - CUST FOUND SOME LEADS WERE NOT TRIMMED*** DEPANEL |  |  | 4/24 - TOP 11:00 4/24 - AOI 6:30 | 1 | 2 | 1T | 51 | 1224 | FEDEX SAVER | Physical Measurement Technologies Inc |  |  | DOC REL 4/17 | 4/19 | 6900 | top only | 2024-05-09 | 1 | 2024-04-24 | 4
2024-05-29 |  | 5/14 - SHORT PCB 5/17 - #16 (R14) DUE 5/17 - PCB DUE 5/21 - KIT CLEAR |  |  |  | 1 |  | 124835 NEW | 25 | 5/29 5D | NL | X | NO ECO NOTES |  |  | 5/24 - BOT 11:00 5/24 - TOP 2:00 5/24 - AOI 4:00 | 17 | 79 | 1B 1T | 0 | 0 | FEDEX GRD | SRI |  |  | NO DOC. | 5/14 | 4610 | TOP 1ST | 2024-05-29 | 2 | 2024-05-24 | 5
2024-05-29 |  | 5/10 - PCB DUE 5/15 - ALMOST SMT CLEAR 5/22 - MAY CLEAR DATE 5/22 - SMT CLEAR 5/23 - KIT CLEAR |  |  | 1 |  |  | 124979 RONC 115393 | 30 | 5/29 3D | RL | RONC | *** 3 DAY TURN *** MECH ASSY REQ (HEATSINKS, THERMAL GREASE, HARDWARE ETC) PER ECO #2 BAR CODE LABELS REQ DEPANEL |  |  | 5/23 - TOP 1:30 5/24 - AOI 7:00 | 41 | 110 | 1T | 27 | 810 | FEDEX P | Piezo Systems (Div of Mide Technology) |  |  | NO DOC. | 5/7 | 3585 | TOP ONLY | 2024-05-29 | 1 | 2024-05-23 | 2
2024-05-29 |  | 5/17 - SHORT #2 (C5..) & #27 (RB1..) ¦ NO ETA 5/20 - WILL CLEAR THIS WEKK 5/21 - SMT CLEAR 5/21 - KIT CLEAR |  |  |  | 1 |  | 125564 RONC 123123 | 150 | 5/29 5D | NL | RONC | #27 (RB1...) BTD LEAD PROCESS |  |  | 5/22 - TOP 11:00 5/24 - AOI 11:00 | 34 | 257 | 1T | 13 | 1950 | FEDEX P | RX Monitoring Service, Inc. |  |  | DOC REL 5/3 | 5/20 | 9184.5 | TOP ONLY | 2024-05-31 | 1 | 2024-05-22 | 12
2024-05-28 |  | 5/24 - PCB DUE 5/24 - KIT CLEAR |  |  | 1 |  |  | 126071 NEW | 45 | 5/28 1D | OL | X | *** ONE DAY TURN *** DEPANEL |  |  | 5/28 - TOP 6:00 5/28 - AOI 7:00 | 1 | 3 |  | 1 | 45 | FEDEX P | Ergotron, Inc. |  |  | NO DOC. | 5/23 | 9215 | TOP ONLY | 2024-05-28 | 1
2024-05-28 |  | 5/22 - PCB DUE 5/22 - KIT CLEAR |  |  | 1 |  |  | 125999 NEW | 23 | 5/28 3D | NN | X | *** 3 DAY TURN *** TRIM LENGTHS (see ECO) |  |  | 5/23 - TOP 6:00 5/23 - AOI 9:30 | 16 | 33 | 1T | 5 | 115 | FEDEX P | Ergotron, Inc. |  |  | NO DOC. | 5/21 | 5444.25 | TOP ONLY | 2024-05-28 | 1 |  | 3.5
2024-05-28 |  | 5/22 - PCB DUE 5/22 - KIT CLEAR |  |  | 1 |  |  | 125996 ROWC 125496 | 23 | 5/28 3D | RT | ROWC | *** 3 DAY TURN *** "PZ1, SW1, SW2" AFTER WASH DEPANEL |  |  | 5/23 - BOT 8:00 5/23 - TOP 10:00 5/23 - AOI 2:00 | 89 | 339 | 1B 1T | 12 | 276 | FEDEX P | Ergotron, Inc. |  |  | NO DOC. | 5/21 | 11559.9 | BOT 1ST | 2024-05-28 | 2 | 2024-05-23 | 6
2024-05-28 |  | 5/15 - SHORT U35 (TOP SIDE) 5/20 - KIT CLEAR |  |  |  |  | 1 | 125344-2ND ROWC 1ST | 37 | 5/28 5D | NL | ROWC | "SW1 & RELATED" AFTER WASH DEPANEL |  |  | 5/22 - BOT 12:30 5/23 - TOP 8:00 5/24 - AOI 8:30 | 125 | 1137 | 1B 2T | 22 | 814 | FEDEX P | Nordson Corporation |  |  | NO DOC. | 5/15 | 16796.15 | BOT 1ST | 2024-05-28 | 2 | 2024-05-21
2024-05-28 |  | 5/17 - PCB DUE 5/13 - KIT CLEAR |  |  | 1 |  |  | 125148 NEW | 210 | 5/28 10D | NL | X | DEPANEL |  |  | 5/15 - TOP 9:00 5/16 - AOI 11:00 | 37 | 134 | 2T | 4 | 840 | FEDEX GRD | Pivot International |  |  | NO DOC. | 5/9 | 5905.2 | TOP ONLY | 2024-05-28 | 1 | 2024-05-14 | 10
2024-05-28 |  | 5/13 - KIT CLEAR |  |  | 1 |  |  | 119411 RONC 117353 | 110 | 5/28 10D | NL | RONC | BTD P1 CLASS 3 |  |  | 5/16 - BOT 10:30 5/16 - TOP 12:30 5/17 - AOI 7:00 | 22 | 45 | 1B 1T | 10 | 1100 | UPS 3D | Coastal Designs, LLC |  |  | NO DOC. | 5/13 | 3971 | BOT 1ST | 2024-05-28 | 2 | 2024-05-16 | 5
2024-05-24 |  | 5/15 - PCB DUE 5/17 - PCB DUE 5/17 - KIT CLEAR |  |  |  | 1 |  | 125612 NEW | 40 | 5/24 5D | NL | X | "SW!, PS1, U5, SW2" AFTER WASH DEPANEL MECH ASSY AND HARDWARE INSTALLED PER ECO #2 NO LEFT OVER FLUX ALLOWED - MUST BE REMOVED |  |  | 5/20 - TOP 8:00 5/21 - BOT 9:00 5/21 - AOI 3:30 | 145 | 560 | 2B 2T | 51 | 2040 | UPS RED | Reprieve Cardiovascular, Inc. |  | TOP 1ST DUE TO GUIDE PIN | DOC REL 5/3 | 5/7 | 16106 | BOT 1ST TOP 1ST | 2024-05-24 | 2 | 2024-05-20 | 13.5
2024-05-24 |  | 5/22 - PCB DUE 5/21 - KIT CLEAR |  |  |  | 1 |  | 125998 NEW | 23 | 5/24 3D | NN | X | *** 3 DAY TURN *** DEPANEL |  |  | 5/22 - TOP 8:00 5/22 - AOI 11:30 | 18 | 26 | 1T | 2 | 46 | FEDEX P | Ergotron, Inc. |  |  | NO DOC. | 5/20 | 4139 | TOP 1ST | 2024-05-24 | 1 |  | 3.5
2024-05-24 |  | 5/2 - PCB DUE 5/17 - KIT CLEAR |  |  |  |  | 1 | 122838 NEW | 4 | 5/24 5D | NL | X | ON HOLD "L7 & L10" CHANGED FROM 0402DC-2N8XJRW TO 0402DC-2N5XJRW "L8 & L9" CHANGED FROM 0402DC-3N5XGRW TO 0402DC-3N0XGRW POST BAKE "CIRC1" IF WASHED DEPANEL |  |  | 5/22 - BOT 5:00 5/22 - TOP 8:30 5/22 - AOI 2:30 | 113 | 408 | 1B 2T | 19 | 76 | FEDEX P | University Of Oklahoma |  |  | DOC REL 1/25 | 4/30 | 4786 | PART VERIFICATION BOT 1ST | 2024-05-24 | 2 |  | 9.5
2024-05-23 |  | 5/9 - KIT CLEAR | [5 empty] | 123601-2 PAR RWK | 60 | 5/23 |  | X | RWK - 475 BAL REMAINING SCHEDULED SHIPMENT 50-100 / WEEK |  |  | BACK |  |  |  | 0 | 0 | FEDEX P | NAL Research Corp
2024-05-22 |  | 5/21 - PCB DUE 5/21 - KIT CLEAR |  |  | 1 |  |  | 126006 NEW | 23 | 5/22 1D | NN | X | "U31" AFTER WASH DEPANEL & SAND |  |  | 5/21 - BOT 11:00 5/21 - TOP 2:30 5/22 - AOI 10:00 | 62 | 213 | 1B 2T | 3 | 69 | FEDEX P | Ergotron, Inc. |  |  | NO DOC. | 5/20 | 12696.7 | NO REFURBRISHED PARTS ALLOWED BOT 1ST | 2024-05-22 | 2 |  | 7
2024-05-22 |  | 5/15 - KIT CLEAR | [5 empty] | 125017 RMA | 15 | 5/22 5D | - |  | Install U22 on 15 boards. |  |  | BACK |  |  |  |  | 0 | FEDEX INT | Alphawave IP, Inc. |  |  | NO DOC. |  | 250
2024-05-22 |  | 5/9 - PCB DUE 5/2 - SHORT QTY 100 #1 (J2) NO ETA 5/8 - KIT CLEAR |  |  |  | 2 |  | 125375 RONC 124241 | 200 | 5/22 10D | NL | RONC | *** XTRA TIME FOR REFLOW *** LAST BUILD SPACED OUT OVER 3 DAYS WEAVING BETWEEN OTHER JOBS "J3-J6" SEE ECO FOR PLACEMENT DEPANEL |  |  | 5/14 - TOP 8:00 5/16 - AOI 12:00 | 3 | 6 | 1T | 0 | 0 | UPS GRD | Sick, Inc. |  |  | DOC REL 5/1 | 5/2 | 3180 | TOP ONLY | 2024-05-22 | 1 | 2024-05-13 | 20
2024-05-21 |  | 5/13 - SHORT PCB W/ NO ETA 5/14 - KIT CLEAR |  |  |  | 1 |  | 125449 NEW | 50 | 5/21 5D | NL | X | SER # REQ DEPANEL |  |  | 5/16 - BOT 11:30 5/16 - TOP 3:00 5/17 - AOI 12:00 | 58 | 242 | 1B 1T | 8 | 400 | UPS BLUE | DE Design Works |  |  | NO DOC. | 5/13 | 4067 | BOT 1ST | 2024-05-21 | 2 | 2024-05-15 | 6.5
2024-05-20 |  | 5/16 - PCB DUE 5/15 - KIT CLEAR |  |  |  |  | 1 | 124857 NEW | 3 | 5/20 5D | NL | X | EXPEDITE "Y4" PLACE AS IS UPDATE 4/23 NOW NO LOAD... "C98, C329, C409, R4, R127, R242, R275, R87, R188, R129, R247, R258, R281, R284, R285, R304" UPDATE 5/2 NOW NO LOAD... "R276" UPDATE 5/2 NOW LOAD... "R86, R275" XRAY & SAVE IMAGES *CAP STACK "C18" & RELATED PER ECO #4 "BT1, SW1, U21" PLACE AFTER WASH |  |  | 5/15 - BOT 6:00 5/16 - TOP 9:00 5/16 - AOI 2:30 | 116 | 677 | 2B 1T | 23 | 69 | FEDEX P | Nokomis |  |  | DOC REL 4/19 | 5/13 | 4841.65 | BOT 1ST | 2024-05-20 | 2 | 2024-05-16 | 8.5
2024-05-20 |  | 5/9 - PCB DUE 5/13 - PCB & #16 (U4) DUE 5/13 - KIT CLEAR |  |  |  |  | 1 | 125261 NEW | 12 | 5/20 5D | NL | X | SERIAL NUMBERS REQ |  |  | 5/14 - BOT 1:00 5/15 - TOP 10:00 5/15 - AOI 2:00 | 40 | 100 | 1B 1T | 2 | 24 | FEDEX P | CACI |  | 5/13 - DEPANEL AFTER SMT & BEFORE REFLOW REQUIRED | DOC REL 5/3 | 5/9 | 2288 | BOT 1ST | 2024-05-20 | 2 | 2024-05-14
2024-05-20 |  | 5/15 - SHORT PCB ¦ NO ETA 5/16 - KIT CLEAR | [5 empty] | 125794 RONC 125636 | 10 | 5/20 2D | X |  | *** 2 DAY TURN *** THT ONLY DEPANEL |  |  | FSU | 0 | 0 |  | 11 | 110 | FEDEX P | Ergotron, Inc. |  |  | NO DOC. |  | 3300
2024-05-17 |  | 4/11 - SHORT PCB & BAL OF #25(U2) 5/6 - KIT CLEAR |  |  | 1 |  |  | 124497 NEW | 25 | 5/20 10D | NL | X | LEAD PROCESS "U5" PLEASE VERIFY MASK OFF PAD PER ECO #3 |  |  | 5/8 - BOT 12:30 5/9 - TOP 5/9 - AOI 9:00 | 42 | 149 | 1B 1T | 0 | 0 | FEDEX P | Hoverfly Technologies Inc |  | 5/9 - insufficient solder on the sides of caps where it touches the shield | DOC REL 4/10 | 4/11 | 2475 | BOT 1ST 4/12 - HAVE STENCIL | 2024-05-20 | 2 |  | 5
2024-05-17 |  | 5/6 - KIT CLEAR |  |  |  | 2 |  | 125525 RONC 125385 | 65 | 5/20 10D | NL | RONC | SPLIT SHIPMENT (SEE PO) QTY 35 TO BIDDEFORD, ME QTY 30 TO NATICK, MA DEPANEL |  |  | 5/7 - BOT 10:00 5/7 - PAUSE 11:00 5/9 - BOT 8:00 5/9 - TOP 2:00 | 2 | 2 | 1B 1T | 0 | 0 | FEDEX P | Aila Technologies, Inc. |  |  | DOC REL 5/2 | 5/7 | 4030 | BOT 1ST | 2024-05-20 | 2 | 2024-05-09 | 6
2024-05-17 |  | 5/9 - PCB DUE 5/7 - #11(J1) DUE ¦ #10(L1) part conf 5/8 - KIT CLEAR |  |  | 1 |  |  | 125522-2S BAL NEW | 135 | 5/16 5D | NL | X | waive - ROSE testing & heat seal (EMAIL) ECO #6 - SHIP QTY 25 ON 5/13 & SHIP QTY 135 ON 5/16 (RUN ALL 160 AT ONCE) "D2 & D3" AFTER WASH QR CODE REQ SER # REQ depanel & sand |  |  | 5/9 - BOT 10:00 | 12 | 14 | 1B 1T | 0 | 0 | UPS RED | Carnegie Robotics |  |  | DOC REL 5/3 | 5/7 | 2793.6 | bot 1st | 2024-05-15 | 2 | 2024-05-09
2024-05-16 |  | 5/2 - KIT CLEAR |  |  |  | 2 |  | 125385 RONC 123855 | 50 | 5/16 10D | NL | RONC | do not ship EXCESS MATL DEPANEL |  |  | 5/6 - BOT 5/7 - TOP 5/7 - AOI | 2 | 2 | 1B 1T | 0 | 0 | FEDEX P | Aila Technologies, Inc. |  |  | DOC REL 5/1 | 5/2 | 3200 | BOT 1ST | 2024-05-16 | 2
2024-05-16 |  | 5/9 - KIT CLEAR | [5 empty] | 123601-1 PAR RWK | 60 | 5/16 |  | X | RWK - 535 BAL REMAINING SCHEDULED SHIPMENT 60 / WEEK |  |  | BACK |  |  |  | 0 | 0 | FEDEX P | NAL Research Corp
2024-05-16 |  | 5/9 - KIT CLEAR |  |  |  |  | 1 | 125716 NEW | 2 | 5/16 5D | NL | X | SW1, S2, SW35 & MIC2 AFTER WASH DEPANEL |  |  | 5/14 - BOT 9:00 5/14 - TOP 11:00 5/14 - AOI 1:00 | 83 | 831 | 1B 2T | 10 | 20 | UPS RED | Delsys, Inc. |  |  | NO DOC. | 5/9 | 5553 | BOT 1ST LARGE BOARD | 2024-05-16 | 2 | 2024-05-14
2024-05-16 |  | 4/16 - SHORT PCB, #63 (U35) & #69 (U33) 4/25 - PCB DUE 4/30 - PCB DUE 4/29 - KIT CLEAR 5/1 - part change (no longer clear) 5/2 - KIT CLEAR |  |  |  |  | 1 | 124127 NEW | 25 | 5/16 5/13 10D | NL | X | part change: C237, C260, C282 to GRM155R61H104KE19D LEAD PROCESS "U3" AFTER WASH ADD SOLDER TO SHIELD FRAME DEPANEL |  |  | 5/8 - TOP 9:00 5/9 - PAUSE 9:00 5/10 - BOT 8:00 5/13 - AOI 10:00 | 157 | 626 | 2B 2T | 12 | 300 | FEDEX P | Hoverfly Technologies Inc |  | 5/8 - TOP 1ST ¦ GUIDE PINS & TOO MANY LARGE BGAs ON BOTTOM 5/9 - TOP DONE | DOC REL 4/5 | 4/16 | 7225 | BOT 1ST | 2024-05-16 | 2 | 2024-05-09 | 18
2024-05-16 |  | 5/9 - KIT CLEAR |  |  | 1 |  |  | 124556-2nd ROWC 1st Article | 52 | 5/16 5D | NL | ROWC | "SW1" AFTER WASH DEPANEL |  |  | 5/10 - BOT 1:00 5/13 - TOP 7:00 5/13 - AOI 11:30 | 93 | 608 | 1B 2T | 7 | 364 | FEDEX P | ABB, Inc. |  |  | DOC REL 5/9 | 5/9 | 10710.44 | BOT 1ST | 2024-05-16 | 2 | 2024-05-10
2024-05-16 |  | 4/26 - SHORTAGES DUE 4/30 - AWT PART CONF (T1) 4/29 - KIT CLEAR |  |  |  | 1 |  | 125273-2 BAL NEW | 260 | 5/16 5/6 5D | NL | X | ship boards to FAB HOUSE to depanel JOB ON HOLD - FAB QUESTION ***FAB INSPECTION REQUIRED UPON RECEIVING INSPECTION - NO VENDORMARKINGS/STAMPS ALLOWED. REPORT ASAP IF FOUND!!! NO IN HOUSE LABELS ALLOWED ***ADD SOLDER (CREATE SOLDER DOME) TO "J1" THRU-HOLE PER ECO #7 "L1" AFTER WASH TRIM THT PARTS TO SOLDER ROUNDING |  |  | 5/1 - BOT 11:00 5/2 - TOP 11:30 5/3 - AOI 8:30 | 7 | 59 | 1B 1T | 2 | 520 | UPS GRD | Moxtek |  | 5/3 - DEPANEL CAUSES CAP PARTS TO FALL 5/7 - EXPECT TO RECEIVE 5/10 OR 5/13 | DOC REL 4/24 | 4/29 | 6120 | TOP 1ST | 2024-05-06 | 2 | 2024-05-01 | 9.5
2024-05-16 |  | 4/29 - SHORT PCBs 4/30 - PCB DUE 5/1 - KIT CLEAR |  |  |  |  | 1 | 124151 NEW | 400 | 5/16 5/15 10D | NL | X | LEAD PROCESS ***START SMT ON OR BEFORE DAY ONE - PCB'S ARE SINGLE UP - PLEASE ALLOW EXTRA TIME FOR SMT AND THRU HOLE |  |  | 5/2 - TOP 9:30 5/3 - AOI 10:30 | 29 | 56 | 1T | 4 | 1600 | UPS GRD | Technical Maintenance & Electronics Inc. |  |  | DOC REL 4/26 | 4/29 | 5640 | TOP ONLY | 2024-05-15 | 1 | 2024-05-03 | 9
2024-05-15 |  | 5/9 - PCB DUE 5/7 - #11(J1) DUE ¦ #10(L1) part conf 5/8 - KIT CLEAR |  |  | 1 |  |  | 125522-1S PAR NEW | 25 | 5/15 5D | NL | X | waive - ROSE testing & heat seal (EMAIL) ECO #6 - SHIP QTY 25 ON 5/13 & SHIP QTY 135 ON 5/16 (RUN ALL 160 AT ONCE) "D2 & D3" AFTER WASH QR CODE REQ SER # REQ depanel & sand |  |  | 5/9 - BOT 10:00 | 12 | 14 | 1B 1T | 0 | 0 | UPS RED | Carnegie Robotics |  |  | DOC REL 5/3 | 5/7 | 2793.6 | bot 1st | 2024-05-15 | 2 | 2024-05-09
2024-05-15 |  | 4/25 - SHORT PCB (NO ETA) 5/10 - PCB DUE 5/8 - KIT CLEAR |  |  | 1 |  |  | 125312-1ST NEW | 1 | 5/15 5D | NL | X | all alternate parts approved DEPANEL SW1 & RELATED PLACE AFTER WASH |  |  | 5/9 - BOT 2:00 5/10 - TOP 5/10 - AOI | 65 | 508 | 1B 1T | 11 | 11 | FEDEX P | Nordson Corporation |  |  | DOC REL 4/24 | 4/25 | 3027.8 | BOT 1ST | 2024-05-15 | 2 | 2024-05-10
2024-05-15 |  | 5/8 - 325 OF 400 CLEAR |  |  | 1 |  |  | 125153-1 PAR NEW | 325 | 5/15 5D | NL | X | ORDER IS FOR APPLE - PLEASE ENSURE GOOD QUALITY THROUGHOUT JUMPERS REQUIRED PER ECO DEPANEL & SAND |  |  | 5/10 - TOP 6:30 5/10 - AOI 9:30 | 4 | 4 | 1T | 2 | 650 | FEDEX P | Summit Santa Clara-Streamline Circuits |  | 5/8 - awt array file | NO DOC. | 5/8 | 5699 | TOP ONLY | 2024-05-15 | 1 | 2024-05-10
2024-05-15 |  | 5/10 - SHORT PCB 5/13 - PCB DUE |  |  |  |  | 2 | 125776 NEW | 20 | 5/16 2D | NL | X | *** 2 DAY TURN *** ***NO VENDOR STAMPS/MARKINGS ALLOWED*** ***SMT/ROBERT TO REVIEW SMT PLACEMENT FORCE SETTINGS FOR FRAGILE PARTS PER ECO #2 AND INSPECT FOR CRACKS AFTER REFLOW PER ECO #3 ***NO LABELS*** DEPANEL & SAND |  |  | 5/15 - AOI | 18 | 48 | 1B 1T | 0 | 0 | FEDEX P | Meta Platforms Technologies, LLC |  |  | NO DOC. | 5/10 | 1674.8 | BOT 1ST | 2024-05-16 | 2
2024-05-14 |  | 2/5 - SMT CLEAR 2/7 - 60 PCBAS OF 360 CLEAR TO SHIP 2/19 2/14 - KIT CLEAR |  |  | 1 |  |  | 116950-3RD BAL RONC | 60 | 5/14 20D | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 180 LEAD PROCESS DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/7 - BOT 1:30 2/8 - AOI 11:00 | 6 | 16 | 1B 1T | 5 | 300 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2/5 | 781.58 |  |  | 2 | 2024-02-07 | 6.5
2024-05-14 |  | 2/5 - SMT CLEAR |  |  | 1 |  |  | 116957-3RD BAL RONC | 60 | 5/14 20D | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 180 #3 (C4) ALT P/N UBT2A221MHD8TN DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/7 - BOT 11:00 2/7 - AOI 1:30 | 1 | 1 | 1B | 12 | 720 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2024-02-05 | 897.63 |  |  | 1 | 2024-02-07 | 2.5
2024-05-14 |  | 2/8 - SHORT #27A (U10) NO ETA 2/9 - KIT CLEAR |  |  | 1 |  |  | 116964-3RD PAR RONC | 60 | 5/14 20D | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 180 U8, U9 – LTC2864MPS-2#PBF U10 – LTC2864MPS-1#PBF DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/13 - BOT 8:30 2/13 - TOP 12:30 2/15 - AOI 9:00 | 68 | 264 | 2B 2T | 5 | 300 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2024-02-08 | 3156.95 | Customer wants to use a different part number for U8, U9 only, PN LTC2864MPS-2#PBF. U10, PN LTC2864MPS-1#PBF, will remain the same. BOT 1ST | 2024-03-19 | 2 | 2024-02-13 | 16.5
2024-05-14 |  | 2/9 - SMT CLEAR; BUILT AND SHIPPED 60 ON 2/23 |  |  |  |  | 1 | 116970-2ND PAR RONC | 60 | 5/14 20D | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 180 L1 – P/N MSS5131-393MLC U2 – P/N LTC2864MPS-2#PBF DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/13 - TOP 9:00 2/13 - BOT 1:30 2/14 - AOI 12:00 | 29 | 54 | 2B 1T | 11 | 660 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2/8 | 1316.64 | L1 IS P/N MSS5131-393MLC BOT 1ST | 2024-03-19 | 2 | 2024-02-13 | 12
2024-05-13 |  | 2/8 - SHORT #10 (U1) & #7 (D10, D11...) NO ETA 2/9 - KIT CLEAR |  |  | 1 |  |  | 116954-2ND BAL RONC | 60 | 5/14 20D | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 180 no 0 OHM rework required U1 – P/N LTC2864MPS-1#PBF L1 – P/N MSS5131-393MLC J1 – P/N M80-5402042 DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/15 - TOP 1:00 2/16 - AOI 11:30 | 24 | 87 | 1T | 1 | 60 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2024-02-08 | 1104 | L1 IS P/N MSS5131-393MLC TOP ONLY | 2024-03-19 | 1 | 2024-02-15 | 6.5
2024-05-13 |  | 2/5 - SMT CLEAR |  |  | 1 |  |  | 116955-3RD BAL RONC | 60 | 5/14 20D | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 180 SHORT #10 (J1,J2) P/N M80-5000000M2-02-331-00-000 DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/7 - TOP 9:00 2/7 - AOI 12:00 | 7 | 8 | 1T | 12 | 720 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2024-02-05 | 816 |  |  | 1 |  | 3
2024-05-13 |  | 2/9 - #15 (IC2) DUE DATE 2/9 - KIT CLEAR |  |  |  | 1 |  | 116966-3RD BAL RONC | 60 | 5/14 20D | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 180 J1 – P/N M80-5402042 2 LABEL TYPES & LOCS TEXT LABEL & QR CODE ENSURE S/N MATCH LABELS SPECIFIED LOCATIONS DEPANEL XRAY & SVE |  |  | 2/13 - BOT 12:00 2/13 - TOP 2:00 2/15 - AOI 2:00 | 34 | 154 | 2B 2T | 1 | 60 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2/8 | 1680.63 | BOT 1ST | 2024-03-19 | 2 | 2024-02-13 | 14
2024-05-13 |  | 2/7 - KIT CLEAR |  |  | 1 |  |  | 116956-2ND BAL RONC | 60 | 5/13 20D | NL | RONC | DNI #20 (FB8) SCHEDULED SHIPMENT: SHIP 60 OF 180 L1 – P/N 1264EY-330M=P3 J1 – P/N M80-5402042 DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/8 - BOT 10:00 2/9 - TOP 5:00 2/9 - STOP 2:30 2/15 - TOP 9:00 2/15 - AOI 1:00 | 28 | 121 | 1B 1T | 3 | 180 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2024-02-07 | 1641.168 | BOT 1ST | 2024-03-19 | 2 | 2024-02-15 | 20
2024-05-13 |  | 2/7 - CLEARED FOR 190 BOARDS (60 BOARDS SHIPPED 2/14/24) 2/22 - SHORT U2 3/1 - KIT CLEAR |  |  |  |  | 2 | 116967-2ND BAL RONC | 60 | 5/13 20D | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 180 30119-102 00500+ J1 – p/n approved M80-5402042 DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 3/4 - TOP 7:30 | 37 | 89 | 1T | 2 | 120 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2/7 | 1182.67 | TOP ONLY | 2024-04-19 | 1 | 2024-02-14
2024-05-13 |  | 5/8 - KIT CLEAR |  |  | 1 |  |  | 125121-1ST NEW | 2 | 5/13 3D | NL | X | *** 3 DAY TURN *** "U15" AFTER WASH DEPANEL NO SOLDER FLUX TO REMAIN ON BOARDS PER ECO #4 |  |  | 5/10 - BOT 7:30 5/10 - TOP 11:00 5/10 - AOI 12:00 | 44 | 98 | 1B 1T | 5 | 10 | FEDEX P | Industrialex Manufacturing |  | 6/11 - top 1st because of module | DOC REL 5/3 | 5/8 | 3557 | BOT 1ST | 2024-05-13 | 2 | 2024-05-10 | 4.5
2024-05-13 |  | 4/26 - SHORTAGES DUE 4/30 - AWT PART CONF (T1) 4/29 - KIT CLEAR |  |  |  | 1 |  | 125273-1 PAR NEW | 40 | 5/13 20D | NL | X | ship boards to FAB HOUSE to depanel JOB ON HOLD - FAB QUESTION ***FAB INSPECTION REQUIRED UPON RECEIVING INSPECTION - NO VENDORMARKINGS/STAMPS ALLOWED. REPORT ASAP IF FOUND!!! NO IN HOUSE LABELS ALLOWED ***ADD SOLDER (CREATE SOLDER DOME) TO "J1" THRU-HOLE PER ECO #7 "L1" AFTER WASH TRIM THT PARTS TO SOLDER ROUNDING |  |  | 5/1 - BOT 11:00 5/2 - TOP 11:30 5/3 - AOI 8:30 | 7 | 59 | 1B 1T | 2 | 80 | UPS GRD | Moxtek |  | 5/3 - DEPANEL CAUSES CAP PARTS TO FALL 5/7 - EXPECT TO RECEIVE 5/10 OR 5/13 | DOC REL 4/24 | 4/29 | 1596 | TOP 1ST | 2024-05-06 | 2 | 2024-05-01 | 9.5
2024-05-10 |  | 4/26 - KIT CLEAR |  |  | 2 |  |  | 124342 NEW | 50 | 5/10 10D | NL | X | U1 NEW P/N IS STM32H753XIH6 U213 DNI U13 P/N IS ECS-1612MV-250-CN-TR "U60" CONFIRM MASK OFF PER ECO #2 BEFORE SMT SERIAL # PER ECO #3 DEPANEL |  |  | 5/6 - TOP 5/7 - BOT 6:00 5/7 - AOI 11:00 | 102 | 502 | 2B 2T | 0 | 0 | FEDEX P | Allocortech Inc. |  |  | DOC REL 4/15 | 4/29 | 5547.5 | TOP 1ST | 2024-05-10 | 2
2024-05-10 |  | 5/10 - PCB DUE 5/7 - KIT CLEAR |  |  | 1 |  |  | 125344-1st NEW | 3 | 5/10 3D | NL | X | *** 3 DAY TURN *** "SW1 & RELATED" AFTER WASH DEPANEL |  |  | 5/7 - BOT 11:00 5/7 - PAUSE 6:00 5/7 - TOP 9:30 5/8 - AOI 12:30 | 124 | 1137 | 1B 2T | 32 | 96 | FEDEX P | Nordson Corporation |  |  | DOC REL 4/24 | 4/30 | 11307 | BOT 1ST LARGE PCB? | 2024-05-10 | 2 |  | 6.5
2024-05-10 |  | 4/16 - SHORT PCB W/ NO ETA 4/29 - PCB DUE 4/26 - KIT CLEAR |  |  | 1 |  |  | 125083 NEW | 5 | 5/10 10D | NL | X | SW9, SW10, SW11 - SW13 AFTER WASH INSERT D1-D12 INTO SO1-SO12 PRIOR TO SOLDERING INSTALL SW9-SW10 W/ BC1-BC2 DEPANEL |  |  | 5/6 - BOT 8:00 5/7 - AOI | 32 | 91 | 1B | 55 | 275 | FEDEX P | SynTech Systems / Fuelmaster |  |  | DOC REL 4/15 | 4/16 | 2791.75 | bot only | 2024-05-10 | 2
2024-05-10 |  | 5/7 - short PCB & #122 (x1) no ETA 5/9 - PCB DUE |  |  |  |  | 1 | 125652 NEW | 20 | 5/10 1D | NL | X | ***1 DAY TURN *** "U43" AFTER WASH "K2, K2" POST BAKE BOARDS IF WASHED DEPANEL & SAND SER # REQ |  |  | 5/9 - BOT 9:00 5/9 - PAUSE 11:00 5/9 - BOT 1:00 5/9 - TOP 3:00 5/9 - AOI 6:00 | 178 | 617 | 1B 3T | 22 | 440 | FEDEX P | Ergotron, Inc. |  | 5/9 - OK TO SKIP OVEN BAKE 5/9 - SETUP | NO DOC. | 5/7 | 39307.2 | BOT 1ST | 2024-05-10 | 3
2024-05-10 |  | 4/25 - PCB DUE 4/26 - KIT CLEAR |  |  |  |  | 1 | 124125 NEW | 25 | 5/10 10D | NL | X | "BT1" LEAVE PASTE ON CENTER PAD DEPANEL |  |  | 4/30 - BOT 8:00 4/30 - TOP 10:30 4/30 - AOI 2:00 | 103 | 344 | 1B 2T | 22 | 550 | FEDEX P | Hoverfly Technologies Inc |  |  | DOC REL 4/4 | 4/12 | 3425 | BOT 1ST 4/12 - HAVE STENCIL | 2024-05-10 | 2 | 2024-04-29 | 6
2024-05-09 |  | 4/25 - PCB DUE 4/25 - KIT CLEAR 4/25 - JOB ON HOLD (NEW BOM) 4/25 - KIT CLEAR |  |  | 1 |  |  | 124495 NEW | 25 | 5/9 10D | NL | X | *** ON HOLD *** LEAD PROCESS ADD SOLDER TO SHIELD FRAME |  |  | 4/29 - BOT 6:00 4/29 - TOP 8:30 4/29 - AOI 2:30 | 86 | 505 | 1B 1T | 0 | 0 | FEDEX P | Hoverfly Technologies Inc |  |  | DOC REL 4/10 | 4/17 | 4175 | BOT 1ST | 2024-05-09 | 2 | 2024-04-26 | 8
2024-05-09 |  | 4/25 - KIT CLEAR |  |  |  | 1 |  | 125359 RONC 107399 | 200 | 5/9 10D | NL | RONC | DEPANEL "LS1" AFTER WASH |  |  | 4/30 - BOT 8:00 4/30 - TOP 11:30 5/1 - PAUSE 11:00 5/3 - TOP 9:00 5/3 - AOI 2:00 | 15 | 33 | 1B 1T | 0 | 0 | FEDEX P | RX Monitoring Service, Inc. |  |  | DOC REL 4/23 | 4/25 | 3182 | BOT 1ST | 2024-05-09 | 2 | 2024-05-02 | 14
2024-05-09 |  | 5/2 - KIT CLEAR |  |  |  |  | 1 | 125253 NEW | 18 | 5/9 5D | NL | X | DEPANEL |  |  | 5/6 - BOT 6:00 5/7 - TOP 6:00 5/8 - AOI 6:00 | 76 | 2228 | 2B 1T | 7 | 126 | FEDEX GRD | Alpheus Medical Inc |  |  | DOC REL 5/1 | 5/2 | 22618.56 | BOT 1ST | 2024-05-09 | 2 |  | 17
2024-05-09 |  | 4/25 - KIT CLEAR |  |  | 1 |  |  | 124627 NEW | 10 | 5/9 10D | NL | X | ECO NOTES 2, 3 &4 ARE WAIVED (NOT REQUIRED) "U9" AFTER WASH 5/6/24 UPDATE - ITEM #90 IS NOW DNI POST BAKE FOR 30 MIN IF BOARDS ARE WASHED PER ECO #6 DEPANEL LABEL PER ECO #9 |  |  | 5/3 - BOT 7:00 5/3 - TOP 9:00 5/6 - AOI 7:00 | 126 | 996 | 1B 2T | 31 | 310 | UPS RED | Innomotics, LLC / Siemens Industry |  |  | DOC REL 4/8 | 4/25 | 7711.5 | CUST RTV & H/S NOT SELECTIVE SOLDER (JOE) SELECTIVE SOLDER WAIVED (4/24 - TAD) | 2024-05-09 | 2 |  | 8
2024-05-09 |  | 4/30 - PCB DUE 4/22 - #6(U5,U6) & #8(AC1,AC2) 4/24 - SMT CLEAR 4/25 - KIT CLEAR |  |  | 1 |  |  | 125092-1 PAR RONC 113097 | 176 | 5/9 10D | NL | RONC | ***QUALITY ALERT - ALL LEADS MUST BE TRIMMED - CUST FOUND SOME LEADS WERE NOT TRIMMED*** DEPANEL |  |  | 4/24 - TOP 11:00 4/24 - AOI 6:30 | 1 | 2 | 1T | 51 | 8976 | FEDEX SAVER | Physical Measurement Technologies Inc |  |  | DOC REL 4/17 | 4/19 | 6900 | top only | 2024-05-09 | 1 | 2024-04-24 | 4
2024-05-08 |  | 4/25 - KIT CLEAR 4/26 - ON HOLD 4/29 - KIT CLEAR |  |  | 1 |  |  | 125456 NEW | 399 | 5/8 5/2 5D 7D | NL | X | *** 2 DAYS GIVEN TO DEPANEL *** DEPANEL |  |  | 4/29 - TOP 12:30 4/30 - AOI 10:00 | 3 | 4 | 1T | 0 | 0 | FEDEX P | Gentex Corporation (MI) |  | 4/26 - no mousebites on PCBs 4/29 - CUST PAID FOR US TO DEPANEL 4/29 - INCORRECT STENCIL | DOC REL 4/25 | 4/25 | 4650.6 | TOP ONLY | 2024-05-08 | 1 | 2024-04-26 | 6
2024-05-08 |  | 5/6 - SHORT PARTS + PCB NO ETA 5/8 - F1 DUE |  |  | 1 |  |  | 125637 NEW | 20 | 5/8 1D | NL | X | *** 1 DAY TURN *** "LS1" AFTER WASH DEPANEL |  |  | 5/8 - AOI | 52 | 136 | 1T | 4 | 80 | FEDEX P | Ergotron, Inc. |  |  | DOC REL 5/6 | 5/7 | 8240 | TOP ONLY | 2024-05-08 | 1
2024-05-08 |  | 5/6 - PCB'S DUE 5/7 - KIT CLEAR | [5 empty] | 125636 NEW | 20 | 5/8 5/9 2D | X |  | expedite to 1-day turn *** 2 DAY TURN *** THT ONLY "P1 & RELATED" HEIGHT REQUIREMENT PER ECO #3 |  |  | FSU | 0 | 0 |  | 11 | 220 | FEDEX P | Ergotron, Inc. |  |  | DOC REL 5/2 | 5/6 | 4550
2024-05-08 |  | 4/29 - PCB DUE 5/3 - PCB DUE 5/3 - KIT CLEAR |  |  |  | 1 |  | 124815 NEW | 20 | 5/8 3D | NL | X | *** 3 DAY TURN *** "SW1, SW2, S2" AFTER WASH XRAY & SAVE IMAGES CofC PER ECO #6 SHIP MATL W/ PCBAs ***EMAIL TRACKING NUMBER TO CUST AS SOON AS IT IS AVAILABLE |  |  | 5/7 - BOT 10:00 5/7 - TOP 2:00 5/8 - AOI 8:00 | 103 | 444 | 1B 2T | 27 | 540 | FEDEX P | South Coast Circuits, Inc. |  |  | DOC REL 4/23 | 4/25 | 5850.2 | BOT 1ST | 2024-05-08 | 2 |  | 4.5
2024-05-07 |  | 4/29 - TECHNICALLY CLEAR, BUT MAY HAVE MORE TIME FOR #31 (D14..) --- LOOSE PARTS |  |  |  |  | 1 | 123853-1st NEW | 8 | 5/3 5D | NL | X | XRAY & SAVE PER ECO #2 DEPANEL AND SAND PER ECO #1 - (PLEASE READ) NO LABEL REQUIRED |  |  | 5/1 - TOP 2:00 5/2 - AOI 10:30 | 88 | 350 | 2T | 1 | 8 | FEDEX P | X-Microwave (A Quantic Company) |  | 5/3 - awt customer reply on whethr to label the boards for XRay requirements or not | DOC REL 4/25 | 4/29 | 3710 | TOP ONLY | 2024-05-03 | 1 | 2024-04-30 | 5
2024-05-07 |  | 4/16 - SHORTAGES DUE 4/24 - KIT CLEAR |  |  | 1 |  |  | 124129 NEW | 60 | 5/8 10D | NL | X | LEAD PROCESS ADD SOLDER TO SHIELD FRAME |  |  | 4/26 - AOI | 17 | 36 | 1T | 0 | 0 | FEDEX P | Hoverfly Technologies Inc |  |  | DOC REL 4/5 | 4/12 | 3920 | top only | 2024-05-08 | 1 | 2024-04-25
2024-05-07 |  | 4/23 - PCB DUE | [5 empty] | 125313 NEW | 18 | 5/8 10D | X |  | THT ONLY SW1 - SW3 PLACE AFTER WASH INSTALL TOGETHER J9, J10 W/ J9_1, J10_1 |  |  | FSU | 0 | 0 |  | 29 | 522 | FEDEX P | NSI-MI Technologies |  |  | DOC REL 4/23 | 4/23 | 1957.5 |  |  | 2
2024-05-07 |  | 5/6 - PCB'S DUE | [5 empty] | 125635 NEW | 30 | 5/7 1D | X |  | ***1 DAY TURN *** IF PCB ARRIVES 5/6/24, MUST SHIP 5/7/27 THT ONLY DISREGARD DWG NOTES #4 & 5 |  |  | FSU | 0 | 0 |  | 2 | 60 | FEDEX P | Ergotron, Inc. |  |  | DOC REL 5/3 | 5/6 | 4560
2024-05-06 |  | 4/9 - SHORT PCB 4/18 - PCB DUE 4/22 - KIT CLEAR |  |  |  | 1 |  | 121981 NEW | 25 | 5/6 10D | NL | X | LEAD PROCESS ADD SOLDER TO SHIELD FRAME DEPANEL |  |  | 4/25 - BOT 7:00 4/25 - TOP 9:30 4/25 - AOI 12:00 | 38 | 174 | 1B 1T | 0 | 0 | FEDEX P | Hoverfly Technologies Inc |  |  | DOC REL 4/4 | 4/9 | 2475 | BOT 1ST | 2024-05-06 | 2 | 2024-04-24 | 5
2024-05-06 |  | 4/22 - #50(U41,U42) SHORT DUE (OK TO SKIP) 4/22 - KIT CLEAR |  |  |  |  | 2 | 124503 NEW | 10 | 5/6 10D | NL | X | LEAD PROCESS CLASS 3 DEPANEL LABEL PER ECO #5 CofC REQ S/N OF BOARDS |  |  | 4/24 - BOT 12:30 4/24 - TOP 9:00 4/26 - aoi | 150 | 542 | 1B 2T | 0 | 0 | FEDEX P | Aeronix Inc |  |  | DOC REL 4/18 | 4/19 | 4623 | BOT 1ST | 2024-05-06 | 2 | 2024-04-23
2024-05-06 |  | 5/1 - PCB DUE 4/29 - KIT CLEAR |  |  | 1 |  |  | 125017 NEW | 20 | 5/6 5D | NL | X | ***NO SOLDER ON DNI PASTE PADS - PLEASE VERIFY PRIOR TO RUNNING 4/17 ADDED TO ECO...*RS1 – RS4 (HCJ2512ZT0R00): Mix pop. For 2 boards (SN: 001-002), install RS2, RS4 and DNI RS1, RS3 For 18 boards (SN: 003-020), install RS1, RS3 and DNI RS2, RS4 |  |  | 4/30 - BOT 12:30 5/1 - TOP 5/1 - AOI 10:30 | 93 | 508 | 1B 2T | 34 | 680 | FEDEX INTERNATIONAL | Alphawave IP Inc. |  |  | DOC REL 4/8 | 4/12 | 7220 | BOT 1ST | 2024-05-06 | 2 |  | 6.5
2024-05-06 |  | 4/26 - EXPECTED SMT CLEAR DATE 4/29 - KIT CLEAR |  |  | 1 |  |  | 125280 ROWC 124685 | 25 | 5/6 5D | NL | ROWC | SHIP SCREWS WITH PCBAS LEAVE CAGES FULLY OPEN ORIENT SW2 & L8 ACCORDING TO ECO MOUNTING SUPPORTS FROM BOTTOM TRIM LEADS TO MAX HEIGHT (ECO) SOLDER MAX HEIGHT (ECO) ENSURE MASK OFF 4 D34 PADS (ECO) DEPANEL |  |  | 4/30 - TOP 10:00 4/30 - AOI 12:30 | 57 | 218 | 1T | 30 | 750 | FEDEX P | Friedrich Air Conditioning LLC |  |  | DOC REL 4/23 | 4/25 | 2939.5 | TOP ONLY | 2024-05-06 | 1 |  | 2.5
2024-05-06 |  | 4/29 - SHORTAGES DUE 4/29 - KIT CLEAR |  |  | 1 |  |  | 125274 NEW | 300 | 5/6 5D | NL | X | ***FAB INSPECTION REQUIRED UPON RECEIVING INSPECTION - NO VENDORMARKINGS/STAMPS ALLOWED. REPORT ASAP IF FOUND!!! NO IN HOUSE LABELS ALLOWED |  |  | 5/1 - TOP 12:00 5/3 - AOI 7:00 | 79 | 190 | 2T | 3 | 900 | UPS GRD | Moxtek |  |  | DOC REL 4/24 | 4/29 | 21180 | TOP ONLY | 2024-05-06 | 1 | 2024-04-30 | 11.5
2024-05-03 |  | 4/23 - PCB DUE 4/19 - KIT CLEAR |  |  | 1 |  |  | 121967 NEW | 50 | 5/3 10D | NL | X | LEAD/NO CLEAN PROCESS "BT1" PLACE AFTER REFLOW DEPANEL |  |  | 4/23 - BOT 2:00 4/24 - TOP 4/24 - AOI 9:30 | 29 | 48 | 1B 1T | 1 | 50 | FEDEX P | Hoverfly Technologies Inc |  |  | DOC REL 4/3 | 4/11 | 2200 | BOT 1ST | 2024-05-03 | 2 | 2024-04-24 | 4
2024-05-02 |  | 4/23 - KIT CLEAR (MAY HAVE MORE TIME FOR ATTRITION "ANNE") |  |  | 2 |  |  | 125047 NEW | 180 | 5/7 10D | NL | X | LEAD PROCESS PS1 AFTER WASH |  |  | 4/25 - TOP 11:30 4/26 - AOI 7:00 | 17 | 32 | 1T | 5 | 900 | FEDEX P | RX Monitoring Service, Inc. |  |  | DOC REL 4/23 | 4/23 | 4076 | TOP 1ST | 2024-05-07 | 1 | 2024-04-25 | 4
2024-05-02 |  | 4/25 - KIT CLEAR |  |  |  | 1 |  | 123504-2ND NEW | 8 | 5/9 10D | NL | X | install U8 as-is w/o removing solder layer (per email) J14_PIN1_2, J15_PIN1_2, J15_PIN3_4, J15_PIN5_6, J16_PIN2_3 (WIRE) - RWK PER ECO #2 |  |  | 4/26 - BOT 12:30 4/29 - TOP 9:00 4/29 - AOI 1:30 | 92 | 1054 | 1B 2T | 12 | 96 | FEDEX INTER | System-On-Chip Technologies |  |  | DOC REL 3/7 | 4/25 | 2384.32 | BOT 1ST | 2024-05-09 | 2 | 2024-04-26 | 5
2024-05-02 |  | 4/9 - SHORT PCB 4/18 - PCB DUE 4/18 - KIT CLEAR |  |  |  |  | 1 | 121984 NEW | 75 | 5/2 10D | NL | X | LEAD PROCESS DEPANEL |  |  | 4/24 - BOT 7:00 4/24 - TOP 4/24 - AOI 11:30 | 5 | 21 | 1B 1T | 0 | 0 | FEDEX P | Hoverfly Technologies Inc |  |  | DOC REL 4/4 | 4/9 | 2300 | BOT 1ST | 2024-05-02 | 2 | 2024-04-18 | 4.5
2024-05-02 |  | 4/10 - SHORT PCB 4/18 - PCB DUE 4/19 - KIT CLEAR |  |  |  |  | 1 | 121971 NEW | 25 | 5/3 10D | NL | X | LEAD PROCESS DEPANEL |  |  | 4/23 - BOT 11:30 4/23 - TOP 4/24 - AOI 2:30 | 8 | 29 | 1B 1T | 0 | 0 | FEDEX P | Hoverfly Technologies Inc |  |  | DOC REL 4/3 | 4/10 | 2200 | BOT 1ST | 2024-05-03 | 2 | 2024-04-24 | 3
2024-05-01 |  | 4/25 - PCB DUE 4/18 - KIT CLEAR |  |  |  |  | 1 | 125000 RONC 122634 | 75 | 5/2 10D | NL | RONC | "S1A, S1B" AFTER WASH SERIAL # PER ECO #3 SERIAL # MUST BE LISTED ON CofC PER ECO |  |  | 4/18 - BOT 2:30 4/19 - PAUSE 7:00 4/19 - BOT 10:00 4/19 - TOP 12:00 4/22 - AOI 10:30 | 53 | 205 | 1B 1T | 2 | 150 | UPS GRD | Churchill Navigation dba Shotover Systems Inc |  | 4/19 - AWT BARE PCB REVIEW | DOC REL 4/15 | 4/16 | 4864.5 | BOT 1ST | 2024-05-02 | 2 | 2024-04-18 | 8
2024-05-01 |  | 4/8 - SHORT PCB 4/18 - PCB DUE 4/18 - KIT CLEAR |  |  | 1 |  |  | 121980 NEW | 25 | 5/2 10D | NL | X | LEAD PROCESS DEPANEL |  |  | 4/19 - BOT 10:00 4/19 - TOP 11:00 4/22 - AOI 10:30 | 33 | 148 | 1B 1T | 6 | 150 | FEDEX P | Hoverfly Technologies Inc |  |  | DOC REL 4/4 | 4/8 | 3000 | bot 1st | 2024-05-02 | 2 | 2024-04-18 | 9
2024-05-01 |  | 4/25 - SHORT U2_5 (SKIPPABLE) 4/26 - U2_5 DUE DATE 4/26 - KIT CLEAR |  |  |  |  | 1 | 124290-2nd ROWC 1st Article | 24 | 5/1 3D | NL | ROWC | *** 3 DAY TURN *** U2_5 changed to LT6108IMS8-2#PBF |  |  | 4/29 - BOT 12:30 4/29 - TOP 2:30 4/29 - AOI 9:00 | 82 | 390 | 1B 1T | 23 | 552 | FEDEX P | ABB Inc. |  |  | DOC REL 4/24 | 4/25 | 5251 | BOT 1ST | 2024-05-01 | 2 | 2024-04-26 | 5
2024-04-30 |  | 10/24 - SHORT #37 (R7A..) 10/26 - KIT CLEAR |  |  | 1 |  |  | 121032-2 BAL NEW | 25 | 4/30 10D | NL | X | BAKE BOARDS BEFORE SHIPPING SOLDER GUIDE PINS NO SHIP EARLY SPLIT SHIPMENT: QTY 25 DUE 11/17/23 QTY 25 DUE 4/30/24 DEPANEL |  |  | 11/2 - TOP 2:00 11/3 - AOI 12:00 | 48 | 313 | 1T | 28 | 700 | FEDEX GRD | Machine Solutions Inc |  |  | DOC REL 10/24 | 2023-10-24 | 7460 | LF; | 2023-11-17 | 1 | 2023-11-02 | 7.5
2024-04-30 |  | 4/17 - #7 (J3) DUE SHORT PCB (NO ETA) 4/29 - PCB DUE 4/22 - KIT CLEAR |  |  | 1 |  |  | 124496 NEW | 10 | 5/6 10D | NL | X | LEAD PROCESS DEPANEL |  |  | 4/24 - TOP 10:00 4/24 - AOI 12:30 | 9 | 16 | 1T | 1 | 10 | FEDEX P | Hoverfly Technologies Inc |  |  | DOC REL 4/10 | 4/11 | 2110 | TOP ONLY | 2024-05-06 | 1 | 2024-04-24 | 2.5
2024-04-30 |  | 4/23 - PCB DUE 4/18 - KIT CLEAR |  |  | 1 |  |  | 124493 NEW | 25 | 5/2 10D | NL | X | LEAD PROCESS "U3" AFTER WASH DEPANEL |  |  | 4/19 - BOT 1:30 4/22 - TOP 4/22 - AOI 8:30 | 31 | 60 | 1B 1T | 7 | 175 | FEDEX P | Hoverfly Technologies Inc |  |  | DOC REL 4/9 | 4/16 | 2175 | 4/12 - HAVE STENCIL BOT 1ST | 2024-05-02 | 2 | 2024-04-19 | 4
2024-04-30 |  | 4/23 - KIT CLEAR |  |  | 1 |  |  | 125225 ROWC 119913 | 59 | 4/30 5D | NL | ROWC | U15 FLUSH WITH BOARD |  |  | 4/25 - BOT 4/25 - TOP 9:00 4/25 - PAUSE 11:30 4/25 - TOP 6:30 4/25 - AOI 8:00 | 47 | 139 | 1B 1T | 6 | 354 | FEDEX P | Atlas Devices |  | 4/25 - MODIFY STENCIL | DOC REL 4/23 | 4/23 | 2891 | bot 1st | 2024-04-30 | 2 | 2024-04-25
2024-04-30 |  | 4/25 - KIT CLEAR |  |  |  |  | 2 | 125211 RONC 118965 | 20 | 4/30 3D | NL | RONC | *** 3 DAY TURN *** DEPANEL & SAND CofC REQUIREMENTS |  |  | 4/26 - AOI | 21 | 229 | 1T | 37 | 740 | FEDEX P | RollPros, LLC |  |  | DOC REL 4/25 | 4/25 | 3166.4 | TOP ONLY | 2024-04-30 | 1 | 2024-04-26
2024-04-29 |  | 4/15 - KIT CLEAR FOR 99 OF 150 |  |  | 1 |  |  | 124791-1 PAR NEW | 99 | 5/6 15D | NL | X | RUN PARTIAL 99 OF 150 DEPANEL & SAND PER ECO LABEL EACH ESD BAG PER ECO #3 |  |  | 4/18 - BOT 2:30 4/19 - TOP 8:00 4/19 - AOI 10:30 | 11 | 17 | 1B 1T | 0 | 0 | UPS RED | Onward Robotics |  |  | DOC REL 4/8 | 4/15 | 3350 | BOT 1ST | 2024-05-06 | 1 | 2024-04-18 | 4.5
2024-04-29 |  | 4/18 - PCB DUE; NO ETA #12(J1) 4/17 - SMT CLEAR 4/18 - KIT CLEAR |  |  |  | 1 |  | 124128 NEW | 100 | 5/2 10D | NL | X | LEAD PROCESS "C3 & C4" ARE NOW DNI FOR THIS BUILD ONLY INSTALL "J1" HARDWARE BEFORE SOLDERING DEPANEL |  |  | 4/18 - BOT 12:30 4/18 - TOP 2:00 4/19 - AOI 2:30 | 12 | 18 | 1B 1T | 4 | 400 | FEDEX P | Hoverfly Technologies Inc |  |  | DOC REL 4/5 | 4/12 | 2800 | bot 1st | 2024-05-02 | 2 | 2024-04-19 | 8
2024-04-29 |  | 4/29 - EXPECTED CLEAR DATE |  |  |  |  | 1 | 125496 NEW | 15 | 4/29 1D | NL | X | *** 1 DAY TURN *** PZ1 PLACE AFTER WASH DEPANEL |  |  | 4/29 - BOT 6:00 4/29 - TOP 8:30 4/29 - AOI 1:00 | 89 | 341 | 1B 1T | 12 | 180 | FEDEX P | Enovate Medical, LLC |  |  | DOC REL 4/26 | 4/29 | 11587.5 | BOT 1ST URGENT | 2024-04-29 | 2 |  | 7
2024-04-29 |  | 4/10 - MAY CLEAR TODAY 4/15 - SHORT 2 PCS OF U22 |  |  | 1 |  |  | 124745 NEW | 100 | 4/29 5D | NL | X | LEAD PROCESS DEPANEL |  |  | 4/17 - BOT 12:00 4/18 - TOP 8:30 4/18 - AOI 2:30 | 73 | 270 | 1B 1T | 10 | 1000 | FEDEX P | Safe Foods |  |  | DOC REL 4/3 | 4/10 | 8600 | BOT 1ST | 2024-04-23 | 2 | 2024-04-17 | 10.5
2024-04-29 |  | 4/23 - PCB DUE 4/16 - KIT CLEAR |  |  |  |  | 1 | 121972 NEW | 100 | 4/30 10D | NL | X | LEAD PROCESS DEPANEL |  |  | 4/16 - TOP 9:30 4/16 - AOI 11:00 | 1 | 1 | 1B | 1 | 100 | FEDEX P | Hoverfly Technologies Inc |  |  | DOC REL 4/3 | 4/10 | 2725 | BOT ONLY 4/11 - HAVE STENCIL | 2024-04-30 | 1 |  | 1.5
2024-04-26 |  | 4/23 - PCB DUE; SHORT #16 (U2..) & #26 (HD1) 4/18 - KIT CLEAR |  |  |  | 1 |  | 124917 NEW | 2 | 5/2 10D | NL | X | SHORT #16 (U2..) OK TO SKIP "LEDB1 & 2" AFTER WASH DEPANEL |  |  | 4/23 - BOT 8:00 4/23 - TOP 10:30 4/23 - AOI 2:00 | 37 | 952 | 1B 1T | 451 | 902 | UPS BLUE | Government Contracting Specialists, Inc. |  |  | DOC REL 4/16 | 4/17 | 7107 | BOT 1ST | 2024-05-02 | 2 | 2024-04-22 | 6
2024-04-25 |  | 4/16 - PCB DUE 4/17 - KIT CLEAR |  |  |  | 2 |  | 124492 NEW | 75 | 5/1 10D | NL | X | LEAD PROCESS DEPANEL |  |  | 4/18 - AOI | 8 | 8 | 1T | 0 | 0 | FEDEX P | Hoverfly Technologies Inc |  |  | DOC REL 4/9 | 4/9 | 2300 | TOP ONLY | 2024-05-01 | 1 | 2024-04-19
2024-04-25 |  | 4/18 - PCB DUE 4/17 - KIT CLEAR |  |  |  |  | 3 | 121977 NEW | 25 | 5/1 10D | NL | X | LEAD PROCESS ADD SOLDER TO SHIELD FRAME DEPANEL |  |  | 4/23 - AOI | 14 | 27 | 1B 1T | 0 | 0 | FEDEX P | Hoverfly Technologies Inc |  | 4/19 - AWT STENCIL | DOC REL 4/3 | 4/10 | 1800 | BOT 1ST | 2024-05-01 | 2 | 2024-04-19
2024-04-25 |  | 4/18 - KIT CLEAR |  |  | 1 |  |  | 125007 NEW | 20 | 4/25 5D | NN | X | CLASS 3 LEAD PROCESS DEPANEL |  |  | 4/22 - BOT 2:00 4/23 - TOP 7:30 4/23 - AOI 2:00 | 37 | 1296 | 2B 2T | 0 | 0 | FEDEX P | Reliable Robotics Corporation |  |  | DOC REL 4/17 | 4/18 | 12464.2 | BOT 1ST | 2024-04-25 | 2 | 2024-04-19 | 8.5
2024-04-25 |  | 4/22 - WILL CLEAR DATE (EST SHIP DATE 4/25) (PHUONG) KIT CLEAR |  |  |  |  | 2 | 125078 ROWC 122774 | 1 | 4/25 8D | NL | ROWC | *** 5-DAY RWK + 3-DAY RUNTIME *** XRAY & SAVE IMAGES DEPANEL |  |  | 4/19 - BOT 7:00 4/19 - TOP 11:00 4/19 - PAUSE 2:30 4/22 - TOP 10:30 4/22 - AOI 12:30 | 41 | 3960 | 1B 1T | 12 | 12 | FEDEX P | CACI |  | 4/22 - GOOP BOTTOM REQ BEFORE RUN TOP | DOC REL 4/15 | 4/16 | 8324 | BOT 1ST LT5 RWK REQ 3-DAY CLEARS | 2024-04-25 | 2 | 2024-04-18 | 9
2024-04-25 |  | 4/11 - KIT CLEAR |  |  | 1 |  |  | 124475-2nd ROWC 1st Article | 248 | 4/25 10D | NL | ROWC | *PLEASE MAKE SURE TO HAVE THE MOST UPDATED ECO WITH ALTA QUALITY ALERT ADDED "L1 & S1" MAKE SURE PADS ARE MASKED OFF PER ECO #2 "MOD1" AFTER WASH "J6" QUALITY ALERT FOR SOLDER BRIDGE FROM 1ST ARTICLES - SEE ECO |  |  | 4/15 - TOP 11:00 4/16 - AOI 11:00 | 43 | 84 | 2T | 3 | 744 | UPS BLUE | Swift Sensors |  |  | DOC REL 4/11 | 4/15 | 4560.72 | TOP ONLY | 2024-04-25 | 1
2024-04-24 |  | 4/17 – PCB due date; No ETA on Q1 4/12 - KIT CLEAR |  |  |  | 1 |  | 124494 NEW | 25 | 4/26 10D | NL | X | DEPANEL & SAND |  |  | 4/12 - TOP 2:00 4/15 - AOI 2:00 | 57 | 142 | 1T | 24 | 600 | FEDEX P | Hoverfly Technologies Inc |  |  | DOC REL 4/9 | 4/10 | 4075 | TOP ONLY 4/11 - HAVE STENCIL | 2024-04-26 | 2 |  | 6
2024-04-24 |  | 4/10 - SHORT #8 (Y1) NO ETA 4/11 - KIT CLEAR |  |  |  |  | 1 | 121979 NEW | 25 | 4/25 10D | NL | X | LEAD PROCESS DEPANEL |  |  | 4/15 - BOT 4/15 - TOP 4/15 - AOI 11:00 | 28 | 92 | 1B 1T | 8 | 200 | FEDEX P | Hoverfly Technologies Inc |  |  | DOC REL 4/3 | 4/10 | 2125 | BOT 1ST 4/12 - HAVE STENCIL | 2024-04-25 | 2
2024-04-24 |  | 4/22 - PCB DUE ¦ AWT PART CONF #49 (J1) & #48 (J3) 4/19 - PCB DUE 4/19 - KIT CLEAR |  |  | 1 |  |  | 125103 NEW | 5 | 4/24 3D | NL | x | *** 3 DAY TURN *** DEPANEL |  |  | 4/22 - BOT 8:30 4/22 - TOP 1:30 4/23 - AOI 6:30 | 82 | 1392 | 1B 1T | 3 | 15 | FEDEX P | Orbit Fab Inc. |  |  | DOC REL 4/12 | 4/17 | 9475.8 | BOT 1ST | 2024-04-24 | 2 | 2024-04-19 | 6
2024-04-24 |  | 4/9 - SHORT PCB 4/10 - KIT CLEAR |  |  |  | 1 |  | 124126 NEW | 25 | 4/24 10D | NL | X | LEAD PROCESS MECH ASSY REQ |  |  | 4/11 - BOT 1:00 4/12 - PAUSE 8:00 4/17 - BOT 1:00 4/17 - TOP 2:30 4/18 - AOI 12:00 | 35 | 74 | 1B 1T | 6 | 150 | FEDEX P | Hoverfly Technologies Inc |  | 4/12 - AWT STENCIL | DOC REL 4/4 | 4/9 | 2250 | BOT 1ST | 2024-04-24 | 2 |  | 6
2024-04-24 |  | 4/17 - PCB DUE 4/17 - KIT CLEAR |  |  |  |  | 1 | 125036 NEW | 50 | 4/24 5D | NL | X | LEAD ASSY "BZ1, U32, C36" AFTER WASH "DS1-DS3" MOUNT PER ECO #8 "J1 & J2" MOUNT PER ECO #9 |  |  | 4/18 - BOT 8:00 4/18 - TOP 10:00 4/19 - AOI 8:00 | 54 | 185 | 1B 1T | 11 | 550 | FEDEX P | Industrialex Manufacturing |  |  | DOC REL 4/11 | 4/12 | 4722.5 | TOP 1ST 4/17 - has stencil | 2024-04-24 | 2 |  | 8
2024-04-23 |  | 4/5 - KIT CLEAR |  |  |  | 1 |  | 124619 RONC 123658 | 20 | 4/26 15D | NL | RONC | SPECIAL LABEL FORMAT REQ PER ECO #3 CofC PER ECO #4 |  |  | 4/10 - BOT 4/11 - TOP 9:00 4/11 - AOI 12:30 | 60 | 450 | 1B 1T | 10 | 200 | UPS RED | Aigen |  |  | DOC REL 4/2 | 4/8 | 3460 | bot 1st | 2024-04-29 | 2 | 2024-04-10
2024-04-23 |  | 4/11 - KIT CLEAR |  |  | 1 |  |  | 125010 NEW | 50 | 4/25 10D | NL | X | LEAD/NO CLEAN PROCESS MAKE SURE THERE IS PASTE ON FRAME PADS PER ECO |  |  | 4/17 - BOT 6:00 4/17 - TOP 9:00 4/17 - AOI | 23 | 54 | 1B 1T | 0 | 0 | FEDEX P | Hoverfly Technologies Inc |  |  | DOC REL 4/10 | 4/11 | 1950 | BOT 1ST | 2024-04-25 | 2 | 2024-04-17
2024-04-23 |  | 4/11 - KIT CLEAR |  |  | 1 |  |  | 121960 NEW | 25 | 4/25 10D | NL | X | LEAD PROCESS DEPANEL |  |  | 4/15 - BOT 9:30 4/15 - PAUSE 11:00 4/16 - BOT 11:00 4/16 - TOP 4/16 - AOI | 10 | 12 | 1B 1T | 2 | 50 | FEDEX P | Hoverfly Technologies Inc |  | 4/15 - AWT STENCIL | DOC REL 4/3 | 4/11 | 1775 | BOT 1ST | 2024-04-25 | 2
2024-04-23 |  | 4/9 - SMT CLEAR 4/11 - KIT CLEAR |  |  |  |  | 1 | 124488 NEW | 3 | 4/25 10D | NL | X | DEPANEL |  |  | 4/10 - BOT 2:00 4/11 - TOP 4/11 - AOI 12:30 | 57 | 405 | 1B 1T | 55 | 165 | FEDEX P | Scientific Research Corporation |  |  | DOC REL 4/8 | 4/9 | 3243.4 | BOT 1ST | 2024-04-23 | 2 |  | 6
2024-04-23 |  | 4/1 - SHORT #16 (SW1) & #18 (Q2) 4/9 - KIT CLEAR | [5 empty] | 123452 ROWC 102455 | 40 | 4/23 10D | X |  | T/H ONLY "C1,C2" PLACE PER ECO ***MASK OFF SPECIFIED LOCATIONS PER ECO #3 DEPANEL |  |  | FSU | 0 | 0 |  | 23 | 920 | FEDEX P | Technical Manufacturing Corporation (TMC) |  |  | DOC REL 3/27 | 4/1 | 1862
2024-04-22 |  | 4/5 - SHORTAGES DUE; 4/14 PCB DUE 4/11 - SMT CLEAR |  |  | 1 |  |  | 124334 ROWC 120730 | 13 | 4/23 5D | NL | ROWC | DNI #81 (J5) "U20" DO NOT WASH XRAY & SAVE IMAGES LABEL/SER # PER ECO #3 |  |  | 4/11 - BOT 2:00 4/12 - TOP 10:30 4/12 - AOI 2:30 | 106 | 608 | 2B 2T | 38 | 494 | FEDEX P | Industrialex Manufacturing |  |  | DOC REL 4/3 | 4/4 | 4732 | BOT 1ST | 2024-04-19 | 2 | 1900-01-06 12:00
2024-04-22 |  | 4/15 - KIT CLEAR | [5 empty] | 124597 RWK | 250 | 4/25 10D | - |  | *** NEEDS UNPACK *** ADD SOLDER ON J3 REMOVE R5 RELABEL |  |  | BACK |  |  |  | 2 | 500 | FEDEX P | QinetiQ |  |  | NO DOC. |  | 3975
2024-04-22 |  | 4/9 - PART SHORTAGES 4/11 - SHORT #18(U5) 4/15 - MAY CLEAR DATE 4/15 - KIT CLEAR |  |  |  |  | 1 | 121282-1ST NEW | 1 | 4/22 5D | NL | X | 12 |  |  | 4/16 - AOI | 42 | 1060 | 1T | 14 | 14 | UPS RED | Nottingham Spirk Design Associates, Inc. |  |  | DOC REL 4/8 | 4/9 | 2128 | TOP ONLY | 2024-04-22 | 3
2024-04-22 |  | 4/16 - PCB DUE; NO ETA #26 (J7..) 4/17 - J7, J8 DUE 4/17 - KIT CLEAR |  |  |  |  | 1 | 125073 NEW | 5 | 4/22 3D | NL | x | *** 3 DAY TURN *** LEAD PROCESS DEPANEL |  |  | 4/17 - BOT 11:00 4/17 - TOP 1:00 4/18 - AOI 7:00 | 37 | 195 | 1B 1T | 8 | 40 | FEDEX P | OnLogic |  |  | DOC REL 4/11 | 4/12 | 4145 | BOT 1ST | 2024-04-22 | 2 | 2024-04-17 | 4
2024-04-22 |  | 4/9 - PART SHORTAGES 4/11 - SHORT #18(U6) 4/15 - MAY CLEAR DATE |  |  |  | 1 |  | 121281-1ST NEW | 1 | 4/22 5D | NL | X | DEPANEL |  |  | 4/16 - TOP 8:00 4/16 - AOI 1:00 | 45 | 3135 | 2T | 26 | 26 | UPS RED | Nottingham Spirk Design Associates, Inc. |  | 4/18 - pin 1 of j19 & j20 doesn't match silkscreen | DOC REL 4/8 | 4/9 | 4227 | TOP ONLY | 2024-04-22 | 3 |  | 5
2024-04-22 |  | 3/27 - AWT 2 PARTS THAN SMT CLEAR 3/29 - SMT CLEAR 4/15 - KIT CLEAR |  |  |  |  | 1 | 124505-2 BAL NEW | 58 | 4/25 8D | NL | X | SHIPPED 142 OF 200 ON 4/10/2024 Dowsil 2145 RTV NEEDED (12 HR CURE) ALUMINUM PACKAGE |  |  | 3/29 - BOT 4/1 - TOP 4/1 - AOI 12:00 | 68 | 142 | 1B 2T | 3 | 174 | FEDEX 2DAY | Liquid Robotics |  |  | DOC REL 3/27 | 3/27 | 2397.72 | BOT 1ST | 2024-04-12 | 2 | 2024-03-29
2024-04-19 |  | 4/10 - SHORT PCB 4/23 - PCB DUE 4/16 - KIT CLEAR |  |  |  |  | 1 | 121965 NEW | 25 | 4/29 10D | NL | X | LEAD/NO CLEAN PROCESS DEPANEL |  |  | 4/16 - TOP 11:00 4/16 - AOI 2:00 | 14 | 30 | 1T | 0 | 0 | FEDEX P | Hoverfly Technologies Inc |  |  | DOC REL 4/3 | 4/10 | 2500 | TOP ONLY 4/12 - HAVE STENCIL | 2024-04-30 | 1
2024-04-19 |  | 4/11 - PCB DUE 4/11 - KIT CLEAR |  |  | 5 |  |  | 121969 NEW | 25 | 4/25 10D | NL | X | LEAD PROCESS DEPANEL |  |  | 4/15 - AOI 10:00 | 8 | 36 | 1B | 0 | 0 | FEDEX P | Hoverfly Technologies Inc |  |  | DOC REL 4/3 | 4/10 | 2725 | bot only 4/12 - HAVE STENCIL | 2024-04-25 | 1
2024-04-19 |  | 4/11 - PCB DUE 4/11 - KIT CLEAR |  |  |  |  | 1 | 121961 NEW | 25 | 4/25 10D | NL | X | LEAD PROCESS ADD SOLDER TO SHIELD FRAME DEPANEL |  |  | 4/15 - AOI | 16 | 33 | 1T | 0 | 0 | FEDEX P | Hoverfly Technologies Inc |  |  | DOC REL 4/3 | 4/10 | 2000 | TOP ONLY 4/12 - HAVE STENCIL | 2024-04-25 | 1
2024-04-19 |  | 4/15 - SMT CLEAR 4/16 - KIT CLEAR |  |  |  |  | 1 | 124949 NEW | 2 | 4/19 3D | NL | x | *** 3 DAY TURN *** CLASS 3 LEAD FORMING REQUIRED BEFORE SMT (ECO #2 & #3) VACUUM APPLIED THERMAL MAT (ECO 4) POLYMIDE TAPE TO BOT OF U32 (ECO 5) EPOXY 2216 APPLY TO U32 (ECO 6) INSTALL GAP PADS (ECO 8 & 9) MECH ASSY w/ torque REQ (ECO 10) |  |  | 4/16 - BOT 9:00 4/17 - TOP 9:00 4/17 - AOI 12:00 | 78 | 989 | 1B 1T | 10 | 20 | UPS RED | Astrobotic Technology, Inc. |  | 4/17 - #72 (R95, R97) part is size 805, while pad is 603 sized. Attempting to see if the part has a good connection before contacting customer | DOC REL 4/15 | 4/15 | 4452 | BOT 1ST A LOT OF MECH ASSY, EPOXY & TRIM PARTS BEFORE SMT AND VACUUMING THERMAL PASTE | 2024-04-19 | 2 | 2024-04-17 | 12
2024-04-19 |  | 4/11 - SHORT #18(U6) 4/15 - KIT CLEAR |  |  |  | 1 |  | 120425-1ST NEW | 1 | 4/22 5D | NL | X | DEPANEL |  |  | 4/16 - TOP 11:00 4/16 - AOI | 45 | 2807 | 2T | 15 | 15 | UPS RED | Nottingham Spirk Design Associates, Inc. |  |  | DOC REL 4/8 | 4/11 | 3316 | TOP ONLY | 2024-04-22 | 3
2024-04-19 |  | 4/15 - pcb due 4/9 - SMT CLEAR (KIT CLEAR FOR 576 OF 600 possibly ship 4/12 (Anne)) 4/17 (TRINH) 4/18 - KIT CLEAR |  |  |  |  | 1 | 123601-2 BAL NEW | 25 | 4/19 3D | NL | X | *** 3 DAY TURN *** "DISP1" AFTER WASH DEPANEL |  |  | 4/11 - TOP 8:00 4/13 - AOI | 2 | 2 | 1T | 2 | 50 | FEDEX P | NAL Research Corporation |  | 4/9 - awt fixture (at least 1 extra needed for fixture) 4/12 - 2 min line tact time (52 SMT complete at 9:15 am; more data needed) (166 COMPLETE AT 11:20 AM) | DOC REL 3/20 | 3/28 | 7750 | extra time needed (joe & tad) TOP ONLY | 2024-04-12 | 1
2024-04-18 |  | 4/10 - KIT CLEAR |  |  | 3 |  |  | 121968 NEW | 50 | 4/24 10D | NL | X | LEAD PROCESS ADD SOLDER TO SHIELD FRAME DEPANEL |  |  | 4/15 - AOI | 15 | 31 | 1B | 0 | 0 | FEDEX P | Hoverfly Technologies Inc |  |  | DOC REL 4/3 | 4/10 | 1700 | bot only 4/11 - STENCIL DUE | 2024-04-24 | 1
2024-04-18 |  | 4/10 - KIT CLEAR |  |  |  | 1 |  | 121966 NEW | 25 | 4/24 10D | NL | X | LEAD/NO CLEAN PROCESS DEPANEL |  |  | 4/12 - BOT 8:00 4/12 - TOP 10:30 4/15 - AOI | 16 | 37 | 1B 1T | 0 | 0 | FEDEX P | Hoverfly Technologies Inc |  |  | DOC REL 4/3 | 4/10 | 2175 | top 1st 4/11 - STENCIL DUE | 2024-04-24 | 2
2024-04-18 |  | 4/8 - SHORT PCB 4/10 - KIT CLEAR |  |  |  | 1 |  | 121964 NEW | 25 | 4/24 10D | NL | X | LEAD PROCESS DEPANEL |  |  | 4/12 - BOT 4/12 - TOP 2:30 4/15 - AOI | 12 | 13 | 1B 1T | 0 | 0 | FEDEX P | Hoverfly Technologies Inc |  |  | DOC REL 4/3 | 4/8 | 1750 | BOT 1ST 4/11 - STENCIL DUE | 2024-04-24 | 2
2024-04-18 |  | 4/10 - KIT CLEAR |  |  | 2 |  |  | 121978 NEW | 30 | 4/24 10D | NL | X | LEAD PROCESS DEPANEL |  |  | 4/12 - AOI | 8 | 11 | 1B | 1 | 30 | FEDEX P | Hoverfly Technologies Inc |  |  | DOC REL 4/3 | 4/10 | 2810 | bot only 4/11 - STENCIL DUE | 2024-04-24 | 1
2024-04-18 |  | 4/8 - SHORT PCB 4/10 - KIT CLEAR |  |  | 4 |  |  | 121973 NEW | 100 | 4/24 10D | NL | X | LEAD PROCESS DEPANEL |  |  | 4/15 - AOI | 1 | 1 | 1B | 1 | 100 | FEDEX P | Hoverfly Technologies Inc |  |  | DOC REL 4/3 | 4/9 | 2100 | TOP ONLY 4/11 - STENCIL DUE | 2024-04-24 | 1
2024-04-18 |  | 4/11 - KIT CLEAR |  |  |  |  | 1 | 124498 NEW | 30 | 4/18 4/25 10D | NL | X | *** EXPEDITE & ship 4/18 *** LEAD PROCESS DEPANEL |  |  | 4/15 - BOT 4/15 - TOP 11:00 4/15 - AOI 2:30 | 46 | 105 | 1B 1T | 28 | 840 | FEDEX P | Hoverfly Technologies Inc |  |  | DOC REL 4/10 | 4/11 | 6710 | BOT 1ST 4/12 - HAVE STENCIL | 2024-04-30 | 2
2024-04-17 |  | 4/10 - MAY CLEAR DATE 4/10 - KIT CLEAR |  |  | 1 |  |  | 124556-1st NEW | 6 | 4/17 5D | NL | X | "SW1" AFTER WASH DEPANEL SPECIAL LABEL REQ PER ECO #4 |  |  | 4/11 - BOT 9:30 4/11 - TOP 11:00 4/11 - AOI 1:30 | 93 | 608 | 1B 2T | 7 | 42 | FEDEX P | ABB, Inc. |  |  | DOC REL 3/21 | 4/9 | 3047 | BOT 1ST | 2024-04-17 | 2 |  | 4
2024-04-17 |  | 3/11 - PCB DUE 3/11 - NO ETA FOR PCB 3/28 - PCB DUE 4/2 OR 4/3 - PCB DUE 4/3 - KIT CLEAR |  |  | 2 |  |  | 123565 NEW | 3 | 4/17 10D | NL | X | BAG & TAG HARDWARE PER ECO #2 |  |  | 4/4 - BOT 9:30 4/4 - TOP 12:00 4/5 - AOI | 136 | 1226 | 1B 2T | 19 | 57 | FEDEX P | GTRI-Ga Tech |  |  | DOC REL 2/28 | 3/1 | 5731.64 | BOT 1ST | 2024-04-17 | 2
2024-04-17 |  | 4/3 - KIT CLEAR |  |  | 1 |  |  | 123722-1st NEW | 1 | 4/17 10D | NL | X | DNI #65 (J2) LEAD PROCESS U1, U6, U24, U28, U30, J3 - XRAY & SAVE IMAGES DEPANEL AND SAND PER ECO #1 DO NOT LABEL PER ECO #4 |  |  | 4/10 - TOP 10:00 4/10 - AOI | 106 | 540 | 2T | 83 | 83 | FEDEX P | X-Microwave - A Quantic Company |  |  | DOC REL 3/11 | 4/3 | 2912 | TOP ONLY | 2024-04-17 | 2 | 2024-04-11
2024-04-17 |  | 4/3 - SHORTAGES DUE 4/4 - SMT CLEAR 4/10 - KIT CLEAR |  |  |  | 1 |  | 124585 RONC 123781 | 40 | 4/17 5D | NL | RONC | LEAD PROCESS DEPANEL "BZ1" AFTER WASH CONN HEUGHT REQUIREMENT PER ECO #8 CofC/PACK SLIP PER ECOO #9 |  |  | 4/9 - BOT 11:30 4/10 - AOI 12:00 | 38 | 217 | 1B | 5 | 200 | UPS RED | Aigen |  |  | DOC REL 3/15 | 4/3 | 2293.6 | BOT ONLY | 2024-04-17 | 2 | 2024-04-09 | 6.5
2024-04-17 |  | 4/15 - pcb due 4/9 - SMT CLEAR (KIT CLEAR FOR 576 OF 600 possibly ship 4/12 (Anne)) 4/17 (TRINH) |  |  |  |  | 1 | 123601-1 PAR NEW | 575 | 4/17 3D | NL | X | *** 3 DAY TURN *** "DISP1" AFTER WASH DEPANEL |  |  | 4/11 - TOP 8:00 4/13 - AOI | 2 | 2 | 1T | 2 | 1150 | FEDEX P | NAL Research Corporation |  | 4/9 - awt fixture (at least 1 extra needed for fixture) 4/12 - 2 min line tact time (52 SMT complete at 9:15 am; more data needed) (166 COMPLETE AT 11:20 AM) | DOC REL 3/20 | 3/28 | 7750 | extra time needed (joe & tad) TOP ONLY | 2024-04-12 | 1
2024-04-17 |  | 4/5 - PCB DUE 4/3 - PCB DUE 4/3 - KIT CLEAR |  |  | 1 |  |  | 123504-1ST NEW | 2 | 4/17 10D | NL | X | J14_PIN1_2, J15_PIN1_2, J15_PIN3_4, J15_PIN5_6, J16_PIN2_3 (WIRE) - RWK PER ECO #2 DEPANEL |  |  | 4/8 - BOT 9:00 4/8 - TOP 11:30 4/8 - PAUSE 2:30 4/9 - TOP 2:30 4/10 - AOI 8:30 | 92 | 1054 | 1B 2T | 12 | 24 | FEDEX INTER | System-On-Chip Technologies |  | 4/8 - U8 pad on PCB is too small compared to part's ground pad 4/9 - ROBERT SCRATCHED OUT THE PAD TO MAKE IT LARGER TO FIT THE PART | DOC REL 3/7 | 4/1 | 2776.04 | bot 1st | 2024-04-17 | 2 | 2024-04-08 | 8.5
2024-04-16 |  | 4/9 - KIT CLEAR |  |  |  |  | 1 | 121970 NEW | 25 | 4/23 10D | OL | X | LEAD PROCESS DEPANEL |  |  | 4/10 - TOP 10:00 4/10 - AOI 2:00 | 7 | 27 |  | 0 | 0 | FEDEX P | Hoverfly Technologies Inc |  |  | DOC REL 4/3 | 4/9 | 2075 | bot only | 2024-04-23 | 1 | 2024-04-10
2024-04-16 |  | 4/9 - KIT CLEAR |  |  | 1 |  |  | 124490 NEW | 25 | 4/23 10D | NL | X | LEAD PROCESS DEPANEL "J2" AFTER WASH!!! |  |  | 4/11 - TOP 6:00 4/11 - AOI 8:00 | 1 | 1 | 1T | 1 | 25 | FEDEX P | Hoverfly Technologies Inc |  |  | DOC REL 4/9 | 4/9 | 1900 | TOP ONLY | 2024-04-23 | 1
2024-04-16 |  | 4/10 - PCB DUE 4/3 - KIT CLEAR |  |  | 2 |  |  | 124737 NEW | 5 | 4/17 10D | NL | X | MOUNT LEDs ON SPACERS W/ LONG LEAD IN SQUARE PAD (SEE ECO) DEPANEL |  |  | 4/9 - TOP 6:00 4/9 - AOI 9:00 | 17 | 163 | 1T | 55 | 275 | FEDEX GRD | Bruker Nano, RMR (FKA RAVE LLC) |  |  | DOC REL 3/27 | 3/28 | 2633.75 | TOP ONLY | 2024-04-17 | 1 | 2024-04-09
2024-04-16 |  | 4/3 - KIT CLEAR |  |  | 1 |  |  | 124289 RONC 123954 | 20 | 4/17 10D | NL | RONC | LEAD PROCESS DEPANEL SER # REQ PER ECO #6 |  |  | 4/5 - BOT 4/5 - TOP 10:00 4/8 - AOI 9:30 | 84 | 631 | 1B 2T | 32 | 640 | UPS RED | Aigen |  |  | DOC REL 3/14 | 4/3 | 3752 | bot 1st | 2024-04-17 | 2
2024-04-16 |  | 3/20 - DAY 1 (ANNE); SHORT 15 PCS OF #20(U2,U6...) 3/25 - officially clear (no ship date change - Anne) |  |  | 1 |  |  | 123511 RONC 121661 | 225 | 4/16 20D | NL | RONC | CLASS 3 |  |  | 3/27 - BOT 11:30 3/28 - TOP 10:00 3/29 - AOI | 60 | 188 | 2B 2T | 0 | 0 | UPS 3D | Coastal Designs, LLC |  |  | DOC REL 3/6 | 3/19 | 13324.5 | BOT SIDE 1ST (PREVIOUS BUILD) ONE FEEDER TWO LOCATIONS (PREV BUILD) | 2024-04-16 | 2 | 2024-03-27
2024-04-16 |  | 3/26 - SHORTAGES DUE 3/26 - SHORT #51 (TP7, TP8..); ENOUGH TO RUN 150 OF 160 4/3 - KIT CLEAR |  |  | 1 |  |  | 124112 ROWC 122469 | 160 | 4/17 10D | NL | ROWC | SKIP ANY SHORT OF #51 (TP7, TP8...) DEPANEL |  |  | 4/1 - TOP 6:00 4/1 - AOI 2:30 | 60 | 207 | 2T | 18 | 2880 | FEDEX 2DAY | Servomex Inc |  |  | DOC REL 3/6 | 3/25 | 9595.2 | top only | 2024-04-30 | 1 | 2024-03-29 | 8
2024-04-15 |  | 3/27 - SHORT PCB (NO DUE DATE) 4/15 - PCB DUE 4/15 - KIT CLEAR |  |  |  |  | 1 | 124615 NEW | 5 | 4/15 5D | NL | X | VERIFY "U12" MASK OFF PER ECO #2 DEPANEL |  |  | 4/9 - BOT 12:30 4/10 - AOI | 92 | 833 | 1B 2T | 33 | 165 | FEDEX P | Nordson Corporation |  |  | DOC REL 3/25 | 3/27 | 4871.5 | bot 1st | 2024-04-15 | 2 | 2024-04-10
2024-04-15 |  | 3/25 - SHORTAGES DUE; NO ETA PCB 4/4 - PCB DUE 4/8 - KIT CLEAR |  |  | 1 |  |  | 124582 NEW | 14 | 4/15 5D | NL | X | DEPANEL |  |  | 4/9 - BOT 8:00 4/9 - TOP 9:30 4/9 - AOI 2:30 | 129 | 1119 | 1B 2T | 73 | 1022 | UPS RED | Beckman Coulter |  |  | DOC REL 3/19 | 3/21 | 10866 | BOT 1ST | 2024-04-15 | 2 | 2024-04-09 | 8.5
2024-04-12 |  | 4/8 - KIT CLEAR |  |  | 2 |  |  | 124299 NEW | 120 | 4/15 5D | NL | X | "J1"MAY NEED MODIFICATION TO FIT PER ECO #2 DEPANEL |  |  | 4/10 - BOT 8:30 4/10 - AOI | 1 | 1 | 1B | 1 | 120 | FEDEX P | Cognex |  |  | DOC REL 4/4 | 4/8 | 1572.8 | TOP ONLY | 2024-04-15 | 1 | 2024-04-09
2024-04-12 |  | 3/18 - SMT CLEAR 3/27 - KIT CLEAR |  |  |  | 1 |  | 123880 ROWC 118601 | 30 | 4/24 20D | NL | ROWC | SHUNTS REQ PER ECO #2 DEPANEL |  |  | 3/22 - TOP 9:00 3/22 - AOI 12:00 | 3 | 12 | 1T | 23 | 690 | FEDEX GRD | Graph-Tech USA, LLC |  |  | DOC REL 3/12 | 3/18 | 2270 | TOP ONLY | 2024-04-30 | 1 |  | 3
2024-04-12 |  | 2/8 - SHORT #27A (U10) NO ETA 2/9 - KIT CLEAR |  |  | 1 |  |  | 116964-3RD BAL RONC | 60 | 4/12 20D | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 240 U8, U9 – LTC2864MPS-2#PBF U10 – LTC2864MPS-1#PBF DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/13 - BOT 8:30 2/13 - TOP 12:30 2/15 - AOI 9:00 | 68 | 264 | 2B 2T | 5 | 300 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2024-02-08 | 18941.69 | Customer wants to use a different part number for U8, U9 only, PN LTC2864MPS-2#PBF. U10, PN LTC2864MPS-1#PBF, will remain the same. BOT 1ST | 2024-03-19 | 2 | 2024-02-13 | 16.5
2024-04-12 |  | 2/5 - SMT CLEAR 2/7 - 60 PCBAS OF 360 CLEAR TO SHIP 2/19 2/14 - KIT CLEAR |  |  | 1 |  |  | 116950-3RD PAR RONC | 60 | 4/12 20D | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 240 LEAD PROCESS DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/7 - BOT 1:30 2/8 - AOI 11:00 | 6 | 16 | 1B 1T | 5 | 300 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2/5 | 4689.47 |  |  | 2 | 2024-02-07 | 6.5
2024-04-12 |  | 3/28 - NO ETA ON SHORTAGES 3/29 - ONLY WTG 1 PART CONF FOR #93 4/3 - OK TO SKIP #93 4/5 - KIT CLEAR |  |  |  |  | 1 | 124290-1ST NEW | 6 | 4/12 5D | NL | X | SKIP #93 Q3_5 "SW1,PS1_6,PS2_6,PS3_6,PS4_6 AFTER WASH DEPANEL |  |  | 4/5 - BOT 7:00 4/5 - TOP 4/5 - AOI 10:00 | 82 | 390 | 1B 1T | 23 | 138 | FEDEX P | ABB Inc. |  |  | DOC REL 3/15 | 3/28 | 2492 | BOT 1ST | 2024-04-11 | 2 |  | 3
2024-04-11 |  | 2/5 - SMT CLEAR |  |  | 1 |  |  | 116955-3RD PAR RONC | 60 | 4/12 20D | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 240 SHORT #10 (J1,J2) P/N M80-5000000M2-02-331-00-000 DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/7 - TOP 9:00 2/7 - AOI 12:00 | 7 | 8 | 1T | 12 | 720 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2024-02-05 | 4896 |  |  | 1 |  | 3
2024-04-11 |  | 2/8 - SHORT #10 (U1) & #7 (D10, D11...) NO ETA 2/9 - KIT CLEAR |  |  | 1 |  |  | 116954-2ND PAR RONC | 60 | 4/12 20D | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 240 no 0 OHM rework required U1 – P/N LTC2864MPS-1#PBF L1 – P/N MSS5131-393MLC J1 – P/N M80-5402042 DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/15 - TOP 1:00 2/16 - AOI 11:30 | 24 | 87 | 1T | 1 | 60 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2024-02-08 | 8324 | L1 IS P/N MSS5131-393MLC TOP ONLY | 2024-03-19 | 1 | 2024-02-15 | 6.5
2024-04-11 |  | 2/7 - CLEARED FOR 190 BOARDS (60 BOARDS SHIPPED 2/14/24) 2/22 - SHORT U2 3/1 - KIT CLEAR |  |  |  |  | 2 | 116967-2ND PAR RONC | 60 | 4/11 20D | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 240 30119-102 00500+ J1 – p/n approved M80-5402042 DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 3/4 - TOP 7:30 | 37 | 89 | 1T | 2 | 120 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2/7 | 8796 | TOP ONLY | 2024-04-19 | 1 | 2024-02-14
2024-04-11 |  | 2/9 - SMT CLEAR; BUILT AND SHIPPED 60 ON 2/23 |  |  |  |  | 1 | 116970-2ND PAR RONC | 60 | 4/11 20D | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 240 L1 – P/N MSS5131-393MLC U2 – P/N LTC2864MPS-2#PBF DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/13 - TOP 9:00 2/13 - BOT 1:30 2/14 - AOI 12:00 | 29 | 54 | 2B 1T | 11 | 660 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2/8 | 9600 | L1 IS P/N MSS5131-393MLC BOT 1ST | 2024-03-19 | 2 | 2024-02-13 | 12
2024-04-11 |  | 2/5 - SMT CLEAR |  |  | 1 |  |  | 116957-3RD PAR RONC | 60 | 4/12 20D | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 240 #3 (C4) ALT P/N UBT2A221MHD8TN DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/7 - BOT 11:00 2/7 - AOI 1:30 | 1 | 1 | 1B | 12 | 720 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2024-02-05 | 5385.78 |  |  | 1 | 2024-02-07 | 2.5
2024-04-11 |  | 3/26 - PCB DUE 3/29 - PCB DUE 4/1 OR 4/2 - PCB DUE 4/4 - KIT CLEAR |  |  |  |  | 1 | 124449 NEW | 20 | 4/11 5D | NL | X | ***SHIP ONE DAY SOONER IF POSSIBLE DNI C34 CLASS 3 DEPANEL |  |  | 4/5 - BOT 10:00 4/8 - TOP 4/8 - AOI | 37 | 396 | 1B 1T | 37 | 740 | UPS RED | Cotsworks, Inc. |  | 4/2 - PREP'D ON LINE 3 | DOC REL 3/22 | 3/25 | 5020.4 | BOT 1ST | 2024-04-11 | 2
2024-04-10 |  | 2/9 - #15 (IC2) DUE DATE 2/9 - KIT CLEAR |  |  |  | 1 |  | 116966-3RD PAR RONC | 60 | 4/10 20D | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 240 J1 – P/N M80-5402042 2 LABEL TYPES & LOCS TEXT LABEL & QR CODE ENSURE S/N MATCH LABELS SPECIFIED LOCATIONS DEPANEL XRAY & SVE |  |  | 2/13 - BOT 12:00 2/13 - TOP 2:00 2/15 - AOI 2:00 | 34 | 154 | 2B 2T | 1 | 60 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2/8 | 10083.78 | BOT 1ST | 2024-03-19 | 2 | 2024-02-13 | 14
2024-04-10 |  | 2/7 - KIT CLEAR |  |  | 1 |  |  | 116956-2ND PAR RONC | 60 | 4/10 20D | NL | RONC | DNI #20 (FB8) SCHEDULED SHIPMENT: SHIP 60 OF 240 L1 – P/N 1264EY-330M=P3 J1 – P/N M80-5402042 DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/8 - BOT 10:00 2/9 - TOP 5:00 2/9 - STOP 2:30 2/15 - TOP 9:00 2/15 - AOI 1:00 | 28 | 121 | 1B 1T | 3 | 180 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2024-02-07 | 11147 | BOT 1ST | 2024-03-19 | 2 | 2024-02-15 | 20
2024-04-10 |  | 3/26 - SHORT PCB; NO DUE DATE 4/3 - PCB DUE 4/3 - KIT CLEAR |  |  |  |  | 1 | 124656 NEW | 10 | 4/10 5D | NL | X | "SW2" AFTER WASH DEPANEL SER # PER ECO #4 |  |  | 4/8 - BOT 8:00 4/8 - TOP 12:00 4/9 - AOI | 194 | 719 | 2B 3T | 2 | 20 | FEDEX 2DAY | Luna Innovations, Inc. |  |  | DOC REL 3/25 | 3/26 | 9677 | bot 1st depanel top before SMT (j19 usb-c) | 2024-04-10 | 2 | 2024-04-08
2024-04-10 |  | 4/5 - KIT CLEAR |  |  |  | 1 |  | 124636 NEW | 2 | 4/10 3D | NL | X | *** 3 DAY TURN *** DEPANEL |  |  | 4/9 - TOP 8:00 4/9 - AOI 11:30 | 49 | 639 | 1T | 53 | 106 | FEDEX P | Forza Ametek |  |  | DOC REL 4/3 | 4/5 | 5944 | TOP ONLY | 2024-04-10 | 1 | 2024-04-09 | 3.5
2024-04-10 |  | 3/27 - AWT 2 PARTS THAN SMT CLEAR 3/29 - SMT CLEAR 4/1 - KIT CLEAR (PHUONG) |  |  |  |  | 1 | 124505-1 PAR NEW | 142 | 4/10 8D | NL | X | Dowsil 2145 RTV NEEDED (12 HR CURE) ALUMINUM PACKAGE |  |  | 3/29 - BOT 4/1 - TOP 4/1 - AOI 12:00 | 68 | 142 | 1B 2T | 3 | 426 | FEDEX 2DAY | Liquid Robotics |  |  | DOC REL 3/27 | 3/27 | 7720.28 | BOT 1ST | 2024-04-12 | 2 | 2024-03-29
2024-04-10 |  | 3/27 - SHORT PCB (NO DUE DATE) 4/3 - PCB DUE 4/3 - KIT CLEAR |  |  |  | 1 |  | 124583 NEW | 10 | 4/10 5D | NL | X | #56 (R13..) OK TO USE DEPANEL |  |  | 4/4 - TOP 8:00 4/4 - PAUSE 9:00 4/5 - TOP 8:00 4/5 - AOI 12:00 | 43 | 203 | 1T | 47 | 470 | FEDEX P | Ursa Navigation Solutions, Inc. |  | 4/4 - PAUSE FOR B124008 | DOC REL 3/27 | 3/27 | 3350 | TOP ONLY | 2024-04-10 | 1 |  | 4
2024-04-10 |  | 4/1 - PCB DUE than SMT clear 3/29 - FABS RECEIVED - NOW SMT CLEAR 4/1 - SMT CLEAR 4/3 - THT PARTS DUE DATE 4/3 - KIT CLEAR |  |  |  | 2 |  | 124685 NEW | 25 | 4/10 5D | NL | X | #21(D1..), #23(D11..) & #79(Q8..) OK TO USE Component lead extension to be 0.140" max PER ECO #2 SPECIAL LABEL FORMAT REQ PER ECO #6 *READ - DEPANEL PER ECO #1 screw terminals ship w/ cages fully open |  |  | 4/1 - TOP 1:00 4/1 - AOI 12:00 | 57 | 218 | 1T | 29 | 725 | FEDEX P | Friedrich Air Conditioning LLC |  |  | DOC REL 3/27 | 3/28 | 2970.5 | TOP ONLY | 2024-04-09 | 1 |  | 5
2024-04-09 |  | 4/8 - PCB DUE 4/3 - KIT CLEAR |  |  | 1 |  |  | 124475-1ST NEW | 2 | 4/10 5D | NL | X | VERIFY MASK OFF @ "L1 & S1" PER ECO #2 "MOD1" AFTER WASH DEPANEL |  |  | 4/4 - TOP 8:00 4/4 - PAUSE 9:30 4/5 - AOI | 43 | 84 | 2T | 3 | 6 | UPS BLUE | Swift Sensors |  | 4/4 - AWT STENCIL | DOC REL 4/2 | 4/3 | 1946 | TOP ONLY | 2024-04-10 | 1
2024-04-09 |  | 4/2 - ENOUGH TO RUN 93 OF 100 PCBs 4/2 - KIT CLEAR |  |  | 1 |  |  | 124712 RONC 119655 | 100 | 4/9 5D | NL | RONC | #8 (U1) BTD DEPANEL |  |  | 4/4 - TOP 6:00 4/4 - AOI 9:30 | 24 | 42 | 1T | 6 | 600 | FEDEX 2DAY | Safe Grain, Inc. / Maxi-Tronic |  |  | DOC REL 3/25 | 4/2 | 2000 | TOP ONLY | 2024-04-09 | 1
2024-04-08 |  | 3/29 - PCB DUE; NO ETA #2 (J1) 3/26 - KIT CLEAR |  |  |  | 1 |  | 124241 RONC 122454 | 100 | 4/9 10D | NL | RONC | DEPANEL |  |  | 3/27 - TOP 11:00 3/29 - AOI | 3 | 6 | 1T | 0 | 0 | FEDEX P | Sick, Inc. |  | 3/27 - EXTRA TIME NEEDED FOR HAND-PLACING | DOC REL 3/19 | 3/21 | 1290 | TOP SIDE ONLY | 2024-04-09 | 1 | 2024-03-28
2024-04-08 |  | 3/12 - KIT CLEAR |  |  | 1 |  |  | 123510 RONC 121599 | 40 | 4/9 20D | NL | RONC | ***CHECK ECO FOR QUALITY ALERT!!! |  |  | 3/19 - BOT 7:00 3/19 - TOP 9:30 3/19 - AOI 1:30 | 106 | 341 | 1B 2T | 11 | 440 | UPS 3D | Coastal Designs, LLC |  |  | DOC REL 3/6 | 3/12 | 4281.6 | BOT 1ST | 2024-04-09 | 2 | 2024-03-18 | 6.5
2024-04-08 |  | 3/29 - PCB DUE 3/21 - AWT PART CONF #31(D11..) 3/25 - KIT CLEAR |  |  | 2 |  |  | 124484 NEW | 6 | 4/8 10D | NL | X | The lead protrusion not to exceed 0.1" (2.54mm). DEPANEL AND SAND PER ECO #1 |  |  | 3/29 - BOT 3/29 - TOP 3/29 - AOI | 136 | 628 | 1B 2T | 28 | 168 | UPS RED | Spectro Inc. |  |  | DOC REL 3/18 | 3/21 | 5291.3 | bot 1st | 2024-04-08 | 2 | 2024-03-29
2024-04-08 |  | 3/27 - PCB DUE 3/18 - KIT CLEAR |  |  | 3 |  |  | 124203 ROWC 119676 | 50 | 4/8 15D | NL | ROWC | "J6" CLIP PIN 8 PER ECO DEPANEL |  |  | 3/21 - TOP 1:00 3/22 - AOI 10:00 | 49 | 176 | 1T | 53 | 2650 | FEDEX P | Beckman Coulter |  |  | DOC REL 3/6 | 3/14 | 3037.5 | TOP ONLY | 2024-04-08 | 1 | 2024-03-21
2024-04-05 |  | 3/26 - PCB DUE 4/12 - PCB DUE DATE 4/2 - PCB DUE 4/2 - KIT CLEAR |  |  |  |  | 1 | 124008 NEW | 40 | 4/5 3D | NL | X | *** 3 DAY TURN **** KIT XFER FROM B121592 CLASS 3 RECORD ALL NON-CONFORMANCES DEPANEL & SAND SEE ECO #8 FOR ANY RWK/REPAIR ***SHIPPING - MARK OUTSIDE OF EACH BOX PER ECO #13 |  |  | 4/4 - TOP 6:00 4/4 - BOT 10:00 4/4 - AOI 7:00 | 227 | 987 | 3B 2T 615/ 374 | 0 | 0 | UPS RED | ICUMedical |  | 3/22 - TOP 1ST 4/3 - PREP'D TOP AND BOTTOM BEFORE STARTING TO RUN ON 4/4 4/4 - TOP RUNTIME: 1MIN50/BOARD; ETA 10AM TOP COMPLETE 4/4 - BOT 2MIN/BOARD | DOC REL 2/22 | 3/5 | 30920 | TEMPURATURE QUESTIONS TOP 1ST SOME SIZE 201 | 2024-04-05 | 2 |  | 12
2024-04-05 |  | 3/29 - SMT CLEAR 4/2 - KIT CLEAR |  |  |  |  | 2 | 124634 NEW | 10 | 4/5 3D | NL | X | *** 3 DAY TURN *** QA SUPERVISOR: PCB Qualifications template Summit PDF DSUB SPACING REQUIREMENTS (ECO) BOARD CLEANING REQUIREMENTS (ECO & M00582 PDF) ***MISSING MOUSE BITES - GIVE TO TAD FOR DEPANEL |  |  | 4/2 - TOP 4/2 - AOI 10:00 | 6 | 31 | 1T | 56 | 560 | FEDEX P | Digital Dynamics, Inc. |  | 4/1 - MOUSE BITES W/O DRILL HOLES 4/1 - ok to run; Tad will depanel (Tad) | DOC REL 3/29 | 4/1 | 4335 | bot 1st | 2024-04-05 | 1
2024-04-05 |  | 4/2 - KIT CLEAR |  |  |  |  | 1 | 124409 NEW | 60 | 4/5 3D | NL | X | *** 3 DAY TURN *** SER # PER ECO #1 "U1" ORIENTATION UPDATED ON NEW DWG, PLEASE CONFIRM MATCHES NEW DWG |  |  | 4/2 - TOP 11:00 4/4 - AOI 7:00 | 36 | 315 | 1T | 16 | 960 | FEDEX P | John Hopkins University Applied Physics Lab |  |  | DOC REL 4/1 | 4/2 | 10657.8 | TOP ONLY | 2024-04-05 | 1 |  | 11
2024-04-05 |  | 3/7 - PCB DUE THAN SMT CLEAR 3/5 - SMT CLEAR 3/29 - T/H SHORTAGE CLEARED |  |  | 1 |  |  | 123759 NEW | 15 | 4/5 5D | NL | X | *** NO MARKINGS/STAMPS ALLOWED *** REMOVE ALL FULX!!! MECH REQ PER ECO #7, 8, 11 & 13 ADHESIVE REQ FOR "J1 & J2 TRIM LEADS MAX LENGTH REQ |  |  | 3/5 - BOT 1:00 3/6 - TOP 3/6 - AOI 9:00 | 13 | 59 | 1B 1T | 70 | 1050 | FEDEX P | ICR, Inc. |  | 3/28 - ASKED CUST ABOUT #5(J_BP..); EXTRA SOLDER LUG 3/29 - TEARDOP PIECE (SOLDER LUG) NO INSTALL | DOC REL 2/27 | 3/4 | 4515.5 | BOT 1ST | 2024-03-13 | 2 | 2024-03-06 | 4.5
2024-04-04 |  | 4/1 - KIT CLEAR |  |  |  | 1 |  | 124635 NEW | 2 | 4/4 3D | NL | X | *** 3 DAY TURN *** DEPANEL |  |  | 4/2 - TOP 10:30 4/3 - AOI 10:00 | 49 | 849 | 1T | 55 | 110 | FEDEX P | Forza Ametek |  | 4/3 - WAITING FOR NEW REFLOW PROFILE (DISCOLORED SOLDER) | DOC REL 4/1 | 4/1 | 6673 | TOP ONLY | 2024-04-04 | 1 |  | 7.5
2024-04-03 |  | 3/22 - KIT CLEAR |  |  |  | 1 |  | 121059 NEW | 25 | 4/5 10D | NL | X | ***"U6" VERIFY PARTS GOT PROGRAMMED & SHIPPED FROM BY PRO-EX PER ECO #2 FAIR REQUIRED DEPANEL SPECIAL LABEL REQ PER ECO #4 |  |  | 3/26 - TOP 9:30 3/26 - AOI 1:30 | 37 | 80 | 1T | 29 | 725 | FEDEX P | IDEX Corporation |  |  | DOC REL 3/21 | 3/22 | 1550 | TOP ONLY | 2024-04-05 | 1 | 2024-03-26 | 4
2024-04-03 |  | 3/14 - PCB DUE 3/20 - KIT CLEAR |  |  |  | 1 |  | 123794 RONC 121601 | 5 | 4/3 10D | NL | RONC | DEPANEL |  |  | 4/1 - BOT 8:00 4/1 - TOP 11:00 4/1 - AOI 1:30 | 51 | 556 | 1B 1T | 8 | 40 | FEDEX P | Genuen, LLC |  |  | DOC REL 3/5 | 3/6 | 2069.4 | bot 1st | 2024-04-03 | 2 | 2024-03-29 | 5.5
2024-04-03 |  | 3/18 - SHORT #59(U18A,U18B...) 3/20 - KIT CLEAR |  |  |  | 1B | 1A | 124147 ROWC B100610 NEW | 4 | 4/3 10D | NL | X | ***KICKOFF MEETING REQUIRED BEFORE JOB IS RELEASED - ASSY'S NEED TO BE PERFECT!!! - THIS IS A QUALIFICATION RUN*** CLASS 3 48 HR BREBAKE REQ ***CHECK IF VIA IS MISSING PER ECO #5 ***"R401 & R430" MAKE SURE P/N IS RC0603FR-0735K7L AND MEASURES 35.7K "U1A8" MOUNT WITH LEAD SOLDER AFTER SMT AND REFLOW - SAME PROCESS AS LAST TIME DO NOT USE ANY "U1A8" PARTS THAT START WITH S/N 2107 |  |  | 3/22 - BOT 6:00 3/25 - TOP 9:30 3/25 - PAUSE 4:30 3/26 - TOP 10:30 3/26 - PAUSE 12:30 3/27 - TOP 7:00 3/27 - AOI 10:00 | 238 | 3856 | 2B 3T | 22 | 88 | FEDEX P | University Of Oklahoma |  | 3/26 - STENCIL CHANGE; JOB PAUSED UNTIL 11AM TODAY 3/26 - PAUSE AGAIN; DUE TO UNEVEN SOLDER PLACEMENT | DOC REL 2/29 | 3/20 | 18322.2 | PART VERIFICATION | 2024-04-03 | 2 | 2024-03-22 | 24
2024-04-03 |  | 3/27 - SHORT PCB & #10 (C68..); COULD ARRIVE THIS WEEK 4/1 - PCB DUE 3/29 - #10 (C68,C69) DUE 4/1 - KIT CLEAR |  |  |  |  | 1 | 124720 NEW | 15 | 4/3 2D | NL | X | *** 2 DAY TURN *** "PZ1, SW1, SW2" AFTER WASH SER # REQ PER ECO DEPANEL |  |  | 4/1 - BOT 12:00 4/2 - TOP 4/2 - AOI 11:00 | 87 | 333 | 1B 1T | 14 | 210 | FEDEX P | Ergotron, Inc. |  |  | DOC REL 3/27 | 3/27 | 7902.5 | TOP 1ST | 2024-04-03 | 2 |  | 7
2024-04-02 |  | 3/19 - KIT CLEAR | [5 empty] | 124201 RWK | 38 | 4/2 10D | - |  | line one has 2pc rework for 3 days |  |  | BACK |  |  |  |  | 0 | FEDEX P | Integrated Consultants |  |  | NO DOC. | 3/19 | 11000
2024-04-02 |  | 3/19 - PCB DUE 3/19 - KIT CLEAR |  |  | 1 |  |  | 124259 NEW | 75 | 4/2 10D | NL | X | J6 - AFTER WASH C31, C21 PLACED ACCORDING TO XY AND may not match SILKSCREEN DEPANEL |  |  | 3/26 - BOT 11:00 3/26 - TOP 2:00 3/27 - AOI 12:00 | 91 | 252 | 1B 2T | 6 | 450 | FEDEX GRD | Graph-Tech USA, LLC |  |  | DOC REL 3/6 | 3/11 | 5544.75 | fab hold 3/6 top only STANDOFFS ON BOT; RUN 1ST | 2024-04-02 | 1 | 2024-03-26 | 9
2024-04-02 |  | 3/26 - SHORT #33(U14) due 3/26 - KIT CLEAR |  |  |  |  | 1 | 124607 NEW | 60 | 4/2 5D | NL | X | LEAD PROCESS |  |  | 3/27 - BOT 12:30 3/28 - TOP 9:00 3/29 - AOI | 82 | 247 | 1B 2T | 8 | 480 | FEDEX P | RX Monitoring Service, Inc. |  |  | DOC REL 3/21 | 3/25 | 4830 | bot 1st MOSTLY 1 SIDE W/ 1 PART ON BOT SIDE | 2024-04-02 | 2 | 2024-03-28
2024-04-01 |  | 3/13 - #34 (UPG2) DUE 3/13 - KIT CLEAR |  |  | 1 |  |  | 119889 ROWC 111791 | 56 | 4/3 15D | NL | ROWC | "PFADT & PFTDT DO NOT INSTALL ON QTY 15 PN#XCF32PVO48C (UPG2) - MUST READ ECO #3 FOR INSTALLATION PP0 (1410147-1) PRESS FIT - SEE ECO #7 XRAY & SAVE DEPANEL EXTRA PACKAGING REQUIRED FOR PROTECTION PER ECO #10 |  |  | 3/14 - BOT 8:00 3/14 - TOP 1:30 3/19 - AOI 7:00 | 48 | 936 | 1B 1T | 8 | 448 | FEDEX GRD? | Jefferson Labs |  | 3/15 - TUAN OUT SICK | DOC REL 1/23 | 3/12 | 12671.36 | BOT 1ST FIBER OPTIC PLUG | 2024-04-03 | 2 | 2024-03-13 | 15.5
2024-04-01 |  | 3/18 - #32(U8) & #47(J6,J7) DUE; 3/19 - PCB DUE 3/18 - KIT CLEAR |  |  |  |  | 1 | 123118 NEW | 12 | 4/1 10D | NL | X | CLASS 3 48 HR PREBAKE REQ DOUBLE CHECK PASTE VOLUME FOR "J4 & 5" PER ECO #5 "J2" PRESS FIT & SOLDER |  |  | 3/21 - BOT 2:30 3/22 - TOP 8:30 3/22 - AOI 1:30 | 80 | 312 | 1B 1T | 3 | 36 | FEDEX P | University Of Oklahoma |  |  | DOC REL 2/27 | 3/14 | 3606.8 | PART VERIFICATION TOP 1ST | 2024-04-01 | 2 | 2024-03-21 | 7
2024-03-29 |  | 3/27 - PCB DUE 3/26 - KIT CLEAR |  |  |  | 1 |  | 124630 NEW | 30 | 3/29 3D | NL | X | *** 3 DAY TURN **** COMPONENT LEAD TO BE TRIMMED TO 0.140" MAX special label on shipping box (ECO) |  |  | 3/26 - BOT 1:00 3/27 - TOP 9:30 3/27 - AOI 12:00 | 6 | 7 | 1B 1T | 27 | 810 | FEDEX P | Rheem Manufacturing Company |  |  | DOC REL 3/22 | 3/25 | 3852.5 | BOT 1ST LABEL ON SHIPPING BOX (ECO) | 2024-03-29 | 2 | 2024-03-27 | 5
2024-03-29 |  | 3/21 - PCB DUE; 3/11 - #17(U5) DUE 3/15 - KIT CLEAR |  |  | 1 |  |  | 124344 ROWC 111701 | 75 | 3/29 10D | NL | ROWC | DEPANEL |  |  | 3/19 - BOT 1:00 3/19 - TOP 3/19 - AOI 12:30 | 42 | 245 | 1B 1T | 34 | 2550 | FEDEX GRD | Graph-Tech USA, LLC |  |  | DOC REL 3/6 | 3/11 | 5315.5 | BOT 1ST | 2024-03-29 | 2 | 2024-03-19 | 7.5
2024-03-29 |  | 3/25 - PCB DUE; SHORT #43(J6) & #48(BT1) 3/21 - SMT CLEAR 3/22 - KIT CLEAR |  |  |  |  | 1 | 124388 NEW | 12 | 3/29 5D | NL | X | DATA MATRIX BARCODE LABEL D12,D13... PART ORIENTATION (ECO) LEAD LENGTH REQUIREMENTS (ECO) DEPANEL |  |  | 3/26 - BOT 6:30 3/26 - TOP 3/26 - AOI 11:00 | 73 | 292 | 1B 2T | 7 | 84 | FEDEX P | Protedyne Corporation - 3274-CTL062 |  |  | DOC REL 3/18 | 3/19 | 2772 | TOP 1ST | 2024-03-29 | 2 | 2024-03-26 | 3.5
2024-03-28 |  | 3/7 - WILL CLEAR SOON 3/20 - #28(Y3) DUE; AWT PART CONF #68(U2) 3/25 - KIT CLEAR |  |  |  |  | 1 | 123787 NEW | 10 | 4/1 5D | NL | X | SHORT Y3, CAN SKIP J4, J7 & J10 FLUSH AND STRAIGHT PLACEMENT REQUIRED U8 U53 PLACEMENT (SEE ECO) DEPANEL |  |  | 3/15 - BOT 7:30 3/15 - TOP 10:00 3/15 - AOI 1:30 | 153 | 770 | 1B 3T | 19 | 190 | UPS GRD | Innerspec Technologies, Inc |  | 3/28 - PCB S/N #10 solder issue; TALK TO CINDY/ROBERT IF THERE ARE ISSUES/RMA | DOC REL 3/5 | 3/7 | 4017.5 | BOT 1ST | 2024-03-30 | 2 | 2024-03-15 | 6
2024-03-28 |  | 3/15 - KIT CLEAR |  |  |  | 1 |  | 121413-2ND ROWC 1st Article | 15 | 3/27 8D 5D | NL | ROWC | CLASS 3 "SW200" AFTER WASH POST BAKE PER ECO #5 PRESS FIT REEQ ***2 RWK CHARGES ADDED 3/21/24 - MAKE SURE CHARGES ARE INVOICED (ERIC) |  |  | 3/19 - BOT 1:00 3/21 - TOP 11:00 3/22 - AOI 9:00 | 130 | 637 | 2B 2T | 19 | 285 | UPS GRD | Diversified Supply |  |  | DOC REL 3/14 | 3/15 | 11750 | bot 1st | 2024-03-27 | 2 | 2024-03-20 | 8.5
2024-03-28 |  | 3/21 - PCB DUE 3/21 - KIT CLEAR |  |  | 1 |  |  | 124479 NEW | 50 | 3/28 5D | NL | X | LEAD PROCESS "C40" AFTER WASH DEPANEL |  |  | 3/25 - TOP 11:00 3/26 - BOT 3/26 - AOI 11:30 | 75 | 288 | 2B 1T | 11 | 550 | FECEX 2D | Urban Sky Theory LLC |  |  | DOC REL 3/19 | 3/21 | 6325 | TOP 1ST | 2024-03-28 | 2 | 2024-03-25 | 8.5
2024-03-27 |  | 3/22 - KIT CLEAR | [5 empty] | 124611 RWK | 349 | 3/29 5D | - |  | WASH AND BAKE BOARDS |  |  | BACK |  |  |  |  | 0 | UPS RED | Reprieve Cardiovascular, Inc. |  |  | NO DOC. |  | 1662.5
2024-03-27 |  | 3/19 - SMT CLEAR 3/20 - KIT CLEAR |  |  | 1 |  |  | 123658-2 BAL NEW | 30 | 3/27 5D | NL | X | DEPANEL CoC/PACK SLIP PER ECO #4 (CUST NAME CHANGED TO AIGEN) |  |  | 3/22 - BOT 10:00 3/22 - TOP 12:00 3/25 - AOI 12:00 | 60 | 450 | 1B 1T | 10 | 300 | UPS RED | Redmond HQ - R&D |  | 3/22 - LINE 1 ("HALF-DAY" WORK) | DOC REL 2/23 | 3/19 | 8635.1 | BOT 1ST | 2024-03-27 | 2 | 2024-03-22 | 8
2024-03-27 |  | AWT PART SHORTAGES 3/21 - PCB DUE; SHORTAGES NO DUE DATE 3/22 - SHORTAGES DUE 3/22 - KIT CLEAR |  |  |  |  | 1 | 123954-3 BAL NEW | 40 | 3/27 3D | NL | X | *** 3 DAY TURN *** DO NOT SHIP EXCESS MATL USE SN/PB LEAD PROCESS NO CLEAN FLUX UPDATE: 2/20 "J21, J27, J28 & J32 ARE NOW DNI PER EMAIL SERIALIZATION REQUIRED CHECK ECO #7 FOR COMPONENT HEIGHT REQUIREMENTS SPECIAL CoC PER ECO #8 ***SHIP BACK ALL EXTRA PARTS W/ PCBA'S DEPANEL |  |  | 3/23 - BOT 6:00 3/24 - TOP 3/24 - AOI | 84 | 631 | 1B 2T | 32 | 1280 | UPS RED | Redmond HQ - R&D |  | 3/11 - SHIPPED INITIAL 30 OF 70 | DOC REL 2/21 | 3/21 | 19145.5 | BOT 1ST #81 & #92; ask salena if we need more of these parts | 2024-03-26 | 2
2024-03-26 |  | 3/11 - PCB DUE 3/12 - KIT CLEAR |  |  | 1 |  |  | 123920 NEW | 65 | 3/26 10D | NL | X | DEPANEL |  |  | 3/20 - BOT 11:00 3/20 - TOP 1:00 3/21 - AOI 9:30 | 36 | 101 | 1B 1T | 8 | 520 | UPS 2DAY | Rocky Research |  |  | DOC REL 2/26 | 3/11 | 3012.6 | bot 1st | 2024-03-26 | 2 | 2024-03-19
2024-03-25 |  | 3/18 - SHORT #63(CIRC1) 3/20 - KIT CLEAR |  |  |  |  | 1 | 122837 NEW | 4 | 3/25 3D | NL | X | *** 3 DAY TURN *** POST BAKE "CIRC1" IF WASHED MIX POP: circ1 2 boards w/ MX-735912529 2 boards w/ MX-735912717 DEPANEL |  |  | 3/20 - BOT 2:00 3/21 - TOP 8:30 3/21 - AOI 12:30 | 113 | 408 | 1B 2T | 19 | 76 | FEDEX P | University Of Oklahoma |  |  | DOC REL 1/25 | 3/18 | 5947.4 | BOT 1ST; UoO DEPANEL BEFORE TOP REQUIRED? PART VERIFICATION | 2024-03-25 | 2 | 2024-03-21 | 6.5
2024-03-25 |  | 3/15 - 3/18 MOST SHORTAGES DUE 3/18 - KIT CLEAR |  |  | 1 |  |  | 124214 ROWC 119565 | 40 | 3/25 5D | NL | ROWC | "SW1" AFTER WASH DEPANEL |  |  | 3/21 - TOP 8:30 3/21 - AOI 12:30 | 59 | 194 | 1T | 4 | 160 | UPS RED | Spectro Inc. |  |  | DOC REL 3/12 | 3/14 | 2787.2 | TOP ONLY | 2024-03-25 | 1 | 2024-03-19 | 4
2024-03-25 |  | 3/21 - KIT CLEAR |  |  | 1 |  |  | 116964-RMA RMA | 22 | 3/25 | NL |  | IC16 (item#33) SHT21 CORRECT PART: W/ MARKING D82JX INCORRECT PART: marking SEEXG |  |  | BACK | 68 | 264 | 2B 2T | 5 | 110 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2024-02-08 | 18941.69 | Customer wants to use a different part number for U8, U9 only, PN LTC2864MPS-2#PBF. U10, PN LTC2864MPS-1#PBF, will remain the same. BOT 1ST | 2024-03-19 | 2 | 2024-02-13 | 16.5
2024-03-25 |  | 3/14 - KIT CLEAR |  |  |  |  | 1 | 122746 NEW | 12 | 3/21 5D | NL | X | CLASS 3 "U12" QUALITY ALERT FOR ORIENTATION - SEE ECO #5 48HR PCB PRE-BAKE REQ TEAR DOWN - KEEP BUILD KIT IN TACT - DO NOT CUT BAGS |  |  | 3/19 - BOT 6:00 3/19 - TOP 3/19 - AOI 12:30 | 61 | 210 | 1B 1T | 8 | 96 | FEDEX P | University Of Oklahoma |  |  | DOC REL 1/25 | 3/14 | 3028 | PART VERIFICATION BOT 1ST | 2024-03-21 | 2 | 2024-03-19 | 6.5
2024-03-22 |  | 3/13 - KIT CLEAR |  |  |  |  | 1 | 122748 NEW | 24 | 3/27 10D | NL | X | CLASS 3 48HR PCB PRE-BAKE REQ TEAR DOWN - KEEP BUILD KIT IN TACT - DO NOT CUT BAGS |  |  | 3/15 - BOT 1:30 3/18 - TOP 8:00 3/18 - AOI 2:00 | 69 | 438 | 1B 1T | 4 | 96 | FEDEX P | University Of Oklahoma |  |  | DOC REL 1/26 | 3/13 | 4315.2 | BOT 1ST PART VERIFICATION | 2024-03-27 | 2 | 2024-03-15 | 8.5
2024-03-22 |  | 3/14 - PCB DUE; SHORT #33A (CIRC1,CIRC2) 3/14 - KIT CLEAR |  |  |  | 1 |  | 123545 NEW | 4 | 3/21 5D | NL | X | CLASS 3 48 HR BREBAKE REQ MIXED POP - DEFAULT Build (Qty 3) CIRC1, CIRC2 – PN MX-735912529 FLT1 - DNI DEVRF Build (Qty 1) CIRC1, CIRC2 – PN MX-735912717 FLT1 - Populated "CIRC1 & 2" BAKE AFTER WASH SEPERATE CoC'S MIXED POP PER ECO 8 |  |  | 3/15 - BOT 1:30 3/18 - TOP 10:00 3/19 - AOI 8:30 | 50 | 113 | 1B 1T | 14 | 56 | FEDEX P | University Of Oklahoma |  | 3/15 - J20, J21, J22 DOES NOT FIT | DOC REL 2/27 | 3/12 | 3024 | BOT 1ST PART VERIFICATION | 2024-03-21 | 2 | 2024-03-18 | 7
2024-03-22 |  | 2/28 - EXPECT CLEAR NEXT WEEK 3/1 - KIT CLEAR |  |  | 1 |  |  | 123201 NEW | 10 | 3/22 15D | NL | X | ***PRIOR TO SMT - REBALL LEAD FREE BGA'S TO LEADED Qty 20 OSD3358-512M-ISM Qty 20 MTFC8GACAENS-AAT |  |  | 3/7 - BOT 12:00 3/7 - TOP 8:00 3/8 - AOI 3:00 | 164 | 947 | 2B 2T | 26 | 260 | FEDEX P | Integrated Consultants |  |  | DOC REL 2/26 | 2/28 | 11101 | top 1st | 2024-03-22 | 2 | 2024-03-07 | 11
2024-03-22 |  | 1/8 - PCB DUE; NO ETA ON BGA 1/9 - KIT CLEAR 3/5 - NEW BGAs DUE DATE 3/14 - KIT CLEAR 3/15 - ship all 8 boards on 3/22 |  |  |  |  | 1 | 122618-1ST BAL NEW | 3 | 3/22 1/12 1/16 5D | NL | X | SKIP X1_1, X1_2 FOR ROBERT TO PLACE DNI #62, 64, 67 & 68 SPECIAL LABEL REQ SHIP RIGID BACKER IN ESD BAG DEPANEL & SAND |  |  | 1/10 - BOT 10:00 1/10 - TOP 11:30 1/11 - ON HOLD 10:00 3/15 - TOP 6:00 3/15 - AOI 10:00 | 60 | 321 | 1B 1T | 90 | 270 | FEDEX P | Cardinal Peak, LLC |  | 1/11 - ISSUE LOCATING PIN 1 FOR X1_1 & X1_2 1/11 - BGA WARPING WHEN GOES THROUGH REFLOW; 3/14 - PROCESS CHANGE SEE ECO 3/15 - JOE (ship 8 boards on 3/22) | DOC REL 1/5 | 1/5 | 6100 | measure label rigid backer in ESD BAG BOT 1ST | 2024-03-19 | 2 | 2024-03-15 | 5
2024-03-22 |  | 3/14 - KIT CLEAR 3/15 - ship all 8 boards on 3/22 |  |  |  |  | 1 | 122618-2nd ROWC 1st Article | 5 | 3/22 5D | NL | ROWC | 2ND ARTICLE LABEL REQ X1_1, X1_2 NON-ROHS LEADED REFLOW PROCESS IGNORE RIGID BACKER REQ (ECO) |  |  | 3/19 - BOT 1:00 3/19 - TOP 3/19 - AOI 12:30 | 56 | 299 | 1B 1T | 86 | 430 | FEDEX P | Cardinal Peak, LLC |  | 3/15 - JOE (ship 8 boards on 3/22) | DOC REL 3/14 | 3/14 | 3295 | top 1st | 2024-03-22 | 2 | 2024-03-19 | 7.5
2024-03-22 |  | 3/6 - KIT CLEAR |  |  |  | 1 |  | 122987 NEW | 100 | 3/22 3/11 3D | NL | X | *** 3 DAY TURN *** HAND-SOLDER NEW J1 REPLACEMENTS DEPANEL CoC PER ECO |  |  | 3/7 - TOP 9:30 3/7 - AOI 11:00 | 7 | 7 | 1T | 0 | 0 | UPS GRD | Myriad Women’s Health |  | 3/7 - technically not clear, awt J1 CONN replacement that will be hand-soldered | DOC REL 2/28 | 3/6 | 2023 | TOP ONLY | 2024-03-11 | 1 | 2024-03-07 | 1.5
2024-03-22 |  | 3/21 - KIT CLEAR |  |  | 1 |  |  | 124708 RONC 124325 | 12 | 3/22 1D | NL | RONC | *** 1 DAY TURN *** |  |  | 3/21 - BOT 11:00 3/21 - TOP 2:00 3/22 - AOI 7:00 | 3 | 11 | 1B 1T | 0 | 0 | UPS RED | Group O, Inc. |  |  | DOC REL 3/20 | 3/21 | 6195 | BOT 1ST | 2024-03-22 | 2 | 2024-03-21 | 4
2024-03-22 |  | 3/21 - KIT CLEAR |  |  | 2 |  |  | 124707 RONC 124326 | 12 | 3/22 1D | NL | RONC | *** 1 DAY TURN *** |  |  | 3/21 - TOP 12:00 3/21 - TOP 2:30 3/22 - AOI 7:00 | 5 | 24 | 1B 1T | 0 | 0 | UPS RED | Group O, Inc. |  |  | DOC REL 3/20 | 3/21 | 7815 | BOT 1ST | 2024-03-22 | 2 | 2024-03-21 | 4
2024-03-21 |  | 2/27 - SMT CLEAR; COMPLETE CLEAR FOR 43 KIT CLEAR 2/28 - day 1 (phuong) for 43 boards 3/15 - shipped 58 |  |  |  | 1 |  | 123781-3 BAL NEW | 39 | 3/21 5D | NL | X | DO NOT SHIP EXCESS MATL LEAD PROCESS "BZ1" AFTER WASH SER # PER ECO CONN HEIGHT REQUIREMENT PER ECO #8 CoC/PACK SLIP PER ECO #9 ***SHIP EXCESS PARTS BACK W/ ASSY'S |  |  | 2/29 - BOT 9:30 3/1 - AOI 12:00 | 38 | 217 | 1B | 5 | 195 | UPS RED | Redmond HQ - R&D |  |  | DOC REL 2/26 | 2/27 | 7797.4 | BOT ONLY | 2024-03-05 | 1 | 2024-02-28 | 5
2024-03-21 |  | 3/11 - PCB DUE 3/11 - KIT CLEAR |  |  | 1 |  |  | 124033 RONC 105145 | 210 | 4/1 15D | NL | RONC | SPECIAL MOUNTING INSTRUCTIONS FOR "H1, H3 & H4" PER ECO |  |  | 3/13 - TOP 8:00 3/13 - AOI 11:00 | 20 | 47 | 1T | 3 | 630 | FEDEX P | Moates.Net |  |  | DOC REL 2/23 | 3/6 | 2555.7 | top only | 2024-04-01 | 1 | 2024-03-13 | 3
2024-03-21 |  | 3/21 - KIT CLEAR |  |  | 1 |  |  | 116964-RMA RMA | 5 | 4/19 20D | NL |  | IC16 (item#33) SHT21 CORRECT PART: W/ MARKING D82JX INCORRECT PART: marking SEEXG |  |  | BACK | 68 | 264 | 2B 2T | 5 | 25 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2024-02-08 | 18941.69 | Customer wants to use a different part number for U8, U9 only, PN LTC2864MPS-2#PBF. U10, PN LTC2864MPS-1#PBF, will remain the same. BOT 1ST | 2024-03-19 | 2 | 2024-02-13 | 16.5
2024-03-19 |  | 3/1 - PCB & SHORTAGES DUE 2/26 - short #40 (EQ5) & #15 (U4A, U4B..) 3/5 - shortages due 3/4 - SMT CLEAR 3/11 - KIT CLEAR |  |  |  | 1 |  | 122774 NEW | 1 | 3/14 3D | NL | X | *** 3 DAY TURN *** DEPANEL & SAND |  |  | 3/12 - BOT 8:00 3/12 - TOP 11:00 3/13 - AOI 11:00 | 41 | 3960 | 1B 1T | 12 | 12 | FEDEX GRD | CACI |  | 3/4 - REQ THT SHLDs TO RUN SMT | DOC REL 2/20 | 2/22 | 5574 | bot 1st | 2024-03-14 | 2 | 2024-03-05 | 9
2024-03-20 |  | 3/14 - PCB DUE 3/13 - KIT CLEAR |  |  |  | 1 |  | 122657-1ST NEW | 2 | 3/20 5D | NL | X | First Article "U15" DO NOT WASH *NO SOLDER FLUX TO BE LEFT ON BOARDS DEPANEL |  |  | 3/15 - BOT 10:00 3/15 - TOP 3/15 - AOI 2:00 | 44 | 98 | 1B 1T | 5 | 10 | FEDEX P | Industrialex Manufacturing |  |  | DOC REL 3/1 | 3/11 | 1247 | BOT 1ST | 2024-03-20 | 2 | 2024-03-15 | 4
2024-03-19 |  | 3/5 - PCB DUE 3/8 - PCB DUE DATE 3/12 - SHORT #164(Q5,Q6,Q7) : SKIPPABLE 3/13 - KIT CLEAR |  |  |  |  | 1 | 124026 NEW | 10 | 3/20 5D | NL | X | DNI j9 & ship to customer DEPANEL BAR CODE LABELS REQUIRED PACKING LABEL REQUIRED |  |  | 3/13 - BOT 6:00 3/13 - TOP 9:00 3/14 - AOI 10:30 | 138 | 1468 | 1B 2T | 116 | 1160 | FEDEX P | Bausch & Lomb |  |  | DOC REL 2/28 | 3/1 | 10672.7 | BOT 1ST | 2024-03-20 | 2 | 2024-03-13 | 12.5
2024-03-19 |  | 3/12 - PCB DUE 3/12 - KIT CLEAR |  |  | 1 |  |  | 124240 NEW | 10 | 3/19 5D | NL | X | DNI #52 (TP1,TP2...) & SHIP W/ PCBAS U12 - PLACE AFTER WASH (ECO #3) |  |  | 3/13 - TOP 11:00 3/14 - AOI 8:00 | 80 | 235 | 2T | 25 | 250 | UPS 2DAY | Veranex |  |  | DOC REL 3/7 | 3/8 | 3378.4 | TOP ONLY | 2024-03-19 | 1 | 2024-03-14 | 5
2024-03-19 |  | 3/11 - PCB DUE 3/6 - PO CHANGED FORM 5D TO 3D 3/12 - KIT CLEAR 3/12 - CONTINUE PRODUCTION, BUT DO NOT SHIP UNTIL PHUONG SAYS OTHERWISE |  |  |  | 1 |  | 123907 NEW | 100 | 3/19 3/15 3D 5D | NL | X | *** 3 DAY TURN *** CLASS 3 NO AA LABELS / QR LABEL ONLY TRIM LEADS ECO #3 & #4 "J26" TRIM BEFORE INSTALLING QR LABEL REQUIRED PER ECO #5 |  |  | 3/13 - BOT 8:00 3/13 - TOP 2:00 3/14 - AOI 2:30 | 71 | 149 | 1B 1T | 16 | 1600 | FEDEX P | Industrialex Manufacturing |  |  | DOC REL 3/4 | 3/5 | 7780 | BOT 1ST | 2024-03-15 | 2 | 2024-03-13 | 12.5
2024-03-15 |  | 2/27 - SMT CLEAR; COMPLETE CLEAR FOR 43 KIT CLEAR 2/28 - day 1 (phuong) for 43 boards |  |  |  | 1 |  | 123781-2 par NEW | 58 | ??? 5D | NL | X | LEAD PROCESS "BZ1" AFTER WASH SER # PER ECO CONN HEIGHT REQUIREMENT PER ECO #8 CoC/PACK SLIP PER ECO #9 ***SHIP EXCESS PARTS BACK W/ ASSY'S |  |  | 2/29 - BOT 9:30 3/1 - AOI 12:00 | 38 | 217 | 1B | 5 | 290 | UPS RED | Redmond HQ - R&D |  |  | DOC REL 2/26 | 2/27 | 7797.4 | BOT ONLY | 2024-03-05 | 1 | 2024-02-28 | 5
2024-03-15 |  | 2/21 - SHORT PCB W/ NO DUE DATE 3/14 - PCB DUE DATE 3/15 - KIT CLEAR |  |  |  |  | 1 | 123248 NEW | 330 | 3/15 5D | NL | X | DEPANEL |  |  | 3/11 - TOP 9:30 3/12 - AOI 2:00 | 29 | 59 | 2T | 0 | 0 | FEDEX P | Turnkey Electronics Group |  |  | DOC REL 2/20 | 2/21 | 8324 | top only | 2024-03-15 | 1 | 2024-03-11
2024-03-15 |  | 3/12 - KIT CLEAR |  |  |  |  | 1 | 123099-2ND RONC 1st Article | 2 | 3/15 3D | NL | RONC | *** 3 DAY TURN *** CLASS 3 ALLOW EXTRA TIME FOR PRESS FIT QTY 43 DEPANEL MECH ASSY REQ |  |  | 3/14 - BOT 10:45 3/14 - TOP 3/14 - AOI 1:30 | 4 | 5 | 1B 1T | 85 | 170 | UPS GRD | Diversified Supply |  |  | DOC REL 3/12 | 3/14 | 6080 | TOP 1ST XTRA TIME NEEDED FOR THT/PRESS-FIT | 2024-03-15 | 2 | 2024-03-14 | 2.75
2024-03-15 |  | 3/4 - #20 (Y2) due 3/5 or 3/6 3/4 - AWT PART CONF #36 (U11) 3/6 - #20 & #36 PARTS DUE 3/6 - KIT CLEAR |  |  | 1 |  |  | 124091 NEW | 50 | 3/15 3/20 10D | NL | X | expedite to 3/15 "BT1" AFTER REFLOW "U11 & U5" DO NOT WASH MARKING & SER # PER ECO #5 |  |  | 3/8 - TOP 2:00 3/11 - BOT 11:00 3/12 - TOP 12:00 | 100 | 467 | 2B 1T | 60 | 3000 | UPS RED | DE Design Works |  | 3/8 - tuan & ngan both ran this job | DOC REL 2/23 | 3/4 | 8715.5 | TOP 1ST | 2024-03-20 | 2 | 2024-03-08 | 14.5
2024-03-14 |  | 2/28 - PCB DUE 3/6 - PCB DUE 3/5 - KIT CLEAR |  |  |  | 1 |  | 122568 NEW | 50 | 3/19 10D | NL | X | RECORD ALL AOI NON-CONFORMANCES DEPANEL |  |  | 3/6 - BOT 8:00 3/6 - TOP 3/7 - AOI 9:00 | 32 | 147 | 1B 1T | 3 | 150 | UPS GRD | ICC, Inc. |  |  | DOC REL 2/12 | 2/21 | 2940.5 | bot 1st non conformance noting required | 2024-03-19 | 2 | 2024-03-06 | 7
2024-03-13 |  | 3/8 - KIT CLEAR |  |  |  |  | 1 | 123871-1st NEW | 2 | 3/13 3D | NL | X | *** 3 DAY TURN *** DEPANEL |  |  | 3/11 BOT 8:00 3/11 - AOI 2:30 | 24 | 172 | 1B | 59 | 118 | FEDEX P | Design Solutions Inc. |  |  | DOC REL 2/26 | 3/8 | 23276 | BOT ONLY | 2024-03-13 | 1 | 2024-03-11 | 6.5
2024-03-13 |  | 2/2 - PCB DUE 2/16 - PCB DUE 2/22 - PCB DUE 2/23 - 895 / 1100 PCBs received 2/26 - short 7 pcbs 2/28 - KIT CLEAR |  |  | 1 |  |  | 123048 RONC 113185 | 1100 | 3/13 10D | NL | RONC | *MAKE SURE PCB'S ARE PRE-BAKED (CUST HAS HISTORY OF DELAM PCB'S DEPANEL |  |  | 2/27 - BOT 1:30 2/28 - TOP 2:30 | 7 | 59 | 1B 1T | 0 | 0 | UPS RED | Benchmark Electronics |  |  | DOC REL 1/23 | 1/31 | 11682 | BOT 1ST | 2024-03-13 | 2 | 2024-02-23 | 16.5
2024-03-13 |  | 3/12 - PCB DUE; SHORT #2(J3) & #3(W4,W5...) 3/12 - KIT CLEAR |  |  | 1 |  |  | 124325 NEW | 12 | 3/13 1D | NL | x | *** 1 DAY TURN *** DEPANEL |  |  | 3/12 - BOT 12:30 3/12 - TOP 1:30 3/12 - AOI 7:00 | 3 | 11 | 1B 1T | 0 | 0 | UPS RED | Group O, Inc. |  | 3/12 - AWT STENCIL | DOC REL 3/7 | 3/11 | 6995 | BOT 1ST | 2024-03-13 | 2 | 2024-03-12 | 3
2024-03-13 |  | 3/12 - PCB DUE; AWT PART CONF #2(J1), #3(J2) & #4(W0,W1...) 3/12 - KIT CLEAR |  |  | 2 |  |  | 124326 NEW | 12 | 3/13 1D | NL | x | *** 1 DAY TURN *** DEPANEL |  |  | 3/13 - BOT 6:30 3/13 - TOP 3/13 - AOI 8:00 | 5 | 24 | 1B 1T | 0 | 0 | UPS RED | Group O, Inc. |  | 3/12 - AWT STENCIL | DOC REL 3/7 | 3/11 | 8615 | BOT 1ST | 2024-03-13 | 2 | 2024-03-12 | 1.5
2024-03-13 |  | 2/27 - short pcb; no due date 3/7 - PCB DUE 3/6 - KIT CLEAR |  |  |  |  | 1 | 123910 (CUI) NEW | 10 | 3/13 5D | NL | X | CUI SHUNT J5 DOUBLE CHECK "D33" ORIENTATION (NATION EMAIL) |  |  | 3/6 - BOT 11:00 3/6 - TOP 2:00 3/7 - AOI 11:00 | 130 | 416 | 1B 2T | 17 | 170 | UPS RED | HII Unmanned Systems, Inc |  | 3/8 - MINUS 3 SMT HOURS DUE TO SHORT SHIFT | DOC REL 2/23 | 2/27 | 352.5 | bot 1st | 2024-03-13 | 2 | 2024-03-06 | 5
2024-03-12 |  | 3/7 - PCB DUE 3/1 - KIT CLEAR |  |  | 1 |  |  | 122735 NEW | 100 | 3/22 15D | NL | X | DEPANEL |  |  | 3/5 - TOP 10:30 3/5 - AOI 1:30 | 14 | 32 | 1T | 7 | 700 | FEDEX GRD | D&K Engineering |  |  | DOC REL 2/20 | 2/21 | 3860 | BOT 1ST DATE LABEL | 2024-03-22 | 2 | 2024-03-07 | 3
2024-03-12 |  | 3/8 - KIT CLEAR | [5 empty] | 124256 NEW | 3 | 3/13 3D | X |  | *** 3 DAY TURN *** NO LABEL REQUIRED THT ONLY CofC REQUIREMETNS |  |  | FSU | 0 | 0 |  | 83 | 249 | UPS RED | Digital Dynamics, Inc. |  |  | DOC REL 3/7 | 3/8 | 2966.5 | no label needed |  | 2
2024-03-11 |  | 3/1 - 30 OF 70 ALMOST CLEAR 3/5 - KIT CLEAR for 30; 40 BAL remaining 3/8 - shipped 1 of 70 |  |  |  |  | 1 | 123954-2 PAR NEW | 29 | 3/8 3D | NL | X | *** 3 DAY TURN *** USE SN/PB LEAD PROCESS NO CLEAN FLUX UPDATE: 2/20 "J21, J27, J28 & J32 ARE NOW DNI PER EMAIL SERIALIZATION REQUIRED CHECK ECO #7 FOR COMPONENT HEIGHT REQUIREMENTS SPECIAL CoC PER ECO #8 - (CUST NAME CHANGED TO AIGEN) ***SHIP BACK ALL EXTRA PARTS W/ PCBA'S DEPANEL |  |  | 3/6 - BOT 8:00 3/6 - TOP 11:00 3/6 - PAUSE; AWT FEEDER SETUP 3/6 - TOP 2:00 3/7 - AOI 12:00 | 84 | 631 | 1B 2T | 32 | 928 | UPS RED | Redmond HQ - R&D |  |  | DOC REL 2/21 | 3/1 | 19145.5 | BOT 1ST partial? | 2024-03-08 | 2 | 2024-03-05 | 9
2024-03-11 |  | 2/23 - EXPECTED CLEAR DATE; awt part conf #31 (TO1) CURRENTLY CLEAR TO RUN 75 BOARDS 2/27 - KIT CLEAR |  |  |  | 1 | 2 | 123291 RONC 120807 | 150 | 3/12 10D | NL | RONC | *** QUALITY ALERT *** PREVIOUS BUILD: CAPS NOT WETTED & MISALIGNED CLASS 3 DEPANEL |  |  | 2/26 - BOT 9:00 2/26 - TOP 2/26 - AOI 75 pcbs 2/28 - BOT 8:30 2/28 - TOP 2/29 - AOI 9:00 | 40 | 54 | 1B 1T | 0 | 0 | FEDEX P | Southwest Research Institute |  | 2/26 - 75 of 150 boards built | DOC REL 2/21 | 2/22 | 2268 | BOT 1ST | 2024-03-12 | 2 | 2024-02-26 | 9
2024-03-11 |  | 2/9 - SMT CLEAR; BUILT AND SHIPPED 60 ON 2/23 |  |  |  |  | 1 | 116970-2ND PAR RONC | 60 | 3/11 3/19 15D | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 300 L1 – P/N MSS5131-393MLC U2 – P/N LTC2864MPS-2#PBF DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/13 - TOP 9:00 2/13 - BOT 1:30 2/14 - AOI 12:00 | 29 | 54 | 2B 1T | 11 | 660 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2/8 | 9600 | L1 IS P/N MSS5131-393MLC BOT 1ST | 2024-03-19 | 2 | 2024-02-13 | 12
2024-03-08 |  | 3/1 - 30 OF 70 ALMOST CLEAR 3/5 - KIT CLEAR for 30; 40 BAL remaining 3/8 - shipped 1 of 70 |  |  |  |  | 1 | 123954-1 PAR NEW | 1 | 3/8 3D | NL | X | *** 3 DAY TURN *** USE SN/PB LEAD PROCESS NO CLEAN FLUX UPDATE: 2/20 "J21, J27, J28 & J32 ARE NOW DNI PER EMAIL SERIALIZATION REQUIRED CHECK ECO #7 FOR COMPONENT HEIGHT REQUIREMENTS SPECIAL CoC PER ECO #8 - (CUST NAME CHANGED TO AIGEN) ***SHIP BACK ALL EXTRA PARTS W/ PCBA'S DEPANEL |  |  | 3/6 - BOT 8:00 3/6 - TOP 11:00 3/6 - PAUSE; AWT FEEDER SETUP 3/6 - TOP 2:00 3/7 - AOI 12:00 | 84 | 631 | 1B 2T | 32 | 32 | UPS RED | Redmond HQ - R&D |  |  | DOC REL 2/21 | 3/1 | 19145.5 | BOT 1ST partial? | 2024-03-08 | 2 | 2024-03-05 | 9
2024-03-08 |  | 3/1 - ALMOST CLEAR 3/5 - KIT CLEAR |  |  | 1 |  |  | 124144 NEW | 20 | 3/8 3D | NL | X | *** 3 DAY TURN *** CLASS 3 CofC REQUIREMENT DEPANEL |  |  | 3/6 - BOT 9:00 3/6 - TOP 2:00 3/7 - AOI 12:00 | 180 | 1453 | 2B 2T | 6 | 120 | UPS RED | Reliable Robotics |  |  | DOC REL 3/1 | 3/1 | 18000 | BOT 1ST | 2024-03-08 | 3 | 2024-03-05 | 12
2024-03-08 |  | 3/4 - pcb & #23 (c46_uadca) due 3/1 - KIT CLEAR |  |  | 1 |  |  | 123806 NEW | 3 | 3/8 5D | NN | X | MECH ASSY (HEATSINKS) REQ DEPANEL |  |  | 3/5 - BOT 6:00 3/5 - TOP 3/5 - AOI 11:00 | 66 | 841 |  | 4 | 12 | FEDEX P | NOV Tuboscope Inc. |  |  | DOC REL 2/28 | 2/29 | 3136.1 | BOT 1ST | 2024-03-08 | 2 | 2024-03-05 | 5
2024-03-08 |  | 2/29 - EXPECTED CLEAR DATE 3/1 - KIT CLEAR |  |  |  | 1 |  | 122381 NEW | 1 | 3/8 5D | NL | X | ***READ ECO & DRAWING NOTES BEFORE RELEASING*** *** LEAD FORMING REQUIRED BEFORE SMT *** NO LABELS & STAMPS "J11& J12" ARE NOW INSTALL (PREVIOUSLY DNI) |  |  | 3/4 - BOT 8:30 3/4 - TOP 1:30 3/5 - AOI 9:00 | 137 | 2826 | 2B 2T | 55 | 55 | FEDEX P | Northrop Grumman Corporation |  |  | DOC REL 2/20 | 2/28 | 9469.7 | U17, U44 PRE-INSTALLATION REQUIREMENTS -> TOP 1ST PRE-BAKE REQUIREMENTS DO NOT PASTE IN SPECIFIED AREAS (ECO 3) | 2024-03-08 | 2 | 2024-03-05 | 8.5
2024-03-08 |  | 3/1 - PCB DUE 3/4 - KIT CLEAR |  |  | 1 |  |  | 123638 NEW | 400 | 3/8 5D | NL | X | NO ECO |  |  | 3/4 - BOT 6:00 3/4 - TOP 10:00 3/5 - AOI 7:00 | 23 | 81 | 1B 2T | 4 | 1600 | UPS RED | QinetiQ NA TSG |  |  | DOC REL 2/14 | 2/21 | 9062 | bot 1st | 2024-03-08 | 2 |  | 9
2024-03-08 |  | 2/9 - #15 (IC2) DUE DATE 2/9 - KIT CLEAR |  |  |  | 1 |  | 116966-3RD PAR RONC | 60 | 3/8 3/15 | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 300 J1 – P/N M80-5402042 2 LABEL TYPES & LOCS TEXT LABEL & QR CODE ENSURE S/N MATCH LABELS SPECIFIED LOCATIONS DEPANEL XRAY & SVE |  |  | 2/13 - BOT 12:00 2/13 - TOP 2:00 2/15 - AOI 2:00 | 34 | 154 | 2B 2T | 1 | 60 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2/8 | 10083.78 | BOT 1ST | 2024-03-19 | 2 | 2024-02-13 | 14
2024-03-08 |  | 2/7 - CLEARED FOR 190 BOARDS (60 BOARDS SHIPPED 2/14/24) |  |  |  |  | 999 | 116967-2ND PAR RONC | 60 | 3/8 3/13 | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 300 J1 – p/n approved M80-5402042 DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | RTR | 37 | 89 | 1T | 2 | 120 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2/7 | 8796 | TOP ONLY | 2024-03-19 | 1 | 2024-02-14
2024-03-07 |  | KIT CLEAR AWT CUSTOMER REPLY | [5 empty] | 122396-RMA RMA | 1 | ??? |  |  | 1. REMOVE ALL CONNECTORS 2. REMOVE ALL EXCESS SOLDER FROM LEADS & PCB HOLES 3. REMOVE EXCESS SOLDER FROM VIA 4. MASK REQUIRED VIA WITH DARK GREEN CIRCUITMEDIC PCB MASK EPOXY 5. CURE & REINSTALL CONNECTORS | [8 empty] | UPS RED |  |  |  | DOC REL 3/1 | 3/1
2024-03-07 |  | 2/8 - SHORT #27A (U10) NO ETA 2/9 - KIT CLEAR |  |  | 1 |  |  | 116964-3RD PAR RONC | 60 | 3/7 3/18 | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 300 U8, U9 – LTC2864MPS-2#PBF U10 – LTC2864MPS-1#PBF DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/13 - BOT 8:30 2/13 - TOP 12:30 2/15 - AOI 9:00 | 68 | 264 | 2B 2T | 5 | 300 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2024-02-08 | 18941.69 | Customer wants to use a different part number for U8, U9 only, PN LTC2864MPS-2#PBF. U10, PN LTC2864MPS-1#PBF, will remain the same. BOT 1ST | 2024-03-19 | 2 | 2024-02-13 | 16.5
2024-03-07 |  | 2/7 - KIT CLEAR |  |  | 1 |  |  | 116956-2ND PAR RONC | 60 | 3/7 3/14 | NL | RONC | DNI #20 (FB8) SCHEDULED SHIPMENT: SHIP 60 OF 300 L1 – P/N 1264EY-330M=P3 J1 – P/N M80-5402042 DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/8 - BOT 10:00 2/9 - TOP 5:00 2/9 - STOP 2:30 2/15 - TOP 9:00 2/15 - AOI 1:00 | 28 | 121 | 1B 1T | 3 | 180 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2024-02-07 | 11147 | BOT 1ST | 2024-03-19 | 2 | 2024-02-15 | 20
2024-03-07 |  | 2/8 - SHORT #10 (U1) & #7 (D10, D11...) NO ETA 2/9 - KIT CLEAR |  |  | 1 |  |  | 116954-2ND PAR RONC | 60 | 3/7 3/15 | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 300 no 0 OHM rework required U1 – P/N LTC2864MPS-1#PBF L1 – P/N MSS5131-393MLC J1 – P/N M80-5402042 DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/15 - TOP 1:00 2/16 - AOI 11:30 | 24 | 87 | 1T | 1 | 60 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2024-02-08 | 8324 | L1 IS P/N MSS5131-393MLC TOP ONLY | 2024-03-19 | 1 | 2024-02-15 | 6.5
2024-03-07 |  | 1/31 - PCB DUE SOON 3/4 - KIT CLEAR |  |  |  |  | 1 | 123188 NEW | 5 | 3/7 3D | NL | X | *** 3 DAY TURN *** "J1,J3,J4,J5,J7" REQ LOCTITE & TORQUE SPEC PRIOR TO SOLDERING PER ECO #2 SER #'S PER ECO #3 DEPANEL & SAND |  |  | 3/5 - BOT 9:00 3/5 - TOP 1:00 3/6 - AOI 10:00 | 94 | 808 | 1B 1T | 6 | 30 | FEDEX P | John Hopkins University Applied Physics La |  |  | DOC REL 1/26 | 1/31 | 6046 | BOT 1ST | 2024-03-07 | 2 | 2024-03-05 | 9
2024-03-06 |  | 12/22 - MAY CLEAR DATES 12/22 - KIT CLEAR |  |  | 1 |  |  | 121008-2ND BAL ROWC 1st Article | 18 | 3/6 20D | NL/NN | ROWC | SCHEDULED split shipment: o 20 boards 20 days after 2nd article clears o 18 boards 30 days after the initial 20 are shipped DEPANEL VERIFY "U24" PRE-BAKE? - SEE ECO #2 *SMT - VERIFY SW1_FT IS MASKED OFF PER ECO #3 - Mask no longer needed |  |  | 12/26 - BOT 11:30 12/27 - TOP 8:00 12/27 - AOI 2:00 | 127 | 800 | 1B 2T | 4 | 72 | UPS RED | Farsounder Inc |  |  | DOC REL 12/20 | 12/20 | 20764.28 | LINE 1 BOT 1ST BAKE #67(U24) FOR 48 HOURS? | 2024-01-23 | 2 | 2023-12-26 | 10.5
2024-03-06 |  | 3/1 - KIT CLEAR | [5 empty] | 124201-1st RMA | 2 | 3/6 3D |  |  | 1. REMOVE ALL CONNECTORS 2. REMOVE ALL EXCESS SOLDER FROM LEADS & PCB HOLES 3. REMOVE EXCESS SOLDER FROM VIA 4. MASK REQUIRED VIA WITH DARK GREEN CIRCUITMEDIC PCB MASK EPOXY 5. take photos and send to customer 5. CURE & REINSTALL CONNECTORS | [8 empty] | UPS RED |  |  |  | DOC REL 3/1 | 3/1 | 550
2024-03-06 |  | 3/1 - PCB DUE 2/28 - KIT CLEAR |  |  | 1 |  |  | 123733 NEW | 100 | 3/6 5D | NL | X | INSTALL "F1" FUSE INTO FUSE HOLDER DEPANEL SER # PER ECO |  |  | 2/29 - TOP 10:00 2/29 - AOI 11:00 | 4 | 4 | 1T | 9 | 900 | FEDEX P | Berkshire Grey |  |  | DOC REL 2/26 | 2/27 | 1583 | TOP ONLY | 2024-03-06 | 1 | 2024-02-29 | 1
2024-03-05 |  | 2/27 - SMT CLEAR; COMPLETE CLEAR FOR 43 KIT CLEAR 2/28 - day 1 (phuong) for 43 boards |  |  |  | 1 |  | 123781-1 PAR NEW | 43 | 3/5 5D | NL | X | LEAD PROCESS "BZ1" AFTER WASH SER # PER ECO CONN HEIGHT REQUIREMENT PER ECO #8 CoC/PACK SLIP PER ECO #9 ***SHIP EXCESS PARTS BACK W/ ASSY'S |  |  | 2/29 - BOT 9:30 3/1 - AOI 12:00 | 38 | 217 | 1B | 5 | 215 | UPS RED | Redmond HQ - R&D |  |  | DOC REL 2/26 | 2/27 | 7797.4 | BOT ONLY | 2024-03-05 | 1 | 2024-02-28 | 5
2024-03-04 |  | 2/23 - SHORT #17 (J225) - SKIP 2/29 - KIT CLEAR |  |  |  |  | 1 | 123516 NEW | 15 | 3/7 5D | NL | X | ICU MEDICAL - TRACK ALL NON-CONCFRMANCES CLASS 3 DEPANEL BARCODE LABLES REQUIRED |  |  | 2/27 - BOT 6:00 2/27 - AOI 11:00 | 31 | 225 | 1B | 32 | 480 | FEDEX INT PRIO | ICUMedical Costa Rica LTD |  |  | DOC REL 2/20 | 2/23 | 3835 | bot only use pogo block to align pins | 2024-03-04 | 2 | 2024-02-28 | 5
2024-03-04 |  | 2/13 - SHORT PARTS #33(U3..), #43(U40...), #44(U1) & #48(U18) 2/16 - SHORTAGES DUE 2/16 - KIT CLEAR |  |  |  | 1 | 1 | 120130-2ND ROWC 1st Article | 4 | 3/4 10D | NL | ROWC | DEPANEL "R547 & R92" CHANGED TO DNI MANUAL RWK REQUIRED PER ECO |  |  | 2/21 - bot 8:00 2/22 - TOP 1:30 2/26 - AOI 9:00 | 100 | 1714 | 1B 2T | 2 | 8 | FEDEX P | Blue Ridge Envisioneering, INC. |  | 2/21 - HAD TO REALIGN PROGRAM IN LINE 2; NOZZLE ISSUES, MOVING JOB TO L3 | DOC REL 2/7 | 2024-02-13 | 6424 | BOT 1ST | 2024-03-04 | 2 | 2024-02-20 | 27
2024-03-04 |  | 2/26 - KIT CLEAR FOR 40 OF 70 BOARDS |  |  |  |  | 1 | 123658-1 PAR NEW | 40 | 3/4 5D | NL | X | DEPANEL CoC/PACK SLIP PER ECO #4 |  |  | 2/27 - BOT 10:30 2/27 - TOP 1:30 2/28 - AOI 11:30 | 60 | 450 | 1B 1T | 10 | 400 | UPS RED | Redmond HQ - R&D |  |  | DOC REL 2/23 | 2/26 | 8635.1 | bot 1st | 2024-03-04 | 2 | 2024-02-27 | 9
2024-03-01 |  | 2/21 - PCB DUB 2/22 - KIT CLEAR |  |  | 1 |  |  | 123320 RONC 119812 | 500 | 3/21 20D | NL | RONC | ECO #4 - No solder on solder pads, DNP footprints, or test points unless indicated/requested. XRAY & SAVE INAGES DEPANEL |  |  | 2/23 - BOT 10:00 2/26 - TOP 1:30 2/27 - AOI 1:30 | 22 | 36 | 1B 1T | 0 | 0 | FEDEX P | Procter & Gamble Company |  |  | DOC REL 1/24 | 2/14 | 7995 | TOP 1ST | 2024-03-21 | 2 | 2024-02-23 | 19.5
2024-03-01 |  | 2/5 - SMT CLEAR |  |  | 1 |  |  | 116957-3RD PAR RONC | 60 | 3/14 20D | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 300 #3 (C4) ALT P/N UBT2A221MHD8TN DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/7 - BOT 11:00 2/7 - AOI 1:30 | 1 | 1 | 1B | 12 | 720 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2024-02-05 | 5385.78 |  |  | 1 | 2024-02-07 | 2.5
2024-03-01 |  | 2/5 - SMT CLEAR |  |  | 1 |  |  | 116955-3RD PAR RONC | 60 | 3/13 20D | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 300 SHORT #10 (J1,J2) P/N M80-5000000M2-02-331-00-000 DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/7 - TOP 9:00 2/7 - AOI 12:00 | 7 | 8 | 1T | 12 | 720 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2024-02-05 | 4896 |  |  | 1 |  | 3
2024-03-01 |  | 2/5 - SMT CLEAR 2/7 - 60 PCBAS OF 360 CLEAR TO SHIP 2/19 2/14 - KIT CLEAR |  |  | 1 |  |  | 116950-3RD PAR RONC | 60 | 3/13 20D | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 300 LEAD PROCESS DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/7 - BOT 1:30 2/8 - AOI 11:00 | 6 | 16 | 1B 1T | 5 | 300 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2/5 | 4689.47 |  |  | 2 | 2024-02-07 | 6.5
2024-03-01 |  | 2/26 - PCB DUE; SHORTAGES DUE BEFORE 2/26 2/26 - KIT CLEAR |  |  |  | 1 |  | 123657 RONC 117628 | 40 | 3/11 10D | NL | RONC | CLASS 3 NO CLEAN PROCESS DEPANEL |  |  | 2/27 - BOT 8:00 2/27 - TOP 12:30 2/27 - AOI 2:30 | 40 | 150 | 1B 1T | 1 | 40 | UPS GRD | Ultra Motion LLC |  |  | DOC REL 2/12 | 2/21 | 2440 | bot 1st | 2024-03-11 | 2 | 2024-02-27 | 8
2024-02-29 |  | 2/19 - PCB DUE 2/20 - KIT CLEAR |  |  | 1 |  |  | 123724 ROWC 121432 | 50 | 3/5 10D | NL | ROWC | All components must be mounted flush with the PCB Surface. NO Space allowed between board and component MECHANICAL ASSY w/paste REQ DEPANEL |  |  | 2/21 - TOP 11:30 2/21 - AOI 2:00 | 29 | 59 | 1T | 35 | 1750 | FEDEX P | Industrialex Manufacturing |  |  | DOC REL 2/12 | 2/13 | 2399 | TOP ONLY | 2024-03-05 | 1 | 2024-02-22 | 2.5
2024-02-28 |  | 2/21 - PCB DUE THAN SMT CLEAR 2/22 - SMT CLEAR 2/27 - KIT CLEAR |  |  | 2 |  |  | 123648-1ST NEW | 5 | 3/5 5D | NL | X | dni #26 (j7 & j8) & ship to customer LEAD PROCESS DEPANEL |  |  | 2/23 - AOI | 39 | 197 | 1B 1T | 8 | 40 | FEDEX GRD | OnLogic |  |  | DOC REL 2/20 | 2/21 | 2127 | bot 1st depanel before top required | 2024-02-29 | 2
2024-02-27 |  | 2/27 - PCB DUE 2/21 - KIT CLEAR |  |  | 1 |  |  | 123855 RONC 120450 | 30 | 3/6 10D | NL | RONC | DEPANEL |  |  | 2/21 - BOT 2:00 2/23 - AOI | 2 | 2 | 1B 1T | 0 | 0 | FEDEX P | Aila Technologies, Inc. |  | 2/22 - LINEMAN DAY OFF | DOC REL 2/14 | 2/15 | 1530 | bot 1st | 2024-03-06 | 2 | 2024-02-22
2024-02-26 |  | 2/20 - PCB DUE; SHORT ATTRITION & PARTS 2/20 - KIT CLEAR |  |  | 2 |  |  | 123537 NEW | 18 | 2/27 5D | NL | X | PARTS NOT MORE THAN 2 YEARS OLD SOME SILKSCREEN MAY BE CUT OFF, REVIEW ECO FOR PART PLACEMENT SANDING REQUIREMENTS POST-BAKE BOARDS BEFORE SHIP |  |  | 2/21 - BOT 7:00 2/21 - TOP 9:00 2/21 - AOI 12:30 | 49 | 181 | 1B 1T | 63 | 1134 | FEDEX P | Nextern Inc. |  |  | DOC REL 2/14 | 2/15 | 3217.32 | bot 1st | 2024-02-27 | 2 |  | 5.5
2024-02-23 |  | 2/15 - KIT CLEAR |  |  | 1 |  |  | 123846 RONC 121472 | 50 | 2/23 5D | NL | RONC | DEPANEL CofC REQ + SHIP EXCESS W/ PCBAS |  |  | 2/20 - BOT 10:30 2/21 - AOI 8:00 | 75 | 143 | 1B 1T | 11 | 550 | UPS RED | Scalvy, Inc. |  | 2/20 - A LOT OF VIA HOLES; NEEDED TO | DOC REL 2/14 | 2/15 | 2253 | bot 1st | 2024-02-23 | 2 | 2024-02-20 | 6
2024-02-23 |  | 2/9 - KIT CLEAR |  |  | 4 |  |  | 123578 RONC 121705 | 12 | 2/26 10D | NL | RONC | DEPANEL |  |  | 2/16 - AOI | 1 | 40 | 1T | 47 | 564 | FEDEX P | Innomotics LLC |  |  | DOC REL 2/7 | 2/9 | 3204 | TOP ONLY | 2024-02-26 | 1 | 2024-02-20
2024-02-23 |  | 2/14 - PCB & SHORTAGES DUE SOON 2/15 - KIT CLEAR |  |  |  |  | 1 | 119322 NEW | 2 | 2/23 5D | NN | X | CLASS 3 |  |  | 2/20 - BOT 6:00 2/20 - TOP 11:00 2/21 - AOI 12:00 | 252 | 2189 | 4B 4T | 24 | 48 | FEDEX P | The Boeing Company |  |  | DOC REL 9/13 | 2024-02-14 | 13851.5 | 4-MACHINE JOB; BOT 1ST; R | 2024-02-23 | 2 | 2024-02-20 | 12
2024-02-23 |  | 2/15 - PCB DUE |  |  | 2 |  |  | 123678 NEW | 45 | 2/23 5D | NL | X | DNI SW1 INSTALL DAUGHTER BOARDS (SEE ECO) INSTALL PS1 AFTER WASH DEPANEL |  |  | 2/16 - TOP 11:00 2/20 - AOI 8:00 | 21 | 213 | 1T | 57 | 2565 | FEDEX P | Seurat Technologies, Inc. |  |  | DOC REL 2/9 | 2/12 | 4413.95 | TOP ONLY | 2024-02-23 | 1 | 2024-02-19 | 5.5
2024-02-23 | [7 empty] | 123335-RMA RWK | 4 | 2/23 3D | X |  |  |  |  | FSU |  |  |  |  | 0 | FEDEX P | Astrobotic Technology, Inc. |  |  | NO DOC. |  | 550
2024-02-22 |  | 2/16 - PCB DUE 2/16 - KIT CLEAR |  |  | 3 |  |  | 123789 NEW | 40 | 2/26 5D | NL | X | DEPANEL |  |  | 2/20 - BOT 8:00 2/20 - TOP 2/20 - AOI 11:00 | 46 | 205 | 1B 1T | 16 | 640 | FEDEX STD | Lake Shore Cryotronics, Inc. |  |  | DOC REL 2/9 | 2/14 | 3295.2 | BOT 1ST | 2024-02-26 | 2 | 2024-02-16 | 3
2024-02-22 |  | 2/13 - KIT CLEAR | [5 empty] | 123679 NEW | 20 | 2/28 10D | X |  | T/H ONLY DEPANEL |  |  | BACK | 0 | 0 | 0 | 38 | 760 | FEDEX P | Seurat Technologies, Inc. |  |  | DOC REL 2/8 | 2/13 | 2867 | THT ONLY
2024-02-22 |  | 2/9 - SMT CLEAR; BUT CAN BUILD 60 BOARDS OF 360 TO SHIP |  |  |  |  | 1 | 116970-2ND PAR RONC | 60 | 2/23 15D | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 360 L1 – P/N MSS5131-393MLC U2 – P/N LTC2864MPS-2#PBF DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/12 - TOP 1:30 2/13 - BOT 8:00 2/13 - AOI 11:00 | 29 | 54 | 2B 1T | 11 | 660 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2/8 | 9600 | L1 IS P/N MSS5131-393MLC BOT 1ST | 2024-02-23 | 2 |  | 5.5
2024-02-22 |  | 2/13 - PCB DUE 2/8 - KIT CLEAR |  |  |  |  | 1 | 123650 RONC 122424 | 200 | 2/23 10D | NL | RONC | NO FLUX ON BOARD (ECO #3) MIX POP: 100 board: Use P/N GRT1555C1H102FA02D for C5, C9, C10, C11, C13, C14, C15 Label S/N: XXXAV3 where XXX: 501-600 100 board: Use P/N GRM1557U1A202JA01D for C5, C9, C10, C11, C13, C14, C15 Label S/N: XXX AV4 where XXX: 601-700 |  |  | 2/14 - BOT 2:30 2/15 - TOP 9:00 2/15 - AOI 11:00 | 26 | 59 | 1B 1T | 4 | 800 | FEDEX P | Open Source Instruments Inc |  |  | DOC REL 2/7 | 2/7 | 2984 | BOT 1ST MIX LOT | 2024-02-23 | 2 | 2024-02-14 | 5
2024-02-22 |  | 2/13 - PCB DUE 2/14 - KIT CLEAR |  |  |  |  | 1 | 122435 RONC 118436 | 50 | 2/22 5D | NL | RONC | PARTS ORIENTATION (ECO) DEPANEL |  |  | 2/15 - BOT 1:00 2/16 - TOP 6:00 2/16 - AOI 10:30 | 32 | 131 | 1B 1T | 7 | 350 | UPS GRD | Churchill Navigation dba Shotover Systems Inc |  |  | DOC REL 2/7 | 2/8 | 2118.5 | BOT 1ST | 2024-02-22 | 2 | 2024-02-15 | 6
2024-02-21 |  | 2/8 - SHORT #27A (U10) NO ETA 2/9 - KIT CLEAR |  |  | 1 |  |  | 116964-3RD PAR RONC | 60 | 2/21 15D | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 360 U8, U9 – LTC2864MPS-2#PBF U10 – LTC2864MPS-1#PBF DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/12 - BOT 8:00 2/12 - TOP 1:30 2/13 - AOI 9:30 | 68 | 264 | 2B 2T | 5 | 300 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2024-02-08 | 18941.69 | Customer wants to use a different part number for U8, U9 only, PN LTC2864MPS-2#PBF. U10, PN LTC2864MPS-1#PBF, will remain the same. BOT 1ST | 2024-02-21 | 2 |  | 9.5
2024-02-20 |  | 2/9 - #15 (IC2) DUE DATE 2/9 - KIT CLEAR |  |  |  | 1 |  | 116966-3RD PAR RONC | 60 | 2/22 15D | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 360 J1 – P/N M80-5402042 2 LABEL TYPES & LOCS TEXT LABEL & QR CODE ENSURE S/N MATCH LABELS SPECIFIED LOCATIONS DEPANEL XRAY & SVE |  |  | 2/13 - BOT 9:00 2/13 - TOP 12:00 2/14 - 10:00 | 34 | 154 | 2B 2T | 1 | 60 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2/8 | 10083.78 | BOT 1ST | 2024-02-22 | 2 | 2024-02-13 | 7
2024-02-16 |  | 2/8 - SHORT #10 (U1) & #7 (D10, D11...) NO ETA 2/9 - KIT CLEAR |  |  | 1 |  |  | 116954-2ND PAR RONC | 60 | 2/20 15D | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 360 no 0 OHM rework required U1 – P/N LTC2864MPS-1#PBF L1 – P/N MSS5131-393MLC J1 – P/N M80-5402042 DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/9 - TOP 12:30 2/9 - AOI 9:00 | 24 | 87 | 1T | 1 | 60 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2024-02-08 | 8324 | L1 IS P/N MSS5131-393MLC TOP ONLY | 2024-02-20 | 1 |  | 4
2024-02-15 |  | 2/5 - SMT CLEAR 2/7 - 60 BOARDS NOT CLEAR TO SHIP ON 2/19; except for C4 which is awaiting for alt part: UBT2A221MHD8TN 2/9 - KIT CLEAR |  |  | 1 |  |  | 116957-3RD PAR RONC | 60 | 2/21 15D | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 360 #3 (C4) ALT P/N UBT2A221MHD8TN DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/7 - BOT 11:00 2/7 - AOI 1:30 | 1 | 1 | 1B | 12 | 720 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2024-02-05 | 5385.78 |  | 2024-02-16 | 1 | 2024-02-07 | 2.5
2024-02-15 |  | 2/7 - KIT CLEAR |  |  | 4 |  |  | 116956-2ND PAR RONC | 60 | 2/16 15D | NL | RONC | DNI #20 (FB8) SCHEDULED SHIPMENT: SHIP 60 OF 360 L1 – P/N 1264EY-330M=P3 J1 – P/N M80-5402042 DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/8 - BOT 10:00 2/9 - TOP 5:00 2/9 - AOI 8:00 | 28 | 121 | 1B 1T | 3 | 180 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2024-02-07 | 11147 | BOT 1ST | 2024-02-16 | 2 | 2024-02-06 | 6
2024-02-15 |  | 2/7 - KIT CLEAR |  |  |  |  | 3 | 123635 RONC 120450 | 30 | 2/22 10D | NL | RONC | DEPANEL |  |  | 2/8 - AOI | 2 | 2 | 1B 1T | 0 | 0 | FEDEX P | Aila Technologies, Inc. |  |  | DOC REL 2/7 | 2/7 | 1530 | BOT 1ST DEPANEL TOP? | 2024-02-21 | 2 | 2024-02-09
2024-02-15 |  | 1/23 - KIT CLEAR |  |  | 1 |  |  | 122994 RONC 118323 | 11 | 2/21 20D | NL | RONC | CLASS 3 DEPANEL |  |  | 1/31 - BOT 6:00 1/31 - BOT DONE 7:00 2/1 - TOP 9:00 2/1 - AOI 12:00 | 80 | 682 | 1B 1T | 7 | 77 | UPS 3DAY | Coastal Designs, LLC |  |  | DOC REL 1/17 | 1/23 | 3910.5 | BOT 1ST | 2024-02-21 | 2 | 2024-01-30 | 4
2024-02-14 |  | 2/5 - SMT CLEAR 2/7 - 60 PCBAS OF 360 CLEAR TO SHIP 2/19 |  |  | 1 |  |  | 116950-3RD PAR RONC | 60 | 2/16 15D | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 360 C7 - Please use the 131 pcs of UBT2A221MHD1TN and we will order 229 of UBT2A221MHD8TN DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/7 - BOT 1:30 2/8 - AOI 11:00 | 6 | 16 | 1B 1T | 5 | 300 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2/5 | 4689.47 |  | 2024-02-16 | 2 | 2024-02-07 | 6.5
2024-02-14 |  | 2/7 - KIT CLEAR |  |  |  |  | 1 | 116967-2ND PAR RONC | 60 | 2/16 15D | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 360 J1 – p/n approved M80-5402042 DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/8 - TOP 9:00 2/8 - AOI 2:00 | 37 | 89 | 1T | 2 | 120 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2/7 | 8796 |  | 2024-02-16 | 1 | 2024-02-08 | 5
2024-02-14 |  | 1/15 - WEEK #19 & #21 PARTS DUE 1/26 - #19 (u14..) due 2/7 - KIT CLEAR |  |  |  |  | 1 | 122596 NEW | 100 | 2/14 5D | NL | X | MECH ASSY WITH LOCTITE 42540 AND TIGHTEN TO 25 cN-m |  |  | 2/9 - BOT 5:00 2/9 - TOP 9:00 2/9 - AOI 9:30 | 49 | 139 | 1B 1T | 1 | 100 | UPS RED | Intuitive Surgical |  | 1/11 - DO NOT ORDER STENCIL UNTIL FINAL ARRAY ARRIVE 1/11 - MOUSEBITES W/O HOLES 2/6 - OK TO RUN TOP ONLY 2/8 - AWT STENCIL | DOC REL 12/20 | 1/11 | 3951 | MECHANICAL W/ THREADLOCKER (MISSING) TOP SIDE 1ST SMALL PARTS (SIZE 201) | 2024-02-14 | 2 | 2024-02-07 | 12.5
2024-02-14 |  | 1/12 - KIT CLEAR 1/15 - ON HOLD (AWT CUST) 1/31 - KIT CLEAR | [5 empty] | 120178-2 BAL NEW | 24 | 2/14 1/26 10D | X |  | attach the other two small threaded inserts to the board RUN ONLY 1 BOARD, TAKE PHOTOS AND SEND TO CUSTOMER TO WAIT REPLY 30-min max |  |  | BACK | 0 | 0 |  | 9 | 216 | UPS GRD | Photonis Scientific, Inc. |  |  | DOC REL 1/3 | 1/12 | 2187.5 | tht only job; build only 1 board and send customer a picture of the board. wait 30 minutes for customer reply before continuing
2024-02-14 |  | 2/8 - PCB DUE 1/31 - KIT CLEAR |  |  | 1 |  |  | 123416 RONC 119275 2nd Article | 25 | 2/14 10D | NL | RONC | "J5" LEAVE PASTE ON CENTER PAD "BUT1 & RST1" AFTER WASH DEPANEL |  |  | 2/5 - TOP 1:30 2/6 - AOI 8:00 | 52 | 118 | 1T | 14 | 350 | FEDEX P | Industrialex Manufacturing |  |  | DOC REL 1/26 | 1/29 | 1345 | TOP ONLY | 2024-02-14 | 1 | 2024-02-05 | 3
2024-02-13 |  | 2/5 - SMT CLEAR 2/7 - CLEARED FOR SHIP 60 OF 360 |  |  | 1 |  |  | 116955-3 PAR RONC | 60 | 2/16 15D | NL | RONC | SCHEDULED SHIPMENT: SHIP 60 OF 360 SHORT #10 (J1,J2) P/N M80-5000000M2-02-331-00-000 DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 2/7 - TOP 9:00 2/7 - AOI 12:00 | 7 | 8 | 1T | 12 | 720 | FEDEX P | Anderson Connectivity |  |  | DOC REL 2/2 | 2024-02-05 | 4896 |  | 2024-02-16 | 1 |  | 3
2024-02-13 |  | 1/31 - KIT CLEAR |  |  | 1 |  |  | 120828 RONC 119129 | 60 | 2/14 10D | NL | RONC | CLASS 3 SER # REQ DEPANEL |  |  | 2/2 - BOT 7:00 2/2 - TOP 10:00 2/5 - AOI 10:00 | 120 | 400 | 2B 2T | 18 | 1080 | UPS 3DAY | Coastal Designs, LLC |  |  | DOC REL 1/30 | 1/31 | 8939.4 | BOT 1ST | 2024-02-14 | 2 | 2024-02-01 | 11
2024-02-12 |  | 2/7 - PCB DUE 2/7 - KIT CLEAR |  |  |  |  | 2 | 123200 NEW | 200 | 2/14 5D | NL | X | ***DO NOT DEPANEL*** CLASS 3 |  |  | 2/8 - AOI | 1 | 15 | 1T | 0 | 0 | UPS GRD | Soderberg Mfg |  |  | DOC REL 1/22 | 2/5 | 1582 | do not depanel top side only | 2024-02-14 | 1 | 2024-02-09
2024-02-12 |  | 2/2 - PCB DUE 2/5 - PCB DUE 2/6 - KIT CLEAR |  |  |  |  | 1 | 123146 NEW | 270 | 2/13 5D | NL | X | Mixed Pop parts required: Q1 – Part Num Lot ID QTY TP65H300G4LSG G23A009 90 TP65H300G4LSG G23I001-1 90 TP65H300G4LSG G23I001-2 90 As per previous request from TPH please keep TPH LotID and serialized ID's unmixed. DEPANEL |  |  | 2/7 - TOP 8:00 2/7 - AOI 11:00 | 2 | 2 | 1T | 0 | 0 | FEDEX P | Transphorm USA |  |  | DOC REL 1/30 | 1/31 | 2755 | TOP ONLY | 2024-02-13 | 1 |  | 3
2024-02-08 |  | 2/2 - SHORTAGES DUE 2/5 - #35, #51, #72, #76 & #99 DUE 2/6 - #51 (U43) DUE 2/6 - KIT CLEAR |  |  | 1 |  |  | 123214 ROWC 121671 | 20 | 2/9 3D | NL | ROWC | ***(2/28/24 ADDED ALTA ALERT FOR SOLDER BRIDGE - CUSTOMER FINDING) #99 (P13) DNI *** 3 DAY TURN *** SEE ECO NOTE #1: BOTTOM SILKSCREEN DOES NOT HAVE ROTATIONAL MARKINGS - USE SMT_PDF TRIANGEL & DOUBLE CHECK WITH ASSY DWG |  |  | 2/6 - BOT 7:00 2/6 - TOP 11:30 2/7 - AOI 10:00 | 90 | 535 | 1B 2T | 40 | 800 | FEDEX P | Saronic Technologies |  | 2/6 - RUN BOTTOM ONLY WHILE WE WAIT FOR U43 | DOC REL 1/30 | 2/1 | 15050 | BOT 1ST | 2024-02-09 | 2 | 2024-02-05 | 11
2024-02-08 |  | 2/2 - KIT CLEAR |  |  |  |  | 1 | 123454 NEW | 50 | 2/9 5D | NL | X | DEPANEL |  |  | 2/5 - BOT 9:00 2/5 - TOP 2/5 - AOI 12:30 | 6 | 36 | 1B 1T | 16 | 800 | FEDEX P | Diligent Robotics |  |  | DOC REL 1/30 | 2/2 | 1602.5 | BOT 1ST | 2024-02-09 | 2 | 2024-02-05 | 3.5
2024-02-08 |  | 2/1 - SMT SHORT ATTRITION & THT SHORT 1 LINE ITEM 2/5 - KIT CLEAR |  |  | 1 |  |  | 123335 NEW | 4 | 2/8 3D | NL | X | #48 (J1, J2) BTD *** 3 DAY TURN *** CLASS 3 MECH ASSY TRIM LENGTH REQUIREMENTS (ECO) |  |  | 2/5 - BOT 9:00 2/5 - TOP 11:00 2/5 - AOI 2:00 | 105 | 890 | 1B 1T | 11 | 44 | UPS RED | Astrobotic Technology, Inc. |  |  | DOC REL 1/31 | 2/1 | 6820 | JOE MONITOR BOT 1ST | 2024-02-08 | 2 | 2024-02-05 | 5
2024-02-08 |  | 1/30 - SHORT PCB & AWT PART CONF #41, 42 & 98 2/2 - PCB DUE 2/5 - PCB DUE 2/5 - KIT CLEAR |  |  |  |  | 1 | 123104-1ST NEW | 4 | 2/8 3D | NL | X | HAND SOLDER Z8 - Z12 *** 3 DAY TURN *** MASK OFF PADS (ECO #2 & #3) AFTER WASH T4, SW1, SW4, Z3-Z7 |  |  | 2/5 - BOT 10:30 2/5 - TOP 3:00 2/6 - AOI 10:30 | 157 | 532 | 1B 3T | 54 | 216 | FEDEX P | Farsounder Inc |  | 2/5 - Z8 - Z12 PART TOO LARGE TO MASK OFF INDICATED AREAS IN ECO; HAND SOLDER REQUIRED AND NEW STENCIL REQUIRED FOR FUTURE BUILDS 2/8 - REQUIRES A LOT OF TRIMMING & TAKES ABOUT 3 MIN / BOARD TO DRY AFTER WASH | DOC REL 1/29 | 1/30 | 4830 | BOT 1ST | 2024-02-08 | 3 | 2024-02-05 | 8
2024-02-08 |  | 2/1 - EXPECT CLEAR DATE 2/1 - KIT CLEAR |  |  |  |  | 1 | 123232 NEW | 60 | 2/8 5D | NL | X | *SPECIAL DEPANEL REQUIREMENTS PER ECO #1 UNIQUE SER # PER ECO#4 |  |  | 2/3 - AOI | 40 | 87 | 1T | 13 | 780 | FEDEX P | Nextern Inc. |  |  | DOC REL 1/19 | 1/31 | 2768.6 | TOP ONLY | 2024-02-08 | 1 | 2024-02-02
2024-02-07 |  | 1/31 - PCB DUE 2/1 - KIT CLEAR |  |  |  |  | 2 | 122932 NEW | 45 | 2/8 5D | NL | X | DEPANEL "J6" - DO NOT TRIM LEADS |  |  | 2/3 - AOI | 3 | 8 | 1T | 12 | 540 | FEDEX P | Novo Space |  |  | DOC REL 1/8 | 1/29 | 3725 | TOP ONLY | 2024-02-08 | 1 | 2024-02-02
2024-02-07 |  | 1/30 - KIT CLEAR, BUT NO JOB RELEASE OR PROGRAM TO START |  |  | 1 |  |  | 119432-2nd ROWC 1st Article | 4 | 2/7 5D | RT/RL | ROWC | BUILD ONLY 4 BOARDS & SHIP 1 BLANK PCB TO CUSTOMER DEPANEL |  |  | 2/1 - BOT 12:30 2/1 - TOP 3:00 2/2 - AOI 7:00 | 148 | 1075 |  | 10 | 40 | FEDEX P | Phoenix Contact, Inc. |  |  | DOC REL 1/30 | 2024-01-31 | 9340.56 | BOT 1ST | 2024-02-07 | 2 | 2024-02-01 | 5
2024-02-06 |  | 1/29 - AWT PART CONF #19 2/6 - KIT CLEAR |  |  | 1 |  | 1 | 123078 RONC 121844 | 220 | 2/6 5D | NL | RONC | XTRA TIME NEEDED FOR THT MASK OFF @ J10 LOCATION (ECO) NO CLEAN JOB (ECO #4 & #5) |  |  | 1/30 - BOT 11:30 1/31 - TOP 8:00 2/1 - AOI 11:00 | 65 | 422 | 2B 2T | 53 | 11660 | FEDEX P | Industrialex Manufacturing |  | 1/31 - SPLIT RUN ON 2 LINES; L1 WILL RUN 70%+ OF TOP WHILE LINE 3 RUNS THE REMAINING SIMULATANEOUSLY NOTES: TOTAL BOT COMP TIME 9 HRS TOTAL TIME TOP 13 HRS | DOC REL 1/24 | 1/29 | 37395.6 | black & white; heavy THT run before job clear bot 1st | 2024-02-06 | 2 | 2024-01-30 | 22
2024-02-06 |  | 2/5 - KIT CLEAR 2/6 - ON HOLD 2/6 - CANCELLED | [5 empty] | 121816 RWK | 4 | 2/12 5D | X |  | 2314020 Remove XA1, XA2 (160-pin connectors) 2314013 Remove XA5 (96-pin connector) 2314017 Replace J16 2314005 Replace J10 |  |  | BACK |  |  |  | 5 | 20 | UPS RED | Coastal Designs, LLC |  |  | DOC REL 2/5 | 2/5 | 2500
2024-02-05 |  | 12/21 - SHORT PCBS 1/17 - PCB DUE 1/23 - KIT CLEAR (WILL |  |  |  |  | 1 | 104573-3 BAL NEW | 10 | 2/6 10D | NL | X | ***PLEASE SHIP ON 2/5 OR SOONER*** CLASS 3 "J2A-J8D & J16 MUST HAVE SUFFICIENT SOLLDER PER ECO # 5 DEPANEL 48 HR PCB PREBAKE BUILD KIT MUST BE KEPT INTACT PER ECO |  |  | 1/25 - BOT 12:30 1/29 - TOP 6:00 1/30 - AOI 12:00 | 240 | 4158 | 2B 3T | 1 | 10 | FEDEX P | University of Oklahoma |  |  | DOC REL 12/12 | 12/21 | 14759.1 | PCBS REQ 48 PRE-BAKE BOT 1ST SMALL PARTS (SIZE 201) | 2024-02-06 | 2 | 2024-01-25 | 23.5
2024-02-02 |  | 1/30 - PCB & U9 DUE 1/30 - KIT CLEAR |  |  | 1 |  |  | 123189 NEW | 5 | 2/2 3D | NL | X | *** 3 DAY TURN *** "J2" REQ LOCTITE & TORQUE SPEC PRIOR TO SOLDERING PER ECO #2 SER #'S PER ECO #3 DEPANEL & SAND |  |  | 1/30 - BOT 2:00 1/30 - TOP 3:00 1/31 - AOI 6:00 | 53 | 753 | 1B 1T | 7 | 35 | FEDEX P | John Hopkins University Applied Physics La |  |  | DOC REL 1/26 | 1/29 | 5714.25 | BOT 1ST | 2024-02-02 | 2 | 2024-01-31 | 3.5
2024-02-02 |  | 1/26 - KIT CLEAR |  |  | 1 |  |  | 123099-1ST NEW | 2 | 2/2 5D | NL | X | CLASS 3 ALLOW EXTRA TIME FOR PRESS FIT QTY 43 DEPANEL MECH ASSY REQ |  |  | 1/30 - BOT 1:00 1/30 - TOP 1/30 - AOI 4:30 | 4 | 5 | 1B 1T | 85 | 170 | UPS GRD | Diversified Supply |  |  | DOC REL 1/17 | 1/29 | 4850 | TOP 1ST XTRA TIME NEEDED FOR THT/PRESS-FIT | 2024-02-02 | 2 | 2024-01-31 | 3.5
2024-02-01 |  | 1/25 - PCB DUE 1/25 - KIT CLEAR |  |  | 1 |  |  | 123193 NEW | 10 | 2/1 5D | NL | X | "LS1, U16 & U20" AFTER WASH "JP4 & JP9" REMOVE MIDDLE PIN" QTY 4 SHUNTS installed REQ DEPANEL |  |  | 1/30 - BOT 9:30 1/30 - TOP 11:00 1/30 - AOI 1:00 | 84 | 312 | 1B 2T | 59 | 590 | FEDEX P | Adona Medical, Inc. |  |  | DOC REL 1/23 | 1/23 | 3854.5 | BOT 1ST | 2024-02-01 | 2 | 2024-01-30 | 3.5
2024-02-01 |  | 1/25 OR 1/26 - CLEAR DATE 1/25 - KIT CLEAR |  |  | 1 |  |  | 123244 NEW | 60 | 2/1 5D | NL | X | BTD #96 (Q10, Q11) *SPECIAL DEPANEL REQUIREMENTS PER ECO #1 CONFIRM "U20" MACK OFF PER ECO #2 "U2" AFTER WASH POST BAKE REQ IF WASHED UNIQUE SER # PER ECO#6 |  |  | 1/29 - TOP 9:00 1/29 - BOT 1:00 1/30 - AOI 10:30 | 78 | 342 | 2B 1T | 77 | 4620 | FEDEX P | Nextern Inc. |  |  | DOC REL 1/19 | 1/24 | 11084.2 | TOP 1ST | 2024-02-01 | 2 | 2024-01-29 | 9.5
2024-01-31 |  | 1/25 - KIT CLEAR |  |  | 1 |  |  | 123245 NEW | 60 | 2/1 5D | NL | X | *SPECIAL DEPANEL REQUIREMENTS PER ECO #1 "BZ1" AFTER WASH UNIQUE SER # PER ECO#5 |  |  | 1/26 - BOT 9:00 1/29 - TOP 1/29 - AOI 10:00 | 59 | 182 | 1B 1T | 43 | 2580 | FEDEX P | Nextern Inc. |  |  | DOC REL 1/19 | 1/25 | 6368.2 | BOT 1ST | 2024-02-01 | 2 | 2024-01-26 | 8
2024-01-31 |  | 1/16 - KIT CLEAR |  |  | 1 |  |  | 122768 NEW | 225 | 2/6 15D | NL | X | CofC REQS BOARD S/N DEPANEL |  |  | 1/17 - BOT 6:00 1/18 - TOP 9:30 1/22 - AOI 1:30 | 71 | 215 | 2B 2T | 2 | 450 | UPS GRD | Churchill Navigation dba Shotover Systems, Inc. |  | 1/17 - AWT STENCIL FROM 7 - 10 AM 1/19 - LINEMAN DAY OFF | DOC REL 1/15 | 1/16 | 8987.75 | BOT 1ST | 2024-02-06 | 2 | 2024-01-17 | 15.5
2024-01-31 |  | 1/9 - WILL CLEAR DATE 1/22 - KIT CLEAR |  |  | 1 |  |  | 123091 NEW | 150 | 2/5 10D | NL | X | DEPANEL NOTE: "J7 & J8"RWK INSTRUSTIONS PER : “RWK_ECN_20200505_Owl-010-150_revE-01-RW01”. |  |  | 1/24 - BOT 11:00 1/25 - TOP 8:00 1/25 - AOI 2:30 | 48 | 226 | 1B 1T | 4 | 600 | FEDEX P | Owl Cyber Defense Solutions, LLC |  |  | DOC REL 1/15 | 1/17 | 7382.5 | BOT 1ST | 2024-02-05 | 2 | 2024-01-24 | 11.5
2024-01-31 |  | 1/17 OR 1/18 - PCB & shortage DUE 1/24 - KIT CLEAR |  |  | 1 |  |  | 122935 NEW | 5 | 1/31 5D | NL | X | NO ALTA STAMPS ALLOWED NOTE ECO#3 FOR INDUCTOR SOLDERING PRESS FIT MECH ASSY W/ TORQUE SPEC AND LOCTITE |  |  | 1/26 - BOT 6:00 1/26 - TOP 1/26 - AOI | 94 | 808 | 1B 1T | 10 | 50 | FEDEX P | John Hopkins University Applied Physics Lab |  |  | DOC REL 1/9 | 1/18 | 5061 | no stamps loctite 242 bot 1st | 2024-01-31 | 2 | 2024-01-25
2024-01-31 |  | 1/24 - KIT CLEAR |  |  |  |  | 2 | 121857-2ND RONC 1st Article | 98 | 1/31 5D | NL | RONC | "U15" DO NOT WASH DEPANEL |  |  | 1/26 - TOP 8:00 1/29 - BOT 1/29 - AOI 11:00 | 44 | 91 | 1B 1T | 7 | 686 | FEDEX P | Industrialex Manufacturing |  |  | DOC REL 1/24 | 1/24 | 3539.76 | TOP 1ST | 2024-01-31 | 2 | 2024-01-26 | 10
2024-01-30 |  | 1/16 - SHORT PARTIALS OF #18 (F1) & #50 (R35, R36...) SKIP IF NEEDED 1/23 - KIT CLEAR |  |  |  |  | 1 | 123012 NEW | 56 | 2/6 10D | NL | X | XRAY & SAVE |  |  | 1/24 - TOP 6:00 1/25 - AOI 6:30 | 57 | 208 | 1T | 10 | 560 | FEDEX 2 DAY | Straight Engineering LLC. |  |  | DOC REL 1/15 | 1/16 | 4026.16 | TOP ONLY | 2024-02-06 | 1 | 2024-01-24 | 8.5
2024-01-30 |  | 1/19 - AWT PART CONF #15 & #16 1/22 - KIT CLEAR |  |  | 1 |  |  | 123123 NEW | 75 | 2/5 10D | NL | X | DEPANEL |  |  | 1/22 - TOP 12:30 1/23 - AOI 12:30 | 34 | 257 | 1T | 13 | 975 | FEDEX P | RX Monitoring Service, Inc. |  | 1/23 - LINEMAN DAY OFF | DOC REL 1/17 | 1/19 | 5198.5 | BOT 1ST? OR TOP ONLY | 2024-02-05 | 2 | 2024-01-22 | 8
2024-01-29 |  | 1/17 OR 1/18 - PCB & shortage DUE 1/18 - KIT CLEAR |  |  |  |  | 2 | 122936 NEW | 5 | 1/29 5D | NL | X | BTD #48 (S1-Q2,S1-Q6...) NO ALTA STAMPS ALLOWED handle w/ care: #33 p/n LTC2992IMS#PBF #34 p/n LTC4231IUD-2#TRPBF NOTE ECO#3 FOR INDUCTOR SOLDERING PRESS FIT MECH ASSY W/ TORQUE SPEC AND LOCTITE |  |  | 1/23 - BOT 8:00 1/23 - TOP 10:00 1/23 - AOI 12:00 | 52 | 753 | 1B 1T | 10 | 50 | FEDEX P | John Hopkins University Applied Physics La |  |  | DOC REL 1/9 | 1/16 | 1813.5 | no stamps loctite 242 bot 1st | 2024-01-25 | 2 | 2024-01-18
2024-01-29 |  | 1/19 - #18 (D2) DUE 1/22 - PCB DUE 1/22 - KIT CLEAR |  |  | 1 |  |  | 123023 NEW | 55 | 2/5 10D | NL | X | CLASS 3 Mark with P/N Dash Number, Revision Letter, and Serial Number - per ECO #5 DEPANEL W/ CARE |  |  | 1/23 - TOP 11:30 1/24 - BOT 7:30 1/24 - AOI 11:00 | 63 | 247 | 1B 1T | 11 | 605 | FEDEX P | Coda Octopus Colmek, Inc. |  |  | DOC REL 1/17 | 1/18 | 7346.4 | TOP 1ST | 2024-02-05 | 2 | 2024-01-23 | 7.5
2024-01-26 |  | 1/16 - PCB DUE 1/17 - PCB DUE 1/18 - KIT CLEAR |  |  |  |  | 1 | 123058 NEW | 25 | 1/26 1/25 5D | NL | X | DEPANEL "SW1-4" AFTER WASH |  |  | 1/19 - BOT 11:00 1/19 - TOP 1:00 1/23 - HOLD 1/25 - TOP 9:30 1/25 - AOI 12:30 | 65 | 506 | 1B 1T | 11 | 275 | FEDEX P | Nordson Corporation |  | 1/22 - LINEMAN DAY OFF 1/23 - #17 WRONG PART; awt correct part due 1/24 | DOC REL 1/9 | 1/11 | 5295 | bot 1st | 2024-01-25 | 2 | 2024-01-24 | 13
2024-01-26 |  | 1/23 - PCB DUE 1/17 - KIT CLEAR |  |  |  |  | 1 | 122868 NEW | 5 | 1/26 1/31 10D | NL | X | LEAD PROCESS DEPANEL |  |  | 1/18 - TOP 11:00 1/18 - AOI 3:30 | 54 | 263 | 1T | 83 | 415 | FEDEX GRD | Capacitech Energy, Inc. |  | 1/24 - #7 part w/ epoxy doesn't install properly on pcb | DOC REL 1/10 | 1/15 | 3423.6 | TOP ONLY | 2024-01-31 | 1 | 2024-01-19 | 4.5
2024-01-25 |  | 12/18 - SHORT 3 PCBS + PARTS 12/21 - 12/22 - WILL CLEAR DATE 12/22 - SMT CLEAR 1/24 - U21 DUE 1/24 - KIT CLEAR |  |  | 1 |  |  | 122526-2 BAL NEW | 30 | 1/29 3D | NL | X | *** 3 DAY TURN *** DEPANEL |  |  | 12/22 - BOT 10:00 12/22 - TOP 12:30 12/26 - AOI 8:00 | 75 | 222 | 1B 2T | 10 | 300 | UPS RED | Flir |  | 12/19 - POSSIBLY SHIP 20 ON 12/22 | DOC REL 12/15 | 12/18 | 5840 | BOT 1ST; MAY NEED TO DEPANEL BEFORE RUNNING TOP SIDE | 2023-12-29 | 2 | 2023-12-22
2024-01-24 |  | 1/11 - PCB DUE 1/4 - SHORT 6PCS K1 (SKIPPABLE) 1/10 - KIT CLEAR |  |  |  | 1 |  | 122397 NEW | 2 | 1/24 10D | NL | X | NO PARTIAL SHPMENT DNI J3 & RETURN TO CUSTOMER |  |  | 1/11 - BOT 10:00 1/11 - TOP 1/11 - AOI 1:00 | 57 | 497 | 1B 1T | 27 | 54 | FEDEX GRD | Naval Surface Warfare Center |  |  | DOC REL 1/3 | 1/4 | 3308 | BOT 1ST | 2024-01-24 | 2 | 2024-01-11 | 3
2024-01-23 |  | 12/22 - MAY CLEAR DATES 12/22 - KIT CLEAR |  |  | 1 |  |  | 121008-2ND PAR ROWC 1st Article | 20 | 1/23 20D | NL/NN | ROWC | SCHEDULED split shipment: o 20 boards 20 days after 2nd article clears o 18 boards 30 days after the initial 20 are shipped DEPANEL VERIFY "U24" PRE-BAKE? - SEE ECO #2 *SMT - VERIFY SW1_FT IS MASKED OFF PER ECO #3 - Mask no longer needed |  |  | 12/26 - BOT 11:30 12/27 - TOP 8:00 12/27 - AOI 2:00 | 127 | 800 | 1B 2T | 4 | 80 | UPS RED | Farsounder Inc |  |  | DOC REL 12/20 | 12/20 | 20764.28 | LINE 1 BOT 1ST BAKE #67(U24) FOR 48 HOURS? | 2024-01-23 | 2 | 2023-12-26 | 10.5
2024-01-23 |  | 1/10 - PCB + 2 OTHER PARTS DUE 1/9 - KIT CLEAR |  |  |  |  | 1 | 122850 NEW | 40 | 1/23 10D | NL | X | DNI #65 (LL1, LR1..) BTD ANY PARTS SHORT ATTRITION TRY TO SHIP AS MANY COMPLETE BOARDS AS POSSIBLE DEPANEL |  |  | 1/12 - BOT 6:00 1/12 - TOP 2:00 1/16 - AOI 2:30 | 86 | 297 | 1B 2T | 4 | 160 | UPS GRD | VersaWare Technologies |  | 1/12 - U18 PART SMALL (OR PAD TOO BIG); CUST REPLY PLACE AS IS 1/13 - L3 DAY OFF | DOC REL 1/4 | 1/8 | 4110 | BOT 1ST SMALL PARTS (SIZE 201) DOUBLE CHECK PART #62 | 2024-01-23 | 2 | 2024-01-10 | 16
2024-01-22 |  | 1/8 - SHORT PCB (UNKNOWN DUE DATE) 1/12 - PCB DUE 1/15 - KIT CLEAR |  |  | 1 |  |  | 121071 NEW | 5 | 1/22 5D | NL | X | CLASS 3 |  |  | 1/5 - BOT 10:00 1/5 - TOP 12:00 1/5 - AOI 2:30 | 11 | 482 | 1B 1T | 23 | 115 | FEDEX P | Wildwood Electronics |  |  | DOC REL 12/26 | 1/8 | 4351.5 | BOT 1ST | 2024-01-22 | 2 | 2024-01-15 | 4.5
2024-01-22 |  | 11/29 - KIT CLEAR 11/30 - AWT CUST REPLY ABOUT FULL RWK (REMOVE & REPLACE BENT PINS) | [5 empty] | 122309-RWK RWK | 91 | ??? 5D |  | X | REMOVE 8-PORT ETH CONN AND REPLACE W/ 4-PORT ETH CONN (RJ1) SHIP EACH BOARD W/ CUSTOMER'S ESD BAG |  |  | BACK |  |  |  | 1 | 91 | UPS GND | GRAPH-TECH USA |  |  |  | 11/29 | 4982
2024-01-22 |  | 12/29 - KIT CLEAR |  |  |  | 1 |  | 122828 NEW | 700 | 1/22 15D | NL | x | process changed to No-Clean using No-Clean flux DEPANEL "U1" PLACE KAPTON TAPE PER ECO #2 |  |  | 1/4 - BOT 8:00 1/4 - TOP 12:00 1/5 - AOI 12:00 | 6 | 14 | 1B 1T | 0 | 0 | UPS BLUE | Reprieve Cardiovascular, Inc. |  | 1/2 - AWT FIXTURE (DUE WEDS 1/3) | DOC REL 12/28 | 12/29 | 6290 | TOP SIDE 1ST PLACE TAPE OVER U1 | 2024-01-29 | 2 | 2024-01-04 | 10
2024-01-19 |  | 1/8 - PCB DUE; NO ETA ON BGA 1/9 - KIT CLEAR |  |  |  | HOLD | HOLD | 122618-1ST BAL NEW | 1 | 1/12 1/16 5D | NL | X | DNI #62, 64, 67 & 68 SPECIAL LABEL REQ SHIP RIGID BACKER IN ESD BAG DEPANEL & SAND |  |  | 1/10 - BOT 10:00 1/10 - TOP 11:30 1/11 - ON HOLD 10:00 | 60 | 321 | 1B 1T | 90 | 90 | FEDEX P | Cardinal Peak, LLC |  | 1/11 - ISSUE LOCATING PIN 1 FOR X1_1 & X1_2 1/11 - BGA WARPING WHEN GOES THROUGH REFLOW | DOC REL 1/5 | 1/5 | 6100 | measure label rigid backer in ESD BAG BOT 1ST | 2024-01-12 | 2
2024-01-19 |  | 11/3 - AWT 1 PART CONF 11/8 - KIT CLEAR |  |  |  | 1 |  | 116970-1st 3PAR NEW | 60 | 1/19 1/15 10D | NL | X | p/n 30122-101 Bake Boards before ship DOUBLE CHECK S/N LABELS SPLIT SHIPMENT (MONTHLY): BAL REMAINING 360 DNI #36 (U3) & ship w/ PCBAs LEAD PROCESS XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! DEPANEL |  |  | 11/10 - BOT 1:30 11/11 - TOP 11/13 - AOI 10:00 | 29 | 54 | 1B 1T | 11 | 660 | FEDEX P | Anderson Connectivity |  |  | DOC REL 11/1 | 11/3 | 4949 | BOT 1ST; R; 1 SMT PART ON TOP | 2023-11-17 | 2 | 2023-11-11 | 11
2024-01-18 |  | 11/29 - KIT CLEAR |  |  |  | 1 |  | 116964-2ND 3BAL ROWC 1st Article | 60 | 1/18 1/15 10D | NL | ROWC | p/n 30117-103 Bake Boards before ship inspection: verify nuts and LED shrouds placed DOUBLE CHECK S/N LABELS SPLIT SHIPMENT (MONTHLY): BAL REMAINING 380 FOR IC17 USE P/N IS21TF32G-JCLI. Use SN 00378 and 00379 SHIPPED LAST BATCH SPLIT SHIPMENT (MONTHLY): BAL REMAINING 380 LEAD PROCESS DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 12/1 - BOT 9:30 12/4 - TOP 9:00 12/4 - STOP 2:00 12/7 - TOP 8:00 12/7 - AOI 2:00 | 67 | 264 | 2B 2T | 5 | 300 | FEDEX P | Anderson Connectivity |  | 11/29 - QTY 58 1ST SHIPMENT 12/4 - STOP AT 60 BOARDS COMPLETE TOP & BOTTOM TO RUN B121348 12/4 - 60 boards complete & stop to run B121348 | DOC REL 11/29 | 11/29 | 12372.88 | BOT 1ST BOT NEEDS TO BE DONE EOD MON | 2023-12-15 | 2 | 2023-12-05 | 17
2024-01-18 |  | 12/1 - WILL CLEAR DATE 12/1- KIT CLEAR |  |  |  |  | 1 | 116966-2ND 3BAL ROWC 1st Article | 84 | 1/18 1/15 10D | NL | ROWC | p/n 30118-102 Bake Boards before ship DOUBLE CHECK S/N LABELS SPLIT SHIPMENT (MONTHLY): BAL REMAINING 380 Skip IC2 for all boards we are short the part. SPLIT SHIPMENT (MONTHLY): BAL REMAINING 380 2 LABEL TYPES & LOCS TEXT LABEL & QR CODE ENSURE S/N MATCH LABELS SPECIFIED LOCATIONS LEAD PROCESS DEPANEL XRAY & SVE |  |  | 12/4 - BOT 6:00 12/4 - TOP 9:00 12/4 - AOI 2:00 | 34 | 154 | 2B 2T | 1 | 84 | FEDEX P | Anderson Connectivity |  | 11/30 - SHIP DATE 12/7 (ANNE) | DOC REL 11/28 | 11/30 | 7912.2 | BOT 1ST; START LOADING AS SOON AS WE HAVE 58 OF TOP COMPLETED IN SMT ETA FULL COMPLETION EOD TUES (START MON) | 2023-12-07 | 2 | 2023-12-04
2024-01-17 |  | 11/6 - PCB DUE & AWT PART CONF 11/9 - KIT CLEAR |  |  |  | 2 |  | 116954-1st 3PAR NEW | 60 | 1/17 1/15 10D | NL | X | p/n 30107-106 Bake Boards before ship DOUBLE CHECK S/N LABELS SPLIT SHIPMENT (MONTHLY): BAL REMAINING 360 EAD PROCESS DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 11/14 - TOP 9:00 11/15 - AOI 10:00 | 24 | 87 | 1T | 1 | 60 | FEDEX P | Anderson Connectivity |  |  | DOC REL 11/1 | 2023-11-03 | 4738.4 | TOP SIDE ONLY; R; received printed email copies of customer req part to use | 2023-11-17 | 1 | 2023-11-15 | 8
2024-01-17 |  | 11/29 - KIT CLEAR |  |  |  |  | 1 | 116955-2ND 3BAL RONC 1st Article | 60 | 1/17 1/15 10D | NL | RONC | p/n 30109-101 Bake Boards before ship DOUBLE CHECK S/N LABELS SPLIT SHIPMENT (MONTHLY): BAL REMAINING 380 LEAD PROCESS DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 11/30 - TOP 10:30 11/30 - AOI 12:00 | 7 | 8 | 1T | 12 | 720 | FEDEX P | Anderson Connectivity |  | 11/29 - 7D TURN FOR ALL ANDERSON JOBS FROM THIS DAY FORWARD (ANNE) 11/29 - QTY 58 1ST SHIPMENT | DOC REL 11/29 | 2023-11-29 | 4726 | TOP SIDE ONLY; | 2023-12-07 | 1 | 2023-11-30
2024-01-17 |  | 12/29 - PCB & SHORTAGES W/ UNKNOWN DUE DATE 1/8 - PCB DUE 1/10 - KIT CLEAR |  |  | 1 |  |  | 122912 NEW | 10 | 1/17 5D | NL | X | DEPANEL ECO INSTAQLL NOTE FOR "J17,J18,J20" SHIP EARLY IF POSSIBLE EPOXY REQ |  |  | 1/11 - BOT 8:00 1/11 - TOP 12:00 1/12 - AOI 9:00 | 114 | 255 | 1B 2T | 57 | 570 | UPS RED | HII Unmanned Systems, Inc. |  | 1/12 - D2 PAD TOO SMALL (OR PART TOO BIG | DOC REL 12/28 | 12/29 | 6108 | BOT 1ST | 2024-01-17 | 2 | 2024-01-11 | 9
2024-01-16 |  | 1/8 - PCB DUE; NO ETA ON BGA 1/9 - KIT CLEAR |  |  |  | HOLD | HOLD | 122618-1ST PAR NEW | 1 | 1/12 1/16 5D | NL | X | DNI #62, 64, 67 & 68 SPECIAL LABEL REQ SHIP RIGID BACKER IN ESD BAG DEPANEL & SAND |  |  | 1/10 - BOT 10:00 1/10 - TOP 11:30 1/11 - ON HOLD 10:00 | 60 | 321 | 1B 1T | 90 | 90 | FEDEX P | Cardinal Peak, LLC |  | 1/11 - ISSUE LOCATING PIN 1 FOR X1_1 & X1_2 1/11 - BGA WARPING WHEN GOES THROUGH REFLOW | DOC REL 1/5 | 1/5 | 6100 | measure label rigid backer in ESD BAG BOT 1ST | 2024-01-26 | 2 | 2024-01-10
2024-01-16 |  | 1/11 - PCB DUE 1/9 - KIT CLEAR |  |  |  | 1 |  | 122873 NEW | 200 | 1/16 5D | NL | X | LEAD PROCESS / NO CLEAN |  |  | 1/10 - TOP 1:00 1/11 - AOI 11:00 | 4 | 4 | 1T | 0 | 0 | FEDEX P | RX Monitoring Service, Inc. |  |  | DOC REL 1/4 | 1/8 | 3200 | TOP SIDE ONLY DOUBLE CHECK PCB BEFORE RUN | 2024-01-16 | 1 | 2024-01-11 | 4
2024-01-16 |  | 11/27 - KIT CLEAR |  |  |  | 1 |  | 116957-2ND 3BAL RONC 1st Article | 60 | 1/16 1/15 10D | NL | RONC | p/n 30115-103 Bake Boards before ship DOUBLE CHECK S/N LABELS SPLIT SHIPMENT (MONTHLY): BALANCE REMAINING 380 LEAD PROCESS DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 11/29 - BOT 8:00 11/29 - AOI 10:00 | 1 | 1 | 1B | 12 | 720 | FEDEX P | Anderson Connectivity |  | 12/1 OR 12/4 - SHIP DATE FOR 58 BOARDS (ANNE) | DOC REL 11/27 | 2023-11-27 | 5060.64 | BOT 1ST; NOT RELEASED YET | 2023-12-01 | 1 | 2023-11-29 | 2
2024-01-16 |  | 11/20 - KIT CLEAR |  |  |  | 1 |  | 116950-2nd 3BAL RONC 1st Article | 60 | 1/16 1/15 10D | NL | RONC | p/n 30106-101 Bake Boards before ship DOUBLE CHECK S/N LABELS SPLIT SHIPMENT (MONTHLY): BALANCE REMAINING 380 LEAD PROCESS DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 11/29 - BOT 10:00 11/29 - TOP 12:00 11/29 - AOI 2:00 | 6 | 16 | 1B 1T | 5 | 300 | FEDEX P | Anderson Connectivity |  |  | DOC REL 11/17 | 11/20 | 4213.36 | BOT 1ST; R; MOSTLY BIG PARTS; PREV L3 MONTHLY: - 12/6 – QTY 58 - 1/8 – QTY 58 - 2/6 – QTY 58 - 3/6 – QTY 4 | 2023-12-06 | 2 | 2023-11-29 | 4
2024-01-15 |  | 1/12 - KIT CLEAR | [5 empty] | 120178-1 PAR NEW | 1 | 1/26 10D | X |  | RUN ONLY 1 BOARD, TAKE PHOTOS AND SEND TO CUSTOMER TO WAIT REPLY 30-min max |  |  | BACK | 0 | 0 |  | 9 | 9 | UPS GRD | Photonis Scientific, Inc. |  |  | DOC REL 1/3 |  | 2187.5 | tht only job; build only 1 board and send customer a picture of the board. wait 30 minutes for customer reply before continuing
2024-01-15 |  | 11/14 - KIT CLEAR |  |  |  |  | 1 | 116967-1ST 3PAR NEW | 60 | 1/19 1/15 10D | NL | X | p/n 30119-101 Bake Boards before ship DO NOT SHIP: WILL NEED TO R&R J1 & J2 DOUBLE CHECK S/N LABELS SPLIT SHIPMENT (MONTHLY): BAL REMAINING 360 LEAD PROCESS DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 11/15 - TOP 8:00 11/15 - AOI 1:00 | 37 | 89 | 1T | 2 | 120 | FEDEX P | Anderson Connectivity |  |  | DOC REL 11/1 | 2023-11-14 | 4668.2 | TOP SIDE ONLY; R | 2023-11-17 | 1 | 2023-11-15 | 5
2024-01-15 |  | 11/3 - PCB DUE TODAY & AWT PART CONF #15 (L1, L2) 11/6 - SHORT ATTRITION & short L1 11/9 - KIT CLEAR |  |  |  | 1 |  | 116956-1st 3PAR NEW | 60 | 1/19 1/15 10D | NL | X | p/n 30110-104 Bake Boards before ship DOUBLE CHECK S/N LABELS REMOVE ALL FB8 SPLIT SHIPMENT (MONTHLY): BAL REMAINING 360 CUST: L1, L2 USE p/n 1264EY-330M=P3 LEAD PROCESS DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 11/13 - BOT 1:30 11/14 - HOLD 9:00 11/15 - BOT 10:00 11/16 - TOP 2:00 11/17 - AOI 7:00 | 28 | 122 | 1B 1T | 3 | 180 | FEDEX P | Anderson Connectivity |  | 11/14 - PCB STAMP ISSUE; JOB ON HOLD | DOC REL 11/1 | 2023-11-03 | 6165.8 | BOT 1ST; R | 2023-11-17 | 2 | 2023-11-13 | 15
2024-01-15 |  | 1/4 - #123 (R271...) DUE 1/3 - KIT CLEAR |  |  |  | 1 | 1 | 122846 NEW | 25 | 1/17 10D | NL | x | LEAD PROCESS DEPANEL VERIFY PADS ON "X8" ARE MASKED OFF PER ECO #3 "SW1 & RELATED" AFTER WASH "TB3-TB7" PER ECO #5 "TB8, TB10,TB36" INSTALL PER SILKSCREEN, NOT PIN 1 PER ECO #6 |  |  | 1/5 - BOT 8:00 1/5 - TOP 1:00 1/9 - AOI 1:00 | 127 | 1137 | 1B 2T | 34 | 850 | FEDEX P | Nordson Corporation |  |  | DOC REL 12/29 | 1/2 | 6896.75 | BOT 1ST | 2024-01-17 | 2 | 2024-01-05 | 19
2024-01-15 |  | 1/9 - KIT CLEAR |  |  | 1 |  |  | 122761 RONC 119442 | 20 | 1/16 3D | NL | RONC | *** 3 DAY TURN *** xtra time given to depanel before build DEPANEL XRAY & SAVE |  |  | 1/11 - TOP 6:00 1/11 - AOI 8:00 | 1 | 1 | 1T | 1 | 20 | FEDEX P | Anderson Connectivity |  |  | DOC REL 1/3 | 1/9 | 4020 | TOP SIDE ONLY | 2024-01-16 | 1 | 2024-01-11 | 2
2024-01-12 |  | 12/18 - SHORT PCB 12/29 - PCB DUE 1/9 - PCB DUE 1/8 - KIT CLEAR |  |  |  |  | 1 | 121938 NEW | 3 | 1/15 5D | NL | X | CARE REQUIRED: U1 P/N AD9276BSVZ DEPANEL XRAY & SAVE "SW1 & T1" AFTER WASH HEATSINKS REQ |  |  | 1/8 - BOT 12:00 1/9 - TOP 2:00 1/9 - AOI 8:00 | 92 | 704 | 1B 2T | 7 | 21 | FEDEX P | NOV Tuboscope Inc. |  |  | DOC REL 12/15 | 12/18 | 5765.25 | BOT 1ST | 2024-01-15 | 2 | 2024-01-09 | 4.5
2024-01-12 |  | 1/8 - PCB DUE; unknown shortages due date 1/9 - PCB DUE 1/9 - KIT CLEAR |  |  | 1 | 1 |  | 122762 ROWC 119437 | 20 | 1/12 3D | NL | ROWC | *** 3 DAY TURN *** BAT1 PASTE IN CENTER PAD XRAY & SAVE IMAGES DEPANEL |  |  | 1/9 - BOT 11:00 1/9 - TOP 1:30 1/10 - AOI 2:00 | 111 | 320 | 1B 2T | 0 | 0 | FEDEX P | Anderson Connectivity |  | 1/10 - A LOT OF HAND LOADING IN SMT AND WE GAVE OUR HAND LOADER THE DAY OFF TODAY | DOC REL 1/3 | 1/3 | 6720 | BOT 1ST some small parts (size 201) | 2024-01-12 | 2 | 2024-01-09 | 9
2024-01-12 |  | 1/8 - PCB DUE 1/3 - KIT CLEAR |  |  | 1 |  |  | 122606 RONC 118879 | 15 | 1/17 10D | NL | RONC | CLASS 3 DEPANEL |  |  | 1/5 - BOT 11:00 1/8 - TOP 8:00 1/8 - AOI 12:00 | 73 | 678 | 1B 1T | 7 | 105 | FEDEX INT PRIORITY | Puzzle Medical Devices, Inc. |  |  | DOC REL 12/21 | 12/29 | 2647.5 | BOT 1ST | 2024-01-17 | 2 | 2024-01-08 | 9
2024-01-12 |  | 12/29 - KIT CLEAR |  |  |  |  | 1 | 121563 NEW | 24 | 1/22 15D | NL | X | DO NOT RETURN MATL TO CUST CLASS 3 "REVIEW" PDF “readme_DBRG-MAIN1 (DEFAULT)” BEFORE RELEASING DEPANEL 48 HR PCB PREBAKE BUILD KIT MUST BE KEPT INTACT PER ECO |  |  | 1/8 - BOT 8:00 1/8 - TOP 1/8 - AOI 11:30 | 51 | 234 | 1B 1T | 0 | 0 | FEDEX P | University Of Oklahoma |  |  | DOC REL 11/9 | 12/29 | 2846.8 | CARE REQUIRED FOR PARTS (ECO) BOT 1ST | 2024-01-29 | 2 | 2024-01-05 | 3.5
2024-01-12 |  | 12/21 - KIT CLEAR |  |  | 1 |  |  | 121564 NEW | 24 | 1/12 1/15 15D | NL | X | do not ship earlier than 1/12 DO NOT RETURN MATL TO CUST CLASS 3 "REVIEW" PDF “readme_DBRG-LO1 (DEFAULT)” BEFORE RELEASING *READ ECO #4 FOR PART MOISTURE DEPANEL 48 HR PCB PREBAKE BUILD KIT MUST BE KEPT INTACT PER ECO |  |  | 12/28 - TOP 9:00 12/28 - BOT 12:00 12/28 - PAUSE 2:30 1/3 - AOI | 29 | 56 | 1B 1T | 0 | 0 | FEDEX P | University Of Oklahoma |  | 12/28 - TOP SIDE 1ST 12/28 - LINEMAN TIME OFF | DOC REL 11/9 | 2023-12-21 | 2144 | CARE REQUIRED FOR PARTS (ECO) BOT 1ST | 2024-01-15 | 2 | 2024-01-03
2024-01-12 |  | 12/21 - KIT CLEAR |  |  | 2 |  |  | 121567 NEW | 12 | 1/12 1/15 15D | NL | X | do not ship earlier than 1/12 DO NOT RETURN MATL TO CUST CLASS 3 "REVIEW" PDF “readme_SUPER-QSFP1 (ALTPWR)” BEFORE RELEASING DEPANEL 48 HR PCB PREBAKE BUILD KIT MUST BE KEPT INTACT PER ECO PRESS FIT |  |  | 1/3 - BOT 1/3 - TOP 1/3 AOI 11:00 | 33 | 124 | 1B 1T | 4 | 48 | FEDEX P | University Of Oklahoma |  |  | DOC REL 11/9 | 12/21 | 2768 | LED ORIENTATION (README) BOT SIDE 1ST | 2024-01-15 | 2 | 2024-01-03
2024-01-11 |  | 1/15 - PCB DUE 1/5 - KIT CLEAR | [5 empty] | 122586 NEW | 20 | 1/19 10D | X |  | THT ONLY DEPANEL |  |  | BACK | 0 | 0 |  | 39 | 780 | UPS RED | Samtec |  |  | DOC REL 1/3 | 1/3 | 2340 | top only |  | 1
2024-01-11 |  | 1/4 - AWT PART CONF #9 (U7) 1/4 - KIT CLEAR |  |  | 1 |  |  | 120603 RONC 109250 | 40 | 1/18 10D | NL | RONC | DEPANEL |  |  | 1/9 - BOT 7:00 1/9 - TOP 1/9 - AOI 11:00 | 23 | 84 | 1B 1T | 0 | 0 | FEDEX 2DAY | Lightning Silicon Technology, Inc. |  |  | DOC REL 12/8 | 1/4 | 1377.6 | BOT 1ST | 2024-01-18 | 2 | 2024-01-09
2024-01-11 |  | 1/15 - PCB due & no ETA on C8 1/5 - KIT CLEAR |  |  | 1 |  |  | 122927 RONC 122169 | 10 | 1/12 5D | NL | RONC | ***CHECK INCOMING FABS FOR VIA HOLES (SHOULD BE TENTED) DEPANEL "IC10" IS MOISTURE SENSITIVE |  |  | 1/8 - BOT 11:30 1/8 - TOP 1:00 1/9 - AOI 7:00 | 97 | 339 | 1B 1T | 6 | 60 | FEDEX P | Ocean Aero, Inc. |  |  | DOC REL 12/29 | 12/29 | 3629.5 | BOT 1ST | 2024-01-12 | 2 | 2024-01-08 | 4
2024-01-10 |  | 1/2 - KIT CLEAR |  |  | 1 |  |  | 122836 NEW | 100 | 1/10 1/11 1/9 5D | NL | x | BTD J1 DEPANEL |  |  | 1/3 - BOT 11:00 1/4 - TOP 10:30 1/5 - AOI 10:00 | 128 | 306 | 2B 2T | 0 | 0 | FEDEX P | Butterfly Network, Inc. |  |  | DOC REL 12/29 | 1/2 | 7161 | BOT 1ST | 2024-01-11 | 2 | 2024-01-04 | 15
2024-01-10 |  | 1/3 - PCB DUE 1/3 - KIT CLEAR |  |  |  |  | 1 | 122608 ROWC 121155 | 40 | 1/10 5D | NL | ROWC | u12 ok to use DEPANEL & SAND "SW6 & T1" AFTER WASH |  |  | 1/4 - BOT 10:00 1/5 - TOP 7:00 1/5 - AOI 12:00 | 86 | 277 | 1B 1T | 8 | 320 | FEDEX P | Powercast Corporation |  |  | DOC REL 12/20 | 12/20 | 3200 | PRINT PART REQ? SMALL PARTS (SIZE 201) BOT 1ST | 2024-01-10 | 2 | 2024-01-04 | 10
2024-01-09 |  | 12/21 - KIT CLEAR |  |  | 1 |  |  | 121566 NEW | 32 | 1/9 1/15 15D | NL | X | do not ship earlier than ship date DO NOT RETURN MATL TO CUST CLASS 3 "REVIEW" PDF “readme_OCTO-TERM1”(DEFAULT) BEFORE RELEASING DEPANEL 48 HR PCB PREBAKE BUILD KIT MUST BE KEPT INTACT PER ECO |  |  | 12/26 - TOP 7:30 12/26 - AOI 11:00 | 2 | 96 | 1T | 0 | 0 | FEDEX P | University Of Oklahoma |  |  | DOC REL 11/9 | 12/21 | 1648 | TOP SIDE ONLY care required for parts (eco) | 2024-01-15 | 1 | 2023-12-22 | 3.5
2024-01-08 |  | 12/20 - SHORT 3 ITMS + ATTRITION 12/28 - U5 & D15 SHORT (CAN SKIP) 1/4 - KIT CLEAR |  |  |  |  | 1 | 122472 NEW | 15 | 1/18 10D | NL | X | SMT SKIPPED U5 & D15 DEPANEL "U3" AFTER WASH |  |  | 1/2 - BOT 9:00 1/2 - TOP 11:00 1/2 - AOI 2:00 | 71 | 295 | 1B 1T | 42 | 630 | FEDEX P | Industrialex Manufacturing |  |  | DOC REL 12/18 | 12/20 | 3713 | BOT 1ST; J4 OVERHANG? DEPANEL REQ? |  | 2 | 1900-01-04
2024-01-08 |  | 1/4 - KIT CLEAR |  |  | 1 |  |  | 122502 NEW | 30 | 1/11 5D | X | X | T/H ONLY CLASS 3 |  |  | 1/5 - TOP 9:00 1/5 - AOI 1:00 | 0 | 0 |  | 18 | 540 | FEDEX P | Artis LLC |  | 1/4 - NOT THT ONLY JOB | DOC REL 12/26 | 1/4 | 2485 | TOP SIDE ONLY THT ONLY | 2024-01-11 | 1 | 2024-01-08 | 4
2024-01-08 |  | 12/21 - KIT CLEAR |  |  |  | 1 | 1 | 122544 NEW | 15 | 1/8 10D | NL | X | BTD SH1 DEPANEL MECH ASSY - SHIELDS, SIGHT PIPES, SHIELD COVERS R72 and R77 should be elevated between 50mil to 200mil. |  |  | 12/28 - BOT 8:00 12/28 - BOT DONE 2:00 1/2 - TOP 6:00 1/2 - AOI 10:30 | 146 | 739 | 1B 2T | 45 | 675 | FEDEX STANDARD | Lake Shore Cryotronics, Inc. |  |  | DOC REL 12/11 | 12/21 | 8190.5 | BOT 1ST | 2024-01-08 | 2 | 2023-12-28 | 10.5
2024-01-04 |  | 12/22 - EXPCTED SMT CLEAR DATE 12/22 - SMT CLEAR 12/28 - KIT CLEAR |  |  | 1 |  |  | 122507 NEW | 6 | 1/4 1/5 5D | NL | X | DEPANEL |  |  | 12/28 - BOT 6:00 12/28 - TOP 12/28 - AOI 9:30 | 58 | 554 | 1B 1T | 10 | 60 | UPS RED | Samtec |  |  | DOC REL 12/20 | 12/21 | 4652.8 | J3 (TOP SIDE) DEPANEL REQ? BOT 1ST SMALL PARTS (SIZE 201) | 2024-01-05 | 2 | 2023-12-28 | 3.5
2024-01-04 |  | 12/18 - AWT PART CONF (X2, J6 & P1) 12/19 - KIT CLEAR |  |  |  | 1 |  | 122551 RONC 120820 | 36 | 1/4 10D | NL / NN | RONC | INSTALL U7 DEPANEL "SW1 & SW2" AFTER WASH |  |  | 12/21 - BOT 11:00 12/21 - TOP 2:00 12/26 - AOI 9:00 | 53 | 224 | 1B 1T | 18 | 648 | FEDEX GRD | LMA Technologies, LLC |  | 12/21 - solder paste issues with Alpha, switch to Indium for top side | DOC REL 12/11 | 12/18 | 3292.64 | BOT 1ST | 2024-01-04 | 2 | 2023-12-22 | 10
2024-01-04 |  | 12/18 - SHORT U3 12/21 - U3 DUE 12/21 - KIT CLEAR |  |  |  |  | 1 | 122634 RONC 120825 | 75 | 1/8 10D | NL | RONC | SHORT U3: SKIPPABLE DEPANEL |  |  | 12/21 - BOT 11:00 12/21 - BOT DONE 2:00 12/26 - AOI 10:00 | 53 | 205 | 1B 1T | 2 | 150 | FEDEX GRD | Churchill Navigation dba Shotover Systems Inc |  |  | DOC REL 12/14 | 12/18 | 4864.5 | BOT 1ST; LABEL: HA-2302-S/N (START AT 0246) | 2023-01-08 | 2 | 2023-12-22 | 7
2024-01-03 |  | 1/2 - PCB DUE 12/28 - KIT CLEAR |  |  |  |  | 2 | 122522 NEW | 250 | 1/3 3D | NL | X | *** 3 DAY TURN *** DEPANEL |  |  | 12/29 - TOP 11:00 12/29 - AOI 1:30 | 5 | 36 | 1T | 0 | 0 | FEDEX P | Royal Circuit Solutions, Inc. |  |  | DOC REL 12/18 | 12/28 | 6300 | TOP SIDE ONLY | 2023-01-03 | 1 | 2023-12-29 | 2.5
2024-01-03 |  | 12/28 - KIT CLEAR |  |  |  |  | 1 | 122562 NEW | 1 | 1/3 3D | NL | X | *** 3 DAY TURN *** REV MARKING W/WHITE MARKER BEFORE SHIPPING DEPANEL |  |  | 12/29 - BOT 9:00 12/29 - TOP 10:00 12/29 - AOI 1:00 | 38 | 394 | 1B 1T | 105 | 105 | FEDEX P | Ball Aerospace and Technologies |  | 12/28 - BORROWED WHITE MARKER FROM ROBERT | DOC REL 12/28 | 12/28 | 4371.5 | BOT 1ST | 2024-01-03 | 2 | 2023-12-29 | 2
2024-01-03 |  | 11/18 - ALMOST CLEAR; POSSIBLY BTD #14 & #23 12/1 - KIT CLEAR |  |  | 2 |  |  | 118628-2 3BAL ROWC 114946 | 1 | 12/29 20D | NL | ROWC | ***MUST LOG ALL NON-CONFORMANCES BY SERIAL NUMBER PER ECO NOTE #5*** ---SEVERAL PAST QUALITY ISSUES - PLEASE TIGHTEN UP QA 100%--- **QUALITY ALERT - LAST RUN MISSING "R124" - SEE ECO #4 |  |  | 11/20 - BOT 10:00 11/22 - TOP 10:00 11/29 - TOP 12:00 12/1 - AOI 7:30 | 30 | 155 | 2B 2T | 3 | 3 | UPS GND | ICC, Inc. |  | 11/27 - IF JOB DOES NOT CLEAR BEFORE 11/30, THEN 12/1 IS DAY 1 (ANNE) 11/27 - ON HOLD TO RUN B121959 | KIT CLEAR 9/6 | 2023-11-18 | 87897 | PREV BUILD L1; A LOT OF SOLDER ISSUES PREVIOUSLY; BOT 1ST; LF | 2023-12-29 | 2 | 2023-11-20
2024-01-03 |  | 12/16 - PCB DUE 12/18 - KIT CLEAR |  |  |  |  | 1 | 122499-2 BAL NEW | 1 | 12/26 5D | NL | X | ***DO NOT LOSE PARTS***... MINIMUM ATTRITION ON MOST PARTS - APROX 20 ITEMS (0402) HAVE ONLY 10 EXTRA PARTS DEPANEL |  |  | 12/19 - BOT 9:00 12/20 - TOP 9:00 12/21 - AOI 7:00 | 77 | 384 | 2B 1T | 0 | 0 | FEDEX P | Butterfly Network Inc. |  | 12/18 - PCBS BAKING, CANNOT RUN UNTIL 12/19 12/20 - POSSIBLY SHORT PARTS, PART COUNT NEEDED ASAP | DOC REL 12/7 | 12/14 | 8391 | BOT 1ST | 2023-12-26 | 2 | 2023-12-19
2024-01-02 |  | 12/1 - WILL CLEAR DATE 12/1- KIT CLEAR 12/1 - SHORT IC2 |  |  |  |  | 1 | 116966-2ND 2PAR ROWC 1st Article | 60 | 12/20 12/15 6D | NL | ROWC | p/n 30118-102 SPLIT SHIPMENT (MONTHLY): BAL REMAINING 464 Skip IC2 for all boards we are short the part. SPLIT SHIPMENT (MONTHLY): BAL REMAINING 444 2 LABEL TYPES & LOCS TEXT LABEL & QR CODE ENSURE S/N MATCH LABELS SPECIFIED LOCATIONS LEAD PROCESS DEPANEL XRAY & SVE |  |  | 12/4 - BOT 6:00 12/4 - TOP 9:00 12/4 - AOI 2:00 | 34 | 154 | 2B 2T | 1 | 60 | FEDEX P | Anderson Connectivity |  | 11/30 - SHIP DATE 12/7 (ANNE) | DOC REL 11/28 | 11/30 | 7912.2 | BOT 1ST; START LOADING AS SOON AS WE HAVE 58 OF TOP COMPLETED IN SMT ETA FULL COMPLETION EOD TUES (START MON) | 2023-12-07 | 2 | 2023-12-04
2024-01-02 |  | 12/19 - PARTS EXPECTED DATE THAN KIT CLEAR 12/20 - KIT CLEAR |  |  |  |  | 1 | 121565 ROWC 100619 | 100 | 1/12 15D | NL | x | CLASS 3 "REVIEW" PDF “readme_FPGA-SJTAG1”(DEFAULT) BEFORE RELEASING DEPANEL 48 HR PCB PREBAKE BUILD KIT MUST BE KEPT INTACT PER ECO |  |  | 12/21 -AOI | 2 | 2 | 1T | 0 | 0 | FEDEX P | University Of Oklahoma |  |  | DOC REL 11/9 | 12/18 | 2369 | TOP ONLY | 2023-01-12 | 1 | 2023-12-26
2024-01-02 |  | 12/21 - EXPECTED DAY 1 IS 12/22 12/22 - KIT CLEAR |  |  |  |  | 1 | 122635 NEW | 3 | 1/3 5D | NL | X | SMT UNABLE TO RUN: #29 (J1, J2..) DUE PANEL ISSUE; HAND SOLDER CARE REQUIRED: U15, U16, U21, U24, U25, U30, U20, U29, U47 AND FL3 MULTIPLE DIFFERENT BOARDS IN ONE ARRAY |  |  | 12/27 - BOT 6:00 12/27 - TOP 12/27 - AOI 9:00 | 64 | 544 | 1B 1T | 35 | 105 | FEDEX P | Technology Service Corporation |  | 12/21 - HIGHER PRIORITY (ANNE) | NO DOC. | 12/21 | 2773.8 | SMALL PARTS (SIZE 201) BOT 1ST LOOK AT PCB WHEN IT ARRIVES | 2024-01-03 | 2 | 2023-12-26 | 3
2023-12-29 |  | 12/14 - KIT CLEAR |  |  |  | 1 |  | 120841 NEW | 150 | 12/29 10D | NL | X | **NEW BOM - ADDED 3 NEW PARTS (9 LOCATIONS) @ "C87, C70,C100,C115" |  |  | 12/15 - BOT 8:00 12/18 - TOP 11:00 12/19 - AOI 2:30 | 87 | 286 | 2B 1T | 5 | 750 | FEDEX GRD | Techkon USA LLC |  | 12/19 - SHORT PARTS FOR 1 BOARD: SEARCHING STOCKROOM FOR XTRAS | DOC REL 11/6 | 2023-12-14 | 8320 | BOT 1ST | 2023-12-29 | 2 | 2023-12-15 | 19
2023-12-29 |  | 11/18 - ALMOST CLEAR; POSSIBLY BTD #14 & #23 12/1 - KIT CLEAR |  |  | 2 |  |  | 118628-2 3PAR ROWC 114946 | 1799 | 12/29 20D | NL | ROWC | ***MUST LOG ALL NON-CONFORMANCES BY SERIAL NUMBER PER ECO NOTE #5*** ---SEVERAL PAST QUALITY ISSUES - PLEASE TIGHTEN UP QA 100%--- **QUALITY ALERT - LAST RUN MISSING "R124" - SEE ECO #4 |  |  | 11/20 - BOT 10:00 11/22 - TOP 10:00 11/29 - TOP 12:00 12/1 - AOI 7:30 | 30 | 155 | 2B 2T | 3 | 5397 | UPS GND | ICC, Inc. |  | 11/27 - IF JOB DOES NOT CLEAR BEFORE 11/30, THEN 12/1 IS DAY 1 (ANNE) 11/27 - ON HOLD TO RUN B121959 | KIT CLEAR 9/6 | 2023-11-18 | 87897 | PREV BUILD L1; A LOT OF SOLDER ISSUES PREVIOUSLY; BOT 1ST; LF | 2023-12-29 | 2 | 2023-11-20
2023-12-28 |  | 12/18 - awt part conf (d15) than SMT clear 12/19 - SMT CLEAR 12/20 - KIT CLEAR |  |  | 1 |  |  | 122597 NEW | 50 | 12/28 5D | NL | X | ADD STANDOFFS (J16-J19) DEPANEL "B1 & B2" AFTER WASH "U7" CRITICAL MOISTURE SENSITIVE PART - POST BAKE ASSY'S 100C 5-10 HRS PRIOR TO SHIPPING |  |  | 12/19 - BOT 10:30 12/19 - BOT DONE 2:00 12/22 - TOP 6:00 12/22 - AOI 11:00 | 79 | 316 | 1B 2T | 9 | 450 | FEDEX P | H3D, Inc. |  | 12/19 - RUN BOT ONLY; AWT CUST REPLY ABOUT INSTALLING PEM NUTS ON TOP SIDE 12/22- SOLDER BRIDGE (U17) ON ALL BOARDS; STENCIL ADJUST MENT REQUIRED FOR NEXT BUILD | DOC REL 12/14 | 12/18 | 4930 | bot 1st; depanel required before smt run?; post bake assy req 5-10 hrs | 2023-12-28 | 2 | 2023-12-22 | 8.5
2023-12-27 |  | 12/12 - KIT CLEAR |  |  |  |  | 2 | 122454 NEW | 100 | 12/27 10D | NL | X | DEPANEL |  |  | 12/18 - TOP 8:00 12/19 - AOI | 3 | 6 | 1T | 0 | 0 | UPS GRD | Sick, Inc. |  | 12/18 - AWT REFLOW FIXTURE 12/18 - 2 FIXTURES AVAILABLE; 9 MIN REFLOW PER PANEL, 3 MIN TO FIT PANEL TO FIXTURE; 2 BOARDS PER PANEL; TOTAL REFLOW TIME = 5HRS TO RFLOW ALL 100 BOARDS | DOC REL 12/12 | 12/13 | 2030 | TOP SIDE ONLY; QUICK JOB | 2023-12-27 | 1 | 2023-12-21 | 6
2023-12-27 |  | 12/15 OR 12/18 - MAY CLEAR DATES 12/19 - KIT CLEAR |  |  | 1 |  |  | 122555 RONC 115908 | 50 | 12/27 5D | NL | RONC | J8 BTD DEPANEL "J3" AFTER WASH |  |  | 12/18 - BOT 11:30 12/19 - BOT DONE 10:30 12/20 - TOP 11:00 12/21 - AOI 12:00 | 79 | 308 | 1B 1T | 2 | 100 | FEDEX STANDARD | H3D, Inc. |  | 12/19 - AWT PARTS FOR TOP SIDE; | DOC REL 12/8 | 12/14 | 3776.5 | BOT 1ST; DOUBLE CHECK PCB | 2023-12-27 | 2 | 2023-12-18 | 11
2023-12-26 |  | 12/22 - KIT CLEAR | [5 empty] | 119432-RMA RMA | 1 | 12/29 3D |  |  | R&R THE FOLLOWING PARTS: IC1001 - P/N LAN9662-I/9MX IC1900 – P/N MT41K256M16TW-107 IT:P |  |  | BACK | [14 empty] | 2 | 2023-12-04
2023-12-26 |  | 12/16 - PCB DUE 12/18 - KIT CLEAR |  |  |  |  | 1 | 122499-1 PAR NEW | 99 | 12/26 5D | NL | X | ***DO NOT LOSE PARTS***... MINIMUM ATTRITION ON MOST PARTS - APROX 20 ITEMS (0402) HAVE ONLY 10 EXTRA PARTS DEPANEL |  |  | 12/19 - BOT 9:00 12/20 - TOP 9:00 12/21 - AOI 7:00 | 77 | 384 | 2B 1T | 0 | 0 | FEDEX P | Butterfly Network Inc. |  | 12/18 - PCBS BAKING, CANNOT RUN UNTIL 12/19 12/20 - POSSIBLY SHORT PARTS, PART COUNT NEEDED ASAP | DOC REL 12/7 | 12/14 | 8391 | BOT 1ST | 2023-12-26 | 2 | 2023-12-19
2023-12-22 |  | 12/18 - SHORT 3 PCBS + PARTS 12/19 - SHORT C27, U21 & U31 |  |  | 1 |  |  | 122526-1 PAR NEW | 20 | 12/22 3D | NL | X | RUN QTY 20 TO SHIP 12/22 SKIP C27 *** 3 DAY TURN *** DEPANEL |  |  | 12/20 - BOT 6:00 12/20 - TOP 8:00 12/20 - AOI 11:30 | 75 | 222 | 1B 2T | 10 | 200 | UPS RED | Flir |  | 12/19 - POSSIBLY SHIP 20 ON 12/22 | DOC REL 12/15 | 12/18 | 5840 | BOT 1ST; MAY NEED TO DEPANEL BEFORE RUNNING TOP SIDE | 2023-12-22 | 2 | 2023-12-20 | 5.5
2023-12-22 |  | 12/12 - SHORT 14 PCS OF U11; WILL CLEAR THIS WEEK 12/13 - KIT CLEAR |  |  |  |  | 3 | 122165 NEW | 40 | 12/22 12/28 10D | NL | X | U15 DNI Pre-bake boards at 125C for 24 hours. DEPANEL XRAY & SAVE IMAGES |  |  | 12/18 - TOP 11:00 12/19 - AOI 8:00 | 73 | 306 | 2T | 9 | 360 | UPS RED | Jefferson Labs |  | 12/21 - okay to ship a week early (Anne) | DOC REL 12/8 | 12/12 | 5738.8 | TOP ONLY | 2023-12-28 | 1 | 2023-12-20 | 5.5
2023-12-22 |  | 11/29 - KIT CLEAR |  |  | 1 |  |  | 122050 ROWC 117914 | 540 | 12/22 15D | NL | ROWC | SMT - ADD EXTRA FLUX TO "U401" (CHK W ROBERT/STENCIL) DEPANEL "U401" XRAY & SAVE |  |  | 12/1 - BOT 8:30 12/1 - STOP 1:30 12/5 - BOT 11:00 12/6 - TOP 1:00 12/6 - STOP 2:30 12/11 - TOP 6:00 12/11 - STOP 1:00 12/14 - TOP 9:00 12/18 - AOI 11:30 | 84 | 373 | 2B 2T | 0 | 0 | FEDEX GRD | Sea Land Aire |  | 11/29 - SHIP DATE 12/22 (ANNE) 12/1 - STENCIL ISSUE; OPEN SOLDER #17 (C524, C525) 12/5 - BOT COMPLETE ETA 12/11 12/6 - STOP JOB TO RUN B121990 | DOC REL 11/13 | 11/29 | 36348.4 | BOT 1ST | 2023-12-22 | 2 | 2023-12-01 | 41
2023-12-21 |  | 12/20 - PCB DUE 12/14 - KIT CLEAR |  |  |  |  | 1 | 122247 NEW | 30 | 12/21 5D | NL | X | ***NO VENDOR MARKING/STAMPS ALLOWED*** EPANEL Q13 Q18 Q20 Q22 - MASK OFF SMALLER FOOTPRINT (R110, R111, R112, R113) PER ECO #2 SMT TO CONFIRM - MAKE SURE NO SOLDER @ MULTIPLE LOCATION PER ECO #3 |  |  | 12/14 - BOT 2:00 12/15 - TOP 8:00 12/15 - AOI 2:00 | 50 | 289 | 1B 1T | 6 | 180 | FEDEX P | Engenious Design |  |  | DOC REL 12/7 | 12/12 | 3288.6 | BOT 1ST | 2023-12-21 | 2 | 2023-12-15 | 8
2023-12-20 |  | 11/29 - KIT CLEAR |  |  |  | 1 |  | 116964-2ND 2PAR ROWC 1st Article | 60 | 12/20 12/15 6D | NL | ROWC | SPLIT SHIPMENT (MONTHLY): BAL REMAINING 440 FOR IC17 USE P/N IS21TF32G-JCLI. Use SN 00378 and 00379 SHIPPED LAST BATCH SPLIT SHIPMENT (MONTHLY): BAL REMAINING 380 LEAD PROCESS DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 12/1 - BOT 9:30 12/4 - TOP 9:00 12/4 - STOP 2:00 12/7 - TOP 8:00 12/7 - AOI 2:00 | 67 | 264 | 2B 2T | 5 | 300 | FEDEX P | Anderson Connectivity |  | 11/29 - QTY 58 1ST SHIPMENT 12/4 - STOP AT 60 BOARDS COMPLETE TOP & BOTTOM TO RUN B121348 12/4 - 60 boards complete & stop to run B121348 | DOC REL 11/29 | 11/29 | 12372.88 | BOT 1ST BOT NEEDS TO BE DONE EOD MON | 2023-12-15 | 2 | 2023-12-05 | 17
2023-12-20 |  | 11/20 - KIT CLEAR |  |  |  | 1 |  | 116950-2nd 2PAR RONC 1st Article | 60 | 12/20 12/15 6D | NL | RONC | SPLIT SHIPMENT (MONTHLY): BALANCE REMAINING 440 LEAD PROCESS DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 11/29 - BOT 10:00 11/29 - TOP 12:00 11/29 - AOI 2:00 | 6 | 16 | 1B 1T | 5 | 300 | FEDEX P | Anderson Connectivity |  |  | DOC REL 11/17 | 11/20 | 4213.36 | BOT 1ST; R; MOSTLY BIG PARTS; PREV L3 MONTHLY: - 12/6 – QTY 58 - 1/8 – QTY 58 - 2/6 – QTY 58 - 3/6 – QTY 4 | 2023-12-06 | 2 | 2023-11-29 | 4
2023-12-20 |  | 11/27 - KIT CLEAR |  |  |  | 1 |  | 116957-2ND 2PAR RONC 1st Article | 60 | 12/20 12/15 6D | NL | RONC | SPLIT SHIPMENT (MONTHLY): BALANCE REMAINING 440 LEAD PROCESS DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 11/29 - BOT 8:00 11/29 - AOI 10:00 | 1 | 1 | 1B | 12 | 720 | FEDEX P | Anderson Connectivity |  | 12/1 OR 12/4 - SHIP DATE FOR 58 BOARDS (ANNE) | DOC REL 11/27 | 2023-11-27 | 5060.64 | BOT 1ST; NOT RELEASED YET | 2023-12-01 | 1 | 2023-11-29 | 2
2023-12-19 |  | 12/5 - KIT CLEAR |  |  |  | 1 |  | 122481 ROWC 119305 | 200 | 12/19 10D | NL | ROWC | label: 201BV1 - 400BV1 DEPANEL |  |  | 12/11 - BOT 1:00 12/12 - TOP 10:00 12/12 - STOP 10:00 12/14 - TOP 11:00 12/14 - AOI 2:00 | 22 | 34 | 1B 1T | 3 | 600 | FEDEX P | Open Source Instruments, Inc. |  | 12/12 - STOPPED TO RUN B121856 | DOC REL 12/4 | 12/5 | 2616 | BOT 1ST | 2023-12-19 | 2 | 2023-12-08 | 6
2023-12-19 |  | 11/15 - PCB DUE 11/14 - KIT CLEAR |  |  |  | 2 |  | 121161 ROWC 118335 | 30 | 12/18 12/14 20D | NL | ROWC | AWT CUSTOMER APPROVAL DEPANEL ***SHIP ON 12/20 WITH B121160 **SHIPPING: BOARDS MUST BE INDIVIDUALLY BOXED W/ CUST PROVIDED BOXES - SHIP IN ONE BOX WITH B121161 FOR INVOIVING PURPOSES |  |  | 11/17 - TOP 10:00 11/17 - AOI 1:00 | 43 | 176 | 1T | 7 | 210 | UPS GRD | EUSA Global LLC |  | ship both B121160 & B121161 ON 12/18 W/ EXCESS MATL (ANNE) | DOC REL 11/6 | 2023-11-13 | 1777.2 | TOP SIDE ONLY; LF | 2023-12-14 | 1 | 2023-11-17 | 3
2023-12-19 |  | 11/20 - PCB DUE 11/16 - KIT CLEAR |  |  | 1 |  |  | 121160 ROWC 118334 | 50 | 12/18 20D | NL | ROWC | AWT CUSTOMER APPROVAL "C24 & C29" SWAP LOCATIONS PER ECO ***SHIP ON 12/20 WITH B121161 DEPANEL **SHIPPING: BOARDS MUST BE INDIVIDUALLY BOXED W/ CUST PROVIDED BOXES - SHIP IN ONE BOX WITH B121161 FOR INVOIVING PURPOSES |  |  | 11/17 - TOP 1:00 11/20 - AOI 10:00 | 34 | 125 | 1T | 35 | 1750 | FEDEX GRD | EUSA Global, LLC |  | SOLDER QUALITY NOT GOOD, DESPITE CHANGING SOLDER TYPE. OPERATOR BELIEVES ITS THE BOARD & RECOMMENDS NITROGEN TO CLEAN IT UP ship both B121160 & B121161 ON 12/18 W/ EXCESS MATL (ANNE) | DOC REL 11/6 | 11/13 | 3575 | TOP SIDE ONLY; LF | 2023-12-18 | 1 | 2023-11-20 | 5.5
2023-12-19 |  | 12/5 - KIT CLEAR |  |  |  | 1 |  | 122235 NEW | 100 | 12/19 10D | NL | X | LABEL: 2614122300001 - 2614122300100 DEPANEL INSTALL FUSES S/N PER ECO #4 |  |  | 12/11 - BOT 8:00 12/11 - TOP 10:00 12/11 - AOI | 4 | 4 | 1T | 9 | 900 | FEDEX P | Berkshire Grey |  |  | DOC REL 11/29 | 12/5 | 1470 | TOP ONLY; DEPANEL BEFORE THT H/L?; FAST JOB | 2023-12-19 | 1 | 2023-12-08 | 2
2023-12-19 |  | 12/15 - KIT CLEAR |  |  | 1 |  |  | 121032-RWK RWK | 23 | 12/19 10D | NL |  | SOLDER GUIDE PINS (X1A, X1B, X1C, X1D, X1E, X1F, X1G & X1H) |  |  | BACK | 48 | 313 | 1T | 28 | 644 | FEDEX GRD | Machine Solutions Inc |  |  | DOC REL 10/24 | 2023-12-15 |  |  |  | 1 |  | 7.5
2023-12-19 | [7 empty] | 121807-RWK RWK | 1 | 12/19 ??? | - |  | TEST FPGA CHIPS (U75) |  |  | BACK | - | - | - | - | - | [6 empty] | 400 |  |  | 1
2023-12-18 |  | 12/8 - KIT CLEAR (REPORTED 12/11) |  |  |  |  | 1 | 121562 NEW | 10 | 12/18 5D | NL | x | CLASS 3 press fit DEPANEL 48 HR PCB PREBAKE BUILD KIT MUST BE KEPT INTACT PER ECO - DO NOT DAMAGE PART PACKAGING |  |  | 12/14 - BOT 11:00 12/14 - TOP 1:00 12/14 - AOI 2:30 | 12 | 72 | 1B 1T | 32 | 320 | FEDEX P | University Of Oklahoma |  |  | DOC REL 11/9 | 12/8 | 3310 | BOT 1ST | 2023-12-18 | 2 | 2023-12-13 | 3.5
2023-12-18 |  | 12/8 - KIT CLEAR (REPORTED 12/11) |  |  |  |  | 3 | 121561 NEW | 10 | 12/18 5D | NL | x | CLASS 3 "REVIEW" ECO AND B100618-P2A (ABRG-FULL1-2.B.1) MFR Problems POWERPOINT SLIDES BEFORE RELEASING - SEVERAL QUALITY ISSUES FROM PREVIOUS SUPPLIER DEPANEL 48 HR PCB PREBAKE press fit BUILD KIT MUST BE KEPT INTACT PER ECO - DO NOT DAMAGE PART PACKAGING |  |  | 12/13 - TOP 8:00 12/13 - AOI 10:00 | 10 | 22 | 1T | 36 | 360 | FEDEX P | University Of Oklahoma |  |  | DOC REL 11/9 | 12/8 | 2798 | top only; printed B100618-P2A to attach to folder | 2023-12-18 | 1 | 2023-12-13 | 2
2023-12-18 |  | 12/11 - KIT CLEAR |  |  |  |  | 1 | 122469 NEW | 30 | 12/18 5D | NL | x | Please Remove the connector pins from the “missing hole” location. Each connector have different missing holes. ECO #4 DEPANEL |  |  | 12/14 - BOT 8:00 12/14 - AOI 11:00 | 60 | 207 | 1T | 20 | 600 | FEDEX P | Servomex Inc |  |  | DOC REL 12/8 | 12/11 | 2988.2 | TOP ONLY; NEED TO LET TRINH KNOW OF PIN REMOVAL | 2023-12-18 | 1 | 2023-12-13 | 3
2023-12-15 |  | 11/20 - AWT PART CONF #104 11/22 - KIT CLEAR |  |  |  |  | 1 | 119023 NEW | 8 | 12/15 15D | NL | X | CLASS 3 |  |  | 12/5 - BOT 2:00 12/7 - TOP 9:00 | 233 | 1978 | 3B 3T | 32 | 256 | FEDEX P | Integrated Consultants |  |  | DOC REL 11/1 | 2023-11-20 | 15924.4 | SMALL PARTS; BOT 1ST | 2023-12-15 | 2 | 2023-12-06 | 10
2023-12-15 |  | 12/6 - PCB & THT PARTS DUE 12/6 - SMT CLEAR; SHORT 12 PCS OF ITM #39 (U14, U15...) 12/8 - KIT CLEAR |  |  | 1 |  |  | 121990 NEW | 10 | 12/15 5D | NL | X | "U14" BTD CLASS 3 *CONFIRM SOLDER PASTE MEETS "HALIDE FREE" PER DWG NOTE #2 (SEE ROBERT) MECH ASSY REQ PER ECO **CONFIRM WE RECEIVED RTV & PRIMER PER CUST SUPPLIED ASSY PDF "FA-011453AP_PCB_ASSY" ECO #3 WAIVED (FLYING PROBE) FILL OUT ASSY FORM FA-011453AP PCB Assy - ONE PER ASSY |  |  | 12/7 - BOT 6:00 12/7 - TOP 10:00 12/8 - AOI | 137 | 455 | 1B 2T | 63 | 630 | FEDEX P | TEST COACH |  | 12/5 - USE WS-809 PASTE 12/7 - NO CLEAN PROCESS; MAY REQUIRE VIBRATION CLEANING 12/6 - DAY 1 IS 12/8 (ANNE) | DOC REL 11/27 | 12/5 | 8236 | BOT 1ST; MAKE SURE FIXTURE & PLATES' HOLES LINE UP BEFORE RUNNING VERIFY PCB REQUIRES BAKING | 2023-12-14 | 2 | 2023-12-07
2023-12-15 |  | 12/6 - 14 OF 15 CLEAR 12/8 - LAST PCB ETA 12/8 - KIT CLEAR |  |  |  |  | 1 | 120886-2 BAL RONC 114618 | 15 | 12/15 5D | NL | RONC | ONLY RONC CHANGE IS STIFFENER PLACED OPPOSITE PREV BUILD REMOVE J1-2 & T1-6 FROM OLD PCBs ONTO NEW PCBs CLASS 3 DATE CODE LABEL CofC REQUIREMENTS |  |  | 12/12 - BOT 11:00 12/13 - TOP 8:00 12/14 - AOI 8:00 | 78 | 768 | 1B 1T | 10 | 150 | FEDEX P | South Coast Circuits Inc |  | 12/6 - MOST PCBS HERE, READY TO RUN | DOC REL 10/10 | 12/6 | 7608.4 | BOT 1ST | 2023-12-15 | 2 | 2023-12-12 | 14
2023-12-15 |  | 12/8 - PCB DUE 12/8 - KIT CLEAR |  |  |  | 1 |  | 121856 NEW | 105 | 12/15 5D | NL | x | BT1: Huntsman Arathane 5753 A/B cut with Cab-O-Sil HS-5 silica powder DP100 is OK TO USE REQUIRED PER ECO LABEL REQUIREMENTS DEPANEL |  |  | 12/12 - TOP 10:00 12/13 - BOT 12:00 12/14 - AOI 11:00 | 67 | 152 | 1B 1T | 6 | 630 | FEDEX P | Industrialex Manufacturing |  |  | DOC REL 12/1 | 12/1 | 5739.2 | BOT 1ST top side 1st | 2023-12-15 | 2 | 2023-12-12 | 15
2023-12-15 |  | 12/7 - ALMOST CLEAR; SHORT 5 PCS OF JP_1 12/8 - HOLD - MG1, MG2, MG3, MG4 ISSUE 12/8 - OFF HOLD - CUST APPVD HAND SOLDER OF MG1.. 12/12 - SHIPPED 100 OF 450 12/12 - KIT CLEAR |  |  | 1 |  |  | 122444-2 BAL NEW | 350 | 12/15 5D | NL | X | *CUST PAID EXPEDITE FOR QTY 100 SHIP EARLY (ALSO PAID TO HAND SOLDER STANDOFFS) DEPANEL GDT1 & 3 PLACE PER ECO#2 HEIGHT REQ FOR GDT2&4 PER ECO #6 |  |  | 12/11 - BOT 1:00 12/12 - TOP 11:30 12/14 - AOI 10:00 | 23 | 92 | 1B 1T | 30 | 10500 | FEDEX P | Industrialex Manufacturing |  | 12/7 - DAY 1 IS 12/11 (ANNE) 12/11 - J-CONNECTOR MISALIGN (FIXTURE OR GLUE NEEDED) 12/11 - MG1, MG2, ETC. TOO LARGE; CUST SENT NUTS DUE 12/12 12/13 - REQUIRES 2 PEOPLE TO H/L PARTS IN SMT. 1 MIN TO RUN ON MACHINE, 2-3 ADDITIONAL MINUTES TO H/L | DOC REL 12/7 | 12/7 | 31516 | BOT 1ST; | 2023-12-15 | 2 | 2023-12-08 | 22
2023-12-14 |  | 11/30 - WILL CLEAR DATE 12/4 - KIT CLEAR |  |  |  | 2 |  | 121601 ROWC 118285 | 5 | 12/18 10D | NL | ROWC | DEPANEL |  |  | 12/11 - BACK | 51 | 556 | 1B 1T | 8 | 40 | FEDEX P | Genuen, LL |  |  | DOC REL 11/15 | 2023-11-21 | 2069.4 | BOT 1ST | 2023-12-18 | 2 | 2023-12-07
2023-12-14 |  | 12/8 - PCB DUE 12/8 - KIT CLEAR |  |  |  |  | 1 | 122396 NEW | 12 | 12/15 5D | NL | X | DEPANEL "BUZZ1" AFTER WASH |  |  | 12/11 - BOT 2:00 12/12 - TOP 8:00 12/12 - AOI 11:00 | 93 | 450 | 1B 2T | 26 | 312 | UPS RED | DE Design Works |  |  | DOC REL 12/4 | 12/6 | 4272.48 | BOT 1ST | 2023-12-15 | 2 | 2023-12-12 | 4
2023-12-14 |  | 12/8 - PCB DUE then SMT clear 12/7 - KIT CLEAR |  |  |  |  | 1 | 121857-1ST NEW | 2 | 12/14 5D | NL | X | label: 231006 - 01 DEPANEL "U15" DO NOT WASH |  |  | 12/11 - BOT 6:00 12/11 - TOP 12/11 - AOI 2:00 | 44 | 91 | 1B 1T | 7 | 14 | FEDEX P | Industrialex Manufacturing |  |  | DOC REL 12/1 | 12/5 | 2270 | TOP 1ST | 2023-12-14 | 2 | 2023-12-11
2023-12-14 |  | 12/8 - PCB DUE 12/7 - KIT CLEAR |  |  |  |  | 1 | 122298 NEW | 2 | 12/14 5D | NL | X | LEAD PROCESS DEPANEL SMT VERIFY ECO #4 "U45" GND PADS NEED UNSOLDERED |  |  | 12/11 - BOT 6:00 12/11 - TOP 12/11 - AOI 1:00 | 30 | 458 | 1B 1T | 14 | 28 | FEDEX P | Duotech Services, Inc. |  |  | DOC REL 12/1 | 12/5 | 3089 | BOT 1ST | 2023-12-14 | 2 | 2023-12-11
2023-12-14 |  | 11/22 - PCB DUE 12/5 - PCB due 12/7 - KIT CLEAR |  |  |  |  | 1 | 121655 NEW | 5 | 12/14 5D | NL | X | x |  |  | 12/11 - BOT 6:00 12/11 - TOP 12/11 - AOI 12:00 | 166 | 681 | 1B 2T | 10 | 50 | FEDEX GRD | L3 |  | 11/29 - do not return excess matl | DOC REL 11/16 | 11/17 | 8941.25 | BOT 1ST; LF | 2023-12-14 | 2 | 2023-12-08
2023-12-13 |  | 11/29 - KIT CLEAR |  |  |  |  | 1 | 116955-2ND 2PAR RONC 1st Article | 60 | 12/20 12/15 6D | NL | RONC | SPLIT SHIPMENT (MONTHLY): BAL REMAINING 440 LEAD PROCESS DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 11/30 - TOP 10:30 11/30 - AOI 12:00 | 7 | 8 | 1T | 12 | 720 | FEDEX P | Anderson Connectivity |  | 11/29 - 7D TURN FOR ALL ANDERSON JOBS FROM THIS DAY FORWARD (ANNE) 11/29 - QTY 58 1ST SHIPMENT | DOC REL 11/29 | 2023-11-29 | 4726 | TOP SIDE ONLY; | 2023-12-07 | 1 | 2023-11-30
2023-12-12 |  | 11/6 - PCB DUE & AWT PART CONF 11/9 - KIT CLEAR |  |  |  | 2 |  | 116954-1st 2PAR NEW | 60 | 12/12 12/15 10D | NL | X | SPLIT SHIPMENT (MONTHLY): BAL REMAINING 420 EAD PROCESS DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 11/14 - TOP 9:00 11/15 - AOI 10:00 | 24 | 87 | 1T | 1 | 60 | 1 | Anderson Connectivity |  | 12/11 - ship 12/12 (anne) | DOC REL 11/1 | 2023-11-03 | 4738.4 | TOP SIDE ONLY; R; received printed email copies of customer req part to use | 2023-11-17 | 1 | 2023-11-15 | 8
2023-12-12 |  | 11/14 - KIT CLEAR |  |  |  |  | 1 | 116967-1ST 2PAR NEW | 60 | 12/12 12/15 10D | NL | X | SPLIT SHIPMENT (MONTHLY): BAL REMAINING 420 LEAD PROCESS DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 11/15 - TOP 8:00 11/15 - AOI 1:00 | 37 | 89 | 1T | 2 | 120 | FEDEX P | Anderson Connectivity |  | 12/11 - ship 12/12 (anne) | DOC REL 11/1 | 2023-11-14 | 4668.2 | TOP SIDE ONLY; R | 2023-11-17 | 1 | 2023-11-15 | 5
2023-12-12 |  | 11/3 - PCB DUE TODAY & AWT PART CONF #15 (L1, L2) 11/6 - SHORT ATTRITION & short L1 11/9 - KIT CLEAR |  |  |  | 1 |  | 116956-1st 2PAR NEW | 60 | 12/12 12/15 10D | NL | X | REMOVE ALL FB8 SPLIT SHIPMENT (MONTHLY): BAL REMAINING 420 CUST: L1, L2 USE p/n 1264EY-330M=P3 LEAD PROCESS DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 11/13 - BOT 1:30 11/14 - HOLD 9:00 11/15 - BOT 10:00 11/16 - TOP 2:00 11/17 - AOI 7:00 | 28 | 122 | 1B 1T | 3 | 180 | FEDEX P | Anderson Connectivity |  | 11/14 - PCB STAMP ISSUE; JOB ON HOLD 12/11 - ship 12/12 (anne) | DOC REL 11/1 | 2023-11-03 | 6165.8 | BOT 1ST; R | 2023-11-17 | 2 | 2023-11-13 | 15
2023-12-12 |  | 11/3 - AWT 1 PART CONF 11/8 - KIT CLEAR |  |  |  | 1 |  | 116970-1st 2PAR NEW | 60 | 12/12 12/15 10D | NL | X | SPLIT SHIPMENT (MONTHLY): BAL REMAINING 420 DNI #36 (U3) & ship w/ PCBAs LEAD PROCESS XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! DEPANEL |  |  | 11/10 - BOT 1:30 11/11 - TOP 11/13 - AOI 10:00 | 29 | 54 | 1B 1T | 11 | 660 | FEDEX P | Anderson Connectivity |  | 12/11 - ship 12/12 (anne) | DOC REL 11/1 | 11/3 | 4949 | BOT 1ST; R; 1 SMT PART ON TOP | 2023-11-17 | 2 | 2023-11-11 | 11
2023-12-12 |  | 12/7 - ALMOST CLEAR; SHORT 5 PCS OF JP_1 12/8 - HOLD - MG1, MG2, MG3, MG4 ISSUE 12/8 - OFF HOLD - CUST APPVD HAND SOLDER OF MG1.. 12/12 - KIT CLEAR |  |  | 3 |  |  | 122444-1 PAR NEW | 100 | 12/12 12/15 5D | NL | X | *CUST PAID EXPEDITE FOR QTY 100 SHIP EARLY (ALSO PAID TO HAND SOLDER STANDOFFS) DEPANEL GDT1 & 3 PLACE PER ECO#2 HEIGHT REQ FOR GDT2&4 PER ECO #6 |  |  | 12/8 - BOT 12/9 - TOP 12/9 - AOI | 23 | 92 | 1B 1T | 30 | 3000 | FEDEX P | Industrialex Manufacturing |  | 12/7 - DAY 1 IS 12/11 (ANNE) 12/11 - J-CONNECTOR MISALIGN (FIXTURE OR GLUE NEEDED) 12/11 - MG1, MG2, ETC. TOO LARGE; CUST SENT NUTS DUE 12/12 | DOC REL 12/7 | 12/7 | 15376 | BOT 1ST; | 2023-12-15 | 2 | 2023-12-08
2023-12-12 |  | 12/7 - KIT CLEAR |  |  |  | 1 |  | 122471 NEW | 6 | 12/12 3D | NL | X | *** 3 DAY TURN *** DEPANEL & SAND INSTALL SHUNTS PER ECO #4 |  |  | 12/8 - BOT 8:00 | 46 | 114 | 1B 1T | 69 | 414 | FEDEX P | Enovate Medical /Stinger Medical |  |  | DOC REL 12/6 | 12/7 | 5165.5 | BOT 1ST | 2023-12-12 | 2 | 2023-12-08
2023-12-11 |  | 11/21 - KIT CLEAR |  |  |  |  | 1 | 121479 NEW | 500 | 12/11 12/21 20D | NL | x | SHIPPING HOLD; CONTINUE PRODUCTION BUT DO NOT SHIP DEPANEL |  |  | 12/1- BOT 6:00 12/1 - TOP 11:30 12/5 - TOP 9:00 12/5 - AOI 10:00 | 3 | 4 | 1B 1T | 0 | 0 | FEDEX GRD | Kopin Corporation |  | 12/1 - HALTED TO RUN B121745 & B116966 1ST (BOT SIDE DONE) | DOC REL 11/3 | 2023-11-21 | 4100 | BOT 1ST | 2023-12-21 | 2 | 2023-12-07 | 6.5
2023-12-08 |  | 12/1 - KIT CLEAR |  |  |  | 1 |  | 121348 ROWC 119067 | 75 | 12/8 5D | NL | ROWC | "S1" AFTER WASH TRIM LEADS - NOT TO EXCEED 0.1" DEPANEL & SAND |  |  | 12/5 - TOP 8:00 12/6 - BOT 9:00 12/6 - AOI 2:00 | 113 | 283 | 1B 2T | 17 | 1275 | FEDEX P | Ocean Aero, Inc. |  |  | DOC REL 11/21 | 12/1 | 5732.25 | TOP 1ST | 2023-12-08 | 2 | 2023-12-05 | 12
2023-12-08 |  | 11/30 - PCB due 12/1 - KIT CLEAR |  |  | 1 |  |  | 122169 NEW | 10 | 12/8 12/6 3D | NL | x | SHIPPING HOLD, CONTINUE PRODUCTION BUT DO NOT SHIP *** 3 DAY TURN *** LEAD PROCESS DEPANEL IC10 MOISTURE SENSITIVE |  |  | 12/5 - BOT 7:00 12/5 - TOP 9:00 12/5 - AOI 11:00 | 97 | 339 | 1B 1T | 6 | 60 | FEDEX P | Ocean Aero, Inc. |  |  | DOC REL 11/21 | 11/22 | 5935.5 | BOT 1ST | 2023-12-06 | 2 | 2023-12-05 | 4
2023-12-08 |  | 11/30 - PCB due 12/1 - KIT CLEAR |  |  | 1 |  |  | 121876 NEW | 21 | 12/8 12/6 3D | NL | x | SHIPPING HOLD, CONTINUE PRODUCTION BUT DO NOT SHIP *** 3 DAY TURN *** LEAD PROCESS DEPANEL :IC19" IS MOISTURE SENSITIVE |  |  | 12/1 - BOT 1:30 12/4 - TOP 9:00 12/5 - AOI 7:00 | 72 | 300 | 1B 1T | 4 | 84 | FEDEX P | Ocean Aero, Inc. |  | 12/4 - JOB HALT, OPERATOR HAS DOCTOR APPOINTMENT 10 AM | DOC REL 11/21 | 11/22 | 5724.75 | BOT 1ST | 2023-12-06 | 2 | 2023-12-04 | 6
2023-12-08 |  | 11/20 – PCB due 11/22 - PCB due 11/22 - KIT CLEAR |  |  |  |  | 1 | 121870 NEW | 105 | 12/8 11/29 3D | NL | X | SHIPPING HOLD, CONTINUE PRODUCTION BUT DO NOT SHIP *** 3 DAY TURN *** DEPANEL |  |  | 11/22 - BOT 10:00 11/27 - TOP 10:00 11/28 - AOI 11:30 | 114 | 518 | 2B 2T | 2 | 210 | FEDEX P | Ocean Aero, Inc. |  | 11/28 - SZESD7351HT1G (D44,D45,D46...) FLEW OFF BOARD IN REFLOW 3, BUT REFLOW 2 OK 11/28 - SER2915H-153KL (L2 - BOT SIDE) FELL OFF WHILE TOP REFLOW | DOC REL 11/6 | 11/8 | 30186.05 | BOT 1ST; R; S/U EARLY PCB here | 2023-11-29 | 2 | 2023-11-22 | 22.5
2023-12-07 |  | 12/1 - KIT CLEAR |  |  |  |  | 1 | 122424 RONC 119410 | 80 | 12/7 12/15 10D | NL | RONC | MIXED POP PER ECO #4 QTY 40 W/ GRT1555C1H102FA02D, BAL QTY 40 W/ GRM1557U1A202JA01D LABEL BOTH LOTS ACCORDINGLY PER ECO #4 |  |  | 12/5 - BOT 10:00 12/5 - TOP 11:30 12/5 - AOI 2:00 | 26 | 52 | 1B 1T | 4 | 320 | FEDEX P | Open Source Instruments Inc |  | ok to ship a week early (Anne) | DOC REL 11/30 | 12/1 | 1547.2 | BOT 1ST | 2023-12-15 | 2 | 2023-12-07 | 4
2023-12-07 |  | 11/30 - KIT CLEAR |  |  |  |  | 1 | 121745 NEW | 30 | 12/7 12/14 10D | NL | X | Care Required when Screwing DEPANEL & SAND MECH ASSY REQ |  |  | 12/1 - TOP 11:30 12/1 - AOI 1:00 | 5 | 8 | 1T | 32 | 960 | UPS RED | Samtec |  | ok to ship a week early (Anne) | DOC REL 11/16 | 11/30 | 3110 | TOP ONLY | 2023-12-14 | 1 |  | 1
2023-12-06 |  | 12/1 - WILL CLEAR DATE 12/1- KIT CLEAR |  |  |  |  | 1 | 116966-2ND 1PAR ROWC 1st Article | 34 | 12/7 5D | NL | ROWC | Skip IC2 for all boards we are short the part. SPLIT SHIPMENT (MONTHLY): BAL REMAINING 524 2 LABEL TYPES & LOCS TEXT LABEL & QR CODE ENSURE S/N MATCH LABELS SPECIFIED LOCATIONS LEAD PROCESS DEPANEL XRAY & SVE |  |  | 12/4 - BOT 6:00 12/4 - TOP 9:00 12/4 - AOI 2:00 | 34 | 154 | 2B 2T | 1 | 34 | FEDEX P | Anderson Connectivity |  | 11/30 - SHIP DATE 12/7 (ANNE) | DOC REL 11/28 | 11/30 | 7912.2 | BOT 1ST; START LOADING AS SOON AS WE HAVE 58 OF TOP COMPLETED IN SMT ETA FULL COMPLETION EOD TUES (START MON) | 2023-12-07 | 2 | 2023-12-04
2023-12-06 |  | 11/29 - KIT CLEAR |  |  |  | 1 |  | 116964-2ND 1PAR ROWC 1st Article | 58 | 12/7 6D | NL | ROWC | 60 boards smt comp; ship 58 only FOR IC17 USE P/N IS21TF32G-JCLI. Use SN 00378 and 00379 for these 2 boards SHIP 2 SPECIAL BOARDS SPLIT SHIPMENT (MONTHLY): BAL REMAINING 500 LEAD PROCESS DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 12/1 - BOT 9:30 12/4 - TOP 9:00 12/4 - AOI 2:00 | 67 | 264 | 2B 2T | 5 | 290 | FEDEX P | Anderson Connectivity |  | 11/29 - QTY 58 1ST SHIPMENT 12/4 - STOP AT 60 BOARDS COMPLETE TOP & BOTTOM TO RUN B121348 12/4 - 60 boards complete & stop to run B121348 | DOC REL 11/29 | 11/29 | 12372.88 | BOT 1ST BOT NEEDS TO BE DONE EOD MON | 2023-12-07 | 2 | 2023-12-05
2023-12-06 |  | 5/10 - KIT CLEAR |  |  |  |  | 1 | 117371-4 BAL NEW | 12 | 12/6 15D | NL | X | BAKE BOARDS BEFORE SHIPPING DEPANEL NON-FLUSH J9 & J10 |  |  | 5/19 - BOT 11:00 5/19 - TOP 1:00 | 18 | 22 | 15 | 18 | 216 | UPS GND |  |  |  |  | 5/11 | 375.06 |  | 2023-12-06
2023-12-06 |  | 7/27 - KIT CLEAR |  |  | 1 |  |  | 117369-3 BAL NEW | 12 | 12/6 15D | NL | X | BAKE BOARDS BEFORE SHIPPING DEPANEL J9 HEIGHT REQUIREMENT |  |  | 7/29 - BOT 12:00 7/29 - TOP 1:00 7/29 - AOI 2:00 | 18 | 22 | 15 | 19 | 228 | UPS GND | THORLABS |  |  |  | 2023-07-27 | 375 |  | 2023-12-06
2023-12-05 |  | 11/21 - KIT CLEAR |  |  |  | 1 |  | 121829 NEW | 10 | 12/6 11/30 5D | NN | X | CLASS 3 SMT - Sn63Pb37 paste required. ALL SOLDERING FLUX USED SHALL BE ROL0 OR ROL1. OK TO USE WS-809 *NO FLUX/RESIDUE PER ECO #5 |  |  | 11/29 - BOT 2:00 11/30 - TOP 11:00 12/1 - AOI 9:30 | 34 | 1266 | 2B 2T | 0 | 0 | UPS RED | Reliable Robotics |  | 11/22 - ROLO0 / ROL1 IS NO-CLEAN FLUX, BUT JOB IS CLEAN 11/29 - JOB OFF HOLD; USE WS-809 | DOC REL 11/13 | 2023-11-21 | 7833 | BOT 1ST | 2023-12-06 | 2 | 2023-11-30 | 7.5
2023-12-05 |  | 11/29 - KIT CLEAR |  |  |  |  | 1 | 116955-2ND 1PAR RONC 1st Article | 58 | 12/5 12/7 6D | NL | RONC | SPLIT SHIPMENT (MONTHLY): BAL REMAINING 500 LEAD PROCESS DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 11/30 - TOP 10:30 11/30 - AOI 12:00 | 7 | 8 | 1T | 12 | 696 | FEDEX P | Anderson Connectivity |  | 11/29 - 7D TURN FOR ALL ANDERSON JOBS FROM THIS DAY FORWARD (ANNE) 11/29 - QTY 58 1ST SHIPMENT | DOC REL 11/29 | 2023-11-29 | 4726 | TOP SIDE ONLY; | 2023-12-07 | 1 | 2023-11-30 | 1.5
2023-12-04 |  | 11/20 - KIT CLEAR |  |  |  |  | 1 | 121834 NEW | 100 | 12/4 12/6 10D | NL | X | DNI #33 (U6) DEPANEL |  |  | 11/29 - BOT 11:30 11/29 - TOP 2:30 11/30 - AOI 10:30 | 55 | 94 | 1B 1T | 1 | 100 | FEDEX P | Hip Science, LLC |  |  | DOC REL 11/8 | 2023-11-20 | 2050 | BOT 1ST ; LF | 2023-12-06 | 2 | 2023-11-29 | 8.5
2023-12-04 |  | 11/17 - PCB DUE 11/9 - SHORTAGES DUE EARLY NEXT WEEK 11/16 - KIT CLEAER |  |  |  |  | 1 | 121581 NEW | 20 | 12/4 10D | NL | X | DNI SW1 and J12. DEPANEL |  |  | 11/21 - TOP 12:30 11/22 - BOT 8:00 11/29 - BOT 9:30 11/29 - AOI 11:30 | 87 | 696 | 2B 1T | 11 | 220 | FEDEX P | Stensat Group LLC |  | 11/22 - JOB ON HOLD TO RUN B121870 | DOC REL 11/9 | 11/9 | 7779 | TOP 1ST; LF | 2023-12-04 | 2 | 2023-11-29 | 6.5
2023-12-04 |  | 11/20 - KIT CLEAR |  |  |  | 1 |  | 116950-2nd 1PAR RONC 1st Article | 58 | 12/4 12/6 10D | NL | RONC | SPLIT SHIPMENT (MONTHLY): BALANCE REMAINING 500 LEAD PROCESS DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 11/29 - BOT 10:00 11/29 - TOP 12:00 11/29 - AOI 2:00 | 6 | 16 | 1B 1T | 5 | 290 | FEDEX P | Anderson Connectivity |  |  | DOC REL 11/17 | 11/20 | 4213.36 | BOT 1ST; R; MOSTLY BIG PARTS; PREV L3 MONTHLY: - 12/6 – QTY 58 - 1/8 – QTY 58 - 2/6 – QTY 58 - 3/6 – QTY 4 | 2023-12-06 | 2 | 2023-11-29 | 4
2023-12-04 |  | 11/21 - PCB due 11/27 - PCB due 11/27 - KIT CLEAR |  |  | 1 |  |  | 121008-1ST NEW | 4 | 12/4 5D | NN | X | PRESS FIT DEPANEL VERIFY "U24" PRE-BAKE? - SEE ECO #2 *SMT - VERIFY SW1_FT IS MASKED OFF PER ECO #3 S/N LABEL |  |  | 11/28 - BOT 11:30 11/29 - TOP 9:00 12/1 - TOP 7:30 12/1 - AOI 8:30 | 127 | 802 | 2B 2T | 4 | 16 | UPS RED | Farsounder Inc |  | 11/29 - TOP SIDE PAUSED TO BAKE #67(U24) FOR 48 HOURS | DOC REL 11/9 | 2023-11-14 | 5314 | BOT 1ST; LF | 2023-12-04 | 2 | 2023-11-29 | 6.5
2023-12-01 |  | 11/27 - KIT CLEAR |  |  |  | 1 |  | 116957-2ND 1PAR RONC 1st Article | 58 | 12/1 10D | NL | RONC | SPLIT SHIPMENT (MONTHLY): BALANCE REMAINING 500 LEAD PROCESS DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 11/29 - BOT 8:00 11/29 - AOI 10:00 | 1 | 1 | 1B | 12 | 696 | FEDEX P | Anderson Connectivity |  | 12/1 OR 12/4 - SHIP DATE FOR 58 BOARDS (ANNE) | DOC REL 11/27 | 2023-11-27 | 5060.64 | BOT 1ST; NOT RELEASED YET | 2023-12-01 | 1 | 2023-11-29 | 2
2023-11-30 |  | 11/13 - PCB DUE 11/15 - SHORTAGES DUE 11/16 - AWT PART CONF 11/20 - SMT CLEAR 11/21 - KIT CLEAR |  |  | 1 |  |  | 121413-1ST NEW | 2 | 11/30 5D | NL | X | 1 FRONT & BACK PHOTO REQUIRED & PUT INTO JOB FOLDER PRESS FIT REQ SHIP P/N 9018 W/ BOARDS POST BAKE 30 MIN IF WASHED MECH ASSY W/ TORQUE REQ EMAIL: "MARK PACKAGE WITH "437148988" DEPANEL |  |  | 11/28 - BOT 8:30 11/28 - TOP 11:30 11/29 - AOI 7:30 | 131 | 651 | 2B 2T | 10 | 20 | UPS GRD | Diversified Supply |  | 11/29 - DIODE ORIENTATION FOLLOW THE YELLOW LINES ON THE PDF | DOC REL 10/30 | 11/9 | 3830 | BOT 1ST; LFT | 2023-11-30 | 2 | 2023-11-28 | 4.5
2023-11-30 |  | 10/26 - MAY CLEAR DATE 11/10 - PCB due 11/17 - PCB due 11/16 - KIT CLEAR |  |  |  | 1 |  | 120130-1st NEW | 2 | 11/30 11/27 5D | NL | X | DEPANEL |  |  | 11/20 - BOT 10:00 11/21 - BOT DONE 12:00 11/27 - TOP 12:30 11/29 - AOI 11:30 | 100 | 1716 | 1B 2T | 0 | 0 | FEDEX P | Blue Ridge Envisioneering, INC. |  | 11/20 - 11/21 - GERBER TO PCB SCALING ISSUE 11/28 - A LOT OF TIME SPENT RECENTERING PARTS ON THE SMT MACHINES 11/30 - A LOT OF BRIDGING & MISSING PART ISSUES | LAN REL 10/12 | 2023-10-20 | 13398 | LARGE BGA & SMALL PARTS; BOT 1ST; L3 RECOMMENDED; R | 2023-11-27 | 2 | 2023-11-29 | 12
2023-11-30 |  | 11/27 - PCB DUE 11/20 - SHORT PARTS W/O DUE DATE 11/28 - KIT CLEAR |  |  |  |  | 1 | 122007 NEW | 10 | 11/30 2D | NL | X | *** 2 DAY TURN *** ***DO NOT WASH U1 DEPANEL |  |  | 11/28 - BOT 1:30 11/28 - TOP 11/28 - AOI 9:30 | 82 | 346 | 1B 2T | 1 | 10 | FEDEX GRD | Viavi Solutions - 3Z Telecom |  |  | DOC REL 11/20 | 11/20 | 7900 | SMALL PARTS; BOT 1ST | 2023-11-30 | 2 | 2023-11-29 | 4.5
2023-11-30 |  | 11/14 - AWT PART CONF #17 (Y1) 11/14 - CLEAR TO RUN WHAT WE HAVE 11/16 - KIT CLEAR |  |  |  |  | 1 | 121844 RONC 120559 | 225 | 11/30 10D | NL | RONC | ***HEAVY T/H - SMT MUST START ON DAY 1!!!*** DEPANEL VERIFY STENCIL IS CLOSED @ "J10" PER ECO 30 MIN POST BAKE REQ IF BOARDS ARE WASHED |  |  | 11/16 - BOT 9:00 11/17 - TOP 7:00 11/21 - AOI 12:00 | 65 | 422 | 1B 2T | 53 | 11925 | FEDEX P | Industrialex Manufacturing |  | 11/14 - CLEAR TO RUN ALL TOP SIDE 1ST AND RUN BOTTOM OF WHAT WE HAVE | DOC REL 11/8 | 11/14 | 26984.25 | HEAVY THT: ON LINE DAY 1 OR SOONER (TAD); BOT 1ST; R | 2023-11-30 | 2 | 2023-11-16 | 23
2023-11-29 |  | 11/15 - MAY CLEAR 11/18 - ALMOST SMT CLEAR; SHORT 2 PCS OF #51 (U2A, U2B) 11/20 - KIT CLEAR |  |  | 1 |  |  | 121959 NEW | 2 | 11/29 5D | NL | X | SMT ALERT - IPC PAD VIOLATION- RUN ONLY 1 BOARD THEN CHECK ENSURE L1A, L1B IS MASKED OFF ESNURE J4, J5 PAD CONNECTED DEPANEL |  |  | 11/27 - BOT 12:30 11/28 - TOP 11/28 - AOI 8:30 | 114 | 896 | 1B 2T | 5 | 10 | UPS RED | Free Wire Tech |  | 11/22 - IPC AIR GAP VIOLATION; REVIEW 1ST BOARD AFTER RUN | DOC REL 11/15 | 11/15 | 4722.4 | BOT 1ST; LF; CHECK W/ TRINH IF SHORT PARTS ARE SKIPPABLE | 2023-11-29 | 2 | 2023-11-27 | 4.5
2023-11-28 |  | 10/23 - WILL CLEAR THIS WEEK 11/6 - KIT CLEAR |  |  | 1 |  |  | 108434 RONC 101523 | 355 | 11/30 12/6 20D | NL | RONC | ***LEAD JOB - NEED TO WATCH REFLOW - DONT LET BOARDS SIT TOO LONG BEFORE REFLOW CLASS 3 DATE CODE LABEL |  |  | 11/11 - BOT 11/13 - TOP 9:00 11/13 - HOLD 10:00 11/16 - TOP 10:00 11/17 - AOI 7:30 | 60 | 188 | 2B 2T | 0 | 0 | UPS 3DAY | Coastal Designs, LLC |  | SHARES FEEDERS W/ B121661 11/13 - WRONG PART USED, RWK REQUIRED ON 150 BOARDS; ONE FEEDER USED FOR 2 LOCATIONS 11/13 - FA FOR TOP DONE; JOB ON HOLD TO RUN B120925 1ST | DOC REL 10/24 | 2023-10-23 | 16929.95 | PREV BUILD L2; R; BOT 1ST | 2023-11-30 | 2 | 2023-11-11 | 30
2023-11-28 |  | 10/31 - KIT CLEAR |  |  | 1 |  |  | 121661 RONC 108434 | 200 | 11/28 20D | NL | RONC | CLASS 3 DATE CODE LABEL |  |  | 11/6 - TOP 8:30 11/6 - BOT 1:00 11/7 - AOI 10:00 | 60 | 188 | 2B 2T | 0 | 0 | UPS 3DAY | Coastal Designs, LLC |  | FAB DOES NOT MATCH STENCIL; REC'D NEW STENCIL S/U BOT SIDE 1ST NEXT TIME 11/11 - CAUGHT PART (ONE FEEDER) USED FOR TWO LOCATIONS; REQUIRES RWK | DOC REL 10/26 | 2023-10-31 | 11844 | TOP 1ST; R; RUN NO LATER THAN MONDAY | 2023-11-28 | 2 | 2023-11-06 | 9.5
2023-11-27 |  | 11/8 – Shortages due 11/15 – PCB due 11/16 - KIT CLEAR |  |  |  | 1 |  | 121854 NEW | 40 | 11/27 5D | NL | X | Depanel, sand and bundle separately. Ok to ship in one box DATE CODE LABEL KEEP 1 DEPANEL ON FILE |  |  | 11/20 - ON HOLD 11/22 - BOT 8:00 11/22 - TOP 12:00 11/27 - AOI 12:00 | 51 | 257 | 1B 1T | 3 | 120 | FEDEX GRD | AimLock |  | 11/17 - JOB ON HOLD. INCORRECT STENCIL/PANELS 11/21 - DEPANEL BEFORE RUN 11/27 - STENCIL HAS A SLIGHT MISALIGNMENT | DOC REL 11/8 | 11/8 | 3898.4 | BOT 1ST; LF | 2023-11-27 | 2 | 2023-11-22 | 10
2023-11-27 |  | 9/14 - J1 WRONG SIZE 9/19 - CUST HOLD UNTIL OCT 10/9 - WILL CLEAR THIS WEEK 11/16 - KIT CLEAR |  |  | 1 |  |  | 120152 R NEW | 30 | 11/27 5D | RL | X | #18 (U9) BTD EXACT U1, U2 & U3: CARE REQ CHECK J1, J2, J4, J5, J6 & U9 ARE OK AFTER REFLOW JP6, JP7... REQUIRES SOLDER BRIDGING (SEE ECO) |  |  | 11/17 - BOT 7:30 11/17 - TOP 9:30 11/17 - AOI 1:00 | 31 | 91 | 1B 1T | 2 | 60 | FEDEX GND | NIST |  |  |  | 2023-09-14 | 1652.5 | CHECK J1, J2, J4, J5, J6, U1, U2, U3 & U9 ARE OK AFTER REFLOW; BOT 1ST; R | 2023-11-27 | 1 | 2023-11-17 | 5.5
2023-11-22 |  | 10/9 - EXPECTED CLEAR DATE 10/11 - KIT CLEAR 10/18 - ON HOLD 11/6 - KIT CLEAR |  |  | 1 |  |  | 120688 ROWC 114869 | 193 | 11/29 11/1 15D | RT | ROWC | DEPANEL & SAND |  |  | 11/9 - BOT 12:00 11/10 - TOP 8:00 11/10 - AOI 1:00 | 68 | 137 | 2B 2T | 6 | 1158 | FEDEX P | Scientific Research Corporation |  | 10/18 - REC'D VER D PCB. REQ VER E PCB |  | 2023-10-11 | 6975.02 | PRIOR BUILD ISSUES; CHECK BOARDS AS THEY COME OUT OF REFLOW; JOB NEEDS 1 WEEK; R | 2023-11-29 | 2 | 2023-11-09 | 9
2023-11-21 |  | 10/26 - SMT CLEAR 11/9 - KIT CLEAR |  |  |  |  | 1 | 117812 NEW | 40 | 11/27 10D | NN | X | DNI j1013 & j1012 X |  |  | 11/8 - BOT 10:00 11/9 - TOP 12:00 11/10 - AOI 10:00 | 119 | 431 | 2B 2T | 1 | 40 | FEDEX P | Industrialex Manufacturing |  | 11/9 - JOB IS NOT SMT CLEAR; SHORT #72 & #73 (j1013 & J1012) | DOC REL 10/10 | 10/26 | 4566.4 | BOT 1ST; R | 2023-11-27 | 2 | 2023-11-08 | 16
2023-11-21 |  | 11/16 - PCB due 11/15 - KIT CLEAR |  |  | 1 |  |  | 121411 ROWC 121410 | 11 | 11/21 3D | NL | X | *** 3 DAY TURN *** CLASS 3 DEPANEL Same GERBER as B121410 so releasing as ROWC. Only difference is THT. Use same program/feeder to run SMT both jobs at once to save time. MECH ASSY REQ (SCREWING) |  |  | 11/16 - BOT 7:30 11/16 - TOP 8:30 11/16 - AOI 9:30 | 8 | 100 | 1B 1T | 45 | 495 | UPS GRD | Diversified Supply |  |  | DOC REL 10/31 | 2023-11-08 | 3473 | TOP 1ST; LF; LABEL BOARD IF THIS RELEASING BEFORE B121410 | 2023-11-21 | 2 | 2023-11-16 | 2
2023-11-21 |  | 11/20 – PCB due OR earlier 11/14 - KIT CLEAR |  |  | 2 |  |  | 121410 NEW | 6 | 11/21 3D | NL | X | *** 3 DAY TURN *** CLASS 3 MECH ASSY REQ (SCREWING) DEPANEL |  |  | 11/16 - BOT 6:00 11/16 - TOP 7:00 11/16 - AOI 8:00 | 8 | 100 | 1B 1T | 58 | 348 | UPS GRD | Diversified Supply |  |  | DOC REL 10/31 | 2023-11-08 | 3365 | TOP 1ST; LF; LABEL BOARD IF THIS RELEASING BEFORE B121411 | 2023-11-21 | 2 | 2023-11-16 | 2
2023-11-20 |  | 10/31 - SHORT #50 & #51; DUE THIS WEEK 11/2 - #51 (r68..) due 11/2 - KIT CLEAR |  |  | 1 |  |  | 120324-2nd ROWC 1st Article | 98 | 11/21 11/20 10D | NL | ROWC | DASH & DATE CODE LABEL |  |  | 11/18 - TOP 6:00 11/18 - AOI 11:00 | 46 | 79 | 1T | 4 | 392 | FEDEX P | Industrialex Manufacturing |  |  | DOC REL 10/31 | 10/31 | 2391.2 | TOP SIDE ONLY; R | 2023-11-20 | 1 | 2023-11-18 | 5
2023-11-20 |  | 11/7 - EXPECTED CLEAR DATE 11/9 - PCB due 11/13 - KIT CLEAR |  |  | 1 |  |  | 121617 NEW | 5 | 11/20 5D | NL | X | HL #113 (R230 - R232) p/n FC0402E49R9BST0 (SMT PART) "R230-232" P/N CHANGED TO MIC5000BFLMGNHT5 PER ECO "U3" WATER SENSITIVE |  |  | 11/15 - BOT 12:00 11/15 - TOP 2:00 11/15 - AOI 3:00 | 124 | 523 | 2B 2T | 7 | 35 | FEDEX P | Area I |  |  | DOC REL 10/31 | 11/1 | 6395 | HAS PARTS SIZED 201; BOT 1ST; R | 2023-11-20 | 2 | 2023-11-15 | 3
2023-11-20 |  | 11/10 - PCB DUE 11/14 - PCB DUE |  |  | 1 |  |  | 121416 NEW | 5 | 11/20 5D | NL | X | CLASS 3 DEPANEL PRESS FIT SCREWS W/ TORQUE SPEC REQ |  |  | 11/15 - BOT 6:00 11/15 - TOP 9:00 11/15 - AOI 12:00 | 113 | 442 | 1B 2T | 11 | 55 | UPS GRD | Diversified Supply |  |  | DOC REL 10/30 | 11/2 | 4160.75 | BOT 1ST; LF | 2023-11-20 | 2 | 2023-11-15 | 6
2023-11-20 |  | 11/6 - AWT PART CONF THEN SMT CLEAR 11/10 - SMT CLEAR 11/13 - KIT CLEAR |  |  | 1 |  |  | 120925 NEW | 15 | 11/20 5D | NL | X | ***NO ALTA STAMPS ALLOWED*** DNI J4 NO IN-HOUSE LABEL ONLY S/N LABEL PER ECO MECH ASSY W/ LOCTITE PER ECO |  |  | 11/13 - TOP 10:00 11/14 - BOT 8:00 11/14 - AOI 12:00 | 161 | 739 | 2B 2T | 35 | 525 | FEDEX P | John Hopkins University Applied Physics Lab |  |  | DOC REL 11/1 | 2023-11-06 | 9753 | TOP 1ST; LF | 2023-11-20 | 2 | 2023-11-13 | 4
2023-11-20 |  | 11/17 - AWT PCBS & PART |  |  |  |  | 1 | 116964-RWK NEW | 2 | 11/20 1D | NL | X | ADD IC17 |  |  |  | 63 | 259 | 1B 2T | 9 | 18 | FEDEX P | Anderson Connectivity |  |  | DOC REL 10/31 | 11/3 | 4084 | BOT 1ST; R | 2023-11-16 | 2 | 2023-11-14 | 2
2023-11-20 |  | 11/9 - PCB DUE 11/13 - KIT CLEAR |  |  |  |  | 1 | 116957-1st NEW | 2 | 11/20 11/16 3D | NL | X | *** 3 DAY TURN *** LEAD PROCESS DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | ON HOLD 11/14 - BOT 6:00 11/14 - AOI 7:00 | 1 | 1 | 1B | 12 | 24 | FEDEX P | Anderson Connectivity |  |  | DOC REL 10/31 | 11/3 | 3160 | mostly tht job; BOT SIDE ONLY; R | 2023-11-16 | 1 | 2023-11-14
2023-11-17 |  | 10/16 - PCB DUE 10/23 - MAY CLEAR DATE 10/26 - KIT CLEAR |  |  |  |  | 1 | 120110 NEW | 4 | 11/9 10D | NN | X | SHIPPING HOLD SHORT/SKIP #45 (U01DI00) MARKING REQUIRED (ECO #2) DEPANEL |  |  | 10/23 - BOT 10:30 10/23 - TOP 2:00 10/24 - AOI 1:00 | 131 | 1338 | 2B 2T | 9 | 36 | UPS GND | Honeywell International Inc |  | extra flux required due to cold solder issues (SMT) | DOC REL 10/2 | 2023-10-11 | 3912.36 | BOT 1ST; LF | 2023-11-06 | 2 | 2023-10-23 | 10
2023-11-17 |  | 11/14 - KIT CLEAR |  |  |  |  | 1 | 116966-1ST NEW | 2 | 11/17 3D | NL | X | 2 LABEL TYPES & LOCS TEXT LABEL & QR CODE ENSURE S/N MATCH LABELS SPECIFIED LOCATIONS |  |  | 11/16 - BOT 5:00 11/16 - TOP 7:00 11/16 - AOI 9:00 | 26 | 154 | 1B 1T | 1 | 2 | FEDEX P | Anderson Connectivity |  |  | DOC REL 10/25 | 2023-11-14 | 3838 | BOT 1ST; R | 2023-11-17 | 2 | 2023-11-16 | 4
2023-11-17 |  | 11/9 - PCB DUE 11/14 - KIT CLEAR |  |  |  |  | 1 | 116955-1st ROWC 112127 | 2 | 11/17 3D | NL | ROWC | *** 3 DAY TURN *** LEAD PROCESS XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! DEPANEL |  |  | 11/15 - TOP 1:00 11/16 - AOI 2:30 | 7 | 8 | 1T | 12 | 24 | FEDEX P | Anderson Connectivity |  |  | DOC REL 10/31 | 2023-11-03 | 2960 | TOP SIDE ONLY; R; | 2023-11-17 | 1 | 2023-11-16
2023-11-17 |  | 10/24 - PCB DUE 11/6 - PCB DUE 11/9 - KIT CLEAR |  |  |  |  | 1 | 120886-1 PAR RONC 114618 | 5 | 11/17 5D | NL | RONC | ONLY RONC CHANGE IS STIFFENER PLACED OPPOSITE PREV BUILD REMOVE J1-2 & T1-6 FROM OLD PCBs ONTO NEW PCBs CLASS 3 DATE CODE LABEL CofC REQUIREMENTS |  |  | 11/14 - BOT 10:00 11/14 - TOP 1:00 11/15 - AOI 8:00 | 78 | 768 | 1B 1T | 10 | 50 | FEDEX P | South Coast Circuits Inc |  |  | DOC REL 10/10 | 10/23 | 7608.4 | PREV BUILD L3; BOT 1ST; LF | 2023-11-17 | 2 | 2023-11-14 | 7.5
2023-11-17 |  | 10/24 - SHORT #37 (R7A..) 10/26 - KIT CLEAR |  |  | 1 |  |  | 121032-1 PAR NEW | 25 | 11/17 10D | NL | X | NO SHIP EARLY SPLIT SHIPMENT: QTY 25 DUE 11/17/23 QTY 25 DUE 4/30/24 DEPANEL |  |  | 11/2 - TOP 2:00 11/3 - AOI 12:00 | 48 | 313 | 1T | 28 | 700 | FEDEX GRD | Machine Solutions Inc |  |  | DOC REL 10/24 | 2023-10-24 | 7460 | LF; | 2023-11-17 | 1 | 2023-11-02 | 7.5
2023-11-17 |  | 11/6 - PCB DUE & AWT PART CONF 11/9 - KIT CLEAR |  |  |  | 2 |  | 116954-1st NEW | 60 | 11/17 11/27 10D | NL | X | SPLIT SHIPMENT (MONTHLY): BAL REMAINING 480 L1 USE p/n MSS5131-393MLC LEAD PROCESS DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 11/14 - TOP 9:00 11/15 - AOI 10:00 | 24 | 87 | 1T | 1 | 60 | FEDEX P | Anderson Connectivity |  |  | DOC REL 11/1 | 2023-11-03 | 4738.4 | TOP SIDE ONLY; R; received printed email copies of customer req part to use | 2023-11-17 | 1 | 2023-11-15 | 8
2023-11-17 |  | 11/14 - KIT CLEAR |  |  |  |  | 1 | 116967-1ST NEW | 60 | 11/17 3D | NL | X | SPLIT SHIPMENT (MONTHLY): BAL REMAINING 480 LEAD PROCESS DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 11/15 - TOP 8:00 11/15 - AOI 1:00 | 37 | 89 | 1T | 2 | 120 | FEDEX P | Anderson Connectivity |  |  | DOC REL 11/1 | 2023-11-14 | 4668.2 | TOP SIDE ONLY; R | 2023-11-17 | 1 | 2023-11-15 | 5
2023-11-17 |  | 11/3 - PCB DUE TODAY & AWT PART CONF #15 (L1, L2) 11/6 - SHORT ATTRITION & short L1 11/9 - KIT CLEAR |  |  |  | 1 |  | 116956-1st NEW | 60 | 11/17 11/27 10D | NL | X | SPLIT SHIPMENT (MONTHLY): BAL REMAINING 480 CUST: L1, L2 USE p/n 1264EY-330M=P3 LEAD PROCESS DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 11/13 - BOT 1:30 11/14 - HOLD 9:00 11/15 - BOT 10:00 11/16 - TOP 2:00 11/17 - AOI 7:00 | 28 | 122 | 1B 1T | 3 | 180 | FEDEX P | Anderson Connectivity |  | 11/14 - PCB STAMP ISSUE; JOB ON HOLD | DOC REL 11/1 | 2023-11-03 | 6165.8 | BOT 1ST; R | 2023-11-17 | 2 | 2023-11-13 | 15
2023-11-17 |  | 11/3 - AWT 1 PART CONF 11/8 - KIT CLEAR |  |  |  | 1 |  | 116970-1st NEW | 60 | 11/17 11/30 12/1 15D | NL | X | SPLIT SHIPMENT (MONTHLY): BAL REMAINING 480 L1 USE p/n MSS5131-393MLC DNI #36 (U3) & ship w/ PCBAs LEAD PROCESS XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! DEPANEL |  |  | 11/10 - BOT 1:30 11/11 - TOP 11/13 - AOI 10:00 | 29 | 54 | 1B 1T | 11 | 660 | FEDEX P | Anderson Connectivity |  |  | DOC REL 11/1 | 11/3 | 4949 | BOT 1ST; R; 1 SMT PART ON TOP | 2023-11-17 | 2 | 2023-11-11 | 11
2023-11-15 | [7 empty] | 104636-4a PAR RONC 2ND | 167 | 11/17 7D |  | X | SHIPPED TO CUST: 11/15 |  |  | BACK | 9 | 148 | 59 | 9 | 1503 | FEDEX P | Emphase Energy |  |  |  |  | 7996 |  | 2023-01-13
2023-11-16 |  | 11/7 - PCB DUE 11/3 - AWT PART CONF #4 & #26 11/13 - KIT CLEAR |  |  |  |  | 1 | 116964-1st NEW | 2 | 11/16 3D | NL | X | *** QUALITY ALERT *** LP1 PLACEMENT VERIFY ROTATION OF ICs (SEE ECO) LEAD PROCESS DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 11/14 - BOT 8:00 11/14 - TOP 9:00 11/14 - AOI 10:00 | 63 | 259 | 1B 2T | 9 | 18 | FEDEX P | Anderson Connectivity |  |  | DOC REL 10/31 | 11/3 | 4084 | BOT 1ST; R | 2023-11-16 | 2 | 2023-11-14 | 2
2023-11-16 |  | 11/8 - PCB ETA 11/9 - PCB due 11/13 - KIT CLEAR |  |  |  |  | 2 | 116950-1st NEW | 2 | 11/16 3D | NL | X | *** 3 DAY TURN *** LEAD PROCESS DEPANEL XRAY & SAVE 2 S/N LABELS PER ECO - S/N'S MUST MATCH PER BOARD!!! |  |  | 11/14 - BOT 7:00 11/14 - TOP 8:00 11/14 - AOI 9:00 | 6 | 16 | 1B 1T | 5 | 10 | FEDEX P | Anderson Connectivity |  |  | DOC REL 10/31 | 11/3 | 2730 | BOT 1ST; R; MOSTLY BIG PARTS | 2023-11-16 | 2 | 2023-11-14 | 2
2023-11-16 |  | 11/3 - PCBS DUE 10/26 - kit clear | [5 empty] | 121576 RONC 119436 | 90 | 11/16 11/9 10D | THT only |  | XRAY & SAVE IMAGES DEPANEL |  |  | BACK | 0 | 0 | - | 4 | 360 | FEDEX P | Anderson Connectivity |  | 10/27 - wrong PCBs received | DOC REL 10/25 | 2023-10-26 | 2160
2023-11-16 |  | 10/31 - PCB DUE DATE 10/30 - KIT CLEAR |  |  | 1 |  |  | 121062 NEW | 200 | 11/20 15D | NL | X | DEPANEL |  |  | 11/3 - BOT 12:00 11/4 - TOP 6:00 11/4 - AOI | 11 | 17 | 1B 1T | 1 | 200 | UPS RED | Virginia Polytechnic Institute (VTTI) |  | 11/3 - BOT DONE 2:00 | LAN REL 10/17 | 2023-10-26 | 1470 | BOT 1ST; LF | 2023-11-20 | 2
2023-11-16 |  | 11/6 - EXPECTED CLEAR DATE 11/9 - KIT CLEAR |  |  | 1 |  |  | 121557 NEW | 17 | 11/16 5D | NL | X | CLASS 3 SCREWS W/ TORQUE SPEC REQ PRESS FIT DEPANEL |  |  | 11/10 - BOT 1:00 11/10 - TOP 3:30 11/11 - AOI 8:00 | 96 | 352 | 1B 2T | 11 | 187 | UPS GRD | Diversified Supply |  |  | DOC REL 10/27 | 11/1 | 5071.65 | BOT 1ST; LF | 2023-11-16 | 2 | 2023-11-10 | 4.5
2023-11-16 |  | 11/3 - PCBS DUE 10/26 - no due dates for short SMT parts 11/2 - KIT CLEAR |  |  |  | 1 |  | 120897 NEW | 200 | 11/16 10D | NL | X | DNI J11 DEPANEL Soldering flux should be IAW. Orl0 "no-clean", organic type flux is preferred Rol0 and rol1 "no-clean", rosin type fluxes are also acceptable. |  |  | 11/6 - BOT 11:00 11/7 - TOP 11:00 11/8 - AOI 1:00 | 58 | 147 | 1B 2T | 2 | 400 | UPS RED | Virginia Polytechnic Institute (VTTI) |  | 11/6 - PRINTER 2 DOWN | DOC REL 10/25 | 2023-10-26 | 6082 | LF; BOT 1ST | 2023-11-16 | 2 | 2023-11-06 | 14
2023-11-15 |  | 11/7- KIT CLEAR |  |  |  | 1 |  | 121159 RONC 112580 | 100 | 11/21 10D | NL | X | NO ECO PROVIDED |  |  | 11/8 - BOT 1:00 11/9 - AOI 12:00 | 4 | 4 | 1B | 0 | 0 | FEDEX 2ND | Ascent AeroSystems |  |  | DOC REL 11/6 | 2023-11-07 | 1460 | BOT SIDE ONLY | 2023-11-21 | 1 | 2023-11-10 | 6
2023-11-15 |  | 11/3 - PCBS DUE 10/26 NO DUE DATES FOR SMT PARS 11/2 - #32 & #41 PARTS DUE 11/2 - KIT CLEAR |  |  | 1 |  |  | 121155 NEW | 40 | 11/16 10D | NL | X | REV MARKING REQ DEPANEL |  |  | 11/7 - BOT 10:00 11/7 - TOP 2:00 11/8 - AOI 1:30 | 86 | 277 | 1B 1T | 8 | 320 | FEDEX P | Powercast Corporation |  |  | DOC REL 10/25 | 2023-10-26 | 3402 | LF; BOT 1ST | 2023-11-16 | 2 | 2023-11-07 | 12
SCRAPPED |  | 1/31 - KIT CLEAR | [5 empty] | 104636-6 BAL | 200 | ??? 20D |  | X |  |  |  | 4/22 - AOI | 9 | 148 | 59 | 9 | 1800 | FEDEX P | ENPHASE |  |  |  | 1/31 | 7996 |  | ???
SCRAPPED |  | 1/31 - KIT CLEAR | [5 empty] | 104636-5 PAR | 200 | ??? 20D |  | X |  |  |  | 4/22 - AOI | 9 | 148 | 59 | 9 | 1800 | FEDEX P | ENPHASE |  |  |  | 1/31 | 7996 |  | ???
SCRAPPED | [7 empty] | 104636-4b PAR RONC 2ND | 33 |  |  | X |  |  |  |  | 9 | 148 | 59 | 9 | 297 | FEDEX P | Emphase Energy |  |  |  |  | 7996 |  | 2023-01-13
2023-11-14 |  | 11/1 - SHORT #30 (U1) NO ETA 11/2 - KIT CLEAR |  |  |  |  | 1 | 119974 ROWC 95823 | 30 | 11/16 10D | NL | ROWC | PHOTOS: CLOSE UP OF #42 (DS1, DS2...) "U24 & C58" AFTER WASH |  |  | 11/7 - BOT 8:00 11/7 - TOP 11:00 11/7 - AOI 2:00 | 58 | 421 | 1B 2T | 19 | 570 | FEDEX P | UCAR |  | #42 (ds1, ds2...) polarity question for customer | KIT CLEAR 11/1 | 2023-11-01 | 3228.6 | BOT 1ST; R | 2023-11-16 | 2 | 2023-11-06 | 7
2023-11-14 | [7 empty] | 120633-2ND RWK | 10 | 11/15 5D |  | - | RWK: All MAX14430EAEE chips will need to be swapped out with SI8645BA-B-IU chips |  |  | 11/1 - IN BACK | 0 | 0 | - | 17 | 170 | FEDEX | HRL Laboratories |  |  | DOC REL 11/1 | 2023-11-01 | 1012 | PAID RWK
2023-11-14 |  | 11/8 - PCB DUE 11/6 - KIT CLEAR |  |  | 2 |  |  | 121705 RONC 118498 | 6 | 11/20 10D | NL | RONC | BARCODE LABEL DEPANEL |  |  | 11/8 - AOI | 1 | 40 | 1T | 47 | 282 | UPS RED | Innomotics LLC |  |  | DOC REL 10/30 | 10/30 | 1962 | TOP SIDE ONLY; LF | 2023-11-20 | 1 | 2023-11-08
2023-11-14 |  | 11/10 - KIT CLEAR |  |  |  | 1 |  | 121418 ROWC 121417 | 17 | 11/15 3D | NL | ROWC | *** 3 DAY TURN *** CLASS 3 DEPANEL Same GERBER as B121417 so releasing as ROWC. Only difference is R5 LABEL & S/N PER ECO 11/3 - SHIP TO CUSTOMER |  |  | 11/13 - BOT 10:00 11/13 - TOP 11:00 11/13 - AOI 1:30 | 15 | 27 | 1B 1T | 3 | 51 | UPS GRD | Diversified Supply |  |  | DOC REL 11/1 | 11/10 | 395.25 | BUILD WITH B121417; Build difference is possibly only R5 | 2023-11-15 | 2 | 2023-11-11 | 3.5
2023-11-14 |  | 11/8 - PCB DUE 11/8 - KIT CLEAR |  |  |  |  | 1 | 121788 NEW | 55 | 11/15 5D | NL | X | ***ALL - READ ECO COMPLETELY*** *NO CLEAN PROCESS REQ AFTER WASH PER ECO #2 & #9 XRAY & SAVE DEPANEL |  |  | 11/11 - BOT 6:00 11/13 - TOP 9:30 11/13 - AOI 2:30 | 104 | 304 | 2B 1T | 4 | 220 | UPS RED | Engenious Design |  | 11/11 - STENCIL WAS OF SINGLE BOARD AND NOT ARRAY | DOC REL 11/2 | 11/3 | 5358.1 | BOT 1ST; LF; MAY HAVE TO DEPANEL BEFORE RUNNING; A LOT OF PART SIZED 201s | 2023-11-15 | 2 | 2023-11-11 | 10
2023-11-13 |  | 10/24 - MAY ALL CLEAR AT ONE TIME 10/26 - ALMOST CLEAR 10/31 - KIT CLEAR |  |  |  | 1 |  | 120807 RONC 110659 | 150 | 11/14 10D | NL | RONC | *** QUALITY ALERT *** SEE ECO CLASS 3 DEPANEL |  |  | 11/4 - BOT 11/4 - TOP 11/6 - AOI 11:00 | 40 | 54 | 1B 1T | 0 | 0 | FEDEX P | Advanced Assembly LLC |  |  | DOC REL 10/24 | 10/24 | 2268 | R: PREV BUILD L1 | 2023-11-14 | 2 | 2023-11-03
2023-11-13 |  | 11/7 - EXPECTED CLEAR DATE 11/6 - SHORT #11 (C31) 11/6 - KIT CLEAR (SHORT ATTRITION) |  |  | 1 |  |  | 121671 NEW | 6 | 11/14 5D | NL | X | LOAD P13 (0094393506621) : PREVIOUSLY DNI X |  |  | 11/8 - BOT 2:00 11/9 - TOP 9:00 11/9 - AOI 12:00 | 89 | 534 | 1B 2T | 43 | 258 | FEDEX STD | Saronic Technologies |  | 11/6 - DAY 1 IS 11/8 (ANNE) 11/9 - STENCIL MISSING U71; NEED NEW STENCIIL 11/9 - SD SLOT BENT; CAUSING NO FLUSH TO BOARD AND OPEN SOLDER | DOC REL 11/1 | 2023-11-03 | 3842.6 | BOT 1ST; LF | 2023-11-14 | 2 | 2023-11-08 | 6
2023-11-13 |  | 11/9 - KIT CLEAR |  |  |  | 1 |  | 121417 NEW | 121 | 11/14 3D | NL | x | *** 3 DAY TURN *** CLASS 3 NOTES: Mark package with 437148992 ASSY, S/N & REV S/N LABEL Do not ship boards when complete. These need to be transferred to B121412 as RefDes A1 11/3 - SPLIT SHIPMENT 17 BOARDS SHIP TO AA 104 SHIP TO CUSTOMER |  |  | 11/10 - BOT 10:00 11/10 - TOP 12:00 11/10 - AOI 1:30 | 15 | 27 | 1B 1T | 3 | 363 | UPS GRD | Diversified Supply |  |  | DOC REL 10/27 | 11/9 | 3613.25 | BUILD WITH B121418; Build difference is possibly only R5; BOT 1ST; LF | 2023-11-14 | 2 | 2023-11-10 | 3.5
2023-11-10 |  | 11/2 - WILL CLEAR 10/30 - SHORT PCB 11/2 - KIT CLEAR |  |  |  | 1 |  | 121621 ROWC 118033 | 110 | 11/10 11/7 3D | NL | ROWC | *** 3 DAY TURN *** DEPANEL |  |  | 11/3 - TOP 8:00 11/4 - AOI | 51 | 141 | 1T | 1 | 110 | FEDEX P | Ocean Aero, Inc. |  |  | DOC REL 10/26 | 2023-10-27 | 6395 | R: PREV BUILD L1 | 2023-11-07 | 1 | 2023-11-03
2023-11-10 |  | 10/26 - KIT CLEAR |  |  | 1 |  |  | 121599 RONC 117944 | 30 | 11/10 10D | NL | RONC | *** QUALITY ALERT **** OLDER BUILD HAD TOO MUCH SOLDER INSIDE P5 MONTH DAY LABEL |  |  | 11/2 - BOT 8:00 11/2 - TOP 10:00 11/2 - AOI 2:00 | 106 | 341 | 1B 2T | 11 | 330 | UPS 3DAY | Coastal Designs, LLC |  | DAY 1 10/30 (ANNE) | DOC REL 10/26 | 2023-10-27 | 4137.3 | PREV BUILD L1; BOT 1ST; R | 2023-11-10 | 2 | 2023-11-02 | 6
2023-11-09 |  | 10/4 - PCB & MATL DUE 11/2 - SHORTAGES DUE 11/2 - KIT CLEAR |  |  |  |  | 1 | 119432-1st PAR NEW | 2 | 11/9 5D | NN | X | DNI IC3200 FOR FA ONLY DEPANEL |  |  | 11/3 - BOT 8:00 11/3 - TOP 10:00 11/4 - AOI | 148 | 1086 | 2B 2T | 10 | 20 | FEDEX P | Phoenix Contact, Inc. |  |  |  | 2023-09-29 | 5834 | BOT 1ST DUE TO BGAS ON TOP SIDE; LF | 2023-11-09 | 3 | 2023-11-03
2023-11-09 |  | 11/2 - PCBS DUE 11/2 - KIT CLEAR |  |  |  |  | 1 | 121693 NEW | 105 | 11/10 11/7 3D | NL | X | *** 3 DAY TURN *** DEPANEL |  |  | 11/3 - TOP 12:00 11/4 - BOT 11/6 - AOI 12:00 | 71 | 199 | 1B 2T | 1 | 105 | FEDEX P | Ocean Aero, Inc. |  | PLAN TO RUN 11/4 BOT S/U & FA READY | DOC REL 10/25 | 10/26 | 7579.5 | R; TOP 1ST | 2023-11-07 | 2 | 2023-11-03
2023-11-09 |  | 10/31 - MAY CLEAR THIS WEEK 11/1 - SMT CLEAR 11/2 - KIT CLEAR |  |  | 1 |  |  | 121559 ROWC 105498 | 5 | 11/9 5D | NL | ROWC | X |  |  | 11/4 - BOT 9:30 11/4 - TOP 11/6 - AOI | 137 | 853 | 2B 2T | 14 | 70 | FEDEX 2ND DAY | Vista Instrumentation LLC |  |  | DOC REL 10/26 | 10/31 | 2755 | BOT 1ST; LF | 2023-11-09 | 2 | 2023-11-06
2023-11-09 |  | 11/1 - PCB WILL ARRIVE 10/31 - KIT CLEAR |  |  | 1 |  |  | 121658 NEW | 21 | 11/9 11/7 5D | NL | X | DEPANEL |  |  | 11/1 - TOP 3:00 11/1 - AOI 8:00 | 80 | 354 | 2T | 8 | 168 | FEDEX P | Ocean Aero, Inc. |  | ***PCB HAS MULTIPLE VIA HOLES ON 40+ LAND PADS - REQUIRES TUOCH UP AND MORRE TIME 11/2 - REC'D NEW PO W/ 2 XTRA DAYS | DOC REL 10/26 | 10/31 | 4840.03 | TOP ONLY; R | 2023-11-07 | 1 | 2023-11-02 | 4.5
2023-11-09 |  | 11/2 - SHORTAGES DUE 11/2 - KIT CLEAR |  |  | 2 |  |  | 121521 NEW | 40 | 11/9 5D | NL | x | BTD #22 (VD1, VD2...) & LABEL BOARDS SHORT VD1, VD2.. X |  |  | 11/3 - BOT 7:00 11/4 - TOP 6:00 11/4 - AOI | 41 | 199 | 1B 1T | 4 | 160 | UPS RED | Iotecha |  | 11/3 - BOT DONE 9:00 | DOC REL 10/20 | 11/1 | 3010 | MATLS XFERRED FROM B118993; TOP 1ST; LF | 2023-11-09 | 2 | 2023-11-03
2023-11-09 |  | 10/3 - KIT CLEAR |  |  |  | 1 |  | 120284-3bal NEW | 50 | 11/9 11/13 10D | RT | X | REM BAL OF SPLIT JOB DEPANEL |  |  | 10/4 - TOP 11:00 10/5 - BOT 10/5 - AOI 2:00 | 58 | 117 |  | 16 | 800 | UPS RED | Alliance Technology, LLC. |  |  |  | 45202 | 2579.5 |  | 2023-11-13
2023-11-08 |  | 11/3 - KIT CLEAR | [5 empty] | 121674 NEW | 100 | 11/8 3D | - |  | *** 3 DAY TURN *** THT ONLY DEPANEL |  |  | BACK | 0 | 0 |  | 2 | 200 | FEDEX P | Cognex |  |  | DOC REL 10/31 |  | 2023
2023-11-07 |  | 10/30 - MAY CLEAR DATE 10/26 - KIT CLEAR |  |  | 1 |  |  | 121672 NEW | 70 | 11/7 11/2 5D | NL | X | PRESS PINS AS PER DRAWING (J1) DEPANEL |  |  | 10/31 - BOT 6:30 10/31 - AOI 8:00 | 1 | 1 | 1B | 4 | 280 | FEDEX P | Spectro Inc. |  | 11/1 - More time request (Tad/Anne) 11/1 - No due date (Anne) | DOC REL 10/25 | 10/26 | 2410 | `REVIEW THT KIT; LF | 2023-11-02 | 1 | 2023-10-31 | 1.5
2023-11-07 |  | 10/17 - SHORT 3 SMT PARTS (34, 58 & 61) 10/20 - SMT CLEAR 10/31 - KIT CLEAR |  |  | 1 |  |  | 120762 NEW | 20 | 11/7 5D | NL | X | OK TO RUN TOP SIDE ONLY DEPANEL |  |  | 11/1 - TOP 8:00 11/1 - BOT 12:00 11/1 - AOI 3:00 | 81 | 287 | 1B 1T | 23 | 460 | FEDEX P | Friedrich Air Conditioning |  | REFLOW LINE 1 DOWN | LAN REL 10/12 | 2023-10-17 | 4415 | S/U TOP SIDE ONLY; LF | 2023-11-07 | 2 | 2023-11-01 | 7
2023-11-07 |  | 10/19 - SHORT 1 PIECE OF USB1 (394 CLEAR) 10/24 - KIT CLEAR |  |  |  | 1 |  | 119480-2ND BAL ROWC 1ST | 395 | 11/7 10D | NL | ROWC | DEPANEL |  |  | 10/30 - BOT 8:00 10/31 - TOP 10:30 11/2 - AOI 1:00 | 43 | 133 | 1B 1T | 5 | 1975 | FEDEX P | Pfeiffer Vacuum, Inc. |  | REC'D 2 WRONG PARTS OF U37 11/1 - HALTED JOB TO RUN NEARLY LATE PINK JOBS | DOC REL 10/20 | 2023-10-19 | 11684.1 | PREV BUILD L1; JOB NEEDS 1.5 WEEKS; LF | 2023-11-07 | 2 | 2023-10-30 | 20
2023-11-06 |  | 10/30 - AWT PART CONF #26 (D15...) THAN SMT CLEAR 10/30 - KIT CLEAR |  |  | 1 |  |  | 121364 NEW | 20 | 11/6 5D | NL | X | #82 (BT1) SMT DNI #71 (j12, j13) THT DNI MONTH DATE LABEL DEPANEL |  |  | 10/31 - TOP 12:00 10/30 - BOT 2:30 11/1 - AOI 8:00 | 101 | 467 | 2B 1T | 61 | 1220 | UPS RED | DE Design Works |  |  | DOC REL 10/27 | 2023-10-30 | 4632 | LF; TOP SIDE 1ST | 2023-11-06 | 2 | 2023-10-31 | 6.5
2023-11-06 |  | 10/19 - SMT CLEAR 10/23 - KIT CLEAR |  |  | 1 |  |  | 119482-2ND BAL RONC 1ST | 395 | 11/6 10D | NL | RONC | LABEL ON BAG DEPANEL 10/25 - ISSUE W PART @ "C1,C2,C13" SEE HISTORY |  |  | 10/24 - BOT 8:00 10/24 - TOP 10/24 - AOI 2:00 | 9 | 20 | 1B 1T | 11 | 4345 | FEDEX P | Pfeiffer Vacuum, Inc. |  | 10/25 - USED WRONG PART (EPOXY) ON "C1, C2, C13" (CGA2B3X7R1H104K050BD IS INCORRECT - BB IS CORRECT | DOC REL 10/20 | 2023-10-19 | 3950 | BOT 1ST; PREV BUILD L1; JOB NEEDS 1.5 WEEKS; LF | 2023-11-06 | 2 | 2023-10-24 | 6
2023-11-03 |  | 11/1 - KIT CLEAR | [5 empty] | 120633-1ST RWK | 2 | 11/3 3D |  | - | RWK: All MAX14430EAEE chips will need to be swapped out with SI8645BA-B-IU chips |  |  | 11/1 - IN BACK | 0 | 0 | - | 17 | 34 | FEDEX | HRL Laboratories |  |  | DOC REL 11/1 | 2023-11-01 | 1012 | PAID RWK
2023-11-03 |  | 9/18 - WILL CLEAR SOON 9/27 - SHORT #56 (U8..) DUE 10/23 10/23 - KIT CLEAR |  |  |  | 1 |  | 119568 NEW | 25 | 11/3 9D | NN | X | OK TO RUN TOP SIDE ONLY DNI D4, D24, D25, D26 DEPANEL ***NUT & O-RING FROM "P7" REMOVED FOR WASH - NEED TO RE-INSTALL @ SHIPPING - PARTS ARE ATTACHED TO THE FOLDER |  |  | 10/23 - TOP 10:30 10/24 - TOP 1:00 10/28 - AOI | 118 | 395 | 2B 2T | 11 | 275 | FEDEX GND | Bridge Diagnostics, Inc. |  | 10/23 - FA COMPLETE; ON HOLD FOR B119482 10/31 - #15 (c67) CGA3E2X7R1H682K080AD is Epoxy Mounting |  | 2023-09-27 | 3121 | S/U TOP SIDE ONLY; LF | 2023-11-03 | 2 | 2023-10-25
2023-11-03 |  | 10/25 - SHOULD CLEAR 10/26 - PROG REQUESTED 10/25 10/27 - SHORT 3PCS OF D9 10/30 - KIT CLEAR |  |  | 1 |  |  | 121284 NEW | 30 | 11/3 5D | NL | X | NO ECO PROVIDED |  |  | 10/31 - TOP 8:00 10/31 - AOI 12:00 | 72 | 301 | 2T | 18 | 540 | FEDEX 2DAY | Rocky Research |  | 10/27 - DAY 1 10/30 (ANNE) 10/31 - REFLOW LINE 1 WORKING IMPROPERLY (POWER OUTAGE DMG/ISSUES) | DOC REL 10/24 | 2023-10-26 | 3546.3 | LF; TOP SIDE ONLY | 2023-11-03 | 1 | 2023-10-31 | 4
2023-11-03 |  | 10/24 - AWT PART CONF & SHORT #19 (U27) 10/26 - SHORT ATTRITION 10/26 - KIT CLEAR |  |  |  |  | 1 | 120927 NEW | 10 | 11/3 11/2 5D | NL | X | DNI PRESS FIT (P1-P6) DNI U27 NO STAMPS/LABELS PRESS FIT NO FLUX ON BOARD DEPANEL & KEEP 1 FRAME |  |  | 10/31 - BOT 9:00 10/31 - TOP 12:00 11/1 - AOI 1:00 | 71 | 1010 | 1B 1T | 29 | 290 | FEDEX P | John Hopkins University Applied Physics Lab |  | 11/2 - AWAITING CUST REPLY ABOUT PRESS FIT ISSUE | DOC REL 10/10 | 10/24 | 7090 | BOT 1ST; A LOT OF 201s; LF | 2023-11-02 | 2 | 2023-10-31 | 8
2023-11-03 |  | 10/20 - AWT PART CONF (#39, #40 & #41) 10/20 - KIT CLEAR |  |  |  |  | 2 | 117944 LEAD - MONITOR REFLOW RONC 108431 114305 | 40 | 11/3 10D | NL | RONC | *** QUALITY ALERT *** DO NOT HAVE EXCESSIVE INSIDE P5 MONTH DATE LABEL |  |  | 10/26 - AOI | 106 | 341 | 1B 2T | 10 | 400 | UPS 3DAY | Coastal Designs, LLC |  |  | LAN REL 10/17 | 2023-10-20 | 5732.8 | PREV BUILD L1; BOT 1ST; R | 2023-11-03 | 2
2023-11-03 |  | 10/26 - SHORT ATTRITION #56 (R21, R23) 10/26 - KIT CLEAR, BUT SHORT ATTRITION |  |  | 1 |  |  | 121472 NEW | 70 | 11/3 11/2 5D | NL | X | WILL CALL 11/3 @4PM CofC REQUIREMENTS DEPANEL |  |  | 10/30 - BOT 6:00 10/30 - TOP 10/31 - AOI 6:30 | 75 | 143 | 1B 1T | 11 | 770 | UPS RED | Scalvy Inc |  | 10/30 - POWER OUTAGE DURING REFLOW | DOC REL 10/24 | 2023-10-26 | 3656.3 | R; BOT 1ST | 2023-11-03 | 2 | 2023-10-30 | 8.5
2023-11-02 |  | 10/25 - 10/26 - EXPECTED CLEAR DATE 10/25 - SMT CLEAR 10/26 - KIT CLEAR |  |  |  |  | 2 | 121432 ROWC 118749 | 100 | 11/2 5D | NL | ROWC | MECH ASSY W/ THERMAL PASTE REQ DEPANEL |  |  | 10/28 - TOP 10/28 - AOI | 29 | 59 | 1T | 35 | 3500 | FEDEX P | Industrialex Manufacturing |  |  | DOC REL 10/24 | 2023-10-24 | 4975 | PREV BUILD L1; LF | 2023-11-02 | 2 | 2023-10-31
2023-11-02 |  | 10/19 - MAY CLEAR DATE 10/19 - KIT CLEAR |  |  |  | 1 |  | 120790 NEW | 4 | 11/2 10D | NL | X | MOD: CUT TRACE BETWEEN VIA & U4 P3; VERIFY R38 NOT INSTALLED; USING WIRE 51, CONNECT LEAD BETWEEN R64 & U4 PIN 4; CONNECT R38 RIGHT PAD TO U4 PIN 3 USING WIRE 51 INSTALL C35 CAPS (52) BETWEEN TERMINAL E25 & SOLDER LUG 53 DEPANEL |  |  | 10/23 - BOT 9:00 10/23 - TOP 10/24 - AOI 8:00 | 26 | 102 | 1B 1T | 13 | 52 | UPS 2ND DAY | Crane Aerospace |  | 10/23 - MOD DONE IN BACK AFTER SMT RUNS | NO DOC. | 2023-10-18 | 2395.92 | BOT 1ST; LF | 2023-11-02 | 2 | 2023-10-23 | 5
2023-11-01 |  | 10/26 - MAY CLEAR DATE 10/26 - KIT CLEAR |  |  |  |  | 1 | 121504 NEW | 21 | 11/1 10/31 3D | NN | X | *** 3 DAY TURN *** DEPANEL |  |  | 10/26 - BOT 2:00 10/27 - TOP 10/28 - AOI | 108 | 435 | 2B 2T | 0 | 0 | FEDEX P | Ocean Aero, Inc. |  | customer sent paste files late | DOC REL 10/20 | 10/20 | 8821.05 | X; LF | 2023-11-01 | 2 | 2023-10-27
2023-10-31 |  | 11/1 - PCB DUE; NO DATE FOR #15 (U5) 10/24 - KIT CLEAR |  |  |  |  | 1 | 121232 NEW | 100 | 10/31 5D | NL | X | MARKING REQ DEPANEL |  |  | 10/28 - TOP 10/30 - BOT 8:00 10/30 - AOI 3:00 | 43 | 155 | 1B 1T | 0 | 0 | FEDEX STAND | Pivot International |  | MAY HAVE XTRA TIME 10/30 - POWER OUTAGE DURING REFLOW | DOC REL 10/20 | 2023-10-20 | 4210 | TOP 1ST; LF | 2023-10-31 | 2 | 2023-10-28
2023-10-31 |  | 10/24 - KIT CLEAR |  |  | 1 |  |  | 120096-2ND RONC 1ST | 13 | 10/31 5D | RT | RONC | CLASS 3 DEPANEL |  |  | 10/27 - BOT 8:00 10/28 - TOP 10/28 - AOI | 51 | 475 | 1B 1T | 4 | 52 | UPS GND | Diversified Supply |  |  | DOC REL 10/24 | 2023-10-24 | 3737.5 | BOT 1ST; LF; PREV BUILD L1 | 2023-10-31 | 2 | 2023-10-27
2023-10-31 |  | 10/23 - EXPECTED CLEAR WEEK 10/31 - PCB DUE 10/24 - KIT CLEAR |  |  |  | 2 |  | 121408 NEW | 50 | 10/31 5D | NL | X | LOAD J7 ON BOT SIDE MARK REVISION DEPANEL |  |  | 10/27 - AOI 7:00 | 47 | 57 | 1B 1T | 15 | 750 | FEDEX P | HunterLab |  |  | DOC REL 10/20 | 2023-10-20 | 1652.5 | BOT 1ST; LF | 2023-10-31 | 2
2023-10-30 |  | 10/9 - SHORT C2 DUE 10/20 - KIT CLEAR |  |  | 1 |  |  | 121252-3BAL NEW | 40 | 10/30 5D | RL | X | MIX POP - 10 BOARDS W/ SEAF-50-05.0-S-08-2-A-K-TR BALANCE (40 BOARDS) W/ SEAF-50-07.5-S-08-2-A-K-TR |  |  | 10/23 - TOP 9:30 10/23 - AOI 2:00 | 15 | 452 | 1B 1T | 0 | 0 | FEDEX P | Forza Ametek |  | 10/12 - BOT SIDE COMPLETE ship date set 10/27 (ANNE) | DOC REL 10/9 | 2023-10-09 | 8474.5 | TOP SIDE DONE; L1; LF | 2023-10-27 | 1 | 2023-10-23
2023-10-30 |  | 10/17 - EXPECT CLEAR DATE 10/17 - KIT CLEAR |  |  |  | 1 |  | 121006 NEW | 36 | 10/30 10D | NN | X | PCB SHARED W/ B121007 QR CODE LABEL - SEE FILE "ENG.STD.2000" ON "T" DRIVE CABLE CUT & ATTACH REQ (ECO) |  |  | 10/19 - BOT 10:00 10/19 - TOP 2:00 10/20 - AOI 2:00 | 66 | 296 | 2B 2T | 3 | 108 | FEDEX 2DAY | Area 1 |  |  | DOC REL 10/10 | 10/11 | 3708 |  | 2023-10-30 | 2 | 2023-10-19 | 10
2023-10-30 |  | 10/23 - KIT CLEAR |  |  |  |  | 1 | 121007 ROWC 121006 | 34 | 10/30 5D | NN | ROWC | CABLE/MOD REQUIRED QR CODE LABEL |  |  | 10/24 - BOT 1:00 | 66 | 296 | 2B 2T | 4 | 136 | FEDEX 2DAY | Area 1 |  |  | DOC REL 10/10 | 10/23 | 4155.84 | Can use same program/setup list as B121006. Only difference is THT; PREV BUILD L2; R | 2023-10-30 | 2 | 2023-10-24
2023-10-30 |  | 7/31 - KIT CLEAR |  |  |  | 1 |  | 119129-2 BAL NEW | 1 | 8/14 10D |  | X | SHORT U31 CLASS 3 |  |  | 8/4 - BOT 2:00 8/8 - TOP 9:00 8/10 - AOI 9:30 | 18 | 400 | 120 | 18 | 18 | UPS ORG | COASTAL DESIGNS |  |  |  | 2023-07-31 | 121.59 |  | 2023-08-14
2023-10-27 |  | 10/9 OR 10/10 - WILL CLEAR 10/12 - NOT CLEAR, SKIP MISSING PART 10/13 - KIT CLEAR |  |  | 1 |  |  | 120533 NEW | 7 | 10/27 10D | NN | X | DNI J3 CARE REQUIRED FOR U18 & U22 DURING REFLOW |  |  | 10/19 - BOT 9:00 10/19 - ON/OFF HOLD 10/20 - BOT 6:00 10/20 - TOP 8:00 10/20 - AOI 2:00 | 128 | 699 | 2B 2T | 8 | 56 | FEDEX P | Integrated Consultants |  | U38 MARKING INCORRECTLY LABELED AS U3 ON PCB 10/19 - J3 PART DOESN'T FIT PAD (DNI) |  | 2023-09-27 | 4725.55 | SPOT CHECKING REQUIRED FOR U18 & U22 AFTER REFLOW | 2023-10-27 | 2 | 2023-10-19 | 8
2023-10-25 |  | 10/4 - SHORT U7; SHOULD CLEAR SOON 10/6 - KIT CLEAR |  |  |  |  | 2 | 120820 NEW | 50 | 10/25 10/19 10/13 5D | NN | X | DNI U7 |  |  | 10/10 - BOT 10:30 10/11 - TOP 8:30 10/16 - AOI 7:30 | 53 | 224 | 1B 2T | 18 | 900 | FEDEX 2D | LMA Technologies, LLC |  | 1.5 HOURS LAST BATCH OF TOP SIDE 3 HOURS INIT TOP SIDE 7.5 HOURS OF BOTTOM SIDE PARTS UNABLE TO STAY ON PADS (SOLDER ISSUE) INCOMPLETE PROGRAM; RESENDING TO NAM TO REDO |  | 2023-09-27 | 4138 |  | 2023-10-19 | 2 | 2023-10-16 | 12
2023-10-24 |  | 10/5 - KIT CLEAR |  |  |  | 1 |  | 120938-2BAL NEW | 2 | 10/19 10D | NN | X | DEPANEL |  |  | 10/13 - BOT 12:00 10/17 - TOP 9:00 10/18 - AOI 12:30 | 74 | 190 | 2B 2T | 0 | 0 | FEDEX P | Rhaeos |  | TOO MANY SMALL PARTS FOR L2 TO HANDLE |  | 2023-09-26 | 4397 |  | 2023-10-19 | 2 | 2023-10-16 | 18
2023-10-23 |  | 9/13 - WILL CLEAR SOON 9/28 - PCB ETA 9/29 - KIT CLEAR |  |  |  |  | 1 | 120297 NEW | 12 | 10/20 15D | NN | X | 10/20 - DNI J10 & J6 C132 HIGH ENOUGH TO BE BENT OVER T3 *** REFLOW 1 U69 POPULATED BOARD ONLY BEFORE PROCEEDING *** J6 BTD #50 (U11) Hl-2130 INSTALLED ON 1 BOARD ONLY 5 OF 12 U69 INSTALLED 7 OF 12 U69 DNI LABEL CORRECTLY DEPANEL |  |  | 10/16 - BOT 10:30 10/17 - TOP 10:00 10/18 - BOT 5:00 10/18 - TOP 9:00 10/18 - AOI 11:00 | 148 | 1339 | 2B 2T | 23 | 276 | FEDEX P | Integrated Consultants |  | 10/20 - HOLD SHIPMENT DUE TO AWATING CUST RESPONSE TO CLARIFY A QUESTION ABOUT A PART 10/17 - BOARDS 0006 - 0007 BOT COMP U69 (BOT SIDE) CAN ONLY BE REFLOWED ONCE |  | 2023-09-14 | 9608.64 | LABEL PRIOR OR DURING SMT RUN | 2023-10-20 | 3 | 2023-10-16 | 18
2023-10-23 |  | 10/3 - KIT CLEAR |  |  |  | 1-XFER | 1 | 114862-3BAL ROWC 103336 | 5 | 10/18 10/17 10D | NL | ROWC | NO SOLDER PASTE ON MP4 & MP5 PADS DEPANEL & SAND |  |  | 10/5 - TOP 9:00 10/11 - TOP DONE 10/12 - BOT 5:00 10/13 - AOI 3:00 | 69 | 229 | 2B 2T | 4 | 20 | FEDEX P | Scientific Research Corporation |  | MOVING TO L3 WEDS AFTRNOON TOP COMP ETA EOD TUES 10/10 BOT COMP ETA THURS 10/12 EXPECTED SMT RUNTIME 3 - 5 DAYS |  | 2023-10-03 | 19305 |  | 2023-10-17 | 2 | 2023-10-05 | 50
2023-10-20 |  | 10/9 - SHORT C2 DUE 10/13 - KIT CLEAR | [5 empty] | 121252-2PAR NEW | 5 | 10/20 5D | RL | X | MIX POP - 10 BOARDS W/ SEAF-50-05.0-S-08-2-A-K-TR BALANCE (40 BOARDS) W/ SEAF-50-07.5-S-08-2-A-K-TR |  |  | 10/17 - TOP 6:00 10/17 - AOI 7:00 | 15 | 452 | 1B 1T | 0 | 0 | FEDEX P | Forza Ametek |  |  | DOC REL 10/9 | 2023-10-09 | 8474.5 |  | 2023-10-20 | 2 | 2023-10-18 | 1
2023-10-20 |  | 10/6 - KIT CLEAR |  |  |  |  | 1 | 116310 NEW | 200 | 10/20 10D | NL | X | INTERNATIONAL SHIPMENT CLASS 3 |  |  | 10/18 - TOP 2:00 10/18 - AOI 5:00 | 1 | 1 | 1T | 2 | 400 | FEDEX INT P1 | Horiba Instruments |  | SMT WILL RUN 1 OF THE THT PARTS |  | 2023-10-06 | 2500 | DEPANEL BEFORE SMT RUN | 2023-10-20 | 1 | 2023-10-19 | 3
2023-10-20 |  | KIT CLEAR |  |  | 1 |  |  | 120970 NEW | 20 | 10/20 5D | NN |  | BE READY TO SHIP SOONER THAN 10/20 IF POSSIBLE DEPANEL |  |  | 10/16 - TOP 7:30 10/16 - AOI 10:30 | 52 | 206 | 2T | 55 | 1100 | FEDEX GND | Handix Scientific, LLC |  |  | DOC REL 9/22 | 2023-10-13 | 3674 |  | 2023-10-20 | 1 | 2023-10-16 | 3
2023-10-19 |  | 9/26 - WILL CLEAR THIS WEEK 10/5 - KIT CLEAR |  |  | 1 |  |  | 119594 NEW | 25 | 10/20 10/19 10D | NN | X | DEPANEL |  |  | 10/13 - BOT 7:00 10/13 - TOP 10:00 10/13 - AOI 2:30 | 98 | 522 | 2B 2T | 37 | 925 | UPS GND | Jefferson Labs |  | L1 ON VACA, XFER TO L2 RUNNER MONDAY |  | 2023-09-14 | 4124.5 |  | 2023-10-19 | 2 | 2023-10-13 | 7.5
2023-10-19 |  | 10/5 - KIT CLEAR |  |  |  | 1 |  | 120938-1PAR NEW | 98 | 10/19 10D | NN | X | DEPANEL |  |  | 10/13 - BOT 12:00 10/17 - TOP 9:00 10/18 - AOI 12:30 | 74 | 190 | 2B 2T | 0 | 0 | FEDEX P | Rhaeos |  | TOO MANY SMALL PARTS FOR L2 TO HANDLE |  | 2023-09-26 | 4397 |  | 2023-10-19 | 2 | 2023-10-16 | 18
2023-10-19 |  | 10/2 - PCB DUE 10/5 - KIT CLEAR 10/6 - ON HOLD DUE TO LACK OF MOUSEBITES 10/11 - KIT CLEAR W/ NEW PCBS |  |  |  |  | 1 | 120969 NEW | 150 | 10/19 10/12 5D |  | X | *** INTERNATIONAL SHIP *** STENCIL ORDER AFTER FINAL ARRY HAS ARRIVED BARCODE LABEL REQUIRED SPECIAL CofC REQUIRED ***DEPANEL - NO MOUSE BITES - NEED TO CUT AND SAND |  |  | 10/18 - BOT 11:00 10/18 - TOP 10/18 - AOI 2:00 | 3 | 3 | 1B 1T | 0 | 0 | UPS WORLD WIDE | Intuitive Surgical Sarl |  | *EXTRA DAY FOR DEPANEL |  | 2023-10-06 | 1572.5 |  | 2023-10-19 | 2 | 2023-10-18 | 3
2023-10-19 |  | 10/4 - SHORT 16 PIECES OF #41 (U53) 10/6 - KIT CLEAR |  |  | 1 |  |  | 120758 ROWC 118253 | 40 | 10/19 10D | RT | ROWC | MECH ASSY REQ DEPANEL |  |  | 10/11 - BOT 8:00 10/11 - TOP 12:00 10/12 - AOI 8:30 | 89 | 653 | 1B 2T | 56 | 2240 | UPS RED | Activ Surgical |  | EXPECTED SMT RUNTIME 1+ DAYS *DAY 1 IS 10/6 PER ANNE |  | 2023-10-03 | 9330 |  | 2023-10-19 | 2 | 2023-10-11 | 10
2023-10-18 |  | BACK | [5 empty] | 120864-RMA RMA | 80 | 10/18 5D |  | X | U$3 ROTATE PART DEPANEL |  |  | 10/11 - KIT REC'D |  |  |  | 1 | 80 | UPS RED | KPM ANALYTICS
2023-10-18 |  | 9/29 - PCB DUE 9/29 - KIT CLEAR | [5 empty] | 120864-1BAL NEW | 20 | 10/18 10/6 5D | NN |  | U$3 ROTATE PART DEPANEL |  |  | 10/2 - TOP 10/3 - AOI 9:00 | 37 | 103 | 2T | 1 | 20 | UPS RED | KPM ANALYTICS |  | REFLOW BLEW PARTS OFF THE BOARD; BOARDS REQ RWK |  | 2023-09-23 | 3310
2023-10-18 |  | 10/3 - KIT CLEAR |  |  |  | 1-XFER | 1 | 114862-2PAR ROWC 103336 | 195 | 10/18 10/17 10D | NL | ROWC | NO SOLDER PASTE ON MP4 & MP5 PADS DEPANEL & SAND |  |  | 10/5 - TOP 9:00 10/11 - TOP DONE 10/12 - BOT 5:00 10/13 - AOI 3:00 | 69 | 229 | 2B 2T | 4 | 780 | FEDEX P | Scientific Research Corporation |  | MOVING TO L3 WEDS AFTRNOON TOP COMP ETA EOD TUES 10/10 BOT COMP ETA THURS 10/12 EXPECTED SMT RUNTIME 3 - 5 DAYS |  | 2023-10-03 | 19305 |  | 2023-10-17 | 2 | 2023-10-05 | 50
2023-10-17 |  | 10/3 - KIT CLEAR |  |  |  | 1-XFER | 1 | 114862-1PAR ROWC 103336 | 250 | 10/17 10D | NL | ROWC | NO SOLDER PASTE ON MP4 & MP5 PADS DEPANEL & SAND |  |  | 10/5 - TOP 9:00 10/11 - TOP DONE 10/12 - BOT 5:00 10/13 - AOI 3:00 | 69 | 229 | 2B 2T | 4 | 1000 | FEDEX P | Scientific Research Corporation |  | MOVING TO L3 WEDS AFTRNOON TOP COMP ETA EOD TUES 10/10 BOT COMP ETA THURS 10/12 EXPECTED SMT RUNTIME 3 - 5 DAYS |  | 2023-10-03 | 19305 | 2023-10-17 | 2 | 2023-10-05 | 50 | 3
2023-10-17 |  | 10/3 - KIT CLEAR |  |  |  | 1 |  | 117366 NEW | 100 | 10/17 10D | - | X | BTD #7 (R1) |  |  | 10/13 - TOP 7:00 10/13 - AOI 9:00 | 7 | 13 |  | 2 | 200 | FEDEX GRD | LMA Technologies, LLC |  |  |  | 2023-10-03 | 1884 | 2023-10-17 | 1 | 2023-10-13 | 2 | 1
2023-10-16 |  | 10/9 - SHORT C2 DUE 10/9 - KIT CLEAR |  |  | 1 |  |  | 121252-1PAR NEW | 5 | 10/16 5D | RL | X | MIX POP - 10 BOARDS W/ SEAF-50-05.0-S-08-2-A-K-TR BALANCE (40 BOARDS) W/ SEAF-50-07.5-S-08-2-A-K-TR |  |  | 10/12 - TOP 10:30 10/12 - BOT 2:00 10/13 - AOI 7:00 | 15 | 452 | 1B 1T | 0 | 0 | FEDEX P | Forza Ametek |  |  |  | 2023-10-09 | 8474.5 | 2023-10-16 | 1 | 2023-10-12 | 5 | 1
2023-10-16 | [7 empty] | 119849-RMA RMA | 49 | 10/16 5D |  |  | RMA (REMAINING BAL) |  |  | BACK | 0 | 0 | 0 | 1 | 49 | FEDEX P | Industrialex Manufacturing |  |  |  | 2023-10-02 | 1030.8 |  |  |  |  | 1
2023-10-16 |  | 10/3 - KIT CLEAR |  |  |  | 1 |  | 120284-2par NEW | 20 | 10/16 10D | RT | X | 10 DAY TURN JOB |  |  | 10/5 - TOP 11:00 10/5 - BOT 10/5 - AOI 2:00 | 58 | 117 |  | 16 | 320 | UPS RED | Alliance Technology, LLC. |  |  |  | 2023-10-03 | 1031.8 | 2023-10-16 |  |  | 3 | 2
2023-10-16 |  | 10/10 - WILL CLEAR DATE |  |  | 1 |  |  | 121051 NEW | 10 | 10/16 5D | NN | X | STAMPS ONLY ON TOP SIDE MASK MOUNTING HOLES TO ENSURE THEY'RE SOLDER FREE RTV REQUIRED DOW #3145 |  |  | 10/12 - TOP 8:30 10/12 - AOI 10:30 | 32 | 17 | 2T | 129 | 1290 | FEDEX P | Steris |  |  |  | 2023-10-05 | 466.7 | 2023-10-16 | 1 | 2023-10-12 |  | 2
2023-10-16 |  | 9/18 - AWT PART CONF 9/18 - KIT CLEAR |  |  | 1 |  |  | 120664 NEW | 100 | 10/16 20D | NN | ROWC | POST BAKE IF ASSY'S ARE WASHED DEPANEL |  |  | 10/6 - BOT 9:00 10/6 - BOT DONE 10/9 - TOP 8:00 10/10 - AOI 11:00 | 110 | 767 | 2B 2T | 35 | 3500 | FEDEX GND | GL Communications |  | PROGRAM BALANCE ISSUE NOZZLE ISSUE PRINTER ISSUE SMT EXPECTED RUNTIME OF 3+ DAYS |  |  | 15060 | 2023-10-16 | 2 | 2023-10-06 | 36 | 4
2023-10-13 |  | 9/28 - SHORTAGES DUE 10/6 - KIT CLEAR |  |  | 1 |  |  | 118067-2nd BAL NEW | 12 | 10/13 5D | NL | X | REM BAL OF SPLIT JOB DEPANEL |  |  | 10/6 - BOT 2:00 10/6 - TOP 4:00 10/7 - AOI 8:00 | 35 | 602 | 93 | 35 | 420 | UPS RED | Tennessee Valley Authority |  |  |  | 2023-09-27 | 2167.8943 | 2023-10-13 |  |  | 4.5 | 2
2023-10-13 |  | 10/6 - EXPECTED CLEAR DATE OR SOONER 10/2 - KIT CLEAR |  |  | 1 |  |  | 120287 NEW | 50 | 10/13 10D |  | X | DEPANEL |  |  | 10/11 - BOT 6:00 10/11 - TOP 10/11 - AOI 8:00 | 6 | 36 |  | 16 | 800 | FEDEX P | Diligent Robotics |  |  |  | 2023-09-28 | 2738.5 | 2023-10-13 | 1 |  | 2 | 1
2023-10-13 |  | 9/14 - AWT PART CONF 9/15 - KIT CLEAR |  |  |  | 1 |  | 119829 RONC 113661 | 200 | 10/16 20D | RT | RONC | DEPANEL |  |  | 10/11 - TOP 11:00 10/12 - AOI 11:00 | 27 | 43 | 2T | 0 | 0 | FEDEX P | Industrialex Manufacturing |  |  |  | 2023-10-04 | 2580 | 2023-10-16 | 1 | 2023-10-11 | 6 | 2
2023-10-12 |  | 9/27 - PCBS RECEIVED & AWT COUNT / BAKE 9/28 - KIT CLEAR | [5 empty] | 120825 ROWC 1ST BATCH | 50 | 10/12 10D | RT | X | Serial number: start at HA-2302-0196 |  |  | 10/7 - BOT 6:00 10/7 - TOP 10/7 - AOI 12:00 | 2 | 205 | 53 | 2 | 100 | UPS GRD | Churchill Navigation dba Shotover Systems Inc |  |  |  | 2023-09-27 | 3583 | 2023-10-12 |  |  | 6 | 1
2023-10-12 |  | 10/5 - SHORT #24 DUE 10/5 - KIT CLEAR |  |  |  |  | 1 | 120932 NEW | 15 | 10/12 5D | NL | X | BARCODE LABEL REQ DEPANEL |  |  | 10/10 - BOT 6:00 10/10 - TOP 7:30 10/10 - AOI 10:00 | 54 | 170 | 1B 1T | 44 | 660 | FEDEX P | Nextern Inc. |  |  |  | 2023-10-04 | 2990.25 | 2023-10-12 | 1 | 2023-10-10 | 4 | 2
2023-10-12 |  | 9/13 - WILL CLEAR SOON 10/5 - KIT CLEAR |  |  |  |  | 1 | 120351 ROWC 111470 | 100 | 10/12 10D 5D | NL | X | XRAY & SAVE IMAGES TRIM LEADS (0.1 INCH MAX) REV MARKING REQUIRED (SEE ECO) DEPANEL *PO STATES 10 DAY - TAD AGREED TO 5 DAY (PO WILL NOT BE REFLECTED) |  |  | 10/6 - TOP 11:30 10/9 - AOI 9:00 | 149 | 695 | 3T | 13 | 1300 | FEDEX P | Servomex Inc |  | *EXPECTED SMT RUNTIME OF 3-4 DAYS 10/9 - ESTIMATED COMPLETION DATE |  | 2023-09-14 | 26940 | 2023-10-12 | 3 | 2023-10-06 | 17 | 5
2023-10-11 |  | 9/29 - MAY CLEAR SOON 10/2 - KIT CLEAR |  |  | 1 |  |  | 118595 NEW | 100 | 10/11 7D | NN | X | DEPANEL |  |  | 10/10 - TOP 11:00 10/10 - BOT 3:00 10/10 - AOI 4:30 | 52 | 83 | 1B 2T | 0 | 0 | FEDEX P | Hip Science, LLC |  | DOUBLE CHECK U9 IS CORRECTLY PLACED INSIDE TAPE & REEL IC PART UPSIDE DOWN IN TAPE & REEL, REQUIRES RELOADING |  | 2023-09-25 | 1875 | 2023-10-11 | 2 | 2023-10-09 | 5.5 | 2
2023-10-11 |  | 9/27 - SHORT PCB 10/6 - PCB DUE 10/4 - KIT CLEAR |  |  |  |  | 1 | 120288 NEW | 50 | 10/11 5D |  | X | PROCESS CHANGE: JOB IS NOW NO CLEAN DEPANEL |  |  | 10/10 - BOT 10:00 10/10 - TOP 11:30 10/10 - AOI 12:30 | 5 | 6 |  | 1 | 50 | FEDEX P | Diligent Robotics |  |  |  | 2023-10-04 | 3900 | 2023-10-11 | 1 | 2023-10-10 | 2.5 | 1
2023-10-11 | [7 empty] | 119436-RMA BAL RMA | 42 | 10/11 1D |  |  | RMA (MIN SHIP IS 25 OF 49) DEPANEL |  |  | BACK | 4 | 0 | 0 | 4 | 168 | FEDEX P | Anderson Connectivity |  |  |  | 2023-10-04 | 0 | 2023-10-17 |  |  |  | 1
2023-10-11 |  | 9/28 - COULD CLEAR DATE 10/4 - KIT CLEAR |  |  | 1 |  |  | 120276 NEW | 6 | 10/11 5D | NN | X | J14 & J15 MAX ANGLE ALLOW +/- 3 DEGREES PRESS FIT DEPANEL |  |  | 10/7 - BOT 9:30 10/7 - TOP 12:00 10/9 - AOI 9:00 | 72 | 682 | 2B 2T | 20 | 120 | UPS RED | Neuralynx Inc |  |  |  | 2023-09-23 | 3955 | 2023-10-11 | 2 | 2023-10-07 | 8 | 3
2023-10-11 |  | 9/25 - PCB DUE 10/4 10/4 - KIT CLEAR |  |  |  |  | 1 | 120730 NEW | 5 | 10/11 5D | NN | X | U20: Do not wash. |  |  | 10/9 - BOT 9:00 10/9 - TOP 11:00 10/10 - AOI 6:00 | 105 | 607 | 2B 2T | 39 | 195 | FEDEX P | CACI |  |  |  | 2023-09-29 | 3423.75 | 2023-10-11 | 2 | 2023-10-09 | 9.5 | 4
2023-10-11 |  | 9/23 - SHORT PCB & AWT PART CONF #32 (K1, K2) 10/4 - KIT CLEAR |  |  |  |  | 1 | 120423 NEW | 26 | 10/11 5D | NN | X | X |  |  | 10/5 - TOP 6:00 10/5 - AOI 12:00 | 19 | 520 | 75 | 19 | 494 | FEDEX P | Draper Laboratory |  |  |  | 2023-09-23 | 5971.28 | 2023-10-11 |  |  |  | 1
2023-10-11 |  | 9/6 - KIT CLEAR |  |  | 1 |  |  | 118628-2 PAR ROWC 1ST | 750 | 10/11 10/10 10/4 20D | NL | X | SHIP DATE 10/04; W/ 100 BOARDS TO SHIP 9/18 ***MUST LOG ALL NON-CONFORMANCES BY SERIAL NUMBER PER ECO NOTE #5*** ---SEVERAL PAST QUALITY ISSUES - PLEASE TIGHTEN UP QA 100%--- **QUALITY ALERT - LAST RUN MISSING "R124" - SEE ECO #4 |  |  | 9/11 - BOT 10:00 9/18 - CONTINUE 9/22 - CONTINUE 9/23 - TOP 9/25 - AOI | 3 | 155 | 30 | 3 | 2250 | UPS GND | ICC,Inc |  | 9/11 - 100 COMPLETE 9/12 - STOPPED BOT (HALF COMPLETE) TO RUN OTHER JOBS 9/14 - WILL RUN IN-BETWEEN OTHER JOBS 9/18 - RESTARTED JOB ON LINE 1 |  | 2023-09-06 | 19110 | 2023-10-10 |  |  |  | 1
2023-10-10 |  | 9/6 - KIT CLEAR |  |  | 1 |  |  | 118628-2 PAR ROWC 1ST | 800 | 10/10 10/4 20D | NL | X | SHIP DATE 10/04; W/ 100 BOARDS TO SHIP 9/18 ***MUST LOG ALL NON-CONFORMANCES BY SERIAL NUMBER PER ECO NOTE #5*** ---SEVERAL PAST QUALITY ISSUES - PLEASE TIGHTEN UP QA 100%--- **QUALITY ALERT - LAST RUN MISSING "R124" - SEE ECO #4 |  |  | 9/11 - BOT 10:00 9/18 - CONTINUE 9/22 - CONTINUE 9/23 - TOP 9/25 - AOI | 3 | 155 | 30 | 3 | 2400 | UPS GND | ICC,Inc |  | 9/11 - 100 COMPLETE 9/12 - STOPPED BOT (HALF COMPLETE) TO RUN OTHER JOBS 9/14 - WILL RUN IN-BETWEEN OTHER JOBS 9/18 - RESTARTED JOB ON LINE 1 |  | 2023-09-06 | 20384 | 2023-10-10 |  |  |  | 1
2023-10-10 |  | 10/4 - SHOULD CLEAR SOON 10/5 - KIT CLEAR |  |  |  |  | 1 | 121088 ROWC 107608 | 5 | 10/10 3D | NN | X | *** 3 DAY TURN *** P/N IGDQ60R035D1A REQS 24 HRS BAKE MASK ANY LOCATIONS MARKED "NO STUFF" CofC REQUIREMENTS |  |  | 10/6 - TOP 5:00 10/6 - BOT 9:00 10/6 - AOI 11:30 | 5 | 699 | 98 | 5 | 25 | WILL CALL | ROYAL CIRCUITS SOLUTIONS INC |  | TOP 1ST 3pm Will Call on ship date (10/10) |  | 2023-10-04 | 6144.7 | 2023-10-10 |  |  |  | 1
2023-10-10 |  | 9/28 - SHORTAGES DUE 10/2 - KIT CLEAR |  |  | 1 |  |  | 118067-2nd PAR NEW | 100 | 10/10 10/9 5D | NL | X | PARTIAL SHIPMENT 100 of 112 DEPANEL |  |  | 10/4 - BOT 11:00 10/5 - TOP 9:30 10/6 - AOI 8:00 | 35 | 602 | 93 | 35 | 3500 | UPS RED | Tennessee Valley Authority |  | NOZZLE ISSUE PRINTER ISSUE 10/5 - 70 COMPLETE |  | 2023-09-27 | 4261 | 2023-10-09 |  |  |  | 2
2023-10-09 |  | 10/3 - KIT CLEAR |  |  |  | 1 |  | 120284-1par NEW | 30 | 10/9 5D | RT | X | PARTIAL EXPEDITE 30 OF 100 DEPANEL |  |  | 10/4 - TOP 11:00 10/5 - BOT 10/5 - AOI 2:00 | 20 | 117 | 58 | 20 | 600 | UPS RED | Alliance Technology, LLC. |  |  |  | 2023-10-03 | 4047.7 | 2023-10-09 |  |  |  | 2
[21 empty] | 0 | [11 empty] | 1
[21 empty] | 0 | [11 empty] | 1
[21 empty] | 0 | [11 empty] | 1
[21 empty] | 0 | [11 empty] | 1
[21 empty] | 0 | [11 empty] | 1
[21 empty] | 0 | [11 empty] | 1
[21 empty] | 0 | [11 empty] | 1
[21 empty] | 0 | [11 empty] | 1
[21 empty] | 0 | [11 empty] | 1
[21 empty] | 0 | [11 empty] | 1
[21 empty] | 0 | [11 empty] | 1
[21 empty] | 0 | [11 empty] | 1
[21 empty] | 0 | [11 empty] | 1
[21 empty] | 0 | [11 empty] | 1
[21 empty] | 0 | [11 empty] | 1
[21 empty] | 0 | [11 empty] | 1
[21 empty] | 0 | [11 empty] | 1
[21 empty] | 0 | [11 empty] | 1
[21 empty] | 0 | [11 empty] | 1
[21 empty] | 0 | [11 empty] | 1
[21 empty] | 0 | [11 empty] | 1
[21 empty] | 0 | [11 empty] | 1
[21 empty] | 0 | [11 empty] | 1
[21 empty] | 0 | [11 empty] | 1
[21 empty] | 0 | [11 empty] | 1
[21 empty] | 0 | [11 empty] | 1

## HISTORY 7.15.21 - 10.6.2023
|  | H I S T O R Y | [6 empty] | 7/15/2021 - 10/6/2024
DATE | BPP | SMT | JOB/REL |  | NOTES | TYPE | QTY | DUE | SHIP | MFG NOTES | STATUS | SMT | KIT CLEAR/ SHORTS | T/H | T/H EXT |  | RELEASE | NC/CLN | T 1ST | COUNT | CUST | ACTUAL (HRS)
2023-10-06 |  |  | 119436-RMA PAR |  |  | ROWC 1ST | 5 | 10/6 ??? | FEDEX P | RMA DEPANEL | BACK | THT ONLY |  | 4 | 20 |  | 2023-08-30 | C |  | X | Anderson Connectivity
2023-10-06 |  | L1 | 119577 R | NEED PROG |  | NEW | 145 | 10/6 10D | FEDEX P | DEPANEL | 10/3 - BOT 9:00 10/3 - TOP 1:30 10/4 - AOI 11:00 | 1B 1T 13/203 | 9/14 - WILL CLEAR SOON 9/22 - KIT CLEAR | 0 | 0 | X | 2023-09-14 | C |  | X | Torch Technologies | 10
2023-10-06 |  | L1 | 120864 NN | NEED PROG |  | NEW | 80 | 10/6 5D | UPS RED | DEPANEL | 10/2 - TOP 10/3 - AOI 9:00 | 2T 37/103 | 9/29 - PCB DUE 9/29 - KIT CLEAR | 1 | 100 |  | 2023-09-23 |  |  |  | KPM Analytics
2023-10-06 |  | L1 | 117371-3 PAR |  |  | NEW | 12 | 10/6 15D | UPS GND | DEPANEL NON-FLUSH J9 & J10 | 5/19 - BOT 11:00 5/19 - TOP 1:00 | 1B 1T 15/22 | 5/10 - KIT CLEAR | 18 | 216 |  | 5/11 | C |  |  | THORLABS
2023-10-06 |  |  | 117369-2 PAR |  |  | NEW | 12 | 10/6 15D | UPS GND | DEPANEL J9 HEIGHT REQUIREMENT | 7/29 - BOT 12:00 7/29 - TOP 1:00 7/29 - AOI 2:00 | 1B 1T 15/22 | 7/27 - KIT CLEAR | 19 | 228 |  | 2023-07-27 | C |  | X | THORLABS | 2
2023-10-06 |  | L3 | 119290 NN | NEED PROG |  | NEW | 50 | 10/6 10D | FEDEX P | DEPANEL SEE ECO FOR AFTERWASH PARTS SPECIAL LABEL REQ ON SHIPPING | 10/2 - BOT 10/3 - TOP 10/3 - AOI 2:00 | 1B/1T 106/296 | 9/18 - WILL CLEAR SOON 9/25 - PCBS DUE 9/22 - KIT CLEAR | 5 | 250 | X |  |  |  |  | Nextern Inc.
2023-10-06 |  | L1-2 | 119291 NN | NEED PROG | PROGRAM BALANCE ISSUE | NEW | 50 | 10/6 10D | FEDEX P | TRIM LEAD HEIGHT REQ DEPANEL & SAND SPECIAL LABEL REQ ON SHIPPING | 9/29 - TOP 11:30 9/29 - BOT 2:30 9/30 - AOI | 99/361 | 9/23 - KIT CLEAR | 12 | 600 | X | 2023-09-23 |  |  |  | Nextern Inc. | 8
2023-10-06 |  | L1-2 | 120528 R | NEED PROG |  | NEW | 98 | 10/6 5D | FEDEX P | DEPANEL | 10/2 - TOP 10/2 - AOI | 1T 25/56 | 9/20 - WILL CLEAR SOON 9/27 - AWT ARRAY FILE 9/29 - KIT CLEAR | 10 | 980 |  | 2023-09-27 |  |  |  | Protocol Insight LLC.
2023-10-06 |  | L2/L3 | 117094-3 BAL | MON 9/11 | 2 | ROWC 1ST BATCH | 400 | 10/6 10/2 20D | UPS GND | ***ICC MEDICAL - NEED EXCEL NON CONFORMANCE LOG*** DEPANEL REV MARKING REQ | 8/31 - BOT 2:00 9/7 - TOP 12:00 9/11 - AOI 12:00 | 2B 1T 24/126 | 9/19 - CN3 DUE 9/18 - KIT CLEAR | 4 | 1600 | X | 2023-08-21 | C | Y | X | ICC MEDICAL | 56
2023-10-06 |  | L2 | 120259 |  | PART ALIGNMENT ISSUES STENCIL CHANGED 3X *EXPECTED SMT RUNTIME OF 3-5 DAYS | RONC 110522 | 335 | 10/5 15D | FEDEX 2 DAY | REMOVE MIDDLE PIN OF J1 DEPANEL | 9/29 - BOT 8:00 10/2 - TOP 10/2 - AOI 11:00 | 1B 1T 18/97 | 9/14 - KIT CLEAR | 0 | 0 | X | 2023-09-14 | C |  | X | Radiation Detection Technologies, Inc. | 50
2023-10-05 |  | L1-2 | 118916 NN | NEED PROG |  | NEW | 5 | 10/5 5D | FEDEX P | DEPANEL THT HEIGHT REQ (ECO #6) MECH ASSY REQ (ECO #7) CofC REQUIRMENTS (ECO #8) | 9/30 - TOP 9/30 - AOI 10:00 | 48/251 | 8/25 - ALMOST SMT CLEAR 9/28 - KIT CLEAR | 126 | 630 |  | 2023-08-22 | C |  | X | Industrialex Manufacturing | 2
2023-10-05 |  | L1-4 | 120499 |  |  | RONC 103224 | 50 | 10/5 10D | FEDEX P | DEPANEL | AOI | 1T 6/125 | 9/13 - WILL CLEAR SOON 9/21 - KIT CLEAR | 17 | 850 |  | 2023-09-14 | C |  | X | Vela Technologies
2023-10-05 |  | L2 | 120259 |  | PART ALIGNMENT ISSUES STENCIL CHANGED 3X *EXPECTED SMT RUNTIME OF 3-5 DAYS | RONC 110522 | 865 | 10/5 15D | FEDEX 2 DAY | REMOVE MIDDLE PIN OF J1 DEPANEL | 9/29 - BOT 8:00 10/2 - TOP 10/2 - AOI 11:00 | 1B 1T 18/97 | 9/14 - KIT CLEAR | 0 | 0 | X | 2023-09-14 | C |  | X | Radiation Detection Technologies, Inc. | 50
2023-10-04 |  | L1-3 | 120636 R | NEED PROG |  | NEW | 40 | 10/4 5D | FEDEX P | DEPANEL | 9/28 - TOP 1:30 9/28 - AOI 3:00 | 1/2 | 9/19 - PCB DUE 9/27 - KIT CLEAR | 0 | 0 |  | 2023-09-14 | C |  | X | Toyon Research Corporation | 1.5
2023-10-04 |  | L1 | 121017 NN | NEED PROG |  | NEW | 2 | 10/4 3D | UPS RED | *** 3 DAY TURN *** DEPANEL | 9/30 - BOT 10:00 9/30 - TOP 1:00 | 2B 2T 84/830 | 9/29 - KIT CLEAR | 17 | 34 |  | 2023-09-29 |  |  |  | Delsys Inc.
2023-10-04 |  | L1 | 120701 R | NEED PROG |  | NEW | 6 | 10/4 5D | FEDEX 2 DAY | X | 9/29 - BOT 7:00 9/29 - AOI 11:30 | 54/634 | 9/26 - EXPECTED CLEAR DATE 9/27 - KIT CLEAR | 32 | 192 |  | 2023-09-21 |  |  |  | Rocky Research | 4
2023-10-04 |  | L3 | 119346-3RD |  | PROG ON LINE | RONC 2ND | 248 | 10/4 5D | FEDEX P | #3 (P2) DUE 10/2 DEPANEL | 9/30 - TOP 1:00 9/30 - AOI 2:30 | 1/1 | 9/27 - PCBS RECEIVED & AWT COUNT / BAKE 9/28 - SHORT P2 10/3 - KIT CLEAR | 1 | 248 |  | 2023-09-27 |  |  |  | Anderson Connectivity
2023-10-03 |  | L3 | 119344-2nd |  |  | RONC 1ST | 248 | 10/3 5D | FEDEX P | DO NOT SHIP EARLY | 9/27 - TOP 6:00 | 2/2 | 9/26 - KIT CLEAR | 0 | 0 |  | 2023-09-26 |  |  |  | Anderson Connectivity
2023-10-03 |  | L3 | 119431-2ND RT |  |  | ROWC 1ST | 20 | 10/3 5D | FEDEX P | *** ALERT *** NEW STENCIL: INSPECT THE FOLLOWING LOCATIONS L1, L2, L3, L4, L5, L6, L7, L8, L9, L10, L11, L12, L13, L14, L15, L30, L31, L32, L33 *** | 9/28 - BOT 6:00 9/29 - TOP 9:00 9/30 - AOI 1:00 | 3b/3t 222/1380 | 9/26 - KIT CLEAR | 0 | 0 | X | 2023-09-26 |  |  |  | Anderson Connectivity | 23
2023-10-03 |  | L1-2 | 120387 | NEED PROG |  | NEW | 2 | 10/3 10D | FEDEX GND | DEPANEL | 9/21- BOT 12:30 9/21 - TOP 4:00 9/22 - AOI | 106/1204 | 9/18 - WILL CLEAR SOON 9/19 - KIT CLEAR | 23 | 46 |  | 2023-09-19 |  |  |  | Southwest Research Institute
2023-10-03 |  | L1 | 120702 | NEED PROG | 9/22 - STENCIL/GERBER ISSUE | ROWC 117480 | 20 | 10/3 9/28 5D | FEDEX P | #75 (R103, R104) SMT SKIP WRONG PART RECEIVED CLASS 3 DEPANEL "U58" AFTER WASH - SCREWS REQ | 9/26 - TOP 9:30 9/26 - AOI 1:30 | 2T 79/418 | 9/20 - WILL CLEAR 9/21 DAY 1 IS 9/22 9/21 - KIT CLEAR | 4 | 80 | [5 empty] | Pronto | 4
2023-10-03 |  | L1 | 118397 NN |  | PROGRAM BALANCE ISSUE | NEW | 90 | 10/3 20D | FEDEX GND | DEPANEL BARCODE LABEL | 9/27 - BOT 6:00 9/27 - TOP 12:00 9/28 - AOI 1:30 | 1B 1T 93/396 | 9/5 - KIT CLEAR | 3 | 270 | X | 2023-09-05 | NC |  | X | Access Sensor Technologies
2023-10-03 |  | L1-2 | 120429 |  |  | RONC 116783 | 50 | 10/3 15D | FEDEX GND | SET DEFAULT PASTE TO 125% DEPANEL | 9/26 - TOP 9/26 - AOI 9:00 | 1T 29/94 | 9/13 - KIT CLEAR | 13 | 650 |  | 2023-09-09 | C |  | X | AMPT
2023-10-03 |  | L3-1 | 120432 |  |  | ROWC 117047 | 13 | 10/3 10D | FEDEX P | DEPANEL | 9/25 - TOP 9:00 9/25 - AOI 2:00 | 1T 43/318 | 9/13 - WILL CLEAR SOON 9/18 - FABS DUE 9/20 9/19 - KIT CLEAR | 84 | 1092 |  | 2023-09-14 | C |  |  | Biolog Inc.
2023-10-02 |  | L1-1 | 120883 |  | PROG NOT REQUESTED - PROG ON THE LINE | NEW | 270 | 10/2 3D | FEDEX P | *** 3 DAY TURN *** *3 DIFFERENT LOT ID LABELS REQUIRED PER ECO #2 - ADD SER # AS WELL DEPANEL | 9/28 - TOP 3:00 9/29 - AOI 7:00 | 1T 2/2 | 9/19 - WIL CLEAR SOON - FABS DUE 9/22 9/26 - PCB DUE 9/27 - KIT CLEAR | 0 | 0 | [5 empty] | Transphorm USA | 2
2023-10-02 |  | L3 | 120474 |  | PROG NOT REQUESTED - PROG ON THE LINE | NEW | 5 | 10/2 10D | UPS RED | DEPANEL | 9/21 - BOT 3:00 9/22 - TOP 9/22 - AOI | 1B 1T 3/30 | 9/18 - KIT CLEAR | 199 | 995 |  | 2023-09-18 |  |  |  | Government Contracting Specialists, Inc.
2023-10-02 |  | L2 | 120559 (9/18) R |  | *EXPECTED SMT RUNTIME 4 - 6 DAYS | ROWC 119543 | 375 | 10/2 (10D) | FEDEX P | ***MUST START SMT ON DAY 1*** DEPANEL | 9/21 - BOT 11:00 9/25 - TOP 2:00 9/28 - AOI 2:00 | 1B 1T 65/422 | 9/13 - WILL CLEAR SOON 9/18 - KIT CLEAR | 53 | 19875 | X | 2023-09-14 | NC |  | X | Industrialex Manufacturing | 50
2023-09-29 |  | L3-2 | 120532 | NEED PROG |  | NEW | 150 | 9/29 5D | FEDEX P | DEPANEL | 9/25 - AOI | 22/33 | 9/18 - SHOULD CLEAR 9/20 9/22 - KIT CLEAR | 0 | 0 | [5 empty] | Taditel US Inc
2023-09-29 |  | L3-1 | 120889 |  | NO PROG; PROG O/L | NEW | 100 | 9/29 5D | UPS GRND | DEPANEL | 9/23 - TOP 1:00 9/25 - AOI | 2/16 | 9/21 - RECV'D ARRAY; KIT CLEAR 9/22 | 4 | 400 |  | 2023-09-21 |  |  |  | Graph-Tech USA, LLC
2023-09-27 | 12 | L2 | 119676 |  |  | NEW | 50 | 9/26 15D | UPS RED | J6 CLIP REQ (SEE ECO) | 9/20 - TOP 921 - AOI | 1T 49/176 | 9/5 - KIT CLEAR | 53 | 2650 |  | 2023-09-05 | C |  | X | Beckman Coulter
2023-09-27 |  | L1-2 | 120529 | NEED PROG |  | NEW | 100 | 9/27 5D | FEDEX P | DEPANEL "J3" IS BTD | 9/22 - TOP 9/23 - AOI | 1T 10/17 | 9/20 - KIT CLEAR | 2 | 200 | [5 empty] | Protocol Insight LLC.
2023-09-27 | 14 | L1-1 | 118702 | FRI 9/15 |  | ROWC 107608 | 100 | 9/27 10D | UPS GND | HAND-SOLDER Y1 DEPANEL | 9/14 - BOT 11:00 9/15 - TOP 9/15 - AOI | 1B 1T 51/157 | 9/13 - KIT CLEAR | 15 | 1500 | X | 2023-09-07 | C |  | X | Graph-Tech USA, LLC
2023-09-26 | 13 |  | 116819-2nd |  |  | ROWC 1ST | 5 | 9/26 15D | FEDEX GND | *DO NOT SOLDER "J1 & 2" DNI J1 & J2 | 9/18 - BOT & TOP 9/18 - AOI | 1B 1T 32/795 | 9/5 - SHORT THT PARTS | 8 | 40 |  | 2023-08-30 | C |  | X | Mission Support and Test Services
2023-09-26 |  | L3-1 | 120745 | NEED PROG |  | NEW | 20 | 9/26 5D | FEDEX P | DEPANEL "S1-4" PLACE AFTER WASH | 9/21 - BOT 9/22 - TOP 9/22 - AOI | 1B 1T 65/506 | 9/18 - FABS DUE 9/19 9/19 - KIT CLEAR | 10 | 200 | X |  |  |  |  | Nordson Corporation
2023-09-26 |  | L3-1 | 120638 |  |  | NEW | 20 | 9/26 5D | FEDEX P | DEPANEL SW1-4 PLACE AFTER WASH | 9/22 - BOT 9/22 - TOP 1:00 9/23 - AOI 12:00 | 1B/1T 123/1085 | 9/19 - KIT CLEAR | 39 | 780 | X | 2023-09-19 |  |  |  | Nordson Corporation
2023-09-26 | 1 | L2 | 118820-2ND |  |  | RONC 2ND | 3 | 9/25 3D | UPS GND | ***3 DAY TURN*** CLASS 3 DEPANEL PRESS FIT REQ | 9/19 - BOT 9/20 - TOP 9/20 - AOI | 1B 1T 68/253 | 9/18 - KIT CLEAR (REPORTED DAY 1 9/20) | 10 | 30 |  | 7/6 | C |  |  | Diversified Supply | 3
2023-09-25 | 10 | L3-1 | 119343-2nd BAL-2 | TUES 9/19 | 9/13 - #55 (U17) BTD 9/15 - PAD SIZE ISSUES @ D5 & RELATED | RONC 1ST | 98 | 9/25 9/21 5D | FEDEX P | *10D CHANGED TO 5D BY CUST 9/15 PAD SIZE ISSUE @ "D5 & RELATED" **SMT TO START THE DAY THIS CLEARS OR SOONER - WILL TAKE EST 4 DAYS TO RUN DEPANEL | 9/14 - BOT 9:30 9/18 - BOT 10:30 9/19 - TOP 10:30 9/21 - AOI | 2B 2T 140/655 | 9/14 - KIT CLEAR | 0 | 0 | X | 2023-09-12 | C |  | X | Anderson Connectivity
2023-09-25 |  | L1-3 | 120614 (9/17) |  | WTG FOR ARRAY FILES - REQ 9/18 RECVD 9/18 | NEW | 5 | 9/25 5d | UPS RED | R124,R126 P/N CHNGD TO ERJ-3EKF6202V PER ECO #1 | 9/21 - BOT 8:00 9/21 - TOP 10:00 9/21 - AOI | 1B 1T 97/392 | 9/18 - KIT CLEAR | 15 | 75 | [5 empty] | HII Unmanned Systems, Inc | 3
2023-09-25 |  | L1-1 | 120092 |  | PROG NOT REQUESTED - PROG ON THE LINE | NEW | 4 | 9/25 3D | UPS RED | ***3 DAY TURN*** DEPANEL 3 DIFF LABELS REQ - SEE ECO | 9/21 - TOP 6:00 9/21 - AOI | 1T 1/40 | 9/20 - KIT CLEAR | 47 | 188 | [5 empty] | Innomotics LLC | 1
2023-09-25 | 11 | L1-1 | 120686 |  | PROG NOT REQUESTED - PROG ON THE LINE | NEW | 110 | 9/25 3D | FEDEX P | *** 3 DAY TURN *** DEPANEL REV NO REQ S/N REQ | 9/22 - TOP 6:00 9/22 - aoi | 1T 2/4 | 9/20 - FABS DUE 9/21 9/21 - KIT CLEAR | 12 | 1320 |  | 2023-09-21 |  |  |  | ITI Engineering
2023-09-25 |  | L1 | 119811 |  | ***DO NOT SHIP EARLY | NEW | 40 | 9/25 9/19 15D | FEDEX GND | #3 (D1, D2, D3...) BTD DEPANEL | 9/7 - TOP 8:00 9/7 - AOI 10:00 | 1T 8/35 | 8/25 - KIT CLEAR | 71 | 2840 |  | 2023-08-26 | C |  | X | FORT Robotics, Inc. | 2
2023-09-22 | 10 | L3-1 | 119343-2nd PAR-1 | TUES 9/19 | 9/13 - #55 (U17) BTD 9/15 - PAD SIZE ISSUES @ D5 & RELATED | RONC 1ST | 150 | 9/22 9/21 5D | FEDEX P | *10D CHANGED TO 5D BY CUST 9/15 PAD SIZE ISSUE @ "D5 & RELATED" **SMT TO START THE DAY THIS CLEARS OR SOONER - WILL TAKE EST 4 DAYS TO RUN DEPANEL | 9/14 - BOT 9:30 9/18 - BOT 10:30 9/19 - TOP 10:30 9/21 - AOI | 2B 2T 140/655 | 9/14 - KIT CLEAR | 0 | 0 | X | 2023-09-12 | C |  | X | Anderson Connectivity
2023-09-22 | 11 | L1-2 | 119574 | TUES 9/19 | 9/19 - STENCIL ISSUE 9/20 - NEW STENCIL 9:00 | ROWC 115651 | 70 | 9/22H 15D | FEDEX GND | *** DO NOT THROW AWAY ALL ASSEMBLY FRAMES *** DEPANEL DATE MANUFACTUR LABL REQ | 9/19 - BOT 9/20 - TOP | 1B 1T 57/330 | 8/30 - KIT CLEAR | 0 | 0 | X | 2023-08-30 | C |  | X | AimLock
2023-09-22 | 25 | L3 | 119346-2nd |  | SQUEEZING THIS IN ON L3 | NEW | 2 | 9/22 ??? 5D | FEDEX P | SHIP FRI 9/22 IF POSSIBLE ***CHECK "P2" FOOTPRINT W/ PART BEFORE SMT DEPANEL | 9/21 - TOP 6:00 | 1B 1/1 | 9/13 - RE-RELEASE, AWT NEW PCBs 9/18 - NEW PCB'S SHIPPED OUT - SHOULD RECV 9/19 9/19 - RECV NEW PCBS - CHANGED ARRAY TO 2 UP FROM 4 UP - NEED NEW STENCIL & ARRAY FILES 9/20 - KIT CLEAR | 1 | 2 |  | 2023-08-22 | C |  | X | Anderson Connectivity | 0.5
2023-09-22 | 1 | L1-L | 120556 | THURS 9/14 WED 9/20 | 9/14 - JOB ON HOLD DUE TO PCB ISSUES 9/18 - DNI PER CUST | NEW | 6 | 9/22 3D | FEDEX P | *** 3 DAY TURN *** BTD J2 | 9/19 - BOT 6:00 9/19 - TOP 1:00 9/19 AOI | 1B 2T 88/533 | 9/13 - KIT CLEAR 9/14 - FOOTPRIINT ISSUES "CR42 & RELATED" 9/18 - DNI "CR42 & RELATED" | 44 | 264 |  | 2023-09-12 | C |  | X | Saronic Technologies
2023-09-21 | 7 | L2 | 120153 | TUES 9/19 | 9/14 - SHORT 1 RT1 (THT PART) | RONC 119038 | 100 | 9/21 5D | FEDEX P | WASH & BAKE REQUIRED | 9/19 - BOT/TOP 9/19 - AOI | 1B 1T 49/120 | 9/14 - SMT CLEAR 9/18 - KIT CLEAR | 11 | 1100 | X | 2023-09-14 | C |  | X | Atlas Devices
2023-09-21 | 8 |  | 118860-2nd | FRI 9/15 SAT 9/16 |  | ROWC 1ST | 12 | 9/21 5D | FEDEX P | QR CODE LABEL DEPANEL | 9/15 - BOT 9/16 - TOP 9/18 - AOI | 1B 1T 83/568 | 9/14 - KIT CLEAR | 6 | 72 |  | 2023-09-14 | C |  | X | ABB, Inc. Bartles Totalflow
2023-09-21 | 6 | L1-5 | 120561 | MON 9/18 |  | NEW | 2 | 9/21 5D | FEDEX P | DEPANEL | 9/16 - BOT & TOP 9/18 - AOI | 1B 1T 63/606 | 9/14 - KIT CLEAR | 42 | 84 |  | 2023-09-12 | C |  | X | Forza Ametek
2023-09-21 | 9 | L2-2 | 119925 | FRI 9/15 SAT 9/16 |  | NEW | 20 | 9/21 10D | UPS 2 DAY | *** SHARE PARTS W/ B119924 DEPANEL U12 & C39 PLACE AS IS | 9/12 - BOT 12:30 9/12 - TOP 2:00 9/15 - AOI | 1B 2T 90/676 | 9/7 - KIT CLEAR | 6 | 120 | X | 2023-09-07 | C |  | X | Union Biometrica
2023-09-20 | 4 |  | 119713 | FRI 9/15 SAT 9/16 |  | NEW | 100 | 9/20 5D | FEDEX P | DEPANEL | 9/16 - BOT/TOP 9/18 - AOI | 1T 33/96 | 9/13 - KIT CLEAR | 19 | 1900 |  | 2023-09-05 | C |  | X | FORT Robotics, Inc.
2023-09-20 | 5 | L3 | 120492 | SAT 9/16 |  | NEW | 80 | 9/20 5D | FEDEX P |  | 9/16 - BOT & TOP 9/18 - AOI | 1B 1T 34/106 | 9/13 - KIT CLEAR | 1 | 80 | X | 2023-09-12 | C |  | X | H3D, Inc.
2023-09-20 |  | L3 | 119188 | WEDS 9/13 | FSU PROG 9/13 - PART ISSUE | NEW | 40 | 9/20H 15D | UPS RED | DEPANEL | 9/13 - BOT 6:00 9/13 - TOP 2:30 9/14 - AOI 9:30 | 1B 2T 45/360 | 8/28 - KIT CLEAR | 12 | 480 | X | 2023-08-19 | C |  | X | Jefferson Labs | 11.5
2023-09-20 |  |  | 119554 |  |  | NEW | 40 | 9/20 10D | FEDEX GND | DEPANEL MECH ASSY & PASTE REQ | BACK | THT ONLY | 9/6 - PASTE DUE | 16 | 640 |  | 2023-08-30 | C |  | X | Switched Source LLC
2023-09-20 |  | L2/L3 | 117094-2 PAR | MON 9/11 |  | ROWC 1ST BATCH | 1100 | 9/20H 20D | UPS GND | ***ICC MEDICAL - NEED EXCEL NON CONFORMANCE LOG*** DEPANEL REV MARKING REQ | 8/31 - BOT 2:00 9/7 - TOP 12:00 9/11 - AOI 12:00 | 2B 1T 24/126 | 8/21 - KIT CLEAR | 4 | 4400 | X | 2023-08-21 | C | Y | X | ICC MEDICAL | 56
2023-09-20 | 2 | L3-1 | 119442-2nd | FRI 9/15 |  | RONC 1ST | 85 | 9/20 3D | FEDEX P | *** 3 DAY TURN *** XRAY & SAVE IMAGES DEPANEL | RTR | 1T 1/1 | 9/15 - KIT CLEAR | 1 | 85 |  | 2023-09-14 | C |  |  | Anderson Connectivity
2023-09-19 | 3 | L2-1 | 120334 | FRI 9/15 SAT 9/16 |  | RONC 117447 | 700 | 9/19 5D | FEDEX P | *7 DIFFERENT LOT ID LABELS REQUIRED PER ECO #3 - ADD SER # AS WELL DEPANEL | 9/16 - TOP 8:00 9/18 - AOI | 1T 2/2 | 9/11 - WILL CLEAR | 0 | 0 |  | 2023-09-11 | NC |  | X | Transphorm USA
2023-09-19 | 2 | L3-1 | 119440-2nd | FRI 9/15 |  | RONC 1ST | 85 | 9/19 3D | FEDEX P | *** 3 DAY TURN *** XRAY & SAVE IMAGES DEPANEL | RTR | 1T 1/1 | 9/14 - KIT CLEAR | 1 | 85 |  | 2023-09-14 | C |  |  | Anderson Connectivity
2023-09-19 |  | L2-1 | 120099 | WEDS 9/13 THURS 9/14 |  | NEW | 150 | 9/19 5D | FEDEX P | DEPANEL | 9/13 - BOT 8:00 9/13 - TOP 2:00 9/14 - AOI 2:00 | 1B 1T 11/62 | 9/12 - KIT CLEAR | 0 | 0 | X | 2023-09-07 | C |  | X | Contrast, Inc. | 8
2023-09-19 | 3 | L2-1 | 120334 | FRI 9/15 SAT 9/16 |  | RONC 117447 | 700 | 9/19 5D | FEDEX P | *7 DIFFERENT LOT ID LABELS REQUIRED PER ECO #3 - ADD SER # AS WELL DEPANEL | 9/16 - TOP 8:00 9/18 - AOI | 1T 2/2 | 9/11 - WILL CLEAR | 0 | 0 |  | 2023-09-11 | NC |  | X | Transphorm USA
2023-09-19 | 2 | L3-1 | 119440-2nd | FRI 9/15 |  | RONC 1ST | 85 | 9/19 3D | FEDEX P | *** 3 DAY TURN *** XRAY & SAVE IMAGES DEPANEL | RTR | 1T 1/1 | 9/14 - KIT CLEAR | 1 | 85 |  | 2023-09-14 | C |  |  | Anderson Connectivity
2023-09-19 |  | L2-1 | 120099 | WEDS 9/13 THURS 9/14 |  | NEW | 150 | 9/19 5D | FEDEX P | DEPANEL | 9/13 - BOT 8:00 9/13 - TOP 2:00 9/14 - AOI 2:00 | 1B 1T 11/62 | 9/12 - KIT CLEAR | 0 | 0 | X | 2023-09-07 | C |  | X | Contrast, Inc. | 8
2023-09-18 |  | L1 | 120096-1st | THURS 9/14 |  | NEW | 2 | 9/18 5D | UPS GRND | CLASS 3 DEPANEL | 9/14 - BOT 6:00 9/14 - TOP 9/14 - AOI 8:00 | 1B 1T 51/475 | 9/11 - KIT CLEAR | 4 | 8 |  | 2023-08-31 | C |  | X | Diversified Supply | 2
2023-09-18 |  | L3 | 118295 | WEDS 9/13 |  | NEW | 4 | 9/18 5D | FEDEX P | ***ALERT - "CIRC1-3" DO NOT APPLY SOLDER!!! - SEE ECO #1 9/6 UPDATE - CUST TO SUPPLY QTY 2 TO POPULATE "CIRC3" ON 2 BOARDS ONLY DNI "CIRC1 & 2" DO NOT APPLY SOLDER PASTE ***XRAY & CONFIRM QUALITY SOLDER @ "CIRC3" - CUST HAS HAS SOLDER ISSUES IN THE PAST | 9/12 - BOT 7:00 9/12 - TOP 9/12 - AOI 10:00 | 1B 1T 50/98 | 9/11 - KIT CLEAR | 12 | 48 |  | 2023-09-11 | C |  | X | University of Oklahoma | 3
2023-09-18 |  | L1 | 118628-1 PAR | QTY 1550 BOT DONE FRI 9/15 | 9/11 - 100 COMPLETE | ROWC 114946 | 100 | 9/18 20D | UPS GND | SHIP DATE 10/04; W/ 100 BOARDS TO SHIP 9/18 ***MUST LOG ALL NON-CONFORMANCES BY SERIAL NUMBER PER ECO NOTE #5*** ---SEVERAL PAST QUALITY ISSUES - PLEASE TIGHTEN UP QA 100%--- **QUALITY ALERT - LAST RUN MISSING "R124" - SEE ECO #4 | 9/8 - BOT 1:00 9/11 - TOP 8:00 9/11 - AOI 10:00 | 2B 2T 30/155 | 9/6 - KIT CLEAR | 3 | 300 | X | 2023-09-06 | C |  | X | ICC,Inc | 6
2023-09-18 |  | L1 | 119275-2ND |  |  | ROWC 1ST | 40 | 9/18H 10D | FEDEX P | DEPANEL | 9/7 - TOP 11:00 9/7 - AOI | 1T 52/118 | 8/31 - KIT CLEAR | 14 | 560 |  | 2023-08-24 | NC |  | X | Industrialex Manufacturing
2023-09-18 |  | L1 | 119275-2ND |  |  | ROWC 1ST | 5 | 9/18H 10D | FEDEX P | DEPANEL | 9/7 - TOP 11:00 9/7 - AOI | 1T 52/118 | 8/31 - KIT CLEAR | 14 | 70 |  | 2023-08-24 | NC |  | X | Industrialex Manufacturing
2023-09-15 |  | L1 | 116508 | FRI 9/8 |  | NEW | 120 | 9/15H 10D | FEDEX GND | DEPANEL | 9/7 - TOP 10:00 9/7 - AOI 11:00 | 1T 12/13 | 8/30 - KIT CLEAR | 0 | 0 |  | 2023-08-30 | C |  | X | Taditel US Inc
2023-09-15 |  | L1 | 119482-1ST | MON 9/11 |  | NEW | 5 | 9/15 5D | FEDEX P | DEPANEL | 9/8 - AOI | 1B 1T 9/20 | 9/7 - KIT CLEAR | 11 | 55 |  | 2023-09-07 | C |  | X | Pfeiffer Vacuum, Inc
2023-09-15 |  | L3 | 120465-1st | TUES 9/12 |  | NEW | 10 | 9/15 5D | FEDEX P | DEPANEL DATE CODE LABEL | 9/11 - BOT 12:00 9/11 - TOP 2:30 9/11 - AOI 7:00 | 1B 1T 45/93 | 9/7 - KIT CLEAR | 8 | 80 |  | 2023-09-07 | NC |  | X | Industrialex Manufacturing | 3.5
2023-09-15 |  | L1 | 119344-1st |  |  | NEW | 2 | 9/15 9/13 5D | FEDEX P | DEPANEL (GIVE TO TAD - RAZOR CUT REQUIRED) | 9/8 - BOT 9:30 9/8 - AOI | 1B 1T 2/2 | 9/6 - KIT CLEAR | 0 | 0 |  | 2023-08-31 | C |  | X | Anderson Connectivity
2023-09-14 | 1 | L1 | 119437-2nd | THURS 9/14 |  | RONC 1ST | 85 | 9/14 3D | FEDEX P | CLASS 3 DEPANEL | 9/13 - BOT 6:00 9/13 - TOP 11:00 9/13 - AOI 5:30 | 1B 2T 111/320 | 9/11 - KIT CLEAR | 0 | 0 | X | 2023-09-11 | C |  | X | Anderson Connectivity
2023-09-14 | 2 | L3 | 120350 | WEDS 9/13 |  | NEW | 12 | 9/14 3D | FEDEX P | *** 3 DAY TURN *** | 9/12 - BOT 10:00 9/12 - TOP 9/12 - AOI 2:30 | 1B 1T 74/492 | 9/11 - KIT CLEAR | 0 | 0 |  | 2023-09-07 | C |  | X | Artis LLC | 4.5
2023-09-13 | 4 | L1 | 120450 |  |  | NEW | 135 | 9/13 5D | FEDEX 2 DAY | DEPANEL | 9/7 - BOT 9/8 - TOP 9/8 - AOI 9:30 | 1B 1T 2/2 | 9/6 - KIT CLEAR | 0 | 0 |  | 2023-08-30 | C |  | X | Aila Technologies, Inc.
2023-09-13 | 1 | L2 | 119924 | MON 9/11 TUES 9/12 |  | NEW | 30 | 9/13H 10D | UPS 2 DAY | *** SMT - DO NOT LOSE ANY ITEM 6 PARTS - 95% SHARED WITH B119925 - TEAR DOWN ONLY ITEMS 3-18, 60-62 & 73-87 DEPANEL U12 & U23 NO THERMAL PASTE BY DESIGN (PLACE AS IS) | 9/8 - BOT 7:00 9/11 - TOP 8:00 9/12 - AOI 12:00 | 1B 2T 89/498 | 8/28 - KIT CLEAR | 6 | 180 | X | 2023-08-23 | C |  | X | Union Biometrica
2023-09-13 | 7 | L1 | 119296 | THU 9/7 | 9/5 - AWT STENCIL | NEW | 64 | 9/13H 10D | FEDEX P | DEPANEL LEAD TRIMMING REQ | 9/6 - BOT 9:00 9/6 - TOP 9/6 - AOI 1:30 | 1B 1T 26/85 | 8/28 - KIT CLEAR | 11 | 704 |  | 2023-08-28 | C |  | X | Industrialex Manufacturing | 4
2023-09-12 | 1 | L3 | 119442-1ST | THU 9/7 | 9/6 - PCBS BAKING 9/7 - PCBS ISSUE | NEW | 5 | 9/12 5D | FEDEX P | DEPANEL XRAY & SAVE IMGS | 9/7 - AOI | 1T 1/1 | 9/5 - KIT CLEAR | 1 | 5 |  | 2023-09-05 | C |  | X | Anderson Connectivity
2023-09-12 | 4 | L3 | 119440-1ST | WED 9/6 |  | NEW | 5 | 9/12 5D | FEDEX P | DEPANEL XRAY & SAVE IMGS | 9/6 - TOP 1:30 9/6 - AOI 2:30 | 1T 1/1 | 9/5 - KIT CLEAR | 1 | 5 |  | 2023-09-05 | C |  | X | Anderson Connectivity | 1
2023-09-12 | 2 | L1 | 120324-1ST | FRI 9/8 |  | NEW | 2 | 9/12 5D | FEDEX P | DATE CODE LABEL | 9/8 - AOI | 1T 44/80 | 9/5 - KIT CLEAR | 4 | 8 |  | 2023-09-05 | C |  | X | Industrialex Manufacturing
2023-09-12 | 4 | L1 | 120020 | FRI 9/8 |  | NEW | 2 | 9/12H 10D | FEDEX P | DEPANEL | 9/6 - BOT 1:30 9/7 - TOP 9/7 - AOI 8:00 | 1B 2T 95/303 | 8/25 - KIT CLEAR | 8 | 16 |  | 2023-08-23 | C |  | X | Diversatek | 3
2023-09-12 | 4 | L3 | 119784-2 BAL |  |  | NEW | 56 | 9/12 10D | FEDEX P | EXPEDITED 4 PCBS ON 9/7 | 8/31 - TOP 7:30 8/31 - BOT 1:30 9/5 - AOI 10:30 | 1B 1T 91/660 | 8/28 - KIT CLEAR | 2 | 112 | X | 2023-08-28 | C | Y | X | L3 | 12
2023-09-11 | 1 | L3 | 119433-2nd |  |  | ROWC 1ST | 20 | 9/11 3D | FEDEX P | *** 3 DAY TURN *** DEPANEL | 9/6 - TOP 12:00 9/7 - BOT 8:00 9/7 - AOI 11:00 | 2B 1T 134/436 | 9/6 - KIT CLEAR | 0 | 0 | X | 2023-08-31 | C | Y | X | Anderson Connectivity | 8
2023-09-11 | 3 | L3 | 119276 | WED 9/6 |  | NEW | 140 | 9/11H 5D | UPS RED | DEPANEL | 9/5 - TOP 10:30 9/6 - AOI 12:00 | 2T 22/549 | 8/31 - KIT CLEAR | 5 | 700 | X | 2023-08-31 | C |  | X | Samtec | 8
2023-09-08 | 7 | L1 | 119071-2ND |  | 8/30 - L1 NOZZLE ISSUE / BOT SIDE 1ST | ROWC 1ST | 70 | 9/8 9/6H 5D | FEDEX P | *** QUALITY ALERT: INSTALLATION CARE REQ ON #39 (J2) *** NOTE: SEPARATE SHIPMENT ADDRESS FOR FA (SEE PO) XRAY & SAVE IMGS (SEE ECO) | 8/30 - TOP 7:00 8/30 - BOT 9:00 8/30 - TOP 12:30 8/31 - AOI 7:00 | 1B 1T 64/173 | 8/28 - KIT CLEAR | 2 | 140 | X | 2023-08-26 | C |  | X | TEST COACH COMPANY | 10
2023-09-08 | 1 | L3 | 119809 |  | 9/5 - JOB TRANSFER FROM L1 TO L3; H/L LAST PARTS | RONC 115113 | 10 | 9/8 3D | FEDEX P | *** 3 DAY TURN *** DEPANEL | 9/5 - BOT 1:00 9/5 - AOI 2:30 | 1B 1T 2/2 | 9/5 - KIT CLEAR | 0 | 0 |  | 2023-08-21 | C |  | X | Industrialex Manufacturing
2023-09-08 | 2 | L1 | 120218 |  |  | NEW | 60 | 9/8 3D | UPS RED | *** 3 DAY TURN *** DEPANEL BARCODE LABEL REQ CofC REQUIREMENTS | 9/5 - TOP 11:30 9/6 - BOT 7:00 9/6 - AOI 9:00 | 1B 1T 122/440 | 9/5 - KIT CLEAR | 0 | 0 |  | 2023-08-24 | C | Y | X | ROYAL CIRCUITS SOLUTIONS INC | 6
2023-09-08 |  |  | 119436-2ND |  |  | ROWC 1ST | 55 | 9/8 3D | FEDEX P | *** 3 DAY TURN *** DEPANEL | BACK | THT ONLY | 9/5 - KIT CLEAR | 4 | 220 |  | 2023-08-30 | C |  | X | Anderson Connectivity
2023-09-07 | 3 | L2 | 120123 |  |  | RONC 117173 | 50 | 9/7H 10D | UPS GND | DEPANEL | 8/30 - BOT 1:00 8/31 - TOP 10:00 8/31 - 2:00 | 1B 1T 53/205 | 8/22 - KIT CLEAR | 2 | 100 | X | 2023-08-22 | C |  | X | Churchill Navigation dba Shotover Systems Inc | 9
2023-09-07 | 2 | L1 | 120472 |  |  | ROWC 119043 | 100 | 9/7 3D | FEDEX P | *** 3 DAY TURN *** DEPANEL SPECIAL LABEL REQUIREMENTS | 8/31 - BOT 3:00 9/5 - TOP 7:30 9/5 - AOI 10:30 | 1B 1T 39/98 | 8/31 - KIT CLEAR | 1 | 100 | X | 2023-08-30 | C |  | X | Edge Autonomy | 6
2023-09-07 | 4 | L3 | 119784-1 PAR |  |  | NEW | 4 | 9/7 10D | FEDEX P | BALANCE SHIP ON 9/12 | 8/31 - TOP 7:30 8/31 - BOT 1:30 9/5 - AOI 10:30 | 1B 1T 91/660 | 8/28 - KIT CLEAR | 2 | 8 |  | 2023-08-28 | C | Y | X | L3 | 12
2023-09-07 | 1 | L1 | 119571 |  | 8/31 - L1 NOZZLE ISSUE | RONC 114955 | 70 | 9/7H 10D | FEDEX GND | DEPANEL & SAND DATE MANUFACTURE LABEL REQ | 8/31 - BOT 7:00 8/31 - TOP 11:00 8/31 - AOI 3:00 | 1B 1T 65/307 | 8/22 - KIT CLEAR | 5 | 350 | X | 2023-08-21 | C |  | X | AIMLOCK | 8
2023-09-07 | 5 | L3 | 119189 |  |  | NEW | 15 | 9/7 9/6H 10D | UPS RED | ***QUALITY ALERT*** DO NOT SKIP AOI 100% INSPECTION REQUIRED *SHIPPING INSPECTION REQ PRESS FIT REQ MECH ASSY REQ | 8/30 - BOT 9:00 8/30 - TOP 12:00 8/31 - AOI 7:30 | 1B 1T 46/257 | 8/21 - KIT CLEAR | 63 | 945 |  | 2023-08-21 | C |  | X | Northrop Grumman - Adaptive Optics Assoc. | 8
2023-09-06 | 6 | L1 | 119788-1ST |  |  | NEW | 45 | 9/6H 5D | FEDEX P | GLUE & BAKE REQ DEPANEL | 8/29 - BOT 12:30 8/29 - TOP 4:30 8/30 - AOI 7:00 | 1B 1T 67/152 | 8/28 - KIT CLEAR | 6 | 270 |  | 2023-08-16 | NC |  | X | Industrialex Manufacturing | 5
2023-09-06 | 4 | L1 | 119655 |  |  | ROWC 112877 | 100 | 9/6H 10D | FEDEX 2D | DEPANEL | 8/29 - TOP 9:30 8/29 - AOI 12:30 | 1T 24/42 | 8/21 - KIT CLEAR | 6 | 600 |  | 2023-08-21 | C |  | X | SAFE GRAND, INC. / MAXI-TRONIC | 3
2023-09-05 | 3 | L2 | 119448 |  | 8/29 - J1 / FAB ISSUE | NEW | 97 | 9/5H 8D | FEDEX P | DEPANEL XRAY & SAVE IMGS | 8/28 - TOP 11:00 8/30 - AOI 1:00 | 2T 94/231 | 8/22 - KIT CLEAR | 0 | 0 | X | 2023-08-22 | NC |  | X | Sierra Innotek, Inc. | 16
2023-09-05 |  |  | 120335 |  |  |  | 250 | 9/5H 5D | FEDEX P |  | BACK | THT ONLY |  | 5 | 1250 |  | 2023-08-26 | C |  | X | Micro Precision Automation
2023-08-31 | 2 | L3 | 120150 |  | 8/29 - A LOT H/L | NEW | 20 | 8/31 5D | FEDEX P | DNI R74 & R97 | 8/28 - BOT 10:00 8/28 - TOP 1:30 8/30 - AOI 9:00 | 1B 1T 103/355 | 8/23 - KIT CLEAR | 5 | 100 |  | 2023-08-22 | C |  | X | Pronto | 8
2023-08-31 | 3 | L1 | 119849 |  |  | NEW | 80 | 8/31 5D | FEDEX P | QR CODE REQ (ECO 2) | 8/28 - TOP 8:00 8/28 - AOI 10:30 | 1T 40/69 | 8/24 - KIT CLEAR | 2 | 160 |  | 2023-08-23 | C | X | X | Industrialex Manufacturing | 2.5
2023-08-31 | 6 | L1 | 118969 |  |  | NEW | 250 | 8/31 10D | FEDEX 2D | DEPANEL | 8/26 - TOP 11:30 8/28 - AOI 8:00 | 2T 29/82 | 8/17 - KIT CLEAR | 5 | 1250 | X | 2023-08-17 | C |  | X | MACHINE SOLUTIONS | 7
2023-08-30 | 1 | L1 | 119913 |  | 8/26 - STENCIL ISSUE | ROWC 117703 | 69 | 8/30 5D | FEDEX P | ROWC 117703 - WAS LEAD FREE - NOW LEADED BTD #20 U13 | 8/28 - BOT 10:30 8/28 - TOP 1:00 8/29 - AOI 9:30 | 1B 1T 48/139 | 8/23 - KIT CLEAR | 7 | 483 | X | 2023-08-23 | C |  | X | Atlas Devices | 7.5
2023-08-29 | 1 | L2 | 118260 |  |  | NEW | 170 | 8/29 10D | FEDEX GND | DEPANEL BARCODE LABEL | 8/22 - BOT 5:00 8/24 - TOP 12:30 8/28 - AOI 11:00 | 1B 1T 49/112 | 8/15 - KIT CLEAR | 9 | 1530 | X | 2023-08-15 | NC |  | X | Access Sensor Technologies | 24
2023-08-29 |  | L2 | 119272-2 BAL |  |  | NEW | 1 | 8/24 10D | FEDEX GND | SOLDER ON NUTS (ECO #1) NUTS ON TOPSIDE (ECO #1) | 8/11 - BOT 9:30 8/14 - TOP 8:00 8/14 - AOI 2:00 | 1B 1T 74/206 | 8/10 - KIT CLEAR | 4 | 4 |  | 2023-08-07 | C |  | X | H3D, Inc. | 20
2023-08-28 | 1 | L1/L3 | 119922-1 PAR |  |  | NEW | 100 | 8/28 8/25 3D | FEDEX P | *** 3 DAY TURN *** DEPANEL CARE REQ SMT PARTS (#75 - 77 & #84) (J9, B2B_J1, B2B_J2, B2B_J3, B2B_J4, J13, J8, J10, J11, P1, P2 & P3) (PER ECO) | 8/23 - BOT 3:30 8/26 - TOP 9:30 8/28 - AOI 10:00 | 2B 2T 122/440 | 8/22 - KIT CLEAR | 3 | 300 | X | 2023-08-21 | C | Y | X | Contrast Inc | 31
2023-08-28 | 2 | L2 | 120136 |  |  | NEW | 170 | 8/28 3D | FEDEX P | *** 3 DAY TURN *** DEPANEL | 8/24 - BOT 12:30 8/25 - AOI 8:30 | 1B 3/3 | 8/23 - KIT CLEAR | 0 | 0 |  | 2023-08-23 | C |  | X | Plexus Engineering Solutions | 2
2023-08-28 | 3 | L2 | 120137 |  |  | NEW | 90 | 8/28 3D | FEDEX P | *** 3 DAY TURN *** DEPANEL DATE CODE LABEL REQ | 8/24 - BOT 2:00 8/25 - TOP 10:00 8/25 - AOI 2:00 | 1B 1T 11/28 | 8/23 - KIT CLEAR | 0 | 0 |  | 2023-08-23 | C |  | X | Plexus Engineering Solutions | 6
2023-08-28 |  | L1 | 119747-2 BAL |  |  | ROWC 108974 | 100 | 8/28 10D | FEDEX 2D | EXPEDITE 25 OF 125 ON 8/24 DEPANEL | 8/21 - TOP 1:30 8/22 - AOI 11:00 | 2T 101/173 | 8/14 - KIT CLEAR 8/19 - +2 SMT setup time | 0 | 0 | X | 2023-08-14 | C |  | x | Marshall Radio Telemetry Inc
2023-08-28 | 5 | L1 | 119486 |  |  | NEW | 20 | 8/28 7/28 5D | FEDEX P | OFF SHIPPING HOLD (8/25) DO NOT DEPANEL IC PREBAKE REQ XRAY & SAVE IMAGES | 7/25 - BOT 9:00 7/25 - TOP 12:30 7/25 - AOI 2:00 | 1B 1T 57/273 | 7/21 - KIT CLEAR | 2 | 40 |  | 2023-07-20 | C |  |  | RIPPLE | 5
2023-08-28 | 4 | L1 | 119734 |  |  | NEW | 10 | 8/28 10D | FEDEX P | DEPANEL DATE MANUFACTURE LABEL REQ | 8/25 - BOT 3:30 8/25 - TOP 8:30 8/25 - AOI 10:00 | 1B 2T 119/387 | 8/14 - KIT CLEAR | 19 | 190 |  | 2023-08-10 | C |  | x | Scythe Robotics | 5
2023-08-28 | 5 | L1 | 119206 |  |  | NEW | 55 | 8/28 5D | UPS RED | DEPANEL MECH ASSY REQ HEIGHT REQUIREMENTS BARCODE LABEL | 8/25 - BOT 10:00 8/25 - TOP 4:30 8/26 - AOI 11:00 | 1B 2T 130/411 | 8/21 - KIT CLEAR | 45 | 2475 | X | 2023-08-14 | C |  | X | IoTecha | 10
2023-08-28 | 8 | L1 | 118686 |  |  | ROWC 111037 | 100 | 8/28 10D | UPS GND | DEPANEL | 8/22 - BOT 11:00 8/23 - TOP 8:00 8/23 - AOI 3:30 | 1B 1T 80/513 | 8/14 - KIT CLEAR | 39 | 3900 | X | 2023-08-14 | C |  | X | Graph-Tech USA, LLC | 14
2023-08-25 | 1 | L3 | 118109-2 BAL |  |  | NEW | 375 | 8/25 8/24 5D | FEDEX P | DEPANEL | 8/21 - TOP 2:00 8/21 - AOI 1:30 | 1T 8/165 | 8/17 - KIT CLEAR | 0 | 0 | X | 2023-08-15 | C |  | X | ERI Group | 14
2023-08-25 | 1 | L3/L2 | 119431-1ST |  |  | NEW | 5 | 8/25 5D | FEDEX P | DEPANEL XRAY & SAVE IMGS | B/23 - BOT 2:00 8/24 - TOP 10:00 8/25 - AOI 12:00 | 3B 3T 221/1380 | 8/18 - KIT CLEAR | 0 | 0 | X | 2023-08-17 | C |  | X | Anderson Connectivity | 12
2023-08-25 | 10 | L1 | 119480-1st |  |  | NEW | 5 | 8/25 5D | FEDEX P | DEPANEL | 8/21 - BOT 10:30 8/21 - TOP 8/21 - AOI 1:30 | 1B 1T 43/852 | 8/18 - KIT CLEAR | 5 | 25 |  | 2023-08-14 | C |  | X | Pfeiffer Vacuum, Inc. | 3
2023-08-25 |  | L3 | 117918 |  |  | NEW | 2 | 8/25 10D | UPS RED | DEPANEL "J19 & J21" REQ XTRA SOLDER AND STAKING X-RAY "J19 & J21" & SAVE IMAGES PACKAGE PER ECO #11 - SHIPPING CONTAINERS WAIVED | 8/17 - TOP 6:00 8/17 - BOT 2:30 8/18 - AOI 2:30 | 3B 2T 204/1483 | 8/11 - KIT CLEAR | 14 | 28 |  | 2023-08-14 | NC | Y | X | DePuy Synthes Products, LLC | 16
2023-08-25 | 2 | L3 | 119492 |  |  | NEW | 75 | 8/25 3D | FEDEX P | *** 3 DAY TURN *** DEPANEL XRAY & SAVE IMGS | 8/22 - BOT 12:30 8/22 - TOP 1:30 8/22 - AOI 9:30 | 1B 1T 19/28 | 8/22 - KIT 8/22 - AWT PART CONF -2 | 1 | 75 |  | 2023-08-18 | C |  | X | Industrialex Manufacturing | 3
2023-08-25 |  | L1 | 114615 |  |  | NEW | 20 | 8/25 10D | FEDEX GND | CLASS 3 CofC PER ECO 4 & 7 MATL EXIT AUDIT REQ DATE CODE LABEL REQ | 8/14 - TOP 10:00 8/15 - BOT 8:00 8/15 - AOI 1:30 | 1B 1T 85/243 | 8/11 - KIT CLEAR | 24 | 480 |  | 2023-08-10 | NC | Y | X | MAGNIX | 11.5
2023-08-25 |  | L1 | 116086-2ND |  |  | ROWC 1ST | 175 | 8/25 10D | FEDEX P | DEPANEL | 8/11 - TOP 7:30 8/14 - AOI 10:00 | 2T 83/250 | 8/11 - KIT CLEAR | 8 | 1400 | X | 2023-08-02 | C |  | X | Servomex | 11
2023-08-25 |  | L2 | 119272-1 PAR |  |  | NEW | 44 | 8/24 10D | FEDEX GND | SOLDER ON NUTS (ECO #1) NUTS ON TOPSIDE (ECO #1) | 8/11 - BOT 9:30 8/14 - TOP 8:00 8/14 - AOI 2:00 | 1B 1T 74/206 | 8/10 - KIT CLEAR | 4 | 176 | X | 2023-08-07 | C |  | X | H3D, Inc. | 20
2023-08-24 | 1 | L3 | 118109-1 PAR |  |  | NEW | 375 | 8/24 5D | FEDEX P | SPLIT SHIPMENT: PLEASE HAVE MINIMUM OF 375 READY TO SHIP ON 8/24 DEPANEL | 8/21 - TOP 2:00 8/23 - AOI 1:30 | 1T 8/165 | 8/17 - KIT CLEAR | 0 | 0 | X | 2023-08-15 | C |  | X | ERI Group | 14
2023-08-24 |  | L1 | 119747-1 PAR |  |  | ROWC 108974 | 25 | 8/24 8/28 10D | FEDEX 2D | EXPEDITE 25 OF 125 ON 8/24 DEPANEL | 8/21 - TOP 1:30 8/22 - AOI 11:00 | 2T 101/173 | 8/14 - KIT CLEAR 8/19 - +2 SMT setup time | 0 | 0 |  | 2023-08-14 | C |  | x | Marshall Radio Telemetry Inc | 14
2023-08-24 |  | L3 | 119826 |  |  | NEW | 20 | 8/24 5D | FEDEX GND | DEPANEL | 8/19 - BOT 10:00 8/21 - TOP 8:00 8/21 - AOI 2:00 | 1B 2T 93/852 | 8/17 - KIT CLEAR | 3 | 60 | X | 2023-08-15 | C |  | X | L3 | 13.5
2023-08-23 |  | L1 | 120011 |  |  | NEW | 300 | 8/23 5D | FEDEX P |  | 8/16 - BOT 3:30 8/16 - AOI 4:30 | 1B 1/1 | 8/16 - KIT CLEAR | 0 | 0 |  | 2023-08-15 | C |  | x | Sterling Medical Devices | 1
2023-08-23 | 2 | L2 | 119430 |  |  | NEW | 10 | 8/23 5D | FEDEX P | XRAY REQ QR CODE +1 LABEL REQS | 8/19 - BOT 10:00 8/19 - TOP 2:00 8/21 - AOI 2:30 | 1B 1T 36/499 | 8/16 - KIT CLEAR | 1 | 10 |  | 2023-08-16 | C |  | X | Anderson Connectivity | 10.5
2023-08-23 |  | L3 | 119866 |  |  | NEW | 5 | 8/23 3D | FEDEX P | *** 3 DAY TURN *** DEPANEL DNI #49 (C139, C140...) | 8/18 - BOT 6:00 8/18 - TOP 8:00 8/19 - AOI 10:00 | 2B 3T 219/1084 | 8/18 - KIT CLEAR | 23 | 115 |  | 2023-08-09 | C |  |  | Scythe Robotics | 12
2023-08-23 |  | L1 | 119182 |  |  | NEW | 50 | 8/23 5D | FEDEX P |  | 8/19 - BOT 8:30 8/19 - TOP 11:30 8/21 - AOI 10:30 | 1B 2T 109/285 | 8/16 - KIT CLEAR | 7 | 350 | X | 2023-08-10 | C |  | X | IonQ, Inc. | 10
2023-08-22 | 5 | L2/L3 | 117522-1 BAL |  | 7/21 - SHIP 77 OF 105 | NEW | 28 | 8/22 10D | UPS GND | *** MUST LOG ALL NON-CONFORMANCES BY SERIAL NUMBER *** | 7/10 - BOT 9:30 7/11 - TOP 11:00 7/11 - AOI 1:30 | 1B 1T 26/137 | 6/29 - SMT CLEAR 7/10 - RUN 77 OF 105 (short THT parts only) | 4 | 112 | X | 7/7 | C |  |  | ICC,Inc | 5
2023-08-22 |  | L1 | 119250 |  |  | NEW | 200 | 8/22 5D | FEDEX GND | DEPANEL | 8/17 - BOT 6:00 8/17 - TOP 1:00 8/18 - AOI 9:00 | 1B 2T 107/290 | 8/15 - KIT CLEAR | 1 | 200 | X | 2023-08-08 | C |  | X | ERI GROUP | 12
2023-08-22 |  | L2 | 119962 |  |  | NEW | 5 | 8/22 5D | UPS GND | DEPANEL MECH ASSY REQ | 8/17 - BOT 11:30 8/17 - TOP 8/17 - AOI 2:00 | 1B 1T 4/14 | 8/15 - KIT CLEAR | 73 | 365 |  | 2023-08-15 | C |  | X | Prima Power Laserdyne, LLC | 2.5
2023-08-22 | 1 | L2 | 119384 |  |  | NEW | 50 | 8/22 10D | FEDEX | DEPANEL | 7/28 - TOP 6:00 7/28 - AOI 8:00 | 1T 5/19 | 7/21 - SMT CLEAR | 19 | 950 |  | 2023-07-21 | C |  | X | Industrialex Manufacturing | 2
2023-08-21 |  | L2 | 119998 |  |  | NEW | 100 | 8/21 5D | FEDEX INTER | DEPANEL INTERNATIONAL SHIPMENT | 8/17 - TOP 8:00 8/17 - AOI 11:30 | 1T 6/8 | 8/14 - KIT CLEAR | 0 | 0 |  | 2023-08-14 | NC |  | X | IRD | 3.5
2023-08-21 |  | L3 | 120057-2 BAL |  |  | NEW | 5 | 8/21 5D | FEDEX P | Expedite 5 of 10 to ship 8/17 DEPANEL | 8/15 - BOT 11:30 8/16 - TOP 7:30 8/16 - AOI 12:00 | 1B 1T 61/340 | 8/14 - KIT CLEAR | 8 | 40 |  | 2023-08-14 | C |  | X | Hubble Network | 4.5
2023-08-21 |  | L1 | 119973 |  |  | NEW | 100 | 8/21 5D | FEDEX INTER | DO NOT TRIM J8 LEADS DEPANEL INTERNATIONAL SHIPMENT | 8/16 - TOP 1:30 8/16 - AOI 3:30 | 1T 10/17 | 8/14 - KIT CLEAR | 3 | 300 |  | 2023-08-10 | C |  | X | IRD | 2
2023-08-18 |  | L1 | 119437-1st |  |  | NEW | 5 | 8/18 5D | FEDEX P | SKIPPABLE #48 (U1) | 8/9 - BOT 1:00 8/10 - TOP 7:30 8/10 - AOI 9:30 | 1B 2T 111/320 | 8/2 - SHORT #48 (U1) 8/11 - KIT CLEAR | 0 | 0 |  | 2023-08-02 | C |  | X | Anderson Connectivity
2023-08-18 |  | L1 | 119822 |  |  | NEW | 30 | 8/18 5D | FEDEX 2D |  | 8/16 - TOP 11:00 8/16 - AOI 1:00 | 1T 3/24 | 8/11 - KIT CLEAR | 0 | 0 |  | 2023-08-14 | C |  | X | Ideal Innovations | 2
2023-08-18 | 1 | L1 | 118335 |  |  | NEW | 30 | 8/18 8/15 8/10 10D | FEDEX GND | Ship same time as B118334 DEPANEL | 8/2 - TOP 1:30 8/4 - AOI 8:30 | 1T 43/176 | 7/27 - KIT CLEAR | 8 | 240 |  | 2023-07-10 | C |  | X | EUSA Global | 5.5
2023-08-18 |  | L1 | 118334 |  |  | NEW | 100 | 8/18 8/15 10D | FEDEX GND | DEPANEL ECO #3: PARTS HEIGHT REQ ECO #4: Single box shipment PO: Ship in individual boxes | 8/2 - TOP 9:30 8/2 - AOI 4:30 | 1T 34/125 | 8/1 - KIT CLEAR | 35 | 3500 | X | 2023-07-25 | C |  | X | EUSA Global | 7
2023-08-18 |  | L3 | 118691 |  |  | NEW | 60 | 8/18 10D | UPS GND | DEPANEL | 8/9 - BOT 7:00 8/9 - TOP 10:00 8/9 - AOI 1:00 | 1B 1T 30/259 | 8/4 - KIT CLEAR | 65 | 3900 | X | 2023-08-04 | C |  | X | Graph-Tech USA, LLC | 6
2023-08-17 |  | L1 | 119812 |  |  | NEW | 250 | 8/17 3D | FEDEX P | *** 3 DAY TURN *** DEPANEL | 8/15 - BOT 11:00 8/16 - TOP 7:30 8/16 - AOI 11:00 | 1B 1T 22/36 | 8/14 - KIT CLEAR | 0 | 0 | X | 2023-08-10 | C |  | X | Procter & Gamble Company | 8
2023-08-17 |  | L3 | 118090-1ST |  |  | NEW | 1 | 8/17 5D | UPS RED | DEPANEL | 8/14 - TOP 6:00 8/14 - AOI 9:30 | 1T 43/1296 | 8/10 - KIT CLEAR | 15 | 15 |  | 2023-08-08 | C |  | X | Nottingham Spirk Design Associates, Inc.
2023-08-17 |  | L3 | 120057-1 PAR |  |  | NEW | 5 | 8/17 8/21 5D | FEDEX P | Expedite 5 of 10 to ship 8/17 DEPANEL | 8/15 - BOT 11:30 8/16 - TOP 7:30 8/16 - AOI 12:00 | 1B 1T 61/340 | 8/14 - KIT CLEAR | 8 | 40 |  | 2023-08-14 | C |  | X | Hubble Network | 4.5
2023-08-17 |  | L3 | 119499 |  |  | NEW | 6 | 8/17 5D | UPS GND | LABEL ON BOARD & BAG REQ SHIP BAT1 W/ PCBS FAI REQ DEPANEL | 8/14 - BOT 9:30 8/15 - TOP 6:00 8/15 - AOI 11:30 | 1B 2T 110/920 | 8/10 - KIT CLEAR | 20 | 120 |  | 2023-08-10 | C |  | X | Cogmedix, Inc.
2023-08-17 | 5 | L2 | 116119 |  |  | NEW | 120 | 8/17 5D | FEDEX GND | DEPANEL | 8/11 - TOP 8:00 8/11 - AOI 9:30 | 1T 3/3 | 8/10 - KIT CLEAR | 2 | 240 |  | 2023-08-09 | C |  |  | Emerson
2023-08-17 |  |  | 117369-1 PAR |  |  | NEW | 24 | 8/17 15D | UPS GND | DEPANEL J9 HEIGHT REQUIREMENT | 7/29 - BOT 12:00 7/29 - TOP 1:00 7/29 - AOI 2:00 | 1B 1T 15/22 | 7/27 - KIT CLEAR | 19 | 456 |  | 2023-07-27 | C |  | X | THORLABS | 2
2023-08-17 | 1 | L1/L3 | 118087-1 BAL |  |  | RONC 116713 | 50 | 8/17 8/22 10D | UPS RED | DEPANEL "J10,15,17" MUST BE FLUSH TO PCB, VERTICAL & NOT TILTED PER ECO 2 | 6/21 - TOP 2:00 6/23 - BOT 7:00 6/24 - AOI | 1B 1T 58/117 | 6/14 - KIT CLEAR 6/22 - TOP DONE | 20 | 1000 | X | 6/14 | NC | Y |  | ALLIANCE TECH
2023-08-16 |  | L3 | 119343-1ST |  |  | NEW | 2 | 8/16 8/15 5D | FEDEX P | DEPANEL XRAY & SAVE IMGS REQ (ECO) | 8/11 - BOT 6:00 8/11 - TOP 8:30 8/11 - AOI 12:00 | 2B 2T 140/655 | 8/8 - KIT CLEAR | 0 | 0 |  | 2023-08-08 | C |  | X | Anderson Connectivity | 6
2023-08-15 |  | L1 | 118979 |  |  | NEW | 20 | 8/15 10D | UPS GND | DEPANEL | 8/9 - BOT 7:30 8/9 - TOP 10:00 8/9 - AOI 1:00 | 1B 1T 58/350 | 8/2 - KIT CLEAR | 42 | 840 |  | 2023-08-02 | C |  | X | Thorlabs | 5.5
2023-08-14 | 10 | L2 | 118778 |  |  | NEW | 250 | 8/14 10D | FEDEX P | NO ADDITIONAL VENDOR MARK DEPANEL & SAND BOARDS REQ BAKING | 8/1 - BOT 6:00 8/1 - TOP 8/1 - AOI 2:00 | 1B 1T 4/5 | 7/31 - KIT CLEAR | 0 | 0 |  | 2023-07-27 | C |  | X | JHU APL Jackie Sharp | 8
2023-08-14 |  | L1 | 119068 |  |  | NEW | 6 | 8/14 5D | UPS RED | BTD #13 (C3...) & #43 (ATT4..) DEPANEL | 8/10 - TOP 9:30 8/11 - AOI 7:30 | 2T 64/421 | 8/7 - KIT CLEAR | 4 | 24 |  | 2023-08-07 | C |  | X | PACIFIC NORTHWEST NATIONAL LIBRARY
2023-08-14 | 1 | L3 | 114618-1 PAR |  | 7/26 - SMT CLEAR | NEW | 5 | 8/14 10D | FEDEX GND | SHIP 5 PCBS W/O J1 CLASS 3 PACKING SLIP PER ECO 5 | 5/15 - BOT 5:00 5/15 - TOP 9:00 | 1B 1T 78/768 | 8/8 - CLEARED FOR 5 OF 20 BOARDS | 10 | 50 | X | 5/9 | NC |  |  | MAGNIX
2023-08-14 |  |  | 119332 |  |  | RONC 115497 | 50 | 8/14 10D | UPS GND | DEPANEL CofC REQUIREMENTS | back | THT ONLY | 7/31 - KIT CLEAR | 1 | 50 |  | 2023-07-31 | C |  |  | Churchill Navigation dba Shotover Systems Inc
2023-08-14 | 2 | L1 | 119469 |  |  | NEW | 25 | 8/14 10D | UPS BLU | ECO #1: DO NOT TRIM LEADS (J4, J5) | 8/1 - BOT 7:30 8/1 - TOP 8:30 8/1 - AOI 11:30 | 1B 1T 35/99 | 7/31 - KIT CLEAR | 9 | 225 |  | 2023-07-28 | C |  | X | Rocky Research | 4
2023-08-14 |  | L2 | 119129-1 PAR |  |  | RONC 106266 | 135 | 8/14 10D | UPS ORG | CLASS 3 | 8/4 - BOT 2:00 8/8 - TOP 9:00 8/10 - AOI 9:30 | 2B 2T 120/400 | 7/31 - KIT CLEAR | 18 | 2430 | X | 2023-07-31 | C |  | X | COASTAL DESIGNS
2023-08-11 | 1 | L1 | 115809 |  |  | NEW | 10 | 8/11 3D | UPS RED | *** 3 DAY TURN *** ECO #2: HAND PLACE "TC1" "U1_EEPROM" CHANGED TO CAT24C512EI-GT3 PRESS FIT REQ SHIP U1 & U1_GPS W/ PCBS #16 DNI | 8/7 - TOP 6:00 8/7 - TOP DONE 8/8 - BOT 8:30 8/8 - AOI 11:30 | 1B 1T 69/298 | 8/8 - KIT CLEAR | 6 | 60 |  | 2023-07-19 | C | Y |  | AST Science | 4
2023-08-11 |  | L1 | 119067-2 BAL |  |  | RONC 115362 | 19 | 8/11 5D | FEDEX P | Build all 50 boards (30 w/ U9 & 20 w/o U9). Hold 19 boards w/o U9 & ship the rest. LABEL board w/o U9 Hand place 19 boards w/o U9 when parts come in. DEPANEL TRIM LEAD REQUIREMENTS | 7/26 - TOP 11:00 7/27 - BOT 7:00 7/27 - AOI 12:00 | 1B 2T 113/283 | 8/4 - KIT CLEAR | 17 | 323 |  | 2023-07-25 | C | X | X | Spectro | 10
2023-08-11 |  | L3 | 118259 |  |  | NEW | 85 | 8/11 5D | FEDEX GND | DEPANEL BARCODE LABEL | 8/8 - BOT 6:00 8/8 - TOP 9:30 8/10 - AOI 2:30 | 1B 1T 60/171 | 8/4 - KIT CLEAR 8/8 - THT PARTS WILL GO THROUGH REFLOW | 10 | 850 | X | 2023-08-03 | NC |  | X | Access Sensor Technologies | 6.5
2023-08-11 | 1 | L2 | 118705 |  |  | NEW | 100 | 8/11 10D | UPS GND | DEPANEL | 7/29 - BOT 8:00 7/31 - TOP 12:00 8/2 - AOI 10:00 | 1B 1T 80/513 | 7/28 - KIT CLEAR | 39 | 3900 | X | 2023-07-27 | C |  | X | Graph-Tech USA, LLC | 26
2023-08-10 |  | L1 | 119754 |  |  | NEW | 30 | 8/10 3D | UPS RED | *** 3 DAY TURN *** DEPANEL REV MARKING REQUIRED | 8/8 - BOT 11:30 8/9 - TOP 6:30 8/9 - AOI 7:30 | 2B 1T 91/310 | 8/7 - KIT CLEAR | 0 | 0 | X | 2023-08-02 | NC |  | X | Engenious Design | 7
2023-08-10 | 1 | L1 | 119071-1ST |  |  | NEW | 40 | 8/10 8/11 5D | FEDEX P | PARTIAL SHIP OF 30+ ON 8/10 NOTE: SEPARATE SHIPMENT ADDRESS FOR FA (SEE PO) XRAY & SAVE IMGS (SEE ECO) | 8/7 - TOP 7:00 8/7 - BOT 3:00 8/8 - AOI 8:30 | 1B 1T 64/173 | 8/4 - KIT CLEAR | 2 | 80 |  | 2023-08-04 | C | Y | X | TEST COACH COMPANY | 8
2023-08-10 |  | L1 | 119468 |  |  | RONC 115735 | 96 | 8/10 10D | FEDEX P | DEPANEL | 7/28 - BOT 12:00 7/28 - TOP 3:00 7/29 - AOI 9:30 | 1B 1T 38/117 | 7/27 - KIT CLEAR | 4 | 384 | X | 2023-07-27 | C |  | X | Beckman Coulter | 7
2023-08-09 | 1 | L3 | 119403 |  |  | NEW | 9 | 8/9 5D | FEDEX P | POST WASH BAKE REQUIREMENTS | 8/4 - TOP 2:30 8/7 - AOI 2:00 | 2T 113/475 | 8/2 - KIT CLEAR | 0 | 0 |  | 2023-07-27 | NC |  |  | John Hopkins University Applied Physics Lab | 6
2023-08-09 | 1 |  | 117989-RMA |  |  | NON PAID | 7 | 8/9 5D | FEDEX GND | NOT PAID REWORK | BACK | THT ONLY | 8/2 - CLEAR |  | 0 |  | 2023-07-25 | C |  | X | Durbin Group
2023-08-09 |  | L1 | 118974 |  |  | NEW | 15 | 8/9 10D | FEDEX P | DEPANEL | 8/4 - TOP 8:30 8/4 - BOT 10:00 8/4 - AOI 4:30 | 1B 1T 88/791 | 7/26 - KIT CLEAR | 13 | 195 | X | 2023-07-19 | C | Y |  | Omnisat | 8
2023-08-09 | 1 | L3 | 119565 |  |  | NEW | 50 | 8/9 5D | FEDEX P | DEPANEL | 8/3 - TOP 11:00 8/4 - AOI 8:00 | 1T 59/194 | 8/2 - KIT CLEAR | 4 | 200 |  | 2023-07-31 | NC |  | X | Spectro Inc. | 5
2023-08-09 |  | L3 | 119659 |  |  | NEW | 15 | 8/9 5D | UPS RED | DEPANEL MECH ASSY REQ | 8/3 - BOT 6:00 8/3 - TOP 8:00 8/3 - AOI 9:30 | 1B 1T 27/527 | 8/2 - KIT CLEAR | 26 | 390 |  | 2023-07-31 | C |  | X | Quarto Tech Services | 3.5
2023-08-08 |  | L2 | 119433-1st |  |  | NEW | 5 | 8/8 5D | FEDEX P | DEPANEL XRAY & SAVE IMGS | 8/4 - TOP 8:00 8/4 - BOT 11:30 8/4 - AOI 2:00 | 2B 1T 137/438 | 8/1 - KIT CLEAR | 0 | 0 |  | 2023-07-27 | C | Y | X | Anderson Connectivity | 6
2023-08-08 | 25 | L1 | 119677 |  |  | NEW | 100 | 8/8 5D | FEDEX P | DEPANEL | 8/2 - BOT 8:30 8/2 - TOP 10:00 8/2 - AOI 12:00 | 1B 1T 4/5 | 8/1 - KIT CLEAR | 0 | 0 |  | 2023-07-31 | C |  | X | Cognex Corporation | 3.5
2023-08-08 | 1 | L1 | 119672 |  |  | NEW | 30 | 8/8 5D | FEDEX P |  | 8/3 - TOP 8:30 8/3 - BOT 8/4 - AOI 9:30 | 1B 1T 62/201 | 8/1 - KIT CLEAR | 6 | 180 |  | 2023-07-28 | C | Y | X | Atlas Devices | 9
2023-08-08 | 1 | L1 | 118651 |  |  | NEW | 3 | 8/8 10D | FEDEX GND | MECH ASSY REQ | 8/1 - BOT 11:30 8/1 - AOI 2:00 | 1B 42/236 | 7/25 - KIT CLEAR | 64 | 192 |  | 2023-07-25 | C |  | X | L3 | 2.5
2023-08-08 | 4 | L3 | 118943 |  |  | NEW | 45 | 8/8 10D | FEDEX P | DEPANEL | 7/28 - TOP 11:00 7/29 - AOI 10:30 | 1T 47/180 | 7/25 - KIT CLEAR | 16 | 720 |  | 2023-07-25 | C |  | X | ABB | 8
2023-08-08 | 1 | L2 | 119660 |  |  | NEW | 15 | 8/8 5D | UPS RED |  | 7/27 - TOP 12:00 7/27 - AOI 2:00 | 1T 10/39 | 8/1 - KIT CLEAR | 80 | 1200 |  | 2023-07-26 | C |  | X | QUARTO TECH SERVICES | 2
2023-08-07 |  | L3 | 119051 |  |  | ROWC 117697 | 20 | 8/7 5D | FEDEX P | QUALITY ALERT! XRAY REQUIRED INCREASE REFLOW FOR J1131 ECO #3: CARE REQ FOR J1131 | 8/2 - BOT 9:00 8/2 - TOP 12:00 8/2 - AOI 3:00 | 1B 1T 55/275 | 7/31 - KIT CLEAR | 0 | 0 |  | 2023-07-26 | NC |  | X | Protocol Insight | 6
2023-08-07 |  | L1 | 118860-1st |  |  | NEW | 8 | 8/7 5D | FEDEX P | DEPANEL DATA MATRIX LABEL | 8/1 - BOT 3:00 8/1 - TOP 4:30 8/2 - 7:30 | 1B 1T 83/568 | 7/31 - KIT CLEAR | 6 | 48 |  | 2023-07-28 | C |  |  | ABB, Inc. Bartles Totalflow | 3
2023-08-07 |  | L2 | 118699 |  |  | NEW | 2 | 8/7 5D | FEDEX P | DEPANEL | 8/2 - TOP 6:00 8/2 - AOI 12:00 | 1T 58/1631 | 7/31 - KIT CLEAR | 158 | 316 |  | 2023-07-17 | C |  |  | Forza Silicon Corporation | 6
2023-08-07 | 3 | L1 | 118222-2nd BAL |  |  | RONC 1st | 80 | 8/7 8/4 5D | UPS RED | DEPANEL | 7/31 - BOT 6:00 7/31 - TOP 9:00 7/31 - AOI 3:00 | 1B 2T 108/253 | 7/28 - KIT CLEAR 7/20 - 5 HRS FOR QTY 25 | 6 | 480 | X | 2023-07-28 | C |  | X | Jabil | 9
2023-08-07 |  | L2 | 119534 |  |  | NEW | 35 | 8/7 3D | FEDEX P | *** 3 DAY TURN *** DEPANEL LABELS HAVE BEEN WAIVED | 8/2 - BOT 12:30 8/3 - TOP 8:00 8/4 - AOI 7:30 | 1B 2T 96/298 | 8/2 - KIT CLEAR | 15 | 525 | X | 2023-07-31 | C |  | X | Hoverfly Technologies Inc
2023-08-04 | 6 | L1 | 117371-2 PAR |  |  | NEW | 12 | 8/4 15D | UPS GND | DEPANEL NON-FLUSH J9 & J10 | 5/19 - BOT 11:00 5/19 - TOP 1:00 | 1B 1T 15/22 | 5/10 - KIT CLEAR | 18 | 216 |  | 5/11 | C |  |  | THORLABS | 2
2023-08-04 | 12 | L1 | 119616 |  |  | NEW | 48 | 8/4 5D | FEDEX P |  | 7/29 - BOT 9:30 7/29 - TOP 11:00 7/29 - AOI 12:00 | 1B 1T 42/82 | 7/28 - KIT CLEAR | 0 | 0 |  | 2023-07-27 | C |  | X | Signal Quest | 2.5
2023-08-04 | 1 | L3 | 118036 |  |  | NEW | 8 | 8/4 10D | UPS GND | CLASS 3 DEPANEL | 7/27 - BOT 2:00 7/28 - TOP 8:00 7/28 - AOI 11:00 | 2B 2T 154/634 | 7/21 - KIT CLEAR | 2 | 16 |  | 2023-07-19 | C |  |  | WWT International Coiled Tubing Services | 6
2023-08-04 | 1 | L1 | 119456 |  |  | NEW | 10 | 8/4 5D | FEDEX 2D | DEPANEL | 7/31 - BOT 3:00 8/1 - TOP 6:30 8/1 - AOI 7:30 | 1B 1T 31/76 | 7/28 - KIT CLEAR | 3 | 30 |  | 2023-07-28 | NC |  | X | Vigilant Onsite | 2.5
2023-08-04 | 1 | L1 | 119317 |  |  | NEW | 60 | 8/4 10D | FEDEX P | DNI #10 (D8) DEPANEL | 7/28 - TOP 8:30 7/28 - AOI 12:00 | 1T 30/110 | 7/21 - KIT CLEAR | 4 | 240 |  | 2023-07-21 | C |  |  | Turnkey Electronics Group | 3.5
2023-08-04 | 1 | L2 | 114318 |  |  | RONC 108951 | 102 | 8/4 10D | UPS 3 DAY |  | 7/26 - BOT 6:00 7/26 - TOP 8:30 7/27 - AOI 12:00 | 1B 1T 23/55 | 7/21 - KIT CLEAR | 3 | 306 |  | 2023-07-17 | C |  |  | Coastal Designs, LLC | 6
2023-08-04 | 1 | L3 | 119543 |  |  | NEW | 165 | 8/4 5D | FEDEX P | DEPANEL | 7/29 - BOT 10:30 7/31 - TOP 1:00 8/1 - AOI 3:00 | 1B 2T 65/422 | 7/28 - KIT CLEAR | 53 | 8745 | X | 2023-07-28 | NC |  | X | INDUSTRIALEX | 22
2023-08-03 |  | L2 | 119614 |  |  | NEW | 40 | 8/3 5D | UPS RED |  | 7/28 - BOT 8:00 7/28 - TOP 2:30 7/29 - AOI 8:00 | 1B 1T 15/500 | 7/27 - KIT CLEAR | 0 | 0 | X | 2023-07-27 | C |  | X | Samtec | 8
2023-08-02 | 1 | L3 | 118707 |  |  | NEW | 25 | 8/2 20D | UPS GND | DEPANEL (THOMAS) LABEL ON ESD BAG | 7/26 - BOT 5:00 7/26 - TOP 7:00 7/26 - AOI 9:30 | 1B 1T 59/190 | 7/5 - KIT CLEAR | 1 | 25 |  | 7/5 | C |  |  | Valco Melton, Inc | 4.5
2023-08-01 | 1 |  | 119436-1ST |  |  | NEW | 5 | 8/1 5D | FEDEX P | DEPANEL | back | THT ONLY | 7/25 - KIT CLEAR | 4 | 20 |  | 2023-07-25 | C |  |  | Anderson Connectivity
2023-08-01 | 1 | L1 | 118985-2ND |  |  | ROWC 1ST | 4 | 8/1 5D | FEDEX P | DNI R1_1..R1_18 2 boards w/ U10_1 (ADC3641) & 2 boards w/ U10_1 (ADC3642) | 7/26 - TOP 8:00 7/26 - AOI 11:00 | 1T 48/1482 | 7/25 - KIT CLEAR | 5 | 20 |  | 2023-07-25 | C |  | x | Hubble Network | 3
2023-08-01 | 1 | L1 | 118986-2ND |  |  | ROWC 1ST | 4 | 8/1 5D | FEDEX P | DNI R1_1..R1_18 2 boards w/ U10_1 (ADC3641) & 2 boards w/ U10_1 (ADC3642) DEPANEL | 7/25 - TOP 4:00 7/26 - AOI 8:00 | 1T 48/1492 | 7/25 - KIT CLEAR | 7 | 28 |  | 2023-07-25 | C |  | X | Hubble Network | 2.5
2023-08-01 | 1 | L2 | 118488 |  |  | NEW | 100 | 8/1 10D | FEDEX 2 DAY | DEPANEL | 7/24 - BOT 9:00 7/26 - TOP 2:00 7/27 - AOI 10:00 | 1B 1T 68/191 | 7/18 - KIT CLEAR | 5 | 500 | X | 2023-07-18 | C |  |  | TendoNova Corporation | 8
2023-08-01 |  | L1 | 119067-1 PAR |  |  | RONC 115362 | 31 | 8/1 5D | FEDEX P | Build all 50 boards (30 w/ U9 & 20 w/o U9). Hold 19 boards w/o U9 & ship the rest. LABEL board w/o U9 Hand place 19 boards w/o U9 when parts come in. DEPANEL TRIM LEAD REQUIREMENTS | 7/26 - TOP 11:00 7/27 - BOT 7:00 7/27 - AOI 12:00 | 1B 2T 113/283 | 7/25 - KIT CLEAR | 17 | 527 | X | 2023-07-25 | C | X | X | Spectro | 8
2023-08-01 | 1 |  | 119234 |  |  | RONC 112309 | 100 | 8/1 7/28 10D | UPS GND | MECH ASSY & GLUE REQ CABLE ASSY PDF | back | THT ONLY | 7/14 - KIT CLEAR BTD #37 | 68 | 6800 |  | 2023-07-15 | C |  |  | Technical Marine Service, Inc.
2023-08-01 |  | L1 | 119507 |  |  | NEW | 5 | 7/28 5D | FEDEX P | DEPANEL = P5 PIN 1 PICTURE SENT TO CUSTOMER FOR FURTHER EVAL | 7/25 - TOP 2:00 7/25 - AOI 4:00 | 1T 60/370 | 7/21 - KIT CLEAR | 15 | 75 |  | 2023-07-20 | C |  |  | MIDI Product Development Corporation | 2
2023-08-01 |  |  | 114814-2 |  |  |  | 105 |  | UPS RED |  |  |  |  | 1 | 105 | [5 empty] | Precision Graphics Inc
2023-07-31 | 1 | L3 | 119491 |  |  | NEW | 40 | 7/31 7/28 3D | FEDEX P | *** 3 DAY TURN *** DEPANEL #23 (D9) PLACE AS IS BARCODE LABEL REQ = L4 POLARITY QUESTION SENT TO CUSTOMER | 7/26 - BOT 9:30 7/27 - TOP 10:30 7/27 - AOI 2:00 | 1B 1T 74/233 | 7/25 - KIT CLEAR | 1 | 40 | X | 2023-07-25 | C | Y | X | Artis LLC | 5
2023-07-31 | 1 | L1 | 119646 |  |  | NEW | 10 | 7/31 3D | FEDEX P | *** 3 DAY TURN *** | 7/27 - TOP 9:00 7/28 - AOI 8:30 | 2T 96/375 | 7/26 - KIT CLEAR | 6 | 60 |  | 2023-07-25 | C |  | X | PRONTO | 8
2023-07-28 | 1 | L1 | 118985-1st |  |  | NEW | 8 | 7/28 5D | FEDEX P | SHARE PARTS WITH 118986 CLEANLINESS REQ WHEN HANDLING PCBS | 7/20 - TOP 10:30 7/24 - AOI 10:30 | 1T 48/1482 | 7/19 - KIT CLEAR | 5 | 40 | X | 2023-07-19 | C |  |  | Hubble Network | 5.5
2023-07-28 | 1 | L2 | 119463 |  |  | NEW | 5 | 7/28 5D | FEDEX P | DEPANEL Ship DNI parts with boards | 7/24 - TOP 7:00 7/24 - AOI 9:00 | 1T 14/477 | 7/21 - KIT CLEAR | 14 | 70 |  | 2023-07-21 | C |  |  | GlobalSim, Inc. | 2
2023-07-28 |  | L1 | 119371 |  |  | NEW | 10 | 7/28 5D | FEDEX GND | DEPANEL U2,U4,U6-U8,U13,U17-U19 HEIGHT REQUIRMENTS | 7/24 - TOP 10:30 7/24 - AOI 12:00 | 1T 20/196 | 7/21 - KIT CLEAR | 25 | 250 |  | 2023-07-21 | C |  |  | Keytronic
2023-07-27 | 1 | L3 | 119607 |  |  | NEW | 10 | 7/27 5D | FEDEX STANDARD | DEPANEL | 7/22 - BOT 1:00 7/24 - TOP 7:00 7/24 - AOI 10:00 | 1B 1T 13/420 | 7/20 - KIT CLEAR | 0 | 0 |  | 2023-07-20 | C |  |  | Kansas State University | 3.5
2023-07-27 | 2 | L1 | 119275-1ST |  |  | NEW | 5 | 7/27 5D | FEDEX P | DEPANEL DNI SW1 | 7/22 - TOP 11:30 7/22 - AOI 2:00 | 1T 51/117 | 7/20 - KIT CLEAR | 14 | 70 |  | 2023-07-20 | NC |  |  | Industrialex Manufacturing | 2.5
2023-07-27 |  | L1 | 119501 |  |  | NEW | 25 | 7/27 3D | FEDEX GND | *** 3 DAY TURN *** NO IN-HOUSE LABELS OR QA STAMPS | 7/24 - TOP 2:00 7/25 - AOI 9:00 | 2T 78/186 | 7/24 - KIT CLEAR | 3 | 75 |  | 2023-07-20 | C |  |  | Moxtek | 4.5
2023-07-27 | 1 | L2 | 119210 |  |  | NEW | 6 | 7/27 5D | FEDEX GND | DEPANEL FAIR REQUIRED | 7/21 - BOT 8:30 7/22 - TOP 10:00 7/22 - AOI 11:00 | 1B 1T 5/149 | 7/20 - KIT CLEAR | 49 | 294 |  | 2023-07-20 | C |  |  | Cogmedix, Inc.
2023-07-27 | 3 | L1 | 119305 |  |  | NEW | 200 | 7/27 7/25 5D | FEDEX P | DEPANEL | 7/20 - BOT 8:30 7/20 - TOP 10:00 7/24 - AOI 2:00 | 1B 1T 21/34 | 7/18 - KIT CLEAR 7/20 - U8 FOOTPRINT ISSUE (due 7/21 - 7/24) | 3 | 600 |  | 2023-07-18 | C |  |  | Open Source Instruments Inc
2023-07-27 | 1 | L1 | 119570 |  |  | NEW | 12 | 7/27 5D | FEDEX GND | DEPANEL SHIPPING ADDRESS REQUIREMENTS (ECO #4) *SPLIT SHIPMENT - SEE PO | 7/24 - TOP 6:00 7/24 - AOI 7:30 | 1T 27/175 | 7/20 - KIT CLEAR | 10 | 120 |  | 2023-07-20 | C |  |  | Panthalassa | 1.5
2023-07-27 | 2 | L3 | 118817 |  | 7/13 - SHIP DATE CHANGED FROM 7/26 TO 7/27 DUE TO ARRAY FILES | NEW | 60 | 7/27 7/26 10D | FEDEX P | DEPANEL FRAGILE THERMISTORS (HANDLE & SHIP W/ CARE) | 7/20 - TOP 9:30 7/20 - AOI 12:00 | 1T 44/149 | 7/12 - KIT CLEAR | 3 | 180 |  | 2023-07-12 | NC |  |  | Industrialex Manufacturing
2023-07-27 | 1 | L3 | 119130 |  |  | NEW | 125 | 7/24 5D | FEDEX GND | CLASSS 3 | 7/17 - BOT 6:30 7/18 - TOP | 1B 1T 27/376 | 710 - KIT CLEAR | 5 | 625 | X | 2023-07-10 | C |  |  | Coastal Designs | 1.5
2023-07-27 | 1 | L1 | 119079 |  |  | NEW | 20 | 7/26 3D | UPS RED | *** 3 DAY TURN *** DEPANEL | 7/21 - BOT 11:00 7/22 - TOP 10:30 7/22 - AOI 11:30 | 1B 1T 82/496 | 7/21 - KIT CLEAR | 0 | 0 | X | 2023-07-20 | C |  |  | Hoverfly Technologies Inc | 8.5
2023-07-27 | 1 | L2 | 119566 |  |  | NEW | 50 | 7/26 7/25 3D | UPS RED | *** 3 DAY TURN *** DEPANEL PACKING SLIP REQUIREMENTS | 7/22 - BOT 11:00 7/24 - TOP 7/25 - AOI 10:30 | 1B 1T 81/153 | 7/20 - KIT CLEAR | 11 | 550 |  | 2023-07-19 | C |  |  | Scalvy Inc
2023-07-26 | 1 | L3 | 119078 |  |  | NEW | 20 | 7/26 3D | UPS RED | *** 3 DAY TURN *** DEPANEL | 7/24 - TOP 10:00 7/24 - BOT 2:30 7/25 - AOI 2:00 | 2B 2T 152/615 | 7/21 - FABS DUE | 11 | 220 | X | 2023-07-20 | C | Y |  | Hoverfly Technologies Inc
2023-07-26 | 1 | L1 | 119254 |  |  | NEW | 2 | 7/26 5D | FEDEX P | DEPANEL | 7/20 - TOP 7/20 - AOI 8:30 | 1T 19/105 | 7/19 - KIT CLEAR | 118 | 236 |  | 2023-07-18 | C |  |  | Globalsim, Inc.
2023-07-26 | 6 | L1 | 118749 |  |  | ROWC 115888 | 50 | 7/26 3D | FEDEX P | *** 3 DAY TURN *** DEPANEL All parts must be flush to PCB MECH ASSY & Thermal Paste | 7/15 - TOP 1:00 7/17 - AOI 8:30 | 1T 29/59 | 7/21 - KIT CLEAR | 35 | 1750 |  | 2023-07-14 | C |  | X | Industrialex Manufacturing | 3
2023-07-25 | 1 | L1 | 118929 |  |  | NEW | 12 | 7/25 3D | FEDEX P | *** 3 DAY TURN *** BARCODE LABEL | 7/20 - TOP 3:00 7/21 - AOI 11:00 | 2T 72/707 | 7/20 - KIT CLEAR | 0 | 0 | X | 2023-07-20 | C |  | X | GatesAir, Inc. | 5
2023-07-25 |  | L3 | 118963 |  |  | NEW | 3 | 7/25 3D | FEDEX P | *** 3 DAY TURN *** DEPANEL NO PRESS FIT RECOMMENDED | 7/20 - BOT 12:30 7/20 - TOP 2:30 7/21 - AOI 8:30 | 1B 2T 78/695 | 7/20 - KIT CLEAR | 22 | 66 |  | 2023-07-12 | C |  | X | IonQ, Inc. | 3
2023-07-25 | 1 | L3 | 119082 |  |  | NEW | 20 | 7/25 3D | UPS RED | *** 3 DAY TURN *** DEPANEL U7 PLACE AS IS | 7/21 - BOT 8:30 7/21 - TOP 1:00 7/22 - AOI 1:00 | 1B 2T 101/325 | 7/20 - KIT CLEAR | 20 | 400 |  | 2023-07-20 | C |  |  | Hoverfly Technologies Inc
2023-07-25 |  | L1 | 119012 |  |  | NEW | 75 | 7/25 10D | UPS GND | DEPANEL POST BAKE REQUIREMENTS | 7/11 - TOP 12:00 7/11 - AOI 1:30 | 1T 6/12 | 7/10 - SMT CLEAR; RUN 7/11 - KIT CLEAR | 11 | 825 |  | 2023-07-10 | C |  |  | Solar Stik, Inc. | 1.5
2023-07-25 | 1 | L1/L3 | 118087-1 PAR2 |  |  | RONC 116713 | 50 | 7/25 10D | UPS RED | DEPANEL "J10,15,17" MUST BE FLUSH TO PCB, VERTICAL & NOT TILTED PER ECO 2 | 6/21 - TOP 2:00 6/23 - BOT 7:00 6/24 - AOI | 1B 1T 58/117 | 6/14 - KIT CLEAR 6/22 - TOP DONE | 20 | 1000 | X | 6/14 | NC | Y |  | ALLIANCE TECH
2023-07-25 | 1 | L3 | 119356 |  |  | NEW | 39 | 7/25 7/24 5D | FEDEX GND *** | BTD #9 (R81, R82...) #9 SHOULD BE SHORT ON 2 BOARDS ONLY | 7/17 - BOT 11:00 7/19 - TOP 1:00 7/20 - AOI | 1B 1T 12/380 | 7/17 - KIT CLEAR | 0 | 0 | X | 2023-07-14 | C |  |  | Polarity Inc.
2023-07-25 | 15 | L3 | 118922 |  |  | NEW | 165 | 7/25 7/24 10D | DHL | DO NOT DEPANEL XTRA TIME REQ FOR INSPECTION REQ TAD REVIEW BEFORE RUN | 7/14 - BOT 8:30 7/14 - TOP 12:30 7/17 - AOI 6:30 | 1B 1T 4/9 | 7/10 - KIT CLEAR | 0 | 0 | X | 2023-07-10 | NC |  | - | Listen AS
2023-07-24 | 1 | L3/L2 | 117914 |  |  | ROWC 112216 | 540 | 7/24 10D | FEDEX P | DEPANEL XRAY & SAVE IMAGES | 7/11 - BOT 1:30 7/14 - TOP 10:00 7/21 - AOI 8:30 | 2B 2T 84/373 | 7/10 - KIT CLEAR | 0 | 0 | X | 2023-07-10 | C |  | - | Sea Land Aire
2023-07-24 | 4 | ALL | 118407 |  |  | NEW | 50 | 7/24 7/20 3D | FEDEX P | *** 3 DAY TURN *** ***DO NOT DEPANEL*** | 7/17 - BOT 10:30 7/18 - TOP 9:30 7/22 - AOI 10:00 | 1B 1T 110/224 | 7/17 - KIT CLEAR | 2 | 100 |  | 2023-07-10 | C |  | X | John Hopkins University Applied Physics Lab
2023-07-24 | 1 | L3 | 119083 |  |  | NEW | 20 | 7/24 3D | UPS RED | *** 3 DAY TURN *** DEPANEL | 7/19 - BOT 9:30 7/19 - TOP 10:30 7/20 - AOI 6:30 | 1B 1T 57/142 | 7/19 - KIT CLEAR | 20 | 400 |  | 2023-07-18 | C |  |  | Hoverfly Technologies Inc
2023-07-21 | 1 | L1 | 118820-1st |  |  | NEW | 2 | 7/21 5D | UPS GND | CLASS 3 DEPANEL PRESS FIT REQ | 7/19 - BOT 7:00 7/19 - TOP 7/19 - AOI 10:00 | 1B 1T 68/253 | 7/14 - KIT CLEAR | 10 | 20 |  | 7/6 | C |  |  | Diversified Supply | 3
2023-07-21 | 1 | L1 | 118986-1ST |  |  | NEW | 8 | 7/21 3D | FEDEX P | *** 3 DAY TURN *** DEPANEL ECO #3: USE ADC3641 CLEANLINESS CARE REQ WHEN HANDLING PCBS | 7/19 - TOP 10:00 7/20 - AOI | 1T 48/1492 | 7/18 - KIT CLEAR | 7 | 56 | X | 2023-07-18 | C |  |  | Hubble Network
2023-07-21 | 5 | L2/L3 | 117522-1 PAR |  |  | NEW | 77 | 7/21 10D | UPS GND | *** MUST LOG ALL NON-CONFORMANCES BY SERIAL NUMBER *** | 7/10 - BOT 9:30 7/11 - TOP 11:00 7/11 - AOI 1:30 | 1B 1T 26/137 | 6/29 - SMT CLEAR 7/10 - RUN 77 OF 105 (short THT parts only) | 4 | 308 | X | 7/7 | C |  |  | ICC,Inc | 5
2023-07-21 | 10 | L1 | 119410 (7/13) |  |  | ROWC 118836 | 200 | 7/20 5D | FEDEX P | DEPANEL MIX POP - 50 boards: Use P/N GRT1555C1H102FA02D for C5, C9, C10, C11, C13, C14, C15 Label S/N: XXXAV3 where XXX: 201-250 150 board: Use P/N GRM1557U1A202JA01D for C5, C9, C10, C11, C13, C14, C15 Label S/N: XXX AV4 where XXX: 251-400 | 7/14 - BOT 10:00 7/14 - TOP 12:00 7/15 - AOI 1:00 | 1B 1T 26/59 | 7/13 - KIT CLEAR | 4 | 800 | X | 2023-07-13 | C |  | X | Open Source Instruments Inc | 5.5
2023-07-20 | 1 | L3 | 118812 |  |  | NEW | 1 | 7/20 10D | FEDEX P |  | 7/17 - BOT 8:30 7/17 - TOP 9:30 7/17 - AOI 11:00 | 1B 1T 54/473 | 7/6 - KIT CLEAR | 2 | 2 |  | 7/6 | NC |  | X | Vesperix
2023-07-20 | 1 | L1 | 118626 |  |  | NEW | 3 | 7/20 10D | UPS RED | DEPANEL CofC REQUIREMENTS | 7/18 - TOP 9:30 7/18 - BOT 11:00 7/18 - AOI 12:00 | 1B 1T 90/653 | 7/6 - KIT CLEAR | 1 | 3 |  | 7/6 | C | Y | X | Reliable Robotics | 2.5
2023-07-20 | 3 | L1 | 118222-1ST |  |  | NEW | 25 | 7/20 5D | UPS RED | *** JOB EXPEDITED *** DEPANEL | 7/18 - BOT 12:30 7/18 - TOP 3:00 7/19 - AOI 7:00 | 1B 2T 108/253 | 7/18 - KIT CLEAR | 6 | 150 |  | 2023-07-10 | C |  | X | Jabil Inc. | 5
2023-07-20 | 15 | L1 | 118847-1 BAL |  |  | NEW | 424 | 7/31 10D | FEDEX P | DEPANEL DEPANEL SIDE WITH USB-CONN BEFORE RUN 50 PCS DUE 7/19 | 7/15 - BOT 6:00 7/15 - TOP 9:00 7/15 - AOI 12:00 | 1B 1T 6/7 | 7/12 - WILL CLEAR 7/14 - PARTIAL CLEAR | 0 | 0 |  | 2023-07-11 | NC |  | - | Hip Science | 6
2023-07-19 | 15 | L1 | 118847-1 PAR |  |  | NEW | 50 | 7/19 10D | FEDEX P | DEPANEL DEPANEL SIDE WITH USB-CONN BEFORE RUN 50 PCS DUE 7/19 | 7/15 - BOT 6:00 7/15 - TOP 9:00 7/15 - AOI 12:00 | 1B 1T 6/7 | 7/12 - WILL CLEAR 7/14 - PARTIAL CLEAR | 0 | 0 |  | 2023-07-11 | NC |  | - | Hip Science | 6
2023-07-19 |  | L1 | 118841 |  |  | NEW | 5 | 7/19 3D | FEDEX P | *** 3 DAY TURN *** DEPANEL | 7/13 - BOT 6:00 7/13 - TOP 9:00 7/13 - AOI 11:30 | 1B 2T 95/1464 | 7/12 - SHORT #41 & 50 - OK TO SKIP 7/18 - KIT CLEAR | 4 | 20 |  | 2023-07-11 | C |  |  | Orbit Fab | 5.5
2023-07-18 | 143 |  | 117479- RWK2 |  |  | UNPAID RWK | 286 | 7/19 10D | UPS BLU | CLASS 3 DO NOT DEPANEL | 7/5 - BACK | THT ONLY | 7/5 - CLEAR | 0 | 0 |  | 7/5 | C |  |  | Monzite dba Impellimax
2023-07-18 | 1 | L3 | 118307 |  |  | NEW | 8 | 7/20 7/12H 10D | FEDEX P | DEPANEL S/N REQUIREMENTS | 7/8 - BOT 1:30 7/10 - TOP 7:30 7/10 - AOI 9:30 | 1B 1T 17/53 | 6/27 - REC'D XTRA TIME 6/27 - KIT CLEAR | 56 | 448 |  | 6/27 | C |  | X | Philips Healthcare | 4.5
2023-07-18 | 1 | L2 | 118743 |  |  | NEW | 20 | 7/18 5D | FEDEX SUPER SAVER | DEPANEL BTD & WRITE LIST PARTS SHORT (IF ANY) SEND TO CUSTOMER | 7/11 - TOP 10:30 7/13 - BOT 7/14 - AOI 11:30 | 2B 1T 104/440 | 7/11 - KIT CLEAR | 10 | 200 | X | 2023-07-11 | C | Y | X | Kopin Corporation | 12
2023-07-18 | 1 | L1 | 118256 |  |  | NEW | 9 | 7/18 5D | FEDEX GND | XTRA TIME IN THT REQ WRITE LIST OF RES + CAPS & SEND TO CUSTOMER | 7/11 - BOT 2:00 7/12 - TOP 8:30 7/12 - AOI 2:00 | 1B 2T 136/665 | 7/11 - KIT CLEAR | 23 | 207 |  | 6/26 | C |  | X | Cummins-Allison Corp | 8
2023-07-18 | 12 | L1 | 119043 |  |  | NEW | 150 | 7/18 3D | FEDEX P | *** 3 DAY TURN *** DEPANEL | 7/13 - BOT 12:45 7/13 - TOP 6:30 7/13 - AOI 10:00 | 1B 1T 40/99 | 7/13 - FABS DUE 7/13 - KIT CLEAR | 2 | 300 | X | 2023-07-11 | C |  | X | Edge Autonomy | 6
2023-07-18 | 1 | L2 | 119038 |  |  | RONC 118402 | 92 | 7/17 5D | FEDEX P | POST BAKE REQUIREMENTS | 7/11 - TOP 7:30 7/11 - BOT 2:00 7/12 - AOI 10:30 | 1B 1T 49/120 | 7/10 - KIT CLEAR | 21 | 1932 | X | 2023-07-10 | C | y | X | Atlas Devices | 8.5
2023-07-17 | 1 | L3 | 116819-1st |  |  | NEW | 1 | 7/17 5D | FEDEX GND | *** DO NOT SOLDER J1 & J2 *** | 7/11 - BOT 8:30 7/11 - TOP 9:30 7/11 - AOI 11:00 | 1B 1T 33/799 | 7/10 - KIT CLEAR | 8 | 8 |  | 7/5 | C |  | X | Mission Support and Test Services, Inc | 2.5
2023-07-17 |  | L3 | 119377-2 |  |  | NEW | 8 | 7/17 2D | FEDEX P | *** 2 DAY TURN *** DEPANEL LABEL ON ESD BAG | 7/13 - BOT 10:00 7/13 - TOP 1:15 7/13 - AOI 8:30 | 1B 2T 121/515 | 7/13 - SHORT PARTS DUE 7/13 - SHORT ONLY 1 ITEM (CAP) - OK TO SKIP | 10 | 80 |  | 2023-07-12 | C |  | X | ZapBatt, Inc. | 8
2023-07-14 | 143 |  | 117479- RWK1 |  |  | UNPAID RWK | 858 | 7/19 10D | UPS BLU | CLASS 3 DO NOT DEPANEL | 7/5 - BACK | THT ONLY | 7/5 - CLEAR | 0 | 0 |  | 7/5 | C |  |  | Monzite dba Impellimax
2023-07-14 |  |  | 114814-2 |  |  |  | 105 |  | UPS RED |  |  |  |  | 1 | 105 | [5 empty] | Precision Graphics Inc
2023-07-14 |  | L3 | 119377-1 PAR |  |  | NEW | 4 | 7/14 2D | FEDEX P | *** 2 DAY TURN *** * PAID EXPEDITE * 7/14 - SHIP QTY 4 BAL QTY 8 DUE 7/17 DEPANEL LABEL ON ESD BAG | 7/13 - BOT 10:00 7/13 - TOP 1:15 7/13 - AOI 4:30 | 1B 2T 121/515 | 7/13 - SHORT PARTS DUE 7/13 - SHORT ONLY 1 ITEM (CAP) - OK TO SKIP 7/13 - PAID EXPEDITE APPVD | 10 | 40 |  | 2023-07-12 | C |  | X | ZapBatt, Inc. | 6
2023-07-13 | 1 | L1 | B118253-2ND |  |  | ROWC 1ST | 10 | 7/13 5D | UPS RED | DEPANEL VERIFY NUTS ARE W/ PCB | 7/7 - BOT 8:30 7/7 - TOP 11:00 7/7 - AOI 3:30 | 1B 2T 89/653 | 7/6 - KIT CLEAR | 56 | 560 |  | 7/6 | C |  |  | Biolog | 7
2023-07-13 | 2 | L1 | 118879 |  |  | NEW | 30 | 7/12 5D | FEDEX P |  | 7/10 - BOT 1:30 7/11 - TOP 8:30 7/11 - AOI 12:00 | 1B 1T 73/678 | 7/5 - KIT CLEAR | 7 | 210 |  | 7/5 | C |  |  | Puzzle Medical Devices | 6
2023-07-13 | 1 | L1 | 118993-1ST BAL |  |  | NEW | 16 | 7/13 5D | UPS Red |  | 7/8 - TOP 10:30 7/8 - BOT 12:30 7/8 - AOI 1:30 | 1B 1T 44/194 | 7/6 - KIT CLEAR | 5 | 80 |  | 7/6 | C | Y | X | IoTecha | 2
2023-07-13 | 1 | L1 | 117047-1ST |  |  | NEW | 2 | 7/13 5D | FEDEX P | DEPANEL | 7/10 - TOP 11:30 7/10 - AOI 1:30 | 1T 43/318 | 7/6 - KIT CLEAR | 84 | 168 |  | 7/6 | C |  |  | Biolog | 2
2023-07-12 | 1 | L3 | 118285 |  |  | NEW | 10 | 7/12H 10D | FEDEX P | DEPANEL | 7/7 - BOT 1:00 7/8 - TOP 11:00 7/8 - AOI 1:30 | 1B 1T 51/556 | 6/27 - KIT CLEAR | 8 | 80 |  | 6/27 | C |  |  | Genuen,LLC | 6.5
2023-07-12 | 2 | L1 | 119010 |  |  | NEW | 2 | 7/12 5D | FEDEX P | DEPANEL | 7/10 - BOT 9:30 7/10 - TOP 10:30 7/10 - AOI 11:30 | 1B 1T 35/306 | 7/5 - KIT CLEAR | 91 | 182 |  | 7/5 | C | Y | X | Forza Ametek | 2
2023-07-12 | 1 | L1 | 118882 |  |  | NEW | 4 | 7/12 3D | UPS RED | *** 3 DAY TURN *** CLASS 3 DEPANEL MECH ASSY W/ TORQUE CofC REQUIREMENTS | 7/7 - BOT 2:00 7/8 - TOP 7:30 7/8 - AOI 10:30 | 1B 1T 124/714 | 7/7 - KIT CLEAR | 57 | 228 |  | 6/30 | C |  | X | Stoke Space Technologies | 5
2023-07-12 | 1 | L3 | 118789 |  |  | NEW | 50 | 7/12 5D | FEDEX P | DEPANEL NO QA STAMPS NO IN-HOUSE LABELS | 7/10 - TOP 10:30 7/11 - AOI 8:30 | 2T 66/339 | 7/5 - KIT CLEAR | 9 | 450 | X | 7/5 | C |  | X | Moxtek | 6.5
2023-07-11 | 1 | L1 | 118993-1ST PAR |  |  | NEW | 4 | 7/13 5D | UPS Red |  | 7/8 - TOP 10:30 7/8 - BOT 12:30 7/8 - AOI 1:30 | 1B 1T 44/194 | 7/6 - KIT CLEAR | 5 | 20 |  | 7/6 | C | Y | X | IoTecha | 2
2023-07-11 | 5 | L1 | 117580 |  |  | NEW | 200 | 7/12H 10D | FEDEX GND | DEPANEL | 6/23 - BOT 9:00 7/10 - AOI 8:30 | 1B 1/2 | 6/12 - KIT CLEAR | 0 | 0 |  | 6/1 | C |  | - | Sterling Medical Devices
2023-07-11 | 1 | L1 | 118885 |  |  | RONC 114417 | 25 | 7/11H 10D | FEDEX GND |  | 7/6 - BOT 1:00 7/6 - TOP 3:30 7/7 - AOI 8:30 | 1B 1T 33/82 | 6/26 - KIT CLEAR | 12 | 300 |  | 6/26 | C |  |  | CACI
2023-07-10 | 1 | L2 | 119029 |  |  | NEW | 60 | 7/10H 5D | FEDEX P | DEPANEL | 7/6 - TOP 8:00 7/7 - AOI 12:00 | 1T 10/100 | 6/30 - KIT CLEAR | 0 | 0 |  | 6/30 | C |  |  | Bruker Nano, RMR | 2.5
2023-07-10 | 1 | L1 | 118731 |  |  | NEW | 5 | 7/10H 10D | FEDEX P | DEPANEL POST BACK REQUIREMENTS | 7/6 - TOP 8:30 7/6 - AOI 1:00 | 2T 67/484 | 6/23 - KIT CLEAR | 21 | 105 |  | 6/23 | C |  |  | Bruker Nano, RMR | 4.5
2023-07-10 | 2 | L1 | 118965 |  |  | NEW | 20 | 7/10H 5D | FEDEX P | DEPANEL CofC REQUIREMENTS | 7/6 - TOP 8:30 7/6 - AOI 1:00 | 1T 21/229 | 6/30 - KIT CLEAR | 37 | 740 |  | 6/28 | C |  |  | RollPros,LLC | 8
2023-07-07 | 2 | L1 | 118473-2ND |  |  | RONC 1ST | 65 | 7/10 7/7H 5D | FEDEX P | QR CODE REQ TRIM LEAD REQ CONFORMAL COATING REQ | 7/5 - BOT 10 7/5 - TOP 1:00 7/6 - AOI 8:30 | 1B 1T 73/150 | 6/12 - KIT CLEAR (+1 DAY TO SHIP) | 16 | 1040 | X | 6/29 | C |  |  | Industrialex Manufacturing | 51
2023-07-07 | 1 | L3 | 118007 |  |  | RONC 107990 | 4000 | 7/7H 20D | FEDEX P | DEPANEL | 6/28 - TOP 8:00 6/30 - BOT 4:30 7/6 - AOI 3:30 | 1B 1T 28/29 | 6/8 - KIT CLEAR | 0 | 0 | X | 6/7 | C | Y |  | Moates.Net | 0.5
2023-07-07 | 1 | L1 | 119011 |  |  | NEW | 2 | 7/7H 5D | FEDEX P |  | 7/5 - BOT 9:30 7/5 - AOI 10:00 | 1B 6/128 | 6/29 - KIT CLEAR | 91 | 182 |  | 6/29 | C |  |  |  | 4.5
2023-07-07 | 2 | L2 | 118436 |  |  | RONC 104894 | 50 | 7/7H 5D | UPS GND | DEPANEL CofC REQUIREMENTS | 6/30 - BOT 9:30 7/5 - TOP 11:00 7/5 - AOI 2:00 | 1B 1T 32/131 | 6/29 - KIT CLEAR | 7 | 350 |  | 6/29 | C |  |  | Churchill Navigation dba Shotover Systems Inc
2023-07-06 |  | L1/HOLD | 118863 |  |  | NEW | 1 | 7/6H 10D | FEDEX P | DEPANEL THT ONLY | 6/21 - BACK | THT ONLY | 6/21 - KIT CLEAR | 22 | 22 |  | 6/16 | C |  |  | Technical Marine Service, Inc
2023-07-06 | 1 | L1/HOLD | 114721 |  |  | ROWC 1ST | 23 | 6/30 10D | FEDEX P | DEPANEL *WIRES REQ ECO #6 | 6/26 - BOT 7:00 6/26 - TOP 9:00 6/26 - AOI 11:00 | 1B 2T 53/228 | 6/16 - KIT CLEAR | 17 | 391 |  | 6/16 | C |  |  | Anderson Connectivity
2023-07-06 | - |  | 118863 |  |  | NEW | 60 | 7/6H 10D | UPS GND | DEPANEL THT ONLY | 6/21 - BACK | THT ONLY | 6/21 - KIT CLEAR | 22 | 1320 |  | 6/21 | C | - |  | Technical Marine Service, Inc
2023-07-06 | 1 |  | 118107-2 |  |  | NEW | 25 | 7/6H 6/30 20D | FEDEX P | *REVIEW JOB & ECO THOROUGHLY | 6/23 - BACK | 1B 1T 48/197 | 5/25 - KIT CLEAR | 15 | 375 | X | 5/25 | C | Y |  | Industrialex Manufacturing | 2
2023-07-06 | 2 | L1 | 118498 |  |  | RONC 118079 | 2 | 7/6H 5D | UPS RED | DEPANEL | 6/30 - TOP 6:00 6/30 - AOI 8:00 | 1T 1/40 | 6/28 - KIT CLEAR | 47 | 94 |  | 6/28 | C |  |  | Siemens Inustry, Inc. | 8
2023-07-06 | 2 | L1 | 118682 |  |  | NEW | 12 | 7/6H 5D | FEDEX P | DEPANEL | 6/30 - BOT 8:00 6/30 - TOP 12:00 6/30 - AOI 4:00 | 1B 1T 94/634 | 6/28 - KIT CLEAR | 6 | 72 |  | 6/26 | C |  |  | John Hopkins University Applied Physics Lab
2023-07-05 | 1 | L1 | 113842-2BAL |  |  |  | 3 | 7/6 3D + 2D FOR RWK | FEDEX GND | *** 3 DAY TURN PLUS 2 DAYS FOR RWK *** CLASS 3 * HEAVY RWK REQ -- SEE INSTRUCTIONS! * | 6/12 - BOT DONE 6/28 - TOP 8:30 6/26 - AOI 1:00 | 2B 3T 179/1326 | 6/9 - QTY 3 PARTIAL CLEAR - CUST PAID 6/27 - KIT CLEAR | 23 | 69 |  | 6/27 | NC |  |  | Magnix | 3
2023-07-05 | 6 | L2 | 118435 |  |  | NEW | 50 | 7/5H 5D | UPS GND | DEPANEL CofC REQUIREMENTS | 6/29 - BOT 8:00 6/29 - TOP 9:30 6/29 - AOI 11:00 | 1B 1T 23/118 | 6/27 - KIT CLEAR | 10 | 500 |  | 6/26 | C |  |  | Churchill Navigation dba Shotover Systems Inc
2023-07-05 | 1 | L1 | 118696 |  |  | NEW | 20 | 7/5H 6/30 5D | FEDEX GND | DEPANEL | 6/24 - AOI | 1T 37/199 | 6/23 - KIT CLEAR | 20 | 400 |  | 6/16 | C |  |  | Flir | 5.5
2023-07-05 | 1 | L1 | 118323 |  |  | NEW | 50 | 7/5 5D | UPS RED | CLASS 3 | 6/28 - BOT 1:00 6/28 - TOP 4:30 6/29 - AOI 8:00 | 1B 2T 80/682 | 6/27 - KIT CLEAR | 7 | 350 | X | 6/23 | C |  |  | Coastal Designs | 2
2023-07-05 | 10 |  | 118656 |  |  | NEW | 125 | 6/30 5D | FEDEX P | DEPANEL *** PART HEIGHT REQ | 6/29 - TOP 11:00 6/29 - AOI 1:00 | 1T 15/19 | 6/21 - KIT CLEAR | 0 | 0 |  | 6/21 | C |  |  | Blueline Sensors LLC
2023-06-30 | 1 | L3 | 113841-1 PAR |  |  | NEW | 6 | 7/1 OR 6/30 3D | FEDEX GND | *** 3 DAY TURN *** CofC & PACK SLIP PER ECO #3 & 4 MATL EXIT AUDIT REQ | 5/11 - BOT 10:00 5/11 - TOP 12:00 5/12 - AOI 7:00 | 1B 1T 78/750 | 6/27 - KIT CLEAR | 8 | 48 |  | 5/9 | NC |  |  | Magnix | 3
2023-06-30 | 1 | L1 | 115385 |  |  | NEW | 1 | 6/30 10D | FEDEX GND |  | 6/28 - BOT 6:00 6/28 - TOP 7:30 6/28 - AOI 8:30 | 1B 2T 104/264 | 6/19 - KIT CLEAR | 15 | 15 |  | 6/19 | C |  |  | CACI | 2.5
2023-06-30 | 10 | L3 | 118836 |  |  | ROWC 118518 | 200 | 6/30 5D | FEDEX P | DEPANEL MIX POP FOR #2A & 2B | 6/26 - BOT 2:00 6/27 - TOP 12:00 AOI - UNKNOWN | 1B 1T 26/59 | 6/23 - KIT CLEAR | 4 | 800 | X | 6/22 | C |  |  | Open Source Instruments, Inc.
2023-06-30 | 1 | L1 | 118769 |  |  | NEW | 30 | 6/30 5D | UPS RED | DEPANEL MECH ASSY | 6/26 - BOT 1:30 6/26 - TOP 4:30 6/27 - AOI UNKNOWN | 2B 2T 148/533 | 6/23 - KIT CLEAR | 51 | 1530 | X | 6/22 | C | Y |  | Reprieve Cardiovascular, Inc.
2023-06-30 | 60 | L3 | 118432 |  |  | RONC 100471 | 400 | 6/30 10D | UPS RED |  | 6/22 - TOP 10:30 6/26 - AOI 12:00 | 1T 37/199 | 6/7 - KIT CLEAR | 1 | 400 |  | 6/5 | C |  |  | Superior Swim Timing
2023-06-29 | 4 | L1 | 118636 |  |  | NEW | 10 | 6/29 5D | UPS RED | DEPANEL | 6/23 - BOT 1:30 6/24 - AOI | 1B 1T 71/261 | 6/22 - KIT CLEAR | 14 | 140 |  | 6/14 | C |  |  | Spark Technologies LLC
2023-06-29 | 1 | L2 | 118399 |  |  | NEW | 50 | 6/29 10D | FEDEX P | DEPANEL | 6/24 - BOT 7:00 6/26 - TOP 9:00 6/27 - AOI 11:30 | 1B 1T 87/264 | 6/20 - KIT CLEAR | 6 | 300 |  | 6/20 | C |  |  | Powercast Corporation
2023-06-29 | 10 | L2 | 118926 |  |  | NEW | 120 | 6/29 3D | FEDEX P | *** 3 DAY TURN *** DEPANEL PCBS ARE FLUX FREE | 6/27 - BOT 11:30 6/27 - TOP 1:30 6/27 - AOI 3:30 | 1B 1T 21/32 | 6/26 - KIT CLEAR | 3 | 360 |  | 6/26 | C |  |  | Open Source Instruments, Inc. | 4
2023-06-29 | 1 | L1 | 118313 |  |  | NEW | 25 | 6/26 5D | FEDEX P | DEPANEL MECH ASSY | 6/22 - BOT 11:30 6/22 - TOP 4:30 AOI - UNKNOWN | 2B 1T 113/385 | 6/20 - KIT CLEAR | 4 | 100 |  | 6/14 | C |  |  | Anderson Connectivity
2023-06-28 | 1 | L1/L3 | 118087-1 PAR1 |  |  | RONC 116713 | 50 | 6/28 10D | UPS RED | DEPANEL J10,15,17 MUST BE | 6/21 - TOP 2:00 6/23 - BOT 7:00 AOI - UNKNOWN | 1B 1T 58/117 | 6/14 - KIT CLEAR | 20 | 1000 |  | 6/14 | NC | Y |  | Alliance Technology, LLC
2023-06-28 | 1 | L1 | 118703 |  |  | NEW | 14 | 6/29 5D | FEDEX P | DEPANEL LABELS MUST MATCH "U1" UNIQUE PART NUMBERS BUILD 13 PCBS W/ U1 1 PCB W/O U1 | 6/23 - BOT 11:30 6/23 - TOP 1:30 6/24 - AOI | 1B 1T 20/77 | 6/22 - KIT CLEAR | 25 | 350 |  | 6/22 | C |  |  | Alphacore, Inc.
2023-06-27 | 10 | L3 | 118184 |  |  | NEW | 100 | 6/29 15D | FEDEX GND | DEPANEL WIRE JUMPERS REQ | 6/22 - TOP 6:00 6/22 - AOI 10:30 | 1T 6/10 | 6/8 - KIT CLEAR | 3 | 300 |  | 6/5 | C |  |  | Boise State University | 4.5
2023-06-27 | 1 | L1 | 116288-1 BAL |  |  | NEW | 2 | ??? 5D | FEDEX P | DEPANEL MECH ASSY | 5/25 - BOT 12:30 5/25 - TOP 2:30 | 1B 1T 56/685 | 5/23 - KIT CLEAR | 1 | 2 |  | 5/23 | C |  |  | ICR, Inc.
|  | 2023-06-26 | 117094-1ST (5/25) | ROWC 115838 | 1200 | L2 |  |  | 6/26H 20D | UPS GND | "U1" PRE BAKE 48 HRS PER ECO #4 DEPANEL FLUSH MOUNT ALL T/H PER ECO #3 *DO NOT SHIP EARLY* | 6/2 - TOP 9:00 6/5 - TOP DONE 1:30 6/9 - BOT 8:00 6/17 - AOI 2:00 | 1B 1T 24/126 | 5/26 - 5/30 - WILL CLER 5/26- KIT CLEAR | 4 | 4800 | X | C | 2 | Y | ICC, Inc.
|  | 2023-06-23 | 117780-2ND (6/13) | RONC 1ST | 3 | L1 |  |  | 6/23 5D | FEDEX GND | DEPANEL | 6/21 - BOT 9:00 6/21 - TOP 11:30 6/21 - AOI 2:00 | 1B 2T 80/1149 | 6/13 - KIT CLEAR | 33 | 99 |  | C | 1 |  | PC Krause & Associates
|  | 2023-06-23 | 117749 (6/20) | NEW | 200 | L3 |  |  | 2023-06-23 | FEDEX GND | *** 3 DAY TURN *** DEPANEL | 6/21 - BOT 6:00 6/21 - TOP 9:00 6/21 - AOI 4:00 | 1B 1T 7/15 | 6/20 - KIT CLEAR | 5 | 1000 |  | C | 3 |  | Treetown Tech
|  | 2023-06-22 | 117557-2nd (6/19) | RONC 1ST | 35 | L1 |  |  | 6/22 3D | UPS RED | *** 3 DAY TURN *** CLASS 3 DEPANEL BAR CODE REQ | 6/20 - BOT 7:00 6/20 - AOI 9:00 | 1B 28/108 | 6/19 - KIT CLEAR | 0 | 0 |  | C | 5 |  | Leonardo DRS - DRS Network & Imaging Systems
|  | 2023-06-22 | 118105 (6/6) | ROWC 111418 | 2 | L1 |  |  | 6/22 10D | FEDEX 2 DAY | DEPANEL | 6/19 - BOT 10:30 6/19 - TOP 12:00 6/19 - AOI 1:30 | 1B 1T 68/578 | 6/6 - SHORT #62 & #65 6/8 - KIT CLEAR | 118 | 236 |  | C | 1 |  | Denmar Technical Services
|  | 2023-06-22 | 113842-1 (6/9) PAR | NEW | 3 | L1 |  |  | 6/16 3D + 2D FOR RWK | FEDEX GND | ***3 DAY TURN PLUS 2 DAYS FOR RWK *** CLASS 3 *HEAVY RWK REQUIRED - SEE RWK INSTRUCTIONS!!! PACKING SLIP PER ECO 11 HOLD MATL UNTIL BALANCE SHIPS | 6/12 - BOT 9:30 6/12 - TOP 1:30 6/13 - AOI 9:00 | 2B 3T 179/1326 | 6/9 - QTY 3 PARTIAL CLEAR - CUST PAID FOR PARTIAL 6/16 - SHIP 3 OF 6 | 23 | 69 |  | NC | 1 |  | Magnix
|  | 2023-06-22 | 118224 |  | 20 |  |  |  | 2023-06-01 | FEDEX GND | [5 empty] | 0 |  |  |  |  | Thermon Heating Systems, Inc.
|  | 2023-06-21 | 118601 (6/8) | RONC 104649 | 50 | L3 |  |  | 6/22 10D | UPS GND | DEPANEL SHUNT/JUMPERS REQ | 6/15 - TOP 8:30 6/15 - AOI 12:30 | 1T 3/12 | 6/8 - KIT CLEAR | 23 | 1150 |  | C | 1 |  | Graph-Tech USA, LLC
|  | 2023-06-21 | 118253-1ST (6/14) | NEW | 2 | L1 |  |  | 6/21 5D | UPS RED | DEPANEL | 6/17 - BOT 3:00 6/19 - TOP 8:30 6/19 - AOI 10:00 | 1B 2T 89/653 | 6/14 - KIT CLEAR | 56 | 112 |  | C | 1 |  | Activ Surgical
|  | 2023-06-21 | 118400 (6/13) | NEW | 16 | L1 |  |  | 6/21 5D | FEDEX P | FAIR REQ ALL THT DNI | 6/20 - TOP 9:00 6/20 - BOT 3:00 6/21 - AOI 9:00 | 2B 2T 130/1365 | 6/14 - KIT CLEAR | 13 | 208 |  | C | 1 | Y | Phoenix Contact, Inc.
|  | 2023-06-21 | 117524 (5/23) | RONC 116837 | 215 | L3 |  |  | 6/21H 20D | UPS GND |  | 6/15 - BOT 12:30 6/16 - TOP 11:00 6/17 - AOI 2:30 | 1B 1T 28/140 | 5/23 - KIT CLEAR 6/15 - PRINTER DOWN | 3 | 645 | X | C | 2 |  | ICC, Inc.
|  | 2023-06-21 | 118086 (6/1) | NEW | 150 | L3 |  |  | 6/21 10D | FEDEX P | DEPANEL | 6/17 - BOT 2:30 6/19 - TOP 12:30 6/20 - AOI 2:30 | 1B 2T 97/303 | 6/2 - FABS DUE 6/7 - KIT CLEAR | 5 | 750 | X | C | 8 |  | Becton, Dickinson and Company
|  | 2023-06-21 | 118711 (6/15) | RONC 109427 | 40 | CANCELLED |  |  | 6/22 5D | FEDEX GND | DEPANEL PLACE COIL AFTER REFLOW - GLUE REQ (ECO #5) CofC PER ECO #7 | WRONG FAB/FILES ISSUE | 1B 1T 31/51 | 6/15 - KIT CLEAR 6/19 - ON HOLD | 2 | 80 |  | NC | 1 | y | Z DEVELOPMENT, LLC
|  | 2023-06-20 | 118374 (6/6) | NEW | 10 | L1 |  |  | 6/22 10D | FEDEX P | CLASS 3 WATER SOLUB PASTE REQ (Sn63Pb37) | 6/14 - BOT 12:30 6/14 - TOP 3:00 6/15 - AOI 10:00 | 1B 2T 106/812 | 6/7 - MAY CLEAR 6/8 - KIT CLEAR | 6 | 60 |  | C | 1 |  | Industrialex Manufacturing
|  | 2023-06-20 | 117221 (6/1) | ROWC 110684 | 50 | L1 |  |  | 6/22 15D | UPS RED | DEPANEL | 6/15 - BOT 10:00 6/15 - TOP 1:30 6/16 - AOI 10:00 | 1B 1T 53/335 | 6/1 - KIT CLEAR 6/16 - PRINTER DOWN | 8 | 400 |  | C | 1 |  | Holland LP
|  | 2023-06-20 | 116459 (6/6) | NEW | 150 | L1 |  |  | 6/20 10D | FEDEX GND | *DO NOT SHIP EARLY* DEPANEL "U1,U2,U3" led LENS MOUNTING PINS ALIGNED PER ECO #3 | 6/14 - TOP 9:30 6/14 - AOI 12:30 | 1T 1/3 | 6/6 - KIT CLEAR | 3 | 450 |  | C | 20 |  | McQ
|  | 2023-06-19 | 118514 (6/9) | RONC 114233 | 67 | L1 |  |  | 6/19 5D | FEDEX P | CLASS 3 ***DO NOT BREAKAWAY MOUSEBITES PER ECO 2 | 6/16 - BOT 10:00 6/17 - TOP 9:00 6/17 - AOI 3:00 | 1B 1T 91/392 | 6/13 - #46 DUE (100 OF 134 ON HAND) 6/12 - KIT CLEAR 6/16 - PRINTER DOWN | 2 | 134 |  | C | 6 |  | Ripple, LLC
|  | 2023-06-16 | 118332 (6/2) | NEW | 10 | L1 |  |  | 6/16 10D | UPS RED | DEPANEL LABEL PER ECO #5 ***SHIPPING: ESD BAG & SEAL W/ ESD WARNING LABEL | 6/13 - BOT 3:00 6/14 - TOP 8:30 6/14 - AOI 9:30 | 1B 1T 60/201 | 6/2 - KIT CLEAR | 10 | 100 |  | C | 1 |  | Markem Imaje
|  | 2023-06-16 | 118473-1ST (6/6) | NEW | 10 | L1 |  |  | 6/16 6/19 5D | FEDEX P | QR CODE REQ TRIM LEAD REQ | 6/13 - BOT 9:00 6/13 - TOP 11:00 6/13 - AOI 1:00 | 1B 1T 73/150 | 6/9 - FABS DUE 6/12 - KIT CLEAR | 16 | 160 |  | C | 2
|  | 2023-06-16 | 118430-1 (6/9) BAL | NEW | 98 | L3 |  |  | 6/16 5D | FEDEX P | CLASS 3 DEPANEL ***SEE ECO 3 FOR "BATT1" PLACEMENT (ADHESIVE) SEE ECO 4 FOR "U13/15 PLACEMENT ***40 PIN BREAKAWAY HEADERS NEED TO CUT IN HALF PER ECO 5 *RTV EPOXY REQ FOR "JP2/JP3" | 6/13 - BOT 12:30 6/14 - TOP 10:00 6/15 - AOI 8:30 | 1B 1T 63/172 | 6/9 - KIT CLEAR 6/15 - SHIP 2 OF 100 6/15 - XTRA TIME IN SMT NEEDED DUE TO SHORT STAFFED | 5 | 490 |  | C | 1 |  | Trendsetter Vulcan Offshore, Inc.
|  | 2023-06-15 | 118430-1 (6/9) PAR | NEW | 2 | L3 |  |  | 6/15 5D | FEDEX P | CLASS 3 DEPANEL ***SEE ECO 3 FOR "BATT1" PLACEMENT (ADHESIVE) SEE ECO 4 FOR "U13/15 PLACEMENT ***40 PIN BREAKAWAY HEADERS NEED TO CUT IN HALF PER ECO 5 *RTV EPOXY REQ FOR "JP2/JP3" | 6/13 - BOT 12:30 6/14 - TOP 10:00 | 1B 1T 63/172 | 6/9 - KIT CLEAR 6/15 - SHIP 2 OF 100 | 5 | 10 |  | C | 1 |  | Trendsetter Vulcan Offshore, Inc.
|  | 2023-06-15 | 118328 (6/13) | NEW | 2 | L1 |  |  | 6/15 2D | UPS GROUND | *** 2 DAY TURN *** CLASS 3 DEPANEL PRESS FIT & MECH ASSY REQ | 6/13 - BOT 1:00 6/13 - TOP 2:00 6/13 - AOI 3:00 | 1B 1T 7/101 | 6/13 - KIT CLEAR | 72 | 144 |  | C | 1 |  | Diversified Supply
|  | 2023-06-15 | 117868 (5/17) | RONC 117102 | 340 | L1 |  |  | 6/15H 20D | FEDEX P | DEPANEL & SAND | 6/9 - BOT 10:30 6/9 - TOP 3:00 6/12 - AOI 9:30 | 2B 2T 38/96 | 5/17 - KIT CLEAR | 3 | 1020 | X | C | 6 | Y | Scientific Research Corporation
|  | 2023-06-14 | 117175-1 (5/24) BAL 3 | ROWC 114054 | 7 | L3 |  |  | 6/14 6/8H 10D | FEDEX P | DEPANEL & SAND SPECIAL DEPANEL INSTRUCTIONS (ECO 2) MECH ASSY REQ | 6/1 - BOT 1:00 6/6 - TOP 2:30 6/13 - AOI 12:30 | 1B 1T 112/1297 | 5/24 - KIT CLEAR 6/5 - PART SHORT #95 & #98 | 12 | 84 | X | C | 1 |  | SILC Technologies, Inc.
|  | 2023-06-14 | 114946-2 (5/16) | NEW | 1340 | L1 |  |  | 6/14H 20D | UPS GND | CLASS 3 DEPANEL | 5/17 - BOT 11:00 5/19 - TOP 2:00 6/6 - AOI 2:30 | 2B 2T 30/155 | 5/16 - WILL CLEAR 5/17 6/6 - ~750 FULL COMP | 3 | 4020 | X | C | 4 |  | ICC, Inc.
|  | 2023-06-13 | 118331 (6/6) | NEW | 6 | L3 |  |  | 6/15 5D | FEDEX 2 DAY | DEPANEL MECH ASSY REQ | 6/9 - TOP 9:30 6/9 - AOI 2:30 | 1T 19/212 | 6/6 - SMT CLEAR 6/8 - KIT CLEAR | 46 | 276 |  | C | 1 |  | Seurat Technologies, Inc.
|  | 2023-06-13 | 118329 (6/6) | NEW | 6 | L3 |  |  | 6/14 5D | FEDEX 2 DAY | DEPANEL MECH ASSY REQ | 6/9 - TOP 6:00 6/9 - AOI 9:30 | 1T 45/105 | 6/9 - FABS DUE 6/6 - FABS HERE | 9 | 54 |  | C | 1 |  | Seurat Technologies, Inc.
|  | 2023-06-13 | 118033 (6/1) | NEW | 150 | L1 |  |  | 6/14 5D | FEDEX P | DEPANEL | 6/7 - TOP 2:30 6/8 - AOI 2:00 | 1T 51/141 | 6/8 - FABS DUE 6/7 - KIT CLEAR | 1 | 150 | X | C | 1 |  | Ocean Aero, Inc.
|  | 2023-06-13 | 118403 (6/1) | NEW | 13 | L1 |  |  | 6/14 5D | UPS RED | DEPANEL | 6/8 - BOT 2:00 6/9 - AOI 10:30 | 2B 82/535 | 6/6 - FABS DUE 6/6 - SMT CLEAR | 13 | 169 |  | C | 1 |  | HF Scientific
|  | 2023-06-12 | 118344 (6/1) | ROWC 113057 | 9 | L1 |  |  | 6/12 5D | FEDEX P | 100% AOI REQ BARCODE LABEL | 6/6 - BOT 2:30 6/7 - TOP 9:30 6/7 - AOI 2:30 | 1B 2T 103/542 | 6/9 - FABS DUE 6/5 - KIT CLEAR | 0 | 0 |  | NC | 2 |  | Artis, LLC
|  | 2023-06-12 | 117175-1 (5/24) PAR 2 | ROWC 114054 | 6 | L3 |  |  | 6/8H 10D | FEDEX P | DEPANEL & SAND SPECIAL DEPANEL INSTRUCTIONS (ECO 2) MECH ASSY REQ | 6/1 - BOT 1:00 6/6 - TOP 2:30 | 1B 1T 112/1297 | 5/24 - KIT CLEAR 6/5 - PART SHORT #95 & #98 | 12 | 72 | X | C | 1 |  | SILC Technologies, Inc.
|  | 2023-06-09 | 118593 (6/6) | NEW | 25 | L1 |  |  | 6/12 3D | FEDEX P | *** 3 DAY TURN *** DEPANEL | 6/7 - TOP 11:00 6/7 - AOI 1:00 | 1T 17/36 | 6/7 - KIT CLEAR | 0 | 0 |  | C | 5 |  | Blueline Sensors LLC
|  | 2023-06-09 | 117896 (5/25) | ROWC 114307 | 16 | L3 |  |  | 6/14 10D | FEDEX P | DEPANEL | 6/5 - BOT 12:00 6/6 - TOP 8:30 6/6 - AOI 11:30 | 1B 1T 44/1097 | 5/26 - FABS DUE 5/31 - KIT CLEAR | 62 | 992 |  | C | 1 |  | Phoenix Contact, Inc.
|  | 2023-06-09 | 118107-1 (5/25) | NEW | 25 | L2 |  |  | 6/23H 20D | FEDEX P | *REVIEW JOB & ECO THUROUGHLY BEFORE STARTING!!! *** DO NOT PLACE "U3, R41-45" (PLACE AFTER CONFORMAL COATING) PER ECO **DO NOT SHIP MATL UNTIL ASSYS COME BACK FROM CONFORMAL COATING AND "U3, R41-45" ARE SOLDERED CLASS 3 | 6/5 - TOP 1:30 6/6 - BOT 9:30 6/6 - AOI 2:00 | 1B 1T 48/197 | 5/25 - KIT CLEAR | 15 | 375 | X | C | 1 | Y | Industrialex Manufacturing
|  | 2023-06-09 | 118016 (5/24) | NEW | 3 | L1 |  |  | ??? 6/8 5D | FEDEX P | DEPANEL ***NO MARKINGS OR STAMPS ALLOWED PER ECO #2 | 6/5 - BOT 11:30 6/5 - TOP 3:30 6/6 - AOI 8:00 | 2B 1T 84/231 | 5/24 - WILL CLEAR TDAY 6/1 - KIT CLEAR | 3 | 9 |  | C | 5 |  | Flextronics America
|  | 2023-06-08 | 118016 (5/24) | NEW | 31 | L1 |  |  | 6/8 5D | FEDEX P | DEPANEL ***NO MARKINGS OR STAMPS ALLOWED PER ECO #2 | 6/5 - BOT 11:30 6/5 - TOP 3:30 6/6 - AOI 8:00 | 2B 1T 84/231 | 5/24 - WILL CLEAR TDAY 6/1 - KIT CLEAR | 3 | 93 |  | C | 5 |  | Flextronics America
|  | 2023-06-08 | 117175-1 (5/24) PAR 1 | ROWC 114054 | 12 | L3 |  |  | 6/8H 10D | FEDEX P | DEPANEL & SAND SPECIAL DEPANEL INSTRUCTIONS (ECO 2) MECH ASSY REQ | 6/1 - BOT 1:00 6/6 - TOP 2:30 6/7 - AOI 12:00 | 1B 1T 112/1297 | 5/24 - KIT CLEAR 6/5 - PART SHORT #95 & #98 | 12 | 144 | X | C | 1 |  | SILC Technologies, Inc.
|  | 2023-06-08 | 117479-1 (4/19) BAL | NEW | 1287 | L3 |  |  | 6/13H 5/17 20D | UPS BLU | CLASS 3 DO NOT DEPANEL | 5/31 - TOP 8:30 6/1 - AOI 1:00 | 2T 8/23 | 4/19 - KIT CLEAR 5/3 - PARTIAL (QTY 143) SHIP 5/10 5/5 - AWT STENCIL 5/11 - #3 (D1, D2) & #5 (U2,U3) DUE 5/15 | 0 | 0 |  | C | 143 |  | Monzite dba Impellimax
|  | 2023-06-07 | 118518 (6/1) | ROWC 117874 | 80 | L1 |  |  | 6/8 5D | FEDEX P | DEPANEL | 6/2 - BOT 1:30 6/2 - TOP 3:30 6/5 - AOI 9:00 | 1B 1T 22/51 | 6/1 - KIT CLEAR | 4 | 320 |  | C | 10 |  | Open Source Instruments Inc
|  | 2023-06-07 | 117557-1ST (5/22) | NEW | 15 | L1 |  |  | 6/8 3D | UPS RED | *** 3 DAY TURN *** CLASS 3 DEPANEL BAR CODE REQ | 6/5 - BOT 9:00 6/5 - AOI 11:30 | 1B 28/108 | 5/23 - UNKNOWN FABS DUE DATE 6/5 - KIT CLEAR | 0 | 0 |  | C | 5 |  | Leonardo DRS - DRS Network & Imaging Systems
|  | 2023-06-06 | 117738 (5/11) | NEW | 7 | L2 |  |  | 6/7H 15D | UPS GND | DEPANEL | 6/1 - BOT 6:00 6/1 - TOP 10:00 6/2 - AOI 9:00 | 1B 1T 63/788 | 5/11 - SMT CLEAR 5/16 - KIT CLEAR | 16 | 112 | X | C | 1 |  | Droplet Measurement Technologies
|  | 2023-06-06 | 117371-1 (5/11) | NEW | 12 | L1 |  |  | 6/6 15D | UPS GND | DEPANEL NON-FLUSH J9 & J10 | 5/19 - BOT 11:00 5/19 - TOP 1:00 5/19 - AOI 2:00 | 1B 1T 15/22 | 5/10 - KIT CLEAR | 18 | 216 |  | C | 6 |  | ThorLabs
|  | 2023-06-06 | 104336 (5/18) | NEW | 168 | L1 |  |  | 6/6H 10D | UPS RED | CLASS 3 | 5/30 - BOT 10:30 5/30 - TOP 2:30 5/31 - AOI 3:00 | 1B 1T 54/210 | 5/18 - WILL CLEAR NEXT WEEK 5/22 - SMT CLEAR | 11 | 1848 | X | C | 1
|  | 2023-06-05 | 114721-1ST (5/18) | NEW | 2 | L1 |  |  | ??? 5D | FEDEX P | DEPANEL POST BAKE IF ASSY IS WASHED | 5/22 - BOT 11:30 5/22- TOP 1:30 5/22 - AOI 2:30 | 1B 2T 53/336 | 5/19 - MAY CLEAR 5/19 - SMT CLEAR; START ON MONDAY | 17 | 34 |  | C | 1 |  | Anderson Connectivity
|  | 2023-06-05 | 116128 (5/19) | NEW | 70 | L1 |  |  | 6/5H 10D | UPS RED | DEPANEL | 5/31 - BOT 3:00 6/1 - TOP 10:00 6/2 - AOI 8:30 | 2B 2T 138/425 | 5/19 - KIT CLEAR | 17 | 1190 | X | C | 1 |  | Coastal Designs, LLC
|  | 2023-06-05 | 117867-1ST (5/30) | NEW | 2 | CANCELLED |  |  | 6/7 5D | UPS GND | CLASS 3 DEPANEL PRESS FIT REQ | 6/2 - BOT 8:30 6/2 - TOP 11:00 | 1B 1T 68/253 | 5/31 - FABS DUE 5/31 - KIT CLEAR 6/2 - #42 (P1..) NO FIT | 9 | 18 |  | C | 1 |  | Diversified Supply
|  | 2023-06-02 | 117989 (5/22) | NEW | 45 | L3 |  |  | 5/30H 5D | FEDEX 2DAY | DEPANEL | 5/23 - BOT 2:00 5/24 - TOP 2:30 5/25 - AOI 1:30 | 1B 2T 89/322 | 5/22 - KIT CLEAR 5/30 - AWT U51 | 3 | 135 |  | C | 2 |  | DURBIN GROUP
|  | 2023-06-02 | 118402 (5/26) | NEW | 60 | L2 |  |  | 6/2 3D | FEDEX P | *** 3 DAY TURN *** | 5/30 - TOP 1:00 5/31 - BOT 8:30 5/31 - AOI 2:00 | 1B 1T 49/120 | 5/26 - SMT CLEAR 5/30 - KIT CLEAR | 21 | 1260 |  | C | 1 | Y | Atlas Devices
|  | 2023-06-02 | 106266 (3/30) | NEW | 600 | L1 |  |  | ??? 5/3 20D | UPS 3DAY | CLASS 3 ***SHIPPING: SHIPPED IN PLACE ON 6/1/23 - DO NOT INVOICE | 4/13 - BOT 8:00 4/20 - TOP 1:30 4/26 - AOI 12:00 | 2B 2T 120/400 | 3/30 - SHORT #130 (R188) THEN SMT CLEAR 4/5 - KIT CLEAR | 18 | 10800 | X |  |  |  | Coastal Designs, LLC
|  | 2023-06-01 | 106266 (3/30) | NEW | 600 | SHIPPED IN PLACE |  |  | ??? 5/3 20D | UPS 3DAY | CLASS 3 ***SHIPPING: SHIPPED IN PLACE ON 6/1/23 - DO NOT INVOICE | 4/13 - BOT 8:00 4/20 - TOP 1:30 4/26 - AOI 12:00 | 2B 2T 120/400 | 3/30 - SHORT #130 (R188) THEN SMT CLEAR 4/5 - KIT CLEAR | 18 | 10800 | X |  |  |  | Coastal Designs, LLC
|  | 2023-06-01 | 116688-1ST (5/23) | NEW | 3 | L1 |  |  | 6/1H 5D | FEDEX P | DEPANEL X-RAY & SAVE IMAGES BAR CODE LABELS REQ | 5/30 - BOT 7:00 5/30 - TOP 8:30 5/30 - AOI 10:30 | 1B 2T 73/401 | 5/23 - L1 & L4 SKIPPABL | 0 | 0 |  | NC | 1 |  | Artis LLC
|  | 2023-06-01 | 115576 (5/17) | NEW | 1 | L3 |  |  | 6/1H 10D | FEDEX GND | REQ EXIT AUDIT | 5/25 - BOT 2:00 5/26 - TOP 8:00 5/26 - AOI 2:00 | 2B 2T 42/4305 | 5/17 - KIT CLEAR | 11 | 11 |  | C | 1 |  | CACI
|  | 2023-06-01 | 118126 (5/23) | NEW | 2 | L2 |  |  | 6/1H 3D | FEDEX P | *** 3 DAY TURN *** DEPANEL | 5/30 - TOP 9:00 5/30 - AOI 11:30 | 2T 69/434 | 5/23 - SMT CLEAR 5/26 - KIT CLEAR | 35 | 70 |  | C | 1 |  | Hypertech
|  | 2023-06-01 | 115080 (5/17) | NEW | 20 | L3 |  |  | 6/1H 10D | FEDEX GND | REQ EXIT AUDIT X-RAY & SAVE IMAGES | 5/30 - BOT 6:00 5/30 - TOP 12:00 5/31 - AOI 8:30 | 1B 1T 32/544 | 5/17 - KIT CLEAR; AWT CUST REPLY STENCIL | 8 | 160 |  | NC | 2 |  | CACI
|  | 2023-05-31 | 116288-1 (5/23) PAR | NEW | 18 | L1 |  |  | 5/31H 5D | FEDEX P | *** ALERT *** #12 (U14_...) #18 (U12…) EXACT QTY GIVEN U1, U2 & U10 REQ 48 HRS BAKE (3 DAYS BAKE) ***SHARED PARTS W/ 116854 | 5/25 - BOT 12:30 5/25 - TOP 2:30 5/26 - AOI 8:00 | 1B 1T 56/685 | 5/19 - FABS DUE BUT FABS & ICS REQ BAKE | 4 | 72 |  | C | 1 |  | ICR, Inc.
|  | 2023-05-31 | 118216 (5/23) | NEW | 5 | L1 |  |  | 5/31H 5D | UPS RED | DEPANEL | 5/26 - TOP 9:00 5/26 - AOI 11:30 | 2T 39/126 | 5/23 - KIT CLEAR | 9 | 45 |  | C |  |  | Bitrode
|  | 2023-05-31 | 117750 (5/18) | NEW | 16 | L1 |  |  | 5/31H 5D | FEDEX P | DEPANEL | 5/23 - BOT 1:00 5/24 - TOP 10:00 5/24 - AOI 11:30 | 1B 1T 100/1312 | 5/19 - WILL CLEAR 5/23 - KIT CLEAR | 7 | 112 |  | NC | 1 |  | Phoenix Contact, Inc.
|  | 2023-05-31 | 117623 (5/25) | NEW | 10 | L2 |  |  | 5/31H 3D | FEDEX P | *** 3 DAY TURN *** | 5/26 - TOP 9:00 5/30 - AOI 1:00 | 2T 62/355 | 5/25 - KIT CLEAR | 16 | 160 |  | C | 1 |  | John Hopkins University Applied Physics Lab
|  | 2023-05-30 | 115838-1 (4/11) BAL | ROWC 113565 | 1 | L3 |  |  | ??? 5/9 20D | UPS GND | DEPANEL | 5/1 - TOP 6:00 5/2 - BOT 10:00 5/5 - AOI 9:30 | 2B 1T 24/126 | 4/11 - KIT CLEAR; TOP 1ST 4/25 - SMT REQ 1 WEEK | 4 | 4 | x |  |  |  | ICC, Inc.
|  | 2023-05-30 | 117933 (5/18) | NEW | 40 | L2 |  |  | 6/2H 10D | FEDEX P | DEPANEL SEE ECO #2 FOR LABEL DATA | 5/23 - BOT 6:00 5/23 - TOP 8:30 5/23 - AOI 11:00 | 1B 1T 30/117 | 5/18 - KIT CLEAR | 17 | 680 |  | C | 3 |  | Becton, Dickinson and Company
|  | 2023-05-30 | 113238 (5/22) | RONC 109226 | 250 | L2 |  |  | 5/30H 5D | FEDEX P | ***NO VENDOR MARKINGS/STAMPS ***LEAD PROCESS W/ LEAD-FREE REFLOW PROFILE DEPANEL& SAND | 5/26 - TOP 6:00 5/26 - AOI 8:00 | 1T 2/4 | 5/22 - KIT CLEAR | 0 | 0 |  | NC | 10 |  | John Hopkins University Applied Physics Lab
|  | 2023-05-30 | 116837 (5/22) | NEW | 500 | L2 |  |  | 5/30H 5D | UPS GND | PACK PER ECO NOTE #3 | 5/23 - BOT 11:30 5/24 - TOP 12:00 5/25 - AOI 4:00 | 1B 1T 28/140 | 5/22 - KIT CLEAR | 3 | 1500 | X | C | 2 |  | ICC, Inc.
|  | 2023-05-26 | 117984-1 (5/12) BAL | NEW | 9 | L1 |  |  | 6/2H 5D | UPS RED | DEPANEL RTV REQ HEAT SEALED PART BAGS | 5/16 - TOP 9:00 5/17 - BOT 8:00 5/17 - AOI 11:00 | 1B 2T 126/478 | 5/12 - EXPEDITE 41 5/15 - PGRM RDY 5/12 - SMT CLEAR 5/25 - KIT CLEAR | 17 | 153 | X | C | 1 | Y | Carnegie Robotics
|  | 2023-05-26 | 117213 (5/16) | NEW | 34 | L3 |  |  | 5/31H 10D | FEDEX P | DEPANEL SEE ECO #2 FOR LABEL DATA | 5/23 - TOP 7:30 5/23 - AOI 2:00 | 1T 55/268 | 5/16 - KIT CLEAR | 21 | 714 |  | C | 1 |  | Becton, Dickinson and Company
|  | 2023-05-26 | 117780-1ST (5/23) | NEW | 1 | L1 |  |  | 5/26 3D | FEDEX GND | *** 3 DAY TURN *** DEPANEL | 5/24 - BOT 11:30 5/25 - TOP 9:00 5/25 - AOI 2:30 | 1B 2T 80/1149 | 5/23 - KIT CLEAR | 33 | 33 |  | C | 1 |  | PC Krause & Associates
|  | 2023-05-26 | 117696 (5/12) | NEW | 10 | L2 |  |  | 5/26 10D | FEDEX P | J1131 & U125 VIA HOLES NEED TO BE SOLDERED PER ECO #1 ***DO NOT LOSE OR DAMAGE J1131 | 5/18 - BOT 1:00 5/19 - TOP 10:00 5/19 - AOI 2:30 | 1B 1T 80/410 | 5/12 - KIT CLEAR | 11 | 110 | X | C | 5 |  | Protocol Insight LLC.
|  | 2023-05-26 | 118067-1ST (5/19) | NEW | 4 | L1 |  |  | 5/26 5D | UPS RED | DEPANEL | 5/22 - BOT 2:30 5/23 - TOP 11:30 5/26 - AOI 1:00 | 2B 1T 89/586 | 5/19 - KIT CLEAR | 35 | 140 |  | C | 1 |  | Tennessee Valley Authority
|  | 2023-05-25 | 114869 (4/7) | ROWC 109746 | 450 | L2 |  |  | 5/25 5D | FEDEX P | DEPANEL & SAND | 4/19 - BOT 6:00 4/25 - TOP 11:30 4/28 - AOI 9:30 | 2B 2T 68/137 | 4/7 - #46 (J5) DUE 4/28; SMT CLEAR 4/20 - BOT DONE 4/25 TOP REQ 2.5 DAYS 4/27 - KIT WILL CLEAR 5/15 | 6 | 2700 |  |  |  |  | Scientific Research Corporation
|  | 2023-05-24 | 116908 (5/11) | NEW | 50 | L2 |  |  | 5/24 8D | FEDEX GND | DEPANEL CLEAN 56 LOOSE PARTS BTD #16 & NOTIFY CUST OF BOARD W/O PART | 5/18 - BOT 12:00 5/23 - TOP 8:00 5/23 - AOI 9:30 | 1B 1T 38/140 | 5/11 - KIT WILL CLEAR EOD 5/12 5/12 - KIT CLEAR | 0 | 0 |  | C | 3 |  | Human Systems Integration, Inc.
|  | 2023-05-24 | 117189 (5/10) | NEW | 15 | L3 |  |  | 5/24 3D 10D | FEDX P | *** 3 DAY TURN *** DEPANEL | 5/22 - BOT 6:00 5/22 - TOP 11:00 5/22 - AOI 2:30 | 1B 1T 53/251 | 5/10 - NEW XY RECV 5/10 - AWT NAT PGRM 5/12 - FABS DUE | 34 | 510 |  | C | 1 |  | UBC, Inc
|  | 2023-05-23 | 117807 (5/12) | NEW | 150 | L3 |  |  | 5/25 5D | UPS RED | DEPANEL | 5/19 - BOT 9:00 5/19 - TOP 12:00 5/19 - AOI 2:30 | 1B 1T 29/29 | 5/15-16 - COULD CLEAR 5/18 - KIT CLEAR | 0 | 0 |  | C | 25 |  | Taditel US Inc
|  | 2023-05-23 | 118079 (5/17) | RONC 106341 | 2 | L3 |  |  | 5/25 5D | UPS RED | DEPANEL BAR CODES REQ | IN BACK | 1/40 | 5/17 - SMT CLEAR 5/18 - KIT CLEAR | 47 | 94 |  | C | 1 |  | Siemens Industry, Inc.
|  | 2023-05-23 | 116350-2ND (5/11) | RONC 1ST | 4 | L2 |  |  | 5/25 10D | UPS 3DAY | CLASS 3 | 5/17 - BOT 12:00 5/18 - TOP 8:00 5/18 - AOI 12:00 | 1B 2T 146/903 | 5/11 - XTRA TIME AVAIL FOR PART COUNT | 72 | 288 | X | C | 1 |  | Coastal Designs, LLC
|  | 2023-05-22 | 117874 (5/17) | NEW | 20 | L3 |  |  | 5/24 5D | FEDEX P | DEPANEL | 5/18 - BOT 7:00 5/18 - TOP 8:00 5/18 - AOI 12:00 | 1B 1T 23/52 | 5/17 - KIT CLEAR | 4 | 80 |  | C | 10 |  | Open Source Instruments, Inc.
|  | 2023-05-22 | 117984-1 (5/12) PAR | NEW | 16 | L1 |  |  | 5/19 5D | UPS RED | DEPANEL RTV REQ HEAT SEALED PART BAGS | 5/16 - TOP 9:00 5/17 - BOT 8:00 5/17 - AOI 11:00 | 1B 2T 126/478 | 5/12 - EXPEDITE 41 5/15 - PGRM RDY 5/12 - SMT CLEAR | 17 | 272 | X | C | 1 | Y | Carnegie Robotics
|  | 2023-05-19 | 117984-1 (5/12) PAR | NEW | 25 | L1 |  |  | 5/19 5D | UPS RED | DEPANEL RTV REQ HEAT SEALED PART BAGS | 5/16 - TOP 9:00 5/17 - BOT 8:00 5/17 - AOI 11:00 | 1B 2T 126/478 | 5/12 - EXPEDITE 41 5/15 - PGRM RDY 5/12 - SMT CLEAR | 17 | 425 | X | C | 1 | Y | Carnegie Robotics
|  | 2023-05-19 | 116458-2 (4/13) BAL | ROWC 107934 | 1 | L3 |  |  | ??? 4/28 10D | FEDEX GND | PREBAKE "U46" NOT A 2ND ARTICLE AWT PART | 4/24 - TOP 6:00 4/24 - BOT 1:00 4/25 - AOI 11:30 | 2B 2T 106/290 | 3/31 - TOP SIDE 1ST 4/3 - 1 DAY RUN FOR 30 4/13 - ETA U20 4/17 4/17 - KIT CLEAR 4/25 - SMT REQ 2 DAYS | 1 | 1 |  |  |  |  | McQ
|  | 2023-05-19 | 117766 (5/9) | NEW | 10 | L2 |  |  | 5/19 5D | FEDEX P | DEPANEL | 5/15 - BOT 5:00 5/15 - TOP 9:30 5/16 - AOI 9:00 | 2B 2T 144/676 | 5/9 - FABS DUE 5/15 5/12 - KIT CLEAR | 0 | 0 |  | C | 2 |  | Tomahawk Robotics, LLC
|  | 2023-05-19 | 117697 (5/12) | NEW | 10 | L2 |  |  | 5/19 5D | FEDEX P | DEPANEL | 5/16 - BOT 9:00 5/16 - TOP 12:00 5/17 - AOI 12:00 | 1B 1T 55/245 | 5/12 - KIT CLEAR | 1 | 10 |  | C | 5 |  | Protocol Insight LLC.
|  | 2023-05-19 | 118035 (5/16) | NEW | 5 | L3 |  |  | 5/19 2D | FEDEX P | *** 2 DAY TURN *** X-RAY & SAVE IMAGES | 5/17 - TOP 10:00 5/17 - AOI 2:30 | 1T 12/215 | 5/17 - KIT CLEAR | 57 | 285 |  | C | 1 |  | Relativity Space Inc
|  | 2023-05-19 | 117932 (5/11) | NEW | 50 | L1 |  |  | 5/19 5D | UPS RED | DEPANEL & SAND PER ECO #1 TRIM LEADS PER ECO #2 | 5/15 - TOP 9:00 5/16 - AOI 9:00 | 2T 90/593 | 5/11 - FABS DUE 5/12 5/12 - KIT CLEAR | 8 | 400 | X | C | 2 |  | Flex Radio Systems
|  | 2023-05-18 | 116125 (5/11) | NEW | 15 | L3 |  |  | 5/18 5D | UPS RED | X | 5/15 - BOT 1:30 5/16 - TOP 9:00 5/17 - AOI 9:00 | 1B 2T 83/234 | 5/11 - KIT CLEAR | 62 | 930 | X | C | 1 |  | HII Unmanned Systems, Inc
|  | 2023-05-18 | 113185 (4/27) | NEW | 550 |  |  |  | 5/25 20D | UPS BLU | DEPANEL | 5/10 - AOI | 1B 1T 7/59 | 4/27 - KIT CLEAR | 0 | 0 |  | C | 5 |  | Benchmark Electronics
|  | 2023-05-17 | 117354-1 (5/4) BAL | NEW | 53 | L1 |  |  | 5/22 10D | FEDEX P | DEPANEL | 5/12 - TOP 12:00 5/15 - AOI 9:00 | 2T 63/139 | 5/4 - NO ETA FOR FABS 5/8 - KIT CLEAR | 12 | 636 |  | C | 1 |  | INFICON Inc.
|  | 2023-05-17 | 115854 (5/10) | NEW | 25 | L1 |  |  | 5/17 5D | FEDEX P | *** DO NOT DEPANEL *** PRE-BAKE FAB & IC'S PER ECO #2 SMT NOTE: LEAD PROCESS BUT USE ROHS REFLOW PROFILE *CofC MUST NOTE PRE-BAKE WAS COMPLETED | 5/10 - TOP SIDE 3:00 5/11 - BOT 1:00 5/12 - AOI 12:00 | 2B 2T 169/1027 | 5/10 - KIT CLEAR | 9 | 225 | X | C | 1 | Y | Ripple, LLC
|  | 2023-05-16 | 117628 (5/4) | NEW | 30 | L1 |  |  | 5/18 10D | UPS GND | CLASS 3 DEPANEL | 5/9 - BOT 12:00 5/10 - TOP 8:00 5/10 - AOI 3:00 | 1B 1T 40/150 | 5/4 - KIT CLEAR | 1 | 30 |  | NC | 9 |  | Ultra Motion LLC
|  | 2023-05-16 | 104334 (5/2) | NEW | 62 | L1 |  |  | 5/16 10D | UPS 3DAY | CLASS 3 | 5/8 - BOT 10:30 5/8 - TOP 1:30 5/9 - AOI 3:00 | 1B 1T 43/106 | 5/2 - KIT CLEAR | 10 | 620 |  |  |  |  | Coastal Designs, LLC
|  | 2023-05-15 | 117447 (5/1) | RONC 109227 | 300 | L1 |  |  | 5/17 5D | FEDEX P | DEPANEL DO NOT MIX LOTS BY Q1 P/N | 5/10 - TOP 10:00 5/10 - BACK 12:00 | 1T 2/2 | 5/1 - FABS DUE 5/5 5/9 - FABS DUE 5/10 5/10 - KIT CLEAR | 0 | 0 |  | C |  |  | Transphorm USA
|  | 2023-05-15 | 113840-1 (3/29) BAL | NEW | 4 | L2 |  |  | 5/17 3D | UPS GND | *** 3 DAY TURN *** CofC PER ECO #2 | 4/6 - BOT SIDE 12:30 4/6 - TOP SIDE 2:30 4/7 - AOI 7:00 | 1B 1T 15/200 | 3/29 - SHORT #13 SMT; #12 THT 4/4 - SMT CLEAR 4/19 - SHIPPED 2 OF 6 | 11 | 44 |  |  |  |  | Magnix
|  | 2023-05-15 | 117377 (5/9) | NEW | 15 | L2 |  |  | 5/17 5D | FEDEX GND | DEPANEL BOARDS REQ BAKING AFTER WASH (ECO 4) | 5/11 - BOT 6:00 5/11 - TOP 8:00 5/11 - AOI 10:00 | 1B 1T 50/284 | 5/9 - FABS DUE 5/10 5/10 - KIT CLEAR | 40 | 600 |  | C | 1 |  | Helmer Scientific LLC
|  | 2023-05-15 | 117631 (5/2) | NEW | 10 | L2 |  |  | 5/16 10D | UPS GND | LEDS FLUSH W/BOARD ECO #3 | 5/9 - BOT 8:00 5/9 - TOP 5/9 - AOI | 1B 1T 48/407 | 5/2 - KIT CLEAR 5/9 - PGRM ISSUES | 13 | 130 |  | C | 1 |  | Jefferson Labs
|  | 2023-05-15 | 117837 (5/9) | RONC 115673 | 4 | L3 |  |  | 5/15 3D | FEDEX GND | *** 3 DAY TURN *** DEPANEL CofC & PACK SLIP PER ECO #1 | 5/12 - BOT 7:00 5/12 - TOP 10:00 5/12 - AOI 2:00 | 1B 1T 32/753 | 5/10 - BTD; KIT CLEAR 5/12 - PGRM ISSUES: XTRA TIME NEEDED TO PRGM JUKIES | 27 | 108 |  | C | 1 |  | dB Systems, Inc.
|  | 2023-05-15 | 117374 (4/28) | NEW | 1 |  |  |  | ??? 5/12 10D | UPS BLU | DEPANEL | IN AOI | 1B 12/24 | 4/28 - KIT CLEAR | 19 | 19 |  |  |  |  | ThorLabs
|  | 2023-05-12 | 116507 (5/3) | RONC 111571 | 100 | L1 |  |  | 5/17 10D | UPS GND | DEPANEL CoC REQ (ECO #3) | 5/8 - TOP 3:00 5/9 - AOI 12:00 | 1T 45/89 | 5/3 - KIT CLEAR | 7 | 700 |  | C | 10 |  | Churchill Navigation dba Shotover Systems Inc
|  | 2023-05-12 | 116578 (5/1) | ROWC 113048 | 4 |  |  |  | 5/16 10D | FEDEX GND | DEPANEL MECH ASSY REQ RTV REQ LOCTITE (222MS) REQ DNI "U1 & U2" - SHIP BACK TO CUST W/ SCREWS & SPACERS TRIM LEADS 0.1 INCHES | IN AOI | 1T 10/33 | 5/1 - MAY CLEAR SOON 5/2 - KIT CLEAR 5/11 - DNI "U1 & U2" - SHIP BACK TO CUST W/ SCREWS & SPACERS | 43 | 172 |  |  |  |  | Mission Support and Test Services, LLC
|  | 2023-05-12 | 116775 (5/8) | NEW | 60 | L3 |  |  | 5/15 5D | UPS RED | MIXED POP - 60 BOARDS TOTAL, EVERY 12 BOARDS HAS DIF LED - SEE ECO #1 *"UA1-UE1" HAS ALT P/N - SEE ECO 2 REVIEW WHEN RELEASE | 5/9 - TOP 8:00 5/10 - BACK (NO AOI) | 1T 18/150 | 5/8 - KIT CLEAR | 0 | 0 |  | C | 1 |  | Form Labs
|  | 2023-05-12 | 116048-2ND (3/3) BAL | PAID RWK | 27 |  |  |  | 5/15 5D | FEDEX GND | R&R ALL MAX14430EAEE TO SI8645BA-B-IU | 3/6 - BACK |  | 3/7 - FA DUE 3/13 3/24 - QTY 1 SHIP 3/31 5/8 - KIT CLEAR | 34 | 918 |  |  |  |  | HRL Laboratories
|  | 2023-05-12 | 117374 (4/28) | NEW | 29 |  |  |  | 5/12 10D | UPS BLU | DEPANEL | IN AOI | 1B 12/24 | 4/28 - KIT CLEAR | 19 | 551 |  |  |  |  | ThorLabs
|  | 2023-05-11 | 117037 (5/2) | NEW | 30 | L2 |  |  | 5/15 9D | UPS GND | DEPANEL "U1" PLACE AS IS PER ECO CofC REQ | 5/9 - BOT 8:00 5/9 - TOP 10:00 5/9 - AOI 11:00 | 1B 1T 14/167 | 5/2 - KIT CLEAR | 0 | 0 |  | 1 | C |  | PhaseX
|  | 2023-05-11 | 115642 (5/1) | NEW | 55 | L1 |  |  | 5/15 10D | FEDEX GND | DEPANEL | 5/5 - BOT 3:00 5/8 - TOP 8:30 5/8 - AOI 10:30 | 1B 1T 17/89 | 5/1 - KIT CLEAR | 13 | 715 | X |  |  |  | Azimuth, Inc
|  | 2023-05-11 | 117353 (4/14) | RONC 106348 | 250 | L1 |  |  | 5/12 20D | UPS 3DAY | CLASS 3 | 5/4 - BOT 10:00 5/4 - TOP 3:00 5/5 - AOI 10:30 | 1B 1T 22/45 | 4/14 - KIT CLEAR 5/4 - AWT STENCIL | 10 | 2500 | X |  |  |  | Coastal Designs, LLC
|  | 2023-05-10 | 116091-2 (3/9) BAL | RONC 109493 | 2 | L2 |  |  | 5/15 15D | FEDEX P | PRESS FIT REQ REBUILD OF DELAM | 5/4 - BOT 1:00 5/8 - TOP 2:00 5/9 - AOI 8:00 | 1B 2T 66/757 | 3/9 - KIT CLEAR 3/29 - AWT CUST REPLY 5/1 - EXPECTED 1 FULL DAY IN SMT | 12 | 24 | X | 1 | C |  | IonQ, Inc.
|  | 2023-05-10 | 117354-1 (5/4) PAR | NEW | 17 | L1 |  |  | 5/12 5D | FEDEX P | DEPANEL | 5/5 - TOP 10:30 5/5 - AOI 3:00 | 2T 63/139 | 5/4 - FABS DUE 5/5 5/5 - KIT CLEAR 5/12 | 12 | 204 |  |  |  |  | INFICON Inc.
|  | 2023-05-10 | 117479-1 (4/19) PAR | NEW | 143 | L3 |  |  | 5/10 20D | UPS BLU | CLASS 3 EARLY PARTIAL SHIPMENT ***DO NOT DEPANEL | 5/5 - TOP 9:30 5/5 - AOI 2:00 | 2T 8/23 | 4/19 - KIT CLEAR | 0 | 0 |  |  |  |  | Monzite dba Impellimax
|  | 2023-05-09 | 115838-1 (4/11) PAR | ROWC 113565 | 1199 | L3 |  |  | 5/9 20D | UPS GND | DEPANEL | 5/1 - TOP 6:00 5/2 - BOT 10:00 5/5 - AOI 9:30 | 2B 1T 24/126 | 4/11 - KIT CLEAR; TOP 1ST 4/25 - SMT REQ 1 WEEK | 4 | 4796 | x |  |  |  | ICC, Inc.
|  | 2023-05-09 | 117703 (5/2) | ROWC 114390 | 59 | L1 |  |  | 5/9 5D | FEDEX P | X | 5/3 - BOT 12:30 5/3 - TOP 3:00 5/4 - AOI 10:00 | 1B 1T 48/139 | 5/2 - KIT CLEAR | 7 | 413 | X |  |  |  | Atlas Devices
|  | 2023-05-08 | 116107-2ND (4/19) BAL | RONC 1ST | 98 | L2 |  |  | 5/8 10D | UPS GND | DEPANEL | 5/2 - BOT 11:30 5/2 - TOP 2:00 5/3 - AOI 2:30 | 1B 2T 91/245 | 4/19 - KIT SHOULD CLEAR 4/20 4/24 - KIT CLEAR | 5 | 490 | x |  |  |  | Graph-Tech USA, LLC
|  | 2023-05-05 | 113364 (4/10) | NEW | 40 | L2 |  |  | 5/5 15D | FEDEX GND | DEPANEL HAND PLACE R6 AFTER SW1 (ECO 5) | 4/28 - TOP 1:00 5/1 - AOI 11:30 | 1T 45/93 | 4/10 - #22 (U4) DUE 4/12; #49 (SW2) DUE 4/13 4/12 - SMT CLEAR 4/14 - KIT CLEAR | 4 | 160 |  | McQ | 1545 Forbes St | Fredericksburg | VA
|  | 2023-05-05 | 117299 (4/24) | NEW | 10 | L1 |  |  | 5/8 10D | FEDEX P | DEPANEL R20 HEIGHT REQ (ECO 3) | 5/2 - 9:30 5/2 - 11:00 | 1T 14/25 | 4/24 - KIT CLEAR | 16 | 160 |  | INFICON Inc. | 2 Technology Pl | East Syracuse | NY
|  | 2023-05-05 | 114123-3RD (1/16) BAL | ROWC 108881 | 16 | L1 |  |  | 5/5 10D | FEDEX P | DO NOT DEPANEL NO CLEAN | 5/1 - BOT 10:00 5/1 - TOP 7:30 5/2 - AOI 12:30 | 1B 1T 48/1224 | 1/18 - COMPLETED 22 4/21 - KIT CLEAR; SMT REQ 1 FULL DAY | 0 | 0 | X | Phoenix Contact, Inc. | 586 Fulling Mill Rd | Middletown | PA
|  | 2023-05-05 | 117601 (4/26) | NEW | 10 | L1 |  |  | 5/5 5/8 5D | FEDEX P | *EXPEDITE* DEPANEL PARTIAL SHIPMENT | 5/2 - BOT 12:30 5/3 - TOP 8:30 5/3 - AOI 12:30 | 1B 2T 112/966 | 4/26 - FABS DUE 4/28 5/1 - KIT CLEAR | 9 | 90 |  | Amatis Controls | 1332 Bedford Rd | Grosse Pointe Park | MI
|  | 2023-05-04 | 116708 (4/18) | ROWC 107054 | 10 | L1 |  |  | 5/5 5D | FEDEX P | X | 5/1 - BOT 7:30 5/2 - TOP 8:30 5/2 - AOI 10:00 | 1B/1T 32/239 | 4/18 - SMT CLEAR ONLY - SHORT "M1" 4/28 - KIT CLEAR | 60 | 600 |  | IonQ, Inc. | 4505 Campus Dr | College Park | MD
|  | 2023-05-04 | 116291 (4/21) | NEW | 1 | L2 |  |  | 5/4 5/2 5D | FEDEX P | NO CUSTOMER NOTES | 4/28 - TOP 11:30 4/28 - AOI 1:00 | 1T 15/74 | 4/21 - FABS DUE 4/25 4/25 - KIT CLEAR | 7 | 7 |  | Genuen, LLC | 14425 College Blvd Ste 155 | Lenexa | KS
|  | 2023-05-04 | 115498 (4/20) | NEW | 100 | L1 |  |  | 5/4 10D | FEDEX P | DEPANEL & SAND *TRIM LEADS - NOT TO EXCEED 2.54MM | 4/28 - BOT 8:30 5/1 - AOI 7:30 | 2B 83/230 | 4/20 - KIT CLEAR | 19 | 1900 |  | Spectro Inc. | 1 Executive Dr | Chelmsford | MA
|  | 2023-05-04 | 117663-1 (4/25) BAL | ROWC 116340 | 305 | L1 |  |  | 5/4 3D | FEDEX EARLY AM | *** 3 DAY TURN *** ***SHIP MIN QTY 20 ON FRI 4/28 DEPANEL -ALERT- SET V-SCORE DEPTH ABOVE 5" MECH ASSY REQ | 4/26 - TOP 2:30 4/27 - AOI 10:00 | 2T 22/50 | 4/25 - SMT CLEAR; REQ 1 FULL DAY SMT/AOI & 1 FULL DAY THT/SHIP | 11 | 3355 | X | Command Alkon Inc. | 6750 Crosby Ct | Dublin | OH
|  | 2023-05-03 | 117101 (4/20) | RONC 108946 | 310 | L1 |  |  | 5/4 10D | FEDEX P | DEPANEL | 4/24 - TOP 10:00 4/26 - AOI 2:30 | 1T 14/19 | 4/20 - KIT CLEAR | 2 | 620 | x | Scientific Research Corporation | 103 Quality Cir Nw Ste 220 | Huntsville | AL
|  | 2023-05-02 | 116612 (4/5) | RONC 112316 | 96 97 | L2 |  |  | 5/3 20D | FEDEX P | "J3 & J4" T/H REQ SOLDER ON MOUNTING PADS - PER ECO 1 | 4/17 - BOT 6:00 4/21 - TOP 6:00 4/28 - AOI 11:30 | 1B 1T 66/370 | 4/5 - KIT CLEAR FOR QTY 96 4/25 - TOP REQ 1.5 DAYS | 2 | 192 |  | Protocol Insight, LLC | 5040 Corporate Plaza Dr Ste 11 | Colorado Spring | CO
|  | 2023-05-02 | 116639 (4/21) | NEW | 5 | L1 |  |  | 5/2 5D | FEDEX P | DEPANEL INSTALL SHUNTS | 4/27 - BOT 11:30 4/27 - TOP 3:30 4/28 - AOI 8:30 | 2B 2T 145/730 | 4/21 - MAY CLEAR 4/26 4/25 - KIT CLEAR | 17 | 85 |  | Becton, Dickinson and Company | 7 Loveton Cir | Sparks Glencoe | MD
|  | 2023-05-01 | 116048-2ND (3/3) BAL | PAID RWK | 1 |  |  |  | ??? 5D | FEDEX GND | R&R ALL MAX14430EAEE TO SI8645BA-B-IU | 3/6 - BACK |  | 3/7 - FA DUE 3/13 3/24 - QTY 1 SHIP 3/31 | 34 | 34 |  | HRL Laboratories | 3011 Malibu Canyon Rd | Malibu | CA
|  | 2023-05-01 | 116493-2ND (4/26) BAL | RONC 1ST | 8 | L1 |  |  | 5/1 3D | FEDEX P | *** 3 DAY TURN *** | 4/27 - BOT 10:00 4/27 - TOP 11:00 4/27 - AOI 11:30 | 1B 1T 1/3 | 4/26 - KIT CLEAR | 0 | 0 |  | Loft Orbital Inc. | 810 Brickyard Cir | Golden | CO
|  | 2023-05-01 | 117091 (4/24) | NEW | 5 | L2/L3 |  |  | 5/1 5D | FEDEX P | MAX LEED PROTRUSION 0.060" PER ECO | 4/28 - TOP 6:00 4/28 - BOT 9:30 4/28 - AOI 2:30 | 2B 3T 169/1173 | 4/24 - KIT CLEAR; #55 (U49) & #56 (U31) DNI 4/24 - TOP SIDE 1ST | 10 | 50 |  | Amazon | 241 18th St S | Arlington | VA
|  | 2023-05-01 | 117663-1 (4/25) PAR | ROWC 116340 | 75 | L1 |  |  | 5/1 3D | FEDEX EARLY AM | *** 3 DAY TURN *** ***SHIP MIN QTY 20 ON FRI 4/28 DEPANEL -ALERT- SET V-SCORE DEPTH ABOVE 5" MECH ASSY REQ | 4/26 - TOP 2:30 4/27 - AOI 10:00 | 2T 22/50 | 4/25 - SMT CLEAR; REQ 1 FULL DAY SMT/AOI & 1 FULL DAY THT/SHIP | 11 | 825 |  | Command Alkon Inc. | 6750 Crosby Ct | Dublin | OH
|  | 2023-04-28 | 117663-1 (4/25) PAR | ROWC 116340 | 20 | L1 |  |  | 4/28 3D | FEDEX EARLY AM | *** 3 DAY TURN *** ***SHIP MIN QTY 20 ON FRI 4/28 DEPANEL -ALERT- SET V-SCORE DEPTH ABOVE 5" MECH ASSY REQ | 4/26 - TOP 2:30 4/27 - AOI 10:00 | 2T 22/50 | 4/25 - SMT CLEAR; REQ 1 FULL DAY SMT/AOI & 1 FULL DAY THT/SHIP | 11 | 220 |  | Command Alkon Inc. | 6750 Crosby Ct | Dublin | OH
|  | 2023-04-28 | 100610-5TH (1/6) BAL | RONC 4TH ARTICLE | 187 | L3 |  |  | 4/28 20D | #VALUE! | ***NEW LEAD SOLDER PROCESS FOR U1A-U1H - DO NOT WASH U1A-U1H - USE SAME PROCESS AS B100606*** | 3/31 - BOT SIDE 6:00 4/7 - TOP SIDE 11:00 4/17 - AOI 2:30 | 2B 3T 237/3848 | 3/29 - 5/6 DAYS TO FINISH BOT; 5/6 DAYS TO FINISH TOP | 7 | 1309 | X | University of Oklahoma | 3190 Monitor Ave Rm 0220 | Norman | OK
|  | 2023-04-28 | 116458-2 (4/13) PAR | ROWC 107934 | 69 | L3 |  |  | 4/28 10D | FEDEX GND | PREBAKE "U46" NOT A 2ND ARTICLE | 4/24 - TOP 6:00 4/24 - BOT 1:00 4/25 - AOI 11:30 | 2B 2T 106/290 | 3/31 - TOP SIDE 1ST 4/3 - 1 DAY RUN FOR 30 4/13 - ETA U20 4/17 4/17 - KIT CLEAR 4/25 - SMT REQ 2 DAYS | 1 | 69 |  | McQ | 1545 Forbes St | Fredericksburg | WA
|  | 2023-04-27 | 116432-2 (3/10) BAL | NEW | 2 | L2 |  |  | 4/28 4/26 3D | FEDEX P | *** 3 DAY TURN *** CLASS 3 DEPANEL & SAND ALL EMPTY PACKAGES/TRAYS RETURN TO CUSTOMER | 4/24 - BOT 6:00 4/24 - TOP 9:30 4/24 - AOI 1:00 | 1B 2T 147/2945 | 3/10 - FABS DUE 3/15 3/24 - CLEARED TO RUN 2 OF 4; DUE 3/30 4/13 - WILL CLEAR 4/17 - 4/18 4/24 - DELAM | 77 | 154 |  | Aeronix Inc | 777 Lowndes Hill Rd | Greenville | SC
|  | 2023-04-26 | 117102 (4/19) | RONC 108947 | 310 | L3 |  |  | 4/27 5D | FEDEX P | DEPANEL & SAND HOLD KIT FOR FUTURE JOB | 4/20 - TOP 10:30 4/21 - BOT 9:00 4/21 - AOI 2:30 | 2B 2T 38/96 | 4/19 - KIT CLEAR 4/20 - TOP SIDE 1ST | 3 | 930 | X | Scientific Research Corporation | 103 Quality Cir Nw Ste 220 | Huntsville | AL
|  | 2023-04-25 | 114233-2 (4/14) BAL | NEW | 20 | L1 |  |  | 4/27 5D | FEDEX P | CLASS 3 ICS REQ BAKING (ECO #3) X-RAY & SAVE IMAGES DO NOT DEPANEL | 4/19 - BOT 11:30 4/19 - TOP 2:30 4/20 - AOI 9:30 | 1B 1T 91/392 | 4/14 - SHIPPED 40 OF 60 4/7 4/14 - KIT CLEAR (ALTA) 4/14 - ICs REQ T&R EXTRA TIME (DAY ONE IS FRI 4/21) | 2 | 40 |  | Ripple, LLC | 2056 S 1100 E | Salt Lake City | UT
|  | 2023-04-25 | 116854 (4/16) | NEW | 20 | L1 |  |  | 4/27 5D | FEDEX P | U1, U2 & U10 REQ 48 HRS BAKE ***SHARED PARTS W/ 116288 (DO NOT LOSE PARTS FROM TEARDOWN) | 4/19 - BOT 9:00 4/20 - TOP 9:30 4/20 - AOI 1:30 | 1B 1T 69/211 | 4/14 - AWT PART CONFS 4/17 - PARTS OK TO USE 4/17 - KIT CLEAR | 3 | 60 |  | ICR Inc | 300 S Craycroft Rd | Tucson | AZ
|  | 2023-04-25 | 116713 (4/12) | NEW | 120 | L2 |  |  | 4/26 10D | UPS RED | DEPANEL VERTICAL PLACEMENT REQ FOR DAUGHTER BOARD | 4/13 - TOP SIDE 8:30 4/14 - BOT SIDE 9:30 4/16 - AOI 10:00 | 1B 1T 58/117 | 4/12 - KIT CLEAR 4/13 - TOP SIDE 1ST | 19 | 2280 | X | Alliance Technology, LLC. | 600 N Dekora Woods Blvd | Saukville | WI
|  | 2023-04-25 | 117099 (4/16) | NEW | 5 | L2/L3 |  |  | 4/25 5D | FEDEX 2 DAY | DEPANEL LABEL REQ ECO #4 SHIP ON 4/25/23 | 4/18 - TOP SIDE 6:00 4/18 - BOT SIDE 1:00 4/18 - AOI 2:30 | 2B 3T 192/702 | 4/14 - AWT PART CONF #101 (L16) 4/18 - OK TO PLACE "L16" AS IS | 3 | 15 |  | Luna Innovations, Inc. | 3155 State St | Blacksburg | VA
|  | 2023-04-24 | 117356 (4/18) | RONC 104338 | 47 | L1 |  |  | 5/2 10D | UPS 3DAY | CLASS 3 | 4/18 - TOP SIDE 2:00 4/19 - AOI 8:30 | 1B/1T 11/23 | 4/18 - KIT CLEAR | 18 | 846 |  | Coastal Designs, LLC | 22 Jordan Cove Rd | Waterford | CT
|  | 2023-04-21 | 116591 (4/14) | RONC 109262 | 30 | L2 |  |  | 4/28 10D | FEDEX GND | XRAY & SAVE IMAGES | 4/16 - TOP SIDE 10:00 4/17 - AOI 6:00 | 1T 45/123 | 4/14 - KIT CLEAR | 12 | 360 |  | CACI | 45150 Business Ct | Sterling | VA
|  | 2023-04-20 | 113840-1 (3/29) PAR | NEW | 2 | L2 |  |  | 4/20 3D | UPS GND | *** 3 DAY TURN *** CofC PER ECO #2 | 4/6 - BOT SIDE 12:30 4/6 - TOP SIDE 2:30 4/7 - AOI 7:00 | 1B 1T 15/200 | 3/29 - SHORT #13 SMT; #12 THT 4/4 - SMT CLEAR 4/19 - KIT CLEAR | 11 | 22 |  | Magnix | 3301 Seaway Blvd | Everett | WA
|  | 2023-04-19 | 117480 (4/13) |  | 5 | L1 |  |  | 4/20 3D | FEDEX P | *** 3 DAY TURN *** CLASS 3 DEPANEL MECH ASSY REQ | 4/18 - TOP SIDE 7:00 4/18 - AOI | 2T 79/418 | 4/13 - WILL CLEAR 4/14 4/18 - KIT CLEAR | 5 | 25 |  | Pronto | 1186 Folsom St | San Francisco | CA
|  | 2023-04-19 | 117199-2 BAL (4/6) | RONC 110751 | 1 | L1 |  |  | 4/19 3D | FEDEX 2 DAY | *** 3 DAY TURN *** DEPANEL J9 J10 TRIM REQ MECH ASSY REQ | 4/13 - TOP SIDE 11:00 4/13 - AOI 1:30 | 2T 44/149 | 4/6 - SHORT #16 (D10) 4/13 - KIT CLEAR | 3 | 3 |  | Dephy, Inc. | 63 Great Rd | Maynard | MA
|  | 2023-04-18 | 117199-1 (4/6) | RONC 110751 | 29/30 |  |  |  | 4/18 3D | FEDEX 2 DAY | *** 3 DAY TURN *** DEPANEL J9 J10 TRIM REQ MECH ASSY REQ | 4/13 - TOP SIDE 11:00 4/13 - AOI 1:30 | 2T 44/149 | 4/6 - SHORT #16 (D10) 4/13 - KIT CLEAR | 3 | 87 |  | Dephy, Inc. | 63 Great Rd | Maynard | MA
|  | 2023-04-17 | 117166-2 (4/10) BAL | NEW | 10 |  |  |  | 4/18 5D | UPS RED | DEPANEL & SAND CofC & PACK SLIP PER ECO | 4/12 - BOT SIDE 10:30 4/12 - TOP SIDE 12:00 4/13 - AOI 8:00 | 1B 2T 74/691 | 4/10 - #38 (U9) DUE 4/11 4/11 - KIT CLEAR | 55 | 550 | X | Agin, Inc. | 12903 Ne 126th Pl | Kirkland | WA
|  | 2023-04-17 | 115998 (4/3) | ROWC 109867 | 500 |  |  |  | 4/17 10D | UPS INT | DEPANEL | 4/9 - BOT SIDE 6:00 4/9 - AOI 12:00 | 1B 1/7 | 4/3 - KIT CLEAR | 0 | 0 |  | ATL Technology CR | Warehouse G1-G2-G3-G4-G5 | SAN RAFAEL DE ALAJUELA
|  | 2023-04-17 | 116640 (3/27) | NEW | 375 |  |  |  | 4/17 15D | FEDEX GND | DEPANEL? - MISSING MOUSE BITES - CUST NOTIFIED #6 (U5) BTD | 3/31 - BOT SIDE 2:30 4/3 - TOP SIDE 8:00 4/3 - AOI 9:30 | 1B 1T 7/8 | 3/27 - KIT CLEAR 4/17 - STILL NO RESPONSE FROM CUST ON MISSING MOUSE BITES | 0 | 0 | X | Bridge Diagnostics, Inc. | 740 S Pierce Ave Ste 15 | Louisville | CO
|  | 2023-04-14 | 117166-1 (4/10) PAR | NEW | 2 | L1 |  |  | 4/18 5D | UPS RED | DEPANEL & SAND CofC REQ | 4/12 - BOT SIDE 10:30 4/12 - TOP SIDE 12:00 4/13 - AOI 8:00 | 1B 2T 74/691 | 4/10 - #38 (U9) DUE 4/11 4/11 - KIT CLEAR | 55 | 110 | X | Agin, Inc. | 12903 Ne 126th Pl | Kirkland | WA
|  | 2023-04-14 | 117148 (4/10) | NEW | 30 | L2 |  |  | 4/14 3D | FEDEX P | *** 3 DAY TURN *** DEPANEL POP 2 BOARDS W/ J1 BTD J1 DNI PS1 | 4/12 - BOT SIDE 6:00 4/12 - TOP SIDE 8:00 4/13 - AOI 8:30 | 1B 1T 33/61 | 4/10 - #15 (IC3..) DUE 4/11 4/11 - KIT CLEAR 4/12 - #37 (PS1) NO FIT | 17 | 510 |  | WiGL, Inc. | 2120 W Braker Ln Ste M | Austin | TX
|  | 2023-04-14 | 116974 (4/3) | NEW | 90 | L1 |  |  | 4/14 5D | FEDEX P | DEPANEL SEE ECO 2 FOR SERIAL #S AND LABELING | 4/10 - BOT SIDE 12:00 4/11 - TOP SIDE 1:00 4/12 - AOI 10:30 | 2B 2T 113/470 | 4/4 - FABS DUE 4/7 4/7 - KIT CLEAR | 10 | 900 | X | Sarcos Group LC | 661 S 600 W | Salt Lake City | UT
|  | 2023-04-14 | 116863 (4/4) | RONC 113064 | 200 | L1 |  |  | 4/14 8D | FEDEX 2 DAY | DEPANEL FOR TAD BAR CODE LABELS REQ PER ECO 2 | 4/5 - BOT SIDE 11:30 4/7 - TOP SIDE 9:30 4/11 - AOI 1:00 | 1B 2T 62/444 | 4/4 - KIT CLEAR 4/5 - AWT NEW STENCIL | 16 | 3200 | X | Command Alkon, Inc. | 6750 Crosby Ct | Dublin | OH
|  | 2023-04-13 | 117173 (4/6) | NEW | 50 | L2 |  |  | 4/13 5D | UPS GND | DEPANEL | 4/11 - BOT SIDE 10:00 4/11 - TOP SIDE 1:00 4/12 - AOI 11:30 | 1B 1T 53/205 | 4/6 - KIT CLEAR | 2 | 100 |  | Churchill Navigation dba Shotover Systems Inc | 5660 Airport Blvd Ste 101 | Boulder | CO
|  | 2023-04-12 | 116863 (4/4) | RONC 113064 | 50 | L1 |  |  | 4/14 8D | FEDEX 2 DAY | DEPANEL FOR TAD BAR CODE LABELS REQ PER ECO 2 | 4/5 - BOT SIDE 11:30 4/7 - TOP SIDE 9:30 4/11 - AOI 1:00 | 1B 2T 62/444 | 4/4 - KIT CLEAR 4/5 - AWT NEW STENCIL | 16 | 800 | X | Command Alkon, Inc. | 6750 Crosby Ct | Dublin | OH
|  | 2023-04-12 | 117116 (4/5) | NEW | 10 | L3 |  |  | 4/14 5D | UPS RED | DEPANEL VERIFY COMP SAFE FOR WASH | 4/9 - TOP SIDE 9:00 4/10 - TOP SIDE 10:00 4/10 - AOI 1:00 | 2B 2T 145/528 | 4/5 - FABS DUE 4/7 4/7 - KIT CLEAR 4/7 - TOP SIDE 1ST | 49 | 490 |  | Reprieve Cardiovascular, Inc. | 459 Fortune Blvd | Milford | MA
|  | 2023-04-12 | 117150 (4/4) | NEW | 45 | L2 |  |  | 4/13 5D | FEDEX P | DEPANEL | 4/6 - BOT SIDE 1:30 4/7 - TOP SIDE 8:30 4/7 - AOI 11:00 | 1B 1T 40/109 | 4/4 - FABS DUE 4/7 4/6 - KIT CLEAR | 13 | 585 |  | Blueline Sensors LLC | 405 Bay Dr | Stevensville | MD
|  | 2023-04-12 | 116995 (4/3) | NEW | 15 | L2 |  |  | 4/12 5D | FEDEX GND |  | 4/10 - BOT SIDE 5:00 4/11 - TOP SIDE 5:00 4/11 - AOI 10:00 | 1B 1T 65/614 | 4/3 - AWT FABS NO ETA 4/5 - KIT CLEAR | 12 | 180 |  | Flir | 3495 Kent Ave Ste U100 | West Lafayette | IN
|  | 2023-04-11 | 100605-6 (5TH ARTICLE) (3/7) BAL | RONC 4TH ARTICLE | 221 | L3 |  |  | 4/12 4/5 20D | FEDEX P |  | 3/13 - BOT SIDE 10:00 3/20 - TOP SIDE 8:30 3/21 - ON HOLD 3/22 - TOP SIDE 10:00 3/31 - AOI 6:00 | 2B 2T 205/2894 | 3/7 - 5/6 DAYS TO FINISH BOT; 5/6 DAYS TO FINISH TOP; 2 WEEKS TOTAL 3/8 - KIT CLEAR 3/21 - STENCIL DUE 3/22 | 4 | 884 | X | University of Oklahoma | 3190 Monitor Ave Rm 0220 | Norman | OK
|  | 2023-04-10 | 116503 (3/23) | NEW | 10 | L2 |  |  | 4/13 15D | UPS GND | DEPANEL | 4/6 - TOP SIDE 9:00 4/6 - AOI 12:30 | 2T 104/542 | 3/23 - KIT CLEAR | 57 | 570 |  | Droplet Measurement Technologies | 4600 Forbes Blvd Ste 201 | Lanham | MD
|  | 2023-04-10 | 115999 (3/6) | RONC 109868 | 500 | L2 |  |  | 4/10 4/7 4/4 10D | UPS WOLD WIDE EXP | DEPANEL FOR TAD ONLY (PLAN AHEAD/TAKES TIME + BAGGING!!!) (DUE 4/4 +3 DAYS FOR DEPANEL) | 4/1 - BOT SIDE 6:00 4/1 - TOP SIDE 11:00 4/6 - AOI 8:00 | 1B 1T 5/9 | 3/6 - FABS DUE 3/10 3/17 - FABS DUE EOD 3/20 3/21 - KIT CLEAR 3/22 - AWT FIXTURE | 0 | 0 | X | ATL Technology CR | 20108 SAN RAFAEL DE ALAJUELA | COSTA RICA
|  | 2023-04-07 | 116350-1ST (3/29) | NEW | 1 | L2 |  |  | 4/7 5D | UPS 3DAY | CLASS 3 | 3/31 - BOT SIDE 6:00 4/6 - TOP SIDE 8:00 4/6 - AOI 9:00 | 1B 2T 146/903 | 3/29 - SMT CLEAR 3/31 - BOT DONE 8:00 4/4 - KIT CLEAR | 72 | 72 |  | Coastal Designs, LLC | 22 Jordan Cove Rd | Waterford | CT
|  | 2023-04-07 | 114233-1 (3/31) PAR | NEW | 40 | L1 |  |  | 4/7 5D | FEDEX P | CLASS 3 ICS REQ BAKING (ECO #3) X-RAY & SAVE IMAGES DO NOT DEPANEL | 4/4 - BOT SIDE 7:00 4/5 - TOP SIDE 7:00 4/5 - AOI 11:30 | 1B 1T 91/392 | 3/31 - KIT CLEAR 3/31 - ICs REQ BAKING; RDY MONDAY MORN | 2 | 80 |  | Ripple, LLC | 2056 S 1100 E | Salt Lake City | UT
|  | 2023-04-07 | 114417 (3/14) | NEW | 25 | L1 |  |  | 4/11 20D | FEDEX GND | BOARD LABEL PER ECO #1 | 3/31 - BOT SIDE 8:00 3/31 - TOP SIDE 11:30 3/31 - AOI 2:30 | 1B 1T 33/82 | 3/14 - KIT CLEAR 3/31 - BOT DONE 10:30 | 12 | 300 |  | CACI | 45150 Business Ct Ste 440 | Sterling | VA
|  | 2023-04-06 | 116221 (3/31) | PAID RWK | 49 |  |  |  | 4/7 5D | FEDEX GND | R&R CN1 & CN2 FROM TOP TO BOTTOM | 3/31 - BACK | THT ONLY | 3/31 - KIT CLEAR | 4 | 196 |  | Technical Marine Service, Inc. | 6040 N Cutter Cir | Portland | OR
|  | 2023-04-05 | 116493-1ST (3/27) | NEW | 2 | L1 |  |  | 4/10 5D | FEDEX P |  | 4/3 - BOT SIDE 12:30 4/3 - TOP SIDE 1:30 4/3 - AOI 2:00 | 1B 1T 1/3 | 3/27 - FABS DUE 3/28 4/3 - KIT CLEAR | 0 | 0 |  | Loft Orbital Inc. | 810 Brickyard Cir | Golden | CO
|  | 2023-04-05 | 116047 (3/27) | NEW | 3 | L1 |  |  | 4/5 5D | FEDX P | CLASS 3 | 3/29 - TOP SIDE 10:00 3/29 - BOT SIDE 2:30 3/30 - AOI 10:30 | 2B 2T 184/1199 | 3/27 -PART SHORT DUE 3/28 3/28 - 2 BOARDS SKIP #77 3/29 - KIT CLEAR | 9 | 27 | X | Critical Frequency Design | 2420 Irwin St | Melbourne | FL
|  | 2023-04-05 | 116458-1 (3/22) PAR | ROWC 107934 | 30 | L2/L1 |  |  | 4/5 10D | FEDEX GND | PREBAKE "U46" | 3/31 - TOP SIDE 9:00 4/3 - BOT SIDE 9:30 4/3 - AOI 12:30 | 2B 2T 106/290 | 3/22 - KIT CLEAR 3/31 - TOP SIDE 1ST | 1 | 30 | X | McQ | 1545 Forbes St | Fredericksburg | WA
|  | 2023-04-05 | 116984 (3/30) | NEW | 4 | L1 |  |  | 4/5 3D | FEDEX P | *** 3 DAY TURN *** DEPANEL MECH ASSY REQ | 3/31 - TOP SIDE 10:30 3/31 - AOI 11:30 | 1T 56/186 | 3/30 - #29 (U603) DUE 3/31 THEN SMT CLEAR 3/31 - KIT CLEAR | 47 | 188 |  | Emerson | 4455 Boeing Dr | Rockford | IL
|  | 2023-04-05 | 116877 (3/29) PAR | NEW | 250 | L1 |  |  | 4/5 5D | FEDEX P | BTD #7 (PS2) | 3/30 - BOT SIDE 10:30 3/30 - TOP SIDE 2:30 3/31 - AOI 8:00 | 1B 1T 7/14 | 3/29 - SMT CLEAR; KIT CLEAR FOR 230/250 3/30 - KIT CLEAR | 2 | 500 | X | PSA-Production Systems Automation | 201 Clark Rd | Duryea | PA
|  | 2023-04-05 | 114946-1 (3/7) PAR 2 | NEW | 795 | L3 |  |  | 4/5 20D | UPS GND | CLASS 3 DEPANEL | 3/8 - BOT SIDE 12:30 3/9 - TOP SIDE 2:30 3/10 - AOI 2:30 | 2B 2T 30/155 | 3/7 - WILL CLEAR 3/8 3/8 - KIT CLEAR | 3 | 2385 | X | ICC, Inc. | 230 Horizon Dr | Verona | WI
|  | 2023-04-04 | 107990 (3/10) | NEW | 1000 | L2 |  |  | 4/4 15D | FEDEX P | DEPANEL | 3/23 - BOT SIDE 6:00 4/1 - TOP SIDE 6:00 4/3 - AOI 2:00 | 1B 1T 28/29 | 3/10 - FABS DUE 3/13 3/14 - KIT CLEAR 3/31 - BOT DONE 12:00 | 0 | 0 | X | Moates.Net | 16848 Jefferson Hwy | Baton Rouge | LA
|  | 2023-04-03 | 115701 (3/20) | ROWC 108135 | 50 | L2 |  |  | 4/4 10D | UPS GND | DEPANEL ENSURE "LD1 & 2" ARE VERTICALLY STRAIGHT | 3/22 - TOP SIDE 12:00 3/22 - AOI 4:30 | 1T 39/150 | 3/20 - PART #21 (U8) DUE TODAY 3/21 - KIT CLEAR | 30 | 1500 |  | Cyber Sciences Inc | 229 Castlewood Dr | Murfreesboro | TN
|  | 2023-04-03 | 116516 (3/17) | NEW | 10 | L2 |  |  | 4/3 10D | FEDEX P | DEPANEL | 3/24 - TOP SIDE 9:00 3/25 - BOT SIDE 2:30 3/28 - AOI 11:00 | 1B 1T 44/554 | 3/17 - SMT CLEAR 3/20 - KIT CLEAR | 2 | 20 |  | Pronto | 1186 Folsom St | San Francisco | CA
|  | 2023-03-31 | 116048-2ND (3/3) PAR | PAID RWK | 1 |  |  |  | 3/31 5D | FEDEX GND | R&R ALL MAX14430EAEE TO SI8645BA-B-IU | 3/6 - BACK |  | 3/7 - FA DUE 3/13 3/24 - CLEARED FOR QTY 1 | 34 | 34 |  | HRL Laboratories | 3011 Malibu Canyon Rd | Malibu | CA
|  | 2023-03-31 | 112908 (3/16) | NEW | 10 | L1 |  |  | 3/31 10D | FEDEX GND | MUST USE CUSTOMER BAR CODE LABELS - ECO #2 | 3/22 - BOT SIDE 2:00 3/23 - TOP SIDE 7:30 3/23 - AOI 10:30 | 1B 2T 104/753 | 3/16 - SHORT U14 (#36) 3/17 - KIT CLEAR | 31 | 310 | X | GatesAir, Inc. | 3200 Wisman Ln | Quincy | IL
|  | 2023-03-30 | 116743 (3/23) | NEW | 2 | L1 |  |  | 3/31 5D | FEDEX P | DEPANEL CLASS 3 DO NOT DMG PACKAGING SHARE PARTS WITH B116744 | 3/28 - BOT SIDE 8:00 3/28 - TOP SIDE 10:30 3/28 - AOI 12:00 | 1B 1T 39/386 | 3/23 - FABS DUE 3/27 3/24 - KIT CLEAR 3/24 - RUN W/ B116744 | 91 | 182 |  | University Of Oklahoma | 3190 Monitor Ave Rm 0220 | Norman | OK
|  | 2023-03-30 | 116744 (3/23) | NEW | 2 | L1 |  |  | 3/31 5D | FEDEX P | DEPANEL CLASS 3 DO NOT DMG PACKAGING SHARE PARTS WITH B116743 | 3/28 - BOT SIDE 8:00 3/28 - TOP SIDE 10:30 3/28 - AOI 12:00 | 1B 1T 39/386 | 3/23 - FABS DUE 3/27 3/24 - KIT CLEAR 3/24 - RUN W/ B116743 | 91 | 182 |  | University Of Oklahoma | 3190 Monitor Ave Rm 0220 | Norman | OK
|  | 2023-03-30 | 115113 (3/15) | NEW | 10 | L2 |  |  | 3/30 3D | FEDEX P | *** 3 DAY TURN *** DEPANEL | 3/28 - BOT SIDE 12:30 3/28 - TOP SIDE 1:30 3/28 - AOI 2:30 | 1B 1T 2/2 | 3/15 - FABS DUE 3/17 3/27 - KIT CLEAR 3/27 | 0 | 0 |  | Tomahawk Robotics, LLC | 2326 Irwin St | Melbourne | FL
|  | 2023-03-30 | 116927 (3/24) | PAID RWK | 2 |  |  |  | 3/30 4D | UPS RED | R&R OLD W/NEW S/N 2124002: U62 S/N 2124001: U66 & U73 | BACK | THT ONLY | 3/24 - KIT CLEAR | 3 | 6 |  | Coastal Designs, LLC | 22 Jordan Cove Rd | Waterford | CT
|  | 2023-03-30 | 116107-1ST (3/21) | NEW | 2 | L1 |  |  | 3/30 5D | UPS GND | 1ST ARTICLE DEPANEL | 3/28 - BOT SIDE 12:30 3/28 - TOP SIDE 1:30 3/29 - AOI 8:00 | 1B 2T 91/245 | 3/21 - FABS DUE 3/24 3/23 - KIT CLEAR | 5 | 10 | x | Graph-Tech USA, LLC | 3200 N Kings Hwy | Fort Pierce | FL
|  | 2023-03-30 | 117025 (3/27) | RONC 116464 | 12 | L2 |  |  | 3/30 3D | FEDEX P | *** 3 DAY TURN *** USE FIXTURE FOR THT PARTS | 3/28 - TOP SIDE 1:30 3/28 - AOI 2:30 | 1T 1/2 | 3/27 - KIT CLEAR | 4 | 48 |  | Loft Orbital Inc. | 321 11th St | San Francisco | CA
|  | 2023-03-30 | 116432-1 (3/10) PAR | NEW | 2 | L2 |  |  | 3/30 3D | FEDEX P | *** 3 DAY TURN *** CLASS 3 DEPANEL & SAND ALL EMPTY PACKAGES/TRAYS RETURN TO CUSTOMER 1 PCB w/ U75 & U77 1 PCB w/o U75 & U77 | 3/27 - BOT SIDE 6:00 3/27 - TOP SIDE 8:30 3/28 - AOI 12:00 | 1B 2T 147/2945 | 3/10 - FABS DUE 3/15 3/24 - KIT CLEAR 3/28 - DELAM TOP SIDE | 77 | 154 |  | Aeronix Inc | 777 Lowndes Hill Rd | Greenville | SC
|  | 2023-03-30 | 115913-2ND (3/22) | ROWC 1ST | 48 | L1 |  |  | 3/30 5D | FEDEX P | QUALITY ALERT! SEE ECO DEPANEL MECH ASSY REQ QR CODE LABEL *X-RAY &SAVE | 3/27 - BOT SIDE 8:00 3/27 - TOP SIDE 12:30 3/28 - AOI 8:00 | 1B 1T 104/753 | 3/22 - KIT CLEAR | 10 | 480 | X | Anderson Connectivity | 601 Atlantis Rd | Melbourne | FL
|  | 2023-03-29 | 116091-1 (3/9) PAR | RONC 109493 | 8 | L2 |  |  | 3/30 15D | FEDEX P | PRESS FIT REQ | 3/13 - BOT SIDE 1:00 3/14 - TOP SIDE 8:00 3/14 - AOI 11:30 | 1B 2T 66/757 | 3/9 - KIT CLEAR | 12 | 96 | X | IonQ, Inc. | 4505 Campus Dr | College Park | MD
|  | 2023-03-29 | 116241 (3/21) | NEW | 250 | L1 |  |  | 3/29 5D | FEDEX P | X | 3/23 - BOT SIDE 10:30 3/23 - TOP SIDE 3:30 3/27 - AOI 8:00 | 1B 2T 45/131 | 3/21 - FABS DUE 3/22 & SHORT ATTRITION 3/22 - KIT CLEAR | 1 | 250 | X | PSA-Production Systems Automation | 201 Clark Rd | Duryea | PA
|  | 2023-03-28 | 115937 (3/28) | PAID RWK | 49 |  |  |  | 3/28 1D | FEDEX P | *** 1 DAY TURN *** ROTATE U16 | BACK | THT ONLY | 3/27 - KIT CLEAR | 1 | 49 |  | Durbin Group | 10950 Pierson Dr | Fredericksburg | VA
|  | 2023-03-28 | 115662 (3/21) | NEW | 205 | L1 |  |  | 3/28 5D | FEDEX GND | DEPANEL | 3/21 - BOT SIDE 12:30 3/22 - TOP SIDE 9:30 3/22 - AOI 2:00 | 1B 1T 45/131 | 3/21 - KIT CLEAR | 5 | 1025 | X | Pfeiffer Vacuum, Inc | 1967 S Oregon St | Yreka | CA
|  | 2023-03-27 | 116061 (3/15) | RONC 108919 | 30 | L2 |  |  | 3/29 10D | UPS RED | MECHANICAL ASSY REQ SHIPPING: WRAP THIN $ THICK BUBBLE - HAD DAMAGED BOARDSLAST TIME!!! | 3/16 - BOT SIDE 6:00 3/16 - TOP SIDE 8:00 3/16 - AOI 9:00 | 1B 1T 26/35 | 3/15 - KIT CLEAR | 25 | 750 |  | Raven - Aerostar International, Inc. | 1001 W Algonquin St | Sioux Falls | SD
|  | 2023-03-27 | 116783 (3/17) | NEW | 50 | L3 |  |  | 3/28 5D | FEDEX GND | DEPANEL | 3/21 - TOP SIDE 8:30 3/21 - AOI 10:30 | 1T 29/94 | 3/17 - KIT WILL BE CLEAR SOON 3/21 - KIT CLEAR | 13 | 650 |  | AMPT | 4850 INNOVATION DR | Fort Collins | CO
|  | 2023-03-27 | 116545 (3/17) | NEW | 24 | L1 |  |  | 3/27 5D | UPS RED | TRIM THT LEADS FLUSH | 3/21 - BOT SIDE 9:00 3/21 - TOP SIDE 10:30 3/21 - AOI 12:30 | 1B 1T 47/141 | 3/17 - FABS DUE 3/21 3/20 - KIT CLEAR | 7 | 168 |  | Particle Measuring Systems | 5475 Airport Blvd | Boulder | CO
|  | 2023-03-24 | 116344 (3/20) | NEW | 250 | L2 |  |  | 3/27 5D | FEDEX P | X | 3/21 - TOP SIDE 6:00 3/22 - AOI 12:00 | 1T 30/50 | 3/20 - KIT CLEAR | 0 | 0 | X | PSA-Production Systems Automation | 201 Clark Rd | Duryea | PA
|  | 2023-03-24 | 115728 (3/17) | NEW | 205 | L2 |  |  | 3/27 5D | FEDEX GND | DEPANEL | 3/20 - TOP SIDE 10:30 3/20 - AOI 2:30 | 1T 9/20 | 3/17 - SHORT #4 (D1) ETA 3/20 3/20 - KIT CLEAR | 11 | 2255 |  | Pfeiffer Vacuum, Inc | 1967 S Oregon St | Yreka | CA
|  | 2023-03-24 | 116624 (3/13) | NEW | 4 | L1 |  |  | 3/24 5D | UPS RED | SWAGE MOUNT CofC REQ | 3/17 - TOP SIDE 10:00 3/17 - AOI 3:00 | 2T 77/282 | 3/13 - SMT CLEAR 3/17 - KIT CLEAR | 68 | 272 |  | South Coast Circuits, Inc. | 3506 W Lake Center Dr Ste A | Santa Ana | CA
|  | 2023-03-24 | 114820-2ND (3/15) | RONC 1ST | 18 | L2 |  |  | 3/29 10D | UPS GND | DEPANEL & SAND | 3/17 - TOP SIDE 11:30 3/17 - AOI 1:00 | 1T 26/56 | 3/15 - KIT CLEAR | 24 | 432 |  | Beckman Coulter | 5355 W 76th St Bldg 87 Dock 39 | Indianapolis | IN
|  | 2023-03-23 | 115580 (3/13) | NEW | 10 | L1 |  |  | 3/27 10D | FEDEX 2ND | *SHIPPING - INCLUDE CofC IN SHIPMENT | 3/15 - TOP SIDE 12:00 3/16 - AOI 8:30 | 1T 59/246 | 3/13 - KIT CLEAR | 1 | 10 |  | Duotech Services Inc | 245 Industrial Park Rd | Franklin | NC
|  | 2023-03-23 | 116605 (3/17) | NEW | 4 | L3 |  |  | 3/24 3D | FEDEX P | *** 3 DAY TURN *** NO LABELING REQ | 3/21 - BOT SIDE 10:30 3/21 - TOP SIDE 12:00 3/21 - AOI 1:30 | 1B 1T 29/693 | 3/17 - FABS DUE 3/20 3/21 - KIT CLEAR | 5 | 20 |  | Jet Propulsion Lab | 4800 Oak Grove Dr | Pasadena | CA
|  | 2023-03-23 | 116391 (3/20) | NEW | 20 | L1 |  |  | 3/23 3D | FEDEX P | *** 3 DAY TURN *** CofC/PACK SLIP PER ECO #2 | 3/20 - BOT SIDE 12:30 3/20 - TOP SIDE 2:30 3/21 - AOI 9:00 | 1B 1T 40/174 | 3/20 - KIT CLEAR | 0 | 0 | X | Attollo Engineering, LLC | 160 Camino Ruiz | Camarillo | CA
|  | 2023-03-22 | 116137 (3/17) | RONC 114452 | 1500 | L2 |  |  | 3/24 5D | UPS RED | DEPANEL | 3/20 - TOP SIDE 6:00 3/20 - AOI 8:00 | 1T 2/4 | 3/17 - KIT CLEAR | 0 | 0 |  | Instron | 825 University Ave | Norwood | MA
|  | 2023-03-22 | 114861 (3/13) | ROWC 103335 | 450 | L1 |  |  | 3/23 5D | FEDEX P | DEPANEL & SAND | 3/17 - BOT SIDE 3:00 3/20 - TOP SIDE 8:00 3/20 - AOI 12:00 | 2B 2T 47/83 | 3/14 - WILL CLEAR 3/16 3/16 - KIT CLEAR | 0 | 0 | X | Scientific Research Corporation | 103 Quality Cir Nw Ste 220 | Huntsville | AL
|  | 2023-03-22 | 116086-1ST (3/7) | NEW | 10 | L1 |  |  | 3/23 5D | FEDEX P | DEPANEL XFER MATL FROM B110680 | 3/16 - TOP SIDE 8:30 3/16 - AOI 10:00 | 2T 83/250 | 3/7 - WILL CLEAR 3/15 3/16 - KIT CLEAR | 8 | 80 |  | Servomex Inc | 4 Constitution Way | Woburn | MA
|  | 2023-03-22 | 112967 (10/27) | NEW | 200 | L2 |  |  | 3/23 11/9 9D | FEDEX P | DEPANEL T/H - "SW1A-5A & SW1B-5B" DNI | 10/31 - BOT SIDE 12:00 11/1 - TOP SIDE 10:30 11/2 - AOI 10:30 | 1B 1T 7/12 | KIT CLEAR 10/27 12/27 - SHORT 2 ITEMS 2/9 - LAST PART (#10) DUE EARLY NEXT WEEK 3/10 - KIT CLEAR | 68 78 | 13600 |  | Disney Worldwide Shared Service | 532 Paula Ave | Glendale | CA
|  | 2023-03-22 | 115888 (3/3) | ROWC 112992 | 50 | L3 |  |  | 3/22 10D | FEDEX P | DEPANEL MECH ASSY REQ DO NOT SHIP EARLY | 3/7 - BOT SIDE 10:00 3/7 - TOP SIDE 11:00 3/7 - AOI 12:00 | 1T 28/59 | 3/3 - SMT CLEAR 3/8 - KIT CLEAR | 35 | 1750 |  | Industrialex Manufacturing | 6250 Joyce DR | Arvada | CO
|  | 2023-03-20 | 115929 (2/21) | NEW | 10 | L1 |  |  | 3/21 3/6 5D | UPS RED | DEPANEL BARCODE LABEL REQ CofC PER ECO 6 | 3/14 - BOT SIDE 10:30 3/14 - TOP SIDE 1:30 3/15 - AOI 8:00 | 1B 2T 99/563 | 2/21 - SHORT #12 & 43 2/27 - #43 DNI; KIT CLEAR | 5 | 50 |  | Tesla | 3500 Deer Creek Rd | Palo Alto | CA
|  | 2023-03-20 | 116601 (3/10) | NEW | 15 | L2 |  |  | 3/20 5D | FEDEX P | CLASS 3 DEPANEL BARCODE LABELLS REQ | 3/14 - BOT SIDE 12:30 3/15 - TOP SIDE 7:00 3/15 - AOI 10:30 | 1B 1T 67/439 | 3/10 - FABS DUE 3/13 3/13 - KIT CLEAR | 0 | 0 |  | Artis, LLC | 4246 S Riverboat Rd Ste 250 | Taylorsville | UT
|  | 2023-03-20 | 116381 (3/7) | NEW | 5 | L1 |  |  | 3/20 5D | FEDEX P | DEPANEL WASH W/CUSTOMER CLEANING AGENT | 3/11 - TOP SIDE 1:30 3/13 - AOI 10:00 | 95/482 | 3/7 - FABS DUE 3/10 3/9 - SMT CLEAR 3/13 - KIT CLEAR | 81 | 405 |  | Lake Shore Cryotronics, Inc. | 550 Tressler Dr - Receiving Dock | Westerville | OH
|  | 2023-03-17 | 107325 (2/27) | NEW | 2 | L1 |  |  | 3/20 15D | FEDEX GND | DEPANEL | 3/8 - BOT SIDE 1:00 3/9 - TOP SIDE 8:30 3/9 - AOI 11:00 | 1B 2T 131/313 | 2/27 - KIT CLEAR | 10 | 20 | X | Golden Security Services US Inc. | 1250 E Hallandale Beach Blvd | Hallandale Beach | FL
|  | 2023-03-17 | 116539 (3/10) | NEW | 10 | L1 |  |  | 3/17 3D | FEDEX P | *** 3 DAY TURN *** DEPANEL | 3/15 - TOP SIDE 8:00 3/15 - AOI 11:00 | 2T 77/266 | 3/10 - FABS DUE 3/14 & #77 (R50) DUE 3/15 3/14 - KIT CLEAR | 51 | 510 |  | Friedrich Air Conditioning LLC | 10001 Reunion Pl | San Antonio | TX
|  | 2023-03-17 | 115259 (3/9) | NEW | 25 | L2 |  |  | 3/16 5D | UPS BLU | DEPANEL | 3/10 - TOP SIDE 8:00 3/13 - BOT SIDE 8:30 3/13 - AOI 1:00 | 2B 1T 117/315 | 3/9 - KIT CLEAR 3/10 - TOP SIDE 1ST | 8 | 200 |  | Newark Electronics | 1901 10th St | Plano | TX
|  | 2023-03-16 | 115476-2ND (3/3) | RONC 1ST | 40 | L2 |  |  | 3/17 10D | FEDEX P | DEPANEL | 3/6 - BOT SIDE 12:30 3/7 - TOP SIDE 8:30 3/7 - AOI 12:00 | 1B 1T 68/200 | 3/3 - KIT CLEAR | 3 | 120 |  | CACI | 45150 Business Ct Ste 200 | Sterling | VA
|  | 2023-03-16 | 116602 (3/10) | NEW | 5 | L1 |  |  | 3/16 3D | FEDEX P | *** 3 DAY TURN *** CLASS 3 DEPANEL BARCODE LABELS | 3/13 - BOT SIDE 10:00 3/13 - TOP SIDE 2:30 3/14 - AOI 10:00 | 1B 2T 96/489 | 3/10 - FABS DUE 3/13 3/13 - KIT CLEAR | 0 | 0 | X | Artis LLC | 4246 S Riverboat Rd | Taylorsville | UT
|  | 2023-03-16 | 116268 (3/9) | NEW | 40 | L1 |  |  | 3/16 5D | FEDX P | DEPANEL ASSY RESTRICTIONS: SEE ECO | 3/9 - BOT SIDE 2:30 3/10 - TOP SIDE 10:00 3/11 - AOI 8:30 | 2B 2T 142/750 | 3/9 - KIT CLEAR | 5 | 200 |  | Allocortech Inc. | 440 N Commerce Ave | Waynesboro | VA
|  | 2023-03-16 | 114946-1 (3/7) PAR 1 | NEW | 105 | L3 |  |  | 3/16 20D | UPS GND | CLASS 3 DEPANEL EXPEDITE 105 OF 900 | 3/8 - BOT SIDE 12:30 3/9 - TOP SIDE 2:30 | 2B 2T 30/155 | 3/7 - WILL CLEAR 3/8 3/8 - KIT CLEAR | 3 | 315 |  | ICC, Inc. | 230 Horizon Dr | Verona | WI
|  | 2023-03-15 | 116221 (2/28) | NEW | 50 |  |  |  | 3/16 10D | FEDEX GND |  | 3/2 - BACK | THT ONLY | 2/28 - FABS DUE 3/1 3/2 - KIT CLEAR | 31 | 1550 |  | Technical Marine Service, Inc. | 6040 N Cutter Cir | Portland | OR
|  | 2023-03-15 | 116240 (3/6) | NEW | 6 | L2/L3 |  |  | 3/15 7D | FEDEX P | X | 3/8 - BOT SIDE 7:00 3/8 - TOP SIDE 10:30 3/8 - AOI 12:30 | 1B 2T 162/798 | 3/6 - KIT CLEAR 3/7 - S/U BOT 1ST | 101 | 606 |  | Alfred E Mann Foundation | 25134 Rye Canyon Loop | Ste 200 | CA
|  | 2023-03-15 | 115975 (2/24) | NEW | 115 | L1 |  |  | 3/15 10D | FEDEX GND | RTV REQ PER ECO #1 | 3/3 - BOT SIDE 3:00 3/6 - TOP SIDE 9:00 3/6 - AOI 12:00 | 1B 1T 17/86 | 2/24 - FABS DUE 2/27 THEN SMT CLEAR 2/28 - SMT CLEAR 3/2 - KIT CLEAR | 16 | 1840 | X | L3 Open Water Power | 1350 Jefferson Rd | Rochester | NY
|  | 2023-03-15 | 116340 (3/6) | ROWC 114404 | 400 | L1 |  |  | 3/15 3D | FEDEX P | *** 3 DAY TURN *** DEPANEL - SET VSCORE DEPTH TO "5" - BELOW "5" WILL CAUSE STRESS DAMAGE BARCODE LABELS | 3/11 - TOP SIDE 8:30 3/11 - AOI 1:30 | 2T 22/50 | 3/6 - KIT WILL CLEAR SOON 3/10 - SMT CLEAR 3/14 - KIT CLEAR | 11 | 4400 |  | Command Alkon Inc. | 6750 Crosby Ct | Dublin | OH
|  | 2023-03-14 | 116084-2ND (3/8) | RONC 1ST | 200 | L2 |  |  | 3/16 5D | FEDEX P | DEPANEL | 3/9 - BOT SIDE 8:30 3/9 - TOP SIDE 10:00 3/9 - AOI 11:30 | 1B 1T 10/22 | 3/9 - KIT CLEAR | 0 | 0 |  | Durbin Group | 10950 Pierson Dr | Fredericksburg | VA
|  | 2023-03-14 | 113565-2 (3/7) BAL | PAID RWK | 720 |  |  |  | 3/14 5D | UPS GND | REMOVE R29 | 3/7 - BACK | THT ONLY | 3/7 - KIT CLEAR | 1 | 720
|  | 2023-03-14 | 109882-2ND (1/23) BAL | ROWC 1ST ARTICLE | 2 | L2 |  |  | 2/17 2/3* 5D | FEDEX P | *ALL HAND SOLDERED RF CONNECTORS HAVE MAX TEMP 165C 100% XRAY REQ & SAVE IMAGES MECH ASSY REQ | 1/25 - TOP SIDE 11:00 2/2 - AOI 2:00 2/11 - BOT SIDE 7:30 2/11 - TOP SIDE 9:00 2/11 - AOI 12:00 | 2T 95/650 | 1/23 - FABS DUE 1/24 - 1/26 1/25 - FABS BAL DUE 2/2 2/10 - KIT CLEAR | 82 | 164 | X | CACI | 45150 Business Ct Ste 200 | Sterling | VA
|  | 2023-03-13 | 116048-1ST (3/3) | PAID RWK | 1 |  |  |  | 3/13 5D | FEDEX GND | R&R ALL MAX14430EAEE TO SI8645BA-B-IU | 3/6 - BACK |  | 3/6 - KIT CLEAR | 34 | 34 |  | HRL Laboratories | 3011 Malibu Canyon Rd | Malibu | CA
|  | 2023-03-13 | 113565-1 (3/6) PAR | PAID RWK | 133 |  |  |  | 3/13 5D | UPS GND | REMOVE R29 | 3/6 - BACK | THT ONLY | 3/6 - KIT CLEAR | 1 | 133
|  | 2023-03-13 | 115421 (2/14) | NEW | 300 | L3 |  |  | 3/13 15D | UPS GND | "HDR1 PLACE ON BOT SIDE PER ECO 1 "LED1-9" SOLDER IN STRAIGHT LINE (HOLES MAY BE OVERSIZED) | 3/2 - BOT SIDE 8:30 3/2 - TOP SIDE 2:00 3/3 - AOI 8:30 | 1B 1T 24/47 | 2/14 - FABS DUE 2/16 2/17 - KIT CLEAR | 13 | 3900 | X | Hamilton Mfg. Corp | 1026 Hamilton Dr | Holland | OH
|  | 2023-03-10 | 116347 (3/3) | NEW | 10 | L1 |  |  | 3/10 3D | FEDEX P | *** 3 DAY TURN *** DEPANEL MECH ASSY REQ | 3/7 - BOT SIDE 11:30 3/7 - TOP SIDE 1:30 3/8 - AOI 7:30 | 1B 1T 53/746 | 3/3 - SHORT #56 (S1_R8...) 3/7 - KIT CLEAR | 10 | 100 |  | John Hopkins University Applied Physics La | 11100 Johns Hopkins Rd | Laurel | MD
|  | 2023-03-10 | 116158-2 (3/2) BAL | NEW | 6 | L3 |  |  | 3/10 5D | FEDEX P |  | 3/3 - TOP SIDE 8:30 3/3 - BOT SIDE 1:30 3/4 - AOI 12:00 | 2B 2T 165/2069 | 3/2 - WILL CLEAR SOON 3/7 - KIT CLEAR | 65 | 390 |  | Skyryse, Inc. | 777 S Aviation Blvd Ste 230 | El Segundo | CA
|  | 2023-03-10 | 116474 (3/3) | NEW | 30 | L3 |  |  | 3/10 3D | FEDEX P | *** 3 DAY TURN *** DEPANEL & SAND | 3/7 - TOP SIDE 11:00 3/8 - AOI 9:30 | 1T 39/120 | 3/6 - FABS DUE 3/7 3/7 - KIT CLEAR | 14 | 420 |  | Waites Wireless | 532 Enterprise Dr | Erlanger | KY
|  | 2023-03-10 | 116438 (3/6) | NEW | 10 | L1 |  |  | 3/10 3D | FEDEX P | *** 3 DAY TURN *** DEPANEL J14 J23 PIN REMOVED | 3/8 - BOT SIDE 7:30 3/8 - TOP SIDE 10:30 3/8 - AOI 1:00 | 1B 1T 80/340 | 3/6 - KIT WILL CLEAR 3/8 3/7 - KIT CLEAR | 43 | 430 |  | Friedrich Air Conditioning LLC | 10001 Reunion Pl | San Antonio | TX
|  | 2023-03-10 | 100610-4TH-2 (1/6) BAL | RONC 3RD ARTICLE | 107 | L3/L2 |  |  | 3/10 3/8 3/3 2/25H 20D | #VALUE! | ***NEW LEAD SOLDER PROCESS FOR U1A-U1H - DO NOT WASH U1A-U1H - USE SAME PROCESS AS B100606*** | 1/10 - BOT SIDE 10:00 2/8 - TOP SIDE 10:30 2/14 - AOI 1:00 | 2B 3T 237/3848 | 1/6 - RUN BOT ONLY; RUN TOP AFTER B100606 1/13 - QTY 121 DONE 1/17 - BOT DONE 11:30 | 7 | 749 | X | University of Oklahoma | 3190 Monitor Ave Rm 0220 | Norman | OK
|  | 2023-03-09 | 115378 (2/24) | RONC 102423 | 400 | L1 |  |  | 3/10 10D | FEDEX P | DEPANEL | 3/3 - TOP SIDE 12:00 3/3 - AOI 3:00 | 1T 3/3 | 2/24 - KIT CLEAR | 0 | 0 |  | Kinetic Vision | 10651 Aerohub Blvd | Cincinnati | OH
|  | 2023-03-09 | 116535 (3/6) | NEW | 5 | L1 |  |  | 3/9 3D | UPS RED | *** 3 DAY TURN *** DEPANEL | 3/7 - BOT SIDE 7:00 3/7 - TOP SIDE 8:00 3/7 - AOI 10:30 | 1B 1T 68/368 | 3/6 - KIT CLEAR | 3 | 15 |  | Pronto | 1186 Folsom St | San Francisco | CA
|  | 2023-03-09 | 115295 (2/27) | NEW | 25 | L1 |  |  | 3/9 5D | UPS BLU | "SMT SOLDER PASTE MUST BE ALPHA WS-820!!!" CLASS 3 DEPANEL | 3/3 - TOP SIDE 9:30 3/3 - BOT SIDE 10:00 3/3 - AOI 12:00 | 1B 1T 49/90 | 2/24 - SMT CLEAR 3/2 - KIT CLEAR 3/3 - TOP SIDE 1ST | 5 | 125 |  | Newark Electronics | 1901 10th St | Plano | TX
|  | 2023-03-09 | 116452 (3/3) | NEW | 15 | L3 |  |  | 3/9 3D | FEDEX P | *** 3 DAY TURN *** DEPANEL | 3/6 - BOT SIDE 9:00 3/6 - TOP SIDE 11:00 3/6 - AOI 1:00 | 1B 1T 5/57 | 3/3 - FABS DUE 3/6 3/6 - KIT CLEAR | 69 | 1035 |  | IonQ, Inc. | 4505 Campus Dr | College Park | MD
|  | 2023-03-08 | 116158-1 (3/2) PAR | NEW | 1 | L3 |  |  | 3/8 5D | FEDEX P | EXPEDITE 1 OF 7 | 3/3 - TOP SIDE 8:30 3/3 - BOT SIDE 1:30 3/4 - AOI 12:00 | 2B 2T 165/2069 | 3/2 - WILL CLEAR SOON 3/3 - TOP SIDE 1ST 3/7 - KIT CLEAR | 65 | 65 |  | Skyryse, Inc. | 777 S Aviation Blvd Ste 230 | El Segundo | CA
|  | 2023-03-08 | 115052 (2/13) | NEW | 100 | L2 |  |  | 3/8H 15D | UPS GND | DEPANEL | 3/2 - TOP SIDE 6:00 3/2 - BOT SIDE 2:00 3/3 - AOI 2:30 | 1B 1T 27/157 | 2/13 - KIT WILL CLEAR 2/14 2/14 - KIT CLEAR 3/2 - TOP SIDE 1ST | 35 | 3500 | X | Graph-Tech USA, LLC | 3200 N Kings Hwy | Fort Pierce | FL
|  | 2023-03-08 | 116106 (2/21) | ROWC 111701 | 100 | L3 |  |  | 3/8 10D | UPS GND | DEPANEL | 2/28 - BOT SIDE 12:30 3/1 - TOP SIDE 11:00 3/1 - AOI 2:30 | 1B 1T 42/245 | 2/21 - FABS DUE 2/23 2/22 - KIT CLEAR | 34 | 3400 | X | Graph-Tech USA, LLC | 3200 N Kings Hwy | Fort Pierce | FL
|  | 2023-03-07 | 114812-6 (12/22) PAR |  | 50 | *SHIP HOLD |  |  | 2/28 2/22 1/9H 10D | UPS RED | DEPANEL CLASS 3 SHIPPING - REMOVE ALL PICK & PLACE PADS (ECO #9) | 12/29 - BOT SIDE 8:30 2/8 - TOP SIDE 10:30 2/9 - AOI 2:30 NEED TO PLACE (REWORK) DNI PARTS ON 15 BOARDS | 1B 2T 92/554 | 12/22 - KIT CLEAR 12/27 - AA SHIPPING HOLD 12/28 - QTY 145 CLEAR FOR BOT SIDE 1/5 - INSTALL #26, 9, 77, 79 & 80 | 16 | 800 |  | Precision Graphics Inc | 21 County Line Rd | Somerville | NJ
|  | 2023-03-07 | 112356 (2/21) | RONC 110797 | 380 | L1 |  |  | 3/7 10D | FEDEX P | CLASS 3 DEPANEL QUALITY ALERT --- SEE ECO | 3/1 - BOT SIDE 3:30 3/2 - TOP SIDE 12:00 3/3 - AOI 9:30 | 1B 1T 39/71 | 2/21 - KIT CLEAR | 0 | 0 | X | INTEGRA LIFE SCIENCES
|  | 2023-03-07 | 115825 (2/21) | RONC 110095 | 70 |  |  |  | 3/7 10D | UPS GND | "J2" REFER TO ECO FOR PLACEMENT DEPANEL | 2/21 - BACK | THT ONLY | 2/21 - KIT CLEAR | 1 | 70 |  | Churchill Navigation dba Shotover Systems Inc | 5660 Airport Blvd Ste 101 | Boulder | CO
|  | 2023-03-07 | 115661 (2/22) | NEW | 20 | L3 |  |  | 3/7 5D | FEDEX P | BARCODE LABEL REQ CofC PER ECO 3 | 3/1 - TOP SIDE 2:30 3/1 - AOI 12:00 | 1T 35/703 | 2/23 - WILL CLEAR EOD 2/28 - KIT CLEAR; FB1 FB2 NO LONGER DNI | 47 | 940 |  | Lunar Energy, Inc. | 755 Ravendale Drive | Nountain View | CA
|  | 2023-03-06 | 115913-1ST (2/23) | NEW | 2 | L1 |  |  | 3/6 5D | FEDEX P | DEPANEL FAIR REQ XRAY & SAVE | 3/1 - BOT SIDE 12:30 3/1 - TOP SIDE 1:30 3/1 - AOI 3:30 | 1B 1T 65/256 | 2/23 - FABS DUE 2/27 2/27 - KIT CLEAR | 10 | 20 |  | Anderson Connectivity | 601 Atlantis Rd | Melbourne | FL
|  | 2023-03-06 | 115294 (2/27) | NEW | 50 | L2 |  |  | 3/6 5D | UPS BLU | X | 2/28 - BOT SIDE 12:30 3/1 - TOP SIDE 7:00 3/1 - AOI 12:00 | 1B 1T 80/201 | 2/24 - KIT CLEAR | 8 | 400 |  | Newark Electronics | 1901 10th St | Plano | TX
|  | 2023-03-06 | 115691 (2/7) | NEW | 49 |  |  |  | 2/24 2/22 10D | FEDEX GND | 2 WIRE JUMPERS REQ - SEE ECO | 2/7 - BACK | T/H ONLY | PIN ISSUE??? - CLEAR 2/23 | 50 | 2450 |  | Technical Marine Service, Inc. | 6040 N Cutter Cir | Portland | OR
|  | 2023-03-06 | 106348 (2/9) | RONC 101205 | 400 | L2 |  |  | 3/3H 10D | UPS 3DAY | CLASS 3 | 2/21 - BOT SIDE 6:00 2/22 - TOP SIDE 8:00 2/27 - AOI 9:00 | 1B 1T 22/45 | 2/10 - KIT CLEAR | 10 | 4000 | X | Coastal Designs, LLC | 22 Jordan Cove Rd | Waterford | CT
|  | 2023-03-03 | 116464 (2/28) | RONC 115328 | 4 | L3 |  |  | 3/3 3D | FEDEX P | *** 3 DAY TURN *** BOARDS REQ BAKING | 3/1 - TOP SIDE 7:00 3/1 - AOI 8:00 | 1T 1/2 | 2/28 - KIT CLEAR | 4 | 16 |  | Loft Orbital Inc. | 321 11th St | San Francisco | CA
|  | 2023-03-03 | 116136 (2/23) | NEW | 5 | L3 |  |  | 3/3 5D | UPS GND | CLASS 3 DEPANEL MECH ASSY & PRESS FIT REQ | 2/28 - BOT SIDE 8:30 2/28 - TOP SIDE 11:00 3/1 - AOI 7:00 | 1B 1T 53/484 | 2/23 - FABS DUE 2/24 2/24 - KIT CLEAR | 5 | 25 |  | Diversified Supply | 3901 Castle Hayne Rd | Castle Hayne | NC
|  | 2023-03-03 | 115908 (2/22) | NEW | 50 | L1 |  |  | 3/3 5D | FEDEX GND | DEPANEL | 2/28 - BOT SIDE 7:00 2/28 - TOP SIDE 2:30 3/1 - AOI 11:30 | 1B 1T 79/308 | 2/23 - #45 (U5) DUE 2/24 2/24 - KIT CLEAR | 2 | 100 |  | H3D, Inc. | 812 Avis Dr | Ann Arbor | MI
|  | 2023-03-03 | 115822 (2/22) | NEW | 7 | L3 |  |  | 3/3 5D | UPS GND | DEPANEL MECH ASSY REQ *NEED POP RIVET TOOL - ORDERED 3/2, DUE 3/3 | 2/27 - TOP 10:00 2/27 - AOI 11:30 | 1T 23/136 | 2/22 - SMT CLEAR 2/24 2/24 - KIT CLEAR | 71 | 497 |  | Michael Zarling Design | 12277 Apple Valley Rd #350 | Apple Valley | CA
|  | 2023-03-03 | 114906-2ND (2/17) | RONC 1ST ARTICLE | 1 | L1 |  |  | 2/28 5D | FEDEX P | FAIR REQUIRED DEPANEL DOUBLE CHECK P/N FOR "R44,45,50,51" SHOULD BE ERJ-PA2F5602X, 56K OHM 1%,1/4W PER ECO #2 "J3" SHOULD BE 12401610E4#2A PER ECO #3 | 2/21 - TOP SIDE 3:00 2/22 - AOI 12:00 | 1B 2T 80/183 | 1/19 - ALL BOT DONE 2/17 - COULD CLEAR 2/17 - KIT CLEAR | 11 | 11 |  | Diagraph | 1 Research Park Dr | Saint Charles | MO
|  | 2023-03-02 | 115651 (2/22) | NEW | 32 | L3 |  |  | 3/2 5D | FEDEX P | DEPANEL & SAND ***KEEP 1 DEPANELED FRAME ON FILE PER ECO #1 | 2/27 - BOT SIDE 11:30 2/28 - TOP SIDE 7:30 2/28 - AOI 12:30 | 1B 1T 58/332 | 2/22 - FABS DUE EOD 2/23 - KIT CLEAR | 0 | 0 | X | AimLock | 8022 Southpark Cir | Littleton | CO
|  | 2023-03-02 | 114305 (2/15) | RONC 108431 | 80 | L1-1 |  |  | 3/2H 10D | UPS 3DAY | QUALITY ALERT!!! - SEE ECO FOR HAND SOLDER | 2/24 - BOT SIDE 11:00 2/25 - TOP SIDE 7:30 2/25 - AOI 11:30 | 1B 2T 106/341 | 2/15 - KIT CLEAR | 11 | 880 | X | Coastal Designs, LLC | 22 Jordan Cove Rd | Waterford | CT
|  | 2023-03-02 | 115589 (2/6) | RONC 109853 | 300 | L3-1 |  |  | 3/2H 10D | FEDEX GND | SHIPPING - PACK CAREFULLY TO PREVENT DAMAGE | 2/21 - TOP SIDE 10:30 2/24 - AOI 11:30 | 2T 84/190 | 2/6 - SHORT #6 2/15 - KIT CLEAR | 8 | 2400 | X | Transparent Technologies | 5665 Airport Blvd | Boulder | CO
|  | 2023-03-02 | 114812-5 (12/22) PAR |  | 25 | *SHIP HOLD |  |  | 2/28 2/22 1/9H 10D | UPS RED | DEPANEL CLASS 3 SHIPPING - REMOVE ALL PICK & PLACE PADS (ECO #9) | 12/29 - BOT SIDE 8:30 2/8 - TOP SIDE 10:30 2/9 - AOI 2:30 NEED TO PLACE (REWORK) DNI PARTS ON 15 BOARDS | 1B 2T 92/554 | 12/22 - KIT CLEAR 12/27 - AA SHIPPING HOLD 12/28 - QTY 145 CLEAR FOR BOT SIDE 1/5 - INSTALL #26, 9, 77, 79 & 80 | 16 | 400 |  | Precision Graphics Inc | 21 County Line Rd | Somerville | NJ
|  | 2023-03-01 | 116084-1 (2/21) | NEW | 40 | L1 |  |  | 3/1 5D | FEDEX P | DEPANEL | 2/25 - BOT SIDE 11:30 2/25 - TOP SIDE 1:30 2/25 - AOI 3:30 | 1B 1T 10/22 | 2/21 - FABS DUE 2/23 2/22 - KIT CLEAR | 0 | 0 |  | Durbin Group | 10950 Pierson Dr | Fredericksburg | VA
|  | 2023-03-01 | 116311 (2/23) | NEW | 4 | SAT |  |  | 3/1 3D | FEDEX P | *** 3 DAY TURN *** | 2/27 - BOT SIDE 6:30 2/27 - TOP SIDE 7:30 2/27 - AOI 8:30 | 1B 1T 27/858 | 2/23 - FABS DUE 2/24 2/24 - KIT CLEAR | 5 | 20
|  | 2023-03-01 | 116156 (2/22) | NEW | 10 | L3 |  |  | 3/1 3D | FEDEX GND | *** 3 DAY TURN *** DEPANEL | 2/24 - BOT SIDE 11:30 2/24 - TOP SIDE 2:30 2/27 - AOI 6:00 | 1B 1T 95/266 | 2/22 - FABS DUE 2/24 2/24 - KIT CLEAR | 38 | 380 | X | Emporia | 7901 Shaffer Pkwy | Littleton | CO
|  | 2023-03-01 | 115909 (2/22) | NEW | 50 | L2 |  |  | 3/1 5D | FEDEX GND | DEPANEL | 2/27 - BOT SIDE 09:00 2/27 - TOP SIDE 11:00 2/28 - AOI 12:30 | 1B 2T 81/315 | 2/22 - KIT CLEAR | 9 | 450 | X | H3D, Inc. | 812 Avis Dr | Ann Arbor | MI
|  | 2023-03-01 | 113565-2 (12/30) BAL | ROWC 108218 | 2 | L1 |  |  | ??? 2/17 2/14 20D | UPS GND | DEPANEL | 1/4 - TOP SIDE 1:00 1/25 - BOT SIDE 3:00 2/3 - BOT SIDE 11:30 2/7 - AOI 9:30 | 2B 1T 25/127 | 12/30 - PARTIAL SHORT #10, #11, #14, #17 OK TO RUN FULL TOP & QTY 1290 BOT 1/4 - TOP SIDE FIRST | 4 | 5160 | X | ICC, Inc. | 230 Horizon Dr | Verona | WI
|  | 2023-03-01 | 103336-2 (1/12) BAL | ROWC 98649 | 7 | L1-4 |  |  | 2/27H 10D | #VALUE! |  | 1/13 - TOP SIDE 2:00 1/16 - BOT SIDE 11:00 2/17 - TOP SIDE 3:00 2/21 - AOI 3:00 | 2B 2T 70/230 | *2/16 - SHORT ITEM 54 BOT & 25 TOP "G1" DUE 1/13 1/16 - REQ G1 TO RUN | 2 | 14 | X | Scientific Research Corporation
|  | 2023-02-28 | 114906-2ND (2/17) | RONC 1ST ARTICLE | 49 | L1 |  |  | 2/28 5D | FEDEX P | FAIR REQUIRED DEPANEL DOUBLE CHECK P/N FOR "R44,45,50,51" SHOULD BE ERJ-PA2F5602X, 56K OHM 1%,1/4W PER ECO #2 "J3" SHOULD BE 12401610E4#2A PER ECO #3 | 2/21 - TOP SIDE 3:00 2/22 - AOI 12:00 | 1B 2T 80/183 | 1/19 - ALL BOT DONE 2/17 - COULD CLEAR 2/17 - KIT CLEAR | 11 | 539 |  | Diagraph | 1 Research Park Dr | Saint Charles | MO
|  | 2023-02-28 | 100610-4TH-1 (1/6) | RONC 3RD ARTICLE | 80 | L3/L2 |  |  | 2/28 2/25H 20D | #VALUE! | ***NEW LEAD SOLDER PROCESS FOR U1A-U1H - DO NOT WASH U1A-U1H - USE SAME PROCESS AS B100606*** | 1/10 - BOT SIDE 10:00 2/8 - TOP SIDE 10:30 2/14 - AOI 1:00 | 2B 3T 237/3848 | 1/6 - RUN BOT ONLY; RUN TOP AFTER B100606 1/13 - QTY 121 DONE 1/17 - BOT DONE 11:30 | 7 | 560 | X | University of Oklahoma | 3190 Monitor Ave Rm 0220 | Norman | OK
|  | 2023-02-28 | 113665-8 (10/17) BAL | RONC 113064 BAL | 50 | L3 |  |  | 2022-02-28 | FEDEX P | NO MOUSE BITE HOLES - GIVE TO TAD TO DEPANEL BAR CODE LABELS REQ | 12/5 - BOT SIDE 1:00 (SHORT ITEM 15 - DUE 12/7) - SMT OFF 12/7 12/15 - TOP SIDE 6:00 12/15 - AOI 10:30 | 1B 2T 62/444 | 10/17 - KIT CLEAR QTY 400 PARTIAL 12/9 - HOLD - QTY 58 SHORT ITEM 16 - ORDERED & DUE 12/12 12/15 - KIT CLEAR | 16 | 800 | X | Command Alkon, Inc. | 6750 Crosby Ct | Dublin | OH
|  | 2023-02-28 | 116017 (2/21) | NEW | 31 | L1-1 |  |  | 2/28 5D | UPS RED | X | 2/23 - TOP SIDE 8:30 2/23 - BOT SIDE 3:00 2/24 - AOI 11:00 | 1B 2T 110/897 | 2/21 - KIT CLEAR 2/22 - TOP SIDE 1ST | 43 | 1333 |  | DE Design Works | 641 Spirit Valley Central Dr | Chesterfield | MO
|  | 2023-02-27 | 103336-2 (1/12) PAR | ROWC 98649 | 144 | L1-4 |  |  | 2/27H 10D | #VALUE! | DEPANEL & SAND - NO SHARP EDGES ALOWED X-RAY REQ | 1/13 - TOP SIDE 2:00 1/16 - BOT SIDE 11:00 2/17 - TOP SIDE 3:00 2/21 - AOI 3:00 | 2B 2T 70/230 | *2/16 - SHORT ITEM 54 BOT & 25 TOP "G1" DUE 1/13 1/16 - REQ G1 TO RUN | 2 | 288 | X | Scientific Research Corporation
|  | 2023-02-27 | 115393 (2/8) | NEW | 30 | L1-1 |  |  | 2/27H 10D | UPS GND | DEPANEL BARCODE LABELS REQ | 2/22 - TOP SIDE 12:00 2/23 - AOI 8:30 | 1T 41/110 | 2/8 - SMT CLEAR 2/10 - KIT CLEAR | 34 | 1020 | X | Mide Technology Corp | 475 Wildwood Ave | Woburn | MA
|  | 2023-02-24 | 115574 (1/31) | RONC 101523 | 450 | L2 |  |  | 2/24H 20D | FEDEX P | CLASS 3 DEPANEL | 2/23 - BOT SIDE 6:00 2/23 - TOP SIDE 11:30 2/23 - AOI 5:00 PM | 2B 2T 60/188 | 1/26 - KIT CLEAR | 0 | 0 |  | Coastal Designs, LLC | 22 Jordan Cove Rd | Waterford | CT
|  | 2023-02-24 | 115362 (2/1) | NEW | 50 | L1 |  |  | 2/24H 5D | FEDEX P | DEPANEL & SAND TRIMMED LEADS NOT TO EXCEED 0.1" PER ECO 4 | 2/2 - TOP SIDE 8:30 2/2 - BOT SIDE 1:30 2/3 - AOI 11:30 | 1B 2T 113/283 | 2/1 - SHORT #126 (SKIPPABLE) 2/15 - #126 DUE 2/16 2/16 - KIT CLEAR | 17 | 850 | X | Spectro Inc. | 1 Executive Dr | Chelmsford | MA
|  | 2023-02-24 | 114820-1ST (1/17) | NEW | 2 | L1 |  |  | 3/2 5D | UPS GND | DEPANEL & SAND | 1/24 - TOP SIDE 10:30 1/24 - AOI 12:30 | 1T 26/56 | 1/17 - AWT PART CONF 15 2/23 - KIT CLEAR | 24 | 48 |  | Beckman Coulter | 5355 W 76th St Bldg 87 Dock 39 | Indianapolis | IN
|  | 2023-02-23 | 115434 (2/16) | NEW | 3 | L3 |  |  | 2/27H 3D | UPS GND | *** 3 DAY TURN *** CLASS 3 DEPANEL *"A1" NEED TO BE HAND SOLDERED PER ECO #7 PRESS FIT REQ | 2/20 - BOT SIDE 6:00 2/21 - TOP SIDE 8:00 2/21 - AOI 10:30 | 1B 1T 72/234 | 2/16 - KIT CLEAR; STRIP LENGTHS TOO SHORT | 12 | 36 |  | GE Hitachi Nuclear Energy | 3901 Castle Hayne Rd | Castle Hayne | NC
|  | 2023-02-23 | 104338 (2/9) | NEW | 47 | L1-2 |  |  | 2/24H 10D | UPS 3DAY | CLASS 3 | 2/17 - BOT SIDE 9:30 2/17 - TOP SIDE 10:30 2/17 - AOI 11:30 | 1B 1T 11/23 | 2/9 - KIT CLEAR | 18 | 846 |  | Coastal Designs, LLC | 22 Jordan Cove Rd | Waterford | CT
|  | 2023-02-23 | 115493-2BAL (2/14) | RONC 114521 | 80 | L2/L3 |  |  | 2/23H 5D | UPS RED | DEPANEL "QUALITY ALERT!!!" - ECO 3 | 2/17 - BOT SIDE 5:00 2/17 - TOP SIDE 9:30 2/17 - AOI 12:00 | 1B 1T 57/114 | 2/14 - SMT CLEAR 2/15 - KIT CLEAR | 20 | 1600 | X | Alliance Technology, LLC. | 600 N Dekora Woods Blvd | Saukville | WI
|  | 2023-02-22 | 113151-3 (12/12) BAL | ROWC 99149 | 1 | L1 |  |  | 2/3 12/28 9D | FEDEX P | DEPANEL | 12/14 - BOT SIDE 10:30 12/14 - TOP SIDE 1:00 12/14 - AOI 3:00 12/27 - H/L | 2B 2T 37/350 | 12/12 - SMT CLLEAR ONLY 12/14 - RECV PARTIAL 54/120 PCS "J2" KIT CLEAR 12/15 12/27 - QTY 54 OK TO SOLDER; 74 AWT PART #21 REPLACEMENT 12/28 - SHIPPED 54 1/20 - #21 DUE 1/23 1/23 - KIT CLEAR | 6 | 6 |  | Design Catapult, Inc. | 17361 NEWHOPE ST | Fountain Valley | CA
|  | 2023-02-22 | 115435 (2/8) | RONC 110659 | 50 | L1-3 |  |  | 2/23H 10D | FEDEX P | CLASS 3 DEPANEL ***SEE ECO 4 FOR PREVIOUS QUALITY ISSUES | 2/17 - STENCIL MISSING ORDERED NEW ONE 11:00 2/17 - BOT SIDE 1:30 2/20 - TOP SIDE 8:00 2/21 - AOI 9:00 | 1B 1T 40/54 | 2/8 - KIT CLEAR | 0 | 0 | X | Southwest Research Institute | 9503 W COMMERCE ST | San Antonio | TX
|  | 2023-02-21 | 114215-2ND (2/13) PAR | RONC 1ST ARTICLE | 22 | L1 |  |  | 2/21H 5D | FEDEX P | FAIR REQUIRED | 2/15 - TOP SIDE 10:30 2/16 - BOT SIDE 12:00 2/17 - AOI 9:30 | 2B 1T 122/1304 | 2/13 - KIT CLEAR | 0 | 0 |  | Phoenix Contact, Inc. | 586 Fulling Mill Rd | Middletown | PA
|  | 2023-02-21 | 114506 (2/9) | NEW | 10 | L2 |  |  | 2/21H 7D | FEDEX GND | CoC REQ | 2/15 - BOT SIDE 10:30 2/16 - TOP SIDE 10:30 2/17 - AOI 9:00 | 2B 2T 126/643 | 2/9 - KIT CLEAR | 1 | 10 |  | 2Alarm.com | 8281 Greensboro Dr | Tysons | VA
|  | 2023-02-21 | 115493-1EXP (2/14) | RONC 114521 | 40 | L2/L3 |  |  | 2/21 2D | UPS RED | *PAID EXPEDITE* DEPANEL *NEED GOOD SHIPPING PICS* "QUALITY ALERT!!!" - ECO 3 | 2/17 - BOT SIDE 5:00 2/17 - TOP SIDE 9:30 2/17 - AOI 12:00 | 1B 1T 57/114 | 2/14 - SMT CLEAR 2/15 - KIT CLEAR | 20 | 800 | X | Alliance Technology, LLC. | 600 N Dekora Woods Blvd | Saukville | WI
|  | 2023-02-21 | 115881 (2/9) | NEW | 4 | L3 |  |  | 2/21H 5D | UPS RED | XRAY 1ST BOARD "ONLY" AND IDENTIFY WITH LABEL - DO NOT XRAY BALANCE QTY 3 - SEE ECO DEPANEL | 2/15 - BOT SIDE 6:00 2/15 - TOP SIDE 10:30 2/16 - AOI 8:00 | 2B 2T 137/990 | 2/9 - FABS DUE 2/13 2/13 - KIT CLEAR | 15 | 60 | X | Instron | 825 UNIVERSITY AVE | Norwood | MA
|  | 2023-02-21 | 100605-6 (4TH ARTICLE) (1/17) | RONC 3RD ARTICLE | 221 | L3 |  |  | 2/21 2/15 20D | FEDEX P | CLASS 3 BOARDS REQ BAKING XRAY & IMAGES REQ | 1/19 - BOT SIDE 2:30 1/31 - TOP SIDE 10:30 2/7 - AOI 4:00 | 2B 2T 205/2894 | 1/24 - QTY 73 DONE 10:30 1/26 - QTY 186 DONE 1:30 1/27 - BOT DONE 2/3 - QTY 100 DONE 12:00 | 4 | 884 |  | University of Oklahoma | 3190 Monitor Ave Rm 0220 | Norman | OK
|  | 2023-02-17 | 116122-RWK (2/14) | PAID RWK | 37/50 |  |  |  | 2/17 1D | FEDEX SAT | *** 1 DAY TURN *** DEPANEL XRAY & SAVE REMOVE PART | FSU | 1T 1/1 | 2/14 - FABS DUE 2/15 | 1 | 37 |  | Tomahawk Robotics, LLC | 2326 Irwin St | Melbourne | FL
|  | 2023-02-17 | 116121-RWK (2/14) | PAID RWK | 40/50 |  |  |  | 2/17 1D | FEDEX SAT | *** 1 DAY TURN *** DEPANEL XRAY & SAVE REMOVE PART | 2/14 - BACK | 1T 1/1 | 2/14 - FABS DUE 2/15 | 1 | 40 |  | Tomahawk Robotics, LLC | 2326 Irwin St | Melbourne | FL
|  | 2023-02-17 | 116121 (2/14) | NEW | 50 | L3 |  |  | 2/17 1D | FEDEX SAT | *** 1 DAY TURN *** DEPANEL XRAY & SAVE | 2/16 - TOP SIDE 8:00 2/16 - AOI 9:00 | 1T 1/1 | 2/14 - FABS DUE 2/15 2/15 - KIT CLEAR | 1 | 50 |  | Tomahawk Robotics, LLC | 2326 Irwin St | Melbourne | FL
|  | 2023-02-17 | 116122 (2/14) | NEW | 50 | L3 |  |  | 2/17 1D | FEDEX SAT | *** 1 DAY TURN *** DEPANEL XRAY & SAVE | 2/16 - TOP SIDE 8:00 2/16 - AOI 9:00 | 1T 1/1 | 2/14 - FABS DUE 2/15 2/15 - KIT CLEAR | 1 | 50 |  | Tomahawk Robotics, LLC | 2326 Irwin St | Melbourne | FL
|  | 2023-02-17 | 115937 (2/11) | NEW | 50 | L2 |  |  | 2/17 5D | FEDEX P | DEPANEL | 2/11 - BOT SIDE 12:30 2/13 - TOP SIDE 1:00 2/14 - AOI 12:00 | 1B 1T 104/405 | 2/10 - KIT CLEAR | 4 | 200 | X | Durbin Group | 10950 Pierson Dr | Fredericksburg | VA
|  | 2023-02-17 | 115735 (2/8) | NEW | 250 | L1 |  |  | 2/17 5D | FEDEX P | DEPANEL | 2/13 - BOT SIDE 10:30 2/13 - TOP SIDE 2:30 2/14 - AOI 3:00 | 1B 1T 38/117 | 2/8 - FABS DUE 2/9 2/10 - KIT CLEAR | 4 | 1000 | X | Priority Designs, Inc. | 100 S Hamilton Rd | Columbus | OH
|  | 2023-02-17 | 113565-2 (12/30) PAR | ROWC 108218 | 1008 | L1 |  |  | 2/17 2/14 20D | UPS GND | DEPANEL | 1/4 - TOP SIDE 1:00 1/25 - BOT SIDE 3:00 2/3 - BOT SIDE 11:30 2/7 - AOI 9:30 | 2B 1T 25/127 | 12/30 - PARTIAL SHORT #10, #11, #14, #17 OK TO RUN FULL TOP & QTY 1290 BOT 1/4 - TOP SIDE FIRST | 4 | 5160 | X | ICC, Inc. | 230 Horizon Dr | Verona | WI
|  | 2023-02-17 | 109882-2ND (1/23) BAL | ROWC 1ST ARTICLE | 70 | L2 |  |  | 2/17 2/3* 5D | FEDEX P | *ALL HAND SOLDERED RF CONNECTORS HAVE MAX TEMP 165C 100% XRAY REQ & SAVE IMAGES MECH ASSY REQ | 1/25 - TOP SIDE 11:00 2/2 - AOI 2:00 2/11 - BOT SIDE 7:30 2/11 - TOP SIDE 9:00 2/11 - AOI 12:00 | 2T 95/650 | 1/23 - FABS DUE 1/24 - 1/26 1/25 - FABS BAL DUE 2/2 2/10 - KIT CLEAR | 82 | 5740 | X | CACI | 45150 Business Ct Ste 200 | Sterling | VA
|  | 2023-02-16 | 114812-4 (12/22) PAR |  | 5 | L2/L3/L1 |  |  | 2/22 1/9H 10D | UPS RED | DEPANEL CLASS 3 SHIPPING - REMOVE ALL PICK & PLACE PADS (ECO #9) | 12/29 - BOT SIDE 8:30 2/8 - TOP SIDE 10:30 2/9 - AOI 2:30 NEED TO PLACE (REWORK) DNI PARTS ON 15 BOARDS | 1B 2T 92/554 | 12/22 - KIT CLEAR 12/27 - AA SHIPPING HOLD 12/28 - QTY 145 CLEAR FOR BOT SIDE 1/5 - INSTALL #26, 9, 77, 79 & 80 | 16 | 80 |  | Precision Graphics Inc | 21 County Line Rd | Somerville | NJ
|  | 2023-02-16 | 115983 (2/13) | NEW | 10 | L2 |  |  | 2/17 3D | FEDEX P | ** 3 DAY TURN ** | 2/15 - BOT SIDE 6:00 2/15 - TOP SIDE 8:00 2/15 - AOI 10:30 | 1B 1T 59/234 | 2/13 - SMT CLEAR; DNI #31 2/14 - KIT CLEAR | 75 | 750 |  | Rheem Manufacturing Company | 9855 Crosspoint Blvd Ste 114 | Indianapolis | IN
|  | 2023-02-16 | 115046 (1/27) | NEW | 60 | L1 |  |  | 2/16 9D | FEDEX GND | DEPANEL | 2/10 - BOT SIDE 12:30 2/15 - TOP SIDE 7:00 2/15 - AOI 10:30 | 1B 1T 61/304 | 1/27 - FABS DUE 1/30 2/3 - KIT CLEAR 2/13 - AWT TOP FIXTURE | 1 | 60 | X | Allocortech, Inc. | 440 N Commerce Ave | Waynesboro | VA
|  | 2023-02-14 | 113997 (2/3) | RONC 108946 | 260 | L1 |  |  | 2/17 10D | FEDEX P | DEPANEL & SAND | 2/9 - TOP SIDE 2:30 2/10 - AOI 9:00 | 1T 14/19 | 2/3 - KIT CLEAR | 2 | 520 |  | Scientific Research Corporation | 103 Quality Cir Nw Ste 220 | Huntsville | AL
|  | 2023-02-14 | 111418 (1/31) | ROWC 104121 | 6 | L1 |  |  | 2/16 10D | FEDEX GND | DEPANEL | 2/9 - BOT SIDE 9:00 2/10 - TOP SIDE 11:30 2/10 - AOI 12:30 | 1B 1T 68/578 | 2/2 - KIT CLEAR | 31 | 186 |  | Denmar Technical Services, Inc. | 741 Radio Dr | Lewis Center | OH
|  | 2023-02-14 | 115375 (2/7) | RONC 108466 | 400 | L2 |  |  | 2/14 5D | FEDEX P | DEPANEL & SAND | 2/10 - TOP SIDE 9:30 2/11 - AOI 7:30 | 1T 3/7 | 2/7 - KIT CLEAR | 0 | 0 | X | Aila Technologies, Inc. | 11 HURON DR | Natick | MA
|  | 2023-02-13 | 115530 (2/1) | NEW | 125 | L1 |  |  | 2/14 3D | FEDEX P | ** 3 DAY TURN ** DEPANEL BAR CODE LABEL REQ | 2/1 - TOP SIDE 3:00 2/2 - AOI 8:30 | 1T 3/5 | 2/1 - SHORT THT ITMS 2/9 - KIT CLEAR | 2 | 250 |  | Command Alkon, Inc. | 6750 Crosby Ct | Dublin | OH
|  | 2023-02-13 | 115874 (2/9) | RONC 114821 | 200 | L2 |  |  | 2/14 3D | FEDEX P | *** 3 DAY TURN *** DEPANEL BARCODE LABEL REQ | 2/9 - TOP SIDE 10:00 2/10 - AOI 7:00 | 1T 15/34 | 2/9 - KIT CLEAR | 4 | 800 |  | Command Alkon, Inc. | 6750 Crosby Ct | Dublin | OH
|  | 2023-02-13 | 107474 (1/30) | NEW | 20 | L3 |  |  | 2/13 10D | FEDEX P | CLASS 3 DEPANEL RTV REQ @ C201 | 2/8 - BOT SIDE 6:00 2/8 - TOP SIDE 8:00 2/8 - AOI 10:30 | 1B 1T 7/33 | 1/30 - KIT CLEAR | 5 | 100 |  | NO NAME ON PO | 216 N Main St | Freeport | NY
|  | 2023-02-13 | 114812-3 (12/22) PAR |  | 15 | L2/L3 |  |  | 2/13 5D | UPS RED | DEPANEL CLASS 3 SHIPPING - REMOVE ALL PICK & PLACE PADS (ECO #9) | 12/29 - BOT SIDE 8:30 12/30 - TOP SIDE 2:30 1/3 - AOI 1:00 1/4 - H/L 1/3 - NEED TO PLACE (REWORK) DNI PARTS | 1B 2T 92/554 | 12/22 - KIT CLEAR 12/27 - AA SHIPPING HOLD 12/28 - QTY 145 CLEAR FOR BOT SIDE | 16 | 560 |  | Precision Graphics Inc | 21 County Line Rd | Somerville | NJ
|  | 2023-02-10 | 115159 (1/27) | NEW | 50 | L1 |  |  | 2/10 10D | UPS GND | DEPANEL"U15-17" TIGHT FIT, PLACE AS IS | 2/7 - BOT SIDE 9:30 2/7 - TOP SIDE 2:00 2/8 - AOI 10:30 | 1B 1T 57/196 | 1/27 - KIT CLEAR; BTD 34 (SMT); DNI 37 (THT) | 19 | 950 | X | S & A Systems | 992 Sids Rd | Rockwall | TX
|  | 2023-02-10 | 115476-1ST (2/3) | NEW | 10 | L2 |  |  | 2/10 5D | FEDEX P | DEPANEL | 2/8 - BOT SIDE 9:00 2/8 - TOP SIDE 10:30 2/8 - AOI 12:00 | 1B 1T 68/200 | 2/3 - KIT CLEAR | 3 | 30 |  | CACI | 45150 Business Ct Ste 200 | Sterling | VA
|  | 2023-02-09 | 115487 (1/24) | PAID RWK 110198 | 350 |  |  |  | 2/15 15D | FEDEX GND | REMOVE J1 FROM TOP SIDE & REPOSITION TO BOT SIDE | 1/25 - BACK | - |  | 1 | 350 |  | WalkMed, LLC | 14190 E Jewell Ave | Aurora | CO
|  | 2023-02-09 | 115497-2 (1/31) BAL | RONC 108347 | 56 |  |  |  | 2/14 5D | UPS GND | X | 1/31 - BACK | THT ONLY | 1/31 - 20 FABS DUE 2/1 & 55 FABS DUE 2/6 2/7 - KIT CLEAR |  | 0 |  | Churchill Navigation dba Shotover Systems Inc | 5660 Airport Blvd Ste 101 | Boulder | CO
|  | 2023-02-09 | 115600 (2/2) | NEW | 2 | L2 |  |  | 2/9 3D | UPS RED | ** 3 DAY TURN ** CLASS 3 *Sn63Pb37 SOLDER PASTE REQUIRED - ECO 2 | 2/6 - BOT SIDE 12:30 2/6 - TOP SIDE 1:30 2/7 - AOI 7:30 | 1B 2T 104/838 | 2/2 - FABS DUE 2/3 & NO ETA ON KIT 2/6 - KIT CLEAR | 6 | 12 |  | Renmark-Pacific Corporation | 2675 Skypark Dr Ste 103 | Torrance | CA
|  | 2023-02-08 | 114958 (1/18) | ROWC 104911 | 350 | L1 |  |  | 2/8 15D | FEDEX GND | DEPANEL *NO LABELS/MARKINGS OVER AREA SHOWN ON ECO 4 | 1/23 - TOP SIDE 10:00 1/24 - AOI 10:30 | 2T 42/107 | 1/18 - KIT CLEAR | 5 | 1750 | X | Oregon State University | 110 Sw Park Ter | Corvallis | OR
|  | 2023-02-08 | 114307-2ND (1/25) PAR | RONC 1ST ARTICL | 22 | L2 |  |  | 2/8 10D | FEDEX P | **DO NOT DEPANEL** | 2/2 - BOT SIDE 2:00 2/7 - TOP SIDE 7:30 2/7 - AOI 11:30 | 1B 1T 43/1101 | 1/25 - KIT CLEAR 2/6 - BOT SIDE DONE | 0 | 0 |  | Phoenix Contact, Inc. | 586 Fulling Mill Rd | Middletown | PA
|  | 2023-02-07 | 114911 (1/24) | RONC 107257 | 30 | L1 |  |  | 2/10 10D | FEDEX GND | DEPANEL | 1/31 - TOP SIDE 1:00 2/1 - AOI 11:30 | 2T 65/393 | 1/24 - FABS DUE 1/25 1/25 - FABS DUE 1/30 1/27 - KIT CLEAR | 10 | 300 | X | AKV, Inc. | 777 Aviation Dr | Camarillo | CA
|  | 2023-02-07 | 115522 (1/27) | NEW | 20 | L1 |  |  | 2/7 5D | FEDEX P | DEPANEL X-RAY & SAVE IMAGES (ECO #3) *SHIPPING - LEADS CANNOT PUNCTURE ESD BAGS **SHIPPING - CARTON DIVIDERS REQUIRED? - ECO 6 | 1/31 - TOP SIDE 9:00 1/31 - AOI 1:00 | 2T 71/461 | 1/27 - SHORT 4 FABS ETA 1/31 1/31 - KIT CLEAR | 26 | 520 |  | D&K Engineering | 11055 Technology Pl | San Diego | CA
|  | 2023-02-06 | 115497-1PAR (1/31) | RONC 108347 | 19 |  |  |  | 2/8 5D | UPS GND |  | 1/31 - BACK |  | 1/31 - 20 FABS DUE 2/1 & 55 FABS DUE 2/6 2/1 - CLEAR FOR 19 |  | 0 |  | Churchill Navigation dba Shotover Systems Inc | 5660 Airport Blvd Ste 101 | Boulder | CO
|  | 2023-02-06 | 114887 (1/31) | NEW | 3 | L1 |  |  | 2/7 5D | FEDEX P | DEPANEL | 2/1 - BOT SIDE 11:30 2/1 - TOP SIDE 1:30 2/1 - AOI 3:00 | 1B 1T 57/511 | 1/31 - KIT CLEAR | 52 | 156 |  | Harsco Rail | 2401 Edmund Hwy | West Columbia | SC
|  | 2023-02-03 | 113908 (1/27) | NEW | 5 | L1 |  |  | 2/6 5D | FEDEX P | DEPANEL | 1/30 - BOT SIDE 8:30 1/30 - TOP SIDE 2:30 1/31 - AOI 10:30 | 2B 2T 185/846 | 1/27 - DNI 74 & SHORT 82 1/30 - KIT CLEAR | 5 | 25 |  | Tomahawk Robotics, LLC | 1333 N Harbor City Blvd | Melbourne | FL
|  | 2023-02-03 | 113151-2 (12/12) BAL | ROWC 99149 | 65 | L1 |  |  | 2/3 12/28 9D | FEDEX P | DEPANEL | 12/14 - BOT SIDE 10:30 12/14 - TOP SIDE 1:00 12/14 - AOI 3:00 12/27 - H/L | 2B 2T 37/350 | 12/12 - SMT CLLEAR ONLY 12/14 - RECV PARTIAL 54/120 PCS "J2" KIT CLEAR 12/15 12/27 - QTY 54 OK TO SOLDER; 74 AWT PART #21 REPLACEMENT 12/28 - SHIPPED 54 1/20 - #21 DUE 1/23 1/23 - KIT CLEAR | 6 | 390 |  | Design Catapult, Inc. | 17361 NEWHOPE ST | Fountain Valley | CA
|  | 2023-02-03 | 115199 (1/20) | PAID RWK 112847 | 40 |  |  |  | 2/3 10D | FEDEX P | REMOVE D1-D4 & HS1-HS4 THEN ASSEMBLE W/THERMAL PASTE & REINSTALL |  |  | 1/20 - KIT CLEAR |  | 0 |  | Switched Source LLC | 200 W Adams St | Chicago | IL
|  | 2023-02-02 | 115422 (1/25) | NEW | 14 | L1 |  |  | 2/2 5D | FEDEX P | DEPANEL CoFC & PACK SLIP PER ECO 6 &7 | 1/27 - BOT SIDE 9:30 1/27 - TOP SIDE 3:00 1/30 - AOI 2:00 | 2B 2T 202/1443 | 1/25 - FABS DUE 1/27 & C76 DUE 1/26 1/26 - KIT CLEAR | 12 | 168 |  | Reliable Robotics | 950 N Rengstorff Ave | Mountain View | CA
|  | 2023-02-01 | 115380 (1/23) BAL | RONC 112985 | 10 | L1 |  |  | 2/8 10D | UPS GND | x | 1/30 - TOP SIDE 2:00 1/31 - AOI 8:00 | 1T 5/26 | 1/23 - PCBS DUE 1/25 OR SOONER 1/25 - KIT CLEAR | 0 | 0 |  | HII Unmanned Systems, Inc | 3 HENRY DR | Pocasset | MA
|  | 2023-02-01 | 114124-2ND (1/26) PAR | RONC 1ST ARTICLE | 22 | L2 |  |  | 2/1 3D | FEDEX P | ** 3 DAY TURN ** DEPANEL BOARDS REQ 48 HRS BAKING PLEASE DOUBLE CHK BEFORE SHIPPING NOTE: 1C906,1006,1106,1206,306,1406" ARE NOW ROTATED 180 DEG | 1/27 - BOT SIDE 6:00 1/28 - TOP SIDE 7:00 1/28 - AOI 2:30 | 1B 1T 101/1331 | 1/26 - KIT CLEAR | 0 | 0 | X | Phoenix Contact, Inc. | 586 Fulling Mill Rd | Middletown | PA
|  | 2023-01-31 | 114812-2 (12/16) |  | 20 | L2/L3 |  |  | ???* 1/4 12/28H 5D | UPS RED | DEPANEL CLASS 3 SHIPPING - REMOVE ALL PICK & PLACE PADS (ECO #9) 12/3 - NEED TO ADD DNI PARTS (PAID REWORK) | 12/21 - BOT SIDE 7:30 12/21 - TOP SIDE 11:30 12/22 - AOI 11:00 12/30 - SHIPPING | 1B 2T 92/554 | 12/16 - WILL CLEAR SOON - SHORT ITEMS 49 & 102 12/19 - ONLY SHORT ITEM 102 (6 PER - COULD SKIP IF NEEDED) 12/27 - AA SHIPPING HOLD | 16 | 320 |  | Precision Graphics Inc | 21 County Line Rd | Somerville | NJ
|  | 2023-01-31 | 100606-7 (4TH ARTICLE) (7/15) | RONC 3RD ARTICLE | 79 | L2B / L3T |  |  | 1/31 20D | #VALUE! | *G5A-H & G2A-H NEW PROCESS - NEED QA INSP 100% - NO SOLDER ALLOWED ON COIL **J1A-H NO EXCESS SOLDER ALLOWED ***THIS QTY 13 WILL USE NEW G1A-H (WHITE) | 1/5 - BOT SIDE 9:30 1/10 - BOT DONE 8:30 1/17 - TOP SIDE 1:00 1/18 - QTY 25 DONE 1/19 - AOI 2:30 | 2B 3T 238/3746 | 1/3 - RUN BOT ONLY; RUN TOP AFTER B100610 BOT HAS RUN 1/10 - BOT SIDE DONE | 8 | 104 | X | University of Oklahoma | 3190 Monitor Ave Rm 0220 | Norman | OK
|  | 2023-01-31 | 113565-1 (12/30) | ROWC 108218 | 1290 | L1 |  |  | 1/31 1/25 20D | UPS GND | DEPANEL | ***NEED TO START SMT RIGHT AWAY 1/4 - TOP SIDE 1:00 1/6 - BOT SIDE 3:30 1/11 - AOI 3:00 1/18 - H/L | 2B 1T 25/127 | 12/30 - PARTIAL SHORT #10, #11, #14, #17 OK TO RUN FULL TOP & QTY 1290 BOT 1/4 - TOP SIDE FIRST | 4 | 5160 | X | ICC, Inc. | 230 Horizon Dr | Verona | WI
|  | 2023-01-30 | 114813-2BAL (12/21) |  | 145 | L1 / SHIP HOLD |  |  | ???* 1/6H 10D | UPS RED | DEPANEL USE BLACK SHARPIE FOR REVISION "E" SHIPPING - REMOVE ALL PICK & PLACE PADS (ECO #9) ***SHIP HOLD - CONTINUE PRODUCTION BUT DO NOT SHIP | 12/21 - BOT SIDE 2:00 12/23 - TOP SIDE 9:30 12/29 - AOI 1:00 1/9 - SHIPPING | 2B 2T 144/1117 | 12/21 - PARTIAL CLEAR 12/22 - SHORT 3 FABS 12/23 - KIT CLEAR (142 TOP & BOT RAN FIRST) 12/27 - AA SHIPPING HOLD | 6 | 600 | X | Precision Graphics Inc | 21 County Line Rd | Somerville | NJ
|  | 2023-01-30 | 115298 (1/23) | NEW | 200 | L1 |  |  | 1/31 5D | FEDEX P | DEPANEL | 1/24 - BOT SIDE 12:30 1/25 - TOP SIDE 8:00 1/25 - AOI 3:00 | 1B 1T 39/45 | 1/23 - WILL CLEAR TODAY 1/24 - KIT CLEAR | 10 | 2000 |  | HunterLab | 11491 Sunset Hills Rd | Reston | VA
|  | 2023-01-30 | 113665-7 (10/17) | RONC 113064 | 100 | L3 |  |  | 1/31 2/8 | FEDEX P | NO MOUSE BITE HOLES - GIVE TO TAD TO DEPANEL BAR CODE LABELS REQ | 12/5 - BOT SIDE 1:00 (SHORT ITEM 15 - DUE 12/7) - SMT OFF 12/7 12/15 - TOP SIDE 6:00 12/15 - AOI 10:30 | 1B 2T 62/444 | 10/17 - KIT CLEAR QTY 400 PARTIAL 12/9 - HOLD - QTY 58 SHORT ITEM 16 - ORDERED & DUE 12/12 12/15 - KIT CLEAR | 16 | 1600 | X | Command Alkon, Inc. | 6750 Crosby Ct | Dublin | OH
|  | 2023-01-30 | 115673 (1/25) | NEW | 4 | L1 |  |  | 1/30 3D | FEDEX P | ** 3 DAY TURN ** PACKING REQ PER ECO | 1/26 - BOT SIDE 12:30 1/27 - TOP SIDE 8:00 1/27 - AOI 9:30 | 1B 1T 32/753 | 1/25 - KIT CLEAR | 27 | 108 |  | dB Systems, Inc. | 2501 S Antenna Avenue | Hurricane | UT
|  | 2023-01-27 | 114955 (1/16) | NEW | 32 | L1 |  |  | 1/31 10D | FEDEX GND | DEPANEL & SAND SPECIAL LABEL REQ PER ECO | 1/20 - BOT SIDE 11:00 1/20 - TOP SIDE 2:00 1/23 - AOI 10:00 | 1B 1T 65/307 | 1/16 - PCB DUE 1/17 1/17 - KIT CLEAR | 5 | 160 |  | AimLock | 8022 Southpark Cir | Littleton | CO
|  | 2023-01-26 | 115173 (1/16) | NEW | 10 | L1 |  |  | 1/30 10D | FEDEX GND | DEPANEL "J4" TABS NEED HAND SOLDER PER ECO 3 | 1/18 - BOT SIDE 10:30 1/19 - TOP SIDE 8:00 1/19 - AOI 12:30 | 1B 2T 106/1204 | 1/16 - KIT CLEAR | 23 | 230 |  | Southwest Research Institute | 9503 W COMMERCE ST | San Antonio | TX
|  | 2023-01-26 | 115289 (1/20) | NEW | 2 | L2 |  |  | 1/30 5D | FEDEX P | X | 1/24 - TOP SIDE 1:00 1/25 - AOI 8:00 | 1T 46/560 | 1/20 - PARTS 5,14,17 & 20 DUE 1/23 1/23 - KIT CLEAR | 44 | 88 |  | Forza Ametek | 2947 Bradley St Ste 130 | Pasadena | CA
|  | 2023-01-25 | 114922 (1/19) | NEW | 3 | L2 |  | 2023-01-11 | 1/25 3D | FEDEX GND | ** 3 DAY TURN ** "T564-571" (ETC1-1-13TR) HAS 5 LEADS BUT FOOTPRINT HAS 6 PADS - PLACE AS IS | 1/20 - BOT SIDE 8:00 1/20 - TOP 11:00 1/23 - AOI 10:00 | 2B 2T 149/1288 | 1/19 - KIT WILL CLEAR 1/23 | 11 | 33 |  | DMEA | 4234 54th St | McClellan Park | CA
|  | 2023-01-25 | 114906-1ST (1/17) | NEW | 50 | L1 |  |  | 1/25 5D | FEDEX P | FAIR REQUIRED DEPANEL DOUBLE CHECK P/N FOR "R44,45,50,51" SHOULD BE ERJ-PA2F5602X, 56K OHM 1%,1/4W PER ECO #2 "J3" SHOULD BE 12401610E4#2A POER ECO #3 | 1/19 - BOT SIDE 12:30 1/19 - TOP SIDE 2:00 1/20 - AOI 11:00 | 1B 2T 80/183 | 1/17 - AWT PART SUB CONF: 21, 23, 24, 37, and 38 (SUB APPROVED) 1/18 - 24 & 33 SHARED (ONLY ENOUGH FOR QTY 50 FA) 1/18 - KIT CLEAR 1/19 - ALL BOT DONE | 11 | 550 | X | Diagraph | 1 Research Park Dr | Saint Charles | MO
|  | 2023-01-24 | 115423 (1/20) | NEW | 140 | L2 |  |  | 1/25 3D | FEDEX INTER | ** 3 DAY TURN ** DEPANEL | 1/23 - TOP SIDE 10:00 1/23 - AOI 2:30 | 1T 5/8 | 1/20 - KIT CLEAR | 3 | 420 |  | ExcelSense Technologies Corp | 3206-1009 Expo Blvd | Vancouver | BC
|  | 2023-01-24 | 114874 (12/30) | ROWC 107127 | 50 | L2 |  |  | 1/24 15D | UPS RED | DEPANEL IF BOARDS WASHED, PLEASE BAKE | 1/5 - BOT SIDE 6:00 1/5 - TOP SIDE 8:00 1/5 - AOI 11:30 1/18 - THT | 1B 1T 47/97 | 12/30 - FABS DUE 1/6 1/3 - KIT CLEAR 1/20 - IC ARRIVE 1/23 FOR 4 BOARD | 16 | 800 |  | Aeroprobe Corporation | 200 Technology Dr | Christiansburg | VA
|  | 2023-01-23 | 110201 (12/19) | NEW | 200 | L2 |  |  | 1/23 5D | FEDEX GND | DEPANEL TRIM LEAD REQ PER ECO | 1/18 - TOP SIDE 10:30 1/18 - AOI 1:30 1/20 - AOI 1/23 - THT | 1T 28/48 | 12/19 - MAY CLEAR TODAY 12/20 - FILES MAY BE BAD 1/16 - KIT CLEAR & AWT PART #5 CONF 1/20 - S2 DNI | 13 | 2600 |  | WalkMed, LLC | 14190 E Jewell Ave Ste 10 | Aurora | CO
|  | 2023-01-23 | 110685 (1/5) | NEW | 50 | L2 |  |  | 1/23 10D | UPS RED | X | 1/13 - BOT SIDE 10:00 1/16 - TOP SIDE 10:30 1/17 - AOI 1:00 1/20 - THT | 2B 2T 134/835 | 1/5 - MAY CLEAR 1/9 1/9 - KIT CLEAR 1/19 - #74 (L13) SHORT 1/20 - #74 HERE | 12 | 600 | X | Holland LP | 750 Central Ave | University Park | IL
|  | 2023-01-20 | 114123-2ND PAR (1/16) | ROWC 108881 | 22/38 | L1 |  |  | ??? 10D | FEDEX P | DO NOT DEPANEL NO CLEAN *SHIPPING INVOICE LINE 3 (2ND S/U) | 1/16 - TOP SIDE 2:30 1/16 - BOT SIDE 3:30 1/18 - AOI 10:30 | 1B 1T 48/1224 | 1/16 - RUN ONLY 22 | 0 | 0 | X | Phoenix Contact, Inc. | 586 Fulling Mill Rd | Middletown | PA
|  | 2023-01-20 | 100617-4(3RD) (12/22) |  | 100 | L2 |  |  | 1/20 1/23H* 20D | #VALUE! | CLASS 3 **FAIR REQUIRED FABS REQ 48 HR BAKING | 1/3 - BOT SIDE 8:30 1/4 - TOP SIDE 8:00 1/5 - AOI 10:00 1/18 - THT | 1B 1T 54/401 | 12/22 - KIT CLEAR | 4 | 601 | X | University of Oklahoma |  | Norman | OK
|  | 2023-01-19 | 114334-3 (11/21) | PAID RWK | 836 |  |  |  | 1/23 10D | UPS RED | R&R 2 LOCATIONS | 1/19 - SHIPPING | T/H |  | 2 | 800 |  | Particle Measuring Systems | 5475 Airport Blvd | Boulder | CO
|  | 2023-01-19 | 113868 (12/28) | NEW | 100 | L1 |  |  | 1/20 1/23H 15D | UPS GND | DEPANEL | 12/30 - BOT SIDE 2:00 1/3 - TOP SIDE 10:00 1/4 - AOI 8:00 1/17 - THT | 1B 1T 50/111 | 12/28 - SHOULD CLEAR 12/30 12/30 - KIT CLEAR | 6 | 600 | X | Holland LP | 750 Central Ave | University Park | IL
|  | 2023-01-19 | 104347 (1/3) | NEW | 85 | L3 |  |  | 1/20 1/24 15D | UPS GND | CLASS 3 @THT, DO ONE BOARD FA ONLY THEN SEND PICTURES NOTE: DO NOT TRIM J12-J18 LEADS | 1/4 - TOP SIDE 10:30 1/4 - AOI 2:30 1/19 - SHIPPING | 1T 10/19 | 1/3 - KIT CLEAR 1/17 - THT CLEAR & CUST RESPONDED - 1ST PART APPROVED | 17 | 17 |  | Coastal Designs, LLC | 22 Jordan Cove Rd | Waterford | CT
|  | 2023-01-18 | 115328 (1/11) | NEW | 8 | L2 |  |  | 1/19 5D | FEDEX P | "J2 & J3" SOLDER HEIGHT REQUIREMENT PER ECO #1 & 2 | 1/12 - TOP 7:30 1/12 - AOI 8:30 1/17 - THT | 1T 1/2 | 1/11 - SMT CLEAR ONLY 1/12 - KIT CLEAR | 4 | 32 |  | Loft Orbital Inc. | 810 Brickyard Cir | Golden | CO
|  | 2023-01-18 | 115240 (1/10) | NEW | 700 | L1 |  |  | 1/18 5D | UPS INTL | DEPANEL | 1/11 - BOT SIDE 3:00 1/12 - TOP SIDE 3:30 1/13 - AOI 2:00 | 2B 1T 43/88 | 1/10 - FABS DUE 1/12 1/11 - KIT CLEAR | 0 | 0 | X | General Starlight Co Inc | 120 Whitmore Rd | Woodbridge | ON
|  | 2023-01-17 | 114734-1 (12/27) | RONC 110779 | 100 | L3/L2 |  |  | 1/19 10D | FEDEX GND | X | 1/6 - BOT SIDE 9:00 1/9 - TOP SIDE 6:00 1/9 - AOI 11:00 1/16 - H/L | 1B 1T 39/287 | 12/29 - ALL 100 BOTTOM DONE 1/3 - 25 OF 100 SMT FULLY COMPLETED 1/5 - KIT CLEAR | 46 | 1150 |  | GL Communications | 818 W Diamond Ave | Gaithersburg | MD
|  | 2023-01-16 | 114860-2ND (1/11) | ROWC 1ST ART | 23 | L2 |  |  | 1/18 5D | FEDEX P | DEPANEL | 1/12 - BOT SIDE 1:00 1/13 - TOP 8:00 1/13 - AOI 10:00 | 1B 1T 62/227 | 1/11 - KIT CLEAR | 7 | 161 | X | Noah Medical | 6601 Owens Dr | Pleasanton | CA
|  | 2023-01-16 | 114124-1ST (1/10) | ROWC* 108878 | 2 | L2 |  |  | 1/17 5D | FEDEX P | DEPANEL BOARDS REQ 48 HRS BAKING *SEVERAL CHANGES FROM LAST BUILD - PLEASE DOUBLE CHK BEFORE SHIPPING NOTE: 1C906,1006,1106,1206,306,1406" ARE NOW ROTATED 180 DEG | 1/12 - BOT SIDE 10:00 1/13 - TOP SIDE 6:00 1/13 - AOI 8:00 | 1B 1T 101/1331 | 1/10 - KIT CLEAR 1/11 - FABS READY 1/12 | 0 | 0 | X | Phoenix Contact, Inc. | 586 Fulling Mill Rd | Middletown | PA
|  | 2023-01-16 | 114791-2BAL (1/10) | PAID RWK | 1 | HOLD |  |  | 1/16 5D | FEDEX P | CLASS 3 - XRAY REQ / MUST SAVE IMAGES | 1/10 - THT 1/12 - SHIPPING | 1B 2T 99/1033 | 1/10 - KIT CLEAR 1/12 - SHIPPED 39/40 | 0 | 0 |  | Aeronix, Inc. | 1775 W Hibiscus Blvd Ste 200 | Melbourne | FL
|  | 2023-01-13 | 114215-1ST (12/30) | ROWC 108880 | 2 | L2 |  |  | 1/18 5D | FEDEX P | FAIR REQUIRED | 1/11 - TOP SIDE 12:30 1/12 - BOT SIDE 8:30 1/12 - AOI 10:00 | 2B 1T 122/1304 | 12/30 - SHORT 1 PCB 1/3 - SKIP #103,122,123 & 12 1/11 - KIT CLEAR 1/11 - TOP SIDE FIRST | 0 | 0 | X | Phoenix Contact, Inc. | 586 Fulling Mill Rd | Middletown | PA
|  | 2023-01-13 | 113665-6 (10/17) | RONC 113064 | 100 | L3 |  |  | 2022-01-17 | FEDEX P | NO MOUSE BITE HOLES - GIVE TO TAD TO DEPANEL BAR CODE LABELS REQ | 12/5 - BOT SIDE 1:00 (SHORT ITEM 15 - DUE 12/7) - SMT OFF 12/7 12/8 - TOP SIDE 6:00 12/9 - AOI 11:30 1/13 - SHIPPING | 1B 2T 62/444 | 10/17 - KIT CLEAR QTY 400 PARTIAL 12/9 - HOLD - QTY 58 SHORT ITEM 16 - ORDERED & DUE 12/12 12/15 - KIT CLEAR | 16 | 1600 | X | Command Alkon, Inc. | 6750 Crosby Ct | Dublin | OH
|  | 2023-01-13 | 114470 (1/6) | NEW | 2 | L2 |  |  | 1/17 5D | FEDEX GND | **GLOVES REQUIRED** PREBAKE MOISTURE SENSITIVE PARTS PER ECO #4 CLASS 3 DEPANEL MECH ASSY REQ **XRAY & EMAIL IMAGES TO EMAILS ON ECO #6 | 1/9 - BOT SIDE 12:00 1/9 - TOP SIDE 1:00 1/9 - AOI 2:30 1/13 - SHIPPING | 1B 1T 18/213 | 1/6 - KIT WILL CLEAR 1/9 1/10 - KIT CLEAR | 84 | 168 |  | York Space | 501 Wazee St | Denver | CO
|  | 2023-01-13 | 114854 (1/5) | NEW | 10 | L2 |  |  | 1/17 5D | FEDEX P | DEPANEL | 1/10 - BOT SIDE 6:00 1/10 - TOP SIDE 9:00 1/10 - AOI 9:30 1/13 -SHIPPING | 1B 1T 10/41 | 1/5 - AWT PART CONF #24 1/10 - SKIPPED #24 1/10 - OK TO USE #24 | 50 | 500 |  | FORT Robotics, Inc. | 1608 Walnut St | Philadelphia | PA
|  | 2023-01-13 | 115013 (1/4) | NEW | 5 | L2 |  |  | 1/16 5D | FEDEX P | DEPANEL LEAD PROCESS | 1/11 - BOT SIDE 6:00 1/11 - TOP SIDE 8:30 1/11 - AOI 12:30 1/13 - SHIPPING | 2B 2T 150/815 | 1/4 - FABS DUE 1/6; OK TO SKIP #24 & 48 1/9 - KIT CLEAR 1/9 - FABS DON’T MATCH STENCIL | 16 | 80 |  | Enovate Medical /Stinger Medical | 1152 Park Ave | Murfreesboro | TN
|  | 2023-01-13 | 104353 (1/3) | NEW | 8 | L3 |  |  | 1/13* 1/17 10D | UPS GND | CLASS 3 | 1/4 - TOP SIDE 6:00 1/4 - AOI 8:00 1/11 - SHIPPING | 1T 26/96 | 1/3 - KIT CLEAR | 16 | 128 |  | Coastal Designs, LLC | 22 Jordan Cove Rd | Waterford | CT
|  | 2023-01-12 | 114791-1PAR (1/10) | PAID RWK | 39 |  |  |  | 1/16 5D | FEDEX P | CLASS 3 - XRAY REQ / MUST SAVE IMAGES | 1/10 - THT 1/12 - SHIPPING | 1B 2T 99/1033 | 1/10 - KIT CLEAR | 0 | 0 |  | Aeronix, Inc. | 1775 W Hibiscus Blvd Ste 200 | Melbourne | FL
|  | 2023-01-11 | 115020 (12/27) | NEW | 150 | L1 |  |  | 1/13 5D | FEDEX P | DEPANEL | 12/30 - BOT SIDE 10:00 1/4 - TOP SIDE 8:00 1/4 - AOI 1:00 | 1B 1T 39/97 | 12/27 - FAB DUE 12/29 12/30 - NEED FIXTURE AND NEW STENCIL 1/4 - COMP 149/150 KIT CLEAR 1/6 | 0 | 0 |  | Durbin Group | 10950 Pierson Dr | Fredericksburg | VA
|  | 2023-01-10 | 114756 (1/4) | NEW | 15 | L2 |  |  | 1/10 3D | FEDEX P | *** 3 DAY TURN *** DEPANEL | 1/5 - TOP SIDE 11:30 1/6 - AOI 7:00 1/6 - THT | 1T 50/198 | 1/3 - SHORT 15 (SKIPPABLE); AWT PART CONF 17, 20, 29 & 66 1/5 - KIT CLEAR | 44 | 660 |  | Friedrich Air Conditioning, LLC | 10001 Reunion Pl Ste 500 | San Antonio | TX
|  | 2023-01-10 | 115160 (1/5) | NEW | 125 | L2 |  |  | 1/10 2D | FEDEX P | ** 2 DAY TURN ** DEPANEL & SAND PER ECO 1 *NO LABELS OR STAMPS OVER TRACES ALLOWED PER ECO 2 **SEE ECO 5 FOR MATL & ASSY PACKING/SHIPPING | 1/6 - BOT SIDE 7:00 1/6 - TOP SIDE 10:30 1/6 - AOI 2:30 1/9 - QC | 1B 1T 27/60 | 1/5 - MAY CLEAR TODAY 1/5 - SHORT #8; NOT OK TO SKIP (#8 IS TOP ONLY; RUN BOT ONLY) 1/6 - KIT CLEAR | 0 | 0 |  | Meta Platforms Technologies, LLC | 9845 Willows Rd Ne | Redmond | WA
|  | 2023-01-10 | 115006 (1/9) | NEW | 2 | L2 |  |  | 1/12 2D | FEDEX P | DEPANEL | 1/10 - TOP SIDE 8:00 1/10 - AOI 9:00 | 1T 14/21 | 1/9 - PCBs due today 1/10 - KIT CLEAR | 8 | 16 |  | Guinn Partners | 2120 W Braker Ln | Austin | TX
|  | 2023-01-09 | 114712 (12/27) | NEW | 40 | L1 |  |  | 1/11H 10D | UPS RED | X | 12/29 - TOP SIDE 1:00 12/30 - AOI 8:30 1/6 - THT | 1T 44/200 | 12/27 - KIT CLLEAR | 21 | 840 | X | Scinomix | 4372 Green Ash Dr | Earth City | MO
|  | 2023-01-09 | 114793 (12/27) | ROWC 110040 | 82 | L2 |  |  | 1/11 10D | UPS GND | DEPANEL SPECIAL LABELING REQ (SEE ECO) | 12/28 - TOP SIDE 11:30 12/29 - AOI 8:30 1/6 - THT | 1T 38/100 | 12/27 - KIT CLEAR | 5 | 410 | X | American Time | 140 3rd St | Dassel | MN
|  | 2023-01-09 | 112596 (12/22) | NEW | 20 | L3 |  |  | 1/10 5D | FEDEX 2 DAY | ***DO NOT DEPANEL | 12/28 - BOT SIDE 12:00 12/29 - TOP SIDE 8:30 12/29 - AOI 12:00 12/30 - QC | 1B 1T 40/145 | 12/22 - AWAITING 2 PART CONF 12/28 - OK TO SKIP 1/3 - KIT CLEAR; D3 & ESD1 OK TO USE | 0 | 0 |  | Ripple, LLC | 2056 S 1100 E | Salt Lake City | UT
|  | 2023-01-06 | 115144 (12/29) | ROWC 103726 | 200 | L1 |  |  | 1/6H 5D | UPS GND | DEPANEL | 12/30 - TOP SIDE 8:30 12/30 - AOI 10:00 1/6 - SHIPPING | 1T 4/7 | 12/29 - KIT CLEAR | 3 | 600 |  | PetroPower LLC | 3003 E 37th St N | Wichita | KS
|  | CANCELLED | 113722 (11/23) | NEW | 40 | STOCKROOM |  |  | ??? 3D | FEDEX P | ***3 DAY TURN*** DEPANEL | CHECK B4 SETTING UP - LOOKS LIKE BOT SIDE (DWG) IS ACTUALLY TOP SIDE (S/U TOP SIDE 1ST) | 2B 2T 80/305 | 11/23 - TOP SIDE (WHICH IS ACTUALLY BOT SIDE DWG) CLEAR ONLY 1/4 - CANCELLED | 14 | 560 |  | AVID Technologies | 2112 Case Pkwy Ste 1 | Twinsburg | OH
|  | 2023-01-05 | 113665-5* (10/17) | RONC 113064 | 100 | L3 |  |  | 2022-01-05 | FEDEX P | NO MOUSE BITE HOLES - GIVE TO TAD TO DEPANEL BAR CODE LABELS REQ | 12/5 - BOT SIDE 1:00 (SHORT ITEM 15 - DUE 12/7) - SMT OFF 12/7 12/8 - TOP SIDE 6:00 12/9 - AOI 11:30 1/5 - SHIPPING | 1B 2T 62/444 | 10/17 - KIT CLEAR QTY 400 PARTIAL (0 LEFT) 11/28 - QTY 50 COMPLETED | 16 | 1600 | X | Command Alkon, Inc. | 6750 Crosby Ct | Dublin | OH
|  | 2023-01-04 | 114307-1 (12/22) 1ST ARTICLE | ROWC 108879 | 2 | L2 |  |  | 1/4 5D | FEDEX P | DEPANEL | 12/28 - BOT SIDE 8:30 12/28 - TOP SIDE 9:30 12/28 - AOI 11:30 | 1B 1T 43/1101 | 12/22 - NOT CLEAR BUT OK TO RUN 12/27 - KIT CLEAR | 0 | 0 |  | Phoenix Contact, Inc. | 586 Fulling Mill Rd | Middletown | PA
|  | 2023-01-04 | 114886-2BAL (12/19) | NEW | 8 | L2 |  |  | 1/3H 5D | UPS RED | LABEL PER ECO | 12/27 - BOT SIDE 6:00 12/27 - TOP SIDE 12:00 12/27 - AOI 2:00 12/29 - T/H | 1B 2T 82/613 | 12/19 - MIGHT CLEAR SOON (WAITING FABS) 12/23 - KIT CLEAR 12/27 - #35 DOESN'T FIT & PART# DOESN'T MATCH AUDIT BOM (SKIP) 1/3 - SHIPPED 2 OF 10 TO CUSTOMER 1/4 - RECEIVED U12; KIT CLEAR | 53 | 424 |  | Activ Surgical | 30 Thomson Pl | Boston | MA
|  | 2023-01-04 | 113097-2BAL (12/15) | NEW | 2 | L2 |  |  | 12/30H 10D | FEDEX P | DEPANEL | 12/20 - TOP SIDE 11:30 12/21 - AOI 7:30 12/30 - SOLDER | 1T 1/2 | KIT CLEAR 12/15 1/4 - SHIPPED 243 OF 245 12/30 | 51 | 102 | X | Physical Measurment Technologies Inc | 4 Ling St | Marlborough | NH
|  | 2023-01-03 | 114886-1 (12/19) | NEW | 2 | L2 |  |  | 1/3H 5D | UPS RED | LABEL PER ECO | 12/27 - BOT SIDE 6:00 12/27 - TOP SIDE 12:00 12/27 - AOI 2:00 12/29 - T/H | 1B 2T 82/613 | 12/19 - MIGHT CLEAR SOON (WAITING FABS) 12/23 - KIT CLEAR 12/27 - #35 DOESN'T FIT & PART# DOESN'T MATCH AUDIT BOM (SKIP) 1/3 - SHIP 2 OF 10 TO CUSTOMER FIRST | 53 | 106 |  | Activ Surgical | 30 Thomson Pl | Boston | MA
|  | 2022-12-30 | 114101 (12/2) | ROWC B97512 | 300 | L3 |  |  | 1/4H 20D | UPS GND | DEPANEL | 12/5 - TOP SIDE 6:00 12/5 - AOI 9:00 12/29 - SHIPPING | 1T 9/23 | 12/2 - KIT CLEAR | 0 | 0 |  | Jefferson Labs | 12000 Jefferson Ave | Newport News | VA
|  | 2022-12-30 | 113097-1 (12/15) | NEW | 243/245 | L2 |  |  | 12/30H 10D | FEDEX P | DEPANEL | 12/20 - TOP SIDE 11:30 12/21 - AOI 7:30 12/30 - SOLDER | 1T 1/2 | KIT CLEAR 12/15 | 51 | 12393 | X | Physical Measurment Technologies Inc | 4 Ling St | Marlborough | NH
|  | 2022-12-30 | 115070 (12/22) | RONC 102179 | 25 |  |  |  | 12/30 3D | UPS RED | ***SMT & QA QUALITY ALERT - COLD SOLDER/SHIFTED COMPONENTS - SEE ALERT/EMAIL SHIPPING - TAKE GOOD CLEAR PHOTOS | 12/27 - BOT SIDE 2:00 12/28 - TOP SIDE 8:30 12/28 - AOI 12:00 12/29 - SHIPPING | 1B 1T 14/354 | 12/22 - SHOULD CLEAR TOMORROW 12/23 12/27 - KIT CLEAR 12/29 - NEEDS DEPANEL | 0 | 0 |  | Delsys Inc. | 23 Strathmore Rd | Natick | MA
|  | 2022-12-30 | 114521-2 (12/16) | RONC 113530 BAL | 1 | L1 |  |  | ??? 12/27H 5D | UPS RED | DEPANEL PREVIOUS ISSUES AT L3/L4 and U11 location. | 12/19 - TOP SIDE 10:30 12/19 - BOT SIDE 1:30 12/20 - AOI 9:30 12/27 - QC | 1B 1T 57/114 | KIT CLEAR 12/16 (NOT REPORTED) 12/19 - KIT CLEAR 12/27 - SHIPPED 99/100 (ISSUE W/ QTY 1) | 20 | 20 | X | Alliance Technology, LLC. | 600 N Dekora Woods Blvd | Saukville | WI
|  | 2022-12-29 | 114123-1ST ARTICLE (12/9) | ROWC 108881 | 2 | L3 |  |  | 12/30H 5D | FEDEX P | ***DO NOT DEPANEL | 12/27 - TOP SIDE 6:00 12/27 - BOT SIDE 12:00 12/27 - AOI 2:00 12/29 - SHIPPING | 1B 1T 48/1224 | 12/9 - WILL CLEAR 12/13, 12/20 12/20 - SHORT #36 & #38 12/21 - TOP SIDE FIRST (#36 & #38 TOP SIDE) 12/22 - KIT CLEAR 12/27 - TOP SIDE FIRST | 0 | 0 |  | Phoenix Contact, Inc. | 586 Fulling Mill Rd | Middletown | PA
|  | 2022-12-29 | 114860-1 (12/21) | FIRST ARTICLE | 12 | L3/L2 |  |  | 12/29H 5D | FEDEX P | DEPANEL | 12/21 - BOT SIDE 10:30 12/22 - TOP SIDE 6:00 12/22 - AOI 8:30 12/29 - QC | 1B 1T 62/227 | 12/21 - KIT CLEAR 12/29 - NEEDS DEPANEL | 9 | 108 |  | Noah Medical | 6601 Owens Dr | Pleasanton | CA
|  | 2022-12-29 | 114571 (12/21) | RONC 110259 | 100 | L2 |  |  | 12/29H 5D | FEDEX P | DEPANEL ESD BAG & LABEL PER DWG NOTE #4 | 12/22 - TOP SIDE 8:30 12/22 - AOI 9:30 12/29 - SHIPPING | 1T 6/14 | 12/21 - KIT CLEAR 12/21 - BAKIN FABS 12/29 - DEPANEL? LABEL? | 0 | 0 |  | Perkinelmer - CT | 732 E Utah Valley Dr | American Fork | UT
|  | 2022-12-28 | 113151-1 (12/12) | ROWC 99149 | 54 | L1 |  |  | 12/28 9D | FEDEX P | DEPANEL | 12/14 - BOT SIDE 10:30 12/14 - TOP SIDE 1:00 12/14 - AOI 3:00 12/27 - SOLDER | 2B 2T 37/350 | 12/12 - SMT CLLEAR ONLY 12/14 - RECV PARTIAL 54/120 PCS "J2" KIT CLEAR 12/15 12/27 - QTY 54 OK TO SOLDER; 74 AWT PART #21 REPLACEMENT | 6 | 324 |  | Design Catapult, Inc. | 17361 NEWHOPE ST | Fountain Valley | CA
|  | 2022-12-27 | 114521-1 (12/16) | RONC 113530 | 99/100 | L1 |  |  | 12/27H 5D | UPS RED | DEPANEL PREVIOUS ISSUES AT L3/L4 and U11 location. | 12/19 - TOP SIDE 10:30 12/19 - BOT SIDE 1:30 12/20 - AOI 9:30 | 1B 1T 57/114 | KIT CLEAR 12/16 (NOT REPORTED) 12/19 - KIT CLEAR | 20 | 1980 | X | Alliance Technology, LLC. | 600 N Dekora Woods Blvd | Saukville | WI
|  | 2022-12-27 | 114054-3 (12/8) | NEW | 5 BAL | L2 |  |  | ??? 12/13 2D | FEDEX P | *2 DAY TURN* DO NOT DEPANEL "U36" IS BTD | 12/12 - BOT SIDE 6:00 12/12 - TOP SIDE 12:00 12/12 - AOI 6:30 PM | 2B 1T 110/1297 | 12/8 - KIT CLEAR - "U36" BTD 12/13 - SHORT & SKIP 2 SMT PARTS | 12 | 180 |  | SILC Technologies, Inc. | 181 W Huntington Dr Ste 200 | Monrovia | CA
|  | 2022-12-23 | 114813-1 (12/15) | NEW | 50 | L2/L3 |  |  | 12/28H 5D | UPS RED | DEPANEL USE BLACK SHARPIE FOR REVISION "E" SHIPPING - REMOVE ALL PICK & PLACE PADS (ECO #9) | 12/19 - BOT SIDE 8:00 12/20 - TOP SIDE 7:00 12/21 - AOI 10:00 | 2B 2T 144/1117 | 12/15 - WILL CLEAR SOON 12/19 - WRONG PART 8:30 | 6 | 300 | X | Precision Graphics Inc | 21 County Line Rd | Somerville | NJ
|  | 2022-12-23 | 114812-1 (12/16) | NEW | 30 | L2/L3 |  |  | 12/28H 5D | UPS RED | DEPANEL CLASS 3 SHIPPING - REMOVE ALL PICK & PLACE PADS (ECO #9) | 12/21 - BOT SIDE 7:30 12/21 - TOP SIDE 11:30 12/22 - AOI 11:00 | 1B 2T 92/554 | 12/16 - WILL CLEAR SOON - SHORT ITEMS 49 & 102 12/19 - ONLY SHORT ITEM 102 (6 PER - COULD SKIP IF NEEDED) | 16 | 480 |  | Precision Graphics Inc | 21 County Line Rd | Somerville | NJ
|  | 2022-12-23 | 114814-1 (12/15) | NEW | 200 | L1 |  |  | 12/23* 12/28H 5D | UPS RED | *EXPEDITE PARTIAL IF POSSIBLE BY 12/23 DEPANEL ALT CONN P/N 0877592450 NEEDS GUIDE PINS CUT (QTY 540) ***DO NOT PLACE AA INHOUSE LABELS | ***NEED TO CUT GUIDE PINS OFF "P4" CONN QTY 540 BEFORE SMT CAN START 12/20 - BOT SIDE 9:30 12/20 - TOP SIDE 3:30 12/21 - AOI 2:00 | 1B 2T 42/92 | FABS DUE 12/19 "P4" DUE 12/19 12/20 - KIT CLEAR | 1 | 200 |  | Precision Graphics Inc | 21 County Line Rd | Somerville | NJ
|  | 2022-12-22 | 114735 (12/9) | ROWC 109885 | 50 | L1 |  |  | 12/30 15D | FEDEX GND | "C3_A & C3_B" SMALLER THAN LAYOUT - PLACE AS IS | 12/12 - BOT SIDE 9:00 12/12 - TOP SIDE 10:30 12/12 - AOI 3:00 | 1B 2T 50/173 | KIT CLEAR 12/9 | 18 | 900 |  | GL Communications | 818 W Diamond Ave | Gaithersburg | MD
|  | 2022-12-22 | 114729 (12/13) | ROWC 110407 | 5 | L3 |  |  | 12/22 5D | FEDEX P | DEPANEL XRAY & SAVE IMAGES FOR ALL BGA/LGA'S SPECIAL PACKING SLIP REQ (SEE ECO) | 12/16 - BOT SIDE 6:00 12/16 - TOP SIDE 10:30 12/19 - AOI 8:00 | 2B 2T 146/618 | 12/13 - FAB DUE 12/14; SHORT #8 & #10 DUE 12/15 12/15 - KIT CLEAR | 77 | 385 |  | Artis LLC | 480 Springpark Pl | Herndon | VA
|  | 2022-12-22 | 114815 (12/15) | NEW | 130 | L3 |  |  | 12/22 5D | UPS RED | ***SPECIAL PACKING SLIP & SHIPPING LABEL REQUIRED - DO NOT USE ADV ASSY PACKING SLIP AND CofC*** SHIPPING - NO REFERENCE TO AA OR ALTA ALLOWED - USE CLEAR PACKING TAPE ONLY!!! DEPANEL *DO NOT PUT AA LABELS PER ECO #2 | 12/19 - BOT SIDE 8:00 12/19 - TOP SIDE 11:30 12/19 - AOI 2:30 | 1B 1T 42/92 | KIT CLEAR 12/15 | 1 | 130 |  | Precision Graphics Inc | 21 County Line Rd | Somerville | NJ
|  | 2022-12-22 | 114404-2 (11/29) | ROWC 113440 | 400 BAL | L2 |  |  | 12/22 10D | FEDEX 2 DAY | SET VSCORE CUTTER DEPTH TO "5" MAX NOTES = SHIP QTY 400 ON 12/8 AND QTY 400 ON 12/22, CAN BUILD QTY 800 ALL AT ONCE ***MECH ASSY REQ | 12/2 - TOP SIDE 9:30 12/5 - AOI 1:00 | 2T 22/50 | 11/29 - AWAITING PART REMOVAL FROM B113440 11/30 - ON HOLD DUE TO FAB ISSUE 12/1 - SHORT A2 DO NOT SKIP 12/2 - KIT CLEAR | 11 | 4400 | X | Command Alkon, Inc. | 6750 Crosby Ct | Dublin | OH
|  | 2022-12-21 | 114272 (12/14) | NEW | 160 | L1 |  |  | 12/21 5D | UPS RED | DEPANEL NEED CofC PER ECO #5 | 12/14 - BOT SIDE 3:00 12/15 - TOP SIDE 11:00 12/16 - TOP HOLD 12:30 12/19 - TOP SIDE 7:00 12/19 - AOI 10:30 | 1B 2T 94/372 | 12/14 - KIT CLEAR | 2 | 320 | X | Trust Automation | 125 Venture Dr Ste 110 | San Luis Obispo | CA
|  | 2022-12-20 | 114027 (12/12) | RONC 102704 | 19 | L2 |  |  | 12/21 5D | UPS RED | X | 12/14 - BOT SIDE 12:30 | 1B 2T 125/656 | 12/12 - SHOULD CLEAR 12/13 12/13 - SHORT U15 (#50) DUE 12/14 12/14 - KIT CLEAR | 26 | 494 |  | General Digital | 60 Prestige Park Rd | East Hartford | CT
|  | 2022-12-20 | 114054-2 (12/8) | NEW | 5/10BAL | L2 |  |  | ??? 12/13 2D | FEDEX P | *2 DAY TURN* DO NOT DEPANEL "U36" IS BTD | 12/12 - BOT SIDE 6:00 12/12 - TOP SIDE 12:00 12/12 - AOI 6:30 PM | 2B 1T 110/1297 | 12/8 - KIT CLEAR - "U36" BTD 12/13 - SHORT & SKIP 2 SMT PARTS | 12 | 180 |  | SILC Technologies, Inc. | 181 W Huntington Dr Ste 200 | Monrovia | CA
|  | 2022-12-19 | 113347-2 (12/6) | RONC 112096 | 50 | L1 |  |  | 12/19 12/14 1D | FEDEX P | ***1 DAY TURN*** DEPANEL *SHORT 1 PC ITEM 40 - SHIP QTY 50 12/14 | 12/13 - BOT SIDE 10:30:00 - SMT WILL RUN QTY 51 LESS 1 PC ITEM 40 (WILL RE-RUN THRU REFLOW WHEN PART COMES) 12/13 - TOP SIDE 11:00 (HOLD - DELAM) 12/16 - TOP SIDE 12:30 (DELAM APPROVED) 12/16 - AOI 3:00 | 1B 1T 72/254 | 12/6 - PARTS COMING WEEK OF 12/12 - SHORT ITEMS 30, 33 & 40 12/12 - SHOULD CLEAR 10:30 AM 12/13 12/13 - ONLY SHORT 1 PC ITEM 40 12/13 - BOT SIDE DELAM - ON HOLD 12/16 - DELAM APPROVED | 21 | 1071 |  | AVID Technologies | 2112 Case Pkwy Ste 1 | Twinsburg | OH
|  | 2022-12-19 | 114185 (12/5) | RONC 114026 | 28 | L2 |  |  | 12/19 9D | UPS RED | 1) HEIGHT ON "U4" NO MORE THAN 0.320" 2) LABEL PER ECO #2 | 12/6 - BOT SIDE 6:00 12/16 - TOP SIDE 6:00 12/16 - AOI 12:30 | 1B 2T 110/462 | 12/5 - SHORT U22 & 4 PART CONF 12/6 - KIT CLEAR; U22 DNI | 1 | 28 |  | General Digital | 60 Prestige Park Rd | East Hartford | CT
|  | 2022-12-19 | 110198-2 (11/3) | NEW | 170 BAL | L2 |  |  | 12/19 10D | FEDEX GND | DEPANEL ***LOAD "J3" & "J3A"*** 11/11 CUST ASK TO RUN PARTIAL QTY 180 ATTACH B110428 (IN THE BACK) TO THIS ASSY 11/3 - FABS RE-BAKED 10:30AM | 11/22 - TOP SIDE 8:00 11/23 - AOI 10:00 | 2T 19/35 | 11/23 - SHORT T/H | 7 | 2450 | X | WalkMed, LLC | 14190 E Jewell Ave Ste 10 | Aurora | CO
|  | 2022-12-19 | 113646-2 (12/7) | 2ND ARTICLE | 4 | L3 |  |  | 12/16 5D | FEDEX 2 DAY | DEPANEL FAIR REQUIRED | 12/9 - BOT SIDE 11:30 12/9 - TOP SIDE 12:45 12/12 - AOI 8:00 | 1B 3T 156/691 | 12/7 - SHORT #43, #54, #145 & #170 (NOT REPORTED) DAY 1 IS MON 12/12 | 28 | 112 |  | Dorner Works LTD | 3445 Lake Eastbrook Blvd Se | Grand Rapids | MI
|  | 2022-12-16 | 114332 (12/12) | RONC 112372 | 100 | L2 |  |  | 12/20 5D | FEDEX P | DOUBLE CHK LED PLACEMENT PER ECO #1 | 12/13 - TOP SIDE 11:30 12/14 - AOI 12:00 | 1T 45/239 | 12/12 - AWAITNG PART CONF #15 12/13 - KIT CLEAR | 0 | 0 |  | Watchfire Signs | 518 Ben Green Industrial Park Rd | Elizabethtown | NC
|  | 2022-12-16 | 114821 (12/12) | RONC 112849 | 120 | L2 |  |  | 12/16 12/15 3D | FEDEX P | ***3 DAY TURN*** DEPANEL BARCODE LABELS REQ | 12/13 - TOP SIDE 9:30 12/13 - AOI 11:30 | 1T 15/34 | 12/12 - KIT CLEAR 12/12 - CUST HOLD | 4 | 480 |  | Command Alkon Inc. | 6750 Crosby Ct | Dublin | OH
|  | 2022-12-15 | 113347-1 (12/6) | RONC 112096 | 1 | L1 |  |  | 12/15 1D | FEDEX P | ***1 DAY TURN*** DEPANEL *SHORT 1 PC ITEM 40 - SHIP QTY 50 12/14 ***12/14 - RAN QTY 1 DELAMED BOARD, TOP SIDE PER CUST SHIP 12/15 | 12/13 - BOT SIDE 10:30:00 - SMT WILL RUN QTY 51 LESS 1 PC ITEM 40 (WILL RE-RUN THRU REFLOW WHEN PART COMES) 12/13 - TOP SIDE 11:00 - DELAM ON BOT SIDE 12/13 - REBAKED BOARDS 3:30 PM (NEED 48 HRS) 12/14 - TOP SIDE 1:30 QTY 1 | 1B 1T 72/254 | 12/6 - PARTS COMING WEEK OF 12/12 - SHORT ITEMS 30, 33 & 40 12/12 - SHOULD CLEAR 10:30 AM 12/13 12/13 - ONLY SHORT 1 PC ITEM 40 12/13 - BOT SIDE DELAM - ON HOLD | 21 | 1071 |  | AVID Technologies | 2112 Case Pkwy Ste 1 | Twinsburg | OH
|  | 2022-12-15 | 104575-3 (12/1) | 3RD ARTICLE | 8 BAL | L1 |  |  | 12/22 15D | FEDEX P | UPDATED ECO NOTE #8 J2 PRESS FIT & DO NOT SOLDER | 12/1 - TOP SIDE 1:30 12/2 - BOT SIDE 10:30 12/5 - AOI 8:30 | 1B 2T 63/203 | 12/1 - KIT CLEAR 12/2 - TOP SIDE FIRST | 2 | 16 | X | University of Oklahoma | 3190 Monitor Ave Rm 0220 | Norman | OK
|  | 2022-12-15 | 113227 (11/10) | NEW | 6 | L3 |  |  | 12/21 15D | FEDEX P | DEPANEL | 11/30 - BOT SIDE 6:00 11/30 - TOP SIDE 10:30 11/30 - AOI 1:00 | 1B 2T 83/439 | 11/10 - WILL CLEAR 11/11 11/16 - WILL CLEAR 11/21 11/21 - SHORT U36 CAN SKIP 11/29 - U36 SUB ARRIVE 11/30 11/30 - KIT CLEAR | 18 | 108 |  | Horiba Instruments | 20 Knightsbridge Rd Main Dock 2 Rear | Piscataway | ND
|  | 2022-12-14 | 113030 (11/11) | NEW | 50 | L1 |  |  | 12/14H 20D | FEDEX GND | DEPANEL CLASS 3 FAB PRE-BAKE REQ | 11/30 - BOT SIDE 8:00 12/1 - TOP SIDE 7:00 12/1 - AOI 9:30 | 1B 1T 48/410 | 11/3 - MISSING #18 CAN'T SKIP 11/4 - ON HOLD 11/11 - OFF HOLD & SHORT R59 11/14 - KIT CLEAR | 0 | 0 |  | EOTech, LLC | 3580 Bassett St | Santa Clara CA | CA
|  | 2022-12-14 | 114544 (12/7) | NEW | 200 | L2 |  |  | 12/14 5D | UPS RED | DEPANEL ***SMT DO NOT DAMAGE "U1" - HANDLE W CARE | 12/9 - BOT SIDE 6:00 12/13 - TOP SIDE 6:00 12/13 - AOI 9:00 | 1B 1T 13/33 | 12/7 - KIT CLEAR | 0 | 0 |  | Carnegie Robotics | 4501 Hatfield St | Pittsburgh | PA
|  | 2022-12-14 | 114587 (12/8) | NEW | 5 | L1 |  |  | 12/14 3D | FEDEX P | DEPANEL CLASS 3 MECH ASSY REQ *DNI ALL HARDWARE DNI "JZ8" | 12/9 - TOP SIDE 2:30 12/12 - BOT SIDE 7:00 12/12 - AOI 9:00 | 1B 1T 77/614 | 12/8 - SHORT T/H ONLY 12/9 - DNI ALL HARDWARE ONLY SHORT ITEM 50 T/H 12/9 - KIT CLEAR | 28 | 140 |  | Aeronix, Inc. | 777 Lowndes Hill Rd Ste 160 | Greenville | SC
|  | 2022-12-14 | 110198-1 (11/3) | NEW | 180 | L2 |  |  | ??? 12/5H 12/2H 10D | FEDEX GND | DEPANEL ***LOAD "J3" & "J3A"*** 11/11 CUST ASK TO RUN PARTIAL QTY 180 ATTACH B110428 (IN THE BACK) TO THIS ASSY 11/3 - FABS RE-BAKED 10:30AM | 11/22 - TOP SIDE 8:00 11/23 - AOI 8:00 | 2T 19/35 | 11/3 - WILL CLEAR SOON 11/10 - SMT CLEAR & SHORT T/H 11/11 - CUST ASKING TO RUN PARTIAL SMT CLEAR / ONLY SHORT T/H - NEED TO SHIP PARTIAL QTY 180 DAY ONE IS 11/17 12/5 - AWAITING CUSTOMER REPLY | 7 | 2450 | X | WalkMed, LLC | 14190 E Jewell Ave Ste 10 | Aurora | CO
|  | 2022-12-13 | 114731 (12/6) | ROWC 114180 | 50 | L1 |  |  | 12/13 3D | FEDEX P | ***3 DAY TURN*** DEPANEL & SAND TRIM LEAD HEIGHT NO MORE THAN 0.1" (2.54MM) | 12/8 - BOT SIDE 3:00 12/9 - TOP SIDE 10:00 12/9 - AOI 2:30 | 1B 1T 11/469 | FABS DUE 12/7 12/8 - KIT CLEAR | 1 | 50 |  | Spectro Inc. | 1 Executive Dr | Chelmsford | MA
|  | 2022-12-13 | 114534 (11/30) | NEW | 60 | L1 |  |  | 12/13* 5D | FEDEX P | BOARDS MUST BE WASHED WITHIN 8 HRS AFTER REFLOW | 12/6 - BOT SIDE 8:30 12/6 - TOP SIDE 11:30 12/8 - AOI 8:30 | 1B 1T 62/231 | 11/30 - FABS DUE 12/2 12/1 - 50 of 60 FABS DUE 12/2; SPLIT SHIPMENT 50 & 10 12/7 - KIT CLEAR | 1 | 60 |  | Engenious Design | 2400 W 75th Street | Prairie Village | KS
|  | 2022-12-13 | 113048 (12/1) | NEW | 4 | L2 |  |  | 12/13 10D | FEDEX GND | DEPANEL RTV & MECH ASSY REQUIRED | 12/2 - TOP SIDE 8:30 12/2 - AOI 9:30 | 1T 10/33 | 12/1 - SMT CLEAR 12/5 - KIT CLEAR | 43 | 172 |  | Mission Support and Test Services, LLC. | 2900 East Rd | Los Alamos | NM
|  | 2022-12-12 | 110416-3 (12/6) | 3RD ARTICLE | 5 | L2 |  |  | 12/13 5D | FEDEX P | DEPANEL SMT RAN QTY 4 EXTRA ON BOT SIDE | 12/8 - BOT SIDE 10:30 12/8 - TOP SIDE 12:30 12/8 - AOI 3:00 | 1B 1T 65/204 | 12/6 - KIT CLEAR | 3 | 120 |  | Innovasea Systems, Inc. | 12 Channel st | Boston | MA
|  | 2022-12-12 | 113835 (11/28) | NEW | 100 | L2 |  |  | 12/12 10D | UPS GND | DEPANEL | 11/29 - BOT SIDE 11:30 12/1 - TOP SIDE 10:00 12/2 - AOI 8:30 | 1B 1T 155/178 | 11/28 - SHORT #45 DUE TODAY 11/28 - KIT CLEAR | 20 | 2000 | X | Graph-Tech USA, LLC | 3200 N Kings Hwy | Fort Pierce | FL
|  | 2022-12-12 | 112874 (11/10) | NEW | 10 | L1 |  |  | 12/12 12/7H 10D | FEDEX GND | DEPANEL SHORT HEAT SINK PINS | 11/28 - BOT SIDE 1:30 11/29 - TOP SIDE 8:30 11/29 - AOI 3:30 | 1B 1T 87/959 | 11/10 - WILL CLEAR SOON 11/21 - KIT CLEAR | 22 | 220 |  | Switched Source, LLC | 200 W Adams St Ste 2230 | Chicago, | IL
|  | 2022-12-12 | 114334-2 (11/21) | PAID RWK | 400 |  |  |  | 12/12 12/1 10D | UPS RED | R&R 2 LOCATIONS | 11/22 - BACK | T/H |  | 2 | 3160 |  | Particle Measuring Systems | 5475 Airport Blvd | Boulder | CO
|  | 2022-12-09 | 113770 (12/5) | ROWC B111713 | 3 |  |  |  | 12/12 5D | FEDEX INTER | DEPANEL ASSY POST BAKE REQ IF WASHED | 12/5 - TOP SIDE 2:00 12/6 - AOI 8:30 | 1T 27/524 | 12/5 - KIT CLEAR | 102 | 306 | X | ICUMedical | 1 Km Noreste del Centro Comercial Real | COSTA RICA
|  | 2022-12-09 | 114426 (12/1) | NEW | 5 |  |  |  | 12/12 5D | FEDEX P | DEPANEL | 12/5 - TOP SIDE 8:30 12/5 - BOT SIDE 11:30 12/5 - AOI 2:00 | 1B 2T 119/592 | 12/1 - FABS DUE 12/6 12/5 - KIT CLEAR | 0 | 0 |  | Luna Innovations, Inc. | 3155 State St | Blacksburg | VA
|  | 2022-12-09 | 114054-1 (12/8) | NEW | 5/15 |  |  |  | 12/9 1D | WILL CALL COURIER | *1 DAY TURN QTY 5* DO NOT DEPANEL "U36" IS BTD | 12/8 - BOT SIDE 1:00 12/9 - TOP SIDE 6:00 12/9 - AOI 10:45 | 2B 1T 110/1297 | 12/8 - KIT CLEAR - "U36" BTD | 12 | 180 |  | SILC Technologies, Inc. | 181 W Huntington Dr Ste 200 | Monrovia | CA
|  | 2022-12-08 | 114452 (11/23) | NEW | 1950 BAL |  |  |  | ??? 12/6 5D | UPS RED | DEPANEL "R1" IS BTD - MARK ALL BOARDS WITHOUT "R1" LABEL/TAG SHIPPING BOX W/ LOT CODE "Z15-202-6-461 ***DO NOT MIX PARTS W/ B114454 & B114455 | 11/30 - TOP SIDE 6:00 11/30 - AOI 8:00 | 1T 2/4 | 11/23 - SHORT ATTRITION ONLY 11/23 - FABS DUE 11/29 11/29 - KIT CLEAR 12/5 - SENT 50 OF 2000 TO CUSTOMER FOR DEPANEL ISSUE 12/5 - AWAITING CUSTOMER REPLY | 0 | 0 | X | Instron | 825 UNIVERSITY AVE | Norwood | MA
|  | 2022-12-08 | 114454 (11/30) | NEW | 2000 |  |  |  | ??? 12/7 5D | UPS RED | DEPANEL LABEL/TAG SHIPPING BOX W/ LOT CODE "Z11-202-6-451 ***DO NOT MIX PARTS W/ B114452 & B114455 | 11/30 - TOP SIDE 1:00 12/1 - AOI 9:30 | 2T 6/6 | 11/30 - KIT CLEAR 12/5 - WAITING CUST REPLY ABOUT DEPANEL ISSUE | 0 | 0 |  | Instron | 825 UNIVERSITY AVE | Norwood | MA
|  | 2022-12-08 | 111857 (11/15) | NEW | 20 |  |  |  | 12/8H 15D | FEDEX P | ***DO NOT SHIP EARLY*** ***DEPANEL 4 OUTSIDE RAILS ONLY!!! ***DO NOT CUT BOARD IN HALF*** (BOARD HAS VSCORE DOWN THE MIDDLE) | 11/23 - BOT SIDE 2:00 11/28 - TOP SIDE 8:30 11/28 - AOI 1:30 | 1B 1T 22/375 | 11/15 - KIT CLEAR; DNI JA500 | 20 | 400 | X | Switched Source LLC | 200 W Adams St | Chicago | IL
|  | 2022-12-08 | 113665-4 (10/17) | RONC 113064 | 100 |  |  |  | 12/8 MULTI | FEDEX P | NO MOUSE BITE HOLES - GIVE TO TAD TO DEPANEL BAR CODE LABELS REQ | 11/23 - BOT SIDE 2:00 11/28 - TOP SIDE 1:30 11/29 - AOI 2:30 | 1B 2T 62/444 | 10/17 - KIT CLEAR QTY 400 PARTIAL (150 LEFT) | 16 | 800 | X | Command Alkon, Inc. | 6750 Crosby Ct | Dublin | OH
|  | 2022-12-08 | 113153 (11/22) | NEW | 120 |  |  |  | 12/8H 10D | FEDEX P | ERIC: USE FedEx Account#: 1396-7551-7 PER ECO NOTE #1 | 11/28 - BOT SIDE 9:00 11/28 - TOP SIDE 11:00 11/28 - AOI 1:30 | 1B 1T 7/82 | 11/22 - KIT CLEAR | 9 | 1080 |  | Design Catapult, Inc. | 17361 Newhope St | Fountain Valley | CA
|  | 2022-12-08 | 114404-1 (11/29) | ROWC 113440 | 400/800 |  |  |  | 12/8 10D | FEDEX 2 DAY | SET VSCORE CUTTER DEPTH TO "5" MAX NOTES = SHIP QTY 400 ON 12/8 AND QTY 400 ON 12/22, CAN BUILD QTY 800 ALL AT ONCE ***MECH ASSY REQ | 12/2 - TOP SIDE 9:30 12/5 - AOI 1:00 | 2T 22/50 | 11/29 - AWAITING PART REMOVAL FROM B113440 11/30 - ON HOLD DUE TO FAB ISSUE 12/1 - SHORT A2 DO NOT SKIP 12/2 - KIT CLEAR | 11 | 4400 | X | Command Alkon, Inc. | 6750 Crosby Ct | Dublin | OH
|  | 2022-12-08 | 114455 (11/23) | NEW | 1950 BAL |  |  |  | ??? 12/8 5D | UPS RED | DEPANEL LABEL/TAG SHIPPING BOX W/ LOT CODE "Z1-202-6-455 ***DO NOT MIX PARTS W/ B114452 & B114454 | 12/1 - TOP SIDE 9:30 12/1 - AOI 1:30 | 1T 2/7 | 11/23 - SHORT ATTRITION ONLY 11/23 - FABS DUE 11/29 11/29 - KIT CLEAR 12/5 - SENT 50 OF 2000 TO CUSTOMER FOR DEPANEL ISSUE 12/5 - AWAITING CUSTOMER REPLY | 0 | 0 |  | Instron | 825 UNIVERSITY AVE | Norwood | MA
|  | 2022-12-07 | 112562-1 (11/16) | ROWC B109333 | 250 | L3 |  |  | 12/7 10D | FEDEX GND | X | LEFTOVER MATL STRIPS FROM 109333 FSU SHORT U1 DUE 11/17 11/18 - TOP SIDE 2:00 11/23 - AOI 2:00 | 1T 42/145 | 11/16 - WILL CLEAR 11/17; PARTIAL SHORT ITEM #12 DUE 11/17 11/18 - KIT CLEAR | 22 | 5500 | X | US Army RDECOM | 8500 Otto Rd Bldg E4301 | Gunpowder | MD
|  | 2022-12-06 | 114184-2 (11/23) | NEW | 300 BAL | L2 |  |  | 12/6 5D | FEDEX P | DO NOT PUT LABELS ON BOARDS PER ECO | 11/30 - BOT SIDE 6:00 12/1 - AOI 10:30 | 1B 7/70 | 11/23 - WILL CLEAR SOON 11/30 - KIT CLEAR | 0 | 0 |  | Kopin Corporation | 125 NORTH DR | Westborough | MA
|  | 2022-12-05 | 114455 (11/23) | NEW | 2000 | L3 |  |  | ??? 12/8 5D | UPS RED | DEPANEL LABEL/TAG SHIPPING BOX W/ LOT CODE "Z1-202-6-455 ***DO NOT MIX PARTS W/ B114452 & B114454 | 12/1 - TOP SIDE 9:30 12/1 - AOI 1:30 | 1T 2/7 | 11/23 - SHORT ATTRITION ONLY 11/23 - FABS DUE 11/29 11/29 - KIT CLEAR 12/5 - INITIAL 50 SENT TO CUSTOMER FOR DEPANEL REVIEW | 0 | 0 |  | Instron | 825 UNIVERSITY AVE | Norwood | MA
|  | 2022-12-05 | 114452 (11/23) | NEW | 50 | L1 |  |  | ??? 12/6 5D | UPS RED | DEPANEL "R1" IS BTD - MARK ALL BOARDS WITHOUT "R1" LABEL/TAG SHIPPING BOX W/ LOT CODE "Z15-202-6-461 ***DO NOT MIX PARTS W/ B114454 & B114455 | 11/30 - TOP SIDE 6:00 11/30 - AOI 8:00 | 1T 2/4 | 11/23 - SHORT ATTRITION ONLY 11/23 - FABS DUE 11/29 11/29 - KIT CLEAR 12/5 - WAITING CUST REPLY ABOUT DEPANEL ISSUE 12/5 - INITIAL 50 SENT TO CUSTOMER FOR DEPANEL REVIEW | 0 | 0 | X | Instron | 825 UNIVERSITY AVE | Norwood | MA
|  | 2022-12-05 | 112132-1 (11/11) | NEW FA | 2 | L1/HOLD |  |  | ??? 11/21 5D | FEDEX P | DEPANEL FAIR REQUIRED XRAY & SAVE IMAGES | 11/14 - BOT SIDE 10:00 11/16 - TOP SIDE 10:30 11/16 - AOI 1:00 ***11/18 - POSS WRONG FAB / DWGS - EMAIL SENT | 1B 1T 64/238 | 11/11 - KIT CLEAR (NOT REPORTED) 11/14 - ON HOLD; WRONG PART #27 | 7 | 14 |  | Anderson Connectivity | 601 Atlantis Rd | Melbourne | FL
|  | 2022-12-05 | 112217-3 (11/28) | 2ND ARTICLE | 41 | L3 |  |  | 12/5 5D | FEDEX P | DEPANEL | 11/28 - TOP SIDE 10:30 11/28 - BACK 1:30 | 1T 1/1 | 11/28 - KIT CLEAR | 0 | 0 |  | Tomahawk Robotics, LLC | 2326 Irwin St | Melbourne | FL
|  | 2022-12-05 | 112218-3 (11/28) | 2ND ARTICLE | 41 | L3 |  |  | 12/5 5D | FEDEX P | DEPANEL | 11/28 - TOP SIDE 10:30 11/28 - BACK 1:30 | 1T 1/1 | 11/28 - KIT CLEAR | 0 | 0 |  | Tomahawk Robotics, LLC | 2326 Irwin St | Melbourne | FL
|  | 2022-12-02 | 113576 (11/2) | ROWC B112810 | 1200 | L2 |  |  | 12/2H 20D | FEDEX P | DEPANEL MECHANICAL ASSY REQ | 11/21 - BOT SIDE 9:30 11/22 - AOI 1:00 | 1B 10/28 | 11/2 - KIT CLEAR | 2 | 2400 | X | Kopin Corporation | 125 North Drive | Westborough | MA
|  | 2022-12-02 | 113152 (11/30) | NEW | 120 | L1 |  |  | 12/2 9D | FEDEX P | DEPANEL | 12/1 - TOP SIDE 9:30 12/1 - AOI 1:30 | 1T 15/56 | 11/16 - KIT CLEAR | 7 | 840 |  | Design Catapult, Inc. | 17361 NEWHOPE ST | Fountain Valley | CA
|  | 2022-12-02 | 114184-1 (11/23) | NEW | 300/600 | L2 |  |  | 12/2 3D | FEDEX P | **3 DAY TURN** DO NOT PUT LABELS ON BOARDS PER ECO | 11/30 - BOT SIDE 6:00 12/1 - AOI 10:30 | 1B 7/70 | FABS DUE 11/17, 11/21, 11/28, 11/29 11/23 - WILL CLEAR SOON 11/28 - FABS ARRIVE 11/30 11/30 - KIT CLEAR | 0 | 0 | X | Kopin Corporation | 125 NORTH DR | Westborough | MA
|  | 2022-12-01 | 105003-2* (11/11) | 2ND ARTICLE | 30* | L1 |  |  | 12/1H 10D | UPS RED | ***SHIP QTY 10-20 ON 11/29*** MECH ASSY REQ INSP J4 AREA BEFORE SOLDERING SHIELD | 11/18 - BOT SIDE 1:00 11/18 - TOP SIDE 2:00 KIM LEFT EARLY 11/21 - TOP SIDE 7:00 11/21 - AOI 10:00 | 1B 1T 38/92 | 11/11 - PARTIAL SHORT 1 ITEM OK TO SKIP 11/15 - KIT CLEAR 11/29 - SHIPPED 20 OF 50 (30 REMAIN) | 4 | 120 |  | Intellisense Systems | 21061 S Western Ave | Torrance | CA
|  | 2022-12-01 | 114390-2 (11/17) | NEW | 39 BAL | L2 |  |  | 12/1H 5D | FEDEX P |  | 11/23 - BOT SIDE 10:00 11/23 - AOI 2:00 | 1B 1T 48/139 | MAY CLEAR 11/17 11/17 - SHORT #2 & #42 11/22 - KIT CLEAR | 15 | 585 |  | Atlas Devices | 21 Alpha Rd | Chelmsford | MA
|  | 2022-12-01 | 114057 (11/15) | ROWC B105738 | 50 | L1 |  |  | 12/1H 10D | FEDEX GND | DEPANEL | 11/21 - TOP SIDE 10:30 11/21 - AOI 11:30 | 1T 6/11 | 11/15 - KIT CLEAR | 3 | 150 | X | Hamilton Mfg. Corp | 1026 Hamilton Dr | Holland | OH
|  | 2022-11-30 | 111796 (11/10) | NEW | 50 | L2 |  |  | 11/30H 10D | UPS GND | DEPANEL | 11/16 - BOT SIDE 8:00 11/16 - TOP SIDE 9:30 11/21 - AOI 9:30 | 1B 1T 80/398 | 11/10 - SHOULD CLEAR TODAY 11/10 - 7 PARF C/F'S | 27 | 1350 | X | Graph-Tech USA, LLC | 3200 N Kings Hwy | Fort Pierce | FL
|  | 2022-11-30 | 111470-2 (11/11) | 2ND ARTICLE | 190 | L2 / L3 |  |  | 11/30H 10D | FEDEX P | DEPANEL ***DOUBLE CHECK SMT - ITEMS 111 & 113 SWAP *** NEED TO LOAD F1 FUSE INTO HOLDER F1A | 11/14 - TOP SIDE 11:30 11/16 - AOI 2:30 | 3T 151/699 | 11/11 - KIT CLEAR (NOT REPORTED) | 9 | 1710 | X | Servomex, Inc. | 4 Constitution Way | Woburn | MA
|  | 2022-11-30 | 110522 (11/7) | ROWC 102221 | 300 | L1 |  |  | 11/30H 15D | FEDEX P | DEPANEL | 11/17 - BOT SIDE 12:00 11/18 - TOP SIDE 10:00 11/18 - AOI 1:00 | 1B 1T 18/97 | 11/7 - KIT CLEAR | 0 | 0 | X | Radiation Detection Technologies, Inc. | 123 Ward Hall | Manhattan | KS
|  | 2022-11-30 | 114351 (11/21) | NEW | 500 | L2 |  |  | 11/30H 5D | FEDEX GND |  | 11/22 - TOP SIDE 6:00 11/22 - AOI 8:00 | 1T 1/1 | 11/21 - KIT CLEAR | 0 | 0 |  | Moxtek, Inc. | 452 W 1260 N | Orem | UT
|  | 2022-11-29 | 105003-2* (11/11) | 2ND ARTICLE | 20/50 | L1 |  |  | 12/1H 10D | UPS RED | ***SHIP QTY 10-20 ON 11/29*** MECH ASSY REQ INSP J4 AREA BEFORE SOLDERING SHIELD | 11/18 - BOT SIDE 1:00 11/18 - TOP SIDE 2:00 KIM LEFT EARLY 11/21 - TOP SIDE 7:00 11/21 - AOI 10:00 | 1B 1T 38/92 | 11/11 - PARTIAL SHORT 1 ITEM OK TO SKIP 11/15 - KIT CLEAR 11/29 - SHIPPED 20 OF 50 | 4 | 80 |  | Intellisense Systems | 21061 S Western Ave | Torrance | CA
|  | 2022-11-29 | 111751-2 (10/25) BAL | 2ND ART NO CHG | 250 | L1 |  |  | 11/29H 20D | FEDEX P | DEPANEL ***DO NOT SHIP MATL*** | 10/26 - BOT SIDE 8:30 10/27 - TOP SIDE 8:30 10/31 - AOI 11:00 | 1B 2T 86/453 | KIT CLEAR 10/25 (NOT REPORTED) OFFICIALLY CLEAR 10/27 | 139 | 34750 |  | Bose Corp. | 100 Mountain Rd | Framingham | MA
|  | 2022-11-29 | 113887 (11/4) | NEW | 5 | L2 |  |  | 11/29H 15D | FEDEX GND | DEPANEL NO ARRAY FILE AVAIL - MAKE CUSTOM STENCIL *DO NOT PUT LABELS ON BOARDS | 11/23 - BOT SIDE 9:00 11/23 - BACK 2:00 | 1B 1T 1/8 | 11/4 - KIT CLEAR | 0 | 0 |  | NIST | 325 BROADWAY ST | Boulder | CO
|  | 2022-11-29 | 103337 109746 (4/5) (11/10) | NEW | 400 | L3 |  |  | 11/29H 10D | #VALUE! | ROWC B100330 - S/U & RUN BOT ONLY - DC: 2921 RE-BAKE FABS 4/5 DEPANEL & SAND | 11/11 - BOT SIDE 1:30 11/12 - TOP SIDE 1:00 11/14 - AOI 11:30 | 2B 2T 68/137 | 11/10 - KIT CLEAR 11/10 - PARTS REMOVED FROM 103337; NEED TO T&R | 6 | 2400 | X | Scientific Research Corporation | 103 Quality Cir Nw Ste 220 | Huntsville | AL
|  | 2022-11-29 | 114334-1 (11/21) | PAID RWK | 20/1600 |  |  |  | 11/29 2D | UPS RED | R&R 2 LOCATIONS | 11/22 - BACK | T/H |  | 2 | 40 |  | Particle Measuring Systems | 5475 Airport Blvd | Boulder | CO
|  | 2022-11-28 | 108880 (11/17) | ROWC B104931 | 10 | L1 |  |  | 11/28H 3D | FEDEX P | DEPANEL - NEED TO CUT & SAND (GIVE TO TAD) ** 3 DAY TURN** HOLD MATL FOR FUTURE JOBS **FAIR REQ** | 11/21 - TOP SIDE 12:00 11/22 - AOI 2:00 | 2B 1T 121/1304 | 11/17 - SHORT PCB; 2 PART CONF 11/21 - KIT CLEAR | 7 | 70 |  | Phoenix Contact, Inc. | 586 Fulling Mill Rd | Middletown | PA
|  | 2022-11-28 | 113975 (10/31) | RONC B106111 | 216 | L3 |  |  | 11/28 11/22 15 10 | UPS RED | SMT - MULTIPLE CUT STRIPS ON REELS ***SHIP ON 11/28 PER CUSTOMER | 11/10 - BOT SIDE 2:30 11/10 - TOP SIDE 7:30 11/10 - AOI 2:30 | 1B 2T 57/154 | 11/1 - KIT CLEAR | 8 | 1728 |  | AQM Acquisition Corp dba Finna Group | 9567 Arrow Rte | Rancho Cucamonga | CA
|  | 2022-11-28 | 112881-2 (11/7) | 2ND ARTICLE | 4 | L2 |  |  | 11/28 11/22 5D | FEDEX GND | DEPANEL | 11/8 - BOT SIDE 1:00 11/9 - TOP SIDE 9:00 11/9 - AOI 2:30 | 2B 2T 156/706 | 11/7 - SHORT ITEMS OK TO SKIP KIT CLEAR 11/15 | 13 | 52 |  | Dorner Works LTD | 3445 Lake Eastbrook Blvd Se | Grand Rapids | MI
|  | 2022-11-23 | 111791 (10/28) | ROWC B100811 | 16 | L2 |  |  | 11/28H 20D | UPS GND | XRAY & SAVE IMAGES "PPO" PRESS FIT REQ - OK TO NOT INSTALL IF WE DO NOT HAVE A TOOL - NEED TO NOTIFY AA | 11/10 - BOT SIDE 6:00 11/10 - TOP SIDE 12:00 11/11 - AOI 12:00 | 1B 1T 48/936 | 10/28 - KIT CLEAR | 8 | 128 | X | Jefferson Labs | 12000 Jefferson Ave Ste 12 | Newport News | VA
|  | 2022-11-23 | 110203-2 (6/9) |  | 60 BAL |  |  |  | 2022-11-23 | FEDEX GND | DEPANEL *SPLIT SHIPMENT* OK TO RUN ALL **DO NOT SHIP EARLY** | NEED PROG 6/15 - TOP SIDE 6/17 - AOI | 1T | WILL CLEAR 6/9 - KIT CLEAR 6/10 | 4 | 240 |  | Frencken America Inc. | 22924 E Appleway Ave | Liberty Lake | WA
|  | 2022-11-22 | 114006 (11/14) | RONC B112985 | 10 | L1 |  |  | 11/30H 10D | UPS GND | X | 11/21 - TOP SIDE 10:00 11/21 - AOI 10:30 | 1T 5/26 | 11/14 - KIT CLEAR | 0 | 0 |  | HII Unmanned Systems, Inc | 3 HENRY DR | Pocasset | MA
|  | 2022-11-22 | 114026 (11/4) | RONC B102703 | 22 | L1 |  |  | 11/22 10D | UPS BLU | "U4" HEIGHT REQUIREMENT 0.320" MAX PER ECO #1 | 11/11 - BOT SIDE 10:00 11/11 - TOP SIDE 12:30 11/14 - AOI 10:00 | 1B 2T 110/462 | 11/4 - SHOULD CLEAR SOON 11/7 - ONLY SHORT ATTRICTION #8 11/8 - KIT CLEAR | 1 | 22 | X | General Digital | 60 Prestige Park Rd | East Hartford | CT
|  | 2022-11-22 | 111695-2 (11/9) | 2ND ARTICLE | 125 | L1 |  |  | 11/22 9D | FEDEX P | DEPANEL & SAND | 11/14 - BOT SIDE 12:00 11/16 - TOP SIDE 8:00 11/17 - AOI 12:00 | 2B 2T 123/423 | 11/4 - REAUDIT 11/9 - KIT CLEAR | 10 | 1250 | X | SILC Technologies, Inc. | Monrovia | CA | 91016
|  | 2022-11-22 | 114390-1 (11/17) | NEW | 20/59 | L3 |  |  | 11/22 2D | FEDEX P | **2 DAY TURN** DNI SMT ITEMS 2 & 42 ON QTY 20 ONLY - LOAD ON BAL QTY 39 | 11/18 - BOT SIDE 9:30 11/18 - TOP SIDE 10:30 11/18 - AOI 2:00 | 1B 1T 48/139 | 11/17 - MAY CLEAR 11/17 11/17 - SHORT #2 & #42 11/18 - KIT CLEAR (DNI ITEMS 2 & 42) | 15 | 300 |  | Atlas Devices | 21 Alpha Rd | Chelmsford | MA
|  | 2022-11-22 | 113426-2 (11/15) | RONC 112228 114025 | 1 | L3/HOLD |  |  | ??? 3D | FEDEX P | DEPANEL ** 3 DAY TURN** DO NOT SHIP MATL | RTR - WTG FOR 1 FAB | 1B 1T 72/254 | 11/17 - STILL SHORT 1 FAB 11/22 - TEAR DOWN & RE-AUDIT - XFER QTY 1 TO ANOTHER KIT | 21 | 0 |  | AVID Technologies | 2112 Case Pkwy Ste 1 | Twinsburg | OH
|  | 2022-11-21 | 113154 (11/7) | NEW | 120 | L3 |  |  | 11/22 10D | FEDEX P | "J4" LOAD PER ECO #3 - OPPOSIDE SIDE OF SILKSCREEN | 11/11 - TOP SIDE 6:00 11/11 - AOI 7:00 | 1T 22/35 | 11/7 - SHOULD CLEAR 11/8 | 15 | 1800 |  | Design Catapult, Inc. | 17361 NEWHOPE ST | Fountain Valley | CA
|  | 2022-11-21 | 113426-1 (11/15) | RONC 112228 114025 | 99/100 | L3 |  |  | 11/22* 3D | FEDEX P | DEPANEL ** 3 DAY TURN** DO NOT SHIP MATL | 11/10 - KIT RE-AUDIT WTG FOR STOCKROOM 11/17 - BOT SIDE 6:00 11/17 - TOP SIDE 10:30 11/17 - AOI 2:30 11/18 - 11/18 - 3 MORE BOARDS DONE | 1B 1T 72/254 | 11/9 - 20 BOARDS & PARTS USED FOR 114025 11/10 - FABS DUE 11/18 11/15 - SHORT 3 PARTS 11/16 - 96 FABS ARRIVED; PARTIAL SHORT 2 ITEMS 11/17 - 3 FABS ARRIVED | 21 | 2100 |  | AVID Technologies | 2112 Case Pkwy Ste 1 | Twinsburg | OH
|  | 2022-11-21 | 112127-2 (11/7) | 2ND ARTICLE | 43 | L3 |  |  | 11/21 10D | FEDEX P | DEPANEL XRAY & SAVE IMAGES NEED QR CODE FOR "J1" FAIR REQUIRED | 11/17 - TOP 9:00 11/17 - BACK 10:00 | 1T 8/10 | 11/7 - WAITING REAUDIT 11/7 - KIT CLEAR | 10 | 430 |  | Anderson Connectivity | 601 Atlantis Rd | Melbourne | FL
|  | 2022-11-21 | 112128-2 (11/7) | 2ND ARTICLE | 38 |  |  |  | 11/21 10D | FEDEX P | DEPANEL ***SHIP W/ 112127 XRAY & SAVE IMAGES NEED QR CODE FOR "J1" FAIR REQUIRED |  | T/H ONLY | 11/7 - KIT CLEAR | 12 | 456 |  | Anderson Connectivity | 601 Atlantis Rd | Melbourne | FL
|  | 2022-11-18 | 108879 (11/10) | NEW | 10 | L2 |  |  | 11/18 5D | FEDEX P | ***DEPANEL (GIVE TO TAD) (NOT ENOUGH MOUSE BITE HOLES - *NEED TO DREMMEL CUT & SAND) | 11/11 - BOT SIDE 12:00 11/12 - TOP SIDE 8:00 11/12 - AOI 2:00 | 1B 1T 43/1101 | 11/10 - FABS SHOULD ARRIVE 11/11 - KIT CLEAR | 62 | 620 | X | Phoenix Contact, Inc. | 586 Fulling Mill Rd | Middletown | PA
|  | 2022-11-17 | 112217-1 (11/11) | NEW FA | 4 | L3 |  |  | 11/18 5D | FEDEX P | DEPANEL | 11/15 - TOP SIDE 6:00 11/15 - AOI 8:00 | 1T 1/1 | 11/11 - KIT CLEAR (PREVIOUS FABS WRONG) | 1 | 4 |  | Tomahawk Robotics, LLC | 2326 Irwin St | Melbourne | FL
|  | 2022-11-17 | 112218-1 (11/11) | NEW FA | 4 | L3 |  |  | 11/18 5D | FEDEX P | DEPANEL | 11/15 - TOP SIDE 6:00 11/15 - AOI 8:00 | 1T 1/1 | 11/11 - KIT CLEAR (PREVIOUS FABS WRONG) | 1 | 4 |  | Tomahawk Robotics, LLC | 2326 Irwin St | Melbourne | FL
|  | 2022-11-17 | 108878 (11/4) | ROWC 104475 | 9 + 1 | L3/L2 |  |  | 11/18 3D | FEDEX P | DEPANEL **3 DAY TURN** | 11/7 - BOT SIDE 10:30 11/8 - TOP SIDE 8:00 11/15 - TOP SIDE 12:00 | 1B/1T 101/1331 | 11/4 - FABS DUE TODAY 11/4 - SHORT #69 OKAY TO SKIP 11/9 - 1 FAB DUE 11/10, 11/14 | 7 | 70 |  | Phoenix Contact, Inc. | 586 Fulling Mill Rd | Middletown | PA
|  | 2022-11-17 | 113292 (11/9) | NEW | 1 | L1 |  |  | 11/18 3D | UPS BLU | CLASS 3 | 11/9 - BOT SIDE 2:30 11/10 - TOP SIDE 8:00 11/10 - AOI 10:00 | 1B 2T 101/799 | 11/9 - SHOULD CLEAR SOON 11/9 - SHORT U2 & R6 OK TO SKIP 11/15 - KIT CLEAR | 6 | 6 |  | Renmark-Pacific Corporation | 2675 Skypark Dr Ste 103 | Torrance | CA
|  | 2022-11-17 | 113665-3 (10/17) | RONC 113064 | 100 | L3 |  |  | 11/17 SS | FEDEX P | NO MOUSE BITE HOLES - GIVE TO TAD TO DEPANEL BAR CODE LABELS REQ | 11/4 - BOT SIDE 1:30 11/8 - TOP SIDE 8:30 11/8 - AOI 2:00 | 1B 2T 62/444 | 10/17 - KIT CLEAR QTY 400 PARTIAL (250 LEFT) | 16 | 800 |  | Command Alkon, Inc. | 6750 Crosby Ct | Dublin | OH
|  | 2022-11-17 | 112505 (11/8) | RONC B108531 | 35 | L1 |  |  | 11/17 5D | FEDEX GND | DEPANEL ***"J5" DO NOT TRIM LEADS*** | 11/10 - BOT SIDE 10:00 11/10 - TOP SIDE 12:00 11/11 - AOI 10:00 | 1B 1T 46/164 | 11/8 - SHORT FAB DUE TOMORROW 11/10 - KIT CLEAR | 10 | 350 |  | Cardinal Peak, LLC | 1380 Forest Park Cir Ste 202 | Lafayette | CO
|  | 2022-11-16 | 113661 (11/2) | ROWC B102579 | 400 | L1 |  |  | 11/16 10D | UPS RED | DEPANEL | 11/4 - TOP SIDE 3:00 11/7 - AOI 12:30 | 2T 27/43 | 11/2 - KIT CLEAR | 0 | 0 |  | PetroPower LLC | 3003 E 37th St N | Wichita | KS
|  | 2022-11-16 | 114073 (11/9) | NEW | 52 | L1 |  |  | 11/16 5D | FEDEX P | X | 11/10 - TOP SIDE 8:00 11/10 - AOI 10:00 | 1T 30/87 | 11/9 - KIT CLEAR | 1 | 52 |  | INFICON Inc. | 2 Technology Pl | East Syracuse | NY
|  | 2022-11-15 | 111675-2 (11/7) | 2ND ARTICLE | 25 | L1 |  |  | 11/15 5D | UPS RED | DEPANEL & SAND *REFLOW MUST BE <240C | 11/8 - BOT SIDE 12:30 11/9 - TOP SIDE 7:30 11/9 - AOI 2:30 | 1B 2T 91/583 | 11/4 - REAUDIT 11/7 - SHORT #26 7 PIECES OK TO SKIP 11/8 -KIT CLEAR | 54 | 540 |  | Samtec | 645 Dawson Drive | Newark | DE
|  | 2022-11-15 | 113662 (11/1) | ROWC B102582 | 200 | L2 |  |  | 11/15 10D | UPS RED | DEPANEL | 11/4 - BOT SIDE 10:00 11/7 - TOP SIDE 8:00 11/8 - AOI 1:00 | 1B 2T 32/97 | 11/1 - FAB DUE TODAY 11/1 - KIT CLEAR | 7 | 1400 |  | PetroPower LLC | 3003 E 37th St N | Wichita | KS
|  | 2022-11-15 | 113440-2 (10/21) | RONC 112573 | 400 | L3 |  |  | 11/15* 10D | FEDEX P | SET VSCORE CUTTER DEPTH TO "5" MAX NOTES = SHIP QTY 300 ON A 5 DAY AND QTY 400 ON A 10 DAY, CAN BUILD QTY 700 ALL AT ONCE | 11/2 - TOP SIDE 10:00 11/3 - AOI 7:00 | 2T 22/50 | 10/21 - QTY 316 CLEAR 11/1 - KIT CLEAR | 10 | 3000 |  | Command Alkon, Inc. | 6750 Crosby Ct | Dublin | OH
|  | 2022-11-15 | 112600 (10/31) | NEW | 10 | L1 |  |  | 11/22 5D | FEDEX 2 DAY | *DO NOT DEPANEL* PCB PREBAKE REQ | 11/7 - BOT SIDE 12:30 11/8 - TOP SIDE 8:00 11/8 - AOI 12:30 | 1B 1T 75/678 | 10/31 - SHORT 3 ITEMS OK TO SKIP WAITING FOR ARRAY FILE 11/11 - SHORTAGES DUE 11/16 11/15 - KIT CLEAR | 3 | 30 |  | Ripple, LLC | 2056 S 1100 E | Salt Lake City | UT
|  | 2022-11-14 | 111560 (10/31) | NEW | 50 | L1 |  |  | 11/15* 9D | FEDEX P | DEPANEL | 11/4 - BOT SIDE 8:00 11/4 - TOP SIDE 10:30 | 1B 1T 34/234 | 10/31 - SHOULD CLEAR C14 NEEDS PARTS CF 11/2 - KIT CLEAR | 0 | 0 |  | Brooksee | 374 S 671 W | Pleasant Grove | UT
|  | 2022-11-14 | 113663 (10/31) | ROWC B102583 | 200 | L2 |  |  | 11/14 10D | UPS RED | DEPANEL | 11/2 - BOT SIDE 2:00 11/3 - AOI 1:30 | 1B 22/38 | 10/31 - KIT CLEAR | 14 | 2800 |  | PetroPower LLC | 3003 E 37th St N | Wichita | KS
|  | 2022-11-14 | 113424 (10/31) | NEW | 10 | L1 |  |  | 11/14 10D | FEDEX GND | CLASS 3 | 11/3 - TOP SIDE 1:30 11/4 - AOI 8:00 | 1T 1/1 | 10/31 - KIT CLEAR | 81 | 810 |  | Duotech Services Inc | 245 Industrial Park Rd | Franklin | NC
|  |  | 112217-2 (9/15) |  | 4 | L3 |  |  | 9/27 9/23 5D | FEDEX P | DEPANEL 11/11 - CANX THIS LINE - CREATED NEW LINE FOR RE-MAKE | 9/19 - TOP SIDE 6:00 HOLD 10:00 9/20 - OFF HOLD 3:45 9/21 - BACK 11:00 9/21 - HOLD (BAD FABS) | 1T 1/1 | KIT CLEAR 9/16 QTY 4 FA 11/11 - NEW FABS ISSUED - NEW LINE CREATED FOR SMT | 0 | 0 |  | Tomahawk Robotics, LLC | 2326 Irwin St | Melbourne | FL
|  |  | 112218-2 (9/16) |  | 4 | L3 |  |  | 9/27 9/23 5D | FEDEX P | DEPANEL 11/11 - CANX THIS LINE - CREATED NEW LINE FOR RE-MAKE | 9/19 - TOP SIDE 6:00 HOLD 10:00 9/20 - OFF HOLD 3:45 9/21 - BACK 11:00 9/21 - HOLD (BAD FABS) | 1T 1/1 | KIT CLEAR 9/16 QTY 4 FA 11/11 - NEW FABS ISSUED - NEW LINE CREATED FOR SMT | 0 | 0 |  | Tomahawk Robotics, LLC | 2326 Irwin St | Melbourne | FL
|  | CANX RE-MAKE | 112217-1 (9/15) |  | 4 | L3 |  |  | 9/27 9/23 5D | FEDEX P | DEPANEL 11/11 - CANX THIS LINE - CREATED NEW LINE FOR RE-MAKE | 9/19 - TOP SIDE 6:00 HOLD 10:00 9/20 - OFF HOLD 3:45 9/21 - BACK 11:00 9/21 - HOLD (BAD FABS) | 1T 1/1 | KIT CLEAR 9/16 QTY 4 FA 11/11 - NEW FABS ISSUED - NEW LINE CREATED FOR SMT | 0 | 0 |  | Tomahawk Robotics, LLC | 2326 Irwin St | Melbourne | FL
|  | CANX RE-MAKE | 112218-1 (9/16) |  | 4 | L3 |  |  | 9/27 9/23 5D | FEDEX P | DEPANEL 11/11 - CANX THIS LINE - CREATED NEW LINE FOR RE-MAKE | 9/19 - TOP SIDE 6:00 HOLD 10:00 9/20 - OFF HOLD 3:45 9/21 - BACK 11:00 9/21 - HOLD (BAD FABS) | 1T 1/1 | KIT CLEAR 9/16 QTY 4 FA 11/11 - NEW FABS ISSUED - NEW LINE CREATED FOR SMT | 0 | 0 |  | Tomahawk Robotics, LLC | 2326 Irwin St | Melbourne | FL
|  | CANX RE-MAKE | 105003-2 (6/24) |  | 20/50 | L1 / HOLD |  |  | ??? 11/1 10D | UPS RED | *DO NOT SHIP EARLY* MECH ASSY REQ INSP J4 AREA BEFORE SOLDERING SHIELD ***11/3 - JOB CANX - WILL NEED TO REMOVE PARTS & RUN NEW BOARDS 11/11 - JOB RE-KITTED FOR NEW RUN | 6/27 - BOT/TOP QTY 50 6/27 - AOI | 1B 1T | 6/21 - SMT CLEAR ONLY KIT CLEAR 10/19 10/26 - RECV ONLY 20 PCS OF D7 11/1 - CUSTOMER ISSUE 11/11 - NEW FABS RECVD FOR RE-MAKE (CANX THIS LINE & CREATED NEW LINE) | 4 | 80 | UPS RED | 21061 S Western Ave | Torrance | CA | 90501-1734
|  | 2022-11-11 | 110859-2 (10/27) | BAL | 120 | L3 |  |  | 11/11 10D | FEDEX P | DEPANEL | 11/1 - BOT SIDE 8:30 11/1 - TOP SIDE 1:00 11/4 - TOP SIDE 12:30 11/7 - AOI 10:30 | 1B 2T 43/265 | WILL CLEAR 10/28 10/28 - KIT CLEAR 11/2 - STENCIL ISSUE 7:00 | 11 | 1100 | AVID Technologies | 2112 Case Pkwy Ste 1 | Twinsburg | OH | 44087
|  | 2022-11-10 | 114025 (11/8) | RONC B112228 | *20 | L3 |  |  | 11/10 *1 | FEDEX P | DEPANEL ** 1 DAY TURN** DO NOT SHIP MATL (RAN QTY 20 FROM KIT 113426 - SHIP AS 114025) *RETURN KIT 113426 TO STOCKROOM FOR RE-AUDIT | 11/9 - BOT SIDE 7:30 11/9 - TOP SIDE 12:00 11/9 - AOI 2:30 | 1B 1T 72/254 | 11/8 - SHOULD CLEAR 11/9 11/9 - KIT CLEAR RAN QTY 20 FROM KIT 113426 | 21 | 420 | AVID Technologies | 2112 Case Pkwy Ste 1 | Twinsburg | OH | 44087
|  | 2022-11-09 | 112814 (10/28) | NEW | 100 | L1 |  |  | 11/11 10D | FEDEX GND | DEPANEL ***NO STAMPS OR LABELS ALLOWED ON BOARDS - "STAMP THE ARRAY FRAME & SAVE | 11/1 - TOP SIDE 11:00 11/2 - AOI 8:00 | 1T 33/102 | 10/28 - KIT CLEAR | 7 | 700 | Moxtek, Inc. | 452 W 1260 N | Orem | UT | 84057
|  | 2022-11-09 | 113647 (11/2) | NEW | 48 | L3/L2 |  |  | 11/9 5D | FEDEX GND | WAIVED SELECTIVE SOLDER REQ PER ECO #3 | 11/3 - BOT SIDE 9:30 11/3 - TOP SIDE 1:30 11/4 - AOI 10:00 | 1B 1T 31/118 | 11/2 - KIT CLEAR | 16 | 768 | Government Contracting Specialists, Inc. | 2455 South Rd | Poughkeepsie | NY | 12601
|  | 2022-11-09 | 112479 (10/19) | NEW | 50 | L1 |  |  | 11/9 9D | UPS GND | DEPANEL PRESS FIT REQ SERIAL #S ON CofC PER ECO 5 | 11/1 - BOT SIDE 7:00 11/1 - TOP SIDE 8:30 11/1 - AOI 11:00 | 1B 1T 32/139 | 10/19 - SMT CLEAR 10/27 - KIT CLEAR | 25 | 1250 | LKC Technologies | 2 Professional Dr Ste 224 | Gaithersburg | ND | 20879
|  | 2022-11-08 | 112722 (10/31) | NEW | 20 | L3 |  |  | 11/8 5D | FEDEX P | DEPANEL PER ECO #1 WAIVE ECO NOTE 4 | 11/2 - TOP SIDE 7:00 11/2 - AOI 10:00 | 2T 81/159 | 10/31 - SHORT R30 OK TO SKIP | 62 | 1240 | Rheem Manufacturing Company | 9855 Crosspoint Blvd Ste 114 | Indianapolis | IN | 46256
|  | 2022-11-07 | 114048 (11/3) | NEW | 120 | L3 |  |  | 11/8 3D | FEDEX P | *3 DAY TURN* | 11/3 - BOT SIDE 10:45 11/3 - TOP SIDE 12:00 11/3 - AOI 1:30 | 1B 1T 6/13 | 11/3 - KIT CLEAR | 0 | 0 | Deeplocal Inc. | 1601 Marys Ave | Sharpsburg | PA | 15215
|  | 2022-11-07 | 112513 (10/12) | RONC 108038 | 50 | L3 |  |  | 11/9 20D | FEEX G |  | 10/31 - BOT SIDE 12:00 11/1 - TOP SIDE 6:00 11/1 - AOI 8:30 | 1B 1T 32/117 | KIT CLEAR 10/12 | 0 | 0 | AR RF Microwave (ARI) | 160 Schoolhouse Rd | Souderton | PA | 18964
|  | 2022-11-07 | 111607-2 (10/24) | 2ND ART | 248 | L1 |  |  | 11/10 10D | UPS RED | CUST PROVIDED SAMPLE BOARD FOR REFERENCE - MUST RETURN TO CUST W/ KIT/MATL | 11/2 - BOT SIDE 8:00 11/3 - TOP SIDE 8:00 11/3 - AOI 1:30 | 1B 1T 27/53 | 10/24 - WILL CLEAR SOON 10/27 - KIT CLEAR | 4 | 992 | Swift Sensors | 4611 Bee Caves Rd | Austin | TX | 78746
|  | 2022-11-04 | 113382 (10/10) | NEW MATRIX | 50 | L3 |  |  | 11/7 10/24 9D | UPS GND | DEPANEL FIXTURE & SWAGING TOOL REQ | 10/13 - TOP SIDE 6:00 10/13 - AOI 7:00 | 1T 11/20 | KIT CLEAR 10/11 MATRIX JOB - NEEDED FIXTURE AND SWAGING TOOL | 11 | 550 | LKC Technologies | 2 Professional Dr | Gaithersburg | MD | 20879
|  | 2022-11-04 | 113665-2 (10/17) | RONC 113064 | 100 | L3 |  |  | 2022-11-04 | FEDEX P | NO MOUSE BITE HOLES - GIVE TO TAD TO DEPANEL BAR CODE LABELS REQ | 10/18 - BOT SIDE 6:00 10/18 - TOP SIDE 10:30 10/19 - QTY 50 DONE 10/24 - BOT SIDE 11:00 10/25 - TOP SIDE 11:00 10/26 - AOI 8:30 | 1B 2T 62/444 | 10/17 - KIT CLEAR QTY 400 PARTIAL | 16 | 800 | Command Alkon, Inc. | 6750 Crosby Ct | Dublin | OH | 43016
|  | 2022-11-04 | 111683 (10/21) | NEW | 100 | L3 |  |  | 11/4 10D | FEDEX P | DEPANEL | 10/28 - TOP SIDE 9:00 10/28 - AOI | 1T 33/167 | KIT CLEAR 10/21 | 9 | 900 | TMC / Technical Manufacturing Corp. | 15 Centennial Dr | Peabody | MA | 01960
|  | 2022-11-04 | 113515 (10/19) | NEW | 10 | L2 |  |  | 11/4 10D | FEDEX P | DEPANEL *RECV 7 PCS "U24" DAMAGED OK TO BTD | 10/27 - RTR 10/28 - BOT SIDE 9:00 10/28 - TOP SIDE 10:30 10/31 - AOI 12:00 | 1B/2T 88/801 | WIL CLEAR SOON 10/20 - RECV BEND LEADS KIT CLEAR 10/21 | 20 | 200 | Sonetics Corporation | 17600 Sw 65th Ave | Lake Oswego | OR | 97035
|  | 2022-11-04 | 113191 (10/19) | NEW | 2 | L2 |  |  | 11/4 11/3 10D | FEDEX GND | X 11/3 - AWAITING CUSTOMER REPLY REGARDING ISSUE 11/4 - ISSUE RESOLVED | 10/27 - BOT SIDE 8:30 10/27 - TOP SIDE 12:00 10/28 - AOI 9:00 | 1B 1T 103/674 | 10/19 - STOCKROOM LOOKING FOR PARTS KIT CLEAR 10/20 | 23 | 46 | Vista Photonics | 3655 Research Dr | Las Cruces | NM | 88003
|  | 2022-11-03 | 112710 (10/13) | NEW | 10 | L1 |  |  | 11/4 10D | FEDEX P | X | 10/20 - BOT SIDE 12:00 10/20 - TOP SIDE 2:30 10/21 - AOI 9:00 | 82/385 | 10/17 - INTERNAL CLEAR - SHORT ATTRITION KIT CLEAR 10/21 | 29 | 290 | ABB Inc. | 7051 Industrial Blvd | Bartlesville | OK | 74006
|  | 2022-11-03 | 113530 (10/21) | NEW | 60 | L3 |  |  | 11/4 10D | UPS RED | DEPANEL NOTE: PREVIOUS ISSUES @ L3/L4 & U11 | 10/26 - BOT SIDE 8:30 10/26 - TOP SIDE 10:00 10/27 - AOI 7:00 | 1B 1T 57/114 | KIT CLEAR 10/21 | 20 | 1200 | Alliance Technology, LLC. | 600 N Dekora Woods Blvd | Saukville | WI | 53080
|  | 2022-11-03 | 113267 (10/20) | NEW | 30 | L1 |  |  | 11/3 10D | UPS GND | DEPANEL | 10/26 - BOT SIDE 1:30 10/27 - TOP SIDE 7:00 10/27 - AOI 8:30 | 1B/1T 26/85 | KIT CLEAR 10/20 | 22 | 660 | Graph-Tech USA, LLC | 3200 N Kings Hwy | Fort Pierce | FL | 34951
|  | CANCELLED | 110721-2 (10/25) | 2ND RUN | 166/440 | L3 |  |  | ??? 10D | UPS RED | DEPANEL RUN PARTIAL QTY 234 SPEC CofC PER ECO 5 |  | 1B 2T | 8/12 - QTY 234 TOP SIDE CLEAR - QTY 440 BOT SIDE CLEAR 10/27 - AA REQUESTS TO CANCEL | 2 |  | Royal Circuit Solutions, Inc. |  | Hollister | CA | 95023-2535
|  | 2022-11-01 | 113166 (10/21) | RONC 113081 | 415 | L1 |  |  | 11/4 10D | FEDEX P | BAG SEALING NOT REQUIRED | 10/31 - TOP SIDE 11:00 10/31 - AOI 3:30 | 1T 3/2 | KIT CLEAR 10/21 | 0 | 0 | Industrialex Manufacturing | 6250 Joyce Dr, | Arvada | CO | 80403
|  | 2022-11-01 | 113167 (10/19) | RONC 113082 | 415 | L1 |  |  | 11/2 10D | FEDEX P | BAG SEALING NOT REQUIRED | 10/21 - TOP SIDE 10:00 10/21 - BACK 12:00 | 1T 2/3 | KIT CLEAR 10/19 | 0 | 0 | Industrialex Manufacturing | 6250 Joyce Dr, | Arvada | CO | 80403
|  | 2022-11-01 | 109791-3 (10/17) | 3RD RUN | 50 | L1 |  |  | 11/1 10D | FEDEX P | DEPANEL SHIPPED QTY 80 ON 8/23 | 8/23 - BOT DONE 10/26 - TOP SIDE 7:00 10/26 - AOI 8:30 | 1B 1T 27/49 | SHOULD CLEAR 10/17 KIT CLEAR 10/18 | 0 | 0 | McQ | 1545 Forbes St | Fredericksburg | VA | 22405-1606
|  | 2022-10-31 | 108881 (10/20) | NEW | 10 | L3 |  |  | 10/31 3D | FEDEX P | * 3 DAY TURN * DEPANEL (NOT ENOUGH MOUSE BITE HOLES - 1 BOARD DELAMED *NEED TO DREMMEL CUT & SAND) Hold Kit for next build to follow in 4-6 weeks | 10/26 - BOT RTR 10/27 - TOP SIDE 10:30 10/28 - BOT SIDE 6:00 10/28 - AOI | 1B/1T 48/1228 | FAB DUE 10/27 10/27- KIT CLEAR | 2 | 20 | Phoenix Contact, Inc. | 586 Fulling Mill Rd | Middletown | PA | 17057
|  | 2022-10-31 | 113823 (10/24) | NEW | 30 | L1 |  |  | 10/31 5D | UPS RED |  | 10/25 - BOT SIDE 11:30 10/25 - TOP SIDE 2:00 10/26 - AOI 7:00 | 1B 2T 22/29 | 10/24 - KIT CLEAR | 0 | 0 | Galvion | 160 Corporate Dr | Portsmouth | NH | 03801
|  | 2022-10-31 | 113077-2 | 2ND ART | 180 | L2 |  |  | 10/31 5D | FEDEX P | MUST SHIP 10/31 OR SOONER ***CUST DROPPED & DAMAGED BOARDS LAST TIME - EXTRA CARE WHEN PACKAGING & BOXING | 10/19 - BOT SIDE 9:00 10/21 - TOP SIDE 6:00 10/25 - AOI 12:00 | 1B 2T- 1:19 1:25 56/374 | 10/18 - KIT CLEAR (NOT REPORTED) | 56 | 10080 | Industrialex Manufacturing | 6250 Joyce Dr | Arvada | CO | 80403
|  | 2022-10-31 | 113454 (10/18) | NEW | 15 | L1 |  |  | 10/31 5D | FEDEX P | X | 10/24 - BOT SIDE 1:30 10/25 - TOP SIDE 9:30 10/25 - AOI 11:30 | 2B 2T 119/393 | FABS DUE 10/21 | 0 | 0 | Tomahawk Robotics, LLC | 1333 N Harbor City Blvd | Melbourne | FL | 32935
|  | 2022-10-31 | 112216 (10/3) |  | 650 | L1 |  |  | 10/31 20D | FEDEX P | DEPANEL XRAY & SAVE IMAGES *ADD FLUX TO "U401* PER ECO #3 | 10/5 - BOT SIDE 10:30 (START & STOP DUE TO SCHD) 10/13 - TOP SIDE 9:30 HOLD 1:30 10/14 - TOP SIDE 10:00 10/19 - AOI 3:00 | 2B 2T 84/373 M1 1:20 M2 1:20 | KIT CLEAR 10/3 (NOT REPORTED) | 0 | 0 | Sea Land Aire | 817 W High St | Jackson | MI | 49203
|  | 2022-10-28 | 112229 10/25 | ROWC B112096 | 30 | L2 |  |  | 10/28 3D | FEDEX P | * 3-DAY TURN * DO NOT SHIP MATL - MATL GOES INTO NEXT JOB 113426 | 10/25 - BOT SIDE 12:30 10/26 - TOP SIDE 12:00 10/27 - AOI 8:30 | 1B/1T 72/254 | KIT CLEAR 10/25 | 21 | 630 | AVID Technologies | 2112 Case Pkwy Ste 1 | Twinsburg | OH | 44087
|  | 2022-10-28 | 113646-1 (10/17) | NEW | 1 | L3 |  |  | ??? 5D | FEDEX 2 DAY | DEPANEL FAIR REQUIRED | 10/20 - BOT SIDE 12:30 10/20 - TOP SIDE 1:00 10/20 - AOI 3:30 | 1B 3T 156/691 | WILL CLEAR BY 10/19 SHORT 3 ITEMS - OK TO SKIP 10/25 - R473 IS DNI | 28 | 28 | Dorner Works LTD | 3445 Lake Eastbrook Blvd Se | Grand Rapids | MI | 49546
|  | 2022-10-27 | 113636 (10/18) | NEW | 5 | L1 |  |  | 10/28 5D | FEDEX GND | DEPANEL POST BAKE 30 MIN IF BOARDS ARE WASHED | 10/20 - BOT SIDE 7:00 10/20 - TOP SIDE 10:30 10/20 - AOI 2:00 | 1B 2T 139/517 | SHOULD CLEAR 10/19 - SHORT U57 - OK TO SKIP KIT CLEAR 10/21 | 43 | 215 | Quantel USA | 49 Willow Peak Dr | Bozeman | MT | 59718
|  | 2022-10-27 | 113459 (10/12) | NEW | 10 | L3 |  |  | 10/27 5D | FEDEX P | POSSIBLE EXPEDITE? DEPANEL | 10/17 - BOT RTR 10/20 - BOT SIDE 9:00 BOT DONE 12:30 10/21 - TOP SIDE 12:30 10/24 - AOI 11:00 | 2B -3:20 4:20 3T 262/1462 | 10/21 - KIT CLEAR | 17 | 170 | Beckman Coulter | 4310 N Harbor Blvd | Fullerton | CA | 92835
|  | 2022-10-26 | 113448 (10/13) | NEW | 8 |  |  |  | 10/27 10D | FEDEX GND | X | 10/15 - BOT SIDE 6:00 10/15- TOP SIDE 12:00 10/15 - AOI 2:30 | 1B 1T 45/558 | 10/13 - PARTIAL SHORT ITEM 11 | 29 | 232 | Government Contracting Specialists, Inc. | 2455 South Rd Bldg 12-3 | Poughkeepsie | NY | 12601
|  | 2022-10-26 | 112171 (10/13) | NEW | 10 | L1 |  |  | 10/26 10/27 10/24 5D | FEDEX P | DEPANEL | 10/18 - BOT SIDE STENCIL/GERBER ISSUE - NEW BOM 10/21 - BOT SIDE 9:00 10/21 - TOP SIDE 2:00 10/24 - AOI 10:00 | 1B 1T 85/535 | WTG PART C/F'S KIT CLEAR 10/17 10/19 HOLD | 6 | 60 | ABB, Inc. | 7051 Industrial Blvd | Bartlesville | OK | 74006
|  | 2022-10-26 | 113033 (10/11) | NEW | 100 | L1 |  |  | 10/26 9D | FEDEX P | DEPANEL SEE ECO FOR T/H DB SOCKET CONN | 10/13 - BOT SIDE 1:30 10/14 - TOP SIDE 7:00 10/14 - AOI 10:30 | 1B 1T 21/196 | WILL CLEAR 10/12, 10/13 KIT CLEAR 10/13 | 9 | 900 | TMC / Technical Manufacturing Corp. | 15 Centennial Dr | Peabody | MA | 01960
|  | 2022-10-26 | 113311 (10/20) | NEW | 3 | L1 |  |  | 10/27 5D | FEDEX P |  | 10/24 - BOT SIDE 10:15 10/24 - TOP SIDE 11:00 10/24 - AOI 1:30 | 1B 1T 62/519 | ONLY SHORT 1 PC - OK TO SKIP 10/21 - KIT CLEAR | 21 | 63 | Forza Ametek | 2947 Bradley St Ste 130 | Pasadena | CA | 91107
|  | 2022-10-26 | 112877 (10/19) | NEW | 100 | L3 |  |  | 10/27 5D | FEDEX P | X | 10/21 - TOP SIDE 6:00 10/21 - AOI 12:00 | 1T 24/42 | 10/19 - PART C/F'S ONLY KIT CLEAR 10/20 | 6 | 600 | Safe Grain, Inc. / Maxi-Tronic, Inc. | 417 Wards Corner Rd | Loveland | OH | 45140
|  | 2022-10-25 | 109349-2 (5/9) |  | '52 BAL |  |  |  | 10/25 9D | FEDEX GND | RUN PARTIAL QTY 128 SHIP 5/27 UPDATED ECO FOR T100/101 ORIENTATION | BACK | 1T | 5/9 - PARTIAL CLEAR QTY 128 SHORT TRANSFORMERS KIT CLEAR 10/12 | 15 |  | SyTech Corporation | 6121 Lincolnia Rd Suite 300A | Alexandria | VA | 22312-2764
|  | 2022-10-24 | 113665-1 (10/17) | RONC 113064 | 50 | L3 |  |  | 2022-10-24 | FEDEX P | QTY 50 DUE 10/24 CANT BE LATE! NO MOUSE BITE HOLES - GIVE TO TAD TO DEPANEL BAR CODE LABELS REQ | 10/18 - BOT SIDE 6:00 10/18 - TOP SIDE 10:30 10/19 - QTY 50 DONE 10/19 - AOI 9:00 | 1B 2T 62/444 | 10/17 - KIT CLEAR QTY 400 PARTIAL | 16 | 800 | Command Alkon, Inc. | 6750 Crosby Ct | Dublin | OH | 43016
|  | 2022-10-24 | 112781-2 (10/14) | 2ND W CHNG | 95 |  |  |  | ??? 5D | FEDEX GND | X | 10/15 - TOP SIDE 6:00 10/15 - AOI 2:30 | 1T 54/127 | 10/14 - PARTIAL SHORT - OK TO SKIP | 4 | 380 | StrideTech Medical | 6060 W 91st Ave | Westminster | CO | 80031
|  | 2022-10-21 | 113057 (10/17) | NEW | 6 | L2 |  |  | 10/24 5D | FEDEX P | BAR CODE LABELS REQ | 10/18 - BOT SIDE 11:00 10/19 - TOP SIDE 10/19 - AOI 11:30 | 1B 2T 103/542 | WILL CLEAR SOON - ONLY SHORT 2 ITEMS KIT CLEAR 10/18 | 0 | 0 | Artis, LLC | 4246 S Riverboat Rd Ste 250 | Taylorsville | UT | 84123
|  | 2022-10-21 | 113502 (10/19) | NEW | 6 | L3 |  |  | 10/24 10/26 5D | FEDEX GND | EXPEDITE - SHIP 10/24 | 10/20 - BOT SIDE 6:00 10/20 - TOP SIDE 9:00 | 1B 1T 65/634 | KIT CLEAR 10/19 | 9 | 54 | Flir | 3495 Kent Ave | West Lafayette | IN | 47906
|  | 2022-10-21 | 113501 (10/13) |  | 25 | L3 |  |  | 10/25 5D | FEDEX P | X | 10/17 - TOP SIDE 6:00 10/17 - AOI 2:30 | 2T 78/241 | 10/14 - SMT CLEAR KIT CLEAR 10/18 | 12 | 300 | Agate Technology | 41743 Enterprise Cir N | Temecula | CA | 92590
|  | 2022-10-20 | 113179 (10/6) | NEW | 21 | L2 |  |  | 10/20 9D | FEDEX P | DEPANEL | 10/14 - BOT SIDE 10:30 10/15 - TOP SIDE 6:00 10/15 - AOI 2:30 | 1B 1T 92/193 | KIT CLEAR 10/7 | 3 | 63 | Allocortech Inc. | 440 N Commerce Ave | Waynesboro | VA | 22980
|  | 2022-10-20 | 111301 (10/6) | NEW | 50 | L3 |  |  | 10/20 9D | FEDEX P | DEPANEL | 10/14 - BOT SIDE 10:30 10/15 - TOP SIDE 6:00 10/15 - AOI 2:30 | 1B 2T 105/285 | KIT CLEAR 10/7 | 7 | 350 | IonQ, Inc. | 4505 Campus Dr | College Park | MD | 20740
|  | 2022-10-20 | 112316 (9/13) |  | 50 | L2 |  |  | 10/20 10D | FEDEX P | X SET UP AND RUN BOT SIDE ONLY "JS1-4" SOME HAVE NO GUIDE PINS | 9/19 - BOT DONE 10/10 - S/U TOP SIDE RTR 10/13 - TOP SIDE 6:00 10/14 - AOI 10:00 | 1B 1T 66/370 | 9/13 - BOT CLEAR ONLY KIT CLEAR 10/6 | 2 | 100 | Protocol Insight, LLC | 5010 Centennial Blvd | Colorado Springs | CO | 80919
|  | 2022-10-20 | 111850-3 (8/25) |  | 50 | L3 |  |  | 10/20 9/26 10/20 | FEDEX P | BOXED UP IN SHIPPING DEPANEL *SPLIT SHIPMENT - DO NOT SHIP EARLY | 8/29 - BOT SIDE 9/1 - TOP QTY 50 9/16 - TOP SIDE 2:00 9/19 - AOI 9:30 9/22 - BOXED IN SHIPPING | 2B 2T 97/425 | KIT CLEAR 8/25 9/1 - RUNNING 50 THEN HOLD | 0 | 0 | Bridge Diagnostics, Inc. | 740 S Pierce Ave Ste 15 | Louisville | CO | 80027
|  | 2022-10-20 | 112827 |  | 20 |  |  |  | 2022-10-07 | UPS RED | X KIT RETURNED TO AA 10/20 | NOT RELEASED* |  | *10/19 - KIT CLEAR W/ MULTI SHORT STRIPS - ON HOLD FOR POSS KIT RETURN |  | 0 | Automation International | 1020 Bahls St | Danville | IL | 61832
|  | 2022-10-19 | 113498 (10/14) | NEW | 6 |  |  |  | 10/21 5D | FEDEX P | X | 10/15 - TOP SIDE 10/15 - AOI | 1T 2/140 | KIT CLEAR 10/14 | 2 | 12 | Artis LLC | 4246 S Riverboat Rd | Taylorsville | UT | 84123
|  | 2022-10-19 | 113277 (10/14) | ROWC 100732 | 2 |  |  |  | 10/21 5D | FEDEX P | CLASS 3 DEPANEL "J2-6" PRESS FIT LP_S2A REQ TORQUE SPEC | 10/15 - TOP SIDE 10/15 - AOI 2:30 | 1T 7/96 | KIT CLEAR 10/14 | 49 | 98 | Diversified Supply | 3901 Castle Hayne Rd | Castle Hayne | NC | 28429
|  | 2022-10-19 | 113148 (10/7) | RONC 112985 | 10 | L2 |  |  | 10/21 10D | UPS GND | X | 10/18 - TOP SIDE 6:00 10/18 - BACK 9:00 | 1T 5/26 | KIT CLEAR 10/7 | 0 | 0 | HII Unmanned Systems, Inc. | 3 Henry Dr | Pocasset | MA | 02559
|  | 2022-10-19 | 112847 (9/20) |  | 40 |  |  |  | 2022-10-25 | FEDEX P | T/H ONLY DEPANEL | 9/20 - BACK 10:00 | T/H | 9/20 - ONLY SHORT "J5" | 15 | 600 | Switched Source LLC | 200 W Adams St | Chicago | IL | 60606
|  | 2022-10-18 | 111607-1 (10/11) | NEW | 2 | L3 |  |  | 10/20 5D | UPS RED |  | 10/14 - BOT SIDE 6:00 10/14 - TOP SIDE 9:30 10/14 - AOI 10:00 | 1B 1T 27/53 | WILL CLEAR 10/12 - SHORT ITEM 12 - OK TO SKIP KIT CLEAR 10/13 | 4 | 8 | Swift Sensors | 4611 Bee Caves Rd | Austin | TX | 78746
|  | 2022-10-18 | 106336-2 (2/17) |  | 8 | L3 |  |  | 10/19 15D | FEDEX P | SHORT | 9/29 - BOT SIDE 6:00 9/29 - TOP SIDE 9:30 9/29 - AOI 2:30 | 2B 2T 109/747 | *2/17 - SHORT 9/26- SHORT U27 - OK TO SKIP | 8 | 64 | McQ | 1545 Forbes St | Fredericksburg | VA | 22405-1606
|  | 2022-10-18 | 113270 (10/10) | NEW | 3 |  |  |  | 10/18 3D | UPS RED | XRAY REQ DNI - U56, SW1, P14 | 10/12 - BOT SIDE 6:00 10/13 - TOP SIDE 10:00 10/13 - AOI 2:30 | 1B 2T 87/499 | NOT REPORTED (SHIPPING HOLD) KIT CLEAR 10/13 OFF SHIPPING HOLD 10/17 | 2 | 6 | Precision Graphics Inc | 21 County Line Rd | Somerville | NJ | 08876
|  | 2022-10-18 | 110275-2 (10/6) | ROWC 110167 | 3 | L1 |  |  | 10/18 3D | FEDEX P | DEPANEL / XRAY & SAVE IMAGES REQ | 10/6 - BOT SIDE 12:00 10/6 - TOP SIDE 2:00 10/6 - AOI 3:30 10/11 - 3 BAD CHASSIS | 1B 1T 90/888 | KIT CLEAR 10/6 USE MATL FROM 110167 | 6 | 18 | Telspan Data | 7002 S Revere Pkwy Ste 60 | Centennial | CO | 80112-6767
|  | 2022-10-17 | 109219-3 (6/15) | 22924 E Appleway Ave | 60 |  | 62 60 60 | 63 60 60 | 2022-10-17 | FEDEX P | DEPANEL - SPLIT SHIPMENTS - DO NOT SHIP EARLY | NEED PROG 6/17 - TOP SIDE 6/17 - AOI | 1T | KIT CLEAR 6/16 | 2 | Frencken America Inc. | Liberty Lake | WA | 99019-9514 | Frencken America, Inc, / Po Box 828 | 234304518
|  | 2022-10-17 | 111751-1ST (9/29) |  | 50/300 | L1 |  |  | 10/17* 10D | FEDEX P | DEPANEL (*10/4 - POWER OUT) | 10/3 - BOT SIDE 7:00 10/3 - TOP SIDE 9:00 10/4 - AOI 2:00 | 1B 2T 86/453 | 9/26 - FABS TO ROYAL FOR MOUSE BITE HOLES KIT CLEAR 10/3 | 139 | 6950 | Bose Corp. | 100 Mountain Rd | Framingham | MA | 01701
|  | 2022-10-17 | 110859-1 (9/16) |  | 100/220 | L3 |  |  | 10/17 10D | FEDEX P | *EXPEDITE SOONER* DEPANEL | 10/6 - BOT SIDE 6:00 10/6 - TOP SIDE 8:00 10/6 - AOI 2:30 | 1B 2T 43/265 | 9/16 - WILL CLEAR SOON - SOME MATL SHIPPED BACK BY MISTAKE KIT CLEAR 10/3 | 11 | 1100 | AVID Technologies | 2112 Case Pkwy Ste 1 | Twinsburg | OH | 44087
|  | 2022-10-14 | 112771 (10/6) | NEW | 75 | L1 |  |  | 10/14 5D | UPS RED | DEPANEL EPOXY REQ "Q1-Q34" CANNOT BE ROTATED MORE THAN +/-20 DEG PER ECO #3 | 10/6 - BOT SIDE 10:00 10/6 - TOP SIDE 1:00 (RUNNING SMALL BATCHES DUE TO H/L TIME) 10/12 - AOI 2:00 | 1B 1T 16/118 | KIT CLEAR 10/7 | 2 | 150 | Automated Packaging Systems Inc. | 10175 Philipp Pkwy | Streetsboro | OH | 44241
|  | 2022-10-14 | 105498 (10/11) | NEW | 5 | L2 |  |  | 10/14 3D | FEDEX P | * 3 DAY TURN * | 10/12 - BOT SIDE 6:00 10/12 - TOP SIDE 11:00 10/12 - AOI 2:00 | 2B 2T 137/853 | KIT CLEAR 10/11 | 14 | 70 | Vista Instrumentation LLC | 58 Lyme Bay | Columbia | SC | 29212
|  | 2022-10-14 | 113440-1 (10/6) | RONC 112573 | 300+400 | L3 |  |  | 10/17 5D | FEDEX P | SET VSCORE CUTTER DEPTH TO "5" MAX NOTES = SHIP QTY 300 ON A 5 DAY AND QTY 400 ON A 10 DAY, CAN BUILD QTY 700 ALL AT ONCE | 10/7 - TOP SIDE 10:00 10/7 - AOI 2:30 | 2T 22/50 | 10/6 - PARTIAL KIT CLEAR | 10 | 3000 | Command Alkon, Inc. | 6750 Crosby Ct | Dublin | OH | 43016
|  | 2022-10-13 | 112357-2 (9/13) SHIP AS 112357 |  | 97/ 243 BAL | L1 |  |  | 10/18 10D | FEDEX P | DEPANEL CLASS 3 (QUALITY ALERT FROM 110797 - DOUBLE CHECK FOR DAMAGED PARTS / EXPOSED COPPER) | 10/12 - BOT SIDE 8:30 10/12 - TOP SIDE 11:00 10/12 - AOI 1:30 | 1B 1T 39/71 | 9/13 - PARTIAL KIT CLEAR QTY 146 10/11 - PARTIAL CLEAR QTY 97 | 0 |  | Integra Life Sciences | 13900 Alton Pkwy | Irvine | CA | 92618
|  | 2022-10-13 | 112357-1 (9/13) SHIP AS 112357 |  | 146/243 | L2 |  |  | 9/27 10D | FEDEX P | ***HOLD*** WTG FOR MORE $ ***SHIP UNDER B112357*** DEPANEL CLASS 3 (QUALITY ALERT FROM 110797 - DOUBLE CHECK FOR DAMAGED PARTS / EXPOSED COPPER) | 9/15 - BOT SIDE 9:30 9/15 - TOP SIDE 10:00 9/15 - AOI 2:30 | 1B 1T 39/71 | 9/13 - PARTIAL KIT CLEAR QTY 146 | 0 | 0 | Integra Life Sciences | 13900 Alton Pkwy | Irvine | CA | 92618
|  | 2022-10-13 | 113037 (10/6) | NEW | 10 | L3 |  |  | 10/13 3D | UPS RED | * 3 DAY TURN * T/H LEADS TRIMMED TO 0.06" MAX EXTRA SERVICES - EXIT AUDIT TO BE PERFORMED | 10/10 - BOT SIDE 2:30 10/11 - TOP SIDE 9:30 10/11 - AOI 1:30 | 2B 3T 186/1126 | KIT INCOMING 10/6, 10/7 KIT CLEAR 10/10 | 14 | 140 | Righthand Technologies, Inc. | 7450 W Wilson Ave | Harwood Heights | IL | 60706
|  | 2022-10-13 | 113394 (10/3) | NEW | 5 | L3 |  |  | 10/13 3D | FEDEX P | * 3 DAY TURN * "NO VENDOR MARKINGS/STAMPS ALLOWED" | 10/10 - BOT SIDE 6:00 10/10 - TOP SIDE 10:30 10/10 - AOI 2:30 | 1B 2T 91/583 | 10/3 - ONLY SHORT ATTRITION 10/6 - MATL CLEAR BUT WTG ARRAY FILE KIT CLEAR 10/10 | 45 | 225 | John Hopkins University Applied Physics La | 11100 Johns Hopkins Rd | Laurel | MD | 20723
|  | 2022-10-13 | 112992 (9/29) |  | 9 |  |  |  | 10/13 10D | FEDEX P | DEPANEL HEAT SINK & THERMAL GREASE REQ | 9/30 - BACK | 1T 28/59 | KIT CLEAR 9/29 | 35 | 315 | Industrialex Manufacturing | 6250 Joyce Dr | Arvada | CO | 80403
|  | 2022-10-13 | 112772-2 (10/5) |  | 1 | L1 |  |  | ??? 5D | UPS RED | DEPANEL "Q1-Q34" CANNOT BE ROTATED MORE THAN +/-20 DEG PER ECO #3 | 10/5 - BOT SIDE 10:30 10/5 - TOP SIDE 1:30 10/6 - AOI 10:00 | 1B 1T 10/135 | KIT CLEAR 10/5 10/12 - LINE SHORT 3 PCS | 35 | 35 | Automated Packaging Systems Inc. | 10175 Philipp Pkwy | Streetsboro | OH | 44241
|  | 2022-10-12 | 113408 (10/5) | NEW | 25 | L1 |  |  | 10/12 2D | FEDEX P | **2 DAY TURN** DEPANEL | 10/11 - BOT SIDE 7:00 10/11 - TOP SIDE 10:30 10/11 - AOI 2:30 | 2B 1T 109/408 | FABS DUE 10/6, 10/7 | 0 | 0 | Durbin Group | 10950 Pierson Dr | Fredericksburg | VA | 22408
|  | 2022-10-12 | 112782 (10/6) | NEW | 3 | L1 |  |  | 10/12 5D | FEDEX P | ***EXPEDITE*** CLASS 3 SHIP EARLY!!! CofC REQ SER #S | 10/10 - TOP SIDE 10:30 10/10 - BOT SIDE 1:30 | 1B 1T 76/602 | KIT CLEAR 10/6 | 34 | 102 | Aeronix, Inc. | 777 Lowndes Hill Rd Bldg 3 Ste 160 | Greenville | SC | 29607
|  | 2022-10-12 | 113064 (9/22) R112573 | NEW | 40 | L2 |  |  | 10/12 3D 5D | FEDEX GND | * 3 DAY TURN * NO MOUSE BITE HOLES - GIVE TO TAD TO DEPANEL | 10/7 - BOT SIDE 6:00 10/7 - TOP SIDE 8:00 10/7 - AOI 1:30 | 1B 2T 62/444 | 20+ ITEMS HAVE MULTIPLE STRIPS - BTD POSSIBLE KIT CLEAR 10/7 - BTD | 16 | 640 | Command Alkon Inc. | 6750 Crosby Ct | Dublin | OH | 43016
|  | 2022-10-12 | 112772-1 (10/5) |  | 75 | L1 |  |  | 10/12 5D | UPS RED | DEPANEL "Q1-Q34" CANNOT BE ROTATED MORE THAN +/-20 DEG PER ECO #3 | 10/5 - BOT SIDE 10:30 10/5 - TOP SIDE 1:30 10/6 - AOI 10:00 | 1B 1T 10/135 | KIT CLEAR 10/5 | 35 | 2625 | Automated Packaging Systems Inc. | 10175 Philipp Pkwy | Streetsboro | OH | 44241
|  | 2022-10-12 | 113077-1 (10/3) |  | 5 | L1 |  |  | 10/12 10/11* 5D | FEDEX P | X (*10/4 - POWER OUT) | 10/5 - BOT SIDE 7:00 10/5 - TOP SIDE 9:00 10/5 - AOI 10:00 | 1B 2T 56/374 | KIT CLEAR 10/4 | 54 | 270 | Industrialex Manufacturing | 6250 Joyce Dr | Arvada | CO | 80403
|  | 2022-10-11 | 113172 (9/30) |  | 10 | L3 |  |  | 10/11 10/10* 5D | FEDEX P | DEPANEL (*10/4 - POWER OUT) | 10/5 - BOT SIDE 9:30 10/5 - TOP SIDE 12:00 10/5 - AOI 2:30 | 1B/1T 76/416 | KIT CLEAR 10/3 | 72 | 720 | Applied Radar, Inc. | 315 Commerce Park Rd | North Kingstown | RI | 02852
|  | 2022-10-11 | 112598 (9/28) |  | 25 | L2 / L3 |  |  | 10/11 5D | FEDEX P | *DO NOT DEPANEL* (10/4 - POWER OUT) | 9/29 - BOT SIDE 12:30 10/3 - TOP SIDE 11:00 10/4 - AOI 1:00 | 2B 2T 166/1023 | 9/28 - SHORT ITEM 3 QTY 108/BOARD ITEM 3 EXACT QTY KIT CLEAR 10/4 | 13 | 325 | Ripple, LLC | 2056 S 1100 E | Salt Lake City | UT | 84106
|  | 2022-10-11 | 110275-1 (10/6) | ROWC 110167 | 9 | L1 |  |  | 10/11 3D | FEDEX P | DEPANEL / XRAY & SAVE IMAGES REQ | 10/6 - BOT SIDE 12:00 10/6 - TOP SIDE 2:00 10/6 - AOI 3:30 | 1B 1T 90/888 | KIT CLEAR 10/6 USE MATL FROM 110167 | 6 | 54 | Telspan Data | 7002 S Revere Pkwy Ste 60 | Centennial | CO | 80112-6767
|  | 2022-10-10 | 113081 (10/3) |  | 160 | L2 |  |  | 10/11 5D | FEDEX P | BAG HEAT SEALING REQ??? | 10/5 - HAND LOAD 10/5 - BACK 2:30 | 1T 2/3 | KIT CLEAR 10/4 | 0 | 0 | Industrialex Manufacturing | 6250 Joyce Dr | Arvada | CO | 80403
|  | 2022-10-10 | 113082 (10/3) |  | 160 | L2 |  |  | 10/10 5D | FEDEX P | BAG HEAT SEALING NOT REQUIRED | 10/5 - HAND LOAD 10/5 - AOI 9:00 | 1T 2/3 | KIT CLEAR 10/3 | 0 | 0 | Industrialex Manufacturing | 6250 Joyce Dr | Arvada | CO | 80403
|  | 2022-10-10 | 112801 (10/10 5D |  | 50 |  |  |  | 2022-10-10 | FEDEX GND | T/H ONLY | 10/3 - BACK |  | KIT CLEAR 10/3 | 33 | 1650 | First Alert | 3901 Liberty St | Aurora | IL | 60504
|  | 2022-10-10 | 112553 (9/26) |  | 60 | 96 |  |  | 10/10 10D | UPS RED | DEPANEL PREVIOUS ISSUES @ L3/L4 & U11 | 9/28 - BOT SIDE 6:00 9/28 - TOP SIDE 10:00 9/28 - AOI 2:00 | 1B 1T 57/114 | KIT CLEAR 9/26 | 20 | 1200 | Alliance Technology, LLC. | 600 N Dekora Woods Blvd | Saukville | WI | 53080
|  | 2022-10-10 | 108431 (9/12) |  | 62 | L2 |  |  | 10/10 20D | UPS 3DAY | X | 9/13 - BOT SIDE 12:00 9/13 - BOT DONE 2:30 9/13 - SCHD HOLD 9/16 - TOP SIDE 6:00 9/16 - AOI 2:30 | 1B 2T 106/341 | KIT CLEAR 9/12 | 12 | 744 | Coastal Designs, LLC | 22 Jordan Cove Rd | Waterford | CT | 06385
|  | 2022-10-07 | 111675-1 (10/3 |  | 10 / 25 | L2 |  |  | 10/10 10/6* 3D | UPS RED | ***SHIP PARTIAL ON 10/7*** * 3 DAY TURN * DEPANEL & SAND *REFLOW MUST BE <240C (*10/4 - POWER OUT) | 10/4 - BOT SIDE 6:00 10/4 - TOP SIDE 2:00 10/5 - AOI 9:00 | 1B 2T 91/583 | KIT CLEAR 10/3 | 54 | 540 | Samtec | 645 Dawson Drive | Newark | DE | 19713
|  | 2022-10-07 | 112443 (9/30) |  | 30 | L1 |  |  | 10/7 5D | FEDEX GND | X | 9/30 - TOP SIDE 12:00 9/30 - AOI 2:00 | 1T 8/244 | KIT CLEAR 9/30 | 66 | 1980 | First Alert | 3901 Liberty St | Aurora | IL | 60504
|  | 2022-10-07 | 100606-6 (7/15) |  | 13 BAL | L2B / L3T |  |  | 2022-10-07 | #VALUE! | *G5A-H & G2A-H NEW PROCESS - NEED QA INSP 100% - NO SOLDER ALLOWED ON COIL **J1A-H NO EXCESS SOLDER ALLOWED ***THIS QTY 13 WILL USE NEW G1A-H (WHITE) | 7/19 - BOT SIDE 7/25 - BOT DONE 8/24 - TOP 1ST ART 8/26 - COUNT 108 | 2B 3T 238/ 3746 | 7/15 - RELEASED BOT ONLY 8/23 - TOP SET UP | 8 | 104 | University of Oklahoma | 3190 Monitor Ave Rm 0220 | Norman | OK | 73019-5004
|  | 2022-10-07 | 110991 (9/13) |  | 500 | L1 |  |  | 10/7 10D | UPS BLU |  | 9/16 - BOT 1ST 10:00 9/16 - SCHD HOLD 9/23 - BOT BAL 3:00 9/26 - TOP SIDE 11:00 9/27 - AOI 2:00 | 1B 1T 41/112 | 9/13 - PARTIAL CLEAR QTY 246 KIT CLEAR 9/23 | 7 | 3500 | Biomeme, Inc. | 401 N Broad St Suite 222 | Philadelphia | PA | 19108-1001
|  | 2022-10-06 | 112881-1 (9/20) |  | 1 | L3 |  |  | 10/6 5D | FEDEX GND | DEPANEL | 9/30 - BOT SIDE 8:00 9/30 - TOP SIDE 10:30 9/30 - AOI 2:30 | 2B 2T 151/707 | COULD CLEAR 9/22 KIT CLEAR 9/29 | 13 | 13 | Dorner Works LTD | 3445 Lake Eastbrook Blvd Se | Grand Rapids | MI | 49546
|  | 2022-10-06 | 112128-1 (9/23) |  | 2 |  |  |  | 10/6 5D | FEDEX P | T/H ONLY DEPANEL XRAY & SAVE IMAGES NEED QR CODE FOR "J1" FAIR REQUIRED | T/H ONLY |  | 9/23 - ONLY SHORT C4, U1 & T1 KIT CLEAR 9/29 | 12 | 24 | Anderson Connectivity | 601 Atlantis Rd | Melbourne | FL | 32904
|  | 2022-10-06 | 112127-1 (9/19) |  | 2 |  |  |  | 10/6 5D | FEDEX P | DEPANEL XRAY & SAVE IMAGES NEED QR CODE FOR "J1" FAIR REQUIRED | 9/20 - TOP SIDE 7:00 9/20 - AOI 8:00 | 1T 8/10 | 9/19 - SMT CLEAR KIT CLEAR 9/29 | 10 | 20 | Anderson Connectivity | 601 Atlantis Rd | Melbourne | FL | 32904
|  | 2022-10-05 | 113150 (9/29) |  | 25 | L1 |  |  | 10/7 5D | FEDEX P | DEPANEL | 9/29 - TOP SIDE 10:00 9/30 - AOI 1:00 | 1T 54/198 | FABS DUE 9/30 KIT CLEAR 9/30 | 23 | 575 | Lab37 | 200 Commonwealth Dr | Warrendale | PA | 15086
|  | 2022-10-05 | 111754-2ND (9/27) |  | 6 | L2 |  |  | 10/7 5D | FEDEX P | 2ND ARTICLE CLASS 3 ***NOTIFY ASAP IF ANY SHORTAGES*** | 9/29 - BOT SIDE 6:00 9/29 - BOT DONE 11 9/30 - TOP SIDE 8:00 9/30 - AOI 11:00 | 1B 1T | COULD CLEAR 9/28 EOD KIT CLEAR 9/29 | 38 | 228 | Parker Hannifin Corp | 1390 Highland Rd E | Macedonia | OH | 44056
|  | 2022-10-05 | 108372 (9/20) |  | 20 | L3 |  |  | 10/5 10D | UPS GND | IF WASH - BOARDS REQ POST BAKE FOR 30 MIN | 9/27 - TOP SIDE 6:00 9/27 - AOI 9:30 | 2T 93/347 | KIT CLEAR 9/21 | 55 | 1100 | RCH Associates, Inc | 6111 Southfront Rd Suite C | Livermore | CA | 94551-5135
|  | 2022-10-05 | 107821 (9/13) |  | 34 | L2 |  |  | 10/5 10D | FEDEX P | DEPANEL | 9/23 - BOT SIDE 6:00 9/23 - TOP SIDE 9:00 9/23 - AOI 11:00 | 1B 1T 1/31 | 9/13 - SMT CLEAR KIT CLEAR 9/21 | 33 | 1122 | Scientific Research Corporation | 2300 Windy Ridge Pkwy Se | Atlanta | GA | 30339
|  | 2022-10-05 | 113094 (9/26) |  | 10 | L1 |  |  | 10/5 10/4* 5D | FEDEX P | SEVERAL ITEMS BTD 9/29 - BAT HOLDER GUIDE PIN ISSUE - DNI (*10/4 - POWER OUT) | 9/28 - BOT SIDE 8:00 9/29 - TOP SIDE 7:00 9/29 - TOP HOLD 12:30 9/29 - AOI 3:30 | 2B 2T 133/861 | 9/26 - ONLY SHORT 1 PART & PART C/F'S | 11 | 110 | Pollen Mobile, LLC | 1186 Folsom St | San Francisco | CA | 94103
|  | 2022-10-03 | 112776-RWK (9/28) | 740 S Pierce Ave Ste 15 | 12 | L3 |  |  | 2022-10-04 | FEDEX SAV | PAID REWORK | 9/28 - BACK |  | KIT CLEAR 9/28 |  | Bridge Diagnostics, Inc. | Louisville | CO | 80027
|  | 2022-10-03 | 111470-1 (9/20) | 4 Constitution Way | 10 | L1 / L2 |  |  | 10/4 10D | FEDEX P | DEPANEL NEED TO LOAD F1 FUSE INTO HOLDER F1A | 9/23 - TOP SIDE 10:00 9/23 - AOI 2:00 | 3T 151/699 | KIT CLEAR 9/20 QTY 10 | 9 | Servomex, Inc. | Woburn | MA | 1801
|  | 2022-10-03 | 112864 (9/15) | 818 W Diamond Ave | 50 | L3 |  |  | 10/3 10D | FEDEX GND | X | 9/21 - BOT SIDE 11:00 9/23 - TOP SIDE 6:00 9/23 - AOI 12:00 | 1B 1T 69/300 | SHOULD CLEAR 9/16 KIT CLEAR 9/19 | 29 | GL Communications | Gaithersburg | MD | 20878 | 3rd Floor
|  | 2022-09-30 | 113279 (9/28) | 480 Springpark Pl Ste 1000 | 150 |  |  |  | 10/4 3D | FEDEX P | * 3 DAY TURN * T/H ONLY | 9/28 - BACK |  | KIT CLEAR 9/28 | 24 | Artis, LLC | Herndon | VA | 20170
|  | 2022-09-30 | 112781-1 (9/21) | 6060 W 91st Ave | 5 | L2 |  |  | 9/30 9/30* 5D | FEDEX GND | X | 9/22 - TOP SIDE 3:00 9/23 - AOI 10:00 | 1T 52/125 | 9/21 - SMT CLEAR / WILL CLEAR 9/22 EOD SHORT J2 - DUE 9/29 KIT CLEAR 9/29 | 6 | StrideTech Medical | Westminster | CO | 80031
|  | 2022-09-30 | 112433 (9/26) | 100 Research Dr | 300 | L2 / L3 |  |  | 9/30 4D | FEDEX P | DEPANEL | 9/27 - BOT SIDE 6:00 9/28 - TOP SIDE 12:00 9/28 - AOI 1:30 | 1B 1T 31/48 | KIT CLEAR 9/26 | 0 | Ascent AeroSystems | Wilmington | MA | 01887
|  | 2022-09-30 | 100606-5 (7/15) | 3190 Monitor Ave Rm 0220 | 87 | L2B / L3T |  |  | 2022-09-30 | #VALUE! | *G5A-H & G2A-H NEW PROCESS - NEED QA INSP 100% - NO SOLDER ALLOWED ON COIL **J1A-H NO EXCESS SOLDER ALLOWED ***LAST ASSY'S W/ G1A-H (SILVER) | 7/19 - BOT SIDE 7/25 - BOT DONE 8/24 - TOP 1ST ART 8/26 - COUNT 108 | 2B 3T 238/ 3746 | 7/15 - RELEASED BOT ONLY 8/23 - TOP SET UP | 8 | University of Oklahoma | Norman | OK | 73019-5004 | Attn: Redmond Kelley | 749026308
|  | 2022-09-29 | 112480 (9/15) | 21 County Line Rd | 50 |  |  |  | 9/29* 10D 5D | UPS RED | T/H ONLY *EXPEDITE PARTIAL* | 9/15 - BACK |  | PARTIAL CLEAR KIT CLEAR 9/15 | 100 | Precision Graphics Inc | Somerville | NJ | 08876
|  | 2022-09-29 | 112985 (9/23) | 3 Henry Dr | 10 | L2 |  |  | 10/7 10D | UPS GND | X | 9/28 - TOP SIDE 6:00 9/28 - AOI 8:00 | 1T 5/26 | KIT CLEAR 9/23 | 0 | HII Unmanned Systems, Inc. | Pocasset | MA | 02559 | Attn: Vito/Dusty
|  | 2022-09-28 | 107816 (9/14) | 2300 Windy Ridge Pkwy Se | 3 | L2 |  |  | 9/28 10D | FEDEX P |  | 9/19 - BOT SIDE 11:30 9/19 - TOP SIDE 1:30 9/20 - AOI 8:00 | 1B 1T 53/792 | KIT CLEAR 9/14 | 108 | Scientific Research Corporation | Atlanta | GA | 30339 | Attn bthurmond Ste 400 S
|  | 2022-09-27 | 112810 (9/20) | 125 North Drive | 125 | L1 |  |  | 9/27 5D | FEDEX P | DEPANEL | 9/22 - BOT SIDE 1:30 9/22 - AOI | 1B 10/28 | KIT CLEAR 9/20 BUT ON SHIPPING HOLD | 0 | Kopin Corporation | Westborough | MA | 01581
|  | 2022-09-27 | 112663 (9/19) | 7 Loveton Cir | 75 | L2 |  |  | 9/27 5D | FEDEX P | DEPANEL | 9/20 - BOT SIDE 8:00 9/21 - TOP SIDE 8:00 9/21 - AOI 2:30 | 1B 1T 90/320 | KIT CLEAR 9/19 | 8 | Becton Dickinson | Sparks Glencoe | MD | 21152 | attn: Andrea SCherz
|  | 2022-09-27 | 113038 (9/22) | 405 Bay Dr | 40 | L1 |  |  | 9/27 3D | FEDEX P | * 3 DAY TURN *DEPANEL | 9/22 - BOT SIDE 3:00 9/23 - AOI 9:00 | 1B 1T | KIT CLEAR 9/22 (NOT REPORTED) | 11 | Blueline Sensors LLC | Stevensville | MD | 21666
|  | 2022-09-26 | 111875 | 8108 Cleburne Ct | 5 |  |  |  | 2022-09-16 | FEDEX P | PAID RWK |  |  |  |  | LMA Technologies, LLC | Willow Spring | NC | 27592
|  | 2022-09-26 | 112580 (9/20) | 100 Research Dr | 250 | L1 |  |  | 9/27 5D | FEDEX P | X | 9/21 - BOT SIDE 7:00 9/21 - BACK 10:00 | 1B 4/4 | KIT CLEAR 9/20 | 0 | Ascent AeroSystems | Wilmington | MA | 01887
|  | 2022-09-26 | 112228 (9/2) | 2112 Case Pkwy Ste 1 | 20 | L1 |  |  | 9/26 3D | FEDEX P | *EXPEDITE* MATL FROM 110296 | NEED PROG RTR | 1B 1T 72/254 | SHOULD CLEAR 9/21 | 21 | AVID Technologies | Twinsburg | OH | 44087 | AVID Technologies,INC
|  | 2022-09-26 | 112809 (9/19) | 6060 W 91st Ave | 200 | L3 |  |  | 9/26 5D | FEDEX P |  | 9/21 - TOP SIDE 6:00 9/21 - AOI 9:00 | 1T 14/17 | KIT CLEAR 9/19 | 1 | StrideTech Medical | Westminster | CO | 80031
|  | 2022-09-26 | 112758 (9/19) | 21719 84th Ave S | 8 | L1 |  |  | 9/26 5D | FEDEX P | DEPANEL XRAY & SAVE IMAGES | 9/19 - TOP SIDE 1:30 9/19 - AOI 3:30 | 1T 21/243 | KIT CLEAR 9/19 | 142 | Blue Origin, LLC | Kent | WA | 98032 | Attn: Richard Garcia
|  | 2022-09-24 | 112750-2 (9/16) | 900 Convention Center Blvd | 405 | L1 / L3 |  |  | 9/24 9/23 5D | FEDEX P | *EXPEDITE QTY 45 SHIP 9/23 BAL 9/24 DEPANEL C9,C10.C4 WRONG SIZE 402 & X1 WRONG PART | 9/19 - TOP SIDE 7:00 9/19 - TOP SIDE 11:00 HOLD WRONG PARTS 9/20 - BOT SIDE 10:30 (HOLD) 9/21 - TOP SIDE 2:00 | 2B 1T 27/54 | KIT CLEAR 9/16 ***RUN TOP SIDE 1ST | 8 | Autodesk, Inc. | New Orleans | LA | 70130
|  | 2022-09-23 | 112096 (9/20) | 2112 Case Pkwy Ste 1 | 35 | L1 |  |  | 9/23 3D | FEDEX P | *EXPEDITE* MATL FROM 112228 *RUN 1ST* | RTR | 1B 1T 72/254 | SHOULD CLEAR 9/21 | 21 | AVID Technologies | Twinsburg | OH | 44087
|  | 2022-09-23 | 112421 (9/9) | 22 Bedford St | 200 | L1 |  |  | 9/23 10D | FEDEX P | DEPANEL 9/21 - 1 BOARD DAMAGED FROM DEPANEL - NEED TO RE-RUN 1 EXTRA | 9/15 - BOT HOLD - ITEM 12 WRONG PART 9/16 - BOT SIDE 11:30 9/16 - TOP SIDE 1:00 9/16 - AOI - 3:30 | 1B 1T 23/48 | KIT CLEAR 9/9 | 4 | Open Source Instruments Inc | Waltham | MA | 02453 | Unit 4 Attention: Kevan Hashemi
|  | 2022-09-23 | 112750-1 (9/16) | 900 Convention Center Blvd | 45 | L1 / L3 |  |  | 9/23 9/23 5D | FEDEX P | *EXPEDITE QTY 45 SHIP 9/23 BAL 9/24 DEPANEL C9,C10.C4 WRONG SIZE 402 & X1 WRONG PART | 9/19 - TOP SIDE 7:00 9/19 - TOP SIDE 11:00 HOLD WRONG PARTS 9/20 - BOT SIDE 10:30 (HOLD) 9/21 - TOP SIDE 2:00 | 2B 1T 27/54 | KIT CLEAR 9/16 ***RUN TOP SIDE 1ST | 8 | Autodesk, Inc. | New Orleans | LA | 70130
|  | 2022-09-23 | 100606-4 (7/15) | 3190 Monitor Ave Rm 0220 | 70 | L2B / L3T |  |  | 2022-09-23 | #VALUE! | *G5A-H & G2A-H NEW PROCESS - NEED QA INSP 100% - NO SOLDER ALLOWED ON COIL **J1A-H NO EXCESS SOLDER ALLOWED | 7/19 - BOT SIDE 7/25 - BOT DONE 8/24 - TOP 1ST ART 8/26 - COUNT 108 | 2B 3T 238/ 3746 | 7/15 - RELEASED BOT ONLY 8/23 - TOP SET UP | 8 | University of Oklahoma | Norman | OK | 73019-5004 | Attn: Redmond Kelley | 749026308
|  | 2022-09-22 | 112461 (9/14) | 2112 Case Pkwy Ste 1 | 25 | L2 / L3 |  |  | 9/22 9/23 5D | FEDEX P | *EXPEDITE 1 DAY EARLY | 9/19 - BOT SIDE 6:00 9/19 - TOP SIDE 11:00 9/20 - AOI 8:00 | 1B 1T 71/381 | FABS DUE 9/15 KIT CLEAR 9/16 | 22 | AVID Technologies | Twinsburg | OH | 44087 | AVID Technologies,INC
|  | 2022-09-22 | 111850-2 (8/25) | 740 S Pierce Ave Ste 15 | 50 | L3 |  |  | 2022-09-22 | FEDEX P | DEPANEL *SPLIT SHIPMENT - DO NOT SHIP EARLY | 8/29 - BOT SIDE 9/1 - TOP QTY 50 9/16 - TOP SIDE 2:00 9/19 - AOI 9:30 | 2B 2T 97/425 | KIT CLEAR 8/25 9/1 - RUNNING 50 THEN HOLD | 0 | Bridge Diagnostics, Inc. | Louisville | CO | 80027
|  | 2022-09-21 | 109892 (9/9) | 2300 Windy Ridge Pkwy Se | 3 | L2 |  |  | 9/26 10D | FEDEX P | DEPANEL 9/12 "U4" IS DNI | 9/15 - BOT SIDE 9:30 9/16 - TOP SIDE 6:00 9/16 - AOI 8:00 | 1B 1T 23/104 | 9/9 - ONLY SHORT U4 - OK TO SKIP KIT CLEAR 9/19 | 22 | Scientific Research Corporation | Atlanta | GA | 30339 | Attn bthurmond Ste 400 S
|  | 2022-09-21 | 112502-2 (9/15) | 7 Loveton Cir | 3 BAL | L1 |  |  | 9/22 5D | FEDEX P | RUN & SHIP QTY 37 ***MISSING MOUSE BITE HOLES - TAD WILL DEPANEL | 9/15 - BOT SIDE 3:30 9/16 - TOP SIDE 9:00 9/16 - AOI 10:30 | 1B 2T 118/447 | SHOULD CLEAR SOON - SHORT 3 FABS - RUN QTY 37 CLEAR 9/9 | 14 | Becton, Dickinson and Company | Sparks Glencoe | MD | 21152 | attn: Kevin Wenger
|  | 2022-09-21 | 111644 (7/23) | 1775 W Hibiscus Blvd Ste 200 | 50 | L3 |  |  | 9/21 6D 10D | FEDEX P | ***EXPEDITE*** CLASS 3 - XRAY REQ / MUST SAVE IMAGES | NEED PROG 9/14 - BOT SIDE 6:00 9/15 - TOP SIDE 6:00 9/16 - AOI 11:30 | 1B 2T 99/1033 | KIT IN AUDIT - COULD CLEAR 7/25 9/13 - KIT CLEAR 9/13 | 0 | Aeronix, Inc. | Melbourne | FL | 32901 | Attn: Jeff Smith
|  | 2022-09-21 | 111571-2 (8/31) | 5660 Airport Blvd Ste 101 | 50 |  |  |  | 9/21 10/10 9D | UPS GND | (PARTS IN SHIPPING) SPLIT SHIPMENT (QTY 50 - 9/14) OK TO SHIP LAST SHIPMENT EARLY DEPANEL NEED SERIAL #S ON CofC ECO #3 | 9/2 - TOP SIDE 9/2 - AOI | 1T 45/89 | KIT CLEAR 8/31 | 7 | Churchill Navigation dba Shotover Systems Inc | Boulder | CO | 80301
|  | 2022-09-21 | 112626 (9/13) | 6750 Crosby Ct | 200 | L1 |  |  | 9/20 5D | FEDEX GND | DEPANEL | 9/14 - TOP SIDE 10:00 9/14 - AOI | 1T 3/31 | KIT CLEAR 9/13 | 14 | Command Alkon Inc. | Dublin | OH | 43016
|  | 2022-09-19 | 111910-2 (8/25) | 10701 East Blvd | 1 | L1 |  |  | 9/19 15D | UPS GND | ***DO NOT TRIM PINS FOR J701 | NEED PROG 9/12 - BOT SIDE 7AM 9/12 - TOP SIDE 9AM 9/12 - AOI 12:30 | 1B 2T 93/353 | KIT CLEAR 8/25 9/6 - KIT RE CLEAR (DNI NOW LOAD) | 29 | Case Western APT - Cleveland VA Medical Center | Cleveland | OH | 44106
|  | 2022-09-19 | 112029-2 (8/18) | 11475 Lakefield Dr | 109 | L2 |  |  | 9/19 5D | FEDEX P | DEPANEL SHIP TO: HOWARD EVANS "U4" IS BTD | 9/12 - BOT SIDE 9/13 - TOP SIDE 12:00 9/15 - AOI 9:00 | 1B 2T 91/284 | 9/6 - PARTIAL SHORT 17 PCS U4 - KIT CLEAR 9/12 "U4" BTD | 12 | Nordson Corporation | Duluth | GA | 30097 | Attn: Howard Evans
|  | 2022-09-19 | 112920 (9/14) | 2112 Case Pkwy Ste 1 | 25 | L1 |  |  | 9/19 3D | FEDEX P | * 3 DAY TURN * | 9/14 - BOT SIDE 1:00 9/14 - TOP SIDE 2:30 9/15 - AOI 4:00 | 1B 1T 14/41 | KIT CLEAR 9/14 | 14 | AVID Technologies | Twinsburg | OH | 44087 | AVID Technologies,INC
|  | 2022-09-19 | 112757 (9/7) | 21719 84th Ave S | 8 | L1 |  |  | 9/19 5D | FEDEX P | DEPANEL XRAY REQUIRED (SAVE IMAGES) BOARD LABEL REQ ON BOTH SIDES SPECIAL CofC REQ | NEED PROG 9/13 - BOT SIDE 7:00 9/13 - TOP SIDE 8:00 9/13 - AOI 9:00 | 1B 1T 34/508 | 9/7 - WILL CLEAR SOON - ONLY SHORT 1 SMT & 2 T/H KIT CLEAR 9/19 | 156 | Blue Origin, LLC | Kent | WA | 98032 | Attn: Richard Garcia
|  | 2022-09-19 | 109219-2 (6/15) | 22924 E Appleway Ave | 60 60 |  | 62 60 60 | 63 60 60 | 9/19 10/17 | FEDEX P | DEPANEL - SPLIT SHIPMENTS - DO NOT SHIP EARLY | NEED PROG 6/17 - TOP SIDE 6/17 - AOI | 1T | KIT CLEAR 6/16 | 2 | Frencken America Inc. | Liberty Lake | WA | 99019-9514 | Frencken America, Inc, / Po Box 828 | 234304518
|  | 2022-09-19 | 112309 (8/22) | 6040 N Cutter Cir Ste 302 | 30 |  |  |  | 9/19 20D | FEDEX GND | T/H ONLY | 8/22 - BACK |  | KIT CLEAR 8/19 | 68 | Technical Marine Service, Inc. | Portland | OR | 97217
|  | 2022-09-19 | 110180 (8/26) | 1 Analog Way | 15 | L1 |  |  | 9/16H 10D | FEDEX 2 DAY | DEPANEL MECH ASSY REQ CABLES MAY NEED INSTALLING, IF NOT SHIP WITH THE ASSYS | NEED PROG R47 CAME LOOSE - NEED TO T&R 9/13 - BOT SIDE 10:30 9/13 - TOP SIDE 2:30 9/14 - AOI 9:00 | 1B 1T 37/284 | FABS DUE 8/26 FAB REMAKE NO ETA KIT CLEAR 9/1 | 53 | Analog Devices Inc. | Wilmington | MA | 01887
|  | 2022-09-16 | 112502-1 (9/6) | 7 Loveton Cir | 37/40 | L3 |  |  | 9/16 5D | FEDEX P | RUN & SHIP QTY 37 ***MISSING MOUSE BITE HOLES - TAD WILL DEPANEL | NEED PROG 9/12 BOT SIDE 6AM 9/12 - TOP SIDE 11AM 9/13 - AOI 11:30 | 1B 2T 118/447 | SHOULD CLEAR SOON - SHORT 3 FABS - RUN QTY 37 CLEAR 9/9 | 14 | Becton, Dickinson and Company | Sparks Glencoe | MD | 21152 | attn: Kevin Wenger
|  | 2022-09-16 | 111910-1 (8/25) | 10701 East Blvd | 14 | L1 |  |  | 9/16H* 15D | UPS GND | ***DO NOT TRIM PINS FOR J701 | NEED PROG 9/12 - BOT SIDE 7AM 9/12 - TOP SIDE 9AM 9/12 - AOI 12:30 | 1B 2T 93/353 | KIT CLEAR 8/25 9/6 - KIT RE CLEAR (DNI NOW LOAD) | 29 | Case Western APT - Cleveland VA Medical Center | Cleveland | OH | 44106
|  | 2022-09-16 | 112759 (9/7) | 21719 84th Ave S | 8 | L2 |  |  | 9/16* 5D | FEDEX P | DEPANEL XRAY REQUIRED (SAVE IMAGES) BOARD LABEL REQ ON BOTH SIDES SPECIAL CofC REQ | NEED PROG 9/12 - TOP SIDE 6AM 9/12 - AOI 9AM | 1T 22/101 | 9/7 - ONLY PART C/Fs 9/9 - KIT CLEAR (INTERNAL) | 107 | Blue Origin | Kent | WA | 98032
|  | 2022-09-16 | 111849 (8/30) | 740 S Pierce Ave Ste 15 | 150 | L1 |  |  | 9/16H 9D | FEDEX P | DEPANEL | 9/7 - BOT SIDE 9/8 - TOP SIDE 1PM 9/9 - AOI 3PM | 2B 2T 95/487 | COULD CLEAR 8/31 - PARTIAL FABS RECV FROM CHINA (NEED TO BAKE) KIT CLEAR 9/2 | 4 | Bridge Diagnostics, Inc. | Louisville | CO | 80027
|  | 2022-09-15 | 112570-1 | 1155 Dairy Ashford Rd | 15 BAL | L1 |  |  | 9/15 3D | UPS RED | * 3 DAY TURN * DEPANEL U4 PLACEMENT PAID REWORK PER "ChangeIMU.PDF" MECHANICAL ASSY | 9/12 - BOT SIDE 1:00 9/12 - TOP SIDE 1:30 9/13 - AOI 9:00 | 1B 1T 63/198 | 9/9 - SHORT U14 - DUE 9/12 KIT CLEAR 9/12 | 16 | Softeq | Houston | TX | 77079 | Suite 125
|  | 2022-09-15 | 109852 (8/30) | 5665 Airport Blvd | 250 | L3 |  |  | 9/15H 9d | FEDEX 2 DAY | NO MARKINGS ALLOWED ON BOTTOM SIDE | START ASAP 9/7 - TOP SIDE 9/8 - HOLD 9/9 - TOP SIDE 6AM 9/9 - AOI 3PM | 2T 52/117 | KIT CLEAR 9/1 | 11 | Transparent Technologies | Boulder | CO | 80301
|  | 2022-09-15 | 112483 (8/26) | 5475 Airport Blvd | 280 |  |  | REWORK | 9/15H 10D | UPS RED | PAID REWORK | 8/25 - BACK |  | SHOULD CLEAR 8/29 8/30 |  | Particle Measuring Systems | Boulder | CO | 80301-2339 |  | 810528
|  | 2022-09-14 | 112492 / (112493) (9/2) | 10950 Pierson Dr | 60 | L1 |  |  | 9/15H 5D | FEDEX P | DEPANEL SHIP TOGETHER W/ 112493 | RUN 2ND - SHARE MATL W 112492 9/6 - BOT SIDE 9/7 - TOP SIDE 9/7 - AOI | 1B 1T 95/270 | KIT CLEAR 9/2 | 0 | Durbin Group | Fredericksburg | VA | 22408 | Suite 700
|  | 2022-09-14 | 111909 (8/23) | 600 N Dekora Woods Blvd | 60 | L2 |  |  | 9/15H 10D | UPS RED | DEPANEL PREVIOUS ISSUES @ l3/L4 & U11 | 9/6 - BOT SIDE 9/6 - TOP SIDE 9/7 - AOI | 1B 1T 57/114 | SHOULD CLEAR 8/24 EOD 8/31 KIT CLEAR 8/31 | 20 | Alliance Technology, LLC. | Saukville | WI | 53080 | Insight Vision
|  | 2022-09-14 | 112493 / (112492) (9/1) | 10950 Pierson Dr | 40 | L1 |  |  | 9/15H 5D | FEDEX P | DEPANEL SHIP TOGETHER W/ 112492 | RUN 1ST - SHARE MATL W 112492 9/6 - BOT SIDE 9/7 - TOP SIDE 9/7 - AOI | 1B 1T 95/271 | KIT CLEAR 9/2 | 0 | Durbin Group | Fredericksburg | VA | 22408 | Suite 700
|  | 2022-09-14 | 109097-2 (5/26) | 2112 Case Pkwy Ste 1 | 75 BAL | L2 |  |  | 9/14 5D | FEDEX P | DEPANEL | 9/9 - BOT SIDE 6AM 9/9 - TOP SIDE 10AM 9/9 - AOI - 3:30PM | 1B 2T 43/265 | COULD CLEAR 5/26 - QTY 55 CLEAR 5/26 - 9/6 - PART C/Fs ONLY - KIT CLEAR 9/7 | 11 | AVID Technologies | Twinsburg | OH | 44087-2378 | Attn:Frank Torrieri
|  | 2022-09-13 | 111571-1 (8/31) | 5660 Airport Blvd Ste 101 | 50 |  |  |  | 9/14H ??? 9D | UPS GND | SPLIT SHIPMENT (QTY 50 - 9/14) DEPANEL NEED SERIAL #S ON CofC ECO #3 | 9/2 - TOP SIDE 9/2 - AOI | 1T 45/89 | KIT CLEAR 8/31 | 7 | Churchill Navigation dba Shotover Systems Inc | Boulder | CO | 80301
|  | 2022-09-13 | 109882-1 (8/22) | 45150 Business Ct Ste 200 | 4FA/76 |  |  |  | 9/13 5D | FEDEX P | 100% XRAY REQ & SAVE IMAGES | 9/7 - TOP SIDE 9/7 - AOI | 2T 93/648 | SHOULD CLEAR 8/22 EOD SHORT SHIELDS - KIT CLEAR 9/6 | 60 | CACI | Sterling | VA | 20166
|  | 2022-09-12 | 112363 (8/31) | 950 N Rengstorff Ave | 3 | L3 |  |  | 9/12* 5D | FEDEX P | NEED BY 12:00 PM 9/12 - HAND DELIVER TO CUSTOMER | 9/6 - BOT SIDE 9/6 - TOP SIDE 9/7 - AOI | 2B 2T 204/ 1385 | 8/31 - SHORT FABS - SMT CLEAR *SHORT T/H | 14 | Reliable Robotics Corporation | Mountain View | CA | 94043 | ATTN:Bryant Perez/ O#2212
|  | 2022-09-12 | 111957 (8/19) | 1 Executive Dr | 10 | L2 |  |  | 9/12H 10D | FEDEX P | DEPANEL & SAND LEADS NOT TO EXCEED 0.1" (2.54MM) | 9/1 - BOT SIDE 9/1 - TOP FA 9/2 - TOP SIDE 9/2 - AOI | 1B 2T 117/ 729 | 8/19 - ONLY SHORT U11 - OK TO SKIP- DUE 8/24 KIT CLEAR 8/26 | 22 | Spectro Inc. | Chelmsford | MA | 01824 | Suite 101
|  | 2022-09-12 | 107033-2 (8/8) | 160 Schoolhouse Rd | 50 BAL |  |  |  | 9/15 20D | FEDEX GND | *** QTY 25 PAID EXPEDITE SHIPPED 8/25 | 8/22 - BOT SIDE 8/23 - TOP SIDE 8/23 - AOI | 1B 1T | 8/8 - REL BOT SIDE ONLY KIT CLEAR 8/18 | 14 | AR RF Microwave (ARI) | Souderton | PA | 18964-2412
|  | 2022-09-09 | 109324-3 (8/24) | 4 Constitution Way | 100 | L3 |  |  | 9/12 3D | UPS RED GND | ***EXPEDITE - SMT MISTAKE*** FH1 FUSE HOLDER CAME LOOSE - NEED TO T&R | 9/8 - BOT SIDE 6AM 9/8 - TOP SIDE 12PM 9/8 - AOI 3PM | 2B 1T 98/347 | KIT CLEAR 8/24 | 9 | Servomex Inc | Woburn | MA | 01801-8510 |  | 014478
|  | 2022-09-09 | 112156 (8/29) | 60 Alhambra Rd | 50 | L1 |  |  | 9/13H 10D | FEDEX GND |  | 9/2 - TOP FA 9/6 - AOI | 1T 23/69 | 8/29 - ONLY WTG FOR PART C/F | 7 | TSRGrow | Warwick | RI | 02886 | Ste 1
|  | 2022-09-09 | 110178 (8/30) | 160 Camino Ruiz | 20 | L2 |  |  | 9/9 9/14H 10D | FEDEX P | ***EXPEDITE*** *FAB PRE BAKE REQ* DEPANEL /SAND *KEEP EXPOSED EDGES FREE OF SOLDER & FLUX - ECO NOTE #2* *P1/P2 CRITICAL POSITIONING PER ECO | 9/1 - BOT SIDE | 1B 1T 24/69 | KIT CLEAR 8/30 | 30 | Attollo Engineering LLC | Camarillo | CA | 93012-6700
|  | 2022-09-08 | 111850-1 (8/25) | 740 S Pierce Ave Ste 15 | 50 | L3 |  |  | 9/9H | FEDEX P | DEPANEL *SPLIT SHIPMENT - DO NOT SHIP EARLY | 8/29 - BOT SIDE 9/1 - TOP QTY 50 9/1 - AOI | 2B 2T 97/425 | KIT CLEAR 8/25 9/1 - RUNNING 50 THEN HOLD | 0 | Bridge Diagnostics, Inc. | Louisville | CO | 80027
|  | 2022-09-08 | 112573 (8/26) | 6750 Crosby Ct | 330 | L1 |  |  | 9/8H 3D | FEDEX P | * 3 DAY TURN * *TAD WILL DEPANEL* (REDUCE CUTTER DEPTH) TZ1 DIODE ROTATION CHANGED (CATH UP) SEE PHOTO FROM CUSTOMER **LABEL WITH "K" | 9/1 - TOP SIDE (320 DONE) 9/2 - TOP DONE +10 | 2T 22/50 | SHOULD CLEAR SOON - NEED ATTRITION 9/2 - KIT CLEAR | 10 | Command Alkon Inc. | Dublin | OH | 43016
|  | 2022-09-08 | 109324-2ND (8/24) | 4 Constitution Way | 400 | L1 |  |  | 9/8H 10D | UPS RED BLUE | FH1 FUSE HOLDER CAME LOOSE - NEED TO T&R | 8/26 - BOT 1ST ART 8/27 - BOT SIDE 8/30 - TOP SIDE 9/1 - HOLD 70 LEFT 9/2 - TOP SIDE 9/2 - AOI | 2B 1T 98/347 | KIT CLEAR 8/24 | 9 | Servomex Inc | Woburn | MA | 01801-8510 |  | 014478
|  | 2022-09-07 | 111789 (8/10) | 3445 Lake Eastbrook Blvd Se | 10 | L3 |  |  | 9/7H 3D | FEDEX P | *3 DAY TURN * DEPANEL | NEED PROG 9/2 - BOT SIDE 9/2 - TOP SIDE NEED NEW STENCIL 9/6 - TOP SIDE 9/6 - AOI | 1B 1T 62/156 | WILL CLEAR SOON | 0 | College Park Industries, Inc. | Grand Rapids | MI | 49546
|  | 2022-09-07 | 112570-1 | 1155 Dairy Ashford Rd | 5/20 | L1 |  |  | 9/7H 3D | UPS RED | * 3 DAY TURN DEPANEL U4 PLACEMENT PAID REWORK PER "ChangeIMU.PDF" MECHANICAL ASSY | 9/1 - BOT SIDE 9/1 - TOP SIDE 9/1 - AOI | 1B 1T 63/198 | KIT CLEAR 9/1 | 16 | Softeq | Houston | TX | 77079 | Suite 125
|  | 2022-09-07 | 112459 (8/29) | 1501 Industrial Rd | 13 | L3 |  |  | 9/7H 5D | FEDEX P | DEPANEL LABEL OUTSIDE BOX PER ECO 4 | 8/31 - BOT SIDE 8/31 - TOP SIDE 8/31 - AOI | 1B 1T 50 559 | KIT CLEAR 8/30 | 3 | Noah Medical | San Carlos | CA | 94070
|  | 2022-09-07 | 112460 (8/26) | 6750 Crosby Ct | 40 | L2 |  |  | 9/7* 2D | FEDEX P | **2 DAY TURN** MISSING MOUSE BITES - TAD WILL DEPANEL | NEED PROG 8/29 - BOT DONE 8/31 - TOP SIDE 8/31 - AOI | 1B 1T 62/444 | 8/29 BOT CLEAR / TOP PARTIAL SHORT 1 PART - D1 DUE 9/6 EOD | 14 | Command Alkon, Inc. | Dublin | OH | 43016
|  | 2022-09-01 | 111713 (8/24) | 1 Km Noreste Del Centro Commercial Real | 2 | L2 |  |  | 9/1 5D | FEDEX INTL | DEPANEL *POST BAKE ASSYS 30 MIN ECO #4 | 8/27 - BOT SIDE 8/27 - TOP SIDE 8/29 - AOI | 1B 1T | KIT CLEAR 8/25 | 102 | ICUMedical Costa Rica LTD | COSTA RICA |  |  | 40104 LA AURORA
|  | 2022-09-01 | 112380 (8/22) | 7400 Paseo Padre Pkwy | 15 | L2M2 |  |  | 9/1 5D | UPS RED | DEPANEL DNI BP1, BP2, BP3_U1 (x12) - SPECIAL CofC ECO NOTE 3 | 8/25 - TOP SIDE 8/25 - AOI | 1T 7 | FABS DUE 8/23 8/25 KIT CLEAR 8/25 | 29 | Neuralink Corporation | Fremont | CA | 94555
|  | 2022-09-01 | 110268 (8/17) | 4155 Theurer Blvd | 75 | L2 |  |  | 9/1 10D | UPS RED | DEPANEL | 8/18 - TOP SIDE 8/19 - AOI | 1T | KIT CLEAR 8/18 | 13 | Benchmark Electronics | Winona, | MN | 55987
|  | 2022-09-01 | 112442 (8/24) | 11491 Sunset Hills Rd | 100 | L2 |  |  | 9/1 3D | FEDEX P | DEPANEL * 3 DAY TURN * MARK REV WITH PERMANENT INK | NEED PROG NEED STENCIL 8/26 - BOT SIDE 8/26 - TOP SIDE 8/26 - AOI | 1B 1T 45 | SMT CLEAR 8/25 - SHORT T/H DUE 8/29 KIT CLEAR 8/29 | 10 | HunterLab | Reston | VA | 20190
|  | 2022-08-31 | 109942-2ND 8/24) | 4 Constitution Way | 190 BAL | L2M2 |  |  | 8/31 5D | UPS RED | DEPANEL 2ND ARTICLE NO CHANGES | 8/25 - BOT SIDE 8/25 - TOP SIDE 8/26 - BACK | 1B 1T 5 | KIT CLEAR 8/24 | 4 | Servomex Inc | Woburn | MA | 01801-8510 |  | 014478
|  | 2022-08-31 | 109333-2ND (8/24) | 8500 Otto Rd | 89 BAL | L1M2 |  |  | 8/31 5D | FEDEX P | DEPANEL 2ND ARTICLE WITH CHANGES - NO LOAD R17,12,5,24,28 / LOAD C22,24,5,7,35,37,38,41 | 8/25 - TOP SIDE 8/26 - AOI | 1T 145 | KIT CLEAR 8/24 | 22 | Mountain Horse Solutions | Gunpowder | MD | 21010-5410 | Attn: William Schuster
|  | 2022-08-31 | 100606-3 (7/15) | 3190 Monitor Ave Rm 0220 | 20/190 | L2B / L3T |  |  | 2022-08-31 | #VALUE! | *G5A-H & G2A-H NEW PROCESS - NEED QA INSP 100% - NO SOLDER ALLOWED ON COIL **J1A-H NO EXCESS SOLDER ALLOWED | 7/19 - BOT SIDE 7/25 - BOT DONE 8/24 - TOP 1ST ART 8/25 - AOI/BACK | 2B 3T 3746 | 7/15 - RELEASED BOT ONLY 8/23 - TOP SET UP | 8 | University of Oklahoma | Norman | OK | 73019-5004 | Attn: Redmond Kelley | 749026308
|  | 2022-08-31 | 111643-2 (8/5) | 601 Atlantis Rd | 15 BAL | L1 |  |  | 8/31 10D | FEDEX P | DEPANEL & SAND ***SHIP QTY 10 8/29 FEDEX 2 DAY | 8/24 - TOP SIDE 8/24 - AOI | 2B 2T 165 | QTY 10 CLEAR /QTY 15 SHORT ITEM 96 - DUE 8/8 | 1 | Anderson Connectivity | Melbourne | FL | 32904
|  | 2022-08-30 | 112358 (8/18) | 22 Bedford St Unit 4 | 200 | L1 |  |  | 9/2 9/1 10D | FEDEX P | DEPANEL & SAND | 8/22 - BOT SIDE 8/23 - TOP SIDE 8/24 - AOI | 1B 1T 21 | KIT CLEAR 8/18 8/23 - HOLD - U8 WRONG PART KIT CLEAR 8/24 | 3 | Open Source Instruments, Inc. | Waltham | MA | 2453 | Attn: Kevan Hashemi
|  | 2022-08-30 | 103558-4 (8/12) | 2015 Chestnut St | 26 BAL | L3 |  |  | 8/31 15D | #VALUE! | TOP SIDE DONE - RUN BOT SIDE - ***8/16 CUST REQ TO EXPEDITE TO 8/23 | 8/23 - BOT SIDE - 8/23 - AOI | 2B 2T | KIT CLEAR 8/10 | 1 | Emcore | Alhambra | CA | 91803-1542 | Attn: Receiving Dept - PO # ALH0025151 | 496548183
|  | 2022-08-30 | 112468 (8/24) | 21 Alpha Rd | 50 | L1M1 |  |  | 8/30 8/29 3D | FEDEX P | 8/25 - HOLD - U2/U4 PART FIT ISSUE - DNI PER CUST 8/26 | 8/25 - BOT SIDE 8/25 - TOP 8/26 - AOI | 1B 1T | KIT CLEAR 8/24 | 7 | Atlas Devices | Chelmsford | MA | 01824 | Suite 202
|  | 2022-08-29 | 109716 (8/8) | 140 South Rd | 20 | L2 |  |  | 8/30 15D | FEDEX P | DEPANEL RTV REQ | NEED PROG 8/15 - TOP SIDE 8/15 - AOI | 1T | KIT CLEAR 8/9 | 10 | Berkshire Grey | Bedford | MA | 01730
|  | 2022-08-29 | 110684-2 (8/10) | 750 Central Ave | 39 BAL | L1 |  |  | 8/30 9D | UPS GND | DO NOT SHIP MATERIAL - KEEP @ ALTA | NEED PROG 8/17 - BOT SIDE 8/18 - TOP SIDE 8/18 - AOI | 1B 1T | ONLY SHORT ITEMS 20 & 27 8/17 - QTY 39 BAL CLEAR | 8 | Holland LP | University Park | IL | 60484
|  | 2022-08-29 | 110684-1 (8/10) | 750 Central Ave | 61/100 | L1 |  |  | 8/30 9D | UPS GND | 8/17 - SMT RUNNING QTY 31 BAL DO NOT SHIP MATL - KEEP @ ALTA | NEED PROG 8/15 - BOT SIDE 8/16 - TOP SIDE 8/16 - AOI | 1B 1T | ONLY SHORT ITEMS 20 & 27 - 8/10 PARTIAL CLEAR - KIT CLEAR 8/17 | 8 | Holland LP | University Park | IL | 60484
|  | 2022-08-29 | 111643-1 (8/5) | 601 Atlantis Rd | 10 15 | L1 |  |  | 8/29 10D | FEDEX P | DEPANEL & SAND ***SHIP QTY 10 8/29 FEDEX 2 DAY | 8/24 - TOP SIDE 8/24 - AOI | 2B 2T 165 | QTY 10 CLEAR /QTY 15 SHORT ITEM 96 - DUE 8/8 | 1 | Anderson Connectivity | Melbourne | FL | 32904
|  | 2022-08-29 | 112067 (8/18) | 4501 Hatfield St | 20 | L2 |  |  | 8/29 5D | UPS RED | DEPANEL & SAND LABEL ON BOARD AND ESD BAG REQ -MATL BAG HEAT SEALING NOT REQ | NEED PROG 8/22 - BOT SIDE 8/23 - TOP SIDE 8/24 - AOI | 1B 1T 84 XR | 8/18 - PART C/F'S ONLY 8/19 - STILL SHORT U9 (WRONG PART) - KIT CLEAR 8/22 | 1 | Carnegie Robotics | Pittsburgh | PA | 15201
|  | 2022-08-29 | 109407 (8/2) | 555 Alter St | 18 | L1 |  |  | 8/29 10D | FEDEX 2 DAY | DEPANEL | NEED PROG 8/17 - BOT SIDE 8/17 - AOI | 1B 2T | COULD CLEAR BY 8/5 | 6 | Vita Inclinata Technologies | Broomfield | VCO | 80020 | Suite 19B
|  | 2022-08-26 | 109853 (7/27) | 5665 Airport Blvd | 200 | L1 |  |  | 8/29 9D | FEDEX 2 DAY |  | NEED PROG 8/18 - TOP SIDE 8/19 - AOI | 2T | SHOULD CLEAR 7/29 8/9 SHORT 50 PCS ITEM 45 DUE 8/16 - KIT CLEAR 8/16 | 6 | Transparent Technologies | Boulder | CO | 80301
|  | 2022-08-26 | 112068 (8/18) | 4501 Hatfield St | 20 | L3 |  |  | 8/26* 5D | UPS RED | DEPANEL & SAND LABEL ON BOARD AND ESD BAG REQ -MATL BAG HEAT SEALING NOT REQ | NEED PROG 8/19 - BOT SIDE 8/20 - TOP SIDE 8/22 - AOI | 2B 1T | KIT CLEAR 8/18 - NOT REPORTED | 0 | Carnegie Robotics | Pittsburgh | PA | 15201
|  | 2022-08-26 | 110721-1 (8/12) | 21 Hamilton Ct | 234/440 | L3 |  |  | 8/26 10D | UPS RED | DEPANEL RUN PARTIAL QTY 234 SPEC CofC PER ECO 5 | 8/18 - BOT SIDE 8/18 - TOP SIDE 8/19 - AOI | 1B 2T | 8/12 - QTY 234 TOP SIDE CLEAR - QTY 440 BOT SIDE CLEAR | 2 | Royal Circuit Solutions, Inc. | Hollister | CA | 95023-2535 |  | 37R281
|  | 2022-08-26 | 110770-2 (7/13) ***HOLD WTG FOR UPDATED PO - PO RECV 8/10 | 20 New King St | 12 8 | L1 |  |  | 8/26 7/28 8/17 5D | UPS GND | DEPANEL CLASS 3 LOAD U29 & U7 COMPLETE BOARDS ONLY (NO PARTIAL LOADING) TERMINAL J1 WIRE ENTRY SIDE TO FACE CENTER OF BOARD ONLY SHIP QTY 12 ON 7/28 | NEED PROG (21 ITEMS EXACT) 7/22 - BOT SIDE 7/25 - BOT/TOP 7/25 - AOI | 2T | KIT CLEAR 7/21 | 9 | Safe Flight Instrument Corp | White Plains | NY | 10604-1204 |  | 140168
|  | 2022-08-25 | 112029-1 (8/18) | 11475 Lakefield Dr | 1 / 109 | L2 |  |  | 8/26 5D | FEDEX P | DEPANEL SHIP TO: HOWARD EVANS | NEED PROG 8/20 - BOT/TOP 8/22 - AOI | 1B 2T 91 | KIT CLEAR 8/19 | 12 | Nordson Corporation | Duluth | GA | 30097 | Attn: Howard Evans
|  | 2022-08-25 | 112227 (8/19) | 12034 134th Ct Ne | 20 | L1 |  |  | 8/25 3D | FEDEX P | * 3 DAY TURN * DEPANEL PER ECO #1 - 0.03" REMNANT ALLOWED *SHIPPING - ESD BAGS REQ LABELS | 8/22 - BOT SIDE 8/22 - TOP SIDE 8/22 - AOI | 1B 2T | KIT CLEAR 8/22 - DNI U37 | 9 | Kymeta | Redmond | WA | 98052 | #105
|  | 2022-08-25 | 110113-2 (6/1) | 22924 E Appleway Ave - PO Box 828 | 15 BAL |  |  |  | 2022-08-25 | FEDEX GND | SPLIT SHIPMENT *DO NOT SHIP EARLY* | 8/4 - BACK | 2T | SHORT ITEM 34 - OK TO SKIP - QTY 15 CLEAR | 2T | Frencken America, Inc. | Liberty Lake | WA | 99019-9514 |  | 234304518
|  | 2022-08-25 | 110203-1 (6/9) | 22924 E Appleway Ave | 60 |  |  |  | 2022-08-25 | FEDEX GND | DEPANEL *SPLIT SHIPMENT* OK TO RUN ALL **DO NOT SHIP EARLY** | NEED PROG 6/15 - TOP SIDE 6/17 - AOI | 1T | WILL CLEAR 6/9 - KIT CLEAR 6/10 | 4 | Frencken America Inc. | Liberty Lake | WA | 99019-9514 | Frencken America, Inc, / Po Box 828 | 23430451
|  | 2022-08-24 | 0115-MARVELL (8/12) |  | 15 | L3 |  |  | 8/24 9D |  | 1ST JOB FOR NEW CUSTOMER - PLEASE MAKE SURE SOLDER/ ASSY LOOKS GOOD!!! | 8/16 - BOT SIDE 8/17 - TOP SIDE 8/17 - AOI | 1B 2T | KIT CLEAR 8/12 | 0 | MARVEL |  | CA
|  | 2022-08-24 | 111735 (8/4) | 49 Willow Peak Dr | 5 | L1 |  |  | 8/24 3D | FEDEX P | * 3 DAY TURN * DEPANEL | BOT RTR 8/5 8/19 - BOT SIDE 8/20 - TOP SIDE | 1B 3T | FABS DUE 8/8 8/19 8/22 - KIT CLEAR 8/19 | 27 | Quantel USA | Bozeman | MT | 59718 | Quantel USA
|  | 2022-08-24 | 107033-1 (8/8) | 160 Schoolhouse Rd | 25 | L3 |  |  | 8/25 9/15 5/20D | FEDEX GND | *** QTY 25 PAID EXPEDITE | 8/22 - BOT SIDE 8/23 - TOP SIDE 8/23 - AOI | 1B 1T | 8/8 - REL BOT SIDE ONLY KIT CLEAR 8/18 | 14 | AR RF Microwave (ARI) | Souderton | PA | 18964-2412
|  | 2022-08-24 | 112235 (8/18) | 4246 S Riverboat Rd | 325 | L3 |  |  | 8/25 5D | FEDEX P | CLASS 3 DEPANEL & SAND | 8/19 - BOT SIDE 8/19 - AOI | 1B | KIT CLEAR 8/18 | 0 | Artis LLC | Taylorsville | UT | 84123 | Suite 250 Attn: Jared Bench
|  | 2022-08-23 | 112337 (8/18) | 480 Springpark Pl | 100 |  |  |  | 8/25 5D | FEDEX P | T/H ONLY PRESS FIT | 8/18 - BACK |  | KIT CLEAR 8/18 | 24 | Artis LLC | Herndon | VA | 20170 | Suite 1000 Attn:Cody Sewell
|  | 2022-08-23 | 109791-2 (7/13) | 1545 Forbes St | 80/130 |  |  |  | 8/23 10D | FEDEX P | DEPANEL SHIP PARTIAL QTY 80 SHIP QTY 80 ON 8/23 *DO NOT SHIP EARLY* | FSU | 1B 1T | SHOULD RECV PARTIAL OF U2 TO RUN QTY 80 | 0 | McQ | Fredericksburg | VA | 22405-1606
|  | 2022-08-23 | 111103 (7/28) | 5900 Heisley Rd | 18 | L2 |  |  | 8/23 15D +5 | FEDEX GND | RTV REQ REMOVE ITEMS 31 & 49 FROM OLD BOARDS BUILD QTY 12 BOARDS COMPLETE - QTY 8 BTD ITEMS 30, 31, 49 | 8/5 - BOT SIDE 8/5 - TOP SIDE 8/8 - AOI | 1B 2T | KIT CLEAR 7/29 BUT NEED TO REMOVE ITEMS 31 & 49 FROM OLD BOARDS +5 DAYS - REMOVED 8/3 | 29 | Steris | Mentor | OH | 44060-1834 | Attn: Vince Vlach | 331041289
|  | 2022-08-22 | 112406 (8/18) | 11824 Jollyville Rd Ste 102 | 200 | L3 |  |  | 8/22 2D | FEDEX P | ***2 DAY TURN *** DEPANEL | 8/19 - BOT SIDE 8/19 - AOI | 1B | KIT CLEAR 8/18 | 0 | TenX Precision, LLC | Austin | TX | 78759
|  | 2022-08-22 | 112148 (8/8) | 3200 N Kings Hwy | 40 |  |  |  | 8/22 10D | UPS GND | PAID REWORK - R&R U7,U8, U17 & U18 | 8/8 - BACK |  | KIT CLEAR 8/8 | 4 | Graph-Tech USA, LLC | Fort Pierce | FL | 34951
|  | 2022-08-22 | 110896 (8/11) | 15 Centennial Dr | 300 | L2 |  |  | 9/6H 10D | FEDEX P | DEPANEL & SAND | 8/15 - TOP SIDE 8/15 - AOI | 2T | ONLY SHORT 20 PCS SOT - OK TO SKIP KIT CLEAR 8/22 | 0 | TMC / Technical Manufacturing Corp. | Peabody | MA | 01960 | Technical Manufacturing Corp
|  | 2022-08-22 | 103336-1 (2/16) | 103 Quality Cir Nw Ste 220 | 249/400 | L1 |  |  | 8/19 10D | #VALUE! | DEPANEL & SAND - NO SHARP EDGES ALOWED | 8/2 - AOI/BACK |  | *2/16 - SHORT ITEM 54 BOT & 25 TOP | 8 | Scientific Research Corporation | Huntsville | AL | 35806-4537 | Attn: Graehm Sack | 153669597
|  | 2022-08-19 | 109249-2ND (8/15) | 110 Forbes Blvd | 3 | L1 |  |  | 8/23 5D | FEDEX P | 2ND ARTICLE RONC MATL SHARED FROM B107486 &B107482 | RTR 8/16 - TOP SIDE 8/16 - AOI | 2T | KIT CLEAR 8/16 | 50 | NextPhase Medical Devices | Mansfield | MA | 02048-1145
|  | 2022-08-19 | 111199 (8/9) | 440 Creamery Way Ste 100 | 5 | L3 |  |  | 8/23 10D | FEDEX P | CLASS 3 MECHANICAL ASSY | NEED PROG 8/11 - BOT SIDE 8/12 - TOP SIDE 8/12 - AOI | 1B 2T | KIT CLEAR 8/9 | 22 | PetroMar Technologies, Inc. | Exton | PA | 19341
|  | 2022-08-19 | 111818 (8/8) | 480 Springpark Pl | 5 | L1 |  |  | 8/23 10D | FEDEX P | XRAY ALL BGA/LGA & SAVE IMAGES | NEED PROG 8/11 - BOT SIDE 8/11 - TOP 3:00 8/12 - AOI | 2B 2T XR | FABS DUE 8/9 | 12 | Artis LLC | Herndon | VA | 20170 | Ste 900 Attn: Sharpley c/o Inventory
|  | 2022-08-17 | 112050 (8/9) | 2521 E Morgan Rd | 20 | L2 |  |  | 8/18 8/17 *** 5D | FEDEX P | DEPANEL ***SHIPPING - NEED GOOD PHOTOS!!! | NEED PROG 8/10 - BOT SIDE 8/10 - TOP SIDE 8/10 - AOI | 1B 1T | KIT CLEAR 8/9 + 1D PCB BAKE - ***8/10 - CUST REQUEST TO PUT ON HOLD (SMT DONE) | 92 | Amatis Controls | Ann Arbor | MI | 48108
|  | 2022-08-17 | 108519 (8/8) | 3200 Wisman Ln | 15 | L3 |  |  | 8/18 5D | FEDEX 2 DAY | CLASS 3 DEPANEL & BARCODE LABEL REQ **FAIR REQ | 8/10 - TOP SIDE 8/11 - AOI | 2T | SHOULD CLEAR 8/9 KIT CLEAR 8/11 | 12 | GatesAir, Inc. | Quincy | IL | 62301-1252
|  | 2022-08-17 | 111434 (8/9) | 6250 Joyce Dr | 96 | L2B/L1T |  |  | 8/17 5D | FEDEX P |  | NEED PROG 8/11 - BOT SIDE 8/12 - TOP SIDE 8/15 - AOI | 1B 1T | KIT CLEAR 8/10 | 5 | Industrialex Manufacturing | Arvada | CO | 80403
|  | 2022-08-17 | 111657 (8/8) | 22 Jordan Cove Rd | 27 | L1 |  |  | 8/17 5D | UPS RED | PRE BAKE FABS ***RUBBER PLUGS - DO NOT LOOSE*** | NEED PROG 8/9 - BOT SIDE 8/10 - TOP SIDE 8/11 - AOI | 1B 2T | 8/8 - SHORT C164 - OK TO SKIP - KIT CLEAR 8/10 | 37 | Coastal Designs, LLC | Waterford | CT | 06385
|  | 2022-08-16 | 111368 (8/4) | 18103 Ne 68th St Ste C100 | 2 | L3 |  |  | 8/19 10D | FEDEX P | DO NOT DEPANEL ITEMS 85 & 96 REQ 48HR BAKE MASK UNPOPULATED | NEED PROG 8/8 - BOT SIDE 8/8 - TOP SIDE 8/9 - AOI | 2B 2T | KIT CLEAR 8/5 | 0 | Basis Software | Redmond | WA | 98052 | Basic Software, Inc. Attn:Alex Sherstuk
|  | 2022-08-16 | 111746 (8/10) | 2112 Case Pkwy Ste 1 | 15 | L3 |  |  | 8/16 3D | FEDEX P | *3 DAY TURN * ***KEEP MATL HERE, DO NOT SHIP MATL | NEED PROG 8/12 - BOT SIDE 8/12 - TOP SIDE 8/12 - AOI |  | MATL CLEAR 8/10 - WAITING FOR NEW DOCS (BOM CHANGE) |  | AVID Technologies | Twinsburg | OH | 44087
|  | 2022-08-15 | 109333 (8/8) |  | 1 |  |  |  | 8/22 10D |  | NO CHARGE RWK - REMOVE R17,R12,R5,R24,R28 - ADD C22,C24,C5,C7,C35, C37,C38,C41 | 8/8 - BACK |  | KIT CLEAR 8/8 | 13
|  | 2022-08-15 | 109833-2 (8/1) | 7205 NE Evergreen Pkwy Ste 100 | 297 BAL | L3 |  |  | 8/25 15D | FEDEX GND UPS ORG | 2ND ARTICLE APPROVED | 8/5 - BOT SIDE 8/5 - TOP SIDE 8/8 - AOI | 1T | SHOULD CLEAR 8/2 8/3 - KIT CLEAR 8/4 | 12 | Engle Dental Systems LLC | Hillsboro | OR | 97124
|  | 2022-08-12 | 111019 (8/8) | 1230 SHOREBIRD WAY | 1 | L2 |  |  | 8/12* 3D | FEDEX P | * 3 DAY TURN * DEPANEL & SAND | NEED PROG 8/9 - TOP SIDE 8/9 - BACK | 1T | KIT CLEAR 8/9 | 154 | Google | MOUNTAIN VIEW | CA | 64043 | ATTN: KUSCHAK
|  | 2022-08-12 | 111364 (8/8) | 1600 Amphitheatre Parkway | 1 | L2 |  |  | 8/12* 3D | FEDEX P | * 3 DAY TURN * DEPANEL & SAND | NEED PROG 8/9 - TOP SIDE 8/9 - BACK | 1T | KIT CLEAR 8/9 | 189 | Google | Mountain View | CA | 94043
|  | 2022-08-12 | 111800 (8/5) | 6750 Crosby Ct | 550 | L1 |  |  | 8/12 5D | FEDEX P | DEPANEL | 8/5 - TOP SIDE 8/8 - BACK | 1T | KIT CLEAR 8/5 | 6 | Command Alkon Inc. | Dublin | OH | 43016
|  | 2022-08-12 | 111695-1FA (8/2) | 181 W Huntington Dr | 5/130 | L1 |  |  | 8/12 5D | FEDEX P | *CAN'T BE LATE* DEPANEL & SAND | NEED PROG 8/4 - BOT SIDE 8/4 - TOP SIDE 8/4 - AOI | 2B 2T | ONLY SHORT FABS - DUE 8/3 KIT CLEAR 8/3 | 10 | SILC Technologies, Inc. | Monrovia | CA | 91016 | Ste 200
|  | 2022-08-11 | 109004 (8/1) | 250 Moonachie Rd Ste. 400 | 150 | LL1 |  |  | 8/11 8/15 5D | FEDEX P |  | 8/5 - BOT SIDE 8/8 - TOP SIDE 8/9 - AOI | 1B 2T | 6/29 - U1 RECV DAMAGED KIT CLEAR 8/4 | 0 | Sterling Medical Devices | Moonachie | NJ | 07074-1378
|  | 2022-08-11 | 111349 (8/2) | 1 Albion Rd, Suite 100 | 50 44 | L1 |  |  | 8/11 5D | FEDEX P | DEPANEL QTY CHANGED FROM 50 TO 44 DNI U9, J16, J17 | NEED PROG 8/5 - TOP SIDE 8/5 - AOI | 1T | SHOULD CLEAR 8/3 - ONLY 44 FABS KIT CLEAR 8/4 - DNI 3 ITEMS | 24 | Zebra Technologies Corp | Lincoln | RI | 2895 | Attn: Raymond LeBlanc
|  | 2022-08-11 | 111754-1ST (8/3) | 1390 Highland Rd E | 2/6 | L1 |  |  | 8/11 5D | FEDEX P | 1ST ARTICLE CLASS 3 | NEED PROG 8/4 - BOT SIDE 8/4 - TOP SIDE 8/4 - AOI | 1B 1T | KIT CLEAR 8/3 8/4 | 38 | Parker Hannifin Corp | Macedonia | OH | 44056 | Attn: Mike Salcone
|  | 2022-08-10 | 109324-1 (8/1) | 4 Constitution Way | 100/500 | L3 |  |  | 8/10 5D | UPS RED | FH1 FUSE HOLDER CAME LOOSE - NEED TO T&R | 8/3 - BOT SIDE 8/4 - TOP SIDE FA 8/5 - TOP SIDE 8/5 - AOI | 2B 1T | WILL CLEAR 8/2 - WTG ITEM 41 PCF KIT CLEAR 8/3 | 9 | Servomex Inc | Woburn | MA | 01801-8510 |  | 014478
|  | 2022-08-10 | 111198 (8/3) | 125 North Drive | 125 | L2 |  |  | 8/10 5D | FEDEX P |  | NEED PROG 8/4 - BOT SIDE 8/5 - AOI | 1B | KIT CLEAR 8/3 | 0 | Kopin Corporation | Westborough | MA | 1581
|  | 2022-08-10 | 111757 (8/2) | 11491 Sunset Hills Rd | 50 | L1 |  |  | 8/10 5D | FEDEX GND | DEPANEL | NEED PROG 8/3 - TOP SIDE 8/3 - AOI | 1T | FAB DUE 8/4 KIT CLEAR 8/3 | 9 | HunterLab | Reston | VA | 20190
|  | 2022-08-09 | 109706-2 (7/26) | 132 Redtail Court | 2 BAL | L2 |  |  | ??? 10D | UPS GND | 8/4 - "J1" IS DNI SHIPPED QTY 28 ON 8/9 | NEED PROG 7/29 - BOT SIDE 7/29 - TOP SIDE 7/29 - AOI | 1B 2T | KIT CLEAR 7/28 ITEM 60, 80, 144 BTD | 12 | AALogic | Weatherford | TX | 76088 | Attn H. W. Mathews | 38E494
|  | 2022-08-09 | 109706-1 (7/26) | 132 Redtail Court | 28 | L2 |  |  | 8/11 10D | UPS GND | 8/4 - "J1" IS DNI | NEED PROG 7/29 - BOT SIDE 7/29 - TOP SIDE 7/29 - AOI | 1B 2T | KIT CLEAR 7/28 ITEM 60, 80, 144 BTD | 12 | AALogic | Weatherford | TX | 76088 | Attn H. W. Mathews | 38E494
|  | 2022-08-09 | 110848 (8/3) | 600 N Dekora Woods Blvd | 60 | L2 |  |  | 8/10 5D | UPS RED | DEPANEL | 8/4 - BOT SIDE 8/4 - TOP SIDE 8/4 - AOI | 1B 1T | KIT CLEAR 8/3 | 20 | Alliance Technology, LLC. | Saukville | WI | 53080 | Insight Vision
|  | 2022-08-08 | 109696-2 (8/2) | 7051 Industrial Blvd | 45 BAL |  |  |  | 8/9 5D | UPS RED | *2ND ARTICLE | 8/2 - BOT/TOP 8/2 - AOI | 1B 1T | KIT CLEAR 8/2 | 11 | ABB, Inc. | Bartlesville | OK | 74006-6036 | ATTN: Brian Smith | 160E6W
|  | 2022-08-08 | 110691 (7/11) | 500 Hunt Valley Rd | 5 |  |  |  | 8/8 10D | FEDEX P | SPECIAL SOLDER PASTE REQD DEPANEL | NEED PROG 7/27 - BOT SIDE 7/27 - TOP SIDE 7/28 - AOI | 1B 2T | SHOULD CLEAR BY 7/13 7/18 7/25 KIT CLEAR 7/26 | 57 | Siemens Industry, Inc | New Kensington | PA | 15068-7060 | Attn: Emily Ross
|  | 2022-08-05 | 110680-1FA (7/28) | 4 Constitution Way | 15/200 | L2 |  |  | 8/8 5D | FEDEX P | DEPANEL ***FAIR REQUIRED*** | 8/1 - TOP SIDE 8/1 - AOI | 2T | KIT CLEAR 8/1 | 7 | Servomex, Inc. | Woburn | MA | 01801-8510
|  | 2022-08-05 | 100610 (7/20) | 3190 Monitor Ave Rm 0220 | 22 | L3 |  |  | 2022-08-05 | #VALUE! | ***NEW LEAD SOLDER PROCESS FOR U1A-U1H - DO NOT WASH U1A-U1H - USE SAME PROCESS AS B100606*** | 7/26 - BOT SIDE 7/27 - TOP SIDE 7/28 - TOP SIDE DONE 11:00AM 7/28 - AOI | 2B 3T | KIT CLEAR 7/19 | 8 | University of Oklahoma | Norman | OK | 73019-5004 | ATTN: Redmond Kelley | 749026308
|  | 2022-08-05 | 100605-4 (6/27) | 3190 Monitor Ave Rm 0220 | 30 | L3 |  |  | 2022-08-05 | FEDEX P |  | 6/30 - BOT SIDE 7/5 - 164 DONE 7/7 - TOP SIDE 7/11 @120 10:00AM 7/12 @206 2:30 PM 7/13 - AOI 8:00 AM | 2B 7M2T 5M | KIT CLEAR 6/27 | 4 | University of Oklahoma | Norman | OK | 73019-5004 | Attn: Redmond Kelley | 749026308
|  | 2022-08-04 | 111671 (8/2) | 11 Huron Drive | 250 |  |  |  | 8/15 9D | FEDEX P | DEPANEL & SAND | 8/3 - TOP SIDE 8/4 - AOI | 1T | KIT CLEAR 8/2 | 0 | Aila Technologies, Inc. | Natick | MA | 01760 | Suite 202
|  | 2022-08-03 | 109872 (7/20) | 100 Nagog Park | 108 | L1 |  |  | 8/5 10D | FEDEX 2 DAY | *DO NOT DEPANEL* SPECIAL PACKING LABEL REQ - ECO #6 | NEED PROG 7/25 - TOP SIDE 7/26 - AOI | 1T | KIT CLEAR 7/22 | 0 | Optimum Design Associates | Acton | MA | 01720-3428 | Attn:Urate, Jeff Corpate Dock7-8
|  | 2022-08-03 | 111439 (7/26) | 4505 Campus Dr | 5 |  |  |  | 8/3 5D | FEDEX P | U2A ITEM 42 IS BTD DEPANEL | 7/29 - BOT SIDE 7/29 - TOP SIDE 7/29 - AOI | 1B 2T | 7/26 - ONLY SHORT 1 PC U17 - OK TO SKIP KIT CLEAR 7/27 | 4 | IonQ, Inc. | College Park | MD | 20740
|  | 2022-08-02 | 111701 (7/23) | 3200 N Kings Hwy | 42 |  |  |  | 8/2 5D | UPS GND | DEPANEL - R6 CHANGED TO RMCF0603JT4K70, 4.7K 5% | 7/29 - BOT SIDE 7/29 - TOP SIDE 7/29 - AOI | 1B 1T | KIT CLEAR 7/26 | 34 | Graph-Tech USA, LLC | Fort Pierce | FL | 34951
|  | 2022-08-02 | 107934 (6/28) | 1545 Forbes St | 70 | L2 |  |  | 8/2 20D | FEDEX P | ECO #1 - PRE BAKE U46 | 7/25 - BOT SIDE 7/25 - TOP SIDE 7/27 - AOI | 2B 2T | 6/28 - SHORT ITEMS 32 & 64 - 8 ITEMS NO ATTRITION - BTD KIT CLEAR 7/5 | 1 | McQ | Fredericksburg | VA | 22405-1606
|  | 2022-08-02 | 109830-2 (7/7) | 3281 Grande Vista Dr | 47 | L1 |  |  | 8/2 15D | UPS RED | DEPANEL EXTRA BUBBLE WRAP EA BOARD PER ECO 9 | 7/15 - TOP SIDE* *RUN TOP 1ST 7/18 - BOT SIDE 7/20 - AOI | 2B 1T | KIT CLEAR 7/12 | 28 | 360 Systems | Newbury Park | CA | 91320-1193 |  | 929-219
|  | 2022-08-01 | 111742 (7/27) | 21 Alpha Rd | 45 | L1 |  |  | 8/1 3D | FEDEX P | * 3 DAY TURN * 7/27 - PCB BAKED (DC 16-22) | 7/28 - TOP SIDE 7/28 - AOI | 1T | KIT CLEAR 7/27 7/27 - SPOTTING ON PCB REPORTED | 2 | Atlas Devices | Chelmsford | MA | 01824 | Suite 202
|  | 2022-08-01 | 110674 (7/15) | 480 Springpark Pl Suite 1000 | 4 | L3 |  |  | 8/1 10D | FEDEX P | BUSS BARS/FIXTURE | NEED PROG 7/25 - BOT/TOP 7/25 - AOI | 1B 1T | 7/15 - SHORT ITEM 65 - OK TO SKIP | 42 | Artis LLC | Herndon | VA | 20170-5294 | Attn:Jared Bench | 4812-3298-8
|  | 2022-07-29 | 110797 (7/26) | 13900 Alton Pkwy #120 | 250 | L1 |  |  | 7/29 3D | FEDEX P | * 3 DAY TURN * DEPANEL CLASS 3 | 7/26 - BOT SIDE 7/27 - TOP SIDE 7/27 - AOI | 1B 1T | KIT CLEAR 7/26 | 0 | Integra Life Sciences | Irvine | CA | 92618-1621 |  | 122816796
|  | 2022-07-29 | 109005 (7/11) | 250 Moonachie Rd Ste. 400 | 150 | L3 |  |  | 7/29 5D | FEDEX P | CHECK STIFFNER FOR ADHESION PREBAKE FABS DEPANEL | FSU - ON HOLD/ FAB ISSUE 7/19 - BOT SIDE 7/20 - TOP SIDE 7/21 - AOI | 1B 1T | KIT CLEAR 7/7 7/8 7/18 7/7 - HOLD (ARRAY ISSUE, CANT PRINT EPOXY ON J2) | 0 | Sterling Medical Devices | Moonachie | NJ | 07074-1378
|  | 2022-07-29 | 111175 (7/21) | 480 Springpark Pl | 3 | L1 |  |  | 7/29 5D | FEDEX P | BUSS BARS/FIXTURE | NEED PROG 7/25 - BOT SIDE 7/26 - AOI | 1B 1T | KIT CLEAR 7/22 | 41 | Artis LLC | Herndon | VA | 20170 | Suite 1000 Attn:Jared Bench
|  | 2022-07-29 | 100605-3 (6/27) | 3190 Monitor Ave Rm 0220 | 200 | L3 |  |  | 2022-07-29 | FEDEX P |  | 6/30 - BOT SIDE 7/5 - 164 DONE 7/7 - TOP SIDE 7/11 @120 10:00AM 7/12 @206 2:30 PM 7/13 - AOI 8:00 AM | 2B 7M2T 5M | KIT CLEAR 6/27 | 4 | University of Oklahoma | Norman | OK | 73019-5004 | Attn: Redmond Kelley | 749026308
|  | 2022-07-29 | 109868 (7/14) | 20108 SAN RAFAEL | 610 | L3 |  |  | 7/28 10D | UPS Worldwide Express Red | DEPANEL *** 7/25 - HOLD*** - MASKING ISSUE | 7/15 - BOT SIDE 7/15 - TOP SIDE 7/21 - AOI/BACK | 1B 1T | KIT CLEAR 7/14 | 0 | ATL Technology CR | DE ALAJUELA | COSTA RICA |  | Warehouse G1-G2-G3-G4-G5 | 9E7173
|  | 2022-07-29 | 110643-3 (6/30) | 6750 Crosby Ct | 13 BAL |  |  |  | 7/26 5D | FEDEX P | QTY 450 SMT CLEAR 7/15 SHIPPED QTY 119 7/26 SHIPPED QTY 318 BARCODE & MECHANICAL REQ -( 7/28 - TZ1 NEEDS TO BE 180 DEG - SEE EMAIL) | 7/19 - BACK 7/26 - SHORT | 2T | 7/19 - RECV A5 QTY 249 | 10 | Command Alkon, Inc. | Dublin | OH | 43016-7644
|  | 2022-07-28 | 110770-1 (7/13) | 20 New King St | 12 | L1 |  |  | 7/28 ??? 5D | UPS GND | DEPANEL CLASS 3 LOAD U29 & U7 COMPLETE BOARDS ONLY (NO PARTIAL LOADING) TERMINAL J1 WIRE ENTRY SIDE TO FACE CENTER OF BOARD ONLY SHIP QTY 12 ON 7/28 | NEED PROG (21 ITEMS EXACT) 7/22 - BOT SIDE 7/25 - BOT/TOP 7/25 - AOI | 2T | KIT CLEAR 7/21 | 9 | Safe Flight Instrument Corp | White Plains | NY | 10604-1204 |  | 140168
|  | 2022-07-27 | 108770-2 (6/22) | 20100 East 32nd Parkway Ste 225 | 500 | L2 |  |  | 7/27 10D | FEDEX P |  | 7/15 - BOT SIDE 7/18 - AOI | 1B | BAL KIT CLEAR 7/13 | 0 | Advanced Assembly, LLC | Aurora | CO | 80011 |  | 180195459
|  | 2022-07-27 | 109165 (7/6) | 26051 Merit Cir Ste 102 | 1000 | L2 |  |  | 7/27 15D | FEDEX P | DEPANEL | 7/13 - TOP SIDE 7/13 - BACK | 1T | KIT CLEAR 7/6 | 0 | Adagio Medical Inc | Laguna Hills | CA | 92653-7008
|  | 2022-07-26 | 111409 (7/19) | 100 Technology Dr Ste B130 | 100 | L1 |  |  | 7/27 7/26 5D | UPS GND | 7/20 - NEED ARRAY FIELS FOR STENCIL | NEED PROG 7/22 - TOP SIDE 7/22 - AOI | 1T | KIT CLEAR 7/19 - NEED ARRAY FILES | 7 | WaveLynx Technologies | Broomfield, | CO | 80021
|  | 2022-07-26 | 111295 (7/19) | 175 Great Rd | 80 | L1 |  |  | 7/26 5D | FEDEX P | DEPANEL SPECIAL CofC REQ PER ECO 5 | 7/21 - BOT SIDE 7/21 - TOP SIDE 7/21 - AOI | 1B 1T | KIT CLEAR 7/19 | 8 | Vivonics, Inc. | Bedford | MA | 1730
|  | 2022-07-26 | 110643-2 (6/30) | 6750 Crosby Ct | 318 |  |  |  | 7/26 5D | FEDEX P | QTY 450 SMT CLEAR 7/15 SHIPPED QTY 119 7/19 QTY 249 CLEAR BARCODE & MECHANICAL REQ | 7/19 - BACK | 2T | 7/19 - RECV A5 QTY 249 | 10 | Command Alkon, Inc. | Dublin | OH | 43016-7644
|  | 2022-07-25 | 109867 (7/12) | 20108 SAN RAFAEL | 610 |  |  |  | 7/26 10D | UPS Worldwide Express Red | DEPANEL REPEAT OF B106595 W/ CHANGES | 7/13 - TOP SIDE 7/14 - BACK | 1T | KIT CLEAR 7/12 | 0 | ATL Technology CR | DE ALAJUELA | COSTA RICA |  | Warehouse G1-G2-G3-G4-G5 | 9E7173
|  | 2022-07-25 | 110779 (6/30) | 818 W Diamond Ave 3rd Floor | 25 | l1 |  |  | 7/25h 15D | FEDEX GND |  | NEED PROG 7/6 - BOT SIDE 7/7 - AOI | 1B 1T | SMT CLEAR 7/1 7/7 - SHORT 1PC ITEM 33 BTD | 46 | GL Communications | Gaithersburg | MD | 20878-1417
|  | 2022-07-25 | 100616 (6/28) | 3190 Monitor Ave Rm 0220 | 174 | l2 |  |  | 2022-07-25 | FEDEX P | 48 HR PRE BAKE FABS | 7/1 - BOT SIDE 7/5 - TOP SIDE |  | KIT CLEAR 6/28 | 0 | University of Oklahoma | Norman | OK | 73019-5004 | Attn: Kurt Konyalioglu
|  | 2022-07-25 | 108218-3 (5/9) | 230 Horizon Dr Suite 100 | 200 BAL | l3 |  |  | 7/25 20D | FEDEX GND | DEPANEL | NEED PROG 6/29 - BOT SIDE 6/30 TOP SIDE 6/30 AOI | 1B 2T | BAL KIT CLEAR 6/27 | 4 | ICC, Inc. | Verona | WI | 53593-1256
|  | 2022-07-22 | 111604 (7/11) | 250 Moonachie Rd Ste. 400 | 65 64 |  |  |  | 7/27 10D | FEDEX P | PAID REWORK | 7/13 - BACK |  | KIT CLEAR 7/13 | 0 | Sterling Medical Devices | Moonachie | NJ | 07074-1378
|  | 2022-07-22 | 110738 (7/8) | 16772 W Bernardo Dr | 50 | L1 |  |  | 7/22 3D | UPS RED | * 3 DAY TURN * DEPANEL CofC PER ECO NOTE 8 | 7/19 - BOT SIDE 7/20 - TOP SIDE 7/20 - AOI | 1B 1T | FABS DUE 7/11 8:00 AM KIT CLEAR 7/19 | 1 | Modular Medical, Inc. | San Diego | CA | 92127-1904 |  | 4E9R38
|  | 2022-07-22 | 110015 (6/8) | 600 N Field Dr | 50 |  |  | RWK ADDED PO LINE 3 / SHIPPED IN PLACE ON 7/8 | 7/22 10D | FEDEX 2 DAY | ***7/15 - NEED TO REMOVE P400 & SHIP 7/22 DEPANEL CLASS 3 6/23 - WRONG CONN @ P400/410/420/430 7/13 - RECVD PO TO REMOVE CONN | 6/14 - BOT SIDE 6/15 - TOP SIDE 6/15 - AOI | 1B 1T | SMT CLEAR 6/7 SHORT P7 T/H 6/14 7/8 - SHIP IN PLACE | 32 | ICUMedical | Lake Forest | IL | 60045-483
|  | 2022-07-21 | 111162 (7/15) | 1665 Highland Dr Ste C | 2 | L3 |  |  | 7/22 5D | FEDEX P | DEPANEL REF X1100 INSTALL SiT5356 (64 PCS) ON QTY 1 BOARD ONLY *MASK 2ND BOARD* | NEED PROG 7/19 - BOT SIDE 7/19 - TOP SIDE 7/19 - AOI | 1B 1T | KIT CLEAR 7/15 | 8 | Treetown Tech | Ann Arbor | MI | 48108-2297
|  | 2022-07-21 | 104560 (7/8) | 2300 Windy Ridge Pkwy Se Ste 400 | 4 |  |  |  | 7/22 10D | FEDEX P |  | 7/15 - BOT/TOP 7/15 - AOI | 1B 1T | KIT CLEAR 7/8 | 111 | Scientific Research Corporation | Atlanta | GA | 30339-5665 | Attn: JSorenson | 153669597
|  | 2022-07-21 | 111105 (7/13) | 2947 Bradley St Ste 130 | 3 | L3 |  |  | 7/21 3D | FEDEX GND | DEPANEL | NEED PROG 7/18 - BOT/TOP 7/18 - AOI | 1B 1T | KIT CLEAR 7/18 | 42 | Forza Ametek | Pasadena | CA | 91107-1566 | Attn: Nguyen Tran
|  | 2022-07-20 | 111037 (7/12) | 3200 N Kings Hwy | 48 |  |  |  | 7/20 5D | FEDEX P | DEPANEL ***DOUBLE CHK 10K RES SWAP W/ CAP LAST TIME ON B109629 | NEED PROG 7/14 - BOT SIDE 7/14 - TOP SIDE 7/15 - AOI | 1B 1T | KIT CLEAR 7/13 | 39 | Graph-Tech USA, LLC | Fort Pierce | FL | 34951-4051
|  | 2022-07-20 | 110060 (6/28) | 49 Willow Peak Dr | 10 |  |  |  | 7/20 5D | FEDEX P | DEPANEL *POST BAKE 30 MIN* | NEED PROG 7/7 - BOT SIDE 7/8 - TOP SIDE 7/8 - AOI | 2B 3T | COULD CLEAR 6/29 KIT CLEAR 7/13 | 34 | Quantel USA | Bozeman | MT | 59718-9811 |  | 120189263
|  | 2022-07-19 | 100617-3 (6/23) | 3190 Monitor Ave Rm 0220 | 70 | L3 |  |  | 7/22 | #VALUE! |  | 6/28 - BOT/TOP 6/29 - AOI |  | KIT CLEAR 6/23 | 3 | University of Oklahoma | Norman | OK | 73019-5004 | Attn: Redmond Kelley | 749026308
|  | 2022-07-19 | 109833-1 (7/14) | 7205 NE Evergreen Pkwy Ste 100 | 3/297 | 44728 |  |  | 7/21 5D | FEDEX GND |  | 7/15 - BOT/TOP 7/15 - AOI | 1B 1T | KIT CLEAR 7/14 | 12 | Engle Dental Systems LLC | Hillsboro | OR | 97124
|  | 2022-07-19 | 110659 (6/28) | 9503 W Commerce St Bldg 238 | 150 | L1 |  |  | 7/20 5D | FEDEX GND | CLASS 3 DEPANEL | 7/14 - BOT SIDE 7/14 - TOP SIDE 7/14 - AOI | 1B 1T | SHOULD CLEAR 6/28 NO FABS KIT CLEAR 7/13 | 0 | Southwest Research Institute | San Antonio | TX | 78227-130 | Attn: K. Payne - Shipping and Receiving
|  | 2022-07-19 | 107482-2ND (7/11) | 110 Forbes Blvd | 3 | L3 |  |  | 7/20 5D | FEDEX P | ADDED QTY 3 2ND ARTICLE ***SAVE MATL - GOES TO B109249*** | 7/15 - TOP SIDE 7/15 - AOI/BACK | 2T | KIT CLEAR 7/8* (7/13) | 52 | NextPhase Medical Devices | Mansfield | MA | 02048-1145
|  | 2022-07-18 | 107486-2ND (7/8) | 110 Forbes Blvd | 3 | L2 |  |  | 7/20 5D | FEDEX P | ADDED QTY 3 2ND ARTICLE ***SAVE MATL - GOES TO B109249*** | 7/13 - TOP SIDE 7/13 - AOI | 2T | KIT CLEAR 7/7* (7/13) | 60 | NextPhase Medical Devices | Mansfield | MA | 02048-1145
|  | 2022-07-18 | 111367 (7/12) | 5040 Corporate Plaza Dr Ste 11 | 50 | L1 |  |  | 7/19 5D | FEDEX GND | DEPANEL & SAND | NEED PROG 7/13 - BOT SIDE 7/14 - TOP SIDE 7/14 - AOI | 1B 1T | KIT CLEAR 7/12 | 2 | Protocol Insight, LLC | Colorado Springs | CO | 80919-6100 | Attn: Ned | 833337629
|  | 2022-07-15 | 111140 (7/11) | 11100 Johns Hopkins Rd | 10 |  |  |  | 7/15 3D | FEDEX P | *3 DAY TURN * NO MARKINGS / STAMPS ALLOWED | 7/12 - BOT SIDE 7/13 - TOP SIDE 7/13 - AOI | 1B 1T | KIT CLEAR 7/12 | 80 | John Hopkins University Applied Physics Lab | Laurel | MD | 20723-6005 | Attn: JHU APL, Matt Krok
|  | 2022-07-15 | 110643-1 (6/30) | 6750 Crosby Ct | 119/450 |  |  |  | 7/15 5D | FEDEX P | QTY 450 SMT CLEAR QTY 119 T/H CLEAR SHIP QTY 119 BARCODE & MECHANICAL REQ | NEED PROG 7/12 - TOP SIDE QTY 450 SMT DONE 7/12 - AOI | 2T | KIT CLEAR 7/5 | 10 | Command Alkon, Inc. | Dublin | OH | 43016-7644
|  | 2022-07-14 | 110244 (7/7) | 9567 Arrow RTE STE E | 140 |  |  |  | 7/14* 5D | UPS GND | DEPANEL PRE BAKE U1, U2, D3, D4 | NEED PROG 7/11 - BOT SIDE 7/11 - TOP SIDE 7/12 - AOI | 1T | KIT CLEAR 7/7 PROG RECV 7/8 PM | 9 | AQM Acquisition Corp DBA Finna Group | Rancho Cucamonga | CA | 91730-4550 | Attn: Hanh S
|  | 2022-07-14 | 110220-2 (6/2) | 11845 W Olympic Blvd Ste 880W | 300 |  |  | SHIPPED TO SNA FOR PAID REWORK BY AA | 7/13 6/30 10D | FEDEX P | DEPANEL ***EXIT AUDIT & RE-LABEL MATL REQ*** 7/13 - SHIP TO SNA FOR PAID CUST RWK | NEED PROG 6/17 - TOP SIDE 6/17 - AOI | 2T | FABS DUE 6/6 - 6/10 QTY 300 CLEAR - 6/16 BAL KIT CLEAR 6/22 - CUST ISSUDE W/ ASSY | 1 | DMS-Service LLC | Los Angeles | CA | 90064-1149
|  | 2022-07-14 | 110514 (6/30) | 401 N Broad St Suite 222 | 500 |  |  |  | 7/18 7/8h 5D | UPS RED | DEPANEL ECO #4 - J1/J2 USE 60 PCS OF 10147606-00007LF & MARK ASSY'S - BAL USE SM07B-SRSS-TB LF SN | 7/1 - TOP SIDE (ISSUE WITH FLEX IN PANEL - NEED TO RUN SINGLE) 7/6 - AOI | 1T | KIT CLEAR 6/30 CAME IN PANEL BUT HAVE TO RUN SINGLE - NEED MORE TIME | 0 | Biomeme, Inc. | Philadelphia | PA | 19108-1001 |  | 49V91V
|  | 2022-07-14 | 110873 (7/7) | 6750 Crosby Ct | 200 |  |  |  | 7/14 5D | FEDEX P | SAVE ANY EXTRA "A1" AD7712AR & RETURN TO CUST | NEED PROG 7/11 - TOP SIDE 7/12 - AOI | 1T | 7/6 - FABS RECV W NO MOUSE BITE HOLES - DC 1621 NEED TO BAKE KIT CLEAR 7/7 PROG RECV 7/8 PM | 7 | Command Alkon Inc. | Dublin | OH | 43016-7644
|  | 2022-07-13 | 106207 (12/23) | 33 Marsiling Industrial Estate Rd 3 | 150 |  |  |  | 7/14h 10D | FEDEX P | U1 IS BTD - ONLY SHORT 1 PC - SMALL LABELS REQ (CUT & APPLY) | 12/28 - BOT SIDE 6/30 - TOP SIDE 6/30 - AOI |  | *12/23 - BOT CLEAR 6/29 - SHORT 1 PC U1 - KIT CLEAR 6/30 | 20 | Life Technologies |  |  | 739256 | Singapore | 241788121
|  | 2022-07-13 | 111046 (7/7) | 501 Mccormick Dr Ste B | 30 |  |  |  | 7/13 5D | FEDEX P |  | NEED PROG 7/11 - BOT SIDE 7/11 - TOP SIDE 7/12 - AOI | 1B 1T | KIT CLEAR 7/6 PROG RECV 7/8 | 10 | 3G Wireless | Glen Burnie | MD | 21061-8205 |  | 2499 3712 6
|  | 2022-07-12 | 110416-2 (7/5) | 12 Channel st | 5 FA2 | L2 |  |  | 7/14 5D | FEDEX P | DEPANEL | 7/7 - BOT SIDE 7/7 - TOP SIDE 7/7 - AOI | 1B 1T | SHOULD CLEAR 7/6 SHORT ITEM 21 DUE 7/7 | 3 | Innovasea Systems, Inc. | Boston | MA | 2210 | Suite 502 C/o MassRobotics
|  | 2022-07-12 | 109333-1 (7/6) | 8500 Otto Rd | 1/90 | L2 |  |  | 7/13 5D | FEDEX P | QTY 1 FA | NEED PROG 7/8 - TOP SIDE 7/8 - AOI | 1T | KIT CLEAR 7/6 | 22 | Mountain Horse Solutions | Gunpowder | MD | 21010-5410 | Attn: William Schuster
|  | 2022-07-11 | 110784 (6/28) | 6750 Crosby Ct | 432 |  |  |  | 7/13h 10D | FEDEX P |  | 6/28 - TOP SIDE 6/29 - BACK | 1T | KIT CLEAR 6/28 | 2 | Command Alkon Inc. | Dublin | OH | 43016-7644
|  | 2022-07-11 | 110675 (6/8) | 818 W Diamond Ave 3rd Floor | 46 | L2 |  |  | 7/12h 9D | FEDEX GND |  | 6/27 - BOT SIDE 6/27 - TOP SIDE 7/1 - AOI | 1B 1T | SHOULD CLEAR 6/9 - SHORT 29 ITEMS 6/21 - SHORT U13 DUE 6/28 - KIT CLEAR 6/28 | 27 | GL Communications | Gaithersburg | MD | 20878-1417
|  | 2022-07-11 | 110743 (6/17) | 6250 Joyce Dr | 159 | L1 |  |  | 7/11h 15D | FEDEX P | ITEM 19 NEEDS TAPE & REEL (CHARGED CUST) | 6/24 - BOT SIDE 6/27 - TOP SIDE 6/30 - AOI | 1B 1T | KIT CLEAR 6/17 - XTRA CHARGE FOR T&R | 56 | Industrialex Manufacturing | Arvada | CO | 80403
|  | 2022-07-08 | 110978 (6/30) | 777 Lowndes Hill Rd Bldg 3 Ste 160 | 11 |  |  |  | 7/11h 5D | FEDEX P | CLASS 3 DEPANEL ECO 2 - DO NOT LOSE U19 | NEED PROG 7/6 - BOT SIDE 7/6 - TOP SIDE 7/6 - aoi | 1B 2T | 6/30 - ONLY PARTIAL SHORT ITEM 11 - KIT CLEAR 7/1 | 31 | Aeronix, Inc. | Greenville | SC | 29607-2101 | Attn: Ken Wheeler
|  | 2022-07-08 | 111077 (6/28) | 5355 W 76th St Bldg 87 Dock 39 | 200 |  |  |  | 7/12h 9D | UPS RED | T/H ONLY | 6/28 - BACK |  | KIT CLEAR 6/28 | 3 | Beckman Coulter | Indianapolis | IN | 46268-4166 |  | E294W3
|  | 2022-07-08 | 109219-1 (6/15) | 22924 E Appleway Ave | 60 60 60 | 61 60 60 | 62 60 60 | 63 60 60 | 7/10 10/12 11/16 | FEDEX P | DEPANEL - SPLIT SHIPMENTS - DO NOT SHIP EARLY | NEED PROG 6/17 - TOP SIDE 6/17 - AOI | 1T | KIT CLEAR 6/16 | 2 | Frencken America Inc. | Liberty Lake | WA | 99019-9514 | Frencken America, Inc, / Po Box 828 | 234304518
|  | 2022-07-08 | 110888 (7/5) | 1665 Highland Dr Ste C | 40 |  |  |  | 7/11 3D | FEDEX P | * 3 DAY TURN * DEPANEL | NEED PROG 7/7 - BOT SIDE 7/7 - TOP SIDE | 2T | SMT CLEAR 7/5 KIT CLEAR 7/6 | 2 | Treetown Tech | Ann Arbor | MI | 48108-2297
|  | 2022-07-07 | 104576 (6/29) | 3190 Monitor Ave Rm 0220 | 10 |  |  |  | 7/8h 5D | FEDEX P | 7/1 - SCHD HOLD | 7/1 - BOT SIDE 7/5 - TOP SIDE |  | KIT CLEAR 6/29 | 12 | University of Oklahoma | Norman | OK | 73019-5004 | Attn: Kurt Konyalioglu | 749026308
|  | 2022-07-06 | 110220-2 (6/2) | 11845 W Olympic Blvd Ste 880W | 310 |  |  | SHIP IN PLACE 7/6 | 7/13 6/30 10D | FEDEX P | DEPANEL ***EXIT AUDIT & RE-LABEL MATL REQ*** 7/13 - SHIP TO SNA FOR PAID CUST RWK | NEED PROG 6/17 - TOP SIDE 6/17 - AOI | 2T | FABS DUE 6/6 - 6/10 QTY 300 CLEAR - 6/16 BAL KIT CLEAR 6/22 - CUST ISSUDE W/ ASSY | 1 | DMS-Service LLC | Los Angeles | CA | 90064-1149
|  | 2022-07-06 | 107222 (6/22) | 22 Jordan Cove Rd | 142 |  |  |  | 7/8 20D | UPS ORG | CLASS 3 | 6/24 - AOI | 1T | 6/22 - SHORT 2 PC P1 - KIT CLEAR 6/29 | 12 | Coastal Designs, LLC | Waterford | CT | 06385-3227 |  | 238V3V
|  | 2022-07-06 | 109331-1 (5/20) | 21111 N 19th Ave | 4 |  |  |  | 7/7 3D | UPS RED | * 3 DAY TURN * FABS BAKE 6/30 CHECK FOR DELAM | RTR | 1T | DAY 1 IS 7/5 | 7 | Resolution Services, LLC | Phoenix | AZ | 85027-2708 | Attn: Gregg Keith Phoenix, AZ 85027-270 | W496X0
|  | 2022-07-05 | 110795 (6/23) | 1330 Ensell Rd | 220 |  |  |  | 7/7h 9D | FEDEX P | DEPANEL | NEED PROG 6/27 - TOP SIDE 6/28 - BACK | 1T | KIT CLEAR 6/23 | 1 | Hose Monster | Lake Zurich | IL | 60047-1574
|  | 2022-07-05 | 108770-1 (6/22) | 20100 East 32nd Parkway Ste 225 | 500 |  |  |  | 7/7h 10D | FEDEX P | DEPANEL | 6/24 - BOT SIDE 6/27 - TOP SIDE 6/27 - AOI | 1B | KIT CLEAR 6/22 | 0 | Advanced Assembly, LLC | Aurora | CO | 80011 |  | 180195459
|  | 2022-07-05 | 110794 (6/20) | 1330 Ensell Rd | 110 |  |  |  | 7/5h 9D | FEDEX P | DEPANEL | NEED PROG 6/24 - TOP SIDE 6/24 - AOI | 1T | KIT CLEAR 6/20 BUT NEED ARRAY FILES - KIT CLEAR 6/20 | 1 | Hose Monster | Lake Zurich | IL | 60047-1574
|  | 2022-07-01 | 110469 (6/27) | 4505 Campus Dr | 25 | L1 |  |  | 7/5h 5D | FEDEX P | DEPANEL | NEED PROG 6/28 - TOP/BOT 6/29 - AOI | 1B 1T | KIT CLEAR 6/27 | 4 | IonQ, Inc. | College Park | MD | 20740-3899 | Attn: Wendy Casker
|  | 2022-07-01 | 100613-3 (6/14) | 3190 Monitor Ave Rm 0220 | 42 BAL |  |  |  | 7/1 15D | #VALUE! |  | 6/27 - BOT SIDE 6/27 - TOP SIDE 6/28 - BACK |  | KIT CLEAR 6/24 (CF FAB REV) | 4 | University of Oklahoma | Norman | OK | 73019-5004 | Attn: Redmond Kelley | 749026308
|  | 2022-06-30 | 110113-1 (6/1) | 22924 E Appleway Ave - PO Box 828 | 15/30 |  |  |  | 6/30 7/1 | FEDEX GND | SPLIT SHIPMENT *DO NOT SHIP EARLY* | 6/6 - BACK | 2T | SHORT ITEM 34 - OK TO SKIP - QTY 15 CLEAR | 2T | Frencken America, Inc. | Liberty Lake | WA | 99019-9514 |  | 234304518
|  | 2022-06-30 | 110745 (6/17) | 6250 Joyce Dr | 25 |  |  |  | 6/30 9D | FEDEX P | DEPANEL | NEED PROG 6/22 - TOP SIDE 6/22 - AOI | 1T | KIT CLEAR 6/17 | 35 | Industrialex Manufacturing | Arvada | CO | 80403
|  | 2022-06-30 | 108135 (6/8) | 229 Castlewood Dr Ste E | 25 |  |  |  | 6/30 7/1 10D | UPS GND | DEPANEL LD1/LD2 NO TILT | NEED PROG 6/20 - TOP SIDE 6/21 - AOI | 1T | SHOULD CLEAR 6/8 - SHORT D1 DUE 6/17- 6/20 | 30 | Cyber Sciences, Inc. | Murfreesboro | TN | 37129-5167 |  | 2Y63Y7
|  | 2022-06-29 | 104575-2 (9/27) | 3190 Monitor Ave Rm 0220 | 8 |  |  |  | 7/7 10D | FEDEX P |  | 6/22 - BOT SIDE 6/24 - TOP SIDE 6/24 - AOI | 1B 2T | KIT CLEAR 6/17 | 1 | University of Oklahoma | Norman | OK | 73019-5004 | Attn: Kurt Konyalioglu | 749026308
|  | 2022-06-29 | 110195 (6/16) | 1 Executive Dr Suite 101 | 25 |  |  |  | 6/29 9D | FEDEX P | DEPANEL | NEED PROG 6/22 - BOT/TOP 6/22 - AOI | 1B 2T | KIT CLEAR 6/16 | 22 | Spectro Inc. | Chelmsford | MA | 01824-2563 |  | 100055635
|  | 2022-06-29 | 110135-2 (6/9) | 9845 Willows Rd Ne | 105 BAL |  |  |  | 6/29* 5D | FEDEX P | DEPANEL & DEBURR *DNI U8* ISSUE @ R22/R24 PER ECO #2 - WTG CUST CONFIRM | 6/23 - BOT SIDE 6/23 - TOPSIDE 6/23 - AOI | 1B 1T | COULD CLEAR 6/10 - 6/15 ONLY CLEAR FOR QTY 46 - BAL KIT CLEAR 6/22 | 0 | Meta Platforms, Inc. | Redmond | WA | 98052-2540 | Attn: Adam Swett
|  | 2022-06-29 | 110311 (6/22) | 250 48th St | 25 |  |  |  | 6/29 5D | FEDEX GND | DEPANEL SPECIAL LABELING ECO 2 & 3 | 6/24 - TOP SIDE 6/24 - BACK | 1T | KIT CLEAR 6/22 | 11 | IAM Robotics | Pittsburgh | PA | 15201
|  | 2022-06-29 | 109558-3 (6/15) | 459 Fortune Blvd | 980 |  |  |  | 7/6h 10D | FEDEX P | 2ND ARTICLE APPROVED | NEED PROG 6/28 - TOP SIDE 6/28 - AOI | 1B 1T | KIT CLEAR 6/21 | 0 | Reprieve Cardiovascular, Inc. | Milford | MA | 01757-1723 |  | 175218688
|  | 2022-06-29 | 109558-2 (6/15) | 459 Fortune Blvd | 500/1480 |  |  |  | 6/29 10D | FEDEX P | 2ND ARTICLE APPROVED | NEED PROG 6/16 - BOT/TOP 6/17 - AOI | 1B 1T | 6/15 - U8 PARTIAL SHORT | 0 | Reprieve Cardiovascular, Inc. | Milford | MA | 01757-1723 |  | 175218688
|  | 2022-06-29 | 110511 (6/22) | 401 N Broad St Suite 222 | 500 |  |  |  | 6/29 5D | UPS RED | DEPANEL | 6/22 - TOP SIDE 6/23 - AOI | 1T | KIT CLEAR 6/22 | 2 | Biomeme, Inc. | Philadelphia | PA | 19108-1001 |  | 49V91V
|  | 2022-06-28 | 110622 (6/22) | 2455 South Rd | 7 |  |  |  | 6/29 5D | UPS RED | CLASS 3 | 6/23 - TOP SIDE 6/23 - AOI | 1T | KIT CLEAR 6/22 | 55 | Government Contracting Specialists, Inc. | Poughkeepsie | NY | 12601-5463 | BLDG 12-3 ATTN: BRUCE COPELAND/ IBM Corp | 149191
|  | 2022-06-28 | 109361 (5/31) | 1324 W Clairemont Ave Ste 8 | 100 |  |  |  | 6/29 6/23* 10D | UPS GND | SHORT J5 BOT SIDE - BTD (LED DOES NOT FIT DUE TO ADJ PART) 6/21 - DNI LED 6/22 - INSTALL LED @ TILT PER EMAIL | 6/9 - BOT SIDE 6/9 - TOP SIDE 6/10 - AOI | 1B 2T | 5/31 - PARTIAL SHORT C13 - PC FOR D10, D5 & J5 - *ALTA KIT CLEAR 6/9 | 4 | I.D.ology | Eau Claire | WI | 54701-6191 |  | 2VV073
|  | 2022-06-28 | 110392-2 (6/17) | 225 Suburban R | 18 |  |  |  | 6/29 6/22 6/24 5D | FEDEX GND | *PAID EXPEDITE* DEPANEL 3 SHIP TO ADDRESSES | 6/22 - BOT SIDE 6/22 - TOP SIDE 6/27 - AOI | 1B 2T | KIT CLEAR 6/17 6/20 WRONG STANDOFF (DUE 6/22) 9/23 WRONG PART AGAIN | 39 | Inspired Flight | San Luis Obispo | CA | 93401-7546 |  | 965848010
|  | 2022-06-28 | 110318 (6/21) | 250 48th St | 25 |  |  |  | 6/28 5D | FEDEX P | DEPANEL | NEED PROG 6/22 - BOT SIDE 6/23 - TOP SIDE 6/23 - AOI | 1B 1T | KIT CLEAR 6/21 | 15 | IAM Robotics | Pittsburgh | PA | 15201
|  | 2022-06-28 | 104636-3 | 47281 Bayside Pkwy | 200/800 |  |  |  | 6/?? | FEDEX P | DEPANEL *DO NOT SHIP EARLY | 2/23 - BACK | 1B 1T |  | 9 | Enphase Energy | Fremont | CA | 94538-6517 | Attn: PO 2035113 | 442722803
|  | 2022-06-27 | 110538 (6/21) | 5900 Heisley Rd | 240 |  |  |  | 6/28 5D | FEDEX GND | DEPANEL *** NO STAMPS/ MARKINGS ALLOWED ON BOT SIDE | 6/22 - TOP SIDE 6/22 - AOI | 1T | KIT CLEAR 6/21 | 0 | Steris | Mentor | OH | 44060-1834 | Attn: Vince Vlach
|  | 2022-06-27 | 110695 (6/22) | 4200 Church St Ste 1066 | 10 |  |  |  | 6/27 3D | FEDEX P | CLASS 3 D2 IS DNI | 6/23 - BOT SIDE 6/23 - TOP SIDE 6/23 - AOI | 2B 2T | KIT CLEAR 6/22 | 0 | Derive Systems | Sanford | FL | 32771-6933
|  | 2022-06-27 | 110405 (6/20) | 3445 Lake Eastbrook Blvd Se | 5 |  |  |  | 6/27 5D | FEDEX P | DEPANEL | NEED PROG 6/21 - BOT SIDE 6/22 - TOP SIDE 6/22 - AOI | 1B 2T | KIT CLEAR 6/20 | 9 | Dorner Works LTD | Grand Rapids | MI | 49546-5935
|  | 2022-06-27 | 110751 (6/20) | 63 Great Rd Suite 204 | 70 |  |  |  | 6/27 5D | FEDEX P | DEPANEL ASSY REQ WIRES | 6/21 - TOP SIDE 6/21 - AOI | 2T | KIT CLEAR 6/20 | 5 | Dephy, Inc. | Maynard | MA | 01754-2097
|  | 2022-06-24 | 110540 (6/20) | 5900 Heisley Rd | 240 |  |  |  | 6/27 5D | FEDEX GND | DEPANEL *** NO STAMPS/ MARKINGS ALLOWED ON BOT SIDE | 6/21 - TOP SIDE 6/21 - AOI | 1T | KIT CLEAR 6/20 | 0 | Steris | Mentor | OH | 44060-1834 | Attn: Vince Vlach
|  | 2022-06-24 | 110928 (6/17) | 777 Lowndes Hill Rd | 3 |  |  |  | 6/24 5D | FEDEX 2 DAY | CLASS 3 XRAY & SAVE | 6/20 - TOP SIDE 6/21 - AOI | 1B 2T | KIT CLEAR 6/17 - DNI L1 | 26 | Aeronix Inc | Greenville | SC | 29607-2101 | Building 3, Suite 160 attn: Ken Wheeler
|  | 2022-06-24 | 109985 (6/16) | 12000 Jefferson Ave | 6 |  |  |  | 6/24 5D | FEDEX GND | 6/16 - PRE BAKE ITEMS 29,30,41 XRAY & SAVE | NEED PROG 6/17 - BOT SIDE 6/20 - TOP SIDE 6/20 - AOI | 1B 1T | KIT CLEAR 6/21 | 14 | Jefferson Labs | Newport News | VA | 23606-4468 | JSA, LLC / Jefferson LAB Suite 12
|  | 2022-06-23 | 109898-2 (6/17) | 16772 W Bernardo Dr | 63 BAL |  |  |  | 6/23 5D | UPS RED | DEPANEL *PAID EXPEDITE* FABS MUST BE BAKED 6/20 - FABS REJECTED | 6/21 - BOT SIDE 6/21 - TOP SIDE 6/22 - AOI | 1B 1T | FABS DUE 6/20 NEED TO BAKE!!! CANT RUN UNTIL 6/21 - 6/20 - FABS REC & QTY 50 REJ | 1 | South Coast Circuits, Inc. | San Diego | CA | 92127-1904 |  | 4E9R38
|  | 2022-06-23 | 109695-2ND (6/15) | 7051 Industrial Blvd | 45 |  |  |  | 6/23 5D | UPS RED | 2ND ARTICLE APPROVED ANY SHORT PARTS USE FROM B109696 | NEED PROG 6/20 - BOT SIDE 6/20 - TOP SIDE 6/20 - AOI | 1B 1T | KIT CLEAR 6/16 | 11 | ABB, Inc. | Bartlesville | OK | 74006-6036 | Attn: Al Hanchette | 160E6W
|  | 2022-06-23 | 108822 (6/15) | 250 Moonachie Rd Ste. 400 | 150 |  |  |  | 6/23 5D | FEDEX P | DEPANEL | 6/16 - BOT SIDE 6/17 - TOP SIDE 6/17 - AOI | 1B 1T | KIT CLEAR 6/16 | 0 | Sterling Medical Devices | Moonachie | NJ | 07074-1378
|  | 2022-06-23 | 109877-3 (5/16) | 600 N Dekora Woods Blvd | 60 |  |  |  | 2022-06-23 | UPS RED | DEPANEL - DOUBLE CHK L3, L4, U11 - *SPLIT SHIPMENTS* ***CHK SOLDER @ U2- CHK ORIENTATION LED1/3/4 | 5/24 - BOT SIDE 5/25 - TOP SIDE 5/26 - AOI | 1B 1T | KIT CLEAR 5/25 | 20 | Alliance Technology, LLC. | Saukville | WI | 53080-1674 | Insight Vision | 58X386
|  | 2022-06-23 | 110135-1 (6/9) | 9845 Willows Rd Ne | 45/150 |  |  | DID NOT SHIP ON 6/21 DUE TO AA EMAIL FOR R22/R24 | ??? 5D | FEDEX P | DEPANEL & DEBURR *DNI U8* | 6/15 - BOT SIDE 6/16 TOP SIDE 6/16 - AOI | 1B 1T | COULD CLEAR 6/10 - 6/15 ONLY CLEAR FOR QTY 46 | 0 | Meta Platforms, Inc. | Redmond | WA | 98052-2540 | Attn: Adam Swett
|  | 2022-06-23 | 109000 (6/15) | 250 Moonachie Rd Ste. 400 | 150 |  |  |  | 6/23 5D | FEDEX P | DEPANEL | 6/17 - TOP SIDE 6/17 - AOI | 1T | KIT CLEAR 6/16 | 5 | Sterling Medical Devices | Moonachie | NJ | 07074-1378
|  | 2022-06-23 | 110614 (6/10) | 150 Congress St Dock 1 | 15 |  |  |  | 6/23 3D | UPS RED | DEPANEL DNI ITEM 52 | NEED PROG 6/14 - SMT S/U ONLY 6/20 - BOT SIDE - 6/21 - TOP SIDE 6/21 - AOI | 1B 2T | SHORT ITEM 26 & 65 KIT CLEAR 6/14 6/20 | 15 | Markem-Imaje | Keene | NH | 03431-4307 |  | 019989
|  | 2022-06-23 | 110220-1 (6/2) | 11845 W Olympic Blvd Ste 880W | 300/600 |  |  |  | 6/24 10D | FEDEX P | DEPANEL ***EXIT AUDIT & RE-LABEL MATL REQ*** | NEED PROG 6/10 - TOP SIDE 6/13 - AOI | 2T | FABS DUE 6/6 - 6/10 QTY 300 CLEAR | 1 | DMS-Service LLC | Los Angeles | CA | 90064-1149
|  | 2022-06-22 | 110392-1 (6/17) | 225 Suburban R | 12/30 |  |  |  | 6/22 6/24 5D | FEDEX GND | *PAID EXPEDITE* DEPANEL & MECH ASSY 3 SHIP TO ADDRESSES | 6/20 - BOT SIDE 6/20 - TOP SIDE 6/20 - AOI | 1B 2T | KIT CLEAR 6/17 6/20 WRONG STANDOFF (DUE 6/22 8AM) | 39 | Inspired Flight | San Luis Obispo | CA | 93401-7546 |  | 965848010
|  | 2022-06-22 | 110857 (6/15) | 13600 Industrial Park Blvd | 31 |  |  |  | 6/22* 3D | UPS RED | * 3 DAY TURN * DEPANEL *CUST ASKED TO EXP BUT DIDNT WANT TO PAY | NEED PROG 6/17 - TOP SIDE 6/17 - AOI | 1T | ONLY SHORT 2 ITEMS - KIT CLEAR 6/17 - ITEM 14 BTD | 57 | Daikin Applied | Minneapolis | MN | 55441-3743 | Attn: Alan Woolfolk | 5X5937
|  | 2022-06-22 | 110733 (6/13) | 2841 Scott Blvd | 25 |  |  |  | 6/22 5D | UPS RED | DEPANEL SPECIAL C OF C & PS REQ ECO #2 | NEED PROG 6/16 - BOT/TOP 6/16 - AOI | 1B 1T | KIT CLEAR 6/15 | 31 | Roche Sequencing Solutions | Santa Clara | CA | 95050-2549 | Attn: James Borthwick | 8W53E6
|  | 2022-06-21 | 110539 (6/17) | 5900 Heisley Rd | 240 |  |  |  | 6/24 5D | FEDEX GND | DEPANEL | 6/20 - TOP SIDE 6/20 - BACK | 1T | KIT CLEAR 6/17 | 0 | Steris | Mentor | OH | 44060-1834 | Attn: Vince Vlach | 3310-4128-9
|  | 2022-06-21 | 110387 (6/17) | 7002 S Revere Pkwy Ste 60 | 3 |  |  |  | 6/23 5D | FEDEX P | T/H ONLY DEPANEL | 6/17 - BACK |  | KIT CLEAR 6/16 | 2 | Telspan Data | Centennial | CO | 80112-6767
|  | 2022-06-20 | 110487 | 1380 Forest Park Cir Ste 202 | 8 |  |  |  | 6/21 3D | FEDEX GND | HOT!!! DEPANEL ***DO NOT MARK/STAMP BOARDS*** | NEED PROG 6/16 - TOP SIDE 6/17 - AOI/BACK | 2T | 6/10 - WAITING FOR FILES - 6/15 SHORT T/H ONLY - KIT CLEAR 6/16 | 38 | Cardinal Peak, LLC | Lafayette | CO | 80026-3377 |  | 977459036
|  | 2022-06-20 | 108241 (4/8) | 7330 Greendale Rd | 20 |  |  |  | 6/21 10D | FEDEX GND | 6/6 - RECV U8 DAMAGED 15/20 - USE QTY 5 BTD BAL | 4/11 - BOT SIDE 4/12 - BACK | 1B | KIT CLEAR 6/7 | 62 | Plasma Process Group, Inc. | Windsor | CO | 80550-8004
|  | 2022-06-20 | 110512 (6/14) | 401 N Broad St Suite 222 | 500 |  |  |  | 6/21 5D | UPS RED | DEPANEL FAIR REPORT REQ | NEED PROG 6/15 - TOP SIDE 6/16 - AOI | 1T | KIT CLEAR 6/14 | 2 | Biomeme, Inc. | Philadelphia | PA | 19108-1001 |  | 49V91V
|  | 2022-06-17 | 109617-2 (6/6) | 2415 3rd St Ste 232 | 60 |  |  |  | 6/21 10D | FEDEX P | DEPANEL - CofC PER ECO #4 | NEED PROG 6/14 - BOT SIDE 6/15 - TOP SIDE 6/15 - AOI | 1B 1T | KIT CLEAR 6/7 | 0 | Royal Circuit Solutions, Inc. | San Francisco | CA | 94107-3165 | Attn: Dave Desrochers
|  | 2022-06-17 | 110172-2ND (6/10) | 6601 Owens Dr Suite 150 | 15 | 44701 |  |  | 6/20 5D | UPS RED | DEPANEL | 6/13 - BOT SIDE 6/14 - TOP SIDE 6/15 - AOI | 1B 2T | 6/10 - SHORT SMT CONN - KIT CLEAR 6/13 | 54 | Noah Medical | Pleasanton | CA | 94588-3362 |  | 420R7
|  | 2022-06-17 | 110186 (6/3) | 1775 W Hibiscus Blvd Ste 200 | 28 |  |  |  | 6/17 10D | FEDEX 2 DAY | CLASS 3 | NEED PROG 6/8 - AOI | 1B 2T | KIT CLEAR 6/3 | 26 | Aeronix, Inc. | Melbourne | FL | 32901-2627 | Attn: Jeff Smith
|  | 2022-06-16 | 110556 (6/8) | 992 Sids Rd | 43 |  |  |  | 6/16 5D | UPS GND | DOUBLE CHK U21, R26 & R33 PER ECO #1 & 2 - ITEM 36 SHARES W/ 34 | 6/13 - BOT SIDE 6/14 - TOP SIDE 6/14 - AOI | 1B 1T | KIT CLEAR 6/9 | 29 | S & A Systems | Rockwall | TX | 75032-6512 |  | 780849
|  | 2022-06-15 | 110481 (6/8) | 5662 N Plumcreek Ave | 15 |  |  |  | 6/16 5D | UPS GND | PRE-BAKE U101 | 6/9 - BOT SIDE 6/10 - TOP SIDE 6/10 - AOI | 1B 1T | KIT CLEAR 6/8 | 0 | Multitronix, Inc. | Boise | ID | 83713-1350 | Attn: Vernon Knowles | Y8218V
|  | 2022-06-15 | 108218-2 (5/9) | 230 Horizon Dr Suite 100 | 300 |  |  |  | 6/15 5D | FEDEX GND | RAN PARTIAL QTY 300 | NEED PROG 6/1 - AOI | 1B 2T | 5/31 - PARTIAL QTY 300 CLEAR | 4 | ICC, Inc. | Verona | WI | 53593-1256
|  | 2022-06-15 | 110214 (5/18) | 22 Jordan Cove Rd | 142 |  |  |  | 6/15 20D | UPS ORG | T/H ONLY - CLASS 3 |  |  |  | 2 | Coastal Designs, LLC | Waterford | CT | 06385-3227 |  | 238V3V
|  | 2022-06-15 | 110099 (6/2) | 740 S Pierce Ave STE 15 | 30 |  |  |  | 6/13 6/15 5D | FEDEX GND | DEPANEL *SHORT U27* (6/14 DNI U27) | NEED PROG 6/8 - BOT/TOP 6/9 - AOI | 1B 1T | KIT CLEAR 6/6 6/8 - FT PRINT & CONN ISSUE - KIT CLEAR 6/14 DNI U27 | 0 | Bridge Diagnostics, Inc. | Louisville | CO | 80027-3057 |  | 158332655
|  | 2022-06-14 | 110042 (6/8) | 2 Professional Dr Ste 224 | 25 |  |  |  | 6/15 5D | UPS RED | DEPANEL | 6/9 - TOP SIDE 6/9 - AOI | 1T | KIT CLEAR 6/8 | 10 | LKC Technologies | Gaithersburg | MD | 20879-3408 |  | 283561
|  | 2022-06-14 | 110550 (6/8) | 402 E Carrillo St Ste A | 25 |  |  |  | 6/15 4D | FEDEX P | AA XFER JOB DNI R111 | 6/10 - TOP SIDE 6/10 - AOI | 1T | SHOULD CLEAR 6/8 PART C/F'S | 10 | Echo Digital Audio | Santa Barbara | CA | 93101-7467 | Attn: Milo Street
|  | 2022-06-14 | 109830-1 (5/26) | 3281 Grande Vista Dr | 3 FA/47 |  |  |  | 6/14 5D | UPS RED | DEPANEL - BAKE FABS 24 HRS? - BOARD #0001 U4-U7 MUST HAVE IM8G16D3FFDG-125 / BOARDS #0002 & 0003 U4-U7 MUST HAVE IM8G16D3FCDG-125 | NEED PROG 6/8 - NEED TO RUN TOP 1ST 6/9 - TOP SIDE 6/9 - AOI | 2B 1T | FABS DUE 5/31 6/1 6/3 KIT CLEAR 6/7 | 28 | 360 Systems | Newbury Park | CA | 91320-1193 |  | 929-219
|  | 2022-06-14 | 108170 (5/26) | 13131 W Little York Rd - PEP PLT Dock C28 | 30 |  |  |  | 6/13 10D | FEDEX P |  | 5/31 - TOP SIDE 6/1 - AOI | 1B 2T | SMT CLEAR 5/27 - KIT CLEAR 5/31 | 23 | Toshiba International Corp | Houston | TX | 77041-5807 | Attn: Kathleen Stanley
|  | 2022-06-13 | 109006 (6/7) | 250 Moonachie Rd Ste. 400 | 150 |  |  |  | 6/14 5D | FEDEX P | DEPANEL | 6/8 - BOT/TOP 6/8 - AOI | 1B 1T | KIT CLEAR 6/7 | 3 | Sterling Medical Devices | Moonachie | NJ | 07074-1378
|  | 2022-06-13 | 110416-1 (6/3) | 12 Channel st | 5FA/50 |  |  |  | 6/13 5D | FEDEX P | DEPANEL | NEED PROG 4/8 - AOI | 1B 1T | KIT CLEAR 6/6 | 3 | Innovasea Systems, Inc. | Boston | MA | 2210 | Suite 502 C/o MassRobotics
|  | 2022-06-10 | 110196 (6/3) | 21076 Bake Pkwy Ste 104 | 100 |  |  |  | 6/10 5D | FEDEX P | DEPANEL | NEED PROG 6/6 - TOP SIDE 6/8 - AOI | 1T | KIT CLEAR 6/3 | 11 | ButterflyMX, Inc. | Lake Forest | CA | 92630-216
|  | 2022-06-10 | 104910-4 (4/1) *HOT* | 11100 Johns Hopkins Road PO 174227 | 20 BAL |  |  |  | 6/10 5D | FEDEX P | *FAB NOTE: NO VENDOR MARKING PERMITTED* *SEE ECO #3 BEFORE RUNNING **ALSO U2, U32, R63 & R64 HAVE ALT PARTS | 4/4 - RTR 6/6 - BOT SIDE 6/6 - TOP SIDE 6/7 - AOI | 2B 2T | *SHOULD CLEAR 4/4 4/7 - FAB REMAKE FAB DUE 4/21 - QTY 200 FABS CAME 4/28 - STILL SHORT 20 FABS - KIT CLEAR 6/3 | 1 | John Hopkins University Applied Physics La | Laurel | MD | 20723
|  | 2022-06-10 | 109885 (5/20) | 818 W Diamond Ave 3rd Floor | 75 |  |  |  | 6/10 15D | FEDEX GND |  | 5/24 - BOT/TOP 5/25 - AOI | 1B 2T | KIT CLEAR 5/20 | 18 | GL Communications | Gaithersburg | MD | 20878-1417
|  | 2022-06-09 | 109898 (5/23) | 16772 W Bernardo Dr | 37/100 |  |  |  | 6/9 5D | UPS RED | NEED TO EXPEDITE FABS BAKED 6/7 | 6/6 - BOT SIDE 6/8 - TOP SIDE 6/8 - AOI | 1B 1T | FAB DUE 5/26, 5/31 - 6/3 RECV 37 FABS | 1 | South Coast Circuits, Inc. | San Diego | CA | 92127-1904 |  | 4E9R38
|  | 2022-06-09 | 110501 (6/7) | 10950 Pierson Dr Ste 700 | 16 |  |  |  | 2022-06-13 | FEDEX P | * 3 DAY TURN * SHIP SOONER IF POSSIBLE DEPANEL AA XFER JOB | 6/7 - WTG FOR STENCIL FILES 6/9 - BOT/TOP 6/9 - AOI | 1B 1T | KIT CLEAR 6/7 BUT NO ARRAY FILES - FILES RECV 6/8 | 0 | Durbin Group | Fredericksburg | VA | 22408-8083
|  | 2022-06-09 | 110168 (6/1) | 501 Wazee St | 3 |  |  |  | 6/15 10D | WILL CALL | DEPANEL - XRAY & SAVE IMAGES REQ - **SPECIAL XRAY NOTE ON ECO #3 | NEED PROG 6/2 - TOP SIDE 6/2 - AOI | 1T | KIT CLEAR 6/1 | 110 | York Space | Denver | CO | 80204-1858
|  | 2022-06-09 | 110699 (6/6) | 3506 W Lake Center Dr Suite A | 100 |  |  |  | 6/9 3D | FEDEX P | * 3 DAY TURN* SHIP TO AA PER ECO | T/H ONLY |  | KIT CLEAR 6/6 | 24 | Artis LLC | Santa Ana | CA | 92704-6985 |  | 481232988
|  | 2022-06-09 | 109877-2 (5/16) | 600 N Dekora Woods Blvd | 30 |  |  |  | 2022-06-09 | UPS RED | DEPANEL - DOUBLE CHK L3, L4, U11 - *SPLIT SHIPMENTS* ***CHK SOLDER @ U2- CHK ORIENTATION LED1/3/4 | 5/24 - BOT SIDE 5/25 - TOP SIDE 5/26 AOI | 1B 1T | KIT CLEAR 5/25 | 20 | Alliance Technology, LLC. | Saukville | WI | 53080-1674 | Insight Vision | 58X386
|  | 2022-06-09 | 109579 (5/12) | 790 6th St | 26/27 |  |  |  | 6/9 5D | FEDEX P | CLOSE SHORT 1 BOARD - SHIP 26 | NEED PROG 5/31 - BOT/TOP 6/1 - AOI | 1B 2T | SHOULD CLEAR 5/26 - SHORT 1 FAB | 41 | Pacific Northwest National Laboratory | Richland | WA | 99354-1873 | Attn: Mendoza Sara A EDL / 100 / Battelle for US DOE
|  | 2022-06-08 | 110100 (5/25) | 741 Radio Dr | 4 |  |  |  | 6/10 10D | FEDEX P | DEPANEL - XRAY ALL BGA'S & SAVE IMAGES | 5/25 - BOT SIDE 5/26 - TOP SIDE 5/26 - AOI | 1B 2T | SHOULD CLEAR 5/25 - ITEM 25 OK TO SKIP KIT CLEAR 5/26 | 27 | Denmar Technical Services, Inc. | Lewis Center | OH | 43035-7134
|  | 2022-06-08 | 109984 (5/20) | 12455D Research Blvd | 110 |  |  |  | 6/8 10D | FEDEX P | DEPANEL | NEED PROG 5/24 - BOT SIDE 5/26 - TOP SIDE 5/26 - AOI | 2B 1T | SHOULD CLEAR 5/20 - KIT CLEAR 5/24 | 7 | Flextronics America | Austin | TX | 78759-2314 | 12455D Research Blvd | 861230104
|  | 2022-06-08 | 109946 (5/11) | 6040 N Cutter Cir Ste 302 | 30 |  |  |  | 6/7 6/8 10D | FEDEX GND | T/H ONLY - 6/6 - DELAM ARND PEM NUTS |  |  | SHOULD CLEAR 5/13 - KIT CLEAR 5/23 | 68 | Technical Marine Service, Inc. | Portland, | OR | 97217-3955
|  | 2022-06-07 | 109791-1FA (5/31) | 1545 Forbes St | 20 |  |  |  | ??? 10D | FEDEX P | DEPANEL | 6/2 - BOT/TOP 6/2 - AOI | 1B 1T | SHOULD CLEAR 5/31 - SHORT ITEM 22 | 0 | McQ | Fredericksburg | VA | 22405-1606
|  | 2022-06-07 | 110400 (6/3) | 100 Jytek Dr Bldg 2 | 115 |  |  |  | 6/16 9D | FEDEX GND | DEPANEL | 6/6 - AOI |  | KIT CLEAR 6/3 | 0 | Fourstar Connections (Genuine Cable Group) | Leominster | MA | 01453-5917 |  | 227759437
|  | 2022-06-06 | 110019 | 2056 S 1100 E | 13 |  |  |  |  | FEDEX P | RWK |  |  |  | 12 | Ripple, LLC | Salt Lake City | UT | 84106-2319
|  | 2022-06-06 | 109678 (5/26) | 2 Technology Pl | 25 |  |  |  | 6/6 5D | FEDEX GND | DEPANEL | NEED PROG 5/31 - TOP SIDE 6/1 - AOI | 2T | KIT CLEAR 5/27 | 30 | INFICON Inc. | East Syracuse | NY | 13057-9707 |  | 0132-0019-0
|  | 2022-06-06 | 110237 (5/26) | 11100 Endeavor Ct Suite 300 | 110 |  |  |  | 6/6 5D | FEDEX P | STAKING REQ - U23 QTY 40 PIC16F15244-E/REB & QTY 70 PIC16F15244-I/REB | NEED PROG 5/26 - BOT SIDE 5/27 - TOP SIDE 5/31 - AOI | 1B 1T | KIT CLEAR 5/27 | 4 | NAL Research Corporation | Manassas | VA | 20109-4027 |  | 230306168
|  | 2022-06-03 | 109097-1 (5/26) | 2112 Case Pkwy Ste 1 | 55/130 |  |  |  | 6/3 5D | FEDEX P | DEPANEL | 6/1 - AOI | 1B 2T | COULD CLEAR 5/26 - QTY 55 CLEAR 5/26 | 11 | AVID Technologies | Twinsburg | OH | 44087-2378 | Attn:Frank Torrieri
|  | 2022-06-03 | 109768 (5/25) | 641 Spirit Valley Central Dr | 200 |  |  |  | 6/3 5D | FEDEX P | DEPANEL | NEED PROG 5/26 - BOT/TOP 5/31 - AOI | 2T | FABS DUE 5/27 - KIT CLEAR 5/26 | 6 | DE Design Works | Chesterfield | MO | 63005-1030
|  | 2022-06-02 | 110354 (5/26) | 2947 Bradley St Ste 130 | 3 |  |  |  | 6/6 5D | FEDEX P |  | NEED PROG 5/31 - BOT/TOP 5/31 - AOI | 1B 1T | SHOULD CLEAR 5/27 SHORT ITEMS 7 & 9 | 60 | Forza Ametek | Pasadena | CA | 91107-1566
|  | 2022-06-02 | 110288 (5/31) | 4260 Us Highway 1 STE 5 | 45 |  |  |  | 6/6 5D | FEDEX 2 DAY |  | 6/1 - BACK | 1T | KIT CLEAR 5/31 | 4 | Polygenesis | Monmouth Junction | NJ | 08852-1964 |  | 196221875
|  | 2022-06-02 | 109877-1 (5/16) | 600 N Dekora Woods Blvd | 30 30 60 |  |  |  | 6/2 6/9 6/23 | UPS RED | DEPANEL - DOUBLE CHK L3, L4, U11 - *SPLIT SHIPMENTS* | 5/24 - BOT SIDE 5/25 - TOP SIDE 5/26 AOI | 1B 1T | KIT CLEAR 5/25 | 20 | Alliance Technology, LLC. | Saukville | WI | 53080-1674 | Insight Vision | 58X386
|  | 2022-06-01 | 108838 (5/17) | 2845 Delta Dr | 9 |  |  |  | 6/8 5D | FEDEX GND | LED BOARD - LED ALIGNMENT CRITICAL | NEED PROG 5/18 - BOT SIDE 5/19 - TOP SIDE 5/19 - AOI | 1B 1T | SHORT 1PC U2 - KIT CLEAR 6/1 | 4 | Skyline Products, Inc | Colorado Springs | CO | 80910-1010
|  | 2022-06-01 | 110177 (5/19) | 4975 E 41st Ave | 60 |  |  |  | 6/4 9D | FEDEX GND |  | RTR 5/24 - BOT/TOP 5/24 - AOI | 1B 1T | SHOULD CLEAR 5/19 - 5/20 SMT CLEAR - KIT CLEAR 5/23 | 18 | Mount Sopris Instrument | Denver | CO | 80216-4424 | Mount Sopris | 14832441
|  | 2022-05-31 | 108701 (5/18) | 210 Executive Dr Ste 5 | 9 |  |  |  | 6/1 10D | FEDEX GND | DEPANEL | NEED PROG 5/24 - TOP SIDE 5/24 - AOI | 1T | KIT CLEAR 5/18 | 0 | Accudyne Systems, Inc. | Newark | DE | 19702-3335
|  | 2022-05-31 | 108951 (5/18) | 22 Jordan Cove Rd | 138 |  |  |  | 6/1 10D | UPS ORG |  | NEED PROG 5/19 - TOP SIDE 5/20 - AOI | 1B 1T | KIT CLEAR 5/18 | 3 | Coastal Designs, LLC | Waterford | CT | 06385-3227 |  | 238V3
|  | 2022-05-31 | 110040 (5/16) | 140 3rd St PO BOX 707 | 100 |  |  |  | 6/3 10D | UPS GND | DEPANEL *DO NOT WASH* | NEED PROG 5/17 - RAN QTY 50 5/20 - AOI | 1T | SHOULD CLEAR 5/18 5/19 ONLY SHORT 1 PC Q3 - 5/20 BTD | 5 | American Time | Dassel | MN | 55325-0707 |  | 554730
|  | 2022-05-31 | 109558-1 (5/25) | 459 Fortune Blvd | 20 |  |  |  | 6/2 5D | FEDEX P | NEED POGO FIXTURES DEPANEL U1 KAPTON TAPE | 5/31 - BOT/TOP 5/31 - AOI | 1B 1T | FABS DUE 5/20 KIT CLEAR 5/25 | 0 | Reprieve Cardiovascular, Inc. | Milford | MA | 01757-1723 |  | 175218688
|  | 2022-05-27 | 104910-3 (4/1) *HOT* | 11100 Johns Hopkins Road PO 174227 | 180/200 |  |  |  | 5/27 5D | FEDEX P | *FAB NOTE: NO VENDOR MARKING PERMITTED* *SEE ECO #3 BEFORE RUNNING **ALSO U2, U32, R63 & R64 HAVE ALT PARTS | 4/4 - RTR 5/20 - BOT SIDE 5/23 - TOP SIDE 5/25 SMT DONE (3.5 DAYS) | 2B 2T | *SHOULD CLEAR 4/4 4/7 - FAB REMAKE FAB DUE 4/21 - QTY 200 FABS CAME 4/28 - HOLD FOR FA RUN 5/19 - Q1 RECV - STILL SHORT 20 FABS | 1 | John Hopkins University Applied Physics La | Laurel | MD | 20723
|  | 2022-05-27 | 109349-1 (5/9) | 6121 Lincolnia Rd Suite 300A | 128/180 |  |  |  | 5/27 9D | FEDEX GND | RUN PARTIAL QTY 128 SHIP 5/27 | 5/17 - AOI | 1T | 5/9 - PARTIAL CLEAR QTY 128 | 15 | SyTech Corporation | Alexandria | VA | 22312-2764
|  | 2022-05-27 | 108945 (5/19) | 601 Atlantis Rd | 32 |  |  |  | 5/27 3D | FEDEX P | * 3 DAY TURN * | 5/20 - BOT SIDE 5/23 - TOP SIDE 5/24 - BACK | 2B 2T | SHOULD CLEAR 5/19 - #86 BTD | 1 | Anderson Connectivity | Melbourne | FL | 32904-2316
|  | 2022-05-27 | 110172-1FA (5/23) | 6601 Owens Dr Suite 150 | 5/15 | 44701 |  |  | 5/27 5/31 5D | UPS RED | *SHIP SOLDER SAMPLE/ECO # 10* DEPANEL - DNI J1/BTD J5 | NEED PROG 5/24 - BOT SIDE | 1B 2T | KIT CLEAR 5/23 | 54 | Noah Medical | Pleasanton | CA | 94588-3362 |  | 420R7
|  | 2022-05-26 | 109970 (5/16) | 10008 N Harris Farm Rd | 25 |  |  |  | 5/27 5D | FEDEX P | *DO NOT DEPANEL* | NEED PROG 5/24 - BOT/TOP 5/25 - BACK | 1B 2T | DNI U17 - FABS DUE 5/17 ALSO 1 ITEM SHORT - KIT CLEAR 5/20 | 37 | The Ascendancy Group | Spotsylvania | VA | 22553-1975 |  | 6808-3411-3
|  | 2022-05-26 | 108218-2 (5/9) | 230 Horizon Dr Suite 100 | 400 |  |  |  | 5/26 5D | FEDEX GND |  | NEED PROG FSU | 1B 2T | 5/9 - PARTIAL QTY 500 CLEAR | 4 | ICC, Inc. | Verona | WI | 53593-1256
|  | 2022-05-25 | 110030 (5/10) | 440 N Commerce Ave | 30 |  |  |  | 5/27 9D | FEDEX P | DEPANEL - RUN TOP SIDE 1ST PER ECO #4 | NEED PROG 5/17 - BOT/TOP 5/17 - AOI | 1B 1T | SHOULD CLEAR 5/13 KIT CLEAR 5/16 5/17 - AOI | 0 | Allocortech Inc. | Waynesboro | VA | 22980-4029
|  | 2022-05-25 | 109679 (5/6) | 2 Technology Pl | 25 |  |  |  | 5/26 5D | FEDEX GND | DEPANEL - U1 & LS2 PLACE AFTER WASH | NEED PROG 5/23 - BOT/TOP 5/24 - BACK | 1B 2T | SHOULD CLEAR 5/17 KIT CLEAR 5/19 | 33 | INFICON Inc. | East Syracuse | NY | 13057-9707 |  | 1320019
|  | 2022-05-24 | 110022 (5/5) | 818 W Diamond Ave 3rd Floor | 60 |  |  |  | 5/26 15D | FEDEX GND | PRE BAKE U6 | NEED PROG 5/10 - BOT/TOP 5/11 - AOI | 1B 2T | KIT CLEAR 5/5 | 38 | GL Communications | Gaithersburg | MD | 20878-141
|  | 2022-05-24 | 110259 (5/18) | 732 E Utah Valley Dr Ste 12 | 300 |  |  |  | 5/25 5D | FEDEX GND |  | NEED PROG 5/19 - TOP SIDE 5/19 - AOI | 1T | KIT CLEAR 5/18 | 0 | Perkinelmer - UT | American Fork | UT | 84003-9741 |  | 447648865
|  | 2022-05-23 | 110088 (5/10) | 295 Interlocken Blvd Suite 175 | 44 |  |  |  | 5/26 9D | FEDEX GND | STAKING REQ PER ECO #1 | NEED PROG 5/18 - BACK | 1T | KIT CLEAR 5/13 | 16 | Vita Inclinita Technologies | Broomfield | CO | 80021-8005
|  | 2022-05-23 | 110167 5/16) | 7002 S Revere Pkwy Ste 60 | 3 |  |  |  | 5/25 3D | FEDEX P | * 3 DAY TURN * DEPANEL & SAND | NEED PROG 5/20 - BOT/TOP 5/23 - BACK | 1B 1T | FABS DUE 5/18 FABS RECV 5/19 NEED BAKE | 56 | Telspan Data | Centennial | CO | 80112-6767 |  | 342527426
|  | 2022-05-23 | 109617-1FA (5/16) | 2415 3rd St Ste 232 | 5/60 |  |  |  | 5/25 5D | FEDEX P | DEPANEL - CofC PER ECO #4 | NEED PROG 5/19 - BOT/TOP 5/20 - AOI | 1B 1T | FABS DUE 5/16 KIT CLEAR 5/18 | 0 | Royal Circuit Solutions, Inc. | San Francisco | CA | 94107-3165 | Attn: Dave Desrochers
|  | 2022-05-23 | 108947 (4/29) | 103 Quality Cir Nw Ste 220 | 300 |  |  |  | 5/25 10D | FEDEX P | DEPANEL & DEBURR | NEED PROG 5/16 - BOT SIDE 5/17 - AOI | 1B 2T | FABS DUE 5/4 *200 CUT TAPE 2 PER KIT CLEAR 5/11 | 3 | Scientific Research Corporation | Huntsville | AL | 35806-453 | Attn: Graehm Sack | 153669597
|  | 2022-05-20 | 106484 (5/10) | 2947 Bradley St Ste 130 | 2 |  |  |  | 5/25 5D | FEDEX P |  | 5/17 - TOP SIDE 5/17 - AOI | 2T | 5/11 - SHORT U9 - OK TO SKIP KIT CLEAR 5/18 | 84 | Forza Ametek | Pasadena | CA | 91107-1566
|  | 2022-05-20 | 109942-1FA (5/18) | 4 Constitution Way | 10/190 | 44694 |  |  | 5/25 5D | UPS RED | DEPANEL | NEED PROG 5/18 - BOT/TOP 5/18 - AOI | 1B 1T | KIT CLEAR 5/18 | 4 | Servomex Inc | Woburn | MA | 01801-8510 |  | 014478
|  | 2022-05-20 | 108252-2 (3/15) | 5100 Boyd Lake Ave | 103 BAL |  |  |  | 5/24 10D | FEDEX 2 DAY |  | 5/16 - AOI |  | SHIP 147 3/29 - BAL KIT CLEAR 5/10 | 5 | Danhydra, Inc. | Loveland | CO | 80538-8944
|  | 2022-05-20 | 108735 (4/28) | 401 N Broad St Suite 222 | 500 |  |  |  | 5/20 15D | FEDEX GND |  | 5/6 - BOT DONE 5/11 - TOP SIDE 5/17 - AOI | 1B 1T | KIT CLEAR 4/27 (ALTA) | 7 | Biomeme, Inc. | Philadelphia | PA | 19108-1001 |  | 49V91V
|  | 2022-05-19 | 108603-2 (5/18) | 1001 W Algonquin St Dock D/E | 10 BAL |  |  |  | 3/23 3D | FEDEX P | * 3 DAY TURN * | FSU | 1B 1T | BAL KIT CLEAR 5/18 | 26 | Raven - Aerostar International, Inc. | Sioux Falls | SD | 57104-0319
|  | 2022-05-19 | 109695-1 (5/16) | 7051 Industrial Blvd | 5 |  |  |  | 5/20 3D | UPS RED | * 3 DAY TURN * | NEED PROG 5/18 - BOT/TOP 5/18 - AOI | 1B 1T | FABS DUE 5/16 | 11 | ABB, Inc. | Bartlesville | OK | 74006-6036 | Attn: Al Hanchette | 160E6W
|  | 2022-05-19 | 109696-1 (5/16) | 7051 Industrial Blvd | 5 |  |  |  | 5/20 3D | UPS RED | * 3 DAY TURN * | NEED PROG 5/18 - BOT/TOP 5/18 - AOI | 1B 1T | FABS DUE 5/16 | 11 | ABB, Inc. | Bartlesville | OK | 74006-6036 | ATTN: Brian Smith | 160E6W
|  | 2022-05-19 | 110176 (5/12) | 891 Feehanville Drive | 5 |  |  |  | ??? 3D | UPS BLU | * 3 DAY TURN * DEPANEL | 5/16 - BOT SIDE 5/16 - TOP SIDE 5/16 - AOI | 2B 2T | SKIP ITEM 21 - DOES NOT FIT - PART CONF ITEM 75 (TOP) | 0 | Cummins-Allison Corp. | Mt. Prospect | IL | 60056 |  | 655983
|  | 2022-05-18 | 109536-2 (4/29) | 817 W High St | 150 BAL |  |  |  | 5/19 5D | FEDEX P | QTY 114 BOT DONE, QTY 150 BARE | NEED PROG SET UP HOLD 5/10 - BOT SIDE 5/16 - AOI | 2B 2T | 5/4 BAL FABS RECV - STILL SHORT PARTS - KIT CLEAR 5/10 | 0 | Sea Land Aire | Jackson | MI | 49203-2986
|  | 2022-05-18 | 110095 (5/16) | 5660 Airport Blvd Ste 101 | 100 |  |  |  | 5/19 3D | UPS GND | * 3 DAY TURN * T/H ONLY |  |  |  | 1 | Churchill Navigation dba Shotover Systems Inc | Boulder | CO | 80301-2596 |  | R8A959
|  | 2022-05-18 | 109847-4 (5/3) | 10525 Willows Rd Ne | 210 BAL |  |  |  | 5/18 10D | FEDEX P | DEPANEL | NEED PROG 5/3 - BOT SIDE 5/4 - TOP SIDE 5/5 - AOI/BACK | 1B 2T | *5/3 - SHORT R149 - OK TO SKIP ON QTY 30. QTY 30 CLEAR KIT CLEAR 5/4 | 1 | Facebook Technologies, LLC | Redmond | WA | 98052-2545 | Attn: Wei Sun (Protoline Materials)
|  | 2022-05-17 | 109847-3 (5/3) | 10525 Willows Rd Ne | 160 |  |  |  | 5/18 10D | FEDEX P | DEPANEL | NEED PROG 5/3 - BOT SIDE 5/4 - TOP SIDE 5/5 - AOI/BACK | 1B 2T | *5/3 - SHORT R149 - OK TO SKIP ON QTY 30. QTY 30 CLEAR KIT CLEAR 5/4 | 1 | Facebook Technologies, LLC | Redmond | WA | 98052-2545 | Attn: Wei Sun (Protoline Materials)
|  | 2022-05-17 | 109054 (5/10) | 1 Km Noreste Del Centro Commercial Real | 1 |  |  |  | 5/18 5D | FEDEX INT P | DEPANEL | NEED PROG 5/16 - AOI | 1B 1T | KIT CLEAR 5/11 | 94 | ICUMedical Costa Rica | LA AURORA | COSTA RICA | 40104 |  | 3369-9581-7
|  | 2022-05-17 | 109419-2 (5/2) | 6250 Joyce Dr | 11 BAL |  |  |  | 5/17 5D | FEDEX P | * 3 DAY TURN * SOLDER VOIDS <20% | NEED PROG 5/7 - BOT SIDE 5/9 - TOP SIDE 5/11 - AOI | 2B 2T | SHOULD CLEAR SOON - DNI ITEM 53 KIT CLEAR 5/10 | 3 | Industrialex Manufacturing | Arvada | CO | 80403
|  | 2022-05-17 | 109536-1 (4/29) | 817 W High St | 150/300 |  |  |  | 5/17 5D | FEDEX P | *QTY 36 DONE, 114 BOT DONE | NEED PROG 5/3 - BOT SIDE 5/4 - AOI | 2B 2T | KIT CLEAR 4/29 4/29 0NLY 150 FABS RECVD - KIT CLEAR 5/4 KIT CLEAR 5/10 | 0 | Sea Land Aire | Jackson | MI | 49203-2986
|  | 2022-05-16 | 109941 (5/10) | 1665 Highland Dr Ste C | 2 |  |  |  | 5/16 5D | UPS RED |  | NEED PROG 5/16 - BACK | 1B 1T | KIT CLEAR 5/10 | 9 | Treetown Tech | Ann Arbor | MI | 48108-2297 |  | 7194E3
|  | 2022-05-16 | 108218-1 (5/9) | 230 Horizon Dr Suite 100 | 100/ 1000 |  |  |  | 5/16 5D | FEDEX GND |  | NEED PROG FSU | 1B 2T | 5/9 - PARTIAL QTY 500 CLEAR | 4 | ICC, Inc. | Verona | WI | 53593-1256
|  | 2022-05-16 | 109527 (5/9) | 10950 Pierson Dr Ste 700 | 50 |  |  |  | 5/16* 3D | FEDEX P | * 3 DAY TURN * DEPANEL *DO NOT SHIP MATL BACK | NEED PROG 5/11 - BOT SIDE 5/12 - TOP SIDE 5/16 - AOI | 1B 1T | FABS DUE 5/10 KIT CLEAR 5/11 | 0 | Durbin Group | Fredericksburg | VA | 22408-8083
|  | 2022-05-13 | 108737 (4/13) | 101 Billerica Ave Bldg #3 | 12 |  |  |  | 4/26* 5/23 9D | FEDEX GND | ECO NOTE 1 - CHK U3/U5 PART #S BEFORE SMT | RTR (SHORT) 4/28 - BOT SIDE 5/2 - BACK | 1B 1T | SHOULD CLEAR 4/13 4/14 - NOW WTG FOR U3/5 NEW PARTS KIT CLEAR 5/10 | 28 | Segue Manufacturing Services, LLC | North Billerica | MA | 01862-1271 |  | 152136714
|  | 2022-05-13 | 108472-2 (4/21) | 6250 Joyce Dr | 138 BAL |  |  |  | 5/13 10D | FEDEX P | QTY 12 PAID EXPEDITE | 5/2 - AOI | 1B 1T | *SHORT U3, U14, L1 | 4 | Industrialex Manufacturing | Arvada | CO | 80403
|  | 2022-05-13 | 109689 (4/29) | 13600 Industrial Park Blvd | 20 |  |  |  | 5/13 5D | UPS RED |  | NEED PROG 5/9 - TOP SIDE 5/9 - AOI | 1T | FABS DUE 5/4 - KIT CLEAR 5/6 | 30 | Daikin Applied | Minneapolis | MN | 55441-3743 | Attn: Alan Woolfolk | 5X5937
|  | 2022-05-13 | 108907 - 3 (3/22) | 3881 Mcgowen St | 21 BAL |  |  |  | 5/17 5D | FEDEX P | T/H ONLY - QTY 23 SHIPPED 4/4, 21 SHIPPED 4/29 |  | T/H | 3/23 - SHORT 1 ITEM AND PARTIAL SHORT 2 ITEMS - KIT CLEAR 5/10 | 70 | Royal Circuits | Long Beach | CA | 90808-1702
|  | 2022-05-12 | 109694 (5/3) | 2 Technology Pl | 10 |  |  |  | 5/12 5D | FEDEX GND |  | NEED PROG 5/9 - BOT SIDE 5/10 - AOI | 1B 2T | *COULD CLEAR 5/3 KIT CLEAR 5/5 | 39 | INFICON Inc. | East Syracuse | NY | 13057-9707 |  | 0132-0019-0
|  | 2022-05-12 | 109774 (5/5) | 9845 Willows Rd Ne | 100 |  |  |  | 5/12 5D | FEDEX 2 DAY | *IC1_A BTD - 15/PER - MAKE SURE TO LOAD 100% | 5/6 - BOT SIDE 5/7 - TOP SIDE 5/9 - AOI | 2B 1T |  | 45 | Meta Platforms, Inc | Redmond | WA | 98052-2540
|  | 2022-05-11 | 109493 (5/2) | 4505 Campus Dr | 15 |  |  |  | 5/12 5D | FEDEX P |  | NEED PROG 5/6 - BOT/TOP 5/9 - AOI | 1B 2T | KIT CLEAR 5/5 | 12 | IonQ, Inc. | College Park | MD | 20740-3899 | Attn: Wendy Casker
|  | 2022-05-11 | 109419-1 (5/2) | 6250 Joyce Dr | 3/14 |  |  |  | 5/12 3D | FEDEX P | * 3 DAY TURN * SOLDER VOIDS <20% | NEED PROG 5/7 - BOT SIDE 5/9 - TOP SIDE 5/10 - AOI | 2B 2T | SHOULD CLEAR SOON - DNI ITEM 53 KIT CLEAR 5/9 | 3 | Industrialex Manufacturing | Arvada | CO | 80403
|  | 2022-05-11 | 109427 (4/26) | 6300 Wissahickon Ave | 10 |  |  |  | 5/11 5D | FEDEX P | ECO #6 - WIRES REQ | 5/5 - BOT/TOP 5/6 - AOI | 1B 1T | FABS DUE 4/27 KIT CLEAR 5/4 | 2 | South Coast Circuits, Inc. | Philadelphia | PA | 19144-3722
|  | 2022-05-11 | 109578-4 (4/26) | 4611 Bee Caves Rd | 230 BAL |  |  |  | 5/4 5D | UPS RED | *SEND PHOTOS OF 1ST T/H BOARD (BATT CLIP) ECO | NEED PROG 4/27 - TOP 4/29 AOI/BACK | 2T | 4/26 SMT CLEAR KIT CLEAR 4/27 *NEED TO REQUOTE | 4 | Swift Sensors | Austin | TX | 78746-5220 |  | 1Y4541
|  | 2022-05-11 | 108749 (4/12) | 510 Lansdowne Rd | 400 |  |  |  | 5/17 25D | FEDEX GND | *FABS MUST BE SERIAL # SILK SCREENED *EXIT AUDIT REQ *SHIPPING SEE ECO #5 *CofC MUST LIST SER #S - FABS MUST BE DEBURRED | 4/13 - RUN TOP SIDE FIRST 4/14 - TOP SIDE DONE QTY 350 4/26 - BOT SIDE 4/26 - AOI | 2T 1B | 4/12 - 90 FAB REJ WRONG SER # & NO SER # - 4/15 RECV 40 MORE FABS W/ SER #S | 0 | HDT Robotics | Fredericksburg | VA | 22408-7302
|  | 2022-05-11 | 109720 (5/4) | Phion Technologies | 4 |  |  |  | 5/11 3D | FEDEX P | * 3 DAY TURN * SHIPPING SEE ECO #2 & 7 - CUST PICK UP | NEED PROG 5/5 - BOT SIDE 5/9 - TOP SIDE 5/9 - AOI | 1B 2T | PARTIAL SHORT U30 - KIT CLEAR 5/6 | 15 | Phion Technologies | Oakland | CA | 94621-2042 | Phion Technologies | 770955750
|  | 2022-05-10 | 109688 (5/3) | 13600 Industrial Park Blvd | 20 |  |  |  | 5/10 5D | UPS RED |  | NEED PROG 5/5 - BACK | 1T | KIT CLEAR 5/3 | 30 | Daikin Applied | Minneapolis | MN | 55441-3743 | Attn: Alan Woolfolk | 5X5937
|  | 2022-05-10 | 109250 (5/4) | 125 North Drive | 75 |  |  |  | 5/11 5D | FEDEX P |  | NEED PROG 5/5 - BOT/TOP 5/6 - AOI | 1B 1T | *COULD CLEAR SOON | 0 | Kopin Corporation | Westborough | MA | 1581 |  | 180195459
|  | 2022-05-10 | 109629-1 (4/29) | 3200 N Kings Hwy | 2 FA |  |  |  | 5/12 5D | UPS GND |  | NEED PROG 5/6 - BOT/TOP 5/6 - AOI | 1B 1T | 4/29 - SHORT U9, U34, U35 OK TO SKIP | 47 | Graph-Tech USA, LLC | Fort Pierce | FL | 34951-4051 |  | 04Y70W
|  | 2022-05-09 | 109847-3 (5/3) | 10525 Willows Rd Ne | 20 |  |  |  | 5/18 10D | FEDEX P | DEPANEL | NEED PROG 5/3 - BOT SIDE 5/4 - TOP SIDE 5/5 - AOI/BACK | 1B 2T | *5/3 - SHORT R149 - OK TO SKIP ON QTY 30. QTY 30 CLEAR KIT CLEAR 5/4 | 1 | Facebook Technologies, LLC | Redmond | WA | 98052-2545 | Attn: Wei Sun (Protoline Materials)
|  | 2022-05-09 | 104910-2 (4/1) *HOT* | 11100 Johns Hopkins Road PO 174227 | 20/220 11 OK 9 BAL |  |  |  | 5/3 5/6 3D *DELAY DUE TO FAB RWK | FEDEX P | *FAB NOTE: NO VENDOR MARKING PERMITTED* *SEE ECO #3 BEFORE RUNNING **ALSO U2, U32, R63 & R64 HAVE ALT PARTS | 4/4 - RTR 4/28 - BOT SIDE 4/29 - TOP SIDE 5/2 - AOI SHIPPED QTY 11 5/6 | 2B 2T | *SHOULD CLEAR 4/4 4/7 - FAB REMAKE FAB DUE 4/21 - FABS CAME 4/28 | 1 | John Hopkins University Applied Physics La | Laurel | MD | 20723
|  | 2022-05-09 | 108909-3 (5/3) | 5511 Capital Center Dr | 2 BAL |  |  |  | 5/10 2D | FEDEX P | **2 DAY TURN** 5/4 - DELAM BOT SIDE QTY 2/8 - 5/5 RUN 1 TOP SIDE | 5/3 - BOT SIDE 5/9 - TOP SIDE 5/9 - AOI | 1B 2T | KIT CLEAR 5/5 | 36 | Plexus Engineering Solutions | Raleigh | NC | 27606-3380 | Ste P125 PLXS-ENG RDC receiving
|  | 2022-05-09 | 108909-2 (5/3) | 5511 Capital Center Dr | 3 |  |  |  | 5/9 2D | FEDEX P | **2 DAY TURN** 5/4 - DELAM BOT SIDE QTY 2/8 - 5/5 RUN 1 TOP SIDE | 5/3 - BOT SIDE 5/5 - TOP SIDE 5/6 - QTY 6 DONE | 1B 2T | KIT CLEAR 5/5 SHIPPED QTY 3 5/6 | 36 | Plexus Engineering Solutions | Raleigh | NC | 27606-3380 | Ste P125 PLXS-ENG RDC receiving
|  | 2022-05-06 | 108909-1 (5/3) | 5511 Capital Center Dr | 3 |  |  |  | 5/5 2D | FEDEX P | **2 DAY TURN** 5/4 - DELAM BOT SIDE QTY 2/8 - 5/5 RUN 1 TOP SIDE | 5/3 - BOT SIDE 5/5 - TOP SIDE 5/6 - QTY 6 DONE | 1B 2T | KIT CLEAR 5/5 | 36 | Plexus Engineering Solutions | Raleigh | NC | 27606-3380 | Ste P125 PLXS-ENG RDC receiving
|  | 2022-05-06 | 104910-1 (4/1) *HOT* | 11100 Johns Hopkins Road PO 174227 | 20/220 11 OK 9 BAD |  |  |  | 5/3 5/6 3D *DELAY DUE TO FAB RWK | FEDEX P | *FAB NOTE: NO VENDOR MARKING PERMITTED* *SEE ECO #3 BEFORE RUNNING **ALSO U2, U32, R63 & R64 HAVE ALT PARTS | 4/4 - RTR 4/28 - BOT SIDE 4/29 - TOP SIDE 5/2 - AOI | 2B 2T | *SHOULD CLEAR 4/4 4/7 - FAB REMAKE FAB DUE 4/21 - FABS CAME 4/28 | 1 | John Hopkins University Applied Physics La | Laurel | MD | 20723
|  | 2022-05-06 | 109578-3 (4/26) | 4611 Bee Caves Rd | 300 BAL |  |  |  | 5/4 5D | UPS RED | *SEND PHOTOS OF 1ST T/H BOARD (BATT CLIP) ECO | NEED PROG 4/27 - TOP 4/29 AOI/BACK | 2T | 4/26 SMT CLEAR KIT CLEAR 4/27 *NEED TO REQUOTE | 4 | Swift Sensors | Austin | TX | 78746-5220 |  | 1Y4541
|  | 2022-05-06 | 109189 (4/29) | 4975 E 41st Ave | 25 |  |  |  | 5/6 5D | FEDEX GND | C26A/B/C SOLDERED ON TOP OF R19/28/31 SEE ECO #1 - TEST POINTS MUST BE @ SPEC ANGLE | 5/2 - BOT SIDE 5/3 - TOP SIDE 5/3 - AOI | 1B 1T | KIT CLEAR 4/29 | 22 | Mount Sopris Instruments | Denver | CO | 80216-4424 |  | 148324417
|  | 2022-05-06 | 109340 (4/28) | 104 Otis St | 10 |  |  |  | 5/6 5D | FEDEX P | SAVE XRAY IMAGES FINAL INSPECTION REPORT REQ | 5/2 - BOT SIDE 5/2 - TOP SIDE 5/3 - AOI | 1B 2T | 4/28 - U13/14 PART CONF. KIT CLEAR 4/28 | 49 | ATSE, LLC | Northborough | MA | 01532-2440
|  | 2022-05-06 | 108725 (4/21) | 3451 E Harbour Dr | 10 |  |  |  | 5/9 5D | UPS GND |  | 5/2 - BOT/TOP 5/3 - AOI | 1B 2T | *SHORT FAB - DUE 5/2 - KIT CLEAR 5/2 | 31 | CollabraTech Solutions, LLC | Phoenix | AZ | 85034-7229 |  | Y85858
|  | 2022-05-05 | 109578-2 (4/26) | 4611 Bee Caves Rd | 100 |  |  |  | 5/4 5D | UPS RED | *SEND PHOTOS OF 1ST T/H BOARD (BATT CLIP) ECO | NEED PROG 4/27 - TOP 4/29 AOI/BACK | 2T | 4/26 SMT CLEAR KIT CLEAR 4/27 *NEED TO REQUOTE | 4 | Swift Sensors | Austin | TX | 78746-5220 |  | 1Y4541
|  | 2022-05-05 | 109847-1 (5/3) | 10525 Willows Rd Ne | 10/400 |  |  |  | 5/9 5/5 3D | FEDEX P | QTY 10 PAID EXPEDITE | NEED PROG 5/3 - BOT SIDE 5/3 - TOP SIDE 5/5 - BACK | 1B 2T | *5/3 - SHORT R149 - OK TO SKIP ON QTY 30. QTY 30 CLEAR 5/3 | 1 | Facebook Technologies, LLC | Redmond | WA | 98052-2545 | Attn: Wei Sun (Protoline Materials)
|  | 2022-05-05 | 108974 (4/18) | 845 W Center St | 160 |  |  |  | 5/19 20D | FEDEX 2 DAY |  | 4/22 - TOP SIDE 4/22 - AOI | 2T | 4/18 - PACKAGE W SHORTAGES/FABS LOST | 0 | Marshall Radio Telemetry Inc | North Salt Lake | UT | 84054-2916 |  | 181712317
|  | 2022-05-04 | 109578-1 (4/26) | 4611 Bee Caves Rd | 100/500 |  |  |  | 5/4 5D | UPS RED | *SEND PHOTOS OF 1ST T/H BOARD (BATT CLIP) ECO | NEED PROG 4/27 - TOP 4/29 AOI/BACK | 2T | 4/26 SMT CLEAR KIT CLEAR 4/27 *NEED TO REQUOTE | 4 | Swift Sensors | Austin | TX | 78746-5220 |  | 1Y4541
|  | 2022-05-04 | 109529 (4/27) | 225 Suburban Rd | 33 |  |  |  | 5/4 5D | FEDEX P | PRESS FIT REQ | 4/27 - BOT SIDE 4/27 - TOP SIDE 4/28 - AOI | 1B 2T | KIT CLEAR 4/27 - ITEM 29 CUT TAPE (52 PCS) | 25 | Inspired Flight | San Luis Obispo | CA | 93401-7546
|  | 2022-05-03 | 108734 (4/22) | 401 N Broad St Suite 222 | 500 |  |  |  | 5/13 15D | FEDEX GND | HAND LOAD U3, U4, U5 PER ECO #3 | 4/25 - TOP SIDE 4/26 - AOI | 1T | KIT CLEAR 4/22 | 0 | Biomeme, Inc. | Philadelphia | PA | 19108-1001 |  | 49V91V
|  | 2022-05-03 | 108039 (4/20) | 1960 Old Cuthbert Rd Ste 100 | 5 |  |  |  | 5/4 10D | FEDEX P | QR LABEL "NOT" REQ | 4/21 - AOI | 2B 2T | KIT CLEAR 4/20 | 40 | Harsco Rail | Cherry Hill | NJ | 08034-1456
|  | 2022-05-03 | 109262 (4/19) | 45150 Business Ct | 22 QTY 16 CLEAR |  |  |  | ??? 10D | FEDEX GND | MIXED POP @ U1 SEE ECO #1 *X-RAY REQ - SAVE IMAGES | 4/20 - TOP SIDE 4/20 - AOI | 1T | FAB DUE 4/20 & SHORT PARTIAL 6 PCS U1 | 12 | CACI | Sterling | VA | 20166-6750 | Suite 440 Attn: Jennifer Miller
|  | 2022-05-03 | 108988 (4/20) | 91 Sandy Ridge Roa | 4 |  |  |  | 5/11 15D | FEDEX GND |  | 4/21 - AOI | 1B 1T | KIT CLEAR 4/20 | 12 | DWB Design Inc. | Fredericksburg | VA | 22405
|  | 2022-05-03 | 107215-2ND (5/2) | 1510 Fm 3224 | 4 BAL |  |  |  | 5/5 3D | FEDEX P | * 3 DAY TURN * T/H ONLY | 5/2 - BACK | T/H | KIT CLEAR 5/2 | 27 | Peraton | Palestine | TX | 75803-2169 |  | 195294062
|  | 2022-05-03 | 109612 (4/28) | 3 Henry Drive | 24 |  |  |  | 5/3 3D | FEDEX P | ** 3 DAY TURN ** | FSU | 1T | KIT CLEAR 4/28 4/29 - TOP SIDE 4/29 - BACK | 0 | HII Unmanned Systems, Inc | Pocasset | MA | 02559-1415 | attn: VITO/ DUSTY | 253053240
|  | 2022-05-02 | 109555 (4/25) | 248 Main Dunstable Rd | 5 |  |  |  | 5/4 3D | FEDEX P | ** 3 DAY TURN ** WIRE RWK FOR U44 REQUIRED - SEE INSTRUCTIONS - DNI J9 | 4/26 - BOT SIDE 4/27 - TOP SIDE 4/27 - AOI | 2B 2T | *4/26 SHORT Y1 - DUE 5/2 - KIT CLEAR 4/29 | 71 | Locus Robotics | Nashua | NH | 03062-1914 | Attn: William Twomey
|  | 2022-05-02 | 109879 (4/28) | 21 Alpha Rd Suite 202 | 50 |  |  |  | 5/2 2D | FEDEX P | ** 2 DAY TURN ** | 4/29 - AOI | 1T | 4/28 - U1 WTG CONF. KIT CLEAR 4/28 | 2 | Atlas Devices | Chelmsford | MA | 01824-4170 |  | P1 370758867
|  | 2022-05-02 | 108472-1 (4/21) | 6250 Joyce Dr | 12/150 |  |  |  | 5/2 5D | FEDEX P | QTY 12 PAID EXPEDITE | 4/25 - AOI | 1B 1T | *SHORT U3, U14, L1 | 4 | Industrialex Manufacturing | Arvada | CO | 80403
|  | 2022-04-29 | 106389 (4/14) | 250 Apollo Rd | 25 |  |  |  | 5/6 15D | UPS GND |  | 4/18 - AOI | 1B 1T | *FABS DUE 4/15 KIT CLEAR 4/15 | 22 | Crow Engineering | Montrose | CO | 81401
|  | 2022-04-29 | 108907 - 2 (3/22) | 3881 Mcgowen St | 21 |  |  |  | 4/29 5D | FEDEX P | T/H ONLY - QTY 23 SHIPPED 4/4 |  | T/H | 3/23 - SHORT 1 ITEM AND PARTIAL SHORT 2 ITEMS | 70 | Royal Circuits | Long Beach | CA | 90808-1702
|  | 2022-04-29 | 109186 (4/5) | 4975 E 41st Ave | 25 |  |  |  | 4/29 5D | FEDEX GND | 4/22 - DNI Q3 | 4/5 NEED PROG 4/7 - BOT SIDE DONE 4/25 - AOI | 1B 1T | 4/5 - BOT SIDE CLEAR ONLY - 4/22 TOP CLEAR | 22 | Mount Sopris Instruments | Denver | CO | 80216-4424 |  | 148324417
|  | 2022-04-29 | 109154-3 (4/15) | 600 N Dekora Woods Blvd | 22 10D |  |  |  | 50-4/29 | UPS RED | ECO NOTE 3 - PREVIOUS ISSUES @ L3/L4/U11 | 4/19 - BOT SIDE 4/19 - TOP SIDE 4/19 - AOI | 2T | *KIT CLEAR FOR QTY 72 4/18 - STILL SHORT FOR BAL 28 | 20 | Alliance Technology, LLC. | Saukville | WI | 53080-1674 | Insight Vision | 58X386
|  | 2022-04-29 | 109154-4 (4/15) | 600 N Dekora Woods Blvd | 28 BAL |  |  |  | 5/11 10D | UPS RED | ECO NOTE 3 - PREVIOUS ISSUES @ L3/L4/U11 | 4/28 - AOI | 2T | *KIT CLEAR FOR QTY 72 4/18 - STILL SHORT FOR BAL 28 - KIT CLEAR 4/27 | 20 | Alliance Technology, LLC. | Saukville | WI | 53080-1674 | Insight Vision | 58X386
|  | 2022-04-28 | 109003 (4/14) | 250 Moonachie Rd Ste. 400 | 150 |  |  |  | 4/27 4/29 5D | FEDEX P | (HOLD) DELAM - 4/27 DELAM APPROVED | 4/21 - TOP (HOLD) 4/27 - BACK | 1B 1T | *FABS DUE 4/14 KIT CLEAR 4/20 - 4/21 DELAM - 4/27 - DELAM APPROVED | 1B | Sterling Medical Devices | Moonachie | NJ | 07074-1378
|  | 2022-04-28 | 107236 (2/10) | 7000 East Ave LLNL FOR US DOE/NNSA Gen Rec Building 411 PO Number U2529495 | 31 BAL |  |  |  | 4/29 20D | UPS GND | QTY 69 SHIPPED | 4/13 - TOP SIDE 4/13 - AOI | 1T | BALANCE KIT CLEAR 4/13 | 15 | Lawrence Livermore National Lab | Livermore | CA | 94550-9698 |  | 956956
|  | 2022-04-28 | 108976 (4/21) | 9535 Waples St Suite 100 | 40 |  |  |  | 4/28 5D | FEDEX P | SEE ECO #5 FOR CofC REQ | 4/25 - TOP SIDE 4/26 - AOI | 2T | KIT CLEAR 4/21 | 28 | South Coast Circuits, Inc. | San Diego | CA | 92121-2993
|  | 2022-04-28 | 108946 (4/20) | 103 Quality Cir Nw Ste 220 | 380 |  |  |  | 4/28 5D | FEDEX P | DEPANEL & SAND | 4/21 - TOP SIDE 4/22 - AOI | 1T | KIT CLEAR 4/21 | 2 | Scientific Research Corporation | Huntsville | AL | 35806-4537 | Attn: Graehm Sack | 153669597
|  | 2022-04-27 | 108875 (4/11) | 3200 Wisman Ln | 10 |  |  |  | 4/29* 10D | FEDEX GND | SEE ECO #1 - EMAIL PHOTOS & FAI BEFORE SHIPPING | 4/11 NEED PROG 4/13 - RTR 4/14 - TOP SIDE 4/15 - AOI | 2T | 4/11 - SHORT ITEMS 34, 36, 69, 99 KIT CLEAR 4/20 (PENDING CR30 CONF) | 0 | GatesAir, Inc. | Quincy | IL | 62301-1252
|  | 2022-04-27 | 107329-2 (3/28) | 2947 Bradley St Ste 130 | 8 BAL |  |  |  | 5/6 9D | FEDEX 2 DAY |  | 4/25 - BOT/TOP 4/25 - AOI | 1B 1T | *SHORT FAB - DUE 2/28 - RECV 32 FABS 4/14 - KIT CLEAR 4/25 BAL QTY 8 | 0 | Forza Ametek | Pasadena | CA | 91107-1566 | Attn: Yramn Nquyen | 255688804
|  | 2022-04-27 | 109007 (4/18) | 100 Four Points Way | 5 |  |  |  | 4/27 5D | FEDEX P |  | 4/20 - TOP SIDE 4/20 - AOI | 1B 1T | FABS DUE 4/19 KIT CLEAR 4/20 | 4 | SynTech Systems / Fuelmaster | Tallahassee | FL | 32305-7091 | Attn: Brian Piertrodangelo
|  | 2022-04-26 | 109524 (4/22) | 1 Cowles Rd | 100 |  |  |  | 4/27 3D | UPS RED | * 3 DAY TURN * | 4/22 - BOT/TOP SIDE 4/22 - AOI | 1B 1T | KIT CLEAR 4/22 | 1 | Gems Sensors | Plainville | CT | 06062-1107 | Attn: Mike Tetreault | 017710
|  | 2022-04-26 | 107257-2ND (4/19) | 777 Aviation Dr | 29 BAL |  |  |  | 4/26 5D | FEDEX GND | QTY 12 BOARDS NO U1 - BTD | 4/20 - TOP SIDE 4/20 - AOI | 2T | KIT CLEAR 4/19 | 10 | AKV, Inc. | Camarillo | CA | 93010-8568 |  | 284194284
|  | 2022-04-26 | 103326-1 (12/22) | 3011 Malibu Canyon Rd | 3FA/30 |  |  |  | ??? 15D | FEDEX P | RUN 3 THEN HOLD UNTIL 1/3 WTG FOR CUST | 12/27 - TOP HOLD 12/28 - 3 AOI |  | *SHORT 13 ALUM CAPS - SKIP - (ADDED FA) | 25 | HRL Laboratories | Malibu | CA | 90265-4737 |  | 187585619
|  | 2022-04-26 | 103326-2 (12/22) | 3011 Malibu Canyon Rd | 27 BAL |  |  |  | 4/29 15D | FEDEX P | RAN 3 FA - IN SHIPPING | 12/27-BOT DONE 4/15 - TOP SIDE 4/18 - AOI |  | KIT CLEAR 4/14 | 25 | HRL Laboratories | Malibu | CA | 90265-4737 |  | 187585619
|  | 2022-04-25 | 109227 (4/19) | 115 Castilian Dr | 540 |  |  |  | 5/4 10D | FEDEX P | ECO #2 - 6 LOTS OF QTY 90 REQ | 4/20 - TOP SIDE 4/20 - AOI | 1T | KIT CLEAR 4/20 | 0 | Transphorm USA | Goleta | CA | 93117 | Attn: Marcia Moore
|  | 2022-04-25 | 109154-2 (4/15) | 600 N Dekora Woods Blvd | 20 5D + 50 10D |  |  |  | 20-4/25 50-4/29 | UPS RED | ECO NOTE 3 - PREVIOUS ISSUES @ L3/L4/U11 | 4/19 - BOT SIDE 4/19 - TOP SIDE 4/19 - AOI | 2T | *KIT CLEAR FOR QTY 72 4/18 - STILL SHORT FOR BAL 28 | 20 | Alliance Technology, LLC. | Saukville | WI | 53080-1674 | Insight Vision | 58X386
|  | 2022-04-25 | 109425 (4/11) | 4975 E 41st Ave | 50 |  |  |  | 4/25 10D | FEDEX GND |  | 4/12 - BOT/TOP 4/12 - AOI | 1B 1T | KIT CLEAR 4/11 | 9 | Mount Sopris Instruments | Denver | CO | 80216-4424 |  | 148324417
|  | 2022-04-25 | 109385 (4/18) | 3451 E Harbour Dr | 40 |  |  |  | 4/29 9D | UPS GND |  | 4/19 - BACK | 1B 1T | KIT CLEAR 4/18 | 0 | CollabraTech Solutions, LLC | Phoenix | AZ | 85034-7229 |  | Y85858
|  | 2022-04-22 | 109631 (4/18) | 380 N Wickham Rd Ste G | 22 |  |  |  | 4/25 5D | FEDEX P |  | 4/19 - AOI | 2T | KIT CLEAR 4/18 | 0 | Turnkey Electronics Group | Melbourne | FL | 32935-8646
|  | 2022-04-22 | 108782 (4/7) | 250 Moonachie Rd Ste. 400 | 50 |  |  |  | 4/22 10D | FEDEX P |  | 4/7 - NEED PROG 4/11 - TOP SIDE 4/12 - AOI | 1B 1T | *4/7 SHORT 8 FABS - DUE 4/8 KIT CLEAR 4/8 | 13 | Sterling Medical Devices | Moonachie | NJ | 07074-1378
|  | 2022-04-22 | 100605-2B (3/11) | 3190 Monitor Ave Rm 0220 | 80 BAL |  |  |  | 2022-04-22 | FEDEX P |  | 3/17 - BOT SIDE 3/21 - BOT DONE 3/29 - TOP SIDE 3/31 - AOI | 2B 2T | KIT CLEAR 3/11 | 4 | University of Oklahoma | Norman | OK | 73019-5004 | Attn: Redmond Kelley | 749026308
|  | 2022-04-21 | 109231 (4/12) | 4501 Hatfield St | 16 |  |  |  | 4/25 5D | UPS RED | NEED 48 HR PREBAKE U7 & U63 - 3M DP420NS STAKING REQ | 4/14 - BOT SIDE 4/14 - TOP SIDE 4/15 - AOI | 2B 1T | *SHORT U6/U23 - OK TO SKIP - NEED PRE-BAKE - KIT CLEAR 4/18 ALT U6 RECV | 1 | Carnegie Robotics | Pittsburgh | PA | 15201-3023 |  | V3725X
|  | 2022-04-21 | 107546-2ND (4/14) | 6250 Joyce Dr | 17 |  |  |  | 4/22 5D | FEDEX P |  | 4/18 - AOI | 1B 1T | 4/14 - SHORT FABS KIT CLEAR 4/15 | 11 | Industrialex Manufacturing | Arvada | CO | 80403
|  | 2022-04-20 | 108919 (3/30) | 1001 W Algonquin St Dock D/E | 55 |  |  |  | 4/20 9D | UPS GND |  | 4/1 - RTR 4/4 - BOT / TOP 4/4 - AOI | 1B 1T | *USE CROSS FOR R20 - SHORT R8 (OK TO SKIP) KIT CLEAR 4/13 | 25 | Raven - Aerostar International, Inc. | Sioux Falls | SD | 57104-0319 |  | 572941
|  | 2022-04-20 | 109154 (4/15) | 600 N Dekora Woods Blvd | 30 |  |  |  | 30-4/20 20-4/26 50-4/29 | UPS RED | ECO NOTE 3 - PREVIOUS ISSUES @ L3/L4/U11 | 4/19 - BOT SIDE 4/19 - TOP SIDE 4/19 - AOI | 2T | *KIT CLEAR FOR QTY 72 4/18 - STILL SHORT FOR BAL 28 | 20 | Alliance Technology, LLC. | Saukville | WI | 53080-1674 | Insight Vision | 58X386
|  | 2022-04-19 | 109163 (4/11) | 11 Huron Drive Suite 202 | 775 |  |  |  | 4/22 9D | FEDEX P |  | 4/12 - TOP SIDE 4/12 - BACK | 1T | KIT CLEAR 4/11 | 0 | Aila Technologies, Inc. | Natick | MA | 1760
|  | 2022-04-19 | 107329-1 (3/28) | 2947 Bradley St Ste 130 | 32/40 |  |  |  | 4/27 9D | FEDEX 2 DAY | RUN & SHIP PARTIAL QTY 32 | 4/18 - AOI | 1B 1T | *SHORT FAB - DUE 2/28 - RECV 32 FABS 4/14 | 0 | Forza Ametek | Pasadena | CA | 91107-1566 | Attn: Yramn Nquyen | 255688804
|  | 2022-04-19 | 108556 (4/13) | 10175 Philipp Pkwy | 100 |  |  |  | 4/20 5D | UPS RED |  | 4/13 - TOP SIDE 4/13 - AOI | 1T | KIT CLEAR 4/13 | 11 | Automated Packaging Systems, Inc. | Streetsboro | OH | 44241-4706 |  | 19E046
|  | 2022-04-18 | 108531 (3/29) | 1380 Forest Park Cir Ste 202 | 50 |  |  |  | 4/19 9D | FEDEX P | *DEPANEL & SAND | 4/7 - BOT SIDE 4/7 - TOP SIDE 4/8 - AOI | 1B 1T | *SHOULD CLEAR 3/30 - KIT CLEAR 4/6 | 7 | Cardinal Peak, LLC | Lafayette | CO | 80026-3377 |  | 977459036
|  | 2022-04-18 | 109386-2 (4/5) | 96 Inverness Drive East | 302 |  |  |  | 4/18 2D | FEDEX P | ** 2 DAY TURN ** MIN QTY 150 ON 2 DAY TURN - SEE SHIPPING INSTRUCTIONS FOR QTYS | 4/5 - NEED PROG 4/11 - RTR 4/13 - RAN 1 FA WITHOUT U3 4/14 - TOP SIDE 4/15 - BACK | 2T 38S | FABS DUE 4/7 SHORT U3 DUE 4/13 KIT CLEAR 4/14 | 0 | Latch Systems, Inc. | Englewood | CO | 80112 | Unit I ATTN: Noah Allstot
|  | 2022-04-18 | 105892-2 (3/29) | 1830 Lefthand Cir Ste A | 3 BAL |  |  |  | 4/21 3D | FEDEX P | * 3 DAY TURN * ***HEAVY T/H*** 4/15 - BAKE FABS | 4/11 - RAN 1 BOARD - 4/14 SMT RAN 2 BOARDS 4/15 | 1B 1T | SHORT FABS - REC 1 FAB 4/7 - 4/15 KIT CLEAR (BAKE ANSWERED) | 385 | Honeybee Robotics | Longmont | CO | 80501-6717 |  | 501565164
|  | 2022-04-15 | 109386-1 (4/5) | 96 Inverness Drive East | 48 |  |  |  | 4/15 1D | FEDEX P | ** EXPEDITE QTY 48 - SEE SHIPPING INSTRUCTIONS FOR QTYS | 4/5 - NEED PROG 4/11 - RTR 4/13 - RAN 1 FA WITHOUT U3 4/14 - TOP SIDE 4/15 - BACK | 2T 38S | FABS DUE 4/7 SHORT U3 DUE 4/13 KIT CLEAR 4/14 | 0 | Latch Systems, Inc. | Englewood | CO | 80112 | Unit I ATTN: Noah Allstot
|  | 2022-04-15 | 109244 (4/11) | 7002 S Revere Pkwy Ste 60 | 3 |  |  |  | 4/18 3D | FEDEX P | **3 DAY TURN** | 4/12 - BOT /TOP 4/12 - BACK | 1B 1T | 4/11 - SHORT TP1 18/BOARD - 4/13 TP1 IS DNI | 75 | Telspan Data | Centennial | CO | 80112-6767 |  | 34252726
|  | 2022-04-15 | 100605-2A (3/11) | 3190 Monitor Ave Rm 0220 | 20/90 |  |  |  | 2022-04-15 | FEDEX P | *SHIP MIN QTY 10 ON 4/15 | 3/17 - BOT SIDE 3/21 - BOT DONE 3/29 - TOP SIDE 3/31 - AOI | 2B 2T | KIT CLEAR 3/11 | 4 | University of Oklahoma | Norman | OK | 73019-5004 | Attn: Redmond Kelley | 749026308
|  | 2022-04-14 | 109309 (4/7) | 22 Eastman Ave Ste A | 72 |  |  |  | 4/15 5D | FEDEX 2 DAY |  | 4/11 - BOT/ TOP 4/11 - AOI | 1B 1T | 4/7 - ONLY WTG FOR PART CONF KIT CLEAR 4/8 | 9 | RX Monitoring Service, Inc. | Bedford | NH | 03110-6702 |  | 199197738
|  | 2022-04-14 | 109183 (4/7) | 1101 KITCHAWAN ROAD | 15 |  |  |  | 4/14 5D | UPS RED |  | 4/7 - NEED PROG 4/8 - BOT SIDE 4/11 - BACK | 1B 1T | KIT CLEAR 4/7 | 3 | Government Contracting Specialists, Inc. IBM CORPORATION | YORKTOWN HEIGHTS | NY | 10598 | ATTN: BRUCE COPELAND | 149191
|  | 2022-04-13 | 108941 (3/31) | 601 Atlantis Rd | 25 |  |  |  | 4/15 10D | FEDEX EARLY |  | 4/7 - TOP SIDE 4/7 - BACK | 1T | KIT CLEAR 4/1 | 3 | Anderson Connectivity | Melbourne | FL | 32904-2316
|  | 2022-04-13 | 108942 (3/31) | 601 Atlantis Rd | 25 |  |  |  | 4/15 10D | FEDEX EARLY |  | 4/7 - TOP SIDE 4/7 - BACK | 1T | KIT CLEAR 4/1 | 2 | Anderson Connectivity | Melbourne | FL | 32904-2316
|  | 2022-04-13 | 109344 (4/11) | 21 Alpha Rd Suite 202 | 100 |  |  |  | 4/14 2D | FEDEX P | **2 DAY TURN** | 4/12 - BOT SIDE 4/12 - TOP SIDE 4/12 - AOI/BACK | 1B 1T | 4/11 -U60 PART CONF-FABS NO DC-BAKE-KIT CLEAR 4/12 | 20 | Atlas Devices | Chelmsford | MA | 01824-4170 |  | 370758867
|  | 2022-04-13 | 107257 (4/7) | 777 Aviation Dr | 1/30 |  |  |  | 4/14 5D | FEDEX GND | QTY 1 FA | 4/8 - RTR 4/11 - AOI | 2T | KIT CLEAR 4/7 FOR 1 PC FA | 10 | AKV, Inc. | Camarillo | CA | 93010-8568 |  | 284194284
|  | 2022-04-12 | 108585 (3/29) | 60 Alhambra Rd Ste 1 | 40 |  |  |  | 4/14 9D | FEDEX P |  | 4/1 - RTR 4/4 - TOP SIDE 4/5 - BACK | 1T | *SHOULD CLEAR 3/30 - KIT CLEAR 4/1 | 7 | TSRgrow | Warwick | RI | 02886-1446
|  | 2022-04-12 | 109249-1 (4/4) | 110 Forbes Blvd | 4 FA/10 |  |  |  | 4/13 5D | FEDEX P |  | 4/6 - RTR 4/7 - TOP SIDE 4/7 - AOI | 2T | *SHOULD CLEAR 4/5 | 50 | NextPhase Medical Devices | Mansfield | MA | 02048-1145
|  | 2022-04-12 | 108910 (4/7) | 5511 CAPITOL CENTER DR, STE P125 | 8 |  |  |  | 4/12 2D | FEDEX P | ** 2 DAY TURN ** | 4/8 - BOT SIDE 4/8 - TOP SIDE 4/8 - AOI/BACK | 1B1T | KIT CLEAR 4/8 | 6 | PLEXUS ENGINEERING SOLUTIONS | RALEIGH | NC | 27606-4884 |  | 49V91V
|  | 2022-04-11 | 109307 (4/4) | 9845 Willows Rd Ne | 10 |  |  |  | 4/11 3D | FEDEX 2 DAY | * 3 DAY TURN * T/H SW1 NEEDS RE TAPE FOR WASH - SEE ECO #2 | 4/4 - NEED PROG 4/6 - BOT/TOP 4/7 - BACK | 1B 1T | KIT CLEAR 4/6 | 42 | Facebook, Inc. | Redmond | WA | 98052-2540
|  | 2022-04-11 | 109306 (4/4) | 4 Sunset Ln | 72 |  |  |  | 4/11 5D | FEDEX P | P1 IS BTD | 4/5 - RTR 4/6 -TOP SIDE 4/6 - AOI | 1T | KIT CLEAR 4/4 - P1 BTD | 13 | RX Monitoring Service, Inc. | Bedford | NH | 03110-6804
|  | 2022-04-11 | 108042 (3/30) | 5660 Airport Blvd Ste 101 | 100 |  |  |  | 4/11 7D | UPS GND | SEE ECO - NEED SER #S ON CofC | 3/31 - RTR 4/1 - TOP SIDE 4/1 - AOI | 1T | KIT CLEAR 3/31 | 7 | Churchill Navigation dba Shotover Systems Inc | Boulder | CO | 80301-2596 |  | R8A959
|  | 2022-04-11 | 104885-2 (3/28) | 3011 Malibu Canyon Rd | 11 BAL |  |  |  | 4/11 10D | FEDEX P |  | 3/30 - TOP SIDE 3/30 - AOI | 2B 2T | 3/28 - SHORT U15 - OK TO SKIP - KIT CLEAR 3/28 | 25 | HRL Laboratories | Malibu | CA | 90265-4737 | Att:Kenny Pruett | 97263508
|  | 2022-04-08 | 107895 (3/11) | 3080 Lomita Blvd | 25 |  |  |  | 4/6 4/11 15D | FEDEX 2 DAY | 4/1 - DNI J5 4/6 - CUST NOW ADDING J5 | 3/29 - RTR 3/31 - TOP SIDE 3/31 - AOI | 1B 1T | 3/17 - POSS BAKE REQ FOR 1 PART - KIT CLEAR 3/17 | 10 | DMK Engineering, Inc. | Torrance | CA | 90505-5103
|  | 2022-04-08 | 109381 | 315 COMMERCE PARK RD, UNIT 3 | 16 RWK |  |  |  | 2022-04-08 | FEDEX P | PAID RWK | 4/7 - BACK |  |  | 1 | APPLIED RADAR | NORTH KINGSTOWN | RI | 02852-8422
|  | 2022-04-08 | 109173 (4/6) | 2326 Irwin St | 10 |  |  |  | 4/11 3D | FEDEX P | * 3 DAY TURN * | 4/7 - BOT/TOP 4/7 - BACK | 1B | KIT CLEAR 4/6 | 1 | Tomahawk Robotics, LLC | Melbourne | FL | 32901-7377 | Attn: 321-888-34-87
|  | 2022-04-08 | 109174 (4/6) | 2326 Irwin St | 10 |  |  |  | 4/11 3D | FEDEX P | * 3 DAY TURN * | 4/7 - BOT/TOP 4/7 - BACK | 1B 1T | KIT CLEAR 4/6 | 0 | Tomahawk Robotics, LLC | Melbourne | FL | 32901-7377 | attn: 321-888-34-87
|  | 2022-04-07 | 108335 (3/31) | 450 Church St | 4 |  |  |  | ??? 10D | FEDEX GND |  | 4/1 - RTR 4/4 - BOT / TOP 4/4 - AOI | 2B 2T | 3/31 - SMT CLEAR | 14 | University of Michigan | Ann Arbor | MI | 48109-1040 | 2281 Ameel 237749 Randall Harrison M Laboratory
|  | 2022-04-07 | 107546-1FA (4/1) | 6250 Joyce Dr | 18/35 |  |  |  | 4/8 5D | FEDEX P |  | 4/1 - BOT SIDE 4/4 - TOP SIDE 4/5 - AOI | 1B 1T | KIT CLEAR 4/1 | 11 | Industrialex Manufacturing | Arvada | CO | 80403
|  | 2022-04-07 | 109021 (4/4) | 100 Research Dr | 150 |  |  |  | 4/11 5D | FEDEX P | NEED PROG | 4/1 - RTR 4/5 - BOT/TOP 4/5 - BACK | 1B 1T | KIT CLEAR 4/4 | 0 | Ascent AeroSystems | Wilmington | MA | 01887-4441
|  | 2022-04-07 | 109020 (4/4) | 100 Research Dr | 150 |  |  |  | 4/11 5D | FEDEX P |  | 4/1 - RTR 4/5 - BOT/TOP 4/5 - BACK | 1B 1T | KIT CLEAR 4/4 | 0 | Ascent AeroSystems | Wilmington | MA | 01887-4441
|  | 2022-04-07 | 108514 (3/30) | 740 S Pierce Ave STE 15 | 100 |  |  |  | 4/7 5D | FEDEX P |  | 4/1 - BOT SIDE 4/4 TOP SIDE 4/4 AOI | 1B 1T | KIT CLEAR 3/30 | 0 | Bridge Diagnostics, Inc. | Louisville | CO | 80027-3057 |  | 158332655
|  | 2022-04-07 | 108859 (3/29) | 19578 Laroda Ln | 10 |  |  |  | 4/7 5D | FEDEX 2 DAY | NOTE ATTRITION & BTD | 3/30 - RTR 4/1 - BOT/TOP 4/4 - AOI | 2T | KIT CLEAR 4/1 | 26 | Essential Consulting Solutions | Saugus | CA | 91350
|  | 2022-04-07 | 100606-2 (3/7) | 3190 Monitor Ave Rm 0220 | 90 |  |  |  | 2022-04-07 | #VALUE! |  | 3/15 - BOT DONE 3/25 - TOP SIDE 3/28 - AOI | 2B 3T | KIT CLEAR 3/7 | 8 | University of Oklahoma | Norman | OK | 73019-5004 | Attn: Redmond Kelley | 749026308
|  | 2022-04-06 | 108145 (3/10) | 9535 Waples S Suite 100 | 1 |  |  |  | 3/30 3D | FEDEX P | * 3 DAY TURN * ECO NOTE 4-C OF C INFO *REMOVE SOLDER MASK | 3/25 - BOT SIDE 3/25 TOP SIDE 3/25 - AOI | 2T | KIT CLEAR 3/24 | 25 | South Coast Circuits, Inc. | San Diego | CA | 92121-2993
|  | 2022-04-06 | 108937 (4/1) | 601 Atlantis Rd | 15 |  |  |  | 4/15 10D | FEDEX EARLY |  | 4/1 - BOT SIDE 4/5 - BACK | 1B | KIT CLEAR 4/1 | 1 | Anderson Connectivity | Melbourne | FL | 32904-2316
|  | 2022-04-06 | 108938 (4/1) | 601 Atlantis Rd | 25 |  |  |  | 4/15 10D | FEDEX EARLY |  | 4/5 - BOT SIDE 4/5 - TOP SIDE 4/5 - BACK | 1B 1T | KIT CLEAR 4/1 | 0 | Anderson Connectivity | Melbourne | FL | 32904-2316
|  | 2022-04-06 | 109226 (4/1) | 11100 Johns Hopkins Road | 220 |  |  |  | 4/8 5D | FEDEX P |  | 4/1 - RTR 4/5 - TOP SIDE 4/5 - BACK | 1T | KIT CLEAR 4/1 | 0 | John Hopkins University Applied Physics | Laurel | MD | 20723 | MS 17-N660V attn: peter kim
|  | 2022-04-06 | 108380-2 (3/21) | 600 N Field Dr | 43 BAL |  |  |  | 4/5 4/6 10D | UPS RED |  | 3/29 - BOT SIDE 3/30 - TOP SIDE 3/30 - BACK | 1B 2T | KIT CLEAR 3/30 | 8 | ICUMedical | Lake Forest | IL | 60045-4835 |  | 05x8e7
|  | 2022-04-04 | 107215-1 (3/30) | 1510 Fm 3224 | 1 FA /5 |  |  |  | 4/4 3D | FEDEX P | * 3 DAY TURN * T/H ONLY | 3/30 - BACK | T/H | KIT CLEAR 3/30 | 27 | Peraton | Palestine | TX | 75803-2169 |  | 195294062
|  | 2022-04-04 | 108639-FA (3/28) | 2 Executive Dr | 24FA/40 |  |  |  | 4/4 5D | UPS RED | DO NOT DEPANEL | 3/28 - FSU 3/29 - RTR 3/30 - BOT SIDE 3/30 - TOP SIDE 3/30 - AOI | 1B 1T | KIT CLEAR 3/28 FABS REJ NO MOUSE BITES - 3/29 NO DEPANEL REQ - KIT CLEAR | 0 | Rockwell Automation | Chelmsford | MA | 01824-2565 | Requestor: Boeun Uy Paul Mullins | 89W837
|  | 2022-04-04 | 109213 (4/1) | 225 W 36th St Ste 706 | 20 |  |  |  | 4/4 3D 1D | FEDEX P | ***1 DAY TURN*** NOTE J17 DNF - EMAIL SENT 4/4 | 4/1 - RTR 4/4 - BOT / TOP 4/4 - AOI | 1B 2T | *SHOULD CLEAR 4/1 | 7 | Bowery Engineering | New York | NY | 10018-752
|  | 2022-04-04 | 108907 - 1 (3/22) | 3881 Mcgowen St | 23P/65 |  |  |  | 4/7 5D | FEDEX P | T/H ONLY - START QTY 23 PARTIAL 3/24 | 3/24 - START PARTIAL QTY | T/H | 3/23 - SHORT 1 ITEM AND PARTIAL SHORT 2 ITEMS | 70 | Royal Circuits | Long Beach | CA | 90808-1702
|  | 2022-04-01 | 106595 (2/23) | Parque Industrial FlexiPark Parque Industrial FlexiPark Calle Potrerillos | 200 |  |  |  | 4/4 10D | UPS INTL BLU |  | 3/25 - RTR 3/28 - TOP SIDE 3/28 - BACK | 1B | *SHOULD CLEAR 2/24 - 2/24 FABS NO GOOD 3/21 - KIT CLEAR | 0 | ATL Technology CR | San Rafael de Alajuela | Costa Rica | 20108 |  | 9E7173
|  | 2022-04-01 | 108392 (3/23) | 3445 Lake Eastbrook Blvd Se | 5 |  |  |  | 4/1 5D | FEDEX 2 DAY | SMT RUN TOP 1ST | 3/28 - TOP SIDE 3/29 - BOT SIDE 3/29 - AOI | 1B 2T | KIT CLEAR 3/25 | 9 | Dorner Works LTD | Grand Rapids | MI | 49546-5935
|  | 2022-03-31 | 107937-2 (3/25) | Vision Dr | 130 BAL |  |  |  | 4/1 5D | FEDEX P |  | 3/25 - RTR 3/28 - BOT SIDE 3/28 - BACK | 1B | KIT CLEAR 3/25 | 0 | Cognex Corporation | Natick | MA | 01760-2083 | Attn: John Alberta | 198814415
|  | 2022-03-31 | 108603-1 (3/18) | 1001 W Algonquin St Dock D/E | 25/35 |  |  |  | 3/31 3D | FEDEX P | * 3 DAY TURN * SHIP QTY 25 PARTIAL | 3/23 - RTR 3/29 - AOI | 1B 1T | 3/18 STILL SHORT R20 3/28 - SMT CLEAR & QTY 25 100% CLEAR | 26 | Raven - Aerostar International, Inc. | Sioux Falls | SD | 57104-0319
|  | 2022-03-31 | 108877 (3/23) | 1515 EUBANK SE BLDG 957 | 10 |  |  |  | 3/31 3D | FEDEX P | 3/24 NEED U2111 REMOVED FROM DAUGHTER BOARDS | 3/24 - RTR 3/29 TOP SIDE 3/29 - AOI | 1T | FABS DUE BY 3/24 3/25 - DAY 1 MON 3/28 | 203 | Sandia National Laboratories | ALBUQUERQUE | NM | 87123 | SANDIA NATIONAL LABS U.S. NNSA ATTN: PO# 2357765 | 1516-4690-5
|  | 2022-03-31 | 108784 (3/18) | 1807 Santa Rita Rd Unit H-361 | 108 |  |  |  | 3/31 9D | FEDEX 2 DAY | *DO NOT DEPANEL | 3/24 - AOI | 1T | KIT CLEAR 3/18 | 0 | Optimum Design Associates | Pleasanton | CA | 94566-4779 |  | 155172711
|  | 2022-03-30 | 108786 (3/21) | 2947 Bradley St Ste 130 | 6 |  |  |  | 3/30 5D | FEDEX 2 DAY |  | 3/28 - BOT SIDE 3/28 - TOP SIDE 3/29 - AOI | 1B 2T | KIT CLEAR 3/23 | 102 | Forza Silicon Corporation | Pasadena | CA | 91107-1566 | Attn: Yramn Nquyen
|  | 2022-03-30 | 109058 (3/22) | 104 Otis St | 10 |  |  |  | 3/30 5D | FEDEX P |  | 3/25 - RTR 3/28 - TOP SIDE 3/28 - AOI | 1T | KIT CLEAR 3/23 - DNI U1_1 | 0 | ATSE, LLC | Northborough | MA | 01532-2440
|  | 2022-03-30 | 108145 (3/10) | 9535 Waples S Suite 100 | 39 |  |  |  | 3/30 3D | FEDEX P | * 3 DAY TURN * ECO NOTE 4-C OF C INFO *REMOVE SOLDER MASK | 3/25 - BOT SIDE 3/25 TOP SIDE 3/25 - AOI | 2T | KIT CLEAR 3/24 | 25 | South Coast Circuits, Inc. | San Diego | CA | 92121-2993
|  | 2022-03-30 | 108380-1 (3/21) | 600 N Field Dr | 32/75 |  |  |  | 3/30 5D | UPS RED | RUN QTY 32 PARTIAL - SEND PICS | 3/24 - BOT SIDE 3/25 - TOP SIDE 3/25 - AOI | 1B 2T | *SHORT 1 PART DUE 3/22 (DAY 1 IS WED) | 8 | ICUMedical | Lake Forest | IL | 60045-4835 |  | 05x8e7
|  | 2022-03-30 | 108252-1 (3/15) | 5100 Boyd Lake Ave | 147 |  |  |  | 3/29 ??? 10D | FEDEX 2 DAY | *WGT FOR CUST * SHIP PARTIAL QTY 147 | 3/17 - AOI |  | PARTIAL CLEAR 3/15 FOR QTY 147 | 5 | Danhydra, Inc. | Loveland | CO | 80538-8944
|  | 2022-03-29 | 109118 (3/22) | 1601 Marys Ave Suite 3G | 130 |  |  |  | 3/29 5D | FEDEX P |  | 3/24 - AOI | 1T | KIT CLEAR 3/22 | 1 | Deeplocal Inc. | Sharpsburg | PA | 15222
|  | 2022-03-29 | 106450 (3/21) | 4505 Campus Dr | 36 |  |  |  | 3/29 5D | FEDEX P |  | 3/23 - AOI | 1B 2T | KIT CLEAR 3/22 | 9 | IonQ, Inc. | College Park, | MD | 20740-3899 | Attn: Stephan Enzone
|  | 2022-03-29 | 104894-RMA (3/23) | 5660 Airport Blvd Ste 101 | 95 |  |  |  | 3/30 5D | FEDEX P | R&R X1 | 3/23 - BACK |  | KIT CLEAR 3/23 | 1 | Churchill Navigation dba Shotover Systems Inc | Boulder | CO | 80301-2596
|  | 2022-03-29 | 107891 (3/15) | 2095 Biltmore Pt | 90 |  |  |  | 4/6 3/31 10D | FEDEX P | 3/23 - EXPEDITE FROM 4/6 TO 3/31 | 3/24 - AOI | 2B 2T | KIT CLEAR 3/23 | 4 | Saturn PCB Design, Inc. | Longwood | FL | 32779-2856
|  | 2022-03-28 | 108317 (3/7) | 2947 Bradley St Ste 130 | 2 |  |  |  | 4/4 5D | FEDEX P |  | 3/23 - AOI | 1B 2T | *FABS DUE 3/11 - SMT CEAR 3/15 KIT CLEAR 3/28 | 82 | Forza Ametek | Pasadena | CA | 91107-1566
|  | 2022-03-28 | 107972-2 (3/24) | 250 Moonachie Rd Ste. 400 | 6 |  |  |  | 3/28 1D | FEDEX P | *1 DAY TURN* 48 HR PRE BAKE FABS | 3/28 - BOT SIDE 3/28 - TOP SIDE 3/28 - BACK | 1B 1T | 3/24 - FABS RECV & IN OVEN | 0 | Sterling Medical Devices | Moonachie | NJ | 07074-1378
|  | 2022-03-28 | 108874 (3/23) | 1170 Howell Mill Rd Nw Ste 210 | 25 |  |  |  | 3/28 3D | UPS RED | * 3 DAY TURN * | 3/24 - TOP SIDE 3/25 - AOI | 2B 2T | KIT CLEAR 3/23 - DNI U302 & 901 | 6 | Flock Safety | Atlanta | GA | 30318-8637 |  | 80739E
|  | 2022-03-25 | 108420-2 (2/25) | 5100 Boyd Lake Ave | 133 BAL |  |  |  | 3/28 5D | FEDEX 2 DAY | SHIPPED PARTIAL QTY 117 ON 3/15 | RTR | 1T | 2/25 - KIT CLEAR FOR QTY 117 | 1 | Danhydra, Inc. | Loveland | CO | 80538-8944
|  | 2022-03-25 | 104008 (3/15) | 22 Jordan Cove Rd | 27 |  |  |  | 3/29 10D | UPS ORG | 3/21 - BOT DONE | 3/22 - AOI | 1B 1T | KIT CLEAR 3/15 | 15 | Coastal Designs, LLC | Waterford | CT | 06385-3227 |  | 238V3V
|  | 2022-03-25 | 107274 (3/18) | 49 Willow Peak Dr | 50 |  |  |  | 3/25* 5D | FEDEX GND | NATION CHECKING PROGRAM 3/21 - U13/45 DOES NOT FIT | 3/22 - AOI | 2T | 3 ITEMS DUE 3/18 U13 PARTIAL SHORT FOR 20 BOARDS - OK TO SKIP | 54 | Quantel USA | Bozeman | MT | 59718-9811 |  | 120-189-263
|  | 2022-03-25 | 108348 (3/21) | 5660 Airport Blvd Ste 101 | 45 |  |  |  | 3/25 3D | FEDEX GND | * 3 DAY TURN * | 3/23 - AOI | 1B 1T | KIT CLEAR 3/22 | 3 | Churchill Navigation dba Shotover Systems Inc. | Boulder | CO | 80301-2596 |  | R8A959
|  | 2022-03-24 | 107347 (3/16) | 2112 Case Pkwy Ste 1 | 5 |  |  |  | 3/28 5D | FEDEX P |  | 3/22 - BACK | 1B 2T | 3/16 - ONLY SHORT 1 T/H BATT 1 - KIT CLEAR 3/18 | 22 | AVID Technologies, Inc. | Twinsburg | OH | 44087-2378
|  | 2022-03-24 | 104009 (3/14) | 22 Jordan Cove Rd | 27 |  |  |  | 3/28 10D | UPS ORG |  | 3/16 - AOI |  | KIT CLEAR 3/14 | 15 | Coastal Designs, LLC | Waterford | CT | 06385-3227 |  | 238V3V
|  | 2022-03-24 | 108358 (3/18) | 6035 Stoneridge Dr | 20 |  |  |  | 3/24 3D | FEDEX P | * 3 DAY TURN * NATION CHECKING PROG | 3/22 - AOI | 2B 1T | 3/18 - SHORT FAB AND U1/U2 - 3/21 - DNI U1/2 - 3/21 KIT CLEAR | 1 | Abbott Point of Care | Pleasanton | CA | 94588
|  | 2022-03-24 | 109041 (3/21) | 480 Springpark Pl Ste 900 | 50 |  |  |  | 3/24 3D | FEDEX P | * 3 DAY TURN * PRESS FIT | 3/21 - PRESS FIT |  | KIT CLEAR 3/21 | 24 | Artis, LLC | Herndon | VA | 20170-5297 | Attn: Cody Sewell | 481232988
|  | 2022-03-24 | 108876 (3/21) | 1170 Howell Mill Rd Nw Ste 210 | 25 |  |  |  | 3/24 2D | UPS RED | **2 DAY TURN** | 3/22 - AOI | 1B 1T | KIT CLEAR 3/22 | 8 | Flock Safety | Atlanta | GA | 30318-8637 |  | 80739E
|  | 2022-03-23 | 108038 (3/17) | 160 Schoolhouse Rd | 50 |  |  |  | 3/24 5D | FEDEX P |  | 3/22 - AOI | 1B 1T | KIT CLEAR 3/17 | 0 | Amplifier Research Corp | Souderton | PA | 18964-2412
|  | 2022-03-23 | 108689 (3/16) | 11100 Endeavor Ct Ste 300 | 15 |  |  |  | 3/24 5D | FEDEX P |  | 3/21 - BACK | 1B 1T | KIT CLEAR 3/17 | 41 | NAL Research Corporation | Manassas | VA | 20109-4027 |  | 230306168
|  | 2022-03-23 | 106596 (3/16) | Parque Industrial FlexiPark Calle Potrerillos | 180 |  |  |  | 3/31 10D | UPS INTL BLU |  | 3/21 - BACK |  | KIT CLEAR 3/16 | 0 | ATL Technology CR | San Rafael de Alajuela | Costa Rica | 20108
|  | 2022-03-22 | 106994 (3/15) | 1150 University Ave | 2 |  |  |  | 3/29 10D | FEDEX P |  | 3/18 - AOI | 1B 1T | KIT CLEAR 3/15 | 40 | University of Wisconsin | Madison | WI | 53706-1302
|  | 2022-03-22 | 106531 (3/7) | 2112 Case Pkwy Ste 1 | 80 |  |  |  | 3/23 5D | FEDEX P |  | 3/16 - AOI |  | *ITEM 17 PARTIAL SHORT - KIT CLEAR 3/15 | 11 | AVID Technologies, Inc. | Twinsburg | OH | 44087-2378
|  | 2022-03-22 | 107565 (3/15) | 22 Jordan Cove Rd | 1 |  |  |  | 3/22 5D | UPS BLU |  | 3/17 - AOI |  | KIT CLEAR 3/15 - ITEMS 41, 45 & 61 REMOVED FROM ANOTHER BOARD | 22 | Coastal Designs, LLC | Waterford | CT | 06385-3227 |  | 238V3V
|  | 2022-03-22 | 108758 (3/15) | 1773 219th Ln | 25 |  |  |  | 3/23 5D | UPS RED |  | 3/21 - BACK | 1T | 3/15 - SMT CLEAR ONLY - KIT CLEAR 3/16 | 41 | Boone Cable Works & Electronics, Inc. | Boone | IA | 50036-7443 |  | E60690
|  | 2022-03-22 | 108347-2 (3/11) | 5660 Airport Blvd Ste 101 | 53 BAL |  |  |  | 4/1 10D | UPS GND | ALL T/H |  | T/H | BALANCE KIT CLEAR 3/18 | 1 | Churchill Navigation dba Shotover Systems Inc | Boulder | CO | 80301-2596 |  | R8A959
|  | 2022-03-22 | 108347-1 (3/11) | 5660 Airport Blvd Ste 101 | 22/75 |  |  |  | 3/25 10D | UPS GND | ALL T/H SHIP QTY 22 PARTIAL |  |  | 3/11 - KIT CLEAR FOR QTY 22 | 1 | Churchill Navigation dba Shotover Systems Inc | Boulder | CO | 80301-2596 |  | R8A959
|  | 2022-03-21 | 108471 (3/11) | 777 Lowndes Hill Rd Bldg 3 Ste 160 | 17 |  |  |  | 3/22 6D | FEDEX P | *FABS PRE-BAKED BY ADVANCED | 3/18 - AOI |  | *3/8 - SHORT FAB ONLY KIT CLEAR 3/14 | 1 | Aeronix, Inc. | Greenville | SC | 29607-2101
|  | 2022-03-21 | 106693 (2/11) | 5660 Airport Blvd Ste 101 | 46 |  |  |  | 2/18 3/25 5D | UPS GND | T/H ONLY *HOLD-WRONG FAB* SHIPPED QTY 4 3/3 |  |  | KIT CLEAR 2/11 - WRONG FAB - KIT CLEAR 3/18 | 1 | Churchill Navigation dba Shotover Systems, Inc. | Boulder | CO | 80301-2596 |  | R8A959
|  | 2022-03-18 | 107719 (2/18) | 475 Wildwood Ave | 30 |  |  |  | ??? 10D | FEDEX GND |  | 3/7 - AOI |  | *2/25 - SHORT ITEM 5 - OK TO SKIP | 38 | Piezo Systems - Div of Mide Technology | Woburn | MA | 1801
|  | 2022-03-18 | 107972-1 (2/8) | 250 Moonachie Rd Ste. 400 | 9/15 |  |  |  | 3/18 5D | FEDEX P | 48 HR PRE BAKE FABS - DONE 3/11 | 3/15 - AOI |  | *RUN PARTIAL QTY 9 - KIT PARTIAL CLEAR 3/10 | 0 | Sterling Medical Devices | Moonachie | NJ | 07074-1378
|  | 2022-03-18 | 108332-2ND (3/14) | 1678 S Pioneer Rd | 130 |  |  |  | 3/21 5D | FEDEX P | 1ST ARTICLE APPROVED | 3/14 - BACK |  | KIT CLEAR 3/14 | 5 | Varex Imaging Corporation | Salt Lake City | UT | 84104-4298 |  | 135447498
|  | 2022-03-18 | 107894 (3/8) | 3080 Lomita Blvd | 25 |  |  |  | 3/29 15D | FEDEX 2 DAY |  | 3/15 - AOI |  | KIT CLEAR 3/8 | 2 | DMK Engineering, Inc. | Torrance | CA | 90505-5103
|  | 2022-03-17 | 108866 | 3 Henry Dr | 5 |  |  | PAID RWK OF 107538 | [6 empty] | 0 | HII Unmanned Systems, Inc. | Pocasset | MA | 02559-1415 |  | 253053240
|  | 2022-03-17 | 107457 (2/7) | 601 Atlantis Rd | 36 |  |  |  | 3/21 5D | FEDEX P | *OK TO SHIP BAL BY 3/21 | 3/5 - BACK |  | *SHOULD CLEAR BY 3/9 - LAST PART DUE 3/11 KIT CLEAR 3/14 | 1 | Anderson Connectivity | Melbourne | FL | 32904-2316
|  | 2022-03-17 | 108553 (3/9) | 4975 E 41st Ave | 25 |  |  |  | 3/18 5D | FEDEX GND |  | 3/11 - AOI |  | 3/9 - SHORT ITEM 9 - OK TO SKIP - KIT CLEAR 3/11 | 18 | Mount Sopris Instruments | Denver | CO | 80216-4424 |  | 148324417
|  | 2022-03-17 | 104573-2ND (3/3) | 3190 Monitor Ave Rm 0220 | 4 |  |  |  | 2022-03-22 | FEDEX P |  | 3/10 - AOI |  | KIT CLEAR 3/3 | 5 | University of Oklahoma | Norman | OK | 73019-5004 | Attn: Kurt Konyalioglu
|  | 2022-03-17 | 104576-2ND (3/7) | 3190 Monitor Ave Rm 0220 | 4 |  |  |  | 2022-03-17 | FEDEX P |  | 3/10 - AOI |  | KIT CLEAR 3/8 | 12 | University of Oklahoma | Norman | OK | 73019-5004 | Attn: Kurt Konyalioglu | 749026308
|  | 2022-03-17 | 106324 (12/16) | 9845 Willows Rd Ne | 3504 |  |  |  | 3/18 10D | FEDEX P | 3/9 - BOT SIDE DONE | 3/14 - BACK |  | PARTIAL CLEAR QTY 2496 SHIPPED 1/14 KIT CLEAR 3/4 | 0 | Facebook Technologies LLC | Redmond | WA | 98052-2540 | Attn: Wei Sun
|  | 2022-03-16 | 108681 (3/9) | 10175 Philipp Pkwy | 100 |  |  |  | 3/16 5D | UPS RED |  | 3/10 - AOI |  | KIT CLEAR 3/9 | 35 | Automated Packaging Systems Inc. | Streetsboro | OH | 44241-4706 |  | 19E046
|  | 2022-03-16 | 108771 (3/9) | 6250 JOYCE DRIVE | 90 |  |  |  | 3/16 5D | FEDEX P | PAID REWORK | 3/9 - BACK |  | KIT CLEAR 3/9 | 0 | INDUSTRILEX | ARVADA | CO | 80403
|  | 2022-03-16 | 108526 (3/4) | 12455 Research Blvd | 15FA/80 |  |  |  | 3/17 3D | FEDEX P | SHIPPED QTY 5 ON 3/11 | 3/10 - AOI/BACK |  | SHORT D20 - DUE 3/17 | 7 | Royal Circuits | Austin | TX | 78759-2314 | FGS Austin 45T | 861230104
|  | 2022-03-16 | 107457 (2/7) | 601 Atlantis Rd | 62 |  |  |  | 3/17 3D | FEDEX P | * 3 DAY TURN * | 3/14 - BOT SIDE |  | *SHOULD CLEAR BY 3/9 - LAST PART DUE 3/11 KIT CLEAR 3/14 | 1 | Anderson Connectivity | Melbourne | FL | 32904-2316
|  | 2022-03-15 | 107730-1 (3/1) | 10525 Willows Rd Ne | 50/650 |  |  |  | 3/16 5D | FEDEX P | SEE ECO NOTE 5 - C OF C INFO FABS NO VSCORE - FABS DUE 3/10 | 3/1 - RTR (HOLD) 3/10 - AOI |  | *SHOULD CLEAR 3/2 - SHORT FAB - KIT CLEAR QTY 50 3/3 (NO VSCORE) 3/7 PICK UP FABS - KIT CLEAR 3/9 | 2 | Facebook Technologies, LLC | Redmond | WA | 98052-2545 | Attn: Sullivan Jon
|  | 2022-03-15 | 108420 (2/25) | 5100 Boyd Lake Ave | 117/ 250 |  |  |  | ??? 5D | FEDEX 2 DAY | RUN PARTIAL QTY 117 | FSU |  | 2/25 - KIT CLEAR FOR QTY 117 | 1 | Danhydra, Inc. | Loveland | CO | 80538-8944
|  | 2022-03-15 | 108655 (3/7) | 205 Apollo Rd | 1/9 |  |  |  | 3/16 5D | FEDEX GND | 3/8 - ITEM 20 WRONG SIZE | 3/11 - BACK |  | *3/4 - COULD CLEAR 3/7 - OK TO SKIP ITEMS 4, 5 & 44 KIT CLEAR 3/11 | 124 | Automation Industries, LLC | Montrose | CO | 81401-4854
|  | 2022-03-14 | 108481 (3/4) | 22 Bedford St Unit 4 | 15 |  |  |  | 3/18 10D | FEDEX P |  | 3/7 - AOI |  | KIT CLEAR 3/4 | 2 | Open Source Instruments, Inc. | Waltham | MA | 02453-3501 | Attn: Kevan Hashemi
|  | 2022-03-14 | 107438 (2/11) | 1020 Bahls St | 2 + 5 |  |  |  | ??? | FEDEX P | 2/28 SHIPPING HOLD QTY 2 SHP /QTY 5 REWORK | 2/14 - AOI |  | 2/11 - OK TO SKIP U33 & U34 - 2/24 - STILL PARTIAL SHORT - | 50 | Automation International | Danville | IL | 61832-3367
|  | 2022-03-14 | 107346-2 (2/7) | 22924 E Appleway Ave | 15 |  |  |  | 2022-06-01 | FEDEX GND | SHIP EARLY TO ADVANCED | 2/8 - AOI |  | KIT CLEAR 2/7 | 117 | Frencken America Inc. | Liberty Lake | WA | 99019-9514 | Frencken America, Inc, / Po Box 828 | 234304518
|  | 2022-03-14 | 104014 (2/22) | 2056 S 1100 E | 20 |  |  |  | 3/14 10D | FEDEX P | *DO NOT DEPANEL - For X1, use 5pcs of P/N ASTX-H11-24.000MHZ-T. Then use the ALT. P/N ASTMHTE-24.000MHZ-AJ-E-T. | 2/28 - AOI |  | *PRE BAKE 16 ITEMS & PCB - SEE ECO - 2/22 - SHORT ITEM 52 | 12 | Ripple, LLC | Salt Lake City | UT | 84106-2319
|  | 2022-03-14 | 106008-2ND (2/16) | 1938 University Ln Unit # C | 86 |  |  |  | 3/25 20D | FEDEX GND | SPLIT SHIPMENT | 3/4 - AOI |  | KIT CLEAR 2/25 | 17 | CPI - Satcom | Lisle | IL | 60532-2178 |  | 0604-1760-1
|  | 2022-03-11 | 108641 (3/9) | 4455 Boeing Dr | 5 |  |  |  | 3/14 3D | FEDEX P | * 3 DAY TURN * | 3/10 - BACK |  | KIT CLEAR 3/9 | 34 | Emerson | Rockford | IL | 61109-2932
|  | 2022-03-11 | 108466 (3/7) | 11 Huron Drive Suite 202 | 150 |  |  |  | 3/14 5D | FEDEX P |  | 3/9 - BACK |  | KIT CLEAR 3/7 | 0 | Aila Technologies, Inc. | Natick | MA | 1760
|  | 2022-03-11 | 106828 (2/22) | 7002 S Revere Pkwy Ste 60 | 7 |  |  |  | 3/4 5D | FEDEX P | 3/4 - SCREW ISSUE 3/7 - PLATES RTV FOR REPAIR | 3/4 - SCREW ISSUE - HOLD |  | KIT CLEAR 2/25 | 6 | Telspan Data | Centennial | CO | 80112-6767 |  | 342527426
|  | 2022-03-11 | 108526 (3/4) | 12455 Research Blvd | 5FA/ 15FA |  |  |  | 3/11 3D | FEDEX P | * 2 DAY TURN * SHIP QTY 5 ON 3/11 | 3/10 - AOI/BACK |  | COULD CLEAR 3/7 - 3/9 SHORT 7 ITEMS | 7 | Royal Circuits | Austin | TX | 78759-2314 | FGS Austin 45T | 861230104
|  | 2022-03-10 | 108412 (2/23) | 11100 Endeavor Ct Ste 300 | 20 |  |  |  | 3/17* 15D | FEDEX P | * TP22 MAX HEIGHT 3.3MM SEE ECO NOTE 5 | 3/4 - AOI |  | *SHOULD CLEAR 2/24 - KIT CLEAR 2/28 | 0 | NAL Research Corporation | Manassas | VA | 20109-4027 |  | 230306168
|  | 2022-03-10 | 106596 (2/25) | Parque Industrial FlexiPark Calle Potrerillos | 20/200 |  |  |  | 3/11* 10D | UPS INTL BLU | RUN PARTIAL QTY 20 - *SHIP EARLY* | 3/4 - BACK |  | KIT CLEAR 2/25 | 0 | ATL Technology CR | San Rafael de Alajuela | Costa Rica | 20108
|  | 2022-03-10 | 108049 (2/28) | 6411 Ivy Ln Ste 510 | 400 |  |  |  | 3/10 5D | FEDEX P | PRE BAKE SW1??? | 3/7 - TOP SIDE |  | *SHOULD CLEAR 3/2 - KIT CLEAR 3/3 | 0 | TRX Systems | Greenbelt | MD | 20770-1405 | Attn: Benjamin Funk
|  | 2022-03-10 | 107937-1 (3/2) | Vision Dr | 320/400 |  |  |  | 3/11 5D | FEDEX P | OK TO RUN PARTIAL QTY 381 | 3/9 - BACK |  | *3/4 - PARTIAL CLEAR | 0 | Cognex Corporation | Natick | MA | 01760-2083 | Attn: John Alberta | 198814415
|  | 2022-03-09 | 108332-1ST (3/4) | 1678 S Pioneer Rd | 20 |  |  |  | 3/9 3D | FEDEX P | T/H ONLY - 1ST ARTICLE |  |  | KIT CLEAR 3/4 | 5 | Varex Imaging Corporation | Salt Lake City | UT | 84104-4298 |  | 135447498
|  | 2022-03-09 | 105219 (2/16) | 110 Parkland Plz Ste B | 24 |  |  |  | 3/11 15D | FEDEX GND | SHORT 1 T/H ITEM | 3/1 - AOI |  | *SHOULD CLEAR 2/17 - KIT CLEAR 3/3 | 80 | ThorLabs | Ann Arbor | MI | 48103-6201
|  | 2022-03-09 | 104574 (2/22) | 3190 Monitor Ave Rm 0220 | 8 |  |  |  | 2022-03-11 | FEDEX P | 2/23 - FAB BAKE 48 HRS | 2/25 - AOI |  | KIT CLEAR 9/22 | 32 | University of Oklahoma | Norman | OK | 73019-5004 | Attn: Kurt Konyalioglu | 749026308
|  | 2022-03-09 | 108048 (2/28) | 6411 Ivy Ln Ste 510 | 100 |  |  |  | 3/10 5D | FEDEX P |  | 3/4 - AOI |  | *SHOULD CLEAR 3/2 - KIT CLEAR 3/3 | 0 | TRX Systems | Greenbelt | MD | 20770-1405 | Attn: Benjamin Funk
|  | 2022-03-08 | 108046 (3/1) | 2947 Bradley St Ste 130 | 2 |  |  |  | 3/9 5D | FEDEX P |  | 3/3 - AOI |  | KIT CLEAR 3/2 | 109 | Forza Silicon Corporation | Pasadena | CA | 91107-1566
|  | 2022-03-08 | 107236 (2/10) | 7000 East Ave LLNL FOR US DOE/NNSA Gen Rec Building 411 PO Number U2529495 | 69/100 |  |  |  | ??? 20D | UPS GND | QTY 87 CLEAR - QTY 13 SHORT | 2/14 - AOI |  | *2/10 - CLEAR TO RUN QTY 87 | 15 | Lawrence Livermore National Lab | Livermore | CA | 94550-9698 |  | 956956
|  | 2022-03-07 | 107345 (2/28) | 741 Radio Dr | 15 |  |  |  | 3/8 3D | FEDEX P | * 3 DAY TURN * | 3/3 - AOI |  | SHORT U2 - OK TO SKIP - KIT CLEAR 3/3 | 24 | Denmar Technical Services | Lewis Center | OH | 43035-7134 |  | 331355488
|  | 2022-03-07 | 108558 (2/23) | 218 Myles Drive | 10 |  |  |  | 3/9 10D | UPS GND |  | 2/23 - BACK |  | KIT CLEAR 2/23 | 47 | Siemens Industry, Inc | New Kensington | PA | 15068-7046 |  | 186569
|  | 2022-03-05 | 107174-2 (2/25) | 12000 Jefferson Ave | 11 |  |  |  | 3/4 5D | FEDEX GND |  | 3/2 - AOI |  | KIT CLEAR 2/25 | 11 | Jefferson Labs | Newport News | VA | 23606-4468 | JSA, LLC / Jefferson LAB Suite 12
|  | 2022-03-05 | 108212 (2/28) | 741 Radio Dr | 10 |  |  |  | 3/4 3D | FEDEX P | * 3 DAY TURN * | 3/2 - AOI |  | SHORT U69 - OK TO SKIP | 24 | Denmar Technical Services | Lewis Center | OH | 43035-7134 |  | 331355488
|  | 2022-03-04 | 106693 (2/11) | 5660 Airport Blvd Ste 101 | 4/50 |  |  |  | 2/18 5D | UPS GND | T/H ONLY *HOLD-WRONG FAB* |  |  | KIT CLEAR 2/11 - WRONG FAB | 1 | Churchill Navigation dba Shotover Systems, Inc. | Boulder | CO | 80301-2596 |  | R8A959
|  | 2022-03-03 | 107492 (2/24) | 1 Moonwalker Rd | 205 |  |  |  | 3/3 5D | FEDEX P |  | 3/1 - BACK |  | KIT CLEAR 2/24 | 11 | ILC Dover | Frederica | DE | 19946-2080 |  | 19118029
|  | 2022-03-02 | 108225 (2/28) | 9845 Willows Rd Ne | 500 |  |  |  | 3/3 3D | FEDEX P | *3 DAY TURN* | 3/1 - AOI |  | KIT CLEAR 2/28 | 0 | Facebook Technologies, LLC | Redmond | WA | 98052-2540
|  | 2022-03-02 | 108063 (2/25) | 9845 Willows Rd Ne | 120 |  |  |  | 3/3 3D | FEDEX P | * 3 DAY TURN * DEPANEL & SAND - RUN PARTIAL QTY 30 | 3/1 - AOI |  | KIT CLEAR 2/28 | 0 | Facebook Technologies LLC | Redmond | WA | 98052-2540
|  | 2022-03-01 | 107346-1 (2/7) | 22924 E Appleway Ave | 15 |  |  |  | 2022-03-01 | FEDEX GND | *DO NOT SHIP EARLY | 2/8 - AOI |  | KIT CLEAR 2/7 | 117 | Frencken America Inc. | Liberty Lake | WA | 99019-9514 | Frencken America, Inc, / Po Box 828 | 234304518
|  | 2022-03-01 | 100616 (2/23) | 3190 Monitor Ave Rm 0220 | 32 |  |  |  | 2022-03-12 | FEDEX P | 2/23 - FAB BAKE 48 HRS | 2/25 - BACK |  | KIT CLEAR 2/23 | 0 | University of Oklahoma | Norman | OK | 73019-5004 | Attn: Kurt Konyalioglu
|  | 2022-02-28 | 106037 (2/2) | 3535 Technology Dr Nw | 192 |  |  |  | 2/24 10D | UPS RED | DO NOT DEPANEL - SHIP QTY 192 ONLY | 2/22 - DELAM - WAITING FOR CUSTOMER |  | KIT CLEAR 2/17 | 2 | Benchmark Electronics | Rochester | MN | 55901-7965 |  | 80E07E
|  | 2022-02-28 | 106336-1 (2/17) | 1545 Forbes St | 2 |  |  |  | ??? 15D | FEDEX P | NEED TO HAND SOLDER SEVERAL ITEMS | 2/24 - AOI |  | *RUN QTY 2 SHORT 12 ITEMS (PAID HAND SOLDER) | 8 | McQ | Fredericksburg | VA | 22405-1606
|  | 2022-02-28 | 107898-2ND (2/21) | 600 N Dekora Woods Blvd | 95 |  |  |  | 2/28 2D | UPS RED | * 2 DAY TURN * MARK BAGS OF NON DEPANELED BOARDS | 2/24 - BACK |  | KIT CLEAR 2/24 | 20 | Alliance Technology, LLC. | Saukville | WI | 53080-1674 | Insight /Vision | 58X386
|  | 2022-02-25 | 107705 (2/23) | 1019 S Heatherwilde BLVD | 996 |  |  |  | 3/5 9D | FEDEX P | *DO NOT DEPANEL | 2/24 - AOI |  | KIT CLEAR 2/23 | 0 | Silicon Audio | Pfugerville | TX | 78660.6163 |  | 253053240
|  | 2022-02-24 | 107438 (2/11) | 1020 Bahls St | 5 |  |  |  | ??? | FEDEX P | 2/24 - STILL PARTIAL SHORT | 2/14 - AOI |  | 2/11 - OK TO SKIP U33 & U34 | 50 | Automation International | Danville | IL | 61832-3367
|  | 2022-02-24 | 104911-2ND (2/9) | 110 Sw Park Ter | 345 |  |  |  | 3/17 20D | FEDEX P | RUN BOT SIDE ONLY | FSU |  | *2/9 BOT CLEAR - TOP SHORT U3 | 5 | Oregon State University | Corvallis | OR | 97331-8676 | Attn: Roger Traylor/ Kelley Engineering CTR.
|  | 2022-02-23 | 106009 (2/3) | 1938 University Ln Unit # C | 106 |  |  |  | 3/3 20D | FEDEX GND | SPLIT SHIPMENT QTY 51 TO CPI/55 TO ADV | 2/14 - AOI |  | 2/3 - 2ND ARTICLE APPVD | 3 | CPI - Satcom | Lisle | IL | 60532-2178 |  | 0604-1760-1
|  | 2022-02-23 | 107918 (2/22) | 1 Analog Way | 6 |  |  |  | 2/23 1D | FEDEX P | ***HOT*** SHIP 2/23 | 2/23 - BACK |  | *SHOULD CLEAR 2/23 | 1 | Analog Devices, Inc. | Wilmington | MA | 01887-2356
|  | 2022-02-23 | 108295 (2/17) | 22 Bedford St Unit 4 | 200 |  |  |  | 2022-02-25 | FEDEX P |  | 2/23 - BACK |  | KIT CLEAR 2/17 | 3 | Open Source Instruments In | Waltham | MA | 02453-3501 | Attention: Kevan Hashem
|  | 2022-02-22 | 105709 (11/16) | 2940 Perrowville Rd | 12 |  |  |  | 2/24 5D | UPS BLUE | RAN PARTIAL - QTY 8/20 | 2/17 - AOI |  | SHOULD CLEAR 11/16 - KIT CLEAR 2/16 | 17 | Innerspec Technologies, Inc | Forest | VA | 24551-2225 |  | 55FE18
|  | 2022-02-18 | 107616 (1/31) | 9567 Arrow Rte | 50 |  |  |  | 3/3 10D | UPS GND | *ECO PRE BAKE D1, U1 U2 | FSU |  | 1/31 - SMT CLEAR ONLY - 2/10 RECV 1000 J3 - STILL SHORT 650 PCS | 62 | AQM Acquisition Corp dba Finna Group | Rancho Cucamonga | CA | 91730-4550 | Ste E / attn: HanH S | 519AW1
|  | 2022-02-18 | 108093 (2/10) | 7815 Silverton Ave Ste 2 | 25 |  |  |  | 2/18 3D | FEDEX P | * 3 DAY TURN * | 2/14 - BACK |  | *2/10 - SMT CLEAR - SHORT T/H | 70 | Rasirc | San Diego | CA | 92126-7301
|  | 2022-02-18 | 100606 (1/26) | 3190 Monitor Ave Rm 0220 | 10/100 |  |  |  | 2022-02-18 | #VALUE! |  | 2/9 - AOI |  | *FABS DUE 1/28, 2/1, 2/4, 2/7 | 8 | University of Oklahoma | Norman | OK | 73019-5004 | Attn: Redmond Kelley | 749026308
|  | 2022-02-17 | 106667 (2/10) | 358 2nd Ave Bldg 2 | 5 |  |  |  | 2/28 10D | UPS RED | *DNI U4, U5 & U6 | 2/11 - TOP SIDE |  | *2/10 - SMT CLEAR - KIT CLEAR 2/16 | 62 | QinetiQ NA TSG | Waltham | MA | 02451-1104 |  | X12456
|  | 2022-02-16 | 107898-1ST (2/8) | 600 N Dekora Woods Blvd | 5/95 |  |  |  | 2/16* 2D | UPS RED | * 2 DAY TURN * | 2/14 - AOI |  | 2/11 - SKIP ITEM 65 BOT & 59 TOP | 20 | Alliance Technology, LLC. | Saukville | WI | 53080-1674 | Insight /Vision | 58X386
|  | 2022-02-16 | 107726 (2/9) | 3500 Deer Creek Rd | 200 |  |  |  | 2/17 5D | FEDEX P | T/H ONLY | 2/9 - BACK |  | *2/9 CLEAR FOR QTY 150 - KIT CLEAR 2/10 | 7 | Tesla | Palo Alto | CA | 94304-1317
|  | 2022-02-16 | 106090 (2/2) | 3535 Technology Dr Nw | 200 |  |  |  | 2/17 5D | UPS RED | DO NOT DEPANEL | 2/14 - AOI |  | *SHOULD CLEAR 2/3 - 2/10 KIT CLEAR - FAB BAKED 48HRS | 3 | Benchmark Electronics | Rochester | MN | 55901-7965 |  | 80E07E
|  | 2022-02-15 | 107903 |  | 7 |  |  | FLEX FABS ONLY | [7 empty] | ANLOG DEVICES - CHRIS LUCCI
|  | 2022-02-15 | 107451 (2/2) | 601 Atlantis Rd | 50 |  |  |  | 2/17 5D | UPS GND |  | 2/10 - AOI |  | *SHOULD CLEAR 2/3 KIT CLEAR 2/10 | 1 | Anderson Connectivity | Melbourne | FL | 32904-2316 |  | 2E6E38
|  | 2022-02-15 | 107799 (2/9) | 3881 McGowen St | 10 |  |  |  | 2/23 10D | FEDEX P |  | FSU |  | KIT CLEAR 2/9 | 90 | Rocket Labs USA | Long Beach | CA | 90808-1702 |  | 122142710
|  | 2022-02-14 | 107632 | 5475 Airport Blvd | 1 |  |  | REWORK | 2022-02-10 | UPS RED | [5 empty] | Particle Measuring Systems | Boulder | CO | 80301-2339 |  | 810528
|  | 2022-02-14 | 106708 (1/18) | 200 Wisman Ln | 12 |  |  |  | 2/18 10D | FEDEX P |  | 1/21 - AOI |  | *SHORT U3 - OK TO SKIP | 50 | GatesAir, Inc. | Quincy | IL | 62301-1252 | Service Department
|  | 2022-02-11 | 107714 (1/31) | 1101 Market St | 1028 |  |  |  | 2022-02-14 | FEDEX P |  | 1/31 - AOI |  | KIT CLEAR 1/31 | 2 | Tennessee Valley Authority | Chattanooga | TN | 37402-2881 | Att: Fletcher Gibbs (MP5G-C)
|  | 2022-02-11 | 108173 |  | 96 |  |  | REWORK | 2022-02-10 | UPS RED
|  | 2022-02-11 | 107632 | 5475 Airport Blvd | 90 |  |  | REWORK | 2022-02-10 | UPS RED | [5 empty] | Particle Measuring Systems | Boulder | CO | 80301-2339 |  | 810528
|  | 2022-02-10 | 100605 (1/28) | 3190 Monitor Ave Rm 0220 | 20/140 |  |  |  | 2022-02-15 | FEDEX P |  | 2/8 - BACK |  | KIT CLEAR 2/2 - PRE BAKE REQD | 4 | University of Oklahoma | Norman | OK | 73019-5004 | Attn: Redmond Kelley | 749026308
|  | 2022-02-10 | 107632 | 5475 Airport Blvd | 100 |  |  |  | 2022-02-10 | UPS RED | [5 empty] | Particle Measuring Systems | Boulder | CO | 80301-2339 |  | 810528
|  | 2022-02-08 | 107538 (2/7) | 3 Henry Dr | 5 |  |  |  | 2022-02-21 | FEDEX P |  | FSU |  | KIT CLEAR 2/7 | 0 | HII Unmanned Systems, Inc. | Pocasset | MA | 02559-1415 |  | 253053240
|  | 2022-02-07 | 104636-2 (1/31) | 47281 Bayside Pkwy | 200/ 1000 |  |  |  | 2022-02-13 | FEDEX P |  | 2/1 - TOP SIDE |  | KIT CLEAR 1/31 | 9 | Enphase Energy | Fremont | CA | 94538-6517 | Attn: PO 2035113 | 442722803
|  | 2022-02-04 | 106017 (1/24) | 1938 University Ln Unit # C | 46 CPI / 50 ADV |  |  |  | 2/4 10D | FEDEX GND | *DO NOT SHIP EARLY - SPLIT SHIPMENT QTY 46/QTY 50 | 1/26 - BACK |  | KIT CLEAR 1/24 | 4 | CPI - Satcom | Lisle | IL | 60532-2178 |  | 0604-1760-1
|  | 2022-02-04 | 106421 (1/26) | 3365 Tree Court Industrial Blvd | 4 |  |  |  | 2/4 5D | FEDEX P |  | 1/28 - BACK |  | *SHORT DIODE - OK TO SKIP - KIT CLEAR 1/31 | 76 | Bausch & Lomb | Saint Louis | MO | 63122-6615
|  | 2022-02-03 | 106701 (1/19) | 22924 E Appleway Ave | 15 |  |  |  | 2/10 10D | FEDEX GND | DO NOT SHIP BEFORE 1/3/22 | 1/25 - AOI |  | KIT CLEAR 2/3 | 117 | Frencken America Inc. | Liberty Lake | WA | 99019-9514 | Po Box 828 | 234304518
|  | 2022-02-03 | 104911 (1/18) | 110 Sw Park Ter | 5FA/20 |  |  |  | 2/9 5D | FEDEX P |  | 1/19 - AOI |  | KIT CLEAR 2/2 | 5 | Oregon State University | Corvallis | OR | 97331-8676 | Attn: Roger Traylor/ Kelley Engineering CTR.
|  | 2022-02-03 | 107590 (1/28) | 22 Bedford St Unit 4 | 10 |  |  |  | 2022-02-07 | FEDEX P |  | 2/1 - AOI |  | KIT CLEAR 1/31 | 3 | Open Source Instruments, Inc. | Waltham | MA | 02453-3501 | Attn: Kevan Hashemi
|  | 2022-02-02 | 107413 (1/20) | 9845 Willows Rd Ne | 20 |  |  |  | 2/3 10D | FEDEX P |  | 1/21 - AOI |  | *1/20 WTG CF FOR U2 - OK TO SKIP | 35 | Facebook Technologies LLC | Redmond | WA | 98052-2540
|  | 2022-02-02 | 107452 (1/26) | 601 Atlantis Rd | 35 |  |  |  | 2/10 10D | UPS GND |  | 1/28 - AOI |  | *WILL CLEAR 1/27 | 0 | Anderson Connectivity | Melbourne | FL | 32904-2316 |  | 2E6E38
|  | 2022-02-01 | 107630 (1/25) | 11 Huron Drive Suite 202 | 255 |  |  |  | 2022-02-08 | FEDEX P |  | 1/26 - BACK |  | KIT CLEAR 1/25 | 0 | Aila Technologies, Inc. | Natick | MA | 1760
|  | 2022-02-01 | 107486 (1/17) | 110 Forbes Blvd | 4FA/10 |  |  |  | ??? 5D | FEDEX P |  | 1/24 - AOI |  | *SHOULD CLEAR 1/18 | 60 | NextPhase Medical Devices | Mansfield | MA | 02048-1145
|  | 2022-02-01 | 106891 (1/24) | 21 Hamilton Ct | 50 |  |  |  | 2/1 3D | FEDEX P | *3 DAY TURN * | RTR - C39,40,41 WRONG SIZE - USE ALTA STOCK |  | KIT CLEAR 1/27 | 68 | Royal Circuits | Hollister | CA | 95023-2535
|  | 2022-01-31 | 107912-2 (1/25) | 6250 Joyce Dr, | 94 |  |  |  | 2022-01-28 | FEDEX P | *NEED QTY 40 1 DAY TURN | 1/26 - BACK |  | *1/26 - STILL SHORT 1 PART | 4 | Industrialex Manufacturing | Arvada | CO | 80403
|  | 2022-01-31 | 107516 (1/18) | 104 Otis St | 55 |  |  |  | 1/31 4D | UPS BLUE | FABS DUE 1/26 | 1/26 - AOI |  | SHOULD CLEAR 1/21, 1/26 | 6 | Point Blank Enterprises, Inc. | Northborough | MA | 01532-2440 | ATSE, LLC | 7842A7
|  | 2022-01-31 | 107608 (1/19) | 3200 N Kings Hwy | 50 |  |  |  | 2/1 9D | UPS GND |  | 1/21 - AOI |  | KIT CLEAR 1/19 | 15 | Graph-Tech USA, LLC | Fort Pierce | FL | 34951-4051 |  | 04Y70W
|  | 2022-01-31 | 107456 (1/25) | 601 Atlantis Rd | 20 |  |  |  | 2022-02-08 | UPS GND |  | 1/26 - BACK |  | KIT CLEAR 1/25 | 0 | Anderson Connectivity | Melbourne | FL | 32904-2316 |  | 2E6E38
|  | 2022-01-28 | 106826 (1/24) | 100 Research Dr | 55 |  |  |  | 2022-01-31 | FEDEX P |  | 1/25 - AOI |  | KIT CLEAR 1/24 | 12 | Ascent AeroSystems | Wilmington | MA | 01887-4441
|  | 2022-01-28 | 107912-1 (1/25) | 6250 Joyce Dr, | 60/160 |  |  |  | 2022-01-28 | FEDEX P | *NEED QTY 40 1 DAY TURN | 1/26 - BACK |  | *1/26 - STILL SHORT 1 PART | 4 | Industrialex Manufacturing | Arvada | CO | 80403
|  | 2022-01-28 | 107607 (1/21) | 9845 Willows Rd Ne | 25 |  |  |  | 1/31 5D | FEDEX 2 DAY |  | 1/24 - AOI |  | KIT CLEAR 1/24 | 38 | Facebook Technologies LLC | Redmond | WA | 98052-2540
|  | 2022-01-27 | 107383 (1/12) | 16848 Jefferson Hwy | 400 |  |  |  | 1/31 10D | FEDEX P |  | 1/18 - BACK |  | KIT CLEAR 1/17 | 4 | Moates.Net | Baton Rouge | LA | 70817-6907 | attn: Craig Moates
|  | 2022-01-27 | 107519 (1/18) | 2300 Windy Ridge Pkwy Se Ste 400 | 5 |  |  |  | 1/31 5D | FEDEX P | LAST SHORTAGES CAME IN 1/25 | 1/21 - AOI |  | *SMT CLEAR 1/21 - DNI U4 - KIT CLEAR 1/25 | 22 | Scientific Research Corporation | Atlanta | GA | 30339-5665 | Attn: bthurmond | 153669597
|  | 2022-01-27 | 107104 (1/18) | 10060 Brecksville Rd | 14 |  |  |  | 2022-01-28 | FEDEX P |  | 1/24 - AOI |  | *1/18 BOT CLEAR - TOP SHORT - KIT CLEAR 1/21 | 5 | USA Firmware LLC. | Brecksville | OH | 44141-3293 | USA Firmware Paul Scaccia Embedeed Systems | 622598299
|  | 2022-01-26 | 107454 (1/19) | 601 Atlantis Rd | 50 |  |  |  | 2/2 10D | UPS GND |  | 1/20 - BACK |  | KIT CLEAR 1/19 | 2 | Anderson Connectivity | Melbourne | FL | 32904-2316 |  | 2E6E38
|  | 2022-01-26 | 107450 (1/19) | 601 Atlantis Rd | 50 |  |  |  | 2/2 10D | UPS GND |  | 1/20 - BACK |  | KIT CLEAR 1/19 | 1 | Anderson Connectivity | Melbourne | FL | 32904-2316 |  | 2E6E38
|  | 2022-01-26 | 107449 (1/19) | 601 Atlantis Rd | 50 |  |  |  | 2/2 10D | FEDEX P |  | 1/20 - BACK |  | KIT CLEAR 1/19 | 3 | Anderson Connectivity | Melbourne | FL | 32904-2316
|  | 2022-01-26 | 107470 (1/17) | 7610 S Alkire Pl Ste B | 50 |  |  |  | 1/26 5D | FEDEX GND |  | 1/21 - AOI |  | KIT CLEAR 1/18 | 9 | Design Solutions Inc. | Littleton | CO | 80127-3223 | ATTN: JON ANDERSON
|  | 2022-01-26 | 107786 (1/25) | 23 STRATHMORE RD | 10 |  |  |  | 2022-01-26 | FEDEX P | * 1 DAY TURN * | 1/25 - AOI |  | KIT CLEAR 1/25 | 0 | DELSYS INC | NATICK | MA | 01760-2444
|  | 2022-01-25 | 107348 (1/20) | 501 Wazee St | 25 |  |  |  | 2/4 10D | FEDEX GND | *HANDLE WITH GLOVES | 1/24 - BACK |  | KIT CLEAR 1/21 - DNI U2 | 0 | York Space Systems | Denver | CO | 80204-1858
|  | 2022-01-25 | 107482 (1/18) | 110 Forbes Blvd | 4FA/10 |  |  |  | 1/27 5D | FEDEX P |  | 1/21 - AOI |  | KIT CLEAR 1/20 | 52 | NextPhase Medical Devices | Mansfield | MA | 02048-1145
|  | 2022-01-25 | 107174-1 (1/18) | 12000 Jefferson Ave | 1 |  |  |  | 1/25 5D | FEDEX GND |  | 1/20 - AOI |  | KIT CLEAR 1/18 | 11 | Jefferson Labs | Newport News | VA | 23606-4468 | JSA, LLC / Jefferson LAB Suite 12
|  | 2022-01-25 | 107081 (1/18) | 2947 Bradley St Ste 130 | 2 |  |  |  | 1/25 5D | FEDEX P |  | 1/19 - BACK |  | KIT CLEAR 1/18 | 28 | Forza Ametek | Pasadena | CA | 91107-1566 | Attn: Jackson Law | 255688804
|  | 2022-01-24 | 107455 (1/19) | 601 Atlantis Rd | 50 |  |  |  | 2/2 10D | UPS GND |  | 1/20 - BACK |  | KIT CLEAR 1/19 | 0 | Anderson Connectivity | Melbourne | FL | 32904-2316 |  | 2E6E38
|  | 2022-01-24 | 103611 (1/17) | 1218 E Broadway | 50 38 |  |  |  | 1/28 5D | #VALUE! |  | 1/19 - AOI |  | *SHORT U33 - OK TO SKIP - KIT CLEAR 1/21 | 4 | Royal Circuits | Long Beach | CA | 90802-3532 | Attn Bryan Sydnor | 122142710
|  | 2022-01-24 | 107127 (1/13) | 200 Technology Dr | 50 |  |  |  | 1/27 9D | UPS BLUE |  | 1/17 - BACK |  | *SHORT ITEM 11 - OK TO SKIP KIT CLEAR 1/14 | 16 | Aeroprobe Corporation | Christiansburg | VA | 24073-7384 |  | 75V830
|  | 2022-01-24 | 107491 (1/17) | 21 Alpha Rd Suite 202 | 100 |  |  |  | 1/24 5D | FEDEX P |  | 1/18 - AOI |  | *1/17 SHORT ONLY 1 PC T/H | 7 | Atlas Devices | Chelmsford | MA | 01824-4170
|  | 2022-01-21 | 107445 (1/17) | 3800 E Centre Ave | 15 |  |  |  | 1/24 5D | FEDEX P |  | 1/19 - AOI |  | KIT CLEAR 1/17 | 6 | Stryker Medical | Portage | MI | 49002-5826 | AttnAnne Boomer /0885825501518 | 793229330
|  | 2022-01-21 | 106658 (1/11) | 1330 Ensell Rd | 1000 |  |  |  | 2/1 15D | FEDEX P |  | 1/17 - BACK |  | KIT CLEAR 1/11 | 2 | Hose Monster | Lake Zurich | IL | 60047-1574
|  | 2022-01-21 | 106403 (1/14) | 100 SANDUNE DR | 15 |  |  |  | 1/25 5D | FEDEX P | 2ND ARTICLE | 1/18 - BACK |  | KIT CLEAR 1/18 | 8 | LETD TECHNOLOGY | PITTSBURGH | PA | 15239-2716 | ATTN: TOM SCHNIEDER | 94123097
|  | 2022-01-21 | 106479 (1/13) | 1414 Harbour Way S Ste 1901 | 10 |  |  |  | 1/20 5D | FEDEX P |  | 1/17 - AOI |  | *DNI 10 LINE ITEMS KIT CLEAT 1/13 | 28 | SunPower Corporation | Richmond | CA | 94804-3606 | Kevin Fischer | 159816613
|  | 2022-01-20 | 107412 (1/14) | 7 Loveton Cir | 25 |  |  |  | 1/20 3D | FEDEX P | * 3 DAY TURN * | 1/19 - BACK |  | *SHORT U22 - OK TO SKIP | 1 | Becton, Dickinson and Company | Sparks | MD | 21152-9212 | Attn: Sandly Clark | 148834733
|  | 2022-01-20 | 106839 (1/10) | 3 Oak Park Dr | 27 |  |  |  | 1/20 5D | FEDEX P | RUN BOT SIDE ONLY - DNI U51 ONLY | 1/17 - AOI |  | *BOT SIDE SHORT ITEM - OK TO SKIP KIT CLEAR 1/14 | 44 | Medica Corporation | Bedford | MA | 01730-1413 |  | 471164747
|  | 2022-01-20 | 106012 (12/27) | 1938 University Ln Unit # C | 90 |  |  |  | 1/15 DO NOT SHIP EARLY | FEDEX GND | SPLIT SHIPMENT QTY 45 TO CUST QTY 45 TO ADV | 12/29 - AOI |  | *SHORT C53 - OK TO SKIP - KIT CLEAR 1/20 | 4 | CPI - Satcom | Lisle | IL | 60532-2178 |  | 60417601
|  | 2022-01-19 | 100617 (1/14) | 3190 Monitor Ave Rm 0220 | 32 FA |  |  |  | 1/28 15D | #VALUE! |  | 1/17 - AOI |  | KIT CLEAR 1/13 | 3 | University of Oklahoma | Norman | OK | 73019-5004 | Attn: Redmond Kelley | 749026308
|  | 2022-01-19 | 100613 (1/14) | 3190 Monitor Ave Rm 0220 | 8 FA |  |  |  | 1/28 15D | #VALUE! |  | 1/17 - AOI |  | KIT CLEAR 1/14 | 4 | University of Oklahoma | Norman | OK | 73019-5004 | Attn: Redmond Kelley | 749026308
|  | 2022-01-18 | 104885 (12/17) | 3011 Malibu Canyon Rd | 3FA/14 |  |  |  | 1/19 10D | FEDEX P | OK TO SHIP 1/18 | 1/7 - AOI |  | *BOT SIDE CLEAR 12/17 - TOP CLEAR 1/5 (ADDED FA) | 25 | HRL Laboratories | Malibu | CA | 90265-4737 | Att:Kenny Pruett | 97263508
|  | 2022-01-18 | 107332 (1/17) | 1 Vision Dr | 150 |  |  |  | 1/28 10D | FEDEX GND |  | 1/17 - AOI |  | KIT CLEAR 1/17 | 0 | Cognex | Natick | MA | 01760-2083 | Attn: ben Evans | 198814415
|  | 2022-01-18 | 105709 (11/16) | 2940 Perrowville Rd | 8/20 |  |  |  | 1/18 5D | UPS BLU | RUN PARTIAL - QTY 8 | 11/23 - TOP SIDE 1/12 - TOP SIDE |  | SHOULD CLEAR 11/16 - SHIP SHORT DC10 | 17 | Innerspec Technologies, Inc | Forest | VA | 24551-2225 |  | 55FE18
|  | 2022-01-17 | 107232 (1/7) | 9567 Arrow Rte | 105 |  |  |  | 2022-01-21 | UPS RED | *D3,D4,U1 & U4 SEAL BAGS PRIOR TO SHIPPING | 1/17 - BACK |  | KIT CLEAR 1/7 | 4 | AQM Acquisition Corp dba Finna Group | Rancho Cucamonga | CA | 91730-4550 | Ste E / attn: HanH S | 519AW1
|  | 2022-01-17 | 106023 (12/23) | 2056 S 1100 E | 20 |  |  |  | 1/24 5D | FEDEX P | PCB PRE BAKE DO NOT DEPANEL XRAY REQ | 1/17 - BACK |  | *SHORT D2 - OK TO SKIP ON BOT SIDE - TOP SIDE SHORT ETA 1/10 KIT CLEAR 1/17 | 3 | Ripple, LLC | Salt Lake City | UT | 84106-2319
|  | 2022-01-14 | 106016 (12/27) | 1938 University Ln Unit # C | 90 |  |  |  | 1/15 DO NOT SHIP EARLY | FEDEX GND | SPLIT SHIPMENT QTY 45 TO CUST QTY 45 TO ADV | 1/3 - IN SHIPPING |  | KIT CLEAR 12/27 | 0 | CPI - Satcom | Lisle | IL | 60532-2178 |  | 0604-1760-1
|  | 2022-01-14 | 106011 (12/27) | 1938 University Ln Unit # C | 300 |  |  |  | 1/15 DO NOT SHIP EARLY | FEDEX GND | SPLIT SHIPMENT QTY 150 TO CUST QTY 150 TO ADV | 1/4 - IN SHIPPING |  | KIT CLEAR 12/27 | 1 | CPI - Satcom | Lisle | IL | 60532-2178 |  | 0604-1760-1
|  | 2022-01-14 | 104636 (12/10) | 47281 Bayside Pkwy | 100/ 1100 |  |  |  | ??? | FEDEX P | QTY 100 SHIPPED | 12/11 - TOP SIDE |  | KIT CLEAR 1/11 | 9 | Enphase Energy | Fremont | CA | 94538-6517 | Attn: PO 2035113 | 442722803
|  | 2022-01-14 | 106324 (12/16) | 9845 Willows Rd Ne | 2496/ 6000 |  |  |  | ??? 10D | FEDEX P | RUN 2496 BOT SIDE ONLY | 12/22 - QTY 2496 BOT DONE |  | PARTIAL CLEAR QTY 2496 BOT SIDE | 0 | Facebook Technologies LLC | Redmond | WA | 98052-2540 | Attn: Wei Sun
|  | 2022-01-13 | 106808 (1/5) | 1001 W Algonquin St Dock D/E | 50 |  |  |  | ??? | FEDEX GND |  | 1/10 - AOI |  | *SMT CLEAR 1/7 | 25 | Raven - Aerostar International, Inc. | Sioux Falls | SD | 57104-0319 |  | 572941
|  | 2022-01-13 | 105892 (12/29) | 1830 Lefthand Cir Ste A | 1FA/4 |  |  |  | 2022-01-17 | FEDEX P | RUN BOT SIDE ONLY | 1/11 - AOI |  | *SHORT ITEMS AND FAB - FAB DUE 1/3, 1/10 - KIT CLEAR 1/10 | 385 | Honeybee Robotics | Longmont | CO | 80501-6717 |  | 501565164
|  | 2022-01-12 | 106008 (12/30) | 1938 University Ln Unit # C | 4FA/90 |  |  |  | 2022-01-11 | FEDEX GND | SHIP QTY 4 FA BAL WILL BE SPLIT SHIPMENT | 1/4 - AOI |  | KIT CLEAR 1/12 | 17 | CPI - Satcom | Lisle | IL | 60532-2178 |  | 0604-1760-1
|  | 2022-01-12 | 106872 (1/10) | 790 6th St | 28 |  |  |  | 2022-01-24 | FEDEX P |  | 1/11 - BACK |  | KIT CLEAR 1/10 | 13 | Pacific Northwest National Laboratory | Richland | WA | 99354-1873 | Contract# 605118 /Battelle for US DOE | 1317-4028-0
|  | 2022-01-12 | 107108 (12/29) | 741 Radio Dr | 3 |  |  |  | 1/14 3D | FEDEX P | * 3 DAY TURN * | 1/3 - AOI |  | KIT CLEAR 1/12 | 24 | Denmar Technical Services | Lewis Center | OH | 43035-7134
|  | 2022-01-11 | 106900 (12/29) | 450 Church St | 4 |  |  |  | 1/20 10D | FEDEX 2 Day |  | 1/7 - AOI |  | KIT CLEAR 1/6 | 21 | University of Michigan | Ann Arbor | MI | 48109-1040
|  | 2022-01-11 | 107260 (1/6) | 6250 Joyce Dr | 33 |  |  |  | 1/20 10D | FEDEX P |  | 1/10 - BACK |  | KIT CLEAR 1/6 | 0 | Industrialex Manufacturing | Arvada | CO | 80403
|  | 2022-01-11 | 107259 (1/5) | 6250 Joyce Dr, | 30 |  |  |  | 1/20 10D | FEDEX P |  | 1/7 - AOI |  | KIT CLEAR 1/6 | 3 | Industrialex Manufacturing | Arvada | CO | 80403
|  | 2022-01-10 | 106756 (12/23) | 8825 Stanford Blvd. #308 | 207 |  |  |  | 1/14 9D | FEDEX P |  | 1/5 - AOI |  | *SHORT FAB - DUE 12/28,KIT CLEAR 1/3 | 11 | Tactical Network Solutions | Columbia | MD | 21045
|  | 2022-01-10 | 107261 (1/5) | 63 Great Rd Ste 204 | 20 |  |  |  | 1/20 10D | FEDEX P |  | 1/7 - BACK |  | KIT CLEAR 1/7 | 0 | Dephy, Inc. | Maynard | MA | 01754-2097
|  | 2022-01-07 | 107226 (1/4) | 11100 Endeavor Ct Ste 300 | 4 |  |  |  | 1/15 5D | FEDEX P | SHIP 1/7 IF POSSIBLE | 1/5 - BOT SIDE |  | *KIT CLEAR 1/5 - DNI TP22 | 0 | NAL Research Corporation | Manassas | VA | 20109-4027 |  | 636328553
|  | 2022-01-07 | 107265 (12/30) | 3561 Nw 97th Ter | 100 |  |  |  | 1/17* 10D | FEDEX GND |  | 1/4 - AOI |  | *ALTA BUY R10 - DUE 1/4 | 2 | Ocean Sensor Systems, Inc | Coral Springs | FL | 33065-2811 | Attn: Thomas Pantelakis
|  | 2022-01-06 | 106797 (12/30) | 11800 Sw 147th Ave | 10 |  |  |  | 1/14 10D | UPS RED | *J1-J6 PLACE TOP NOT BOT (ECO) | 1/5 - TOP SIDE |  | KIT CLEAR 12/30 | 14 | Beckman Coulter | Miami | FL | 33196-2500 |  | F59725
|  | 2022-01-06 | 107027 (12/14) | 28 Park St | 15 |  |  |  | ??? | FEDEX P | * 3 DAY TURN * SHIPPING HOLD 12/17 | 12/16 - BACK |  |  | 0 | L3 Open Water Power | Somerville | MA | 02143-3214 | Ship to Code: A232 | 882931013
|  | 2022-01-05 | 105929 (11/9) | 10175 Philipp Pkwy | 100 |  |  |  | 2022-01-11 | UPS RED |  | 11/18 - AOI |  | KIT CLEAR 1/5 | 12 | Automated Packaging Systems, Inc. | Streetsboro | OH | 44241-4706 |  | 19E046
|  | 2022-01-05 | 107399 (1/3) | 22 Eastman Ave Ste A | 100 |  |  |  | 1/10 5D | FEDEX 2 day |  | 1/4 - AOI |  | KIT CLEAR 1/3 | 0 | RX Monitoring Service, Inc. | Bedford | NH | 03110-6702 |  | 199197738
|  | 2022-01-05 | 104894 (10/29) | 5660 Airport Blvd Ste 101 | 42 |  |  |  | 1/7* | UPS GND | BAL QTY 42 SHORT T/H | 11/16 - BACK |  | * SHORT J3 42 PCS SHIP PARTIAL QTY 53 11/19 - KIT CLEAR 1/4 | 7 | Churchill Navigation dba Shotover Systems Inc | Boulder | CO | 80301-2596 |  | R8A959
|  | 2022-01-04 | 106009 (12/27) | 1938 University Ln Unit # C | 4FA/110 |  |  |  | 1/11 10D | FEDEX GND | SHIP QTY 4 FA BAL WILL BE SPLIT SHIPMENT | 1/3 - AOI |  | KIT CLEAR 12/27 | 3 | CPI - Satcom | Lisle | IL | 60532-2178 |  | 0604-1760-1
|  | 2022-01-04 | 106969 (12/20) | 1775 W Hibiscus Blvd Ste 200 | 10 |  |  |  | 1/10 10D | FEDEX P |  | 12/28 - AOI |  | KIT CLEAR 12/23 | 0 | Aeronix Inc | Melbourne | FL | 32901-2627 | attn: Jeff Smith
|  | 2022-01-04 | 106940 (12/28) | 6060 Spine Rd | 60 |  |  |  | 1/5 5D | FEDEX P |  | 1/3 - BACK |  | KIT CLEAR 12/28 | 12 | Suez WTS Analytical Instruments, Inc. | Boulder | CO | 80301-3323 |  | 227369477
|  | 2022-01-03 | 100607 RMA | 110 Sw Park Ter | 85 | [10 empty] | Oregon State University | Corvallis | OR | 97331-8676
|  | 2022-01-03 | 106017 (12/27) | 1938 University Ln Unit # C | 4FA/100 |  |  |  | 1/11 10D | FEDEX GND | SHIP QTY 4 FA BAL WILL BE SPLIT SHIPMENT | 1/3 - BACK |  | KIT CLEAR FOR QTY FA 12/27 | 4 | CPI - Satcom | Lisle | IL | 60532-2178 |  | 0604-1760-1
|  | 2022-01-03 | 106972 (12/20) | 1775 W Hibiscus Blvd Ste 200 | 2 |  |  |  | 2021-01-07 | FEDEX P |  | 12/22 - AOI |  | KIT CLEAR 12/22 | 39 | Aeronix Inc | Melbourne | FL | 32901-2627 | attn: Jeff Smith
|  | 2021-12-30 | 107247 (12/28) | 8560 State Route 47 | 8 |  |  |  | 1/3 3D | UPS RED | * 3 DAY TURN * NEED TO HAND SOLDER Y1 | 12/29 - TOP SIDE |  | KIT CLEAR 12/28 DNI 19 ITEMS/BTD BAL | 17 | Midmark Corporation | Versailles | OH | 45380 | Attn: Todd Dues Plant B-North Docks #1, 4-6
|  | 2021-12-30 | 106794 (12/21) | 7051 Industrial Blvd | 25 |  |  |  | 12/30 5D | UPS RED |  | 12/28 - AOI |  | KIT CLEAR 12/22 | 10 | ABB Inc. | Bartlesville | OK | 74006-6036 |  | 160E6W
|  | 2021-12-30 | 106126 (12/22) | 452 W 1260 N | 50 |  |  |  | 12/30 5D | UPS GND |  | 12/23 - AOI |  | KIT CLEAR 12/22 | 12 | oxtek | Orem | UT | 84057-2941 |  | 84W253
|  | 2021-12-30 | 106882 (12/20) | 2947 Bradley St Ste 130 | 2 |  |  |  | 12/30 5D | FEDEX P |  | 12/23 - BACK |  | *SHORT 4 ITEMS - OK TO SKIP | 96 | Forza Ametek | Pasadena | CA | 91107-1566 | 91107-1566
|  | 2021-12-30 | 106200 (12/20) | 9845 Willows Rd Ne | 20 |  |  | DNI SHORT T/H | 12/27* | FEDEX P | * 3 DAY TURN * | 12/22 - AOI |  | 12/21 - SHORT T/H ONLY | 14 | Facebook Technologies LLC | Redmond | WA | 98052-2540
|  | 2021-12-29 | 106964 (12/23) | 125 North Drive | 20 |  |  |  | 1/3 3D | FEDEX P | * 3 DAY TURN * | 12/27 - AOI |  | KIT CLEAR 12/28 DNI SHORTAGES | 1 | Kopin Corporation | Westborough | MA | 1581
|  | 2021-12-29 | 107054 (12/17) | 4505 Campus Dr | 3 |  |  |  | 2021-12-30 | FEDEX P |  | 12/22 - AOI |  | *SHORT 2 LINE ITEMS - OK SKIP KIT CLEAR 12/28 | 60 | IonQ, Inc. | College Park | MD | 20740-3899 | Attn: Shea Metzgar
|  | 2021-12-29 | 106772 (12/21) | 1607 Grand Ave Unit 23 | 29 |  |  |  | 12/30 5D | FEDEX P | T&R BAKE 12/6 2ND ARTICLE | 12/22 - AOI |  | KIT CLEAR 12/22 | 24 | Engineering Design Group, LLC | Glenwood Springs | CO | 81601-3873
|  | 2021-12-28 | 106580 (12/14) | 7 Loveton Cir | 20 |  |  |  | 12/30 5D | FEDEX P | QTY 12 DONE 12/16 | 12/22 - AOI |  | *SHORT FAB ONLY - DUE 12/21 - CLEAR 12/22 | 11 | Becton, Dickinson and Company | Sparks | MD | 21152-9212 | Attn: Changyi Li | 148834733
|  | 2021-12-28 | 106776 (12/21) | 1607 Grand Ave Unit 23 | 29 |  |  |  | 12/30 5D | FEDEX P | T&R BAKE 12/6 2ND ARTICLE | 12/23 - AOI |  | KIT CLEAR 12/22 | 24 | Engineering Design Group, LLC | Glenwood Springs | CO | 81601-3873
|  | 2021-12-28 | 107024 (12/20) | 2118 Washington Avenue Suite 1000 | 10 |  |  |  | 2021-12-29 | FEDEX P | ECO NOTE FOR U12 | 12/22 - AOI |  | KIT CLEAR 12/21 - SKIP ITEM 8 (BUY) | 5 | Exyn Technologies | Philadelphia | PA | 19146
|  | 2021-12-28 | 104636 (12/10) | 47281 Bayside Pkwy | 100/1200 |  |  |  | 2021-12-28 | FEDEX P | QTY 100 CLEAR ONLY | 12/20 - AOI |  |  | 9 | Enphase Energy | Fremont | CA | 94538-6517 | Attn: PO 2035113 | 442722803
|  |  | 106839 (12/9) | 3 Oak Park Dr | 3FA/30 |  |  |  | 2021-12-28 | FEDEX P | SHIP 2 BARE FABS WITH JOB | 12/21 - AOI |  | KIT CLEAR 12/20 | 44 | Medica Corporation | Bedford | MA | 01730-1413 |  | 471164747
|  | 2021-12-27 | 106785 (12/13) | 202 Burlington Rd | 5 |  |  |  | 2021-12-27 | FEDEX P | SHIELDS BUILD TO DEPLETION | 12/21 - AOI |  | KIT CLEAR 12/17 | 11 | Mitre | Bedford | MA | 01730-1407 |  | 363437125
|  | 2021-12-27 | 106784 (12/7) | 1152 Park Ave | 5 |  |  |  | 2021-12-30 | FEDEX P | XRAY REQ | 12/14 - AOI |  | *PARTIAL CLEAR BY 12/10 - SKIP U2 - KIT CLEAR 12/27 | 8 | Enovate Medical /Stinger Medical | Murfreesboro | TN | 37129-4912
|  | 2021-12-27 | 105483 (12/8) | 7975 N Central Dr | 30 |  |  |  | 2021-12-30 | FEDEX GND | ALL T/H - 15 DAY TURN |  |  | *12/8 - ONLY SHORT 2 ITEMS - KIT CLEAR 12/27 | 74 | Gilson Company, Inc. | Lewis Center | OH | 43035-9409 |  | 358755674
|  | 2021-12-23 | 107087 |  | 6 |  |  | RWK B97453 | 2021-12-23 |  | PAID REWORK | 11/22 - BACK |  | KIT CLEAR 12/13 | [6 empty] | 810528
|  | 2021-12-23 | 107402 | 5475 Airport Blvd | 3 |  |  |  | 2021-12-23 | UPS RED | PAID REWORK | 11/22 - BACK |  | KIT CLEAR 12/13 | 8 | Particle Measuring Systems | Boulder | CO | 80301-2339 |  | 810528
|  | 2021-12-23 | 106039 (12/8) | 2112 Case Pkwy Ste 1 | 100 |  |  |  | 2021-12-23 | FEDEX P | *** DO NOT SHIP EARLY *** | 12/17 - AOI |  | *SHOULD CLEAR 12/8, 12/15 - CLEAR 12/16 | 11 | AVID Technologies | Twinsburg | OH | 44087-2378
|  | 2021-12-23 | 107159 (12/17) | 22 Eastman Ave Ste A | 28 |  |  |  | 2021-12-27 | FEDEX P |  | 12/21 - AOI |  | KIT CLEAR 12/17 | 13 | RX Monitoring Service, Inc. | Bedford | NH | 03110-6702 |  | 199197738
|  | 2021-12-22 | 104378 (12/17) | 4291 W 96th St | 5 |  |  |  | 2021-12-27 | FEDEX P | 2ND ARTICLE APPROVED | 12/20 - AOI |  | KIT CLEAR 12/17 | 24 | PC Krause & Associates | Indianapolis | IN | 46268-1113
|  | 2021-12-22 | 105929 (11/9) | 10175 Philipp Pkwy | 150/250 |  |  |  | 2021-12-22 | UPS RED | QTY 150 CONN RECEIVED | 11/18 - AOI |  | *SMT CLEAR 11/8 | 12 | Automated Packaging Systems, Inc. | Streetsboro | OH | 44241-4706 |  | 19E046
|  | 2021-12-22 | 106622 (12/14) | 600 N Field Dr | 50 |  |  |  | 2021-12-27 | FEDEX P |  | 12/20 - AOI |  | KIT CLEAR 12/17 | 11 | ICUMedical | Lake Forest | IL | 60045-4835 |  | 224197349
|  | 2021-12-21 | 106584 (12/14) | 5391 Three Notched Rd | 27 |  |  |  | 12/21, 12/27 | FEDEX P | 2ND ARTICLE | 12/17 - AOI |  | KIT CLEAR 12/14, 12/17 | 0 | Allocortech Inc. | Crozet | VA | 22932-3181 | Front Lobby
|  | 2021-12-21 | 107206 (12/17) | 11100 Endeavor Ct Suite 300 | 200 |  |  |  | 2021-12-22 | FEDEX P | * 3 DAY TURN * | 12/20 - BACK |  | KIT CLEAR 12/17 | 0 | NAL Research Corporation | Manassas | VA | 20109-4027 |  | 636328553
|  | 2021-12-20 | 106913 (12/9) | 22 Bedford St | 300 |  |  |  | 2021-12-28 | FEDEX P | RUN BOT ONLY TOP SHORT | 12/14 - AOI |  | KIT CLEAR 12/13 | 4 | Open Source Instruments, Inc | Waltham | MA | 02453-3501 | Unit 4 Attn: Kevan Hashemi
|  | 2021-12-20 | 106325 (12/9) | 9845 Willows Rd Ne | 1000 |  |  |  | 2021-12-23 | FEDEX P | QTY 1000 SHIPPED 12/17 | 12/10 - AOI/BACK |  | KIT CLEAR 12/9 | 0 | Facebook Technologies LLC | Redmond | WA | 98052-2540 | Attn: Wei SUn
|  | 2021-12-17 | 106325 (12/9) | 9845 Willows Rd Ne | 1000/2000 |  |  |  | 2021-12-23 | FEDEX P |  | 12/10 - AOI/BACK |  | KIT CLEAR 12/9 | 0 | Facebook Technologies LLC | Redmond | WA | 98052-2540 | Attn: Wei SUn
|  | 2021-12-17 | 106836 (12/10) | 226 E Main St Ste 1 | 5 |  |  |  | 2021-12-20 | FEDEX P |  | 12/14 - AOI |  | KIT CLEAR 12/13 - SHORT ATTRITION | 31 | MIDI Product Development Corporation | Smithtown | NY | 11787-2918 | Attn; Chris Montalbano
|  | 2021-12-17 | 106614 (12/8) | 5511 Capital Center Dr Ste P125 | 10 |  |  |  | 2021-12-17 | FEDEX P |  | 12/10 - AOI |  | *12/8 - SHORT ATTRITION ONLY | 20 | Plexus Engineering Solutions | Raleigh | NC | 27606-4884 | PLXS-ENG RDC receiving
|  | 2021-12-17 | 105008 (11/22) | 6250 Joyce Dr | 20 |  |  |  | 2021-12-13 | FEDEX P | WTG CUST PART | 11/30 - AOI |  | KIT CLEAR 11/24 | 18 | Industrialex Manufacturing | Arvada | CO | 80403
|  | 2021-12-17 | 105640 (11/16) | 9500 Spallation Dr | 37 |  |  |  | 2021-12-03 | FEDEX P | *SHIP HOLD - RE QUOTING | 11/18 - BACK |  | KIT CLEAR 11/17 | 72 | Oak Ridge National Labs | Oak Ridge, | TN | 37830 | Attn: 4000172979 U.S. DOE C/O UT-Battle, LLC | 569242886
|  | 2021-12-16 | 104302 (12/1) | 1025 W 1700 N | 240 |  |  |  | 2021-12-30 | UPS GND | 2ND ARTICLE | 12/6 - AOI |  | 2ND ARTICLE CLEAR 12/2 | 1 | Automation Products | Logan | UT | 84321-1713 |  | X92925
|  | 2021-12-16 | 103015 (11/22) | 650 W Cherry St | 5 |  |  |  | 2021-12-16 | FEDEX P |  | 12/9 - AOI |  | KIT CLEAR 11/23 | 5 | Kinze Manufacturing | North Liberty | IA | 52317-9024
|  | 2021-12-15 | 107141 (12/13) | 5475 Airport Blvd | 25 |  |  |  | 2021-12-16 | UPS RED | PAID REWORK | 11/22 - BACK |  | KIT CLEAR 12/13 | 8 | Particle Measuring Systems | Boulder | CO | 80301-2339 |  | 810528
|  | 2021-12-15 | 106367 (12/1) | 150 Congress St. | 5 |  |  |  | 2021-12-15 | FEDEX P |  | 12/1 - AOI |  | KIT CLEAR 12/1 | 45 | Markem Imaje | Keene | NH | 3431 | Markem-Imaje Corporation (Keene) Dock 1
|  | 2021-12-15 | 105082 (12/1) | 3110 N Oakland Ste 101 | 10 |  |  |  | 2021-12-15 | FEDEX P |  | 12/9 - AOI |  | KIT CLEAR 12/8 | 64 | H&S Technical Services, Inc. | Mesa | AZ | 85215-1167 |  | 214715309
|  | 2021-12-15 | 106717 (12/2) | 218 Myles Dr | 10 |  |  |  | 2021-12-16 | FEDEX GND |  | 12/2 - BACK |  | KIT CLEAR 12/2 | 47 | Siemens Industry, Inc. | New Kensington | PA | 15068-7046 |  | 186569
|  | 2021-12-15 | 106764 (12/3) | 225 Suburban Rd | 20 |  |  |  | 2021-12-16 | FEDEX P |  | 12/8 - AOI |  | KIT CLEAR 12/13 | 21 | Inspired Flight | San Luis Obispo | CA | 93401-7546 |  | 965848010
|  | 2021-12-15 | 106616 (12/6) | 1020 Bahls St | 10 |  |  |  | 2021-12-20 | UPS GND | 1 SMT / 20 T/H | 12/7 - BACK |  | KIT CLEAR 12/6 | 20 | Automation International | Danville | IL | 61832-3367 |  | 648-26E
|  | 2021-12-15 | 105088 (10/1) | 4501 Hatfield St | 100 |  |  |  | 2021-12-22 | UPS GND | SPLIT SHIPMENT LAST 100 PCS | 10/8 - AOI |  | KIT CLEAR 10/1 | 0 | Carnegie Robotics | Pittsburgh | PA | 15201-3023 |  | V3725X
|  | 2021-12-13 | 106095 (11/19) | 6250 Joyce Dr | 3 |  |  |  | 12/8* 12/16 | FEDEX P | REMOVE LOCATING PINS - SEE ECO | 11/22 - AOI |  | KIT CLEAR 11/23 | 50 | Industrialex Manufacturing | Arvada | CO | 80403
|  | 2021-12-13 | 105880 (12/7) | 5355 W 76th St | 24 |  |  |  | 2021-12-14 | UPS RED |  | 12/8 - AOI |  | 12/7 - PARTIAL SHORT 4 FABS | 0 | Beckman Coulter | Indianapolis | IN | 46268-4166 | Building 87 Dock 39, | E294W3
|  | 2021-12-13 | 106710 (12/3) | 3200 N Kings Hwy | 30 |  |  |  | 2021-12-14 | UPS GND |  | 12/8 - AOI |  | KIT CLEAR 12/7 | 7 | Graph-Tech USA, LLC | Fort Pierce | FL | 34951-4051 |  | 04Y70W
|  | 2021-12-13 | 106403 (11/16) | 100 SANDUNE DR | 5FA /20 |  |  |  | 2021-12-13 | FEDEX P | SHORT T/H | 11/18 - AOI |  | KIT CLEAR 12/9 | 8 | LETD TECHNOLOGY | PITTSBURGH | PA | 15239-2716 | ATTN: TOM SCHNIEDER | 94123097
|  | 2021-12-13 | 104586 (9/28) | 3260 Industry Dr Ste 5 | 57 |  |  |  | 2021-12-15 | FEDEX P | LAST PARTIAL SHIPMENT | 11/13 - BACK |  | KIT CLEAR 10/1 | 2 | Ace Electronics, Inc. | North Charleston | SC | 29418-8478
|  | 2021-12-13 | 106805 (12/8) | 25101 Rye Canyon Loop | 10 |  |  |  | 2021-12-13 | UPS RED | * 3 DAY TURN * | 12/8 - AOI |  | KIT CLEAR 12/8 | 28 | SetPoint Medical Corporation | Valencia | CA | 91355-5004 |  | 37YF94
|  | 2021-12-13 | 106458 (12/6) | 7610 S Alkire Pl Ste B | 14 |  |  |  | 2021-12-13 | FEDEX GND |  | 12/7 - AOI |  | KIT CLEAR 12/6 | 45 | Design Solutions Inc. | Littleton | CO | 80127-3223 | ATTN: JON ANDERSON
|  | 2021-12-13 | 106772 (12/2) | 1607 Grand Ave Unit 23 | 1FA/30 |  |  |  | 2021-12-13 | FEDEX P | T&R BAKE 12/6 | 12/7 - AOI |  | FA CLEAR 12/6 - ITEM 6 SHARED | 24 | Engineering Design Group, LLC | Glenwood Springs | CO | 81601-3873
|  | 2021-12-13 | 106776 (12/2) | 1607 Grand Ave Unit 23 | 1FA/30 |  |  |  | 2021-12-13 | FEDEX P | T&R BAKE 12/6 | 12/7 - AOI |  | FA CLEAR 12/6 - ITEM 6 SHARED | 24 | Engineering Design Group, LLC | Glenwood Springs | CO | 81601-3873
|  | 2021-12-13 | 105166 (11/29) | 22 Jordan Cove Rd | 75 |  |  |  | 2021-12-13 | UPS ORG |  | 11/30 - AOI |  | KIT CLEAR 11/29 | 3 | Coastal Designs, LLC | Waterford | CT | 06385-3227 |  | 238V3V
|  | 2021-12-10 | 105783 (12/7) | 15711 Waynita Way Ne Apt H101 | 500 |  |  |  | 2021-12-10 | FEDEX P | * 3 DAY TURN * | 12/9 - BACK |  | KIT CLEAR 12/7 | 0 | Facebook Technologies LLC | Bothell | WA | 98011-7424 | Attn Kevin Rhodes
|  | 2021-12-10 | 103012 |  | 20 |  |  | WIRE SAMPLES
|  | 2021-12-10 | 104539 (8/31) | 33 Marsiling Industrial Estate Rd 3 | 30 |  |  |  | 2021-12-10 | FEDEX INT P | RECV U8 11/24 | 11/24 - BACK |  | KIT CLEAR 11/24 | 20 | Life Technologies Holding PTE Ltd |  |  | 739256 | Singapore | 241788121
|  | 2021-12-10 | 106140 (11/30) | 50 Alberigi Drive, Ste 103 | 10 |  |  |  | 2021-12-10 | FEDEX P | QTY 10 DAMAGED PART | 12/9 - BACK |  | SHIPPED QTY 35 12/9 | 34 | Assetlink Global | Jessup | PA | 18434
|  | 2021-12-09 | 105881 (11/4) | 4483 Parkway Dr | 2 |  |  |  | 2021-12-06 | FEDEX 2 DAY |  | 11/18 - AOI |  | *SHORT U37,38,39 40 (SKIP) BOT SIDE | 76 | ES Controls, LLC | Melbourne | FL | 32934-7767 | Attn; Jeff Stephens
|  | 2021-12-09 | 106410 (12/2) | 145 Pine Haven Shores Rd Ste 2095 | 20 |  |  |  | 2021-12-09 | FEDEX GND |  | 12/7 - AOI |  | KIT CLEAR 12/2 | 0 | St Jude Medical | Shelburne | VT | 05482-7815 | Att: Aaron Stein | 450036900
|  | 2021-12-09 | 106544 (11/30) | 595 Anglum Rd | 5 |  |  |  | 2021-12-09 | FEDEX P | * 3 DAY TURN * | 12/2 - AOI |  | KIT CLEAR 12/6 | 19 | BioMerieux | Hazelwood | MO | 63042-2320 | Attn: Jim VanGordon | 293024243
|  | 2021-12-09 | 106219 (12/1) | 7051 Industrial Blvd | 20 |  |  |  | 2021-12-09 | UPS RED | 2ND ARTICLE | 12/3 - AOI |  | KIT CLEAR 12/2 | 14 | ABB Inc. | Bartlesville | OK | 74006-6036 | ABB Inc Bartles Totalflow ATTN: Brian Smith | 160E6W
|  | 2021-12-09 | 106140 (11/30) | 50 Alberigi Drive, Ste 103 | 35 |  |  |  | 2021-12-09 | FEDEX P |  | 12/3 - AOI |  | KIT CLEAR 12/2 - BUILD TO DEPLETION | 34 | Assetlink Global | Jessup | PA | 18434
|  | 2021-12-08 | 106532 (12/3) | 303 S Technology Ct | 6 |  |  |  | 2021-12-08 | FEDEX P | * 3 DAY TURN * SHIELD DNF | 12/6 - AOI |  | KIT CLEAR 12/3 | 18 | Honeywell International Inc | Broomfield | CO | 80021-3489 | Attn Leonardo Ascarrunz | 2022-3188-8
|  | 2021-12-08 | 105305 (12/3) | 11100 Endeavor Ct Suite 300 | 100 |  |  |  | 2021-12-08 | FEDEX P | * 3 DAY TURN * | 12/6 - BACK |  | KIT CLEAR 12/3 | 2 | NAL Research Corporation | Manassas | VA | 20109-4027 |  | 636328553
|  | 2021-12-08 | 104509 (11/5) | 4 Constitution Way | 600 |  |  |  | 2021-12-08 | UPS RED |  | 11/12 - AOI |  | KIT CLEAR - 11/8 | 2 | Servomex Inc | Woburn | MA | 01801-8510 |  | 014478
|  | 2021-12-07 | 106777 (12/6) | 6030 W Harold Gatty Dr | 120 |  |  |  | 2021-12-09 | UPS RED | REWORK ONLY |  |  | KIT CLEAR 12/6 | 1 | Biosonix | Salt Lake City | UT | 84116-3928 |  | 59TT20
|  | 2021-12-07 | 105972 (11/9) | 6250 Joyce Dr. | 8 |  |  |  | 11/26* 12/6 | FEDEX P | T/H ONLY | 11/9 - BACK |  | KIT CLEAR 11/18 | 35 | Industrialex Manufacturing | Arvada | CO | 80403
|  | 2021-12-07 | 106782 (11/30) | 22A Eastman Ave Ste A | 28 |  |  |  | 2021-12-07 | Fedex 2 day |  | 12/2 - AOI |  | KIT CLEAR 11/30 | 9 | RX Monitoring Service, Inc. | Bedford | NH | 03110-6702 |  | 199197738
|  | 2021-12-07 | 106711 (11/29) | 3200 N Kings Hwy | 30 |  |  |  | 2021-12-07 | UPS GND |  | 12/1 - AOI |  | KIT CLEAR 11/30 | 34 | Graph-Tech USA, LLC | Fort Pierce | FL | 34951-4051 |  | 04Y70W
|  | 2021-12-07 | 104662 (11/30) | 7610 S Alkire Pl Ste B | 90 |  |  |  | 2021-12-07 | FEDEX P | 2ND ARTICLE | 12/1 - AOI |  | 2ND ARTICLE RELEASED 11/30 | 1 | Design Solutions Inc. | Littleton | CO | 80127-3223 | ATTN: JON ANDERSON
|  | 2021-12-06 | 105881 (11/4) | 4483 Parkway Dr | 8 |  |  |  | 2021-12-06 | FEDEX 2 DAY |  | 11/18 - AOI |  | *SHORT U37,38,39 40 (SKIP) BOT SIDE | 76 | ES Controls, LLC | Melbourne | FL | 32934-7767 | Attn; Jeff Stephens
|  | 2021-12-06 | 106584 (11/24) | 5391 Three Notched Rd | 3FA/30 |  |  |  | 2021-12-06 | FEDEX P |  | 11/30 - AOI |  | KIT CLEAR 11/29 | 0 | Allocortech Inc. | Crozet | VA | 22932-3181 | Front Lobby
|  | 2021-12-06 | 105944 (11/12) | 1901 10th St #300 | 50 |  |  |  | 2021-12-06 | UPS GND |  | 11/19 - BACK |  | KIT CLEAR 11/12 | 67 | Newark Electronics | Plano | TX | 75074-8036 |  | V90E84
|  | 2021-12-06 | 106145 (11/18) | 253 Fuller Rd | 5 |  |  |  | 2021-12-06 | FEDEX P |  | 11/19 - AOI |  | KIT CLEAR 11/19 | 91 | SUNY Polytechnic Institute | Albany | NY | 12203-3640 |  | 196000038
|  | 2021-12-03 | 106121 (11/23) | 42 Old Ridgebury Rd | 20 |  |  |  | 2021-12-03 | FEDEX P | *3 DAY TURN* *SHORT* | 12/1 - AOI |  | KIT CLEAR 11/29 | 16 | Owl Cyber Defense Solutions, LLC | Danbury | CT | 06810-5246 |  | 254842575
|  | 2021-12-03 | 106502 (11/24) | 2947 Bradley St Ste 130 | 2 |  |  |  | 2021-12-03 | FEDEX P |  | 11/30 - AOI |  | KIT CLEAR 11/24 | 46 | Forza Ametek | Pasadena | CA | 91107-1566 | Attn: Jackson Law | 255688804
|  | 2021-12-03 | 104421 (11/10) | 535 Indigo Dr | 450 |  |  |  | 2021-12-03 | FEDEX P |  | 11/15 - AOI |  | KIT CLEAR 11/10 | 1 | Barminder | Roswell | GA | 30075-2859
|  | 2021-12-02 | 104931 (10/1) | 586 Fulling Mill Rd | 22 |  |  |  | 2021-12-02 | FEDEX P | 2ND ARTICLE ROWC | 11/30 - AOI |  | KIT CLEAR 11/22 | 14 | Phoenix Contact, Inc. | Middletown | PA | 17057-2966 | Attn: Receiving-350 | 958605234
|  | 2021-12-02 | 106455 (11/22) | 1 Vision Dr | 80 |  |  |  | 2021-12-02 | FEDEX P |  | 11/24 - AOI |  | KIT CLEAR 11/22 | 4 | Cognex | Natick | MA | 01760-2083 | attn receiving department | 198814415
|  | 2021-12-02 | 106260 (11/17) | 11734 S Election Rd | 210 |  |  |  | 2021-12-02 | FEDEX S | LONG ECO | 11/19 - AOI |  | KIT CLEAR 11/17 | 1 | Snap One | Draper | UT | 84020-6877 |  | 303456104
|  | 2021-12-02 | 106524 (11/23) | 75 Castilian Dr | 650 |  |  |  | 2021-12-02 | FEDEX P | SEE EMAIL FOR ITEM #3 | 11/24 - BACK |  | KIT CLEAR 11/23 | 0 | Transphorm USA | Goleta | CA | 93117-3090
|  | 2021-12-02 | 101761 (11/11) | 6030 W Harold Gatty Dr | 150 |  |  |  | 2021-12-02 | UPS GND |  | 11/24 - AOI |  | KIT CLEAR 11/22 | 81 | BIOSONIX | Salt Lake City | UT | 84116-3928 |  | 8V5459
|  | 2021-12-01 | 106598 (11/19) | 7 Loveton Cir | 8 |  |  |  | ??? | FEDEX P | HOLD PER CUST 11/30 | 11/23 - AOI |  | KIT CLEAR 11/19 | 1 | BD Life Sciences | Sparks | MD | 21152-9212 | Attn: Kevin Wenger | 225836043
|  | 2021-12-01 | 106384 (11/22) | 9538 E Old Vail Rd | 6 |  |  |  | 2021-12-02 | FEDEX P |  | 11/24 - AOI |  | KIT CLEAR 11/22 | 3 | TuSimple, Inc. | Tucson | AZ | 85747-9330
|  | 2021-12-01 | 106343 (11/15) | 18103 Ne 68th St Ste C100 | 50 |  |  |  | 2021-12-01 | FEDEX P |  | 11/19 - AOI |  | KIT CLEAR 11/15 | 0 | Basis Software | Redmond | WA | 98052-8593 | Basic Software, Inc. Attn:Alex Sherstuk | 174975302
|  | 2021-12-01 | 106689 (11/22) | 5475 Airport Blvd | 104 |  |  |  | 2021-12-01 | UPS RED | PAID REWORK | 11/22 - BACK |  | KIT CLEAR 11/22 | 8 | Particle Measuring Systems | Boulder | CO | 80301-2339 |  | 810528
|  | 2021-11-30 | 105088 (10/1) | 4501 Hatfield St | 150 |  |  |  | 2021-10-15 | UPS GND |  | 10/8 - AOI |  | KIT CLEAR 10/1 | 0 | Carnegie Robotics | Pittsburgh | PA | 15201-3023 |  | V3725X
|  | 2021-11-30 | 105187 (9/28) | 315 Commerce Park Rd Unit 3 | 12 |  |  |  | ??? | FEDEX P | *SHIPPING HOLD BY CUST | 10/1 - AOI |  |  | 74 | Applied Radar, Inc. | North Kingstown | RI | 02852-8422
|  | 2021-11-30 | 106534 (11/22) | 16706 13th Ave W | 6 |  |  |  | 2021-12-02 | UPS BLU |  | 11/24 - AOI |  | KIT CLEAR 11/22 | 8 | Crane Aerospace | Lynnwood | WA | 98037-8503 |  | 890614
|  | 2021-11-30 | 106341 (11/15) | 218 Myles Drive | 10 |  |  |  | 2021-12-01 | FEDEX P |  | 11/16 - BACK |  | KIT CLEAR 11/15 | 47 | Siemens Industry, Inc | New Kensington | PA | 15068-7046
|  | 2021-11-30 | 106093 (11/18) | 601 Atlantis Rd | 25 |  |  |  | 2021-11-30 | FEDEX P |  | 11/23 - AOI |  | KIT CLEAR 11/18 | 1 | Anderson Connectivity | Melbourne | FL | 32904-2316
|  | 2021-11-30 | 100607 (9/29) | 110 Sw Park Ter | 85 |  |  |  | 2021-12-07 | FEDEX P |  | 10/13 - AOI |  | *RECV U1 11/29 | 5 | Oregon State University | Corvallis | OR | 97331-8676
|  | 2021-11-29 | 106663 (11/23) | 1170 Howell Mill Rd Nw Ste 210 | 50 |  |  |  | 2021-11-30 | FEDEX P | *2 DAY TURN* | 11/24 - BACK |  | KIT CLEAR 11/23 | 0 | Flock Safety | Atlanta | GA | 30318-8637
|  | 2021-11-29 | 105090 (11/9) | 91 Sandy Ridge Road | 3 |  |  |  | 2021-11-30 | FEDEX P |  | 11/12 - AOI |  | KIT CLEAR 11/9 | 11 | DWB Design Inc. | Fredericksburg | VA | 22405
|  | 2021-11-29 | 106662(11/22) | 1170 Howell Mill Rd Nw Ste 210 | 50 |  |  |  | 2021-11-29 | FEDEX P | *2 DAY TURN* | 11/23 - BACK |  | KIT CLEAR 11/23 | 2 | Flock Safety | Atlanta | GA | 30318-8637
|  | 2021-11-29 | 105917 (11/18) | 10525 Willows Rd Ne | 50 |  |  |  | 2021-11-29 | FEDEX P | * 3 DAY TURN * | 11/23 - BACK |  | *SHORT ITEMS 11 & 22 | 0 | Facebook Technologies LLC | Redmond | WA | 98052-2545
|  | 2021-11-29 | 99731 (11/11) | 6030 W Harold Gatty Dr | 275 |  |  |  | 2021-11-29 | UPS RED |  | 11/16 - AOI |  | KIT CLEAR 11/11 | 0 | Biosonix | Salt Lake City | UT | 84116-3928 |  | 59TT20
|  | 2021-11-29 | 104794 (11/12) | 6035 Stoneridge Dr | 10 |  |  |  | 11/23, ??? | FEDEX P | WTG FOR J14 (RECV W/P) | 11/18 - AOI |  | KIT CLEAR 11/15, 11/17 | 42 | St Jude Medical | Pleasanton | CA | 94588 | St. Jude Medical, Inc. Thoratec | 94123097
|  | 2021-11-23 | 105951 (11/4) | 6030 W Harold Gatty Dr | 70 |  |  |  | 11/22 11/24 | UPS RED | CORRECT U1 RECV 11/22 | 11/10 - AOI |  | KIT CLEAR - 11/8 | 0 | Biosonix | Salt Lake City | UT | 84116-3928 |  | 59TT20
|  | 2021-11-23 | 93544 | 2500 ALMEDA AVE | XXX |  |  |  | 2021-11-24 | FEDEX GND | RMA |  |  |  |  | WR SYSTEMS, LTD | NORFOLK | VA | 23513- 2403 | SUITE 104 - DELIVERY ENTRANCE IN REAR
|  | 2021-11-23 | 106219 (11/15) | 7051 Industrial Blvd | 5FA/25 |  |  |  | 2021-11-23 | UPS RED |  | 11/18 - AOI |  | KIT CLEAR 11/16 | 14 | ABB Inc. | Bartlesville | OK | 74006-6036 | ABB Inc Bartles Totalflow ATTN: Brian Smith | 160E6W
|  | 2021-11-23 | 106087 (11/9) | 1180 John St | 250 |  |  |  | 2021-11-23 | UPS RED | SMT TRIM J1 - PAID REWORK | 11/12 - AOI |  | KIT CLEAR 11/9 | 3 | IDEX Health and Science | West Henrietta | NY | 14586-9757 |  | 112043
|  | 2021-11-22 | 104974 (10/26) | 510 Lansdowne Rd | 200 |  |  |  | 2021-11-23 | FEDEX GND |  | 11/5 - AOI |  | KIT CLEAR 10/26 | 0 | HDT Robotics | Fredericksburg | VA | 22408-7302
|  | 2021-11-22 | 106440 (11/12) | 10175 Philipp Pkwy | 10 |  |  |  | 2021-11-22 | UPS GND | *3 DAY TURN* | 11/18 - BACK |  | KIT CLEAR 11/17 | 68 | Automated Packaging Systems Inc. | Streetsboro | OH | 44241-4706 |  | 19E046
|  | 2021-11-19 | 104737 (11/9) | 438 Shotwell St | 5 |  |  |  | ??? | UPS GND | TOP SHORT 4 ITEMS (SKIP) | 11/12 - AOI |  | *11/9 BOT SIDE CLEAR | 81 | Capella Space | San Francisco | CA | 94110-1914 |  | 8V5459
|  | 2021-11-19 | 106233 (11/15) | 601 Atlantis Rd | 25 |  |  |  | 2021-11-22 | FEDEX P |  | 11/18 - BACK |  | KIT CLEAR 11/15 | 0 | Anderson Connectivity | Melbourne | FL | 32904-2316
|  | 2021-11-19 | 105947 (11/12) | 3500 Scarlet Oak Blvd | 4 |  |  |  | 2021-11-22 | FEDEX P |  | 11/16 - AOI |  | KIT CLEAR 11/15 | 93 | Bausch & Lomb | Saint Louis | MO | 63122-6604
|  | 2021-11-18 | 105575 (11/15) | 10060 Brecksville Rd | 20 |  |  |  | 2021-11-22 | FEDEX P |  | 11/16 - AOI |  | KIT CLEAR 11/15 | 5 | USA Firmware LLC. | Brecksville | OH | 44141-3293 | USA Firmware Paul Scaccia Embedeed Systems Engineer | 816592459281
|  | 2021-11-18 | 105914 (11/10) | 818 W Diamond Ave 3rd Floor | 75 |  |  |  | 2021-11-22 | FEDEX GND | *HOT* PLEASE EXPEDITE EARLY | 11/12 - AOI |  | KIT CLEAR 11/10 | 45 | GL Communications | Gaithersburg | MD | 20878-1417
|  | 2021-11-18 | 105915 (11/4) | 818 W Diamond Ave 3rd Floor | 75 |  |  |  | 2021-11-22 | FEDEX GND |  | 11/9 - AOI |  | KIT CLEAR - 11/8 | 18 | GL Communications | Gaithersburg | MD | 20878-1417
|  | 2021-11-16 | 105291 (11/3) | 15720 Main St Suite 100 | 15 |  |  |  | 2021-11-17 | FEDEX GND |  | 11/4 - AOI |  | KIT CLEAR 11/3 | 41 | Huntron, Inc. | Mill Creek | WA | 98012-1555
|  | 2021-11-16 | 104894 (10/29) | 5660 Airport Blvd Ste 101 | 53/95 |  |  |  | 2021-11-19 | UPS GND | SMT CLEAR ONLY *SHIP PARTIAL 11/19 | 11/3 - AOI |  | * SHORT J3 42 PCS SHIP PARTIAL 11/19 | 7 | Churchill Navigation dba Shotover Systems Inc | Boulder | CO | 80301-2596 |  | R8A959
|  | 2021-11-15 | 104586 (9/28) | 3260 Industry Dr Ste 5 | 58 |  |  |  | 2021-11-15 | FEDEX P | PARTIAL SHIPMENT | 11/12 - AOI |  | KIT CLEAR 10/1 | 2 | Ace Electronics, Inc. | North Charleston | SC | 29418-8478
|  | 2021-11-15 | 106057 (10/25) | 22 Bedford St Unit 4 | 190 |  |  |  | 2021-11-15 | FEDEX P | 2ND ARTICLE RELEASED | 11/4 - BACK |  | KIT CLEAR 11/1 | 3 | Open Source Instruments, Inc. | Waltham | MA | 02453-3501 | Attn: Kevan Hashemi
|  | 2021-11-15 | 103558 (11/9) | 2015 Chestnut St | 85 |  |  |  | 2021-12-03 | #VALUE! | PARTIAL QTY 85 (SHIP EARLY) | 11/10 - AOI |  | KIT CLEAR 11/9 FOR QTY 85 PARTIAL | 1 | Emcore | Alhambra | CA | 91803-1542 | Attn: Receiving Dept - PO # ALH0025151 | 496548183
|  | 2021-11-15 | 105807 (11/9) | 6030 W Harold Gatty Dr | 58 |  |  |  | 2021-11-16 | FEDEX P | BAL QTY 58 *EXPEDITE* | 11/12 - BOT SIDE 11/12 - TOP SIDE |  | BAL QTY 58 CLEAR 11/12 | 0 | Biosonix | Salt Lake City | UT | 84116-3928
|  | 2021-11-12 | 106208 (11/5) | 9845 Willows Rd Ne | 40 |  |  |  | 2021-11-16 | FEDEX 2 DAY |  | 11/9 - AOI |  | *SHORT U5 - OK TO SKIP | 45 | Facebook Technologies LLC | Redmond | WA | 98052-2540
|  | 2021-11-12 | 105652 (11/4) | 601 Atlantis Rd | 50 |  |  |  | ??? | UPS BLU | *NEED 25 PCS IN 2 DAYS* | 11/4 - BACK |  | 11/4 - SHORT T/H ONLY | 1 | Anderson Connectivity | Melbourne | FL | 32904-2316 |  | 2E6E38
|  | 2021-11-12 | 104419 (10/26) | 535 Indigo Dr | 450 |  |  |  | 2021-11-15 | FEDEX P | 2ND ARTICLE RELEASED | 11/1 - AOI |  | KIT CLEAR 10/27 | 1 | BarMinder, Inc. | Roswell | GA | 30075-2859
|  | 2021-11-11 | 105234 (11/5) | 9775 Ford Rd | 10 |  |  |  | 2021-11-15 | FEDEX P |  | 11/9 - BACK |  | *SHORT U48 - OK TO SKIP | 18 | Stryker Medical | Delton | MI | 49046-9444
|  | 2021-11-11 | 105807 (11/9) | 6030 W Harold Gatty Dr | 85/143 |  |  |  | 2021-11-11 | FEDEX P | RUN PARTIAL QTY 85 *PAID EXPEDITE* | 11/10 - AOI |  | QTY 85 CLEAR 11/9 | 0 | Biosonix | Salt Lake City | UT | 84116-3928
|  | 2021-11-11 | 106084 (11/9) | 100 Research Dr | 12 |  |  |  | 2021-11-11 | FEDEX P | * 2 DAY TURN * | 11/10 - AOI |  | KIT CLEAR 11/9 | 1 | Ascent AeroSystems | Wilmington | MA | 01887-4441
|  | 2021-11-10 | 106107 | 4975 E 41st Ave | 64 |  |  | NO CHARGE REWORK | 2021-11-11 | FEDEX GND |  | 11/1 - AOI |  | KIT CLEAR 10/29 | 18 | Mount Sopris Instruments | Denver | CO | 80216-4424 |  | 148324417
|  | 2021-11-10 | 106413 | 9567 Arrow Rte Ste E | 2 |  |  | PAID REWORK | 2021-11-10 | UPS RED |  | 11/3 - AOI |  | KIT CLEAR 11/3 | 8 | Finna Sensors | Rancho Cucamonga | CA | 91730-4550 |  | 519AW1
|  | 2021-11-10 | 105822 (10/29) | 4975 E 41st Ave | 35 |  |  |  | 2021-11-11 | FEDEX GND |  | 11/1 - AOI |  | KIT CLEAR 10/29 | 18 | Mount Sopris Instruments | Denver | CO | 80216-4424 |  | 148324417
|  | 2021-11-10 | 106111 (11/2) | 9567 Arrow Rte Ste E | 102 |  |  |  | 2021-11-10 | UPS RED |  | 11/3 - AOI |  | KIT CLEAR 11/3 | 8 | Finna Sensors | Rancho Cucamonga | CA | 91730-4550 |  | 519AW1
|  | 2021-11-10 | 106241 (11/3) | 5475 Airport Blvd | 10 |  |  |  | 2021-11-10 | UPS RED | REWORK ONLY |  |  | 11/3 RECV BOARDS KIT CLEAR 11/3 | 1 | Particle Measuring Systems | Boulder | CO | 80301-2339 |  | 810528
|  | 2021-11-09 | 105937 (10/19) | 153 Washington St 4th Floor | 25 |  |  |  | 2021-11-09 | UPS RED | * 3 DAY TURN * | 11/9 - AOI |  | *CLEAR 10/19, 10/20, 11/4 | 0 | Human Systems Integration, Inc. | East Walpole, | MA | 2032 | Attn: Phillip Johns | X407W3
|  | 2021-11-09 | 106112 (11/2) | 567 Arrow Rte Ste E | 103 |  |  |  | 2021-11-09 | UPS RED |  | 11/3 - AOI |  | KIT CLEAR 11/3 | 18 | Finna Sensors | Rancho Cucamonga | CA | 91730-4550 |  | 519AW1
|  | 2021-11-08 | 105928 (11/1) | 10175 Philipp Pkwy | 250 |  |  |  | 2021-11-15 | UPS RED |  | 11/3 - AOI |  | KIT CLEAR 11/1 | 6 | Automated Packaging Systems Inc. | Streetsboro | OH | 44241-4706 |  | 19E046
|  | 2021-11-08 | 105669 (10/25) | 2021 Industrial Dr | 10 |  |  |  | 2021-11-10 | UPS Blue | *EXPEDITE* SHIP 11/8 | 11/4 - AOI |  | KIT CLEAR 11/3 | 9 | Tamarack Aerospace Group | Sandpoint | ID | 83864-5248 |  | 37E210
|  | 2021-11-08 | 105905 (10/27) | 45150 Business Ct Suite 440 | 22 |  |  |  | 2021-11-10 | FEDEX P |  | 11/1 - AOI |  | KIT CLEAR 10/29 | 12 | CACI | Sterling | VA | 20166-6750 | Attn: Jennifer Miller BB#17359
|  | 2021-11-08 | 105716 (11/1) | 812 Avis Dr | 50 |  |  |  | 2021-11-08 | FEDEX GND |  | 11/3 - AOI |  | KIT CLEAR 11/1 | 1 | H3D, Inc. | Ann Arbor | MI | 48108-9649 | Attn: Michael Streicher
|  | 2021-11-05 | 105244 (11/3) | 2300 Windy Ridge Pkwy | 24 |  |  |  | 2021-11-10 | FEDEX P |  | 11/3 - AOI |  | KIT CLEAR 11/3 | 3 | Scientific Research Corporation | Atlanta | GA | 30339-5665 | Justin Vuong/Robert McDonald/ Bill Blackwell Ste 400 S | 153669597
|  | 2021-11-05 | 105264 (10/29) | 160 Schoolhouse Rd | 50 |  |  |  | 2021-11-05 | FEDEX P |  | 11/2 - AOI |  | KIT CLEAR 10/29 | 0 | Amplifier Research Corp. | Souderton | PA | 18964-2412 |  | 18105292
|  | 2021-11-05 | 105552 (10/25) | 601 Atlantis Rd | 10 |  |  |  | 2021-11-05 | UPS GND |  | 10/28 - AOI |  | KIT CLEAR 10/22 | 0 | Anderson Connectivity | Melbourne | FL | 32904-2316 |  | 2E6E38
|  | 2021-11-05 | 103877 (10/27) | 9319 Robert D Snyder Rd. STE 340E | 6 |  |  |  | 2021-11-05 | FEDEX P | 2ND ARTICLE RELEASED | RTR |  | KIT CLEAR 10/27 QTY REDUCED TO 6 | 4 | BluEyeQ LLC | Charlotte | NC | 28223-0001
|  | 2021-11-05 | 105111 (10/25) | 4840 63rd St | 350 |  |  |  | 2021-11-05 | FEDEX P | *MIXED POP* | 10/28 - BACK |  | KIT CLEAR 10/22 | 0 | Rocky Mountain Circuits | Boulder | CO | 80301
|  | 2021-11-04 | 105655 (10/25) | 601 Atlantis Rd | 25 |  |  |  | 2021-11-05 | UPS GND |  | 10/28 - AOI |  | KIT CLEAR 10/22 | 0 | Anderson Connectivity | Melbourne | FL | 32904-2316 |  | 2E6E38
|  | 2021-11-04 | 104432 (10/27) | 1015 Chestnut St Ste 801 | 22 |  |  |  | 2021-11-10 | UPS GND |  | 10/28 - AOI |  | KIT CLEAR 10/27 SHIPPED 59 + 44 | 0 | Biomeme, Inc. | Philadelphia | PA | 19107-4331 | Attn: PO 10000641 | 49V91V
|  | 2021-11-04 | 103558 (10/27) | 2015 Chestnut St | 34 |  |  |  | 2021-11-05 | #VALUE! | PARTIAL QTY | 10/27 - AOI |  | KIT CLEAR FOR QTY 34 10/19 PARTIAL | 1 | Emcore | Alhambra | CA | 91803-1542 | Attn: Receiving Dept - PO # ALH0025151 | 496548183
|  | 2021-11-04 | 106107 (11/1) | 12455 Research Blvd | 70 |  |  |  | 2021-11-04 | FEDEX P | * 3 DAY TURN * | 11/2 - AOI |  | KIT CLEAR 11/1 | 1 | Flextronics America, LLC | Austin | TX | 78759-2314 | FGS Austin 45T - Attn: Just Pack | 861230104
|  | 2021-11-04 | 105795 (11/1) | 11294 Sunrise Park Dr | 20 |  |  |  | 2021-11-04 | FEDEX P | * 3 DAY TURN * | 11/2 - AOI |  | KIT CLEAR 11/1 | 15 | Polarity, Inc. | Rancho Cordova | CA | 95742-6599
|  | 2021-11-03 | 105080 (10/13) | 2051 Palomar Airport Rd Ste 110 | 147 |  |  |  | 2021-11-03 | UPS RED | 2ND ARTICLE RELEASED | 10/28 - AOI |  | KIT CLEAR 10/27 | 3 | IDEX Health and Science | Carlsbad | CA | 92011-1461 |  | 112043
|  | 2021-11-03 | 105208 (10/25) | 3090 Center Green Dr | 200 |  |  |  | 2021-11-03 | FEDEX GND |  | 10/26 - AOI |  | KIT CLEAR 10/21 | 4 | UCAR | Boulder | CO | 80301-2252 | Attn: Clayton Arendt | 354289814
|  | 2021-11-03 | 105016 (10/27) | 10525 Willows Rd Ne | 132 |  |  |  | 2021-11-03 | FEDEX P | 10/29 BOT DONE NEED BAKE | 10/29 - QA / TOUCH UP / BAKE |  | KIT CLEAR 10/27 | 1 | Facebook Technologies LLC | Redmond | WA | 98052-2545 | ATTN: Alejandra Albarran
|  | 2021-11-02 | 105535 (10/25) | 7051 Industrial Blvd | 13 |  |  |  | 2021-11-02 | UPS RED |  | 10/27 - AOI |  | *SHORT FAB - DUE 10/26 | 28 | ABB Inc. | Bartlesville | OK | 74006-6036 | ABB Inc Bartles Totalflow | 160E6W
|  | 2021-11-02 | 104515 (10/12) | 818 W Diamond Ave | 31 |  |  |  | 2021-11-02 | FEDEX GND |  | 10/25 - AOI |  | KIT CLEAR 10/12 | 37 | GL Communications | Gaithersburg | MD | 20878-1417 | 3rd Floor
|  | 2021-11-02 | 105653 (10/14) | 601 Atlantis Rd | 25 |  |  |  | 2021-11-02 | FEDEX P |  | 10/25 - AOI |  | KIT CLEAR 10/19 | 0 | Anderson Connectivity | Melbourne | FL | 32904-2316
|  | 2021-11-02 | 105883 (10/19) | 2 Professional Dr Suite 224 | 60 |  |  |  | 2021-11-02 | UPS GND |  |  |  | KIT CLEAR 10/19 | 2 | LKC Technologies | Gaithersburg | MD | 20879-3408 |  | 283561
|  | 2021-11-02 | 105079 (10/18) | 6250 Joyce Dr. | 7 |  |  |  | 2021-11-02 | FEDEX P |  | 10/26 - AOI |  | KIT CLEAR 10/20 | 2 | Industrialex Manufacturing | Arvada | CO | 80403
|  | 2021-11-01 | 104923 (10/11) | 47650 Westinghouse Dr | 47 |  |  |  | 2021-11-01 | UPS BLUE |  | 10/14 - BACK |  | KIT CLEAR 10/18 | 67 | Alta Manufacturing | Fremont | CA | 94539
|  | 2021-11-01 | 105618 (10/27) | 250 Moonachie Rd Ste. 400 | 6FA/20 |  |  |  | 2021-11-01 | FEDEX P | * 3 DAY TURN * | 10/29 - BACK |  | KIT CLEAR 10/27 | 9 | Sterling Medical Devices | Moonachie | NJ | 07074-1378
|  | 2021-10-28 | 104952 (10/11) | 3 Henry Dr | 9 |  |  |  | ??? | FEDEX P | * 1 DAY TURN * FAB ISSUE 10/27 *HOLD* | RTR |  | *SHORT FABS - DUE 10/19, 10/22 RECV 10/27 | 0 | HII Unmanned Systems, Inc | Pocasset | MA | 02559-1415 | attn: VITO/ DUSTY | 253053240
|  | 2021-10-28 | 106057 (10/25) | 22 Bedford St Unit 4 | 10FA/200 |  |  |  | 2021-10-29 | FEDEX P | * 3 DAY TURN * RECV U2 10/28 | 10/26 - AOI |  | KIT CLEAR 10/26 *CUST SENDING U2 | 3 | Open Source Instruments, Inc. | Waltham | MA | 02453-3501 | Attn: Kevan Hashemi
|  | 2021-10-28 | 105477 (10/5) | 18103 Ne 68th St Ste C100 | 50 |  |  |  | ??? | FEDEX P | XRAY REQUIRED | 10/7 - TOP SIDE |  | *SEND XRAY TO DATEST (NXT DOOR) | 0 | Basis Software | Redmond | WA | 98052-8593 | Basic Software, Inc. Attn:Alex Sherstuk | 174975302
|  | 2021-10-28 | 105584 (10/12) | 832 E Utah Valley Dr | 30 |  |  |  | 2021-10-29 | FEDEX P |  | 10/25 - AOI |  | KIT CLEAR 10/25 | 19 | Perkinelmer - UT | American Fork | UT | 84003 | Attn: Christian Mills | 447648865
|  | 2021-10-28 | 104957 (9/23) | 14230 Lochridge Blvd Ste D | 50 |  |  |  | 2021-10-29 | FEDEX P | BAKE & DRY REFLOW | 10/25 - AOI |  | KIT CLEAR 10/18 | 62 | Agrify Corporation | Covington | GA | 30014-4953 |  | 623744175
|  | 2021-10-28 | 100606 (10/15) | 3190 Monitor Ave Rm 0220 | 7FA |  |  |  | 2021-10-29 | #VALUE! |  | 10/25 - AOI |  | KIT CLEAR 10/15 | 8 | University of Oklahoma | Norman | OK | 73019-5004 | Attn: Redmond Kelley | 749026308
|  | 2021-10-28 | 105145 (10/15) | 16848 Jefferson Hwy | 300 |  |  |  | 2021-10-29 | FEDEX P |  | 10/20 - AOI |  | KIT CLEAR 10/15 | 3 | Moates.Net | Baton Rouge | LA | 70817-6907 | attn: Craig Moates
|  | 2021-10-27 | 105404 (10/18) | 303 S Technology Ct | 1 |  |  |  | 2021-10-26 | FEDEX P |  | 10/20 - AOI |  | KIT CLEAR 10/19 | 12 | Honeywell International Inc | Broomfield | CO | 80021-3489 | Attn Corey Barnes | 2022-3188-8
|  | 2021-10-27 | 105241 (10/25) | 8500 Otto Rd Bldg E4301 | 50 |  |  |  | 2021-10-28 | FEDEX P | *PAID EXPEDITE* | 10/26 - AOI |  | *U1&Q1 BTD *SHORT 6PCS U12 | 22 | US Army RDECOM | Gunpowder | MD | 21010-9999 | General Delivery
|  | 2021-10-27 | 104420 (10/8) | 535 Indigo Dr | 450 |  |  |  | 2021-10-28 | FEDEX P |  | 10/12 - BACK |  | KIT CLEAR 10/7 | 4 | Barminder | Roswell | GA | 30075-2859
|  | 2021-10-27 | 105376 (10/14) | 1177 Quarry Ln | 15 |  |  |  | 2021-10-28 | FEDEX GND | T/H ONLY | 10/14 - BACK |  | KIT CLEAR 10/14 | 158 | Hitachi Particle Engineering and Services, Inc | Pleasanton | CA | 94566-4787 |  | F7632R
|  | 2021-10-26 | 105554 (10/15) | 601 Atlantis Rd | 10 |  |  |  | 2021-10-29 | UPS GND |  | 10/26 - BACK |  | KIT CLEAR 10/15 | 0 | Anderson Connectivity | Melbourne | FL | 32904-2316 |  | 2E6E38
|  | 2021-10-26 | 105555 (10/15) | 601 Atlantis Rd | 10 |  |  |  | 2021-10-29 | FEDEX P |  | 10/26 - BACK |  | KIT CLEAR 10/15 | 0 | erson Connectivity | Melbourne | FL | 32904-2316 |  | 2E6E38
|  | 2021-10-26 | 105738 (10/15) | 1026 Hamilton Dr | 150 |  |  |  | 2021-10-29 | UPS GND |  | 10/18 - AOI |  | KIT CLEAR 10/15 | 3 | Hamilton Mfg. Corp | Holland | OH | 43528-8210 | Hamilton Manufactoring Corp | 473071
|  | 2021-10-26 | 105388 (10/20) | 7 Loveton Cir | 30 |  |  |  | 2021-10-27 | FEDEX P |  | 10/25 - AOI |  | KIT CLEAR 10/20 | 11 | Becton, Dickinson and Company | Sparks | MD | 21152-9212 | attn ; Sandy W Clark | 148834733
|  | 2021-10-26 | 103335 (10/13) | 103 Quality Cir Nw Ste 220 | 400 |  |  |  | 2021-10-27 | #VALUE! |  | 10/19 - AOI |  | KIT CLEAR 10/13 | 0 | Scientific Research Corporation | Huntsville | AL | 35806-4537 | Attn: Graehm Sack | 153669597
|  | 2021-10-24 | 105404 (10/18) | 303 S Technology Ct | 19 |  |  |  | 2021-10-26 | FEDEX P |  | 10/20 - AOI |  | KIT CLEAR 10/19 | 12 | Honeywell International Inc | Broomfield | CO | 80021-3489 | Attn Corey Barnes | 2022-3188-8
|  | 2021-10-24 | 105661 (10/19) | 4616 W Howard Ln Ste 150 | 13 |  |  |  | 10/22 10/26 | UPS RED | * 3 DAY TURN * 10/26 CUST DNI | 10/20 - AOI |  | KIT CLEAR 10/19 *SHORT J5 & J2 | 21 | Flex Radio Systems | Austin | TX | 78728-6300 |  | Y226R4
|  | 2021-10-24 | 103255 (10/8) | 3901 Liberty St | 15 |  |  |  | 2021-10-28 | FEDEX P |  | 10/18 - AOI |  | KIT CLEAR 10/8 FAB ISSUE OK 10/14 | 130 | First Alert | Aurora | IL | 60504-8122
|  | 2021-10-25 | 105648 (10/20) | 12455 Research Blvd | 25 |  |  |  | 2021-10-25 | FEDEX P | *EXPEDITE* | 10/25 - BACK |  | KIT CLEAR 10/20 | 6 | Royal Circuits | Austin | TX | 78759-2314 | FGS Austin 45T | 861230104
|  | 2021-10-25 | 105799 (10/13) | 550 Tressler Dr | 4 |  |  |  | 2021-10-25 | FEDEX P |  | 10/19 - AOI |  | KIT CLEAR 10/18 | 42 | Lake Shore Cryotronics, Inc. | Westerville | OH | 43082-7587 | Attn: Receiving Dock | 679588281
|  | 2021-10-25 | 104372 (9/29) | 6250 Joyce Dr, | 140 |  |  |  | 2021-10-25 | FEDEX P |  | 10/18 - AOI |  | KIT CLEAR 10/12 | 1 | Industrialex Manufacturing | Arvada | CO | 80403
|  | 2021-10-22 | 105283(10/15) | 115 Castilian Dr | 270 |  |  |  | 2021-10-22 | FEDEX 2 DAY | *CUST PICK UP 10/22 | 10/19 - AOI |  | KIT CLEAR 10/15 | 0 | Transphorm USA | Goleta | CA | 93117
|  | 2021-10-22 | 105593 (10/19) | 5355 W 76th st | 120 |  |  |  | 2021-10-22 | FEDEX P | * 3 DAY TURN * REWORK | 10/19 - BACK |  | KIT CLEAR 10/19 | 7 | Beckman Coulter | Indianapolis | IN | 46268-4166 | Bldg 87, Dock 39
|  | 2021-10-22 | 105787 (10/15) | 1 Executive Dr Suite 101 | 1 |  |  |  | ASAP | FEDEX P | * 3 DAY TURN * | 10/18 - AOI |  | KIT CLEAR 10/15 | 19 | Spectro Inc. | Chelmsford | MA | 01824-2563 |  | 100055635
|  | 2021-10-22 | 104615 (10/14) | 2674 Piedmont Dr | 39 |  |  |  | 2021-10-22 | #VALUE! | 2ND ARTICLE RELEASED | 10/15 - AOI |  | KIT CLEAR 10/14 | 11 | Nanotok LLC | Merced | CA | 95340-9364
|  | 2021-10-22 | 104618 (10/13) | 2674 Piedmont Dr. | 39 |  |  |  | 2021-10-22 | #VALUE! | *CUST PICK UP 10/22 | 10/19 - AOI |  | KIT CLEAR 10/15 | 12 | Nanotok LLC | Merced | CA | 95340
|  | 2021-10-21 | 103012 | 6250 Joyce Dr, | 50 |  |  |  | 2021-10-25 | FEDEX P |  | 10/18 - AOI |  | KIT CLEAR 10/12 | 1 | Industrialex Manufacturing | Arvada | CO | 80403
|  | 2021-10-21 | 104266 (10/12) | 10224 Knoll Cir | 5 |  |  |  | 2021-10-21 | FEDEX P |  | 10/15 - AOI |  | KIT CLEAR 10/15 | 26 | Embedded Power Labs, LLC | Highlands Ranch, | CO | 80130
|  | 2021-10-21 | 105546 (10/14) | 2 Technology Pl | 200 |  |  |  | 2021-10-21 | FEDEX GND |  | 10/15 - AOI |  | KIT CLEAR 10/14 | 2 | Inificon Inc. | East Syracuse | NY | 13057-9707 |  | 0132-0019-0
|  | 2021-10-21 | 104925 (9/30) | 50 Dartmouth Dr | 23 |  |  |  | 2021-10-21 | FEDEX GND |  | 10/6 - AOI |  | KIT CLEAR 9/30 | 31 | Analog Devices, Inc. | Auburn | NH | 03032-3981
|  | 2021-10-20 | 105332 (10/11) | 601 Atlantis Rd | 25 |  |  |  | 10/25* | FEDEX P |  | 10/14 - BACK |  | *SHORT CONN - DUE 10/12 | 3 | Anderson Connectivity | Melbourne | FL | 32904-2316
|  | 2021-10-20 | 105331 (10/11) | 601 Atlantis Rd | 25 |  |  |  | 10/25* | FEDEX P |  | 10/14 - BACK |  | *SHORT CONN - DUE 10/12 | 2 | Anderson Connectivity | Melbourne | FL | 32904-2316
|  | 2021-10-20 | 105787 (10/15) | 1 Executive Dr Suite 101 | 19 |  |  |  | 2021-10-20 | FEDEX P | * 3 DAY TURN * | 10/18 - AOI |  | KIT CLEAR 10/15 | 19 | Spectro Inc. | Chelmsford | MA | 01824-2563 |  | 100055635
|  | 2021-10-20 | 105641 (10/13) | 10008 N Harris Farm Rd | 10 |  |  |  | 2021-10-20 | FEDEX P |  | 10/14 - AOI |  | KIT CLEAR 10/13 | 53 | Hoisington Design Group | Spotsylvania | VA | 22553-1975
|  | 2021-10-20 | 105377 (10/6) | 1177 Quarry Ln | 15 |  |  |  | 2021-10-20 | FEDEX GND | T/H ONLY |  |  | KIT CLEAR 10/6 | 154 | Hitachi Particle Engineering and Services, Inc | Pleasanton | CA | 94566-4787 |  | F7632R
|  | 2021-10-19 | 105242 (10/7) | 13020 Middletown Industrial Blvd | 200 |  |  |  | 2021-10-27 | FEDEX GND |  | 10/13 - AOI |  | KIT CLEAR 10/6 | 2 | Justice AV Solutions | Louisville | KY | 40223-4761
|  | 2021-10-19 | 100616 (10/8) | 3190 Monitor Ave Rm 0220 | 4FA /210 |  |  |  | 2021-10-20 | FEDEX P | QTY 4 FA | 10/12 - BACK |  | KIT CLEAR 10/6 | 0 | University of Oklahoma | Norman | OK | 73019-5004 | Attn: Kurt Konyalioglu
|  | 2021-10-19 | 105375 (9/30) | 1177 Quarry Ln | 15 |  |  |  | 2021-10-20 | UPS GND | T/H ONLY |  |  | KIT CLEAR 10/6 | 121 | Hitachi Particle Engineering and Services, Inc | Pleasanton | CA | 94566-4787 |  | F7632R
|  | 2021-10-19 | 105374 (10/6) | 1177 Quarry Ln | 5 |  |  |  | 2021-10-20 | FEDEX GND | T/H ONLY |  |  | KIT CLEAR 10/6 | 90 | Hitachi Particle Engineering and Services, Inc | Pleasanton | CA | 94566-4787 |  | F7632R
|  | 2021-10-18 | 105769 (10/13) | 35 Hartwell Ave | 12 |  |  |  | 2021-10-19 | UPS Blue | * 3 DAY TURN * | 10/15 - BACK |  | KIT CLEAR 10/14 | 27 | CamX Power LLC | Lexington | MA | 02421-3102 |  | 5R1268
|  | 2021-10-18 | 105373 (9/30) | 1177 Quarry Ln | 20 |  |  |  | 2021-10-18 | UPS RED | T/H ONLY |  |  | KIT CLEAR 10/4 | 151 | achi Particle Engineering and Services, Inc | Pleasanton | CA | 94566-4787 |  | F7632R
|  | 2021-10-15 | 105599 (10/8) | 2335 Broadway Ste 100 | 20 |  |  |  | 2021-10-15 | FEDEX P |  | 10/12 - AOI |  | KIT CLEAR 10/8 | 1 | Credence ID, LLC. | Oakland | CA | 94612-2495 | Att: Kai Aiello
|  | 2021-10-15 | 102813 (10/8) | 6250 Joyce Drive | 25 |  |  |  | 2021-10-15 | FEDEX P |  | 10/12 - AOI |  | KIT CLEAR 10/8 | 21 | Industrialex Manufacturing | Arvada | CO | 80403
|  | 2021-10-15 | 100610 (10/7) | 3190 Monitor Ave Rm 0220 | 4FA |  |  |  | 2021-10-15 | #VALUE! |  | 10/12 - AOI |  | KIT CLEAR 10/4 | 8 | University of Oklahoma | Norman | OK | 73019-5004 | ATTN: Redmond Kelley | 749026308
|  | 2021-10-15 | 105088 (10/1) | 4501 Hatfield St | 150 |  |  |  | 2021-10-15 | UPS GND |  | 10/8 - AOI |  | KIT CLEAR 10/1 | 0 | Carnegie Robotics | Pittsburgh | PA | 15201-3023 |  | V3725X
|  | 2021-10-14 | 104931 (10/1) | 586 Fulling Mill Rd | 10/22 |  |  |  | 2021-10-14 | FEDEX P | QTY 10 FA | 10/11 - AOI |  | KIT CLEAR 10/7 | 14 | Phoenix Contact, Inc. | Middletown | PA | 17057-2966 | Attn: Receiving-350 | 958605234
|  | 2021-10-14 | 104586 (9/28) | 3260 Industry Dr Ste 5 | 58 /173 |  |  |  | 2021-10-15 | FEDEX P | * SHIP QTY 58 ONLY | 10/11 - BACK |  | KIT CLEAR 10/1 | 2 | Ace Electronics, Inc. | North Charleston | SC | 29418-8478
|  | 2021-10-14 | 104859 (9/30) | 452 W 1260 N | 50 |  |  |  | 2021-10-14 | FEDEX GND |  | 10/11 - AOI |  | KIT CLEAR 9/30 | 7 | Moxtek | Orem | UT | 84057-2941
|  | 2021-10-14 | 104573 (10/4) | 3190 Monitor Ave Rm 0220 | 2FA /4FA /16 |  |  |  | 2021-10-14 | FEDEX P | QTY 2 FA | 10/8 - AOI |  | KIT CLEAR 9/30 | 5 | University of Oklahoma | Norman | OK | 73019-5004 | Attn: Kurt Konyalioglu
|  | 2021-10-13 | 104957 (9/23) | 14230 Lochridge Blvd Ste D | 50 |  |  |  | ??? | FEDEX P | *SHIPPED QTY 50 10/4 | 9/24 - BACK |  | CLEAR 9/23 | 62 | Agrify Corporation | Covington | GA | 30014-4953 |  | 623744175
|  | 2021-10-13 | 104302 (10/7) | 1025 W 1700 N | 10 /240 |  |  |  | 2021-10-14 | UPS GND | QTY 10 FA | 10/11 - AOI |  | KIT CLEAR 10/7 FA 10 | 1 | Automation Products | Logan | UT | 84321-1713 |  | X92925
|  | 2021-10-13 | 105662 (10/8) | 4616 W Howard Ln Ste 150 | 13 |  |  |  | 2021-10-13 | UPS RED | *3 DAY TURN* | 10/11 - AOI |  | KIT CLEAR 10/8 | 16 | Flex Radio Systems | Austin | TX | 78728-6300 |  | Y226R4
|  | 2021-10-13 | 105062 (10/1) | 150 Congress St. | 10 |  |  |  | 2021-10-13 | FEDEX P |  | 10/11 - AOI |  | KIT CLEAR 10/6 | 20 | Markem Imaje | Keene | NH | 3431
|  | 2021-10-12 | 105178 (10/5) | 2137 N Main St | 64 |  |  |  | 2021-10-12 | FEDEX 2 DAY |  | 10/8 - AOI |  | KIT CLEAR 10/5 | 6 | Scientific Data Systems, LLC | Las Cruces | NM | 88001-1128 |  | 2392-5794-
|  | 2021-10-12 | 105434 (10/6) | 2 Technology Pl | 30 |  |  |  | 2021-10-13 | FEDEX P |  | 10/8 - AOI |  | KIT CLEAR 10/6 | 16 | Inificon Inc. | East Syracuse | NY | 13057-9707 |  | 0132-0019-0
|  | 2021-10-12 | 105816 (10/11) | 405 Bay Dr | 150 |  |  |  | 2021-10-14 | FEDEX P | * 3 DAY TURN * | 10/12 - TOP SIDE |  | KIT CLEAR 10/11 | 0 | Blueline Sensors LLC | Stevensville | MD | 21666-3447
|  | 2021-10-12 | 105496 (10/6) | 7000 East Ave | 5 |  |  |  | 2021-10-13 | FEDEX P |  | 10/8 - AOI |  | KIT CLEAR 10/6 | 50 | Optimum Design Associates | Livermore | CA | 94550-9698 |  | 779588491
|  | 2021-10-11 | 104907 (9/27) | 601 Atlantis Rd | 25 |  |  |  | 2021-10-12 | FEDEX P |  | 9/30 - AOI |  | KIT CLEAR 9/28 | 1 | Anderson Connectivity | Melbourne | FL | 32904-2316
|  | 2021-10-11 | 104922 (9/30) | 812 Avis Dr | 50 |  |  |  | 2021-10-11 | FEDEX P |  | 10/6 - AOI |  | KIT CLEAR 10/4 | 13 | H3D, Inc. | Ann Arbor | MI | 48108-9649 | Attn: Michael Streicher
|  | 2021-10-11 | 104957 (9/23) | 14230 Lochridge Blvd Ste D | 50 |  |  |  | 2021-10-07 | FEDEX P | *SHIPPED QTY 50 10/4 | 9/24 - BACK |  | CLEAR 9/23 | 62 | Agrify Corporation | Covington | GA | 30014-4953 |  | 623744175
|  | 2021-10-11 | 100605 (9/21) | 3190 Monitor Ave Rm 0220 | 8FA/16FA/800 |  |  |  | 2021-10-12 | FEDEX P | 9/22 RAN QTY 4 9/29 RAN QTY BOT SIDE | 9/24 - WTG FOR FABS. 9/28 ONLY RECV 3 FABS |  | KIT CLEAR 10/1 | 4 | University of Oklahoma | Norman | OK | 73019-5004 | Attn: Redmond Kelley | 749026308
|  | 2021-10-08 | 105318 (9/24) | 1941 Stryker Way | 42/60 |  |  |  | 2021-10-07 | FEDEX P | REWORK HARVEST | 9/24 - BACK |  | CLEAR 9/23 | 248 | Stryker Instruments | Portage | MI | 49002-9711 | Attn: Bryan Burkhart
|  | 2021-10-08 | 105042 (9/24) | 1941 Stryker Way | 10 |  |  |  | 2021-10-07 | FEDEX P | REWORK HARVEST | 9/24 - BACK |  | CLEAR 9/23 | 180 | Stryker Instruments | Portage | MI | 49002-9711 | Attn: Bryan Burkhart
|  | 2021-10-08 | 100481 (9/15) | 430 10th St Nw | 4 |  |  |  | ??? | FEDEX 2D |  | 9/17 - BACK |  | *SHORT U712 / OK TO SKIP | 58 | GTRI-Ga Tech | Atlanta | GA | 30318-5701 | Attn: John Paul Halliwell Room: GTRI HQ - 450 - Non Academic Offic Department: GTRI Research Bui
|  | 2021-10-08 | 104521 (9/28) | 2940 Perrowville Rd | 180 |  |  |  | 2021-10-19 | UPS BLU |  | 10/1 - AOI |  |  | 2 | Innerspec Technologies, Inc | Forest | VA | 24551-2225 |  | 55FE18
|  | 2021-10-08 | 104957 (9/23) | 14230 Lochridge Blvd Ste D | 100 |  |  |  | 2021-10-07 | FEDEX P | *SHIPPED QTY 50 10/4 | 9/24 - BACK |  | CLEAR 9/23 | 62 | Agrify Corporation | Covington | GA | 30014-4953 |  | 623744175
|  | 2021-10-07 | 105319 (9/24) | 1941 Stryker Way | 35 |  |  |  | 2021-10-07 | FEDEX P | REWORK HARVEST | 9/24 - BACK |  | CLEAR 9/23 | 35 | Stryker Instruments | Portage | MI | 49002-9711 | Attn: Bryan Burkhart
|  | 2021-10-07 | 104957 (9/23) | 14230 Lochridge Blvd Ste D | 50 |  |  |  | 2021-10-07 | FEDEX P | *SHIPPED QTY 50 10/4 | 9/24 - BACK |  | CLEAR 9/23 | 62 | Agrify Corporation | Covington | GA | 30014-4953 |  | 623744175
|  | 2021-10-07 | 103180 (9/15) | 245 E Gay St | 19 |  |  |  | 2021-10-13 | FEDEX GND | 2ND ARTICLE | 9/30 - BACK |  | *RELEASED 9/29 | 27 | Analytic Designs | Columbus | OH | 43215-3210
|  | 2021-10-07 | 104372 (9/29) | 6250 Joyce Dr, | 20/250 |  |  |  | 2021-10-06 | FEDEX P | *** HOT *** EXPEDITE | 10/4 - AOI |  | *3RD ARTICLE * QTY 5 SHIPPED 10/4 | 1 | Industrialex Manufacturing | Arvada | CO | 80403
|  | 2021-10-06 | 104722 (9/23) | 6381 Chittenden Rd Ste E7 | 200 |  |  |  | 2021-10-15 | UPS GND | *NEED ZIP CODE | 9/28 - BACK |  | KIT CLEAR 9/24 | 2 | ALD Systems | Hudson | OH | 44236-2032 |  | Y35429
|  | 2021-10-06 | 104372 (9/29) | 6250 Joyce Dr, | 35/250 |  |  |  | 2021-10-05 | FEDEX P | *** HOT *** EXPEDITE | 10/4 - AOI |  | *3RD ARTICLE * QTY 5 SHIPPED 10/4 | 1 | Industrialex Manufacturing | Arvada | CO | 80403
|  | 2021-10-05 | 105270 (9/28) | 41743 Enterprise Cir N 105-B | 25 |  |  |  | 2021-10-13 | FEDEX GND |  | 9/29 - AOI |  | *BTD K1 - KIT CLEAR 9/29 | 18 | Agate Technology | Temecula | CA | 92590-5645
|  | 2021-10-05 | 104419 (10/1) | 535 Indigo Dr | 20FA /450 |  |  |  | 2021-10-05 | FEDEX P | ***2 DAY TURN*** | 10/5 - TOP SIDE |  | KIT CLEAR 10/1 10/4 RECV ARRAY FILE | 1 | BarMinder, Inc. | Roswell | GA | 30075-2859
|  | 2021-10-05 | 105303 (9/27) | 10525 Willows Rd Ne | 200 |  |  |  | 2021-10-06 | FEDEX P | ***3 DAY TURN*** | 10/4 - BACK |  | KIT CLEAR 10/1 | 0 | Facebook Technologies LLC | Redmond | WA | 98052-2545 | ATTN: Pirie, Gabe
|  | 2021-10-04 | 104957 (9/23) | 14230 Lochridge Blvd Ste D | 50 |  |  |  | 2021-10-07 | FEDEX P | HOLD - DELAM | 9/23 - TOP SIDE |  | CLEAR 9/23 | 62 | Agrify Corporation | Covington | GA | 30014-4953 |  | 623744175
|  | 2021-10-04 | 104372 (9/29) | 6250 Joyce Dr, | 5/250 |  |  |  | 2021-10-05 | FEDEX P | *** HOT *** EXPEDITE | 10/4 - AOI |  | *3RD ARTICLE * QTY 5 SHIPPED 10/4 | 1 | Industrialex Manufacturing | Arvada | CO | 80403
|  | 2021-10-04 | 105250 (9/24) | 915 Murphy Ranch Rd | 62 |  |  |  | ??? | FEDEX P | ***3 DAY TURN*** | 9/27 - BACK |  | *SHORT CONN | 2 | Renesas Electronics America, Inc. | Milpitas | CA | 95035-7912 | Attn: Brad Rex | 463500240
|  | 2021-10-01 | 105029 (9/30) | 9845 Willows Rd Ne | 15 |  |  |  | 2021-10-05 | FEDEX 2 DAY | *** 3 DAY TURN *** | 9/30 - AOI |  | KIT CLEAR 9/30 | 36 | Facebook Technologies LLC | Redmond | WA | 98052-2540
|  | 2021-10-01 | 104522 (9/23) | N50w28321 Maes Walke | 11 |  |  |  | 2021-10-08 | #VALUE! |  | 9/30 - AOI |  | CLEAR 9/22 | 36 | T&M Automation | Pewaukee | WI | 53072-1738 |  | 68587572
|  | 2021-10-01 | 104575 (9/27) | 3190 Monitor Ave Rm 0220 | 4FA/20 |  |  |  | ??? | FEDEX P |  | 9/28 - AOI |  | *SHORT Y2 | 1 | University of Oklahoma | Norman | OK | 73019-5004 | Attn: Kurt Konyalioglu | 749026308
|  | 2021-09-30 | 104574 (9/24) | 3190 Monitor Ave Rm 0220 | 2FA/10 |  |  |  | 2021-10-05 | FEDEX P |  | 9/28 - BACK |  | CLEAR 9/24 | 32 | University of Oklahoma | Norman | OK | 73019-5004 | Attn: Kurt Konyalioglu | 749026308
|  | 2021-09-30 | 103695 (9/14) | 26051 Merit Cir Ste 102 | 1000 |  |  |  | 2021-10-05 | #VALUE! |  | 9/16 - BACK |  |  | 0 | Adagio Medical, Inc. | Laguna Hills, | CA | 92653-7008 |  | 780546697
|  | 2021-09-30 | 105201 (9/24) | 145 Graham Ave. | 30 |  |  |  | 2021-10-08 | FEDEX GND |  | 9/28 - AOI |  | CLEAR 9/22 | 17 | Signal Solutions, LLC | Lexington | KY | 40506-0001
|  | 2021-09-29 | 104576 (9/23) | 3190 Monitor Ave Rm 0220 | 2FA/16 |  |  |  | 2021-10-05 | FEDEX P |  | 9/27 - AOI |  |  | 12 | University of Oklahoma | Norman | OK | 73019-5004 | Attn: Kurt Konyalioglu | 749026308
|  | 2021-09-29 | 105250 (9/24) | 915 Murphy Ranch Rd | 63 |  |  |  | 2021-09-29 | FEDEX P | ***3 DAY TURN*** | 9/27 - BACK |  | CLEAR 9/24 | 2 | Renesas Electronics America, Inc. | Milpitas | CA | 95035-7912 | Attn: Brad Rex | 463500240
|  | 2021-09-29 | 104221 (9/27) | 9535 Waples St Ste 100 | 50 |  |  |  | 2021-10-05 | FEDEX P |  | 9/28 - AOI |  | KIT CLEAR 9/28 | 4 | Codex DNA | San Diego, | CA | 92121-2993
|  | 2021-09-29 | 103895 (9/21) | 95 Billerica Ave | 35 |  |  |  | 9/29* | UPS GND |  | 9/28 - BACK |  | *U901 WRONG PART - DUE 9/29 | 10 | Aved Electronics, LLC | North Billerica, | MA | 01862-1231 |  | 664287
|  | 2021-09-28 | 104308 (9/22) | 13131 W Little York Rd | 50 |  |  |  | 2021-09-29 | FEDEX P |  | 9/24 - AOI |  | CLEAR 9/22 | 19 | Toshiba International Corp. | Houston | TX | 77041-5807 | PEP PLT Dock C28 attn: Kathleen Stanley
|  | 2021-09-27 | 104930 (9/16) | 1015 Chestnut St Ste 801 | 120 |  |  |  | 2021-09-30 | UPS RED |  | 9/22 - AOI |  |  | 7 | Biomeme, Inc. | Philadelphia | PA | 19107-4331 |  | 49V91V
|  | 2021-09-27 | 105253 (9/21) | 11 Mark Ter | 10 |  |  |  | 2021-09-27 | FEDEX P | ***3 DAY TURN*** | 9/23 - AOI |  | *CLEAR/FAB RECV 9/22 | 62 | Latch Systems, Inc. | Randolph | MA | 02368-4817
|  | 2021-09-24 | 105170 | 11100 Endeavor Ct Suite 300 | 35 |  |  |  | 2021-09-24 | FEDEX P | BAL 35 | 9/22 - AOI |  | *DNI U27 | 0 | NAL Research Corporation | Manassas | VA | 20109-4027 |  | 636328553
|  | 2021-09-24 | 105020 |  | 84 |  |  |  | ??? |  | BAL QTY 84 | *RWK BOARDS |  | *SHIPPED QTY 58 9/10
|  | 2021-09-23 | 105039 | 1211 Flynn Rd Unit 104 | 4000 |  |  |  | 2021-09-23 | #VALUE! |  | 9/16 - BACK |  |  | 0 | Signum Systems | Camarillo | CA | 93012
|  | 2021-09-23 | 104605 (9/16) | 220 E Ludington Dr | 25 |  |  |  | 2021-09-23 | UPS GND |  | 9/17 - AOI |  |  | 20 | The Swain Meter Company | Farwell | MI | 48622 |  | 322FV0
|  | 2021-09-23 | 104475 (9/16) | 586 Fulling Mill Rd | 16 |  |  |  | 2021-09-23 | FEDEX P |  | 9/21 - AOI |  |  | 7 | Phoenix Contact, Inc. | Middletown | PA | 17057-2966 | Attn: Receiving-350 | 958605234
|  | 2021-09-23 | 105170 | 11100 Endeavor Ct Suite 300 | 5/40 |  |  |  | 2021-09-23 | FEDEX P | ***3 DAY TURN*** | 9/22 - BACK - QTY 5 SHIP ONLY |  | *PARTIAL SHORT U27/CAN RUN 5 BOARDS ONLY | 0 | NAL Research Corporation | Manassas | VA | 20109-4027 |  | 636328553
|  | 2021-09-23 | 104121 (8/17) | 741 Radio Dr | 20 |  |  |  | 2021-09-29 | FEDEX P |  | 9/10 - BACK |  | *LAST SHORTS RECV 9/22 | 34 | Denmar Technical Services | Lewis Center | OH | 43035-7134 | Denmar Technical Services, Inc.
|  | 2021-09-22 | 103628 | 6250 Joyce Drive | 8 |  |  |  | 8/20* | #VALUE! |  | 8/17 - BACK |  | *SHORT BAT - T/H | 5 | Industrialex Manufacturing | Arvada | CO | 80403
|  | 2021-09-22 | 102224 | 6250 Joyce Drive | 160 |  |  |  | 8/20* | #VALUE! |  | 8/17 - BACK |  | *SHORT BAT - T/H | 5 | Industrialex Manufacturing | Arvada | CO | 80403
|  | 2021-09-22 | 104615 | 2674 Piedmont Dr | 3FA /42 |  |  |  | 2021-09-20 | #VALUE! |  | 9/15 - AOI |  |  | 11 | Nanotok LLC | Merced | CA | 95340-9364
|  | 2021-09-22 | 104618 (6/16) | 2674 Piedmont Dr. | 39 |  |  |  | 2021-09-23 | #VALUE! |  | 9/17 - AOI |  | *SHORT FEW PCS T/H ONLY | 12 | Nanotok LLC | Merced | CA | 95340
|  | 2021-09-22 | 105117 (9/20) | 550 Tressler Dr | 3 |  |  |  | 2021-09-22 | FEDEX P | ***3 DAY TURN*** | 9/21 - AOI |  |  | 20 | Lake Shore Cryotronics, Inc. | Westerville | OH | 43082-7587 | Receiving Dock | 67958828
|  | 2021-09-22 | 104919 (9/16) | 303 S Technology Ct | 3 |  |  |  | 2021-09-25 | FEDEX P | QTY CHANGED FROM 6 TO 3 | 9/21 - BACK |  | *SHORT PARTS / DUE 9/17 | 101 | Honeywell International, Inc. | Broomfield | CO | 80021-3489 | Attn: Jeremy Parks | 202231888
|  | 2021-09-21 | 104372 (9/20) | 6250 Joyce Dr, | 2/250 |  |  |  | 2021-09-21 | FEDEX P | ***2 DAY TURN*** | 9/20 - AOI |  | *2ND ARTICLE | 1 | Industrialex Manufacturing | Arvada | CO | 80403
|  | 2021-09-21 | 102530 (9/16) | 430 10th St Nw | 10 |  |  |  | 2021-09-22 | FEDEX SUP SVR |  | 9/20 - AOI |  |  | 9 | GTRI-Ga Tech | Atlanta | GA | 30318-5701 | Attn: John Paul Halliwell Room: GTRI HQ - 450 - Non Academic Offic Department: GTRI Research Bui
|  | 2021-09-21 | 104766 (9/15) | 100 Four Points Way | 2 |  |  |  | 2021-09-22 | FEDEX S |  | 9/17 - AOI |  |  | 9 | SynTech Systems - Fuelmaster | Tallahassee | FL | 32305-7091 | Attn: Brian Piertrodangelo
|  | 2021-09-20 | 104432 (9/2) | 1015 Chestnut St Ste 801 | 103/125 |  |  |  | 9/20* | UPS GND | *RAN QTY 59 PARTIAL | 9/9 - BACK |  | *SHORT FAB QTY 66/ DUE 9/16 | 0 | Biomeme, Inc. | Philadelphia | PA | 19107-4331 | Attn: PO 10000641 | 49V91V
|  | 2021-09-20 | 99596 | 16848 Jefferson Hwy | 283 |  |  |  | ??? | FEDEX P | QTY 500 SHIP 8/24 | 8/13 - HOLD IN SHIPPING |  | *NEED TO SOLDER TO B99600 QTY 500 | 0 | Moates.Net | Baton Rouge | LA | 70817-6907 | Attn: Craig Moates
|  | 2021-09-20 | 99600 (8/10) | 16848 Jefferson Hwy | 283 |  |  |  | ??? | #VALUE! | QTY FA SHIP 8/24 | BACK |  | *MARK BOARDS W/ ALT PART T491D157K016AT | 1 | Moates.Net | Baton Rouge | LA | 70817-6907
|  | 2021-09-17 | 103180 (9/15) | 245 E Gay St | 1/20 |  |  |  | 2021-09-23 | FEDEX GND |  | RTR |  | *SHORT 1 ITEM / DUE 9/16 | 27 | Analytic Designs | Columbus | OH | 43215-3210
|  | 2021-09-17 | 100617 (9/14) | 3190 Monitor Ave Rm 0220 | 8FA/202 |  |  |  | 2021-09-21 | #VALUE! |  | 9/15 - AOI |  |  | 3 | University of Oklahoma | Norman | OK | 73019-5004 | Attn: Redmond Kelley | 749026308
|  | 2021-09-17 | 104968 | 1180 John St | 200 |  |  |  | 9/20* | FEDEX P |  | 9/14 - BACK |  | *QTY 120 PARTIAL/ SHORT BAL FABS | 2 | IDEX Health and Science | West Henrietta, | NY | 14586-9757
|  | 2021-09-17 | 100613 (9/14) | 3190 Monitor Ave Rm 0220 | 4FA/50 |  |  |  | 2021-09-21 | #VALUE! |  | 9/16 - BACK |  |  | 4 | University of Oklahoma | Norman | OK | 73019-5004 | Attn: Redmond Kelley | 749026308
|  | 2021-09-16 | 99596 | 16848 Jefferson Hwy | 200 |  |  |  | ??? | FEDEX P | QTY 500 SHIP 8/24 | 8/13 - HOLD IN SHIPPING |  | *NEED TO SOLDER TO B99600 QTY 500 | 0 | Moates.Net | Baton Rouge | LA | 70817-6907 | Attn: Craig Moates
|  | 2021-09-16 | 99600 (8/10) | 16848 Jefferson Hwy | 200 |  |  |  | ??? | #VALUE! | QTY FA SHIP 8/24 | BACK |  | *MARK BOARDS W/ ALT PART T491D157K016AT | 1 | Moates.Net | Baton Rouge | LA | 70817-6907
|  | 2021-09-16 | 103363 | 2100 CENTRAL AVE | 354 |  |  |  | ??? | FEDEX P |  | 7/15 - BACK |  | * SHORT T/H - QTY 46 SHIPPED 7/16 | 5 | LONGPATH TECHNOLOGIES | BOULDER | CO | 80301-2838
|  | 2021-09-14 | 100619 (9/2) | 3190 Monitor Ave Rm 0220 | 800 |  |  |  | 2021-10-04 | #VALUE! |  | 9/9 - BACK |  |  | 0 | University of Oklahoma | Norman | OK | 73019-5004 | Attn: Redmond Kelley | 749026308
|  | 2021-09-15 | 104955 | 1152 Park Ave | 5 |  |  |  | 2021-09-15 | FEDEX P | * 3 DAY TURN * | 9/14 - AOI |  |  | 8 | Enovate Medical - Stinger Medical | Murfreesboro | TN | 37129-4912
|  | 2021-09-15 | 105112 | 10 Water St Ste 425 | 15 |  |  |  | 2021-09-15 | FEDEX S | * 1 DAY TURN * | 9/14 - AOI |  |  | 0 | SignalQuest, LLC | Lebanon | NH | 03766-4200 | Attn: Chelsea Hadlock
|  | 2021-09-15 | 104717 | 3333 Coyote Hill Rd | 3 |  |  |  | 2021-09-15 | FEDEX P | * 3 DAY TURN * | 9/14 - AOI |  | *HOT* *EXPEDITE* | 6 | Palo Alto Research Center Incorporated | Palo Alto, | CA | 94304-1314 | Attn: P316651
|  | 2021-09-15 | 104777 | 1 Albion Rd, Suite 100 | 25 |  |  |  | 9/15* | FEDEX P | * 3 DAY TURN * | 9/13 - AOI |  |  | 2 | Zebra Technologies Corp | Lincoln | RI | 2895 | Attn: Frank Calabresi
|  | 2021-09-15 | 105138 | 250 Moonachie Rd Ste 400 | 12 |  |  |  | 9/15* | FEDEX P | * 3 DAY TURN * | 9/10 - AOI |  | *SHORT R107 - OK TO SKIP | 37 | Sterling Medical Devices | Moonachie | NJ | 07074-1378
|  | 2021-09-13 | 103377 (9/2) | 9319 Robert D Snyder Rd. STE 340E | 60 |  |  |  | 2021-09-20 | FEDEX P | 2ND ARTICLE | 9/9 - BACK |  |  | 4 | BluEyeQ LLC | Charlotte | NC | 28223-0001
|  | 2021-09-13 | 104662 | 7610 S Alkire Pl Ste B | 10/100 |  |  |  | 2021-09-14 | FEDEX P | 1ST ARTICLE | 9/10 - BACK |  |  |  | Design Solutions Inc. | Littleton | CO | 80127-3223 | ATTN: JON ANDERSON
|  | 2021-09-10 | 104704 (8/31) | 309 N Pastoria Ave | 5 |  |  |  | 2021-09-10 | WILL CALL |  |  |  | *SHORT FABS/ DUE 9/3 | 8 | Daimler North America | Sunnyvale | CA | 94085-4109
|  | 2021-09-10 | 94215 |  | 19 |  |  |  | ??? |  | BAL QTY 84 | *RWK BOARDS |  | *SHIPPED QTY 58 9/10
|  | 2021-09-10 | 105020 |  | 58 |  |  |  | ??? |  | BAL QTY 84 | *RWK BOARDS |  | *SHIPPED QTY 58 9/10
|  | 2021-09-10 | 104781 (9/2) | 7011 E Ave | 10 |  |  |  | 2021-09-28 | #VALUE! |  | 9/9 - BACK |  | *SHORT FAB - DUE 9/3 | 56 | Sandia National Laboratories | Livermore | CA | 94550-9610 | Attn: Keith Penney - Mail Stop 9053
|  | 2021-09-08 | 99596 | 16848 Jefferson Hwy | 16 |  |  |  | 2021-09-01 | FEDEX P | QTY 500 SHIP 8/24 | 8/13 - HOLD IN SHIPPING |  | *NEED TO SOLDER TO B99600 QTY 500 | 0 | Moates.Net | Baton Rouge | LA | 70817-6907 | Attn: Craig Moates
|  | 2021-09-08 | 99600 (8/10) | 16848 Jefferson Hwy | 16 |  |  |  | 2021-08-23 | #VALUE! | QTY FA SHIP 8/24 | 8/16 - AOI |  | *MARK BOARDS W/ ALT PART T491D157K016AT | 1 | Moates.Net | Baton Rouge | LA | 70817-6907
|  | 2021-09-08 | 104648 (9/1) | 245 E Gay St | 300 |  |  |  | 2021-09-16 | #VALUE! | T/H ONLY |  |  |  | 4 | Analytic Designs | Columbus | OH | 43215-3210 |  | 18418889
|  | 2021-09-07 | 102356 (8/25) | 21 Hamilton Ct | 27 |  |  |  | ??? | FEDEX P | 2ND ARTICLE | 9/2 - AOI |  | *SHORT FABS/ DUE 8/31 | 1 | Royal Circuits Solutions | Hollister | CA | 95023-2535
|  | 2021-09-03 | 104504 (8/26) | 601 Atlantis Rd | 25 |  |  |  | 2021-12-23 | UPS GND |  | 8/31 - BACK |  | KIT CLEAR 12/9 | 0 | Anderson Connectivity | Melbourne | FL | 39204-2316
|  | 2021-09-03 | 104300 | 1330 Ensell Rd | 1500 |  |  |  | 2021-09-14 | FEDEX P |  | 8/25 - AOI |  |  | 3 | Hose Monster | Lake Zurich Rd | IL | 60047-1574
|  | 2021-09-03 | 104189 (8/30) | 2102 Miller Dr, STE A | 5 |  |  |  | 2021-09-08 | FEDEX P | *** 3 DAY TURN *** | 8/31 - AOI |  |  | 55 | Scythe Robotics | Longmont | CO | 80501
|  | 2021-09-03 | 104582 (8/30) | 803 W Broad St Ste 520 | 5 |  |  |  | 2021-09-07 | FEDEX P |  | 9/2 - AOI |  |  | 0 | Vesperix | Falls Church | VA | 22046-3130
|  | 2021-09-03 | 104254 (8/24) | 22924 E Appleway Ave | 10 |  |  |  | ??? | UPS GND | SHORT | 8/31 - BACK |  | *SHORT - MAY CLEAR 8/25 | 117 | Frencken America Inc. | Liberty Lake | WA | 99019-9514
|  | 2021-09-02 | 103435 (8/17) | 303 S Technology Ct | 1 |  |  |  | 2021-09-16 | #VALUE! | HOLD | 9/1 - BACK |  | *RECV 1 FAB W SCRATCH | 80 | Honeywell International Inc | Broomfield | CO | 80021-3489 | Attn Dylan Gorman Court bldg B | 202231888
|  | 2021-09-02 | 104703 (8/27) | 2906 33 St | 200 |  |  |  | 2021-09-03 | FEDEX INT P |  | 9/1 - BACK |  |  | 0 | VO2 | Vernon | BC | V1T 5S7 | Canada
|  | 2021-09-02 | 102493 | 2940 Perroville Rd | 5 |  |  |  | 2021-09-03 | UPS GND |  | 7/30 - BACK |  | *DNI SHORT PART - OK TO SHIP | 8 | Innerspec Technologies | Forrest | VA | 24551-2225 |  | 55FE18
|  | 2021-09-01 | 104371 (8/25) | 1015 Chestnut St Ste 801 | 55 |  |  |  | 2021-09-01 | UPS GND |  | 8/26 - AOI |  |  | 6 | Biomeme, Inc. | Philadelphia | PA | 19107-4331 | Attn: PO 10000641 | 49V91V
|  | 2021-09-01 | 104649 (8/30) | 3200 N Kings Hwy | 50 |  |  |  | 2021-09-14 | UPS GND |  | 8/31 - BACK |  |  | 23 | Graph-Tech USA, LLC | Fort Pierce | FL | 34951-4051 |  | 04Y70W
|  | 2021-08-31 | 103416 (8/26) | 2420 Park Central Blvd | 3 |  |  |  | 2021-09-07 | #VALUE! |  | 8/27 - AOI |  |  | 0 | JSL, Inc. | Decatur | GA | 30035-3901
|  | 2021-08-31 | 104272 (8/20) | 47281 Bayside Pkwy | 76 |  |  |  | 2021-09-07 | FEDEX 2D |  | 8/24 - AOI |  |  | 9 | Enphase Energy | Fremont | CA | 94538-6517 |  | 442722803
|  | 2021-08-31 | 104253 (8/24) | 23 Strathmore Rd | 200 |  |  |  | ??? | UPS RED | 2 LOTS 150 & 50 | 8/26 - AOI |  | *SHORT PARTIAL U5 (QTY 10) | 0 | Delsys Inc. | Natick | MA | 01760-2444 |  | 9Y6648
|  | 2021-08-30 | 101525 (8/11) | 22 Jordan Cove Rd | 68 |  |  |  | 2021-09-09 | UPS ORG |  | 8/17 - AOI |  |  | 0 | Coastal Designs, LLC | Waterford | CT | 06385-3227 |  | 238V3V
|  | 2021-08-30 | 104778 (8/26) | 1330 Ensell Rd | 50 |  |  |  | 2021-08-31 | FEDEX P | ***3 DAY TURN*** | 8/26 - AOI |  |  | 3 | Hose Monster | Lake Zurich | IL | 60047-1574
|  | 2021-08-30 | 104211 (8/23) | 1607 Grand Ave Unit 23 | 99 |  |  |  | 2021-08-31 | FEDEX P | 2ND ARTICLE | 8/25 - AOI |  | *SHIPPED 1 PC FA 8/18 | 9 | Engineering Design Group, LLC | Glenwood Springs | CO | 81601-3873
|  | 2021-08-30 | 102333 | 1350 JEFFERSON RD F DOCK | 30 |  |  |  | ??? | FEDEX GND |  | 7/30 - BACK |  | *WRONG CAP SIZE/ WTG FOR PART | 11 | L3 OPEN WATER POWER | ROCHESTER | NY | 14623-3106 |  | 220825477
|  | 2021-08-30 | 103489 (8/26) | 2326 Irwin St | 30 |  |  |  | 2021-08-30 | #VALUE! | *SHIP MON 8/20* | 8/27 - BACK |  | *QTY 10 SHIPPED 8/25 | 0 | Tomahawk Robotics, LLC | Melbourne | FL | 32901-7377 | Attn: 321-888-34-87 | 308992624
|  | 2021-08-30 | 104705 (8/24) | 710 Bridgeport Ave | 200 |  |  |  | 2021-09-01 | UPS GND | SEAL BAGS | 8/24 - BACK |  |  | 3 | PerkinElmer, Inc. | Shelton | CT | 06484-4750 |  | 8W1F33
|  | 2021-08-27 | 104341 (8/17) | 1380 Forest Park Cir Ste 202 | 70 |  |  |  | 2021-08-30 | FEDEX P |  | 8/23 - AOI |  |  | 9 | Cardinal Peak, LLC | Lafayette | CO | 80026-3377
|  | 2021-08-27 | 101523 (8/11) | 22 Jordan Cove Rd | 415 |  |  |  | 2021-09-02 | UPS ORG | SHIP 8/27 | 8/17 - AOI |  |  | 0 | Coastal Designs, LLC | Waterford | CT | 06385-3227 |  | 238V3V
|  | 2021-08-27 | 103819 (8/20) | 75 Castilian Dr | 300 |  |  |  | 2021-08-30 | FEDEX S |  | 8/23 - AOI |  | *SHORT 1 ITEM - DUE 8/23 | 0 | Transphorm USA | Goleta | CA | 93117-3090 | Attn: Jose Guerrero | 39166544
|  | 2021-08-26 | 103877 (8/23) | 9319 Robert D Snyder Rd. STE 340E | 2FA/15 |  |  |  | 8/26* | FEDEX P | *** 3 DAY TURN*** | 8/24 - AOI |  | *SHORT FAB/ DUE 8/23 | 4 | BluEyeQ LLC | Charlotte | NC | 28223-0001
|  | 2021-08-25 | 103489 | 2326 Irwin St | 10/40 |  |  |  | 2021-08-25 | #VALUE! | *SAME DAY TURN* | *FABS DUE 8/25 12:00 PM |  | *RUN QTY 10 ONLY | 0 | Tomahawk Robotics, LLC | Melbourne | FL | 32901-7377 | Attn: 321-888-34-87 | 308992624
|  | 2021-08-25 | 103435 (8/17) | 303 S Technology Ct | 3 |  |  |  | 2021-08-25 | #VALUE! | SHIP 8/25 | 8/19 - RUN QTY 3 THEN HOLD |  | *SHORT 1 FAB | 80 | Honeywell International Inc | Broomfield | CO | 80021-3489 | Attn Dylan Gorman Court bldg B | 202231888
|  | 2021-08-25 | 104444 (8/18) | 35 Hartwell Ave | 20 |  |  |  | 2021-08-26 | UPS BLU | SHIP 8/25 | 8/23 - AOI |  |  | 27 | CamX Power LLC | Lexington | MA | 02421-3102 |  | 5R1268
|  | 2021-08-25 | 103697 (8/19) | 221 Armstrong Blvd | 3 |  |  |  | 2021-09-02 | FEDEX P | SHIP 8/25 | 8/23 - AOI |  |  | 5 | Armstrong Hot Water, Inc | Three Rivers | MI | 49093-2374
|  | 2021-08-25 | 102940 (8/23) | 1101 Kitchawan Rd Rte 134 | 6 |  |  |  | 9/8* | UPS RED | SHIP 8/25 | 8/24 - AOI |  | *SHORT ITEM 39/ OK TO SKIP |  | Compro Business Services | Yorktown Heights | NY | 10598-0000 | Bruce Copeland V.A. | 9268V0
|  | 2021-08-25 | 104412 (8/24) | 5660 Airport Blvd Ste 101 | 75 |  |  |  | 2021-09-08 | UPS GND | SHIP 8/25 | 8/24 -BACK |  |  | 1 | Churchill Navigation dba Shotover Systems Inc | Boulder | CO | 80301-2596 |  | R8A959
|  | 2021-08-24 | 99600 (8/10) | 16848 Jefferson Hwy | 1 |  |  |  | 2021-08-23 | #VALUE! | QTY FA SHIP 8/24 | 8/16 - AOI |  | *MARK BOARDS W/ ALT PART T491D157K016AT | 1 | Moates.Net | Baton Rouge | LA | 70817-6907
|  | 2021-08-24 | 104372 (8/18) | 6250 Joyce Dr, | 2/250 |  |  |  | 2021-08-25 | FEDEX P | *** 3 DAY TURN*** | 8/23 - AOI |  | *SHORT 1 PART/ SKIP | 1 | Industrialex Manufacturing | Arvada | CO | 80403
|  | 2021-08-24 | 103946 | 3901 Castle Hayne Rd | 3 |  |  |  | 2021-09-01 | UPS GND |  | 8/18 - AOI |  |  | 50 | Diversified Supply | Castle Hayne | NC | 28429 |  | 206306
|  | 2021-08-24 | 103605 (8/17) | 5900 Heisley Rd | 11 |  |  |  | 2021-09-07 | FEDEX P | P200 CONN ISSUE | 8/18 - AOI |  | *SHORTAGE ARRIVED 8/24 | 31 | Steris | Mentor | OH | 44060-1834 | Attn: Vince Vlach | 209098334
|  | 2021-08-24 | 103012 (8/12) | 6250 Joyce Dr. | 249 |  |  |  | 2021-08-26 | #VALUE! | 2ND ARTICLE | 8/17 - BACK |  | *FAB ROUTING ISSUE - RTV 8/17 | 5 | Industrialex Manufacturing | Arvada | CO | 80403
|  | 2021-08-24 | 99596 | 16848 Jefferson Hwy | 500 |  |  | QTY 500 SHIPPED QTY 500 NEED ASSY TO B99600 | 2021-09-01 | FEDEX P | QTY 500 SHIP 8/24 | 8/13 - HOLD IN SHIPPING |  | *NEED TO SOLDER TO B99600 QTY 500 | 0 | Moates.Net | Baton Rouge | LA | 70817-6907 | Attn: Craig Moates
|  | 2021-08-23 | 102526 (8/5) | 6250 Joyce Dr. | 50 |  |  |  | 2021-08-23 | #VALUE! | SHIP 8/20 | 8/18 - AOI |  |  | 5 | Industrialex Manufacturing | Arvada | CO | 80403 |  | 308992624
|  | 2021-08-20 | 104100 (8/16) | 452 W 1260 N | 200 |  |  |  | 2021-09-07 | #VALUE! | SHIP 8/20 | 8/17 - BACK |  |  | 0 | Moxtek | Orem | UT | 84057-2941
|  | 2021-08-20 | 103881 | 47281 Bayside Pkwy | 30 |  |  |  | 2021-08-20 | FEDEX P | SHIP 8/20 | 8/18 - AOI |  | *NEED 8/19 5:00 PM SHIP FRI/NOT THURS | 9 | Royal Circuits | Fremont | CA | 94538-6517 | Enphase Energy-
|  | 2021-08-20 | APPLE |  | 140 |  |  |  | 2021-08-16 | W/C | SHIP 8/20 | 7/26 - BACK |  |  | 8 | APPLE
|  | 2021-08-19 | 103488 | 2326 Irwin St | 40 |  |  |  | 2021-08-19 | #VALUE! | SHIP 8/19 | 8/18 - BACK ***CLASS 3*** |  | *SHIP 8/19!!! | 0 | Tomahawk Robotics, LLC | Melbourne | FL | 32901-7377 | Attn: 321-888-34-87 | 308992624
|  | 2021-08-18 | 104211 (8/12) | 1607 Grand Ave Unit 23 | 1FA/100 |  |  |  | 2021-08-23 | FEDEX P | SHIP 8/18 | 8/18 - BACK |  |  | 9 | Engineering Design Group, LLC | Glenwood Springs | CO | 81601-3873
|  | 2021-08-18 | 103558 (8/16) | 2015 Chestnut St | 30/ 175 |  |  |  | 2021-08-20 | #VALUE! | SHIP 8/18 | 8/17 - AOI |  | *SHIP 30 SOONER IF POSSIBLE | 1 | Emcore | Alhambra | CA | 91803-1542 | Attn: Receiving Dept - PO # ALH0025151 | 496548183
|  | 2021-08-18 | 103742 (8/11) | 7051 Industrial Blvd | 2FA/ 15 |  |  |  | 2021-08-20 | FEDEX P | SHIP 8/18 | 8/16 - AOI |  |  | 28 | ABB Inc. | Bartlesville | OK | 74006-6036 | ABB Inc Bartles Totalflow ATTN: TONY MOORE | 242540859
|  | 2021-08-18 | 104337 (8/13) | 3510 Breakwater Ct | 20 |  |  |  | 2021-08-20 | FEDEX P | SHIP 8/18 | 8/13 - BACK |  |  | 30 | Motiv Power Systems | Hayward | CA | 94545-3611 |  | 631116663
|  | 2021-08-18 | 104378 (8/10) | 4291 W 96th St | 1/6 |  |  |  | 2021-08-19 | FEDEX P | SHIP 8/18 | 8/16 - AOI |  |  | 24 | PC Krause & Associates | Indianapolis | IN | 46268-1113
|  | 2021-08-18 | 103984 (8/10) | 7000 East Ave | 50 |  |  |  | 2021-08-30 | UPS GND | SHIP 8/18 | 8/17 - BACK |  | *SHORT 3 FABS - 8/10 RECV 47/50 FABS | 13 | Lawrence Livermore National Lab | Livermore | CA | 94550-9698 | LLNL FOR US DOE/NNSA Gen Rec Bldg 411 PO # B641295 | 956956
|  | 2021-08-17 | 104335 (8/12) | 3510 Breakwater Ct | 20 |  |  |  | 2021-08-19 | FEDEX P | SHIP 8/17 | 8/12 - BACK |  |  | 42 | Motiv Power Systems | Hayward | CA | 94545-3611 |  | 631116663
|  | 2021-08-17 | 103554 (8/9) | 170 Granada Dr Ste A | 5 |  |  |  | 2021-08-18 | #VALUE! | SHIP 8/17 | 8/13 - AOI |  |  | 4 | Rosen - San Luis Obispo | San Luis Obispo | CA | 93401-7360 |  | 292615612
|  | 2021-08-17 | 103780 (8/11) | 170 Granada Dr Ste A | 5 |  |  |  | 2021-08-17 | #VALUE! | SHIP 8/17 | 8/13 - AOI |  |  | 14 | Rosen - San Luis Obispo | San Luis Obispo | CA | 93401-7360 |  | 292615612
|  | 2021-08-16 | 104181 (8/9) | 586 Fulling Mill Rd | 30 |  |  |  | 2021-08-17 | FEDEX SS | SHIP 8/16 | 8/12 - AOI |  | *NO ATTRITION- DNI IF SHORT | 0 | Phoenix Contact, Inc. | Middletown | PA | 17057-2966 | ATTN: Receiving-350 | 958605234
|  | 2021-08-16 | 103983 | 7000 East Ave | 25 |  |  |  | 2021-08-16 | UPS GND | SHIP 8/16 |  |  |  | 21 | Lawrence Livermore National Lab | Livermore | CA | 94550-9698 | LLNL FOR US DOE/NNSA Gen Rec Building 411 PO Number B641295 | 956956
|  | 2021-08-16 | 103309 (7/30) | 5660 Airport Blvd Ste 101 | 50 |  |  |  | 2021-08-23 | UPS GND | SHIP 8/16 |  |  | *SHORT FAB DUE 8/2 | 1 | Churchill Navigation dba Shotover Systems Inc | Boulder | CO | 80301-2596 |  | R8A959
|  | 2021-08-16 | 104330 | 6250 Joyce Dr, | 15 |  |  |  | ??? | FEDEX P | SHIP 8/16 | 8/12 - BACK |  | *SHORT 1 ITEM - 1206 PART | 6 | Industrialex Manufacturing | Arvada | CO | 80403
|  | 2021-08-13 | 103754 (7/30) | 2007 Gandy Blvd N # 100 | 53 |  |  |  | 2021-08-13 | UPS RED | SHIP 8/13 | 8/10 - AOI |  |  | 0 | Jabil Inc. | Saint Petersburg | FL | 33702-2169 | ATTN: Bill Gregory | 6W7Y62
|  | 2021-08-13 | 103908 (7/30) | 10175 Philipp Pkwy | 200 |  |  |  | 2021-08-16 | UPS RED | SHIP 8/13 | 8/4 - AOI |  |  | 6 | Automated Packaging Systems, Inc. | Streetsboro | OH | 44241-4706 |  | 19E046
|  | 2021-08-13 | 104245 | 245 Industrial Park Rd | 3 |  |  |  | 2021-08-16 | FEDEX 2D | SHIP 8/13 | 8/10 - AOI |  | *SHORT ITEM 9 "U2" - SKIP | 75 | Duotech Services Inc | Franklin | NC | 28734-7920
|  | 2021-08-13 | 103760 (8/9) | 4501 Hatfield St | 200 |  |  |  | 8/13- 8/18 | UPS RED | SHIP 8/13 | 8/11 - AOI |  | *DO NOT REMOVE KAPTON TAPE U1 | 0 | Carnegie Robotics | Pittsburgh | PA | 15201-3023 |  | V3725X
|  | 2021-08-12 | 103557 (7/30) | 10300 Energy Dr | 10 |  |  |  | 2021-08-19 | #VALUE! | SHIP 8/12 | 8/6 - AOI |  |  | 3 | HP, Inc. | Spring | TX | 77389-1864 |  | 786982570
|  | 2021-08-12 | 103546 (7/26) | 7000 E Ave | 25 |  |  |  | 2021-08-17 | UPS GND | SHIP 8/12 |  |  |  | 21 | Lawrence Livermore National Lab | Livermore | CA | 94550-9698 | LLNL FOR US DOE/NNSA Gen Rec Bldg 411 PO # B641295 | 956956
|  | 2021-08-12 | 103822 (7/30) | 49 Willow Peak Dr PO Box 8100 Quantel USA | 4 |  |  |  | 2021-08-16 | FEDEX GND | SHIP 8/12 | 8/10 - BACK |  |  | 65 | Quantel USA | Bozeman | MT | 59718-9811 |  | 120183263
|  | 2021-08-11 | 103581 (8/4) | 1900 Mckinley Ave | 30 |  |  |  | 2021-08-11 | #VALUE! | SHIP 8/11 | 8/9 - BACK |  |  | 27 | Cummins Inc. | Columbus | IN | 47201-6414 | Attn Chris Dale Peveler | 308992624
|  | 2021-08-11 | 103962 (7/28) | 410 Sakett Point Rd | 60 |  |  |  | 2021-08-11 | UPS RED | SHIP 8/11 | 8/4 - AOI |  |  | 25 | Precision Combustion | North Haven | CT | 06473-3168
|  | 2021-08-11 | 103274 | 2305 Presidential Dr | 6 |  |  |  | 2021-08-18 | UPS RED | SHIP 8/11 | 7/30 - BACK |  | *SHORT U46 | 2 | Nuvotronics | Durham | NC | 27703-8039 |  | A9W605
|  | 2021-08-11 | 103690 (8/3) | 10175 Philipp Pkwy | 5 |  |  |  | ??? | UPS RED | SHIP 8/11 | 8/5 - AOI |  | *SHORT 4 ITEMS - OK TO SKIP | 57 | Automated Packaging Systems, Inc. | Streetsboro | OH | 44241-4706 |  | 19E046
|  | 2021-08-10 | 103365 (7/27) | 4975 E 41st Ave | 35 |  |  |  | ??? | #VALUE! | SHIP 8/10 | 7/30 - AOI |  | *SHORT PARTIAL ON 2 ITEMS | 18 | Mount Sopris Instruments | Denver | CO | 80216-4424 |  | 148324417
|  | 2021-08-10 | 104145 (8/4) | 253 E Rincon Ave | 50 |  |  |  | 2021-08-10 | FEDEX P | SHIP 8/10 | 8/9 - AOI |  | *DNI ANY SHORT ITEMS | 0 | Royal Circuits | Campbell | CA | 95008-2920 | ATTN: PERTER NYSEN | 122142710
|  | 2021-08-09 | 103441 | 5900 Heisley Rd | 20 |  |  |  | 2021-08-09 | #VALUE! | SHIP 8/9 | 8/3 - AOI |  |  | 28 | Steris | Mentor | OH | 44060-1834 | Attn: Vince Vlach | 209098334
|  | 2021-08-09 | 103728 (8/4) | 253 E Rincon Ave | 50 |  |  |  | 2021-08-10 | #VALUE! | SHIP 8/9 | 8/6 - AOI |  | *DNI ANY SHORT ITEMS | 0 | Loto Labs | Campbell | CA | 95008-2920 | Attn: Peter Nysen | 122142710
|  | 2021-08-09 | 103310 (7/30) | 5660 Airport Blvd Ste 101 | 75 |  |  |  | 2021-08-16 | UPS GND | SHIP 8/9 | 8/3 - AOI |  |  | 1 | Churchill Navigation dba Shotover Systems, Inc. | Boulder | CO | 80301-2596 |  | R8A959
|  | 2021-08-09 | 103338 (7/29) | 10175 Philipp Pkwy | 200 |  |  |  | 2021-08-13 | UPS RED | SHIP 8/9 | 7/30 - AOI |  |  | 12 | Automated Packaging Systems Inc. | Streetsboro | OH | 44241-4706 |  | 19E046
|  | 2021-08-09 | 103843 (8/3) | 11 Huron Drive Suite 202 | 525 |  |  |  | 2021-08-10 | #VALUE! | SHIP 8/9 | 8/4 - BACK |  |  | 0 | Aila Technologies, Inc. | Natick | MA | 01760
|  | 2021-08-06 | 103542 (7/26) | 7000 E Ave | 33 |  |  |  | 2021-08-17 | UPS GND | SHIP 8/6 | 7/30 - AOI |  |  | 13 | Lawrence Livermore National Lab | Livermore | CA | 94550-9698 | LLNL FOR US DOE/NNSA Gen Rec Bldg 411 PO # B641295 | 956956
|  | 2021-08-06 | 104116 (8/3) | 103 Quality Cir Nw Ste 220 | 400 |  |  |  | 2021-08-06 | FEDEX P | SHIP 8/6 | 8/3 - AOI |  |  | 0 | Scientific Research Corporation | Huntsville | AL | 35806-4537 |  | 153669597
|  | 2021-08-06 | 103542 (7/26) | 7000 E Ave | 17/50 |  |  |  | 2021-08-17 | UPS GND | SHIP 8/6 | 7/30 - BACK |  | *QTY 33 HAVE PLATING ISSSUE | 13 | Lawrence Livermore National Lab | Livermore | CA | 94550-9698 | LLNL FOR US DOE/NNSA Gen Rec Bldg 411 PO # B641295 | 956956
|  | 2021-08-05 | 103603 (7/23) | 4 Constitution Way | 150 |  |  |  | 2021-08-11 | UPS RED | SHIP 8/5 | 8/3 - BACK |  | SHORT ITEM 17/ OK TO SKIP/ 1 PER | 2 | Servomex Inc | Woburn | MA | 01801-8510 |  | 014478
|  | 2021-08-05 | 104156 (8/2) | 7000 E Ave | 4 |  |  |  | 2021-08-06 | UPS GND | SHIP 8/5 | 8/4 - AOI |  | *SHORT FAB AND 1 ITEM- DUE 8/2 | 26 | Lawrence Livermore National Lab | Livermore | CA | 94550-9698 | LLNL FOR US DOE/NNSA Gen Rec Bldg 411 PO # B641295 | 956956
|  | 2021-08-04 | 103909 (7/30) | 10175 Philipp Pkwy | 200 |  |  |  | 2021-08-13 | UPS RED | SHIP 8/4 | 7/30 - AOI |  |  | 0 | Automated Packaging Systems, Inc. | Streetsboro | OH | 44241-4706 |  | 19E046
|  | 2021-08-04 | 104185 | 110 Parkland PLaza | 20 |  |  |  | 2021-08-04 | UPS RED | SHIP 8/4 | NO DOC. |  |  |  | ThorLabs | Ann Arbor | MI | 48103 | ThorLabs- UFO | R4X430
|  | 2021-08-04 | 103512 (7/28) | 1015 Chestnut St Suite 1401 | 100 |  |  |  | 2021-08-04 | UPS RED | SHIP 8/4 | 7/30 - AOI |  |  | 6 | Biomeme, Inc. | Philadelphia | PA | 19107-4331 | PO10000571 | 49V91V
|  | 2021-08-04 | 102284 (7/21) | 6250 Joyce Drive | 1000 |  |  |  | 2021-08-04 | #VALUE! | SHIP 8/4 | 7/23 - BACK |  | *TRIM LEADS/ DO NOT LOSE ITEM 4 | 4 | Industrialex Manufacturing | Arvada | CO | 80403
|  | 2021-08-03 | 103559 (7/20) | 11100 Endeavor Ct Ste 300 | 100 |  |  |  | 2021-08-10 | #VALUE! | ROWC B100172 | 7/28 - AOI |  |  | 0 | NAL Research Corporation | Manassas | VA | 20109-4027 |  | 636328553
|  | 2021-08-03 | 102806 | 16848 JEFFFERSON HWY | 1000 |  |  |  | 2021-08-05 | FEDEX P |  | 7/20 - BACK |  |  | 1 | MOATES.NET | BATON ROUGE | LA | 70817-6907 | Attn: Craig Moates
|  | 2021-08-02 | 103755 | 1650 Robert J Conlan Blvd Ne | 100 |  |  |  | 2021-08-03 | #VALUE! | *3 DAY TURN | 7/30 - BACK |  |  | 5 | Renesas Electronics America, Inc. | Palm Bay | FL | 32905-3406
|  | 2021-08-02 | 103509 (7/27) | 1015 Chestnut St Ste 1401 | 100 |  |  |  | 2021-08-03 | UPS RED |  | 7/28 - AOI |  |  | 7 | Biomeme, Inc. | Philadelphia | PA | 19107-4331 | PO10000571 | 49V91V
|  | 2021-08-02 | 103726 (7/26) | 3003 E 37th St N Ste 100 | 150 |  |  |  | 2021-08-03 | #VALUE! |  | 7/27 - BACK |  |  | 3 | PetroPower LLC | Wichita | KS | 67219-3503
|  | 2021-07-30 | 103727 (7/23) | 11475 Lakefield Dr | 20 |  |  |  | 2021-08-04 | #VALUE! | SHIP 7/30 | 7/27 - AOI |  |  | 26 | Nordson Corporation | Duluth | GA | 30097-1511 | Attn Jeff Owen
|  | 2021-07-30 | 101909 (7/22) | 586 Fulling Mill Rd | 47 |  |  |  | 2021-07-30 | FEDEX GND | SHIP 7/30 | 7/27 - AOI |  | *7/23 PHOTOS SENT/ APPVD BY CUST 7/26 | 0 | Phoenix Contact | Middletown | PA | 17057-2966 | Attn: Receiving - 350 | 958605234
|  | 2021-07-29 | 102914 (7/23) | 6250 Joyce Dr. | 100 |  |  |  | 2021-07-30 | #VALUE! | SHIP 7/29 | 7/27 - BACK |  |  | 7 | Industrialex Manufacturing | Arvada | CO | 80403
|  | 2021-07-29 | 103418 | 22924 E Appleway Ave | 10 |  |  |  | 2021-08-09 | FEDEX P | SHIP 7/29 | 7/26 - BACK |  |  | 117 | Frencken America INC | Liberty Lake | WA | 99019-9514 |  | 234304518
|  | 2021-07-28 | 103345 (7/20) | 2300 Windy Ridge Pkwy Se STE 400 | 5 |  |  |  | 2021-08-05 | #VALUE! |  | 7/26 - BACK |  |  | 1 | Scientific Research Corporation | Atlanta | GA | 30339-5665 | attn: JSorenson | 153669597
|  | 2021-07-28 | 102725 | 185 ALEWIFE BROOK PWKY STE 401 | 797 |  |  |  | 2021-08-05 | FEDEX P | SHIP 7/28 - 7/29 | 7/21 - BACK |  | *2ND ARTICLE RELEASED 7/15 | 1 | ELEMENTAL MACHINES | CAMBRIDGE | MA | 02138-1100
|  | 2021-07-28 | 103539 | 7911 Zionsville Rd | 130 |  |  |  | 2021-08-03 | FEDEX P |  | 7/23 - AOI |  | *SHORT ATTRITION FOR R16 (402) | 0 | 3M | Indianappolis | IN | 46268-1650 | Attn: David Albean - 3M Personal Safety
|  | 2021-07-26 | 103019 | 411 WASHINGTON ST | 4 |  |  |  | 2021-07-26 | FEDEX P | SHIP 7/26 | 7/21 - BACK |  |  | 113 | SAFARI CIRCUITS | OTSEGO | MI | 49078-1241
|  | 2021-07-26 | 102550 | 8108 CLEBURNE CT | 50 |  |  |  | 2021-08-03 | UPS GND | SHIP 7/26 | 7/21 - BACK |  | *SHORT 1 ITEM U24/U25 - SKIP | 17 | LMA TECHNOLIGIES. LLC | WILLOW SPRING | NC | 27592-7590
|  | 2021-07-22 | 103276 (7/20) | 3200 N KINGS HWY | 50 |  |  |  | 2021-08-03 | UPS GND |  | 7/21 - AOI |  |  | 18 | GRAPH-TECH USA, LLC | FORT PIERCE | FL | 34951-4051 |  | 04Y70W
|  | 2021-07-21 | 103417 | 245 INDUSTRIAL PARK RD | 8 |  |  |  | 2021-07-23 | FEDEX 2 D | SHIP 7/21 | 7/16 - BACK |  |  | 281 | DUOTECH SERVICES INC | FRANKLIN | NC | 28734-7920
|  | 2021-07-20 | 103315 | 4975 E 41ST AVE | 25 |  |  |  | ??? | FEDEX GND | SHIP 7/20 | 7/19 - BACK |  | *SHORT 1 ITEM DIODE/OK SKIP | 22 | MOUNT SOPRIS INSTRUMENTS | DENVER | CO | 80216-4424
|  | 2021-07-20 | 103593 | 1915 MARATHON AVE | 12 |  |  |  | 2021-07-22 | FEDEX P | SHIP 7/20 | 7/19 - BACK |  |  | 34 | GEORGIA PACIFIC CONSUMER | NEENAH | WI | 54956-4067 | R&D NEENAH TEHNICAL CENTER (1108)
|  | 2021-07-20 | 103297 | 7000 E AVE GEN REC BLDG 411 - PO # B641295 | 110 |  |  |  | 2021-07-21 | FEDEX P | SHIP 7/20 | 7/19 - BACK |  | ***SHIP EARLY | 8 | LLNL DOE/NNSA | LIVERMORE | CA | 94550-9698 | LAWRENCE LIVERMORE NATIONAL LAB
|  | 2021-07-19 | 103295 | 5700 STONERIDGE DR STE 102 | 4 |  |  |  | 2021-07-22 | FEDEX P |  | 7/15 - AOI |  |  | 18 | VECTOR ATOMIC | PLEASANTON | CA | 94588-2897
|  | 2021-07-19 | 102471 | 106 E WARREN ST | 15 |  |  |  | 2021-07-28 | UPS GND |  | 7/16 - AOI |  | *BUILD TO DEPLETION | 0 | NON-CONTACT TECHNOLOGIES | TULLAHOMA | TN | 37388-4519 | ATTN: TERRY HAYES
|  | 2021-07-16 | 103497 | 110 PARKLAND PLAZA, SUITE B | 20 |  |  |  | 2021-07-19 | FEDEX P |  | 7/15 - BACK |  |  | 48 | THORLABS | ANN ARBOR | MI | 48103
|  | 2021-07-15 | 98989 | 499 BOEING BLVD SW BLDG 48-18 | 28 |  |  |  | 2021-07-23 | FEDEX P |  | 7/12 - BACK |  |  | 36 | THE BOEING COMPANY | HUNTSVILLE | AL | 35824-3001 | ATTN: JOANN VANSANDT | 048201407

## MS Hist
B |  | QTY | PDD | L/T | CLEAR DATE | SHIP DATE | NEW DATE | PROG | PLCMNT | T/H | LINES | BOT | TOP | # MACH | NOTES | NOTES | NOTES
BELOW THIS LINE - RELEASED & IN-PROCESS JOBS
121252 | 8474.5 | 50 | 2023-10-13 | 5 | N/C | ??? |  | NEED | 450 | 0 | 15 | 1 | 1 |  |  | Tad REL 10/9
120969 | 1572.5 | 150 | 2023-10-04 | 5 | N/C | ??? |  | NEED | 3 | 0 | 3 | 1 | 1 |  |  | ON HOLD 10/6
120533 | 4725.55 | 7 | 2023-10-12 | 10 | N/C | ??? |  | NEED | 699 | 20 | 128 | 1 | 1 |  |  | DOC REL 9/28
121051 | 466.7 | 10 | 2023-10-18 | 5 | N/C | ??? |  | NEED | 173 | 129 | 32 | 0 | 1 |  |  | DOC REL 10/4
120688 | 6975.02 | 193 | 2023-11-06 | 15 | N/C | ??? |  | NEED | 137 | 6 | 68 | 1 | 1 |  | ROWC B114869 | DOC REL 9/25
119432-1st | 5834 | 2 | 2023-10-10 | 5 | N/C | ??? |  | NEED | 1086 | 10 | 148 | 1 | 1 |  |  | DOC REL 9/21
120152 | 1652.5 | 30 | 2023-09-01 | 5 | N/C | ??? |  | XR | 91 | 11 | 31 | 1 | 1 |  |  | JOB HOLD/FREEZE 9/14
119568 | 3121 | 25 | 2023-09-25 | 9 | N/C | ??? |  | NEED | 395 | 12 | 118 |  |  |  |  | DOC REL 9/19
120288 | 3900 | 50 | 2023-09-20 | 5 | 2023-10-04 | 2023-10-11 |  | NEED | 6 | 1 | 5 | 1 | 1 |  |  | KIT CLEAR 10/4
118595 | 1875 | 100 | 2023-10-04 | 7 | 2023-10-02 | 2023-10-11 |  | NEED | 83 | 0 | 52 | 1 | 1 |  |  | KIT CLEAR 10/2
120730 | 3423.75 | 5 | 2023-10-09 | 5 | 2023-10-04 | 2023-10-11 |  | NEED | 607 | 39 | 105 | 1 | 1 |  |  | KIT CLEAR 10/4
120276 | 3955 | 6 | 2023-10-05 | 5 | 2023-10-04 | 2023-10-11 |  | NEED | 682 | 20 | 72 | 1 | 1 |  |  | KIT CLEAR 10/4
120932 | 2990.25 | 15 | 2023-10-11 | 5 | 2023-10-05 | 2023-10-12 |  | X | 170 | 44 | 54 | 1 | 1 | 1B/1T |  | KIT CLEAR 10/5
120351 | 26940 | 100 | 2023-10-05 | 5 10 | 2023-10-05 | 2023-10-12 |  | X | 695 | 13 | 149 | 0 | 1 | 3T | ROWC B111470 | KIT CLEAR 10/5
120820 | 4138 | 50 | 2023-10-09 | 5 | 2023-10-06 | 2023-10-13 |  | NEED | 224 | 18 | 53 | 1 | 1 |  |  | KIT CLEAR 10/6
120287 | 2738.5 | 50 | 2023-10-19 | 10 | 2023-09-29 | 2023-10-13 |  | NEED | 36 | 16 | 6 | 1 | 1 |  |  | KIT CLEAR 9/29
119829 | 2580 | 200 | 2023-10-30 | 20 | 2023-09-15 | 2023-10-16 |  | NEED | 43 | 0 | 27 | 0 | 1 |  | RONC B113661 | 9/15 - KIT CLEAR
120664 | 15060 | 100 | 2023-09-28 | 20 | 2023-09-18 | 2023-10-16 |  | NEED | 767 | 35 | 110 | 1 | 1 |  | ROWC 115231 | KIT CLEAR 9/18
117366 | 1884 | 100 | 2023-10-16 | 10 | 2023-10-03 | 2023-10-17 |  | NEED | 13 | 2 | 7 | 0 | 1 |  |  | KIT CLEAR 10/3
114862 | 19305 | 450 | 2023-03-20 | 10 | 2023-10-03 | 2023-10-17 |  | X | 229 | 4 | 69 | 1 | 1 | 2B/2T | With change B103336 | KIT CLEAR 10/3
120938 | 4397 | 100 | 2023-10-19 | 10 | 2023-10-05 | 2023-10-19 |  | NEED | 190 | 0 | 74 | 1 | 1 |  |  | KIT CLEAR 10/5
119594 | 4124.5 | 25 | 2023-10-09 | 10 | 2023-10-05 | 2023-10-19 |  | NEED | 522 | 37 | 98 | 1 | 1 |  |  | KIT CLEAR 10/5
120758 | 9330 | 40 | 2023-10-17 | 10 | 2023-10-06 | 2023-10-19 |  | NEED | 653 | 56 | 89 | 1 | 1 |  | ROWC B118253 | DOC REL 9/21
120297 | 9608.64 | 12 | 2023-10-10 | 15 | 2023-09-29 | 2023-10-20 |  | NEED | 1339 | 23 | 148 | 1 | 1 |  |  | KIT CLEAR 9/29
BACK
104636-6 | 7996 | 200/200 | 2021-02-28 | 20 | N/C | ??? |  | X | 148 | 9 | 59 | 1 | 1 | 1B/1T | ROWC B104272 | SHORT PCB + 62 ITEMS
104636-5 | 7996 | 200/400 | 2021-11-28 | 20 | N/C | ??? |  | X | 148 | 9 | 59 | 1 | 1 | 1B/1T | ROWC B104272 | SHORT PCB + 62 ITEMS
107703-1 | 1572.4 | 1 | 2022-02-10 | 5 | N/C | ??? |  | X | 326 | 124 | 41 | 1 | 1 | 1B/1T | ROWC B95933 | DOC REL 2/15
110428 | 3361 | 350 | 2022-06-22 | 10 | N/C | ??? |  | X | 1 | 2 | 1 | 0 | 1 | 1T
114334-4 | 2050.24 | 344 | 2022-06-17 | 10 | 2022-11-16 | ??? |  | X | 35 | 7 | 19 | 0 | 1 | 2T | PAID RWK
114618-2BAL | 3727.8 | 15 | 2023-02-10 | 10 | N/C | ??? |  | X | 768 | 10 | 78 | 1 | 1 | 1B/1T |  | SMT CLEAR 7/26
117371-4BAL | 375.06 | 12 | 2023-06-06 | 15 | 2023-05-11 | 2023-12-06 |  | XR | 22 | 18 | 15 | 1 | 1 | 1B/1T |  | KIT CLEAR 5/9
117369-3BAL | 375 | 12 |  | 15 | 2023-07-27 | 2023-12-06 |  | X | 22 | 18 | 15 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/27 | SHIPPED 8/17/2023
120284-3BAL | 2579.5 | 50 | 2023-10-04 | 10 | 2023-10-02 | 2023-11-13 |  | NEED | 117 | 20 | 58 | 1 | 1 |  | ROWC B118087 | KIT CLEAR 10/2
116310 | 2500 | 200 | 2023-05-22 | 10 | 2023-10-06 | 2023-10-20 |  | X | 0 | 2 | 0 | 0 | 0 | 0 | THT Only | KIT CLEAR 10/6
119436-RMAbal | 0 | 42 | 2023-09-07 | 3 | ??? | 2023-10-17 |  | - | 0 | 4 | 0 | 0 | 0 | 0 | UNPAID RMA | KIT CLEAR 9/5
120284-2PAR | 1031.8 | 20 | 2023-10-04 | 10 | 2023-10-02 | 2023-10-16 |  | NEED | 117 | 20 | 58 | 1 | 1 |  | ROWC B118087 | KIT CLEAR 10/2
118067-2ndBAL | 2167.8943 | 12 | 2023-05-22 | 5 | 2023-10-06 | 2023-10-13 |  | X | 602 | 35 | 93 | 1 | 1 | 2B/2T | Treat as new/gerber changed and need new stencil/program. | KIT CLEAR 10/13
120825 | 3583 | 50 | 2023-10-16 | 10 | 2023-09-28 | 2023-10-12 |  | NEED | 205 | 2 | 53 | 1 | 1 |  | RONC B120123 | KIT CLEAR 9/28
120423 | 5971.28 | 26 | 2023-10-03 | 5 | 2023-10-04 | 2023-10-11 |  | NEED | 520 | 19 | 75 | 0 | 1 |  |  | KIT CLEAR 10/4
121088 | 6144.7 | 5 | 2023-10-05 | 3 | 2023-10-05 | 2023-10-10 |  | NEED | 699 | 5 | 98 | 1 | 1 |  |  | KIT CLEAR 10/5
118628-2PAR | 39489.9565 | 1550 | 2023-09-01 | 20 | 2023-09-06 | 10/10 10/4 |  | X | 155 | 3 | 30 | 1 | 1 | 2B/2T | ROWC B114946 | KIT CLEAR 9/6
120284-1PAR | 4047.7 | 30 | 2023-10-04 | 5 10 | 2023-10-02 | 2023-10-09 |  | NEED | 117 | 20 | 58 | 1 | 1 |  | ROWC B118087 | KIT CLEAR 10/2
118067-2ndPAR | 20989 | 100 | 2023-05-22 | 5 | 2023-10-02 | 2023-10-09 |  | X | 602 | 35 | 93 | 1 | 1 | 2B/2T | Treat as new/gerber changed and need new stencil/program. | KIT CLEAR 10/2
120864 | 3310 | 20 | 2023-10-05 | 5 | 2023-09-29 | 2023-10-06 |  | NEED | 103 | 1 | 37 | 0 | 1 |  |  | KIT CLEAR 9/29 | SHIPPED 10/6/2023
119129-2BAL | 121.59 | 1 | 2023-08-07 | 10 | 2023-07-31 | 2023-08-14 |  | X | 400 | 18 | 120 | 1 | 1 | 2B/2T | RONC B106266 | KIT CLEAR 7/31 | SHIPPED 8/14/2023
114812-7 | 5642 | 50 | 2022-01-10 | 10 | 2022-12-22 | 2/28 2/22 *1/9H | BOT DONE | X | 554 | 16 | 92 | 1 | 1 | 1B/2T | QTY 50 expedited. Can build all 195 at once. | KIT CLEAR 1/20 | SHIPPING HOLD
104636-4 | 7996 | 200/600 | 2021-08-31 | 20 | 2022-12-27 | 2023-01-13 |  | X | 148 | 9 | 59 | 1 | 1 | 1B/1T | ROWC B104272 | SHORT PCB + 62 ITEMS | SHIPPING HOLD
108218-3 | 3500 | 200 | 2022-05-16 | 20 | 2022-06-27 | 2022-07-25 |  | X | 127 | 4 | 25 | 1 | 1 | 2B/1T |  | BAL KIT CLEAR 6/27
BELOW THIS LINE - SHIPPED JOBS | [16 empty] | SHIP DATE | 2020-11-16 | 2020-11-17 | 2020-11-18 | 2020-11-19 | 2020-11-20 | 2020-11-23 | 2020-11-24 | 2020-11-25 | 2020-11-26 | 2020-11-27 | 2020-11-30 | 2020-12-01 | 2020-12-02 | 2020-12-03 | 2020-12-04 | 2020-12-07 | 2020-12-08 | 2020-12-09 | 2020-12-10 | 2020-12-11 | 2020-12-14 | 2020-12-15 | 2020-12-16 | 2020-12-17 | 2020-12-18 | 2020-12-21 | 2020-12-22 | 2020-12-23 | 2020-12-24 | 2020-12-25 | 2020-12-28 | 2020-12-29 | 2020-12-30 | 2020-12-31 | 2020-01-01 | 2020-01-04 | 2020-01-05 | 2020-01-06 | 2020-01-07 | 2020-01-08 | 2020-01-11 | 2020-01-12 | 2020-01-13 | 2020-01-14 | 2020-01-15 | 2020-01-18 | 2020-01-19 | 2020-01-20 | 2020-01-21 | 2020-01-22
119436-RMApar | 0 | 5 | 2023-09-07 | 3 | ??? | 2023-10-06 |  | - | 0 | 4 | 0 | 0 | 0 | 0 | UNPAID RMA | KIT CLEAR 9/5 | SHIPPED 10/6/2023
119577 | 5825.1 | 145 | 2023-09-20 | 10 | 2023-09-22 | 2023-10-06 |  | NEED | 203 | 0 | 13 | 1 | 1 |  |  | KIT CLEAR 9/22 | SHIPPED 10/6/2023
120864 | 3310 | 80 | 2023-10-05 | 5 | 2023-09-29 | 2023-10-06 |  | NEED | 103 | 1 | 37 | 0 | 1 |  |  | KIT CLEAR 9/29 | SHIPPED 10/6/2023
119290 | 3944 | 50 | 2023-10-05 | 10 | 2023-09-22 | 2023-10-06 |  | NEED | 296 | 5 | 106 | 1 | 1 |  |  | KIT CLEAR 9/22 | SHIPPED 10/6/2023
117371-3PAR | 375.06 | 12 | 2023-06-06 | 15 | 2023-05-11 | 2023-10-06 |  | XR | 22 | 18 | 15 | 1 | 1 | 1B/1T |  | KIT CLEAR 5/9 | SHIPPED 10/6/2023
117369-2PAR | 375 | 12 |  | 15 | 2023-07-27 | 2023-10-06 |  | X | 22 | 18 | 15 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/27 | SHIPPED 10/6/2023
119291 | 4642 | 50 | 2023-10-05 | 10 | 2023-09-22 | 2023-10-06 |  | NEED | 361 | 12 | 99 | 1 | 1 |  |  | KIT CLEAR 9/22 | SHIPPED 10/6/2023
120528 | 3131 | 98 | 2023-09-20 | 5 | 2023-09-29 | 2023-10-06 |  | NEED | 56 | 10 | 25 | 0 | 1 |  |  | KIT CLEAR 9/29 | SHIPPED 10/6/2023
117094-3BAL | 14492.16 | 400 | 2023-05-09 | 20 | 2023-08-21 | 10/6 10/2 |  | X | 126 | 4 | 24 | 1 | 1 | 2B/1T | 2nd batch 1500 - only change is new reflow profile | 9/18 - KIT CLEAR | SHIPPED 10/6/2023
120259 | 6013.25 | 335 | 2023-10-05 | 15 | 2023-09-14 | 2023-10-05 |  | X | 97 | 0 | 18 | 1 | 1 | 1B/1T | RONC B110522 | KIT CLEAR 9/14 | SHIPPED 10/6/2023
118916 | 3642.5 | 5 | 2023-07-10 | 5 | 2023-09-28 | 2023-10-05 |  | NN | 251 | 126 | 48 | 0 | 1 |  |  | KIT CLEAR 9/28 | SHIPPED 10/5/2023
120499 | 2650 | 50 | 2023-09-13 | 10 | 2023-09-21 | 2023-10-05 |  | X | 125 | 17 | 6 | 0 | 1 | 1T | RONC B103224 | KIT CLEAR 9/21 | SHIPPED 10/5/2023
120259 | 15526.75 | 865 | 2023-10-05 | 15 | 2023-09-14 | 2023-10-05 |  | X | 97 | 0 | 18 | 1 | 1 | 1B/1T | RONC B110522 | KIT CLEAR 9/14 | SHIPPED 10/5/2023
121017 | 4169 | 2 | 2023-09-28 | 3 | 2023-09-29 | 2023-10-04 |  | NEED | 830 | 17 | 84 | 1 | 1 |  |  | KIT CLEAR 9/29 | SHIPPED 10/4/2023
119346-3rd | 4712 | 248 | 2023-08-11 | 5 | 2023-10-02 | 2023-10-04 |  | NEED | 1 | 1 | 1 | 1 | 0 |  | RONC 2nd Article | KIT CLEAR 10/2 | SHIPPED 10/4/2023
120636 | 3370 | 40 | 2023-09-27 | 5 | 2023-09-27 | 2023-10-04 |  | NEED | 2 | 0 | 1 | 0 | 1 |  |  | KIT CLEAR 9/27 | SHIPPED 10/4/2023
120701 | 3938.74 | 6 | 2023-10-03 | 5 | 2023-09-27 | 2023-10-04 |  | NEED | 634 | 32 | 54 | 0 | 1 |  |  | KIT CLEAR 9/26 | SHIPPED 10/4/2023
120387 | 4234 | 2 | 2023-10-04 | 10 | 2023-09-19 | 2023-10-03 |  | NEED | 1204 | 23 | 106 |  |  |  |  | 9/19 - KIT CLEAR | SHIPPED 10/3/2023
119431-2nd | 17940 | 20 | 2023-08-28 | 5 | 2023-09-26 | 2023-10-03 |  | NEED | 1380 | 0 | 222 | 1 | 1 |  | ROWC 1st Article | KIT CLEAR 9/26 | SHIPPED 10/3/2023
120702 | 4842 | 20 | 2023-09-26 | 5 | 2023-09-21 | 10/3 9/28 |  | NEED | 417 | 4 | 77 | 0 | 1 | 2T |  | KIT CLEAR 9/21 | SHIPPED 10/3/2023
119344-2nd | 5927 | 248 | 2023-08-18 | 5 | 2023-09-26 | 2023-10-03 |  | NEED | 2 | 0 | 2 | 1 | 1 |  | RONC 1st Article | KIT CLEAR 9/26 | SHIPPED 10/3/2023
118397 | 6331.4 | 90 | 2023-09-18 | 20 | 2023-09-05 | 2023-10-03 |  | NN | 336 | 3 | 96 | 1 | 1 |  |  | KIT CLEAR 9/5 | SHIPPED 10/3/2023
120429 | 2407.5 | 50 | 2023-09-18 | 15 | 2023-09-12 | 2023-10-03 |  | X | 94 | 13 | 29 | 0 | 1 | 1T | RONC B116783 | KIT CLEAR 9/12 | SHIPPED 10/3/2023
120432 | 3371.63 | 13 | 2023-10-03 | 10 | 2023-09-19 | 2023-10-03 |  | XR | 318 | 84 | 43 | 0 | 1 |  | ROWC B117047 | 9/19 - KIT CLEAR | SHIPPED 10/3/2023
120883 | 4680 | 270 | 2023-09-27 | 3 | 2023-09-27 | 2023-10-02 |  | NEED | 2 | 0 | 2 | 0 | 1 |  |  | KIT CLEAR 9/27 | SHIPPED 10/2/2023
120474 | 7575 | 5 | 2023-10-09 | 10 | 2023-09-18 | 2023-10-02 |  | NEED | 30 | 199 | 3 | 1 | 1 |  |  | 9/18 - KIT CLEAR | SHIPPED 10/2/2023
120559 | 37852.5 | 375 | 2023-09-20 | 10 | 2023-09-18 | 2023-10-02 |  | XR | 422 | 53 | 65 | 1 | 1 |  | ROWC B119543 | 9/18 - KIT CLEAR | SHIPPED 10/2/2023
120532 | 1602.5 | 150 | 2023-09-25 | 5 | 2023-09-22 | 2023-09-29 |  | NEED | 33 | 0 | 22 |  |  |  |  | KIT CLEAR 9/22 | SHIPPED 9/29/2023
120889 | 1583 | 100 | 2023-10-02 | 5 | 2023-09-22 | 2023-09-29 |  | SMT | 16 | 4 | 2 | 0 | 1 |  |  | KIT CLEAR 9/21 | SHIPPED 9/29/2023
119676 | 3927.5 | 50 | 2023-09-19 | 15 | 2023-09-05 | 2023-09-26 |  | XR | 176 | 53 | 49 | 0 | 1 |  |  | KIT CLEAR 9/5 | SHIPPED 9/27/2023
120529 | 1583 | 100 | 2023-09-19 | 5 | N/C | 2023-09-27 |  | NEED | 17 | 2 | 10 | 1 | 1 |  |  | 9/20 - KIT CLEAR | SHIPPED 9/27/2023
118702 | 4420 | 100 | 2023-08-01 | 10 | 2023-09-13 | 2023-09-27 |  | X | 157 | 15 | 51 | 1 | 1 | 1B/1T | ROWC B107608 | KIT CLEAR 9/13 | SHIPPED 9/27/2023
116819-2nd | 1758 | 5 | 2023-07-06 | 15 | N/C | 2023-09-26 |  | X | 795 | 8 | 32 | 1 | 1 | 1B/1T | ROWC 1st Article | SHORT THRU-HOLE 9/5 | SHIPPED 9/26/2023
120745 | 4812 | 20 | 2023-09-26 | 5 | 2023-09-19 | 2023-09-26 |  | XR | 506 | 10 | 65 | 1 | 1 |  |  | 9/19 - KIT CLEAR | SHIPPED 9/26/2023
120638 | 10946.8 | 20 | 2023-09-25 | 5 | 2023-09-19 | 2023-09-26 |  | NN | 1085 | 39 | 123 | 1 | 1 |  |  | 9/19 - KIT CLEAR | SHIPPED 9/26/2023
118820-2ND | 2570.25 | 3 | 2023-07-07 | 3 | 2023-09-19 | 2023-09-25 |  | NEED | 253 | 10 | 68 | 1 | 1 | 1B/1T |  | 9/18 - KIT CLEAR (REPORTED 9/20) | SHIPPED 9/26/2023
119343-2nd | 10912.379 | 98 | 2023-08-15 | 5 | 2023-09-14 | 9/25 9/22 |  | X | 655 | 0 | 140 | 1 | 1 | 2B/2T | RONC 1st Article | KIT CLEAR 9/21 | SHIPPED 9/25/2023
120614 | 2841.5 | 5 | 2023-09-20 | 5 | 2023-09-18 | 2023-09-25 |  | NN | 392 | 15 | 97 | 1 | 1 |  |  | KIT CLEAR 9/18 (ALTA REPORTED) | SHIPPED 9/25/2023
120092 | 2428 | 4 | 2023-09-25 | 3 | 2023-09-20 | 2023-09-25 |  | NEED | 40 | 47 | 1 | 0 | 1 |  |  | DOC REL 9/20 (Phuong) | SHIPPED 9/25/2023
120686 | 2032.3 | 110 | 2023-09-25 | 3 | 2023-09-21 | 2023-09-25 |  | NEED | 4 | 12 | 2 | 0 | 1 |  |  | KIT CLEAR 9/21 | SHIPPED 9/25/2023
119811 | 6520 | 40 | 2023-09-20 | 15 | 2023-08-25 | 9/25 9/19H |  | X | 35 | 71 | 8 | 0 | 1 | 1T |  | KIT CLEAR 8/25 | SHIPPED 9/25/2023
119346-2nd | 2812 | 2 | 2023-08-11 | 5 | 2023-08-22 | 2023-08-29 |  | X | 1 | 1 | 1 | 1 | 0 | 1B |  | RE-RELEASE / AWT NEW PCBS 9/13 | SHIPPED 9/22/2023
120556 | 5921.3 | 6 | 2023-09-14 | 3 | 2023-09-12 | 2023-09-22 |  | XR | 533 | 44 | 88 | 1 | 1 |  |  | KIT CLEAR 9/12 - FOOTPRINT ISSUES - 9/18 RESOLVED | SHIPPED 9/22/2023
119574 | 4067 | 70 | 2023-09-19 | 15 | 2023-08-30 | 9/22H |  | X | 330 | 0 | 57 | 1 | 1 | 1B/1T | ROWC B115651 | KIT CLEAR 8/30 | SHIPPED 9/22/2023
119343-2nd | 16702.621 | 150 | 2023-08-15 | 5 | 2023-09-14 | 2023-09-22 |  | X | 655 | 0 | 140 | 1 | 1 | 2B/2T | RONC 1st Article | KIT CLEAR 9/21 | SHIPPED 9/22/2023
120153 | 4070 | 100 | 2023-09-13 | 5 | 2023-09-14 | 2023-09-21 |  | XR | 120 | 11 | 49 | 1 | 1 |  | RONC B119038 | 9/18 - KIT CLEAR | SHIPPED 9/21/2023
118860-2nd | 2694.6 | 12 | 2023-07-21 | 5 | 2023-09-14 | 2023-09-21 |  | X | 568 | 6 | 83 | 1 | 1 | 1B/1T | ROWC 1st Article | KIT CLEAR 9/14 | SHIPPED 9/21/2023
120561 | 3708 | 2 | 2023-09-12 | 5 | 2023-09-14 | 2023-09-21 |  | XR | 606 | 42 | 63 | 1 | 1 |  |  | KIT CLEAR 9/14 | SHIPPED 9/21/2023
119925 | 5095.6 | 20 | 2023-09-05 | 10 | 2023-09-07 | 2023-09-21 |  | X | 676 | 8 | 90 | 1 | 1 | 1B/2T |  | KIT CLEAR 9/7 | SHIPPED 9/21/2023
119713 | 4007 | 100 | 2023-09-20 | 5 | 2023-09-13 | 2023-09-20 |  | XR | 96 | 19 | 33 | 0 | 1 |  |  | KIT CLEAR 9/13
120492 | 3074 | 80 | 2023-09-06 | 5 | 2023-09-13 | 2023-09-20 |  | XR | 106 | 1 | 34 | 1 | 1 |  |  | KIT CLEAR 9/13 | SHIPPED 9/20/2023
119188 | 3949.6 | 40 | 2023-08-25 | 15 | 2023-08-28 | 9/20H |  | XR | 360 | 12 | 45 | 1 | 1 | 1B/2T |  | KIT CLEAR 8/27 | SHIPPED 9/20/2023
119554 | 2960 | 40 | 2023-09-11 | 10 | 2023-09-06 | 2023-09-20 |  | - | 0 | 16 | 0 | 0 | 0 | 0 | THT Only | KIT CLEAR 9/6 | SHIPPED 9/20/2023
117094-2PAR | 39853.44 | 1100 | 2023-05-09 | 20 | 2023-08-21 | 9/20H |  | X | 126 | 4 | 24 | 1 | 1 | 2B/1T | 2nd batch 1500 - only change is new reflow profile | KIT CLEAR 8/21 | SHIPPED 9/20/2023
119442-2nd | 3383 | 85 | 2023-08-18 | 3 | N/C | 2023-09-20 |  | NEED | 1 | 1 | 1 | 0 | 1 | 1T |  | NO DOC. | SHIPPED 9/20/2023
119440-2nd | 3383 | 85 | 2023-08-18 | 3 | 2023-09-14 | 2023-09-19 |  | NEED | 1 | 1 | 1 | 0 | 1 |  |  | KIT CLEAR 9/12 | SHIPPED 9/19/2023
120334 | 4970 | 700 | 2023-09-13 | 5 | 2023-09-12 | 2023-09-19 |  | X | 2 | 0 | 2 | 0 | 1 | 1T | RONC B117447 | KIT CLEAR 9/12 | SHIPPED 9/19/2023
120099 | 3733 | 150 | 2023-09-01 | 5 | 2023-09-12 | 2023-09-19 |  | X | 62 | 0 | 11 | 1 | 1 | 1B/1T |  | KIT CLEAR 9/12 | SHIPPED 9/19/2023
120096-1st | 1650.75 | 2 | 2023-09-12 | 5 | 2023-09-11 | 2023-09-18 |  | X | 475 | 4 | 51 | 1 | 1 | 1B/1T |  | KIT CLEAR 9/11 | SHIPPED 9/18/2023
118295 | 2274 | 4 | 2023-09-08 | 5 | 2023-09-11 | 2023-09-18 |  | X | 98 | 12 | 50 | 1 | 1 | 1B/1T |  | KIT CLEAR 9/11 | SHIPPED 9/18/2023
118628-1PAR | 2547.7391 | 100 | 2023-09-01 | 20 | 2023-09-06 | 2023-09-18 |  | X | 155 | 3 | 30 | 1 | 1 | 2B/2T | ROWC B114946 | KIT CLEAR 9/6 | SHIPPED 9/18/2023
119275-2nd | 1260 | 40 | 2023-08-09 | 10 | 2023-08-31 | 9/18H |  | X | 118 | 14 | 52 | 0 | 1 | 1T | ROWC 1st Article | KIT CLEAR 8/31 | SHIPPED 9/18/2023
119275-2nd | 157.5 | 5 | 2023-08-09 | 10 | 2023-08-31 | 9/18H |  | X | 118 | 14 | 52 | 0 | 1 | 1T | ROWC 1st Article | KIT CLEAR 8/31 | SHIPPED 9/18/2023
116508 | 1470 | 120 | 2023-08-25 | 10 | 2023-08-30 | 9/15H |  | X | 13 | 0 | 12 | 0 | 1 | 1T |  | KIT CLEAR 8/30 | SHIPPED 9/15/2023
119482-1st | 2393 | 5 | 2023-08-15 | 5 | 2023-09-07 | 2023-09-15 |  | X | 20 | 11 | 9 | 1 | 1 | 1B/1T |  | KIT CLEAR 9/7 | SHIPPED 9/15/2023
120465-1st | 2260 | 10 | 2023-09-12 | 5 | 2023-09-07 | 2023-09-15 |  | X | 93 | 6 | 45 | 1 | 1 | 1B/1T |  | KIT CLEAR 9/7 | SHIPPED 9/15/2023
119344-1st | 6912 | 2 | 2023-08-18 | 5 | 2023-09-06 | 9/15 9/13 |  | X | 2 | 0 | 2 | 1 | 1 | 1B/1T |  | KIT CLEAR 9/6 | SHIPPED 9/15/2023
119437-2nd | 9982 | 85 | 2023-08-16 | 3 | 2023-09-11 | 2023-09-14 |  | X | 320 | 0 | 111 | 1 | 1 | 1B/2T | RONC 1st Article | KIT CLEAR 9/11 | SHIPPED 9/14/2023
120350 | 6284.4 | 12 | 2023-09-11 | 3 | 2023-09-11 | 2023-09-14 |  | X | 492 | 0 | 74 | 1 | 1 | 1B/1T |  | KIT CLEAR 9/11 | SHIPPED 9/14/2023
120450 | 1572.65 | 135 | 2023-09-11 | 5 | 2023-09-06 | 2023-09-13 |  | X | 2 | 0 | 2 | 1 | 1 | 1B/1T |  | KIT CLEAR 9/6 | SHIPPED 9/13/2023
119924 | 7687.5 | 30 | 2023-09-05 | 10 | 2023-08-28 | 9/13H |  | X | 498 | 6 | 89 | 1 | 1 | 1B/2T |  | KIT CLEAR 8/28 | SHIPPED 9/13/2023
119296 | 2468.96 | 64 | 2023-08-22 | 10 | 2023-08-28 | 9/13H |  | X | 85 | 11 | 26 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/28 | SHIPPED 9/13/2023
119442-1ST | 1380 | 5 | 2023-08-18 | 5 | 2023-09-05 | 2023-09-12 |  | X | 1 | 1 | 1 | 0 | 1 | 1T |  | KIT CLEAR 9/5 | SHIPPED 9/12/2023
119440-1ST | 1380 | 5 | 2023-08-18 | 5 | 2023-09-05 | 2023-09-12 |  | X | 1 | 1 | 1 | 0 | 1 | 1T |  | KIT CLEAR 9/5 | SHIPPED 9/12/2023
120324-1ST | 2292 | 2 | 2023-09-21 | 5 | 2023-09-05 | 2023-09-12 |  | X | 80 | 4 | 44 | 0 | 1 | 1T |  | KIT CLEAR 9/5 | SHIPPED 9/12/2023
120020 | 2796 | 2 | 2023-09-14 | 10 | 2023-08-25 | 9/12H |  | X | 303 | 8 | 95 | 1 | 1 | 1B/2T |  | KIT CLEAR 8/25 | SHIPPED 9/12/2023
119784 | 7075.44 | 54 | 2023-09-07 | 10 | 2023-08-28 | 2023-09-12 |  | X | 660 | 2 | 91 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/28 | SHIPPED 9/12/2023
119433-2nd | 3504 | 20 | 2023-08-14 | 3 | 2023-09-06 | 2023-09-11 |  | X | 436 | 0 | 134 | 1 | 1 | 2B/1T | ROWC 1st Article | KIT CLEAR 9/6 | SHIPPED 9/11/2023
119276 | 15329 | 140 | 2023-08-21 | 5 | 2023-08-31 | 9/11H |  | X | 549 | 5 | 22 | 0 | 1 | 2T |  | KIT CLEAR 8/31 | SHIPPED 9/11/2023
119071-2ND | 3531 | 70 | 2023-07-31 | 5 | 2023-08-28 | 9/8 9/6H |  | X | 173 | 4 | 64 | 1 | 1 | 1B/1T | ROWC 1st Article | KIT CLEAR 8/28 | SHIPPED 9/8/2023
119809 | 2200 | 10 | 2023-09-08 | 3 | 2023-09-05 | 2023-09-08 |  | X | 2 | 0 | 2 | 1 | 1 | 1B/1T | RONC B115113 | KIT CLEAR 9/8 | SHIPPED 9/8/2023
120218 | 3382 | 60 | 2023-08-25 | 3 | 2023-09-05 | 2023-09-08 |  | X | 98 | 0 | 45 | 1 | 1 | 1B/1T |  | KIT CLEAR 9/8 | SHIPPED 9/8/2023
119436-2ND | 1470 | 55 | 2023-09-07 | 3 | 2023-09-05 | 2023-09-08 |  | - | 0 | 4 | 0 | 0 | 0 | 0 | THT only/ROWC 1st Article (gerber change only, same BOM) | KIT CLEAR 9/5 | SHIPPED 9/8/2023
120123 | 4530 | 50 | 2023-09-11 | 10 | 2023-08-22 | 9/7H |  | X | 205 | 2 | 53 | 1 | 1 | 1B/1T | RONC B117173 | KIT CLEAR 8/22 | SHIPPED 9/7/2023
120472 | 4663 | 100 | 2023-09-07 | 3 | 2023-08-31 | 2023-09-07 |  | X | 98 | 1 | 39 | 1 | 1 | 1B/1T | ROWC B119043 | KIT CLEAR 8/31 | SHIPPED 9/7/2023
119784 | 524.1067 | 4 | 2023-09-07 | 10 | 2023-08-28 | 2023-09-07 |  | X | 660 | 2 | 91 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/28 | SHIPPED 9/7/2023
119571 | 5507.6 | 70 | 2023-09-05 | 10 | 2023-08-22 | 9/7H |  | X | 307 | 5 | 65 | 1 | 1 | 1B/1T | RONC B114955 | KIT CLEAR 8/22 | SHIPPED 9/7/2023
119189 | 4240 | 15 | 2023-08-18 | 10 | 2023-08-21 | 9/7 9/6H |  | X | 257 | 63 | 46 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/21 | SHIPPED 9/7/2023
119788-1ST | 3611 | 45 | 2023-08-28 | 5 | 2023-08-25 | 9/6H |  | X | 152 | 6 | 67 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/28 | SHIPPED 9/6/2023
119655 | 1876 | 100 | 2023-08-24 | 10 | 2023-08-21 | 9/6H |  | X | 42 | 6 | 24 | 0 | 1 | 1T | ROWC B112877 | KIT CLEAR 8/21 | SHIPPED 9/6/2023
119448 | 5674.71 | 97 | 2023-09-01 | 9 | 2023-08-22 | 9/5H |  | X | 231 | 0 | 94 | 0 | 1 | 2T |  | KIT CLEAR 8/22 | SHIPPED 9/5/2023
120335 | 1572.5 | 250 | 2023-09-04 | 5 | 2023-08-25 | 9/5H |  | - | 0 | 5 | 0 | 0 | 0 | 0 | THT only | KIT CLEAR 8/25 | SHIPPED 9/5/2023
120150 | 4314 | 20 | 2023-08-25 | 5 | 2023-08-24 | 2023-08-31 |  | X | 355 | 5 | 103 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/24 | SHIPPED 8/31/2023
119849 | 3335.6 | 80 | 2023-08-28 | 5 | 2023-08-24 | 2023-08-31 |  | X | 69 | 2 | 40 | 0 | 1 | 1T |  | KIT CLEAR 8/24 | SHIPPED 8/31/2023
118969 | 7650 | 250 | 2023-08-18 | 10 | 2023-08-17 | 2023-08-31 |  | X | 82 | 5 | 29 | 0 | 1 | 2T |  | KIT CLEAR 8/16 | SHIPPED 8/31/2023
119913 | 2801.4 | 69 | 2023-08-22 | 5 | 2023-08-23 | 2023-08-30 |  | X | 139 | 7 | 48 | 1 | 1 | 1B/1T | ROWC B117703 | KIT CLEAR 8/23 | SHIPPED 8/30/2023
119272 | 66.5856 | 1 | 2023-07-28 | 10 | 2023-08-10 | 2023-08-24 |  | X | 206 | 4 | 74 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/10 | SHIPPED 8/29/2023
118260 | 5853.6 | 170 | 2023-08-21 | 10 | 2023-08-15 | 2023-08-29 |  | X | 112 | 9 | 49 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/15 | SHIPPED 8/29/2023
119922-1PAR | 20004 | 100 | 2023-08-18 | 3 | 2023-08-22 | 8/28 8/25 |  | X | 440 | 3 | 122 | 1 | 1 | 2B/2T |  | KIT CLEAR 8/22 | SHIPPED 8/28/2023
120136 | 2022.4 | 170 | 2023-08-25 | 3 | 2023-08-23 | 2023-08-28 |  | X | 3 | 0 | 3 | 1 | 0 | 1B |  | KIT CLEAR 8/23 | SHIPPED 8/28/2023
120137 | 2042.2 | 90 | 2023-08-25 | 3 | 2023-08-23 | 2023-08-28 |  | X | 28 | 0 | 11 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/23 | SHIPPED 8/28/2023
119747-2BAL | 3985 | 100 | 2023-08-23 | 10 | 2023-08-14 | 2023-08-28 |  | X | 173 | 0 | 101 | 0 | 1 | 2T | ROWC B108974 | KIT CLEAR 8/14 | SHIPPED 8/28/2023
119486 | 2851 | 20 | 2023-08-01 | 5 | 2023-07-21 | 8/28 7/28 |  | X | 273 | 2 | 57 | 1 | 1 | 1B/1T | Do not De-panel | KIT CLEAR 7/21 | SHIPPED 8/28/2023
119734 | 3559.5 | 10 | 2023-08-21 | 10 | 2023-08-14 | 2023-08-28 |  | X | 387 | 19 | 119 | 1 | 1 | 1B/2T |  | KIT CLEAR 8/14 | SHIPPED 8/28/2023
119206 | 7068.5 | 55 | 2023-08-22 | 5 | 2023-08-21 | 2023-08-28 |  | X | 411 | 45 | 130 | 1 | 1 | 1B/2T |  | KIT CLEAR 8/21 | SHIPPED 8/28/2023
118686 | 18983 | 100 | 2023-08-03 | 10 | 2023-08-14 | 2023-08-28 |  | X | 513 | 39 | 80 | 1 | 1 | 1B/1T | ROWC B111037 | KIT CLEAR 8/14 | SHIPPED 8/28/2023
118109-2BAL | 9999.93 | 375 | 2023-08-14 | 5 | 2023-08-17 | 8/25 8/24 |  | X | 165 | 0 | 8 | 0 | 1 | 1T |  | KIT CLEAR 8/17 | SHIPPED 8/25/2023
119431-1st | 2492 | 5 | 2023-08-28 | 5 | 2023-08-18 | 2023-08-25 |  | X | 1380 | 0 | 221 | 1 | 1 | 3B/3T |  | KIT CLEAR 8/18 | SHIPPED 8/25/2023
119480-1st | 2575 | 5 | 2023-08-15 | 5 | 2023-08-18 | 2023-08-25 |  | X | 133 | 5 | 43 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/18 | SHIPPED 8/25/2023
117918 | 7106.24 | 2 | 2023-06-16 | 10 | 2023-08-11 | 2023-08-25 |  | X | 1483 | 14 | 204 | 1 | 1 | 3B/2T |  | KIT CLEAR 8/11 | SHIPPED 8/25/2023
119492 | 2052.5 | 75 | 2023-08-25 | 3 | 2023-08-22 | 2023-08-25 |  | X | 28 | 1 | 19 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/22 | SHIPPED 8/25/2023
114615 | 3670 | 20 | 2023-01-31 | 10 | 2023-08-11 | 2023-08-25 |  | X | 243 | 24 | 85 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/11 | SHIPPED 8/25/2023
116086-2ND | 10069.5 | 175 | 2023-03-23 | 10 | 2023-08-11 | 2023-08-25 |  | X | 250 | 8 | 83 | 0 | 1 | 2T | ROWC 1st Article | KIT CLEAR 8/11 | SHIPPED 8/25/2023
119272 | 2929.7644 | 44 | 2023-07-28 | 10 | 2023-08-10 | 2023-08-24 |  | X | 206 | 4 | 74 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/10 | SHIPPED 8/25/2023
118109-1PAR | 9999.93 | 375 | 2023-08-14 | 5 | 2023-08-17 | 2023-08-24 |  | X | 165 | 0 | 8 | 0 | 1 | 1T |  | KIT CLEAR 8/17 | SHIPPED 8/24/2023
119747-1PAR | 996.25 | 25 | 2023-08-23 | 10 | 2023-08-14 | 8/24 8/28 |  | X | 173 | 0 | 101 | 0 | 1 | 2T | ROWC B108974 | KIT CLEAR 8/14 | SHIPPED 8/24/2023
119826 | 5037.2 | 20 | 2023-08-25 | 5 | 2023-08-17 | 2023-08-24 |  | X | 852 | 3 | 93 | 1 | 1 | 1B/2T |  | KIT CLEAR 8/17 | SHIPPED 8/24/2023
120011 | 3860 | 300 | 2023-08-25 | 5 | 2023-08-16 | 2023-08-23 |  | X | 1 | 0 | 1 | 1 | 0 | 1B |  | KIT CLEAR 8/16 | SHIPPED 8/23/2023
119430 | 3100 | 10 | 2023-08-09 | 5 | 2023-08-16 | 2023-08-23 |  | X | 499 | 1 | 36 | 1 | 1 | 1B/1T |  | KIT CLEEAR 8/16 | SHIPPED 8/23/2023
119866 | 20721.1 | 5 | 2023-08-10 | 3 | 2023-08-18 | 2023-08-23 |  | X | 1084 | 23 | 219 | 1 | 1 | 2B/3T |  | KIT CLEAR 8/18 | SHIPPED 8/23/2023
119182 | 4919 | 50 | 2023-07-31 | 5 | 2023-08-16 | 2023-08-23 |  | X | 285 | 7 | 109 | 1 | 1 | 1B/2T |  | KIT CLEAR 8/16 | SHIPPED 8/23/2023
117522-1BAL | 987.4 | 28 | 2023-05-29 | 10 | 2023-08-08 | 2023-08-22 |  | X | 137 | 4 | 26 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/8 | SHIPPED 8/22/2023
119250 | 13954 | 200 | 2023-08-04 | 5 | 2023-08-15 | 2023-08-22 |  | X | 290 | 1 | 107 | 1 | 1 | 1B/2T |  | KIT CLEAR 8/15 | SHIPPED 8/22/2023
119962 | 2445 | 5 | 2023-08-22 | 5 | 2023-08-15 | 2023-08-22 |  | X | 14 | 73 | 4 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/15 | SHIPPED 8/22/2023
119384 | 1480 | 50 | 2023-08-22 | 10 | 2023-08-08 | 2023-08-22 |  | X | 19 | 13 | 5 | 0 | 1 | 1T |  | KIT CLEAR 8/8 | SHIPPED 8/22/2023
119998 | 1573 | 100 | 2023-08-23 | 5 | 2023-08-14 | 2023-08-21 |  | X | 8 | 0 | 6 | 0 | 1 | 1T |  | KIT CLEAR 8/14 | SHIPPED 8/21/2023
120057-2BAL | 1701 | 5 | 2023-08-16 | 5 | 2023-08-14 | 2023-08-21 |  | X | 340 | 8 | 61 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/14 | SHIPPED 8/21/2023
119973 | 1593 | 100 | 2023-08-23 | 5 | 2023-08-14 | 2023-08-21 |  | X | 17 | 3 | 10 | 0 | 1 | 1T |  | KIT CLEAR 8/14 | SHIPPED 8/21/2023
119437-1ST | 2710 | 5 | 2023-08-16 | 5 | 2023-08-11 | 2023-08-18 |  | X | 320 | 0 | 111 | 1 | 1 | 1B/2T |  | KIT CLEAR 8/11 | SHIPPED 8/18/2023
119822 | 2830 | 30 | 2023-08-17 | 5 | 2023-08-11 | 2023-08-18 |  | X | 24 | 0 | 3 | 0 | 1 | 1T |  | KIT CLEAR 8/11 | SHIPPED 8/18/2023
118335 | 2478 | 30 | 2023-07-26 | 10 | 2023-07-27 | 8/18 8/15 8/10 |  | X | 176 | 17 | 43 | 0 | 1 | 1T |  | KIT CLEAR 7/27 | SHIPPED 8/18/2023
118334 | 4712 | 100 | 2023-07-27 | 10 | 2023-08-01 | 8/18 8/15 |  | X | 125 | 35 | 34 | 0 | 1 | 1T |  | KIT CLEAR 8/1 | SHIPPED 8/18/2023
118691 | 7802.6 | 60 | 2023-08-08 | 10 | 2023-08-04 | 2023-08-18 |  | X | 259 | 65 | 30 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/4 | SHIPPED 8/18/2023
119812 | 7512.5 | 250 | 2023-08-18 | 3 | 2023-08-14 | 2023-08-17 |  | X | 36 | 0 | 22 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/14 | SHIPPED 8/17/2023
118090-1ST | 2910 | 1 | 2023-08-21 | 5 | 2023-08-10 | 2023-08-17 |  | X | 1296 | 15 | 43 | 0 | 1 | 1T |  | KIT CLEAR 8/10 | SHIPPED 8/17/2023
120057-1PAR | 1701 | 5 | 2023-08-16 | 5 | 2023-08-14 | 8/17 8/21 |  | X | 340 | 8 | 61 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/14 | SHIPPED 8/17/2023
119499 | 5162.7 | 6 | 2023-08-16 | 5 | 2023-08-10 | 2023-08-17 |  | X | 920 | 20 | 110 | 1 | 1 | 1B/2T |  | KIT CLEAR 8/10 | SHIPPED 8/17/2023
116119 | 3020 | 120 | 2023-08-23 | 5 | 2023-08-10 | 2023-08-17 |  | X | 3 | 2 | 3 | 0 | 1 | 1T |  | KIT CLEAR 8/10 | SHIPPED 8/17/2023
117369-1PAR | 750 | 24 |  | 15 | 2023-07-27 | 2023-08-17 |  | X | 22 | 18 | 15 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/27 | SHIPPED 8/17/2023
118087-1BAL | 2130.5 | 50 | 2023-06-27 | 10 | 2023-06-14 | 8/17 8/22 |  | X | 117 | 20 | 58 | 1 | 1 | 1B/1T | RONC B116713 | KIT CLEAR 6/14 | SHIPPED 8/17/2023
119343-1ST | 5224 | 2 | 2023-08-15 | 5 | 2023-08-08 | 8/16 8/15 |  | X | 655 | 0 | 140 | 1 | 1 | 2B/2T |  | KIT CLEAR 8/8 | SHIPPED 8/16/2023
118979 | 3655.4 | 20 | 2023-08-01 | 10 | 2023-08-02 | 2023-08-15 |  | X | 350 | 42 | 58 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/2 | SHIPPED 8/15/2023
118778 | 1460 | 250 | 2023-07-26 | 10 | 2023-07-31 | 2023-08-14 |  | X | 5 | 0 | 4 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/31 | SHIPPED 8/14/2023
119068 | 2492.56 | 6 | 2023-07-11 | 5 | 2023-08-07 | 2023-08-14 |  | X | 421 | 4 | 64 | 0 | 1 | 2T |  | KIT CLEAR 8/7 | SHIPPED 8/14/2023
114618-1PAR | 1242.6 | 5 | 2023-02-10 | 10 | 2023-08-08 | 2023-08-14 |  | X | 768 | 10 | 78 | 1 | 1 | 1B/1T |  | KIT PARTIAL CLEAR 8/8 | SHIPPED 8/14/2023
119332 | 1400 | 50 | 2023-08-09 | 10 | 2023-07-31 | 2023-08-14 |  | - | 0 | 1 | 0 | 0 | 0 | 0 | THT Only/RONC B115497 | KIT CLEAR 7/31 | SHIPPED 8/14/2023
119469 | 1560 | 25 | 2023-08-14 | 10 | 2023-07-31 | 2023-08-14 |  | X | 99 | 9 | 35 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/31 | SHIPPED 8/14/2023
119129-1PAR | 16414.65 | 135 | 2023-08-07 | 10 | 2023-07-31 | 2023-08-14 |  | X | 400 | 18 | 120 | 1 | 1 | 2B/2T | RONC B106266 | KIT CLEAR 7/31 | SHIPPED 8/14/2023
115809 | 1800 | 10 | 2023-03-10 | 3 | 2023-08-08 | 2023-08-11 |  | X | 298 | 6 | 69 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/8 | SHIPPED 8/11/2023
119067-2BAL | 1489.03 | 19 | 2023-07-14 | 5 | 2023-08-04 | 2023-08-11 |  | X | 283 | 17 | 113 | 1 | 1 | 1B/2T | No changes B115362 | KIT CLEAR 8/4 | SHIPPED 8/11/2023
118259 | 4022.85 | 85 | 2023-08-07 | 5 | 2023-08-04 | 2023-08-11 |  | X | 171 | 10 | 60 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/4 | SHIPPED 8/11/2023
118705 | 11089 | 100 | 2023-08-10 | 10 | 2023-07-28 | 2023-08-11 |  | X | 513 | 39 | 80 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/28 | SHIPPED 8/11/2023
119754 | 4612.2 | 30 | 2023-08-09 | 3 | 2023-08-07 | 2023-08-10 |  | X | 310 | 0 | 91 | 1 | 1 | 2B/1T |  | KIT CLEAR 8/7 | SHIPPED 8/10/2023
119071-1ST | 20164 | 40 | 2023-07-31 | 5 | 2023-08-04 | 8/10 8/11 |  | X | 173 | 2 | 64 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/4 | SHIPPED 8/10/2023
119468 | 3938.56 | 96 | 2023-08-17 | 10 | 2023-07-27 | 2023-08-10 |  | X | 117 | 4 | 38 | 1 | 1 | 1B/1T | RONC B115735 | KIT CLEAR 7/27 | SHIPPED 8/10/2023
119403 | 11932.47 | 9 | 2023-07-24 | 5 | 2023-08-02 | 2023-08-09 |  | X | 475 | 0 | 113 | 0 | 1 | 2T |  | KIT CLEAR 8/2 | SHIPPED 8/9/2023
117989-RMA | FREE | 7 |  | 5 | 2023-08-02 | 2023-08-09 |  | - | [6 empty] | UNPAID REWORK | CLEAR 8/2 | SHIPPED 8/9/2023
118974 | 4633.25 | 15 | 2023-08-03 | 10 | 2023-07-26 | 2023-08-09 |  | X | 791 | 13 | 88 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/26 | SHIPPED 8/9/2023
119565 | 3122 | 50 | 2023-08-01 | 5 | 2023-08-02 | 2023-08-09 |  | X | 194 | 4 | 59 | 0 | 1 | 1T |  | KIT CLEAR 8/2 | SHIPPED 8/9/2023
119659 | 4221.75 | 15 | 2023-08-09 | 5 | 2023-08-02 | 2023-08-09 |  | X | 527 | 26 | 27 | 0 | 1 | 1B/1T |  | KIT CLEAR 8/2 | SHIPPED 8/9/2023
119433-1st | 2951 | 5 | 2023-08-14 | 5 | 2023-08-01 | 2023-08-08 |  | X | 438 | 0 | 137 | 1 | 1 | 2B/1T |  | KIT CLEAR 8/1 | SHIPPED 8/8/2023
119677 | 1573 | 100 | 2023-08-09 | 5 | 2023-08-01 | 2023-08-08 |  | X | 5 | 0 | 4 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/1 | SHIPPED 8/8/2023
119672 | 2728.5 | 30 | 2023-08-01 | 5 | 2023-08-01 | 2023-08-08 |  | X | 201 | 6 | 62 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/1 | SHIPPED 8/8/2023
118651 | 3067.2 | 3 | 2023-08-01 | 10 | 2023-07-25 | 2023-08-08 |  | XR | 236 | 64 | 42 | 1 | 0 | 1B |  | KIT CLEAR 7/25 | SHIPPED 8/8/2023
118943 | 2993.45 | 45 | 2023-08-03 | 10 | 2023-07-25 | 2023-08-08 |  | XR | 180 | 16 | 47 | 0 | 1 | 1T |  | KIT CLEAR 7/25 | SHIPPED 8/8/2023
119660 | 1652.5 | 15 | 2023-08-07 | 5 | 2023-08-01 | 2023-08-08 |  | X | 39 | 80 | 10 | 0 | 1 | 1T |  | KIT CLEAR 8/1 | SHIPPED 8/8/2023
119051 | 1265 | 20 | 2023-07-10 | 5 | 2023-07-31 | 2023-08-07 |  | X | 275 | 0 | 55 | 1 | 1 | 1B/1T | ROWC B117697 | KIT CLEAR 7/31 | SHIPPED 8/7/2023
118860-1st | 3098 | 8 | 2023-07-21 | 5 | 2023-07-31 | 2023-08-07 |  | X | 568 | 6 | 83 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/31 | SHIPPED 8/7/2023
118699 | 4385.8 | 2 | 2023-06-28 | 5 | 2023-07-31 | 2023-08-07 |  | X | 1631 | 158 | 58 | 0 | 1 | 1T |  | KIT CLEAR 7/31 | SHIPPED 8/7/2023
118222-2nd | 5620.8 | 80 | 2023-07-05 | 5 | 2023-07-28 | 8/7 8/4 |  | X | 253 | 6 | 108 | 1 | 1 | 1B/2T | RONC 1st Article | KIT CLEAR 7/28 | SHIPPED 8/7/2023
119534 | 6838.75 | 35 | 2023-08-04 | 3 | 2023-08-02 | 2023-08-07 |  | X | 298 | 15 | 96 | 1 | 1 | 1B/2T |  | KIT CLEAR 8/2 | SHIPPED 8/7/2023
117371-2PAR | 375.06 | 12 | 2023-06-06 | 15 | 2023-05-11 | 2023-08-04 |  | XR | 22 | 18 | 15 | 1 | 1 | 1B/1T |  | KIT CLEAR 5/9 | SHIPPED 8/4/2023
119616 | 1642.56 | 48 | 2023-07-28 | 5 | 2023-07-28 | 2023-08-04 |  | X | 82 | 0 | 42 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/28 | SHIPPED 8/4/2023
118036 | 6270 | 8 | 2023-08-03 | 10 | 2023-07-21 | 2023-08-04 |  | X | 634 | 2 | 154 | 1 | 1 | 2B/2T |  | KIT CLEAR 7/21 | SHIPPED 8/4/2023
119456 | 2198.3 | 10 | 2023-08-03 | 5 | 2023-07-28 | 2023-08-04 |  | X | 76 | 3 | 31 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/28 | SHIPPED 8/4/2023
119317 | 3046 | 60 | 2023-07-24 | 10 | 2023-07-21 | 2023-08-04 |  | X | 110 | 4 | 30 | 0 | 1 | 1T |  | KIT CLEAR 7/21 | SHIPPED 8/4/2023
114318 | 1832.94 | 102 | 2023-07-26 | 10 | 2023-07-21 | 2023-08-04 |  | X | 55 | 3 | 23 | 1 | 1 | 1B/1T | RONC B108951 | KIT CLEAR 7/21 | SHIPPED 8/4/2023
119543 | 17399.35 | 165 | 2023-08-01 | 5 | 2023-07-28 | 2023-08-04 |  | X | 422 | 53 | 65 | 1 | 1 | 1B/2T |  | KIT CLEAR 7/28 | SHIPPED 8/4/2023
119614 | 8520 | 40 | 2023-08-02 | 5 | 2023-07-27 | 2023-08-03 |  | X | 500 | 0 | 15 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/27 | SHIPPED 8/3/2023
118707 | 2075 | 25 | 2023-08-03 | 20 | 2023-07-05 | 2023-08-02 |  | XR | 190 | 1 | 59 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/5 | SHIPPED 8/2/2023
114814-2 | 2325.76 | 105 | 2022-12-23 | 5 | 2022-12-20 | 1/4 12/28H |  | X | 92 | 1 | 42 | 1 | 1 | 1B/2T |  | KIT CLEAR 12/20 | SHIPPED 8/1/2023
119436-1st | 1100 | 5 | 2023-08-04 | 5 | 2023-07-25 | 2023-08-01 |  | - | 0 | 4 | 0 | 0 | 0 | 0 | THT only | KIT CLEAR 7/25 | SHIPPED 8/1/2023
118985-2ND | 2348 | 4 | 2023-07-17 | 5 | 2023-07-25 | 2023-08-01 |  | X | 1482 | 5 | 48 | 0 | 1 | 1T | ROWC 1st Article | KIT CLEAR 7/25 | SHIPPED 8/1/2023
118986-2ND | 2353.6 | 4 | 2023-07-12 | 5 | 2023-07-25 | 2023-08-01 |  | X | 1492 | 7 | 48 | 0 | 1 | 1T | ROWC 1st Article | KIT CLEAR 7/25 | SHIPPED 8/1/2023
118488 | 6606 | 100 | 2023-06-30 | 10 | 2023-07-18 | 2023-08-01 |  | X | 191 | 5 | 68 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/18 | SHIPPED 8/1/2023
119067-1PAR | 2429.47 | 31 | 2023-07-14 | 5 | 2023-07-25 | 2023-08-01 |  | X | 283 | 17 | 113 | 1 | 1 | 1B/2T | No changes B115362 | KIT CLEAR 7/25 | SHIPPED 8/1/2023
119234 | 9996 | 100 | 2023-07-25 | 10 | 2023-07-14 | 8/1 7/28 |  | - | 0 | 68 | 0 | 0 | 0 | - | THT Only/RONC B112309 | KIT CLEAR 7/14 | SHIPPED 8/1/2023
119507 | 2875 | 5 | 2023-07-31 | 5 | 2023-07-21 | 2023-07-28 |  | X | 370 | 15 | 60 | 0 | 1 | 1T |  | KIT CLEAR 7/21 | SHIPPED 8/1/2023
119491 | 4506.4 | 40 | 2023-07-27 | 3 | 2023-07-25 | 7/31 7/28 |  | X | 233 | 1 | 74 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/25 | SHIPPED 7/31/2023
119646 | 4634.5 | 10 | 2023-07-27 | 3 | 2023-07-26 | 2023-07-31 |  | XR | 375 | 6 | 96 | 0 | 1 | 2T |  | KIT CLEAR 7/26 | SHIPPED 7/31/2023
118985-1st | 4888 | 8 | 2023-07-17 | 5 | 2023-07-21 | 2023-07-28 |  | X | 1482 | 5 | 48 | 0 | 1 | 1T |  | KIT CLEAR 7/19 | SHIPPED 7/28/2023
119463 | 2596.05 | 5 | 2023-07-28 | 5 | 2023-07-21 | 2023-07-28 |  | X | 477 | 14 | 14 | 0 | 1 | 1T |  | KIT CLEAR 7/21 | SHIPPED 7/28/2023
119371 | 2391 | 10 | 2023-07-28 | 5 | 2023-07-21 | 2023-07-28 |  | X | 196 | 25 | 20 | 0 | 1 | 1T |  | KIT CLEAR 7/21 | SHIPPED 7/28/2023
119607 | 2186 | 10 | 2023-07-26 | 5 | 2023-07-20 | 2023-07-27 |  | X | 420 | 0 | 13 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/20 | SHIPPED 7/27/2023
119275-1ST | 1680 | 5 | 2023-08-09 | 5 | 2023-07-20 | 2023-07-27 |  | X | 117 | 14 | 51 | 0 | 1 | 1T |  | KIT CLEAR 7/20 | SHIPPED 7/27/2023
119501 | 3317.5 | 25 | 2023-07-25 | 3 | 2023-07-24 | 2023-07-27 |  | X | 186 | 3 | 78 | 0 | 1 | 2T |  | KIT CLEAR 7/24 | SHIPPED 7/27/2023
119210 | 2705.5 | 6 | 2023-07-26 | 5 | 2023-07-20 | 2023-07-27 |  | X | 168 | 49 | 5 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/20 | SHIPPED 7/27/2023
119305 | 3366 | 200 | 2023-07-19 | 5 | 2023-07-18 | 7/27 7/25 |  | X | 34 | 3 | 21 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/18 | SHIPPED 7/27/2023
119570 | 1702.56 | 12 | 2023-07-27 | 5 | 2023-07-20 | 2023-07-27 |  | X | 175 | 10 | 27 | 0 | 1 | 1T |  | KIT CLEAR 7/20 | SHIPPED 7/27/2023
118817 | 3088.8 | 60 | 2023-07-28 | 10 | 2023-07-12 | 7/27 7/26 |  | X | 149 | 3 | 44 | 0 | 1 | 1T |  | KIT CLEAR 7/12 | SHIPPED 7/27/2023
119566 | 4419.5 | 50 | 2023-07-24 | 3 | 2023-07-20 | 7/26 7/25 |  | X | 153 | 11 | 81 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/20 | SHIPPED 7/27/2023
119079 | 5761 | 20 | 2023-07-24 | 3 | 2023-07-21 | 2023-07-26 |  | X | 496 | 0 | 82 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/21 | SHIPPED 7/27/2023
119130 | 8855 | 125 | 2023-07-17 | 10 | 2023-07-10 | 2023-07-24 |  | X | 376 | 5 | 27 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/10 | SHIPPED 7/27/2023
119078 | 27128 | 20 | 2023-07-24 | 3 | 2023-07-21 | 2023-07-26 |  | X | 615 | 11 | 152 | 1 | 1 | 2B/2T |  | KIT CLEAR 7/21 | SHIPPED 7/26/2023
119254 | 3197 | 2 | 2023-07-25 | 5 | 2023-07-19 | 2023-07-26 |  | X | 105 | 118 | 19 | 0 | 1 | 1T |  | KIT CLEAR 7/19 | SHIPPED 7/26/2023
118749 | 3677.5 | 50 | 2023-07-13 | 3 | 2023-07-21 | 2023-07-26 |  | X | 59 | 35 | 29 | 0 | 1 | 1T | ROWC B115888 | KIT CLEAR 7/21 | SHIPPED 7/26/2023
118929 | 4967.8 | 12 | 2023-07-11 | 3 | 2023-07-20 | 2023-07-25 |  | X | 707 | 0 | 72 | 0 | 1 | 2T |  | KIT CLEAR 7/20 | SHIPPED 7/25/2023
118963 | 3632.7 | 3 | 2023-07-20 | 3 | 2023-07-20 | 2023-07-25 |  | X | 695 | 22 | 78 | 1 | 1 | 1B/2T |  | KIT CLEAR 7/20 | SHIPPED 7/25/2023
119082 | 5647.8 | 20 | 2023-07-24 | 3 | 2023-07-20 | 2023-07-25 |  | X | 325 | 20 | 101 | 1 | 1 | 1B/2T |  | KIT CLEAR 7/20 | SHIPPED 7/25/2023
119012 | 2370 | 75 | 2023-07-28 | 10 | 2023-07-11 | 2023-07-25 |  | X | 12 | 11 | 6 | 0 | 1 | 1T |  | KIT CLEAR 7/11 | SHIPPED 7/25/2023
118087-1PAR2 | 2130.5 | 50 | 2023-06-27 | 10 | 2023-06-14 | 2023-07-25 |  | X | 117 | 20 | 58 | 1 | 1 | 1B/1T | RONC B116713 | KIT CLEAR 6/14 | SHIPPED 7/25/2023
119356 | 3432.2 | 39 | 2023-07-18 | 5 | 2023-07-17 | 7/25 7/24 |  | X | 380 | 0 | 12 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/17 | SHIPPED 7/25/2023
118922 | 4180 | 165 | 2023-07-17 | 10 | 2023-07-10 | 7/25 7/24 |  | X | 9 | 0 | 4 | 1 | 1 | 1B/1T | Do not de-panel | KIT CLEAR 7/10 | SHIPPED 7/25/2023
117914 | 39172.4 | 540 | 2023-07-21 | 10 | 2023-07-10 | 2023-07-24 |  | X | 373 | 0 | 84 | 1 | 1 | 2B/2T | With changes B112216 | KIT CLEAR 7/10 | SHIPPED 7/24/2023
118407 | 6250 | 50 | 2023-07-11 | 3 | 2023-07-17 | 7/24 7/20 |  | X | 224 | 2 | 110 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/17 | SHIPPED 7/24/2023
119083 | 5900 | 20 | 2023-07-24 | 3 | 2023-07-19 | 2023-07-24 |  | X | 142 | 20 | 57 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/19 | SHIPPED 7/24/2023
118820-1st | 2871 | 2 | 2023-07-07 | 5 | 2023-07-14 | 2023-07-21 |  | X | 253 | 10 | 68 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/14 | SHIPPED 7/21/2023
118986-1st | 3295 | 8 | 2023-07-12 | 3 | 2023-07-18 | 2023-07-21 |  | X | 1492 | 7 | 48 | 0 | 1 | 1T |  | KIT CLEAR 7/18 | SHIPPED 7/21/2023
117522-1PAR | 2715.35 | 77 | 2023-05-29 | 10 | 2023-07-07 | 2023-07-21 |  | X | 137 | 4 | 26 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/7 (TAD) | SHIPPED 7/21/2023
119410 | 4088 | 200 | 2023-07-19 | 5 | 2023-07-13 | 2023-07-20 |  | X | 59 | 4 | 26 | 1 | 1 | 1B/1T | ROWC B118836 | KIT CLEAR 7/13 | SHIPPED 7/21/2023
118812 | 2329 | 1 | 2023-07-12 | 10 | 2023-07-06 | 2023-07-20 |  | X | 473 | 2 | 54 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/6 | SHIPPED 7/20/2023
118626 | 2760.4 | 3 | 2023-07-14 | 10 | 2023-07-06 | 2023-07-20 |  | X | 653 | 1 | 90 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/6 | SHIPPED 7/20/2023
118222-1ST | 5794.75 | 25 | 2023-07-05 | 5 | 2023-07-18 | 2023-07-20 |  | X | 253 | 6 | 108 | 1 | 1 | 1B/2T |  | KIT CLEAR 7/18 | SHIPPED 7/20/2023
118847-1BAL | 2850 | 424 500 | 2023-07-13 | 10 | 2023-07-17 | 2023-07-31 |  | X | 7 | 0 | 6 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/17 | SHIPPED 7/20/2023
118847-1PAR | 2850 | 50 | 2023-07-13 | 10 | 2023-07-14 | 2023-07-19 |  | X | 7 | 0 | 6 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/14 | SHIPPED 7/19/2023
118841 | 7505.5 | 5 | 2023-07-14 | 3 | 2023-07-18 | 2023-07-19 |  | X | 1464 | 4 | 95 | 1 | 1 | 1B/2T |  | KIT CLEAR 7/18 | SHIPPED 7/19/2023
117479-RWK2 | - | 286 |  | 10 | 2023-07-05 | 2023-07-19 |  | X | 23 | 0 | 8 | 0 | 1 | 2T |  | CLEAR 7/5 | SHIPPED 7/18/2023
118743 | 3488.6 | 20 | 2023-07-10 | 5 | 2023-07-11 | 2023-07-18 |  | X | 440 | 10 | 104 | 1 | 1 | 2B/1T |  | KIT CLEAR 7/10 | SHIPPED 7/18/2023
118256 | 5795.05 | 9 | 2023-06-19 | 5 | 2023-07-11 | 2023-07-18 |  | X | 665 | 23 | 136 | 1 | 1 | 1B/2T |  | KIT CLEAR 7/11 | SHIPPED 7/18/2023
119043 | 6940 | 150 | 2023-07-18 | 3 | 2023-07-13 | 2023-07-18 |  | X | 99 | 2 | 40 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/13 | SHIPPED 7/18/2023
119038 | 3877.96 | 92 | 2023-07-10 | 5 | 2023-07-10 | 2023-07-17 |  | X | 120 | 21 | 49 | 1 | 1 | 1B/1T | No changes B118402 | KIT CLEAR 7/10 | SHIPPED 7/18/2023
118307 | 2312 | 8 | 2023-06-26 | 10 | 2023-06-27 | 7/20 7/12H |  | X | 53 | 56 | 17 | 1 | 1 | 1B/1T |  | KIT CLEAR 6/27 | SHIPPED 7/18/2023
116819-1st | 2556 | 1 | 2023-07-06 | 5 | 2023-07-10 | 2023-07-17 |  | X | 799 | 8 | 33 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/10 | SHIPPED 7/17/2023
119377 | 3988.8 | 8 | 2023-07-13 | 2 | 2023-07-13 | 2023-07-17 |  | X | 515 | 10 | 121 | 1 | 1 | 1B/2T |  | DOC REL 7/12 | SHIPPED 7/17/2023
117479-RWK | 0 | 858 |  | 10 | 2023-07-05 | 2023-07-19 |  | X | 23 | 0 | 8 | 0 | 1 | 2T |  | CLEAR 7/5 | SHIPPED 7/14/2023
114814-2 | 2325.76 | 105 | 2022-12-23 | 5 | 2022-12-20 | 1/4 12/28H |  | X | 92 | 1 | 42 | 1 | 1 | 1B/2T |  | KIT CLEAR 12/20 | SHIPPED 7/14/2023
119377 | 2321.0667 | 4 | 2023-07-13 | 2 | 2023-07-13 | 2023-07-14 |  | X | 515 | 10 | 121 | 1 | 1 | 1B/2T |  | DOC REL 7/12 | SHIPPED 7/14/2023
117047-1ST | 2811.4 | 2 | 2023-07-11 | 5 | 2023-07-06 | 2023-07-13 |  | X | 318 | 84 | 43 | 0 | 1 | 1T |  | KIT CLEAR 7/6 | SHIPPED 7/13/2023
118993-1ST | 600 | 16 | 2023-07-10 | 5 | 2023-07-06 | 2023-07-13 |  | X | 194 | 5 | 44 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/6 | SHIPPED 7/13/2023
118879 | 5465.5 | 30 | 2023-07-13 | 5 | 2023-07-05 | 2023-07-12 |  | X | 678 | 7 | 73 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/5 | SHIPPED 7/13/2023
118253-2nd | 3150.4 | 10 | 2023-06-20 | 5 | 2023-07-06 | 2023-07-13 |  | X | 653 | 56 | 89 | 1 | 1 | 1B/2T | With changes 1st Article | KIT CLEAR 7/6 | SHIPPED 7/13/2023
118285 | 3965.2 | 10 | 2023-07-14 | 10 | 2023-06-27 | 7/12H |  | X | 556 | 8 | 51 | 1 | 1 | 1B/1T |  | KIT CLEAR 6/27 | SHIPPED 7/12/2023
119010 | 2602.2 | 2 | 2023-07-07 | 5 | 2023-07-05 | 2023-07-12 |  | X | 306 | 91 | 35 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/5 | SHIPPED 7/12/2023
118882 | 5380 | 4 | 2023-06-29 | 3 | 2023-07-07 | 2023-07-12 |  | X | 714 | 57 | 124 | 1 | 1 | 1B/2T |  | KIT CLEAR 7/7 | SHIPPED 7/12/2023
118789 | 4765.5 | 50 | 2023-07-07 | 5 | 2023-07-05 | 2023-07-12 |  | X | 339 | 9 | 66 | 0 | 1 | 2T |  | KIT CLEAR 7/5 | SHIPPED 7/12/2023
118993-1ST | 1500 | 4 | 2023-07-10 | 5 | 2023-07-06 | 2023-07-13 |  | X | 194 | 5 | 44 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/6 | SHIPPED 7/11/2023
117580 | 3922 | 200 | 2023-06-12 | 10 | 2023-06-12 | 7/12H 6/26 |  | XR | 2 | 0 | 1 | 1 | 0 | 1B |  | KIT CLEAR 6/12 (ERIC) | SHIPPED 7/11/2023
118885 | 1350 | 25 | 2023-07-19 | 10 | 2023-06-26 | 7/11H |  | X | 82 | 12 | 33 | 1 | 1 | 1B/1T | No changes B114417 | KIT CLEAR 6/26 | SHIPPED 7/11/2023
119029 | 2505.6 | 60 | 2023-07-06 | 5 | 2023-06-30 | 7/10H |  | X | 100 | 0 | 10 | 0 | 1 | 1T |  | KIT CLEAR 6/30 | SHIPPED 7/10/2023
118731 | 2583 | 5 | 2023-07-13 | 10 | 2023-06-23 | 7/10H |  | X | 484 | 21 | 67 | 0 | 1 | 2T |  | KIT CLEAR 6/23 | SHIPPED 7/10/2023
118965 | 3457 | 20 | 2023-07-05 | 5 | 2023-06-30 | 7/10H |  | X | 229 | 37 | 21 | 0 | 1 | 1T |  | KIT CLEAR 6/30 | SHIPPED 7/10/2023
118473-2ND | 3980.6 | 65 | 2023-06-14 | 5 | 2023-06-29 | 7/10 7/7H |  | X | 150 | 16 | 73 | 1 | 1 | 1B/1T | No changes 1st Article | KIT CLEAR 6/29 | SHIPPED 7/10/2023
118007 | 13600 | 4000 | 2023-06-23 | 20 | 2023-06-08 | 7/7H |  | X | 29 | 0 | 28 | 1 | 1 | 1B/1T | RONC B107990 | KIT CLEAR 6/8 | SHIPPED 7/7/2023
119011 | 2370 | 2 | 2023-07-05 | 5 | 2023-06-29 | 7/7H |  | X | 128 | 91 | 6 | 1 | 0 | 1B |  | SMT CLEAR 6/29 | SHIPPED 7/7/2023
118436 | 2118.5 | 50 | 2023-07-05 | 5 | 2023-06-29 | 7/7H |  | X | 131 | 7 | 32 | 1 | 1 | 1B/1T | No changes B104894 | KIT CLEAR 6/29 | SHIPPED 7/7/2023
118863 | 24.6667 | 1 | 2023-07-05 | 10 | 2023-06-21 | 7/6H |  | - | 0 | 22 | 0 | 0 | 0 |  | THT Only | KIT CLEAR 6/21 | SHIPPED 7/7/2023
114721-2nd | 3197 | 23 | 2023-05-19 | 10 | 2023-06-16 | 7/5 6/30H |  | X | 338 | 17 | 53 | 1 | 1 | 1B/2T | With change 1st Article | KIT CLEAR 6/13 | SHIPPED 7/6/2023
113842-1BAL | 12197.8 | 3 | 2023-01-11 | 3 | 2023-06-28 | 7/6H |  | X | 1326 | 23 | 179 | 1 | 1 | 2B/3T | Feeder dated 1/23 okay. Already includes the rework parts from the extra parts list. | KIT CLEAR 6/27 | SHIPPED 7/6/2023
118682 | 4928.4 | 12 | 2023-06-23 | 5 | 2023-06-28 | 7/6H |  | X | 634 | 6 | 94 | 1 | 1 | 1B/1T |  | KIT CLEAR 6/28 | SHIPPED 7/6/2023
118498 | 1208 | 2 | 2023-06-29 | 5 | 2023-06-28 | 7/6H |  | X | 40 | 47 | 1 | 0 | 1 | 1T | No changes B118079 | KIT CLEAR 6/28 | SHIPPED 7/6/2023
118107-2 | 3494 | 25 |  | 20 | 2023-05-25 | 7/6 6/30H |  | XR | 197 | 15 | 48 | 1 | 1 | 1B/1T |  | KIT CLEAR 5/25 | recv from industrialex for rework
118863 | 1455.3333 | 59 | 2023-07-05 | 10 | 2023-06-21 | 7/6H |  | - | 0 | 22 | 0 | 0 | 0 |  | THT Only | KIT CLEAR 6/21 | SHIPPED 7/6/2023
118323 | 12944 | 50 | 2023-06-29 | 5 | 2023-06-27 | 7/5H |  | X | 682 | 7 | 80 | 1 | 1 | 1B/2T |  | KIT CLEAR 6/27 | SHIPPED 7/5/2023
118696 | 3266 | 20 | 2023-06-29 | 5 | 2023-06-23 | 7/5 6/30H |  | X | 199 | 20 | 37 | 0 | 1 | 1T |  | KIT CLEAR 6/23 | SHIPPED 7/5/2023
118435 | 2750 | 50 | 2023-07-05 | 5 | 2023-06-27 | 7/5H |  | X | 118 | 10 | 23 | 1 | 1 | 1B/1T |  | KIT CLEAR 6/27 | SHIPPED 7/5/2023
118656 | 1592.5 | 125 | 2023-06-30 | 5 | 2023-06-21 | 2023-06-30 |  | X | 19 | 0 | 15 | 0 | 1 | 1T |  | KIT CLEAR 6/21 | SHIPPED 7/5/2023
113841 | 5996 | 6 | 2023-02-20 | 3 | 2023-06-27 | 2023-06-30 |  | X | 750 | 8 | 78 | 1 | 1 | 1B/1T |  | KIT CLEAR 6/27 | SHIPPED 6/30/2023
115385 | 2220 | 1 | 2023-06-26 | 10 | 2023-06-19 | 2023-06-30 |  | X | 264 | 15 | 104 | 1 | 1 | 1B/2T |  | KIT CLEAR 6/19 | SHIPPED 6/30/2023
118432 | 1444 | 400 | 2023-06-23 | 10 | 2023-06-07 | 2023-06-30 |  | X | 9 | 1 | 4 | 0 | 1 | 1T | RONC B100471 | KIT CLEAR 6/7 (ERIC) | SHIPPED 6/30/2023
118836 | 4088 | 200 | 2023-06-23 | 5 | 2023-06-23 | 2023-06-30 |  | X | 59 | 4 | 26 | 1 | 1 | 1B/1T | With changes B118518 | KIT CLEAR 6/23 | SHIPPED 6/30/2023
118769 | 5519.4 | 30 | 2023-06-28 | 5 | 2023-06-23 | 2023-06-30 |  | X | 533 | 51 | 148 | 1 | 1 | 2B/2T |  | KIT CLEAR 6/23 | SHIPPED 6/30/2023
118636 | 2590 | 10 | 2023-06-23 | 5 | 2023-06-22 | 2023-06-29 |  | X | 261 | 14 | 71 | 1 | 1 | 1B/1T |  | KIT CLEAR 6/22 | SHIPPED 6/29/2023
118399 | 4427.5 | 50 | 2023-06-29 | 10 | 2023-06-20 | 2023-06-29 |  | X | 264 | 6 | 87 | 1 | 1 | 1B/1T |  | KIT CLEAR 6/20 | SHIPPED 6/29/2023
118926 | 3656 | 120 | 2023-06-27 | 3 | 2023-06-26 | 2023-06-29 |  | X | 32 | 3 | 21 | 1 | 1 | 1B/1T |  | KIT CLEAR 6/26 | SHIPPED 6/29/2023
118313 | 3825 | 25 | 2023-06-16 | 5 | 2023-06-20 | 2023-06-26 |  | X | 385 | 4 | 113 | 1 | 1 | 2B/1T |  | KIT CLEAR 6/20 | SHIPPED 6/29/2023
118087-1PAR1 | 2130.5 | 50 | 2023-06-27 | 10 | 2023-06-14 | 2023-06-28 |  | X | 117 | 20 | 58 | 1 | 1 | 1B/1T | RONC B116713 | KIT CLEAR 6/14 | SHIPPED 6/28/2023
118703 | 2357.5 | 14 | 2023-06-27 | 5 | 2023-06-22 | 2023-06-29 |  | X | 77 | 25 | 20 | 1 | 1 | 1B/1T |  | KIT CLEAR 6/22 | SHIPPED 6/28/2023
118184 | 2178 | 100 | 2023-06-28 | 15 | 2023-06-08 | 2023-06-29 |  | X | 10 | 3 | 6 | 0 | 1 | 1T |  | KIT CLEAR 6/8 | SHIPPED 6/27/2023
116288-1BAL | 459.5 | 2 | 2023-04-07 | 5 | 2023-05-23 | ??? 5/31H |  | X | 685 | 1 | 56 | 1 | 1 | 1B/1T |  | KIT CLEAR 5/23 | SHIPPED 6/27/2023
117094-1ST | 25044 | 1200 | 2023-05-09 | 20 | 2023-05-26 | 6/26H |  | X | 126 | 4 | 24 | 1 | 1 | 2B/1T | With change B115838 - 1st batch 1200 - can run all 2700 at once if cleared | KIT CLEAR 5/26 | SHIPPED 6/26/2023
117780-2ND | 2134.08 | 3 | 2023-05-05 | 5 | 2023-06-13 | 2023-06-23 |  | X | 1149 | 33 | 80 | 1 | 1 | 1B/2T | No changes 1st Article | KIT CLEAR 6/13 | SHIPPED 6/23/2023
117749 | 3052 | 200 | 2023-06-23 | 3 | 2023-06-20 | 2023-06-23 |  | X | 15 | 5 | 7 | 1 | 1 | 1B/1T |  | KIT CLEAR 6/20 | SHIPPED 6/23/2023
113842-1PAR | 12197.8 | 3 | 2023-01-11 | 3 | 2023-06-08 | 2023-06-16 |  | X | 1326 | 23 | 179 | 1 | 1 | 2B/3T | Feeder dated 1/23 okay. Already includes the rework parts from the extra parts list. | KIT CLEAR 6/8 | SHIPPED 6/22/2023
117557-2nd | 2027.9 | 35 | 2023-05-30 | 3 | 2023-06-19 | 2023-06-22 |  | X | 106 | 0 | 28 | 1 | 0 | 1B | No changes 1st Article | KIT CLEAR 6/19 | SHIPPED 6/22/2023
118105 | 1970.4 | 2 | 2023-06-23 | 10 | 2023-06-08 | 2023-06-22 |  | X | 578 | 118 | 68 | 1 | 1 | 1B/2T | ROWC B111418 | KIT CLEAR 6/8 | SHIPPED 6/22/2023
118224 | 1900 | 20 | 2023-06-01 | 5 | N/C |  |  | - | [6 empty] | REWORK | NO DOC. | SHIPPED 6/22/2023
118601 | 1480 | 50 | 2023-07-03 | 10 | 2023-06-08 | 2023-06-22 |  | X | 12 | 23 | 3 | 0 | 1 | 1T | RONC B104649 | KIT CLEAR 6/8 | SHIPPED 6/21/2023
118253-1st | 2778 | 2 | 2023-06-20 | 5 | 2023-06-14 | 2023-06-21 |  | X | 653 | 56 | 89 | 1 | 1 | 1B/2T |  | KIT CLEAR 6/14 | SHIPPED 6/21/2023
118400 | 8486.8 | 16 | 2023-06-01 | 5 | 2023-06-14 | 2023-06-21 |  | X | 1365 | 13 | 130 | 1 | 1 | 2B/2T |  | KIT CLEAR 6/14 | SHIPPED 6/21/2023
117524 | 6987.5 | 215 | 2023-06-22 | 20 | 2023-05-23 | 6/21H |  | X | 140 | 3 | 28 | 1 | 1 | 1B/1T | RONC B116837 | KIT CLEAR 5/23 (PHUONG) | SHIPPED 6/21/2023
118086 | 9587.5 | 150 | 2023-06-14 | 10 | 2023-06-07 | 2023-06-21 |  | XR | 303 | 5 | 97 | 1 | 1 | 1B/2T |  | KIT CLEAR 6/7 | SHIPPED 6/21/2023
118711 | 4506.8 | 40 | 2023-06-16 | 5 | 2023-06-15 | 2023-06-22 |  | X | 51 | 2 | 31 | 1 | 1 | 1B/1T | RONC B109427 | KIT CLEAR 6/15 (HOLD) | JOB CANX 6/21/2023
118374 | 4426.8 | 10 | 2023-06-14 | 10 | 2023-06-08 | 2023-06-22 |  | X | 812 | 6 | 106 | 1 | 1 | 1B/2T |  | KIT CLEAR 6/8 | SHIPPED 6/20/2023
117221 | 4257.5 | 50 | 2023-06-16 | 15 | 2023-06-01 | 2023-06-22 |  | XR | 335 | 8 | 53 | 1 | 1 | 1B/1T | ROWC B110684 | KIT CLEAR 6/1 (PHUONG) | SHIPPED 6/20/2023
116459 | 1460 | 150 | 2023-04-11 | 10 | 2023-06-06 | 2023-06-20 |  | X | 3 | 3 | 1 | 0 | 1 | 1T |  | KIT CLEAR 6/6 | SHIPPED 6/20/2023
118514 | 12865.56 | 67 | 2023-06-14 | 5 | 2023-06-12 | 2023-06-19 |  | X | 392 | 2 | 91 | 1 | 1 | 1B/1T | RONC B114233 | KIT CLEAR 6/12 | SHIPPED 6/19/2023
118332 | 1630 | 10 | 2023-06-21 | 10 | 2023-06-02 | 2023-06-16 |  | X | 201 | 10 | 60 | 1 | 1 | 1B/1T |  | KIT CLEAR 6/2 | SHIPPED 6/16/2023
118473-1 | 2314 | 10 | 2023-06-14 | 5 | 2023-06-12 | 6/16 6/19 |  | X | 150 | 16 | 73 | 1 | 1 | 1B/1T |  | KIT CLEAR 6/12 | SHIPPED 6/16/2023
118430 | 5468.4 | 98 | 2023-06-15 | 5 | 2023-06-09 | 2023-06-16 |  | X | 172 | 5 | 63 | 1 | 1 | 1B/1T |  | KIT CLEAR 6/9 | SHIPPED 6/16/2023
118430 | 111.6 | 2 | 2023-06-15 | 5 | 2023-06-09 | 2023-06-15 |  | X | 172 | 5 | 63 | 1 | 1 | 1B/1T |  | KIT CLEAR 6/9 | SHIPPED 6/15/2023
118328 | 4020 | 2 | 2023-06-09 | 2 | 2023-06-13 | 2023-06-15 |  | X | 101 | 72 | 7 | 1 | 1 | 1B/1T |  | KIT CLEAR 6/13 | SHIPPED 6/15/2023
117868 | 5916 | 340 | 2023-06-01 | 20 | 2023-05-17 | 6/15H |  | X | 96 | 3 | 38 | 1 | 1 | 2B/2T | RONC B117102 | KIT CLEAR 5/17 | SHIPPED 6/15/2023
117175 | 4196.78 | 7 | 2023-06-02 | 10 | 2023-05-24 | 6/14 6/8H |  | X | 1297 | 12 | 112 | 1 | 1 | 2B/1T | ROWC B114054 | KIT CLEAR 5/24 (PHUONG) | SHIPPED 6/14/2023
114946-2BAL | 47667 | 1340 | 2023-02-22 | 20 | 2023-05-16 | 6/14H |  | X | 155 | 3 | 30 | 1 | 1 | 2B/2T |  | KIT CLEAR 5/16 | SHIPPED 6/14/2023
118331 | 1752.5 | 6 | 2023-06-16 | 5 | 2023-06-08 | 2023-06-15 |  | X | 212 | 46 | 19 | 0 | 1 | 1T |  | KIT CLEAR 6/8 | SHIPPED 6/13/2023
118329 | 1672.5 | 6 | 2023-06-16 | 5 | 2023-06-07 | 2023-06-14 |  | X | 105 | 9 | 45 | 0 | 1 | 1T |  | KIT CLEAR 6/7 | SHIPPED 6/13/2023
118033 | 8002 | 150 | 2023-06-15 | 5 | 2023-06-07 | 2023-06-14 |  | XR | 141 | 1 | 51 | 0 | 1 | 1T |  | KIT CLEAR 6/7 | SHIPPED 6/13/2023
118403 | 3310 | 13 | 2023-06-14 | 5 | 2023-06-07 | 2023-06-14 |  | X | 535 | 13 | 82 | 1 | 0 | 2B |  | KIT CLEAR 6/7 | SHIPPED 6/13/2023
118344 | 5775.38 | 9 | 2023-06-09 | 5 | 2023-06-05 | 2023-06-12 |  | X | 542 | 0 | 103 | 1 | 1 | 1B/2T | ROWC B113057 | KIT CLEAR 6/5 | SHIPPED 6/12/2023
117175 | 3597.24 | 6 | 2023-06-02 | 10 | 2023-05-24 | 6/8H |  | X | 1297 | 12 | 112 | 1 | 1 | 2B/1T | ROWC B114054 | KIT CLEAR 5/24 (PHUONG) | SHIPPED 6/12/2023
118593 | 1602.5 | 25 | 2023-06-15 | 3 | 2023-06-07 | 2023-06-12 |  | X | 36 | 0 | 17 | 0 | 1 | 1T |  | KIT CLEAR 6/7 | SHIPPED 6/9/2023
117896 | 5017.28 | 16 | 2023-06-01 | 10 | 2023-05-31 | 2023-06-14 |  | XR | 1097 | 62 | 44 | 1 | 1 | 1B/1T |  | KIT CLEAR 6/14 (ERIC) | SHIPPED 6/9/2023
118107-1 | 0 | 25 |  | 20 | 2023-05-25 | 6/23H |  | XR | 197 | 15 | 48 | 1 | 1 | 1B/1T |  | KIT CLEAR 5/25 | SHIPPED to industrialex 6/9/2023
118016 | 280.11 | 3 | 2023-05-16 | 5 | 2023-06-01 | ??? 6/8 |  | XR | 231 | 3 | 84 | 1 | 1 | 2B/1T |  | KIT CLEAR 6/1 (TAD) | SHIPPED 6/9/2023
117175 | 7194.48 | 12 | 2023-06-02 | 10 | 2023-05-24 | 6/8H |  | X | 1297 | 12 | 112 | 1 | 1 | 2B/1T | ROWC B114054 | KIT CLEAR 5/24 (PHUONG) | SHIPPED 6/8/2023
118016 | 2894.47 | 31 | 2023-05-16 | 5 | 2023-06-01 | 2023-06-08 |  | XR | 231 | 3 | 84 | 1 | 1 | 2B/1T |  | KIT CLEAR 6/1 (TAD) | SHIPPED 6/8/2023
118518 | 3145.6 | 80 | 2023-06-07 | 5 | 2023-06-01 | 2023-06-08 |  | X | 51 | 4 | 22 | 1 | 1 | 1B/1T | ROWC B117874 | KIT CLEAR 6/1 | SHIPPED 6/7/2023
117557-1ST | 1772 | 15 | 2023-05-30 | 3 | 2023-06-05 | 2023-06-08 |  | X | 108 | 0 | 28 | 1 | 0 | 1B |  | KIT CLEAR 6/5 (ERIC) | SHIPPED 6/7/2023
117738 | 2636.47 | 7 | 2023-06-08 | 15 | 2023-05-16 | 6/7H |  | XR | 788 | 16 | 63 | 1 | 1 | 1B/1T |  | KIT CLEAR 5/16 | SHIPPED 6/6/2023
117371-1 | 375.06 | 12 | 2023-06-06 | 15 | 2023-05-11 | 2023-06-06 |  | XR | 22 | 18 | 15 | 1 | 1 | 1B/1T |  | KIT CLEAR 5/9 | SHIPPED 6/6/2023
104336 | 8290.72 | 168 | 2023-05-17 | 10 | 2023-05-23 | 6/6H |  | XR | 210 | 11 | 54 | 1 | 1 | 1B 1T |  | 5/23 KIT CLEAR (TAD) | SHIPPED 6/6/2023
114721-1 | 4988 | 2 | 2023-05-19 | 5 | N/C | ??? |  | XR | 336 | 17 | 53 | 1 | 1 | 1B/2T |  | DOC REL 4/26 | SHIPPED 6/5/2023
116128 | 6809.5 | 70 | 2023-05-23 | 10 | 2023-05-19 | 6/5H |  | XR | 425 | 17 | 138 | 1 | 1 | 1B/2T |  | KIT CLEAR 5/19 | SHIPPED 6/5/2023
117867-1ST | 2871 | 2 | 2023-05-12 | 5 | 2023-05-31 | 2023-06-07 |  | X | 253 | 9 | 68 | 1 | 1 | 1B/1T |  | KIT CLEAR 5/31 | CANCELLED 6/5/2023
118402 | 4337.6 | 60 | 2023-05-24 | 3 | 2023-05-30 | 2023-06-02 |  | XR | 120 | 21 | 49 | 1 | 1 | 1B/1T |  | KIT CLEAR 5/30 (ERIC) | SHIPPED 6/2/2023
117989 | 4305.3 | 45 | 2023-05-24 | 5 | 2023-05-22 | ??? 5/30H |  | XR | 322 | 3 | 89 | 1 | 1 | 1B/2T |  | KIT CLEAR 5/22 (ERIC) | SHIPPED 6/2/2023
106266 | 0 | 600 | 2023-04-19 | 20 | 2023-04-05 | ??? 5/3 |  | X | 400 | 18 | 120 | 1 | 1 | 2B/2T |  | KIT CLEAR 4/5 | SHIPPED 6/2/2023
106266 | 40828 | 600 | 2023-04-19 | 20 | 2023-04-05 | ??? 5/3 |  | X | 400 | 18 | 120 | 1 | 1 | 2B/2T |  | KIT CLEAR 4/5 | SHIPPED IN PLACE 6/1
116688-1ST | 3366 | 3 | 2023-05-31 | 5 | 2023-05-24 | 6/1H |  | XR | 401 | 0 | 73 | 1 | 1 | 1b 2t |  | KIT CLEAR 5/24 (ERIC) | SHIPPED 6/1/2023
115576 | 2992.25 | 1 | 2023-05-16 | 10 | 2023-05-17 | 6/1H |  | XR | 4305 | 11 | 42 | 1 | 1 | 2B 2T |  | KIT CLEAR 5/17 (PHUONG) | SHIPPED 6/1/2023
118126 | 2915.8 | 2 | 2023-05-25 | 3 | 2023-05-26 | 6/1H |  | XR | 434 | 29 | 69 | 0 | 1 | 2T |  | KIT CLEAR 5/26 (ERIC) | SHIPPED 6/1/2023
115080 | 5051.6 | 20 | 2023-05-23 | 10 | 2023-05-17 | 6/1H |  | XR | 577 | 8 | 34 | 1 | 1 | 1B 1T |  | KIT CLEAR 5/17 (PHUONG) | SHIPPED 6/1/2023
116288 | 4135.5 | 18 | 2023-04-07 | 5 | 2023-05-23 | 5/31H |  | X | 685 | 1 | 56 | 1 | 1 | 1B/1T |  | KIT CLEAR 5/23 | SHIPPED 5/31/2023
118216 | 2190 | 5 | 2023-06-02 | 5 | 2023-05-23 | 5/31H |  | XR | 126 | 9 | 39 | 0 | 1 | 2t |  | KIT CLEAR 5/23 | SHIPPED 5/31/2023
117750 | 6280.24 | 16 | 2023-05-12 | 5 | 2023-05-23 | 5/31H |  | X | 1312 | 7 | 100 | 1 | 1 | 1B/1T |  | KIT CLEAR 5/23 (TAD) | SHIPPED 5/31/2023
117623 | 2700 | 10 | 2023-05-02 | 3 | 2023-05-25 | 5/31H |  | XR | 355 | 16 | 62 | 0 | 1 | 2T |  | KIT CLEAR 5/25 (TAD) | SHIPPED 5/31/2023
115838-1BAL | 23.91 | 1 | 2023-04-18 | 20 | 2023-04-11 | ??? 5/9 |  | X | 126 | 4 | 24 | 1 | 1 | 2B/1T | With change B113565 | KIT CLEAR 4/11 | SHIPPED 5/30/2023
117933 | 3400 | 40 | 2023-06-06 | 10 | 2023-05-18 | 6/2H |  | X | 117 | 17 | 30 | 1 | 1 | 1B/1T |  | KIT CLEAR 5/18 (ERIC) | SHIPPED 5/30/2023
113238 | 2500 | 250 | 2023-05-31 | 5 | 2023-05-22 | 5/30H |  | XR | 4 | 0 | 2 | 0 | 1 | 1T | RONC B109226 | KIT CLEAR 5/22 (ERIC) | SHIPPED 5/30/2023
116837 | 15350 | 500 | 2023-05-08 | 5 | 2023-05-22 | 5/30H |  | X | 140 | 3 | 28 | 1 | 1 | 1B/1T |  | KIT CLEAR 5/22 | SHIPPED 5/30/2023
117984-1BAL | 1502.28 | 9 | 2023-05-19 | 5 | 2023-05-25 | 6/2H |  | XR | 478 | 17 | 126 | 1 | 1 | 2B/2T |  | KIT CLEAR 5/25 (PHUONG) | SHIPPED 5/26/2023
117213 | 3202.76 | 34 | 2023-06-06 | 10 | 2023-05-16 | 5/31H |  | XR | 268 | 21 | 55 |  |  | 1T |  | KIT CLEAR 5/16 (ERIC) | SHIPPED 5/26/2023
117780-1ST | 2874 | 1 | 2023-05-05 | 3 | 2023-05-23 | 2023-05-26 |  | XR | 1149 | 33 | 80 | 1 | 1 | 1b 2t |  | KIT CLEAR 5/23 (ERIC) | SHIPPED 5/26/2023
117696 | 2400 | 10 | 2023-05-12 | 10 | 2023-05-12 | 2023-05-26 |  | X | 410 | 11 | 80 | 1 | 1 | 1B/1T |  | KIT CLEAR 5/12 | SHIPPED 5/26/2023
118067-1ST | 21788.68 | 4 |  | 5 | 2023-05-19 | 2023-05-26 |  | XR | 586 | 35 | 89 |  |  | 2B 1T |  | KIT CLEAR 5/19 (ERIC) | SHIPPED 5/26/2023
114869 | 13386.83 | 450 | 2023-02-20 | 5 | 2023-05-18 | 2023-05-25 |  | X | 137 | 6 | 68 | 1 | 1 | 2B/2T | With change B109746 | KIT CLEAR 5/18 | SHIPPED 5/25/2023
116908 | 2700 | 50 | 2023-05-19 | 8 | 2023-05-12 | 2023-05-24 |  | XR | 140 | 0 | 38 | 1 | 1 | 1B/1T |  | KIT CLEAR 5/12 (ERIC) | SHIPPED 5/24/2023
117189 | 3790.35 | 15 | 2023-04-27 | 3 10 | 2023-05-19 | 2023-05-24 |  | XR | 251 | 34 | 53 | 1 | 1 | 1B/1T |  | KIT CLEAR 5/19 | SHIPPED 5/24/2023
117807 | 1592.5 | 150 | 2023-05-16 | 5 | 2023-05-18 | 2023-05-25 |  | XR | 29 | 0 | 29 | 1 | 1 | 1B/1T |  | KIT CLEAR 5/18 (TAD) | SHIPPED 5/23/2023
118079 | 1188 | 2 |  | 5 | 2023-05-18 | 2023-05-25 |  | - | 40 | 47 | 1 | - | - | - | RONC B106341 | KIT CLEAR 5/18 (ERIC) | SHIPPED 5/23/2023
116350-2ND | 9445.6 | 4 | 2023-03-29 | 10 | 2023-05-11 | 2023-05-25 |  | X | 903 | 72 | 146 | 1 | 1 | 1B/2T | RONC 1ST | KIT CLEAR 5/11 | SHIPPED 5/23/2023
117874 | 2206 | 20 | 2023-05-18 | 5 | 2023-05-17 | 2023-05-24 |  | XR | 52 | 4 | 23 |  |  |  |  | KIT CLEAR 5/17 (TAD) | SHIPPED 5/22/2023
117984-1PAR | 2670.72 | 16 | 2023-05-19 | 5 | 2023-05-15 | 2023-05-19 |  | XR | 478 | 17 | 126 | 1 | 1 | 2B/2T |  | KIT CLEAR 5/15 (PHUONG) | SHIPPED 5/22/2023
117984-1PAR | 4173 | 25 | 2023-05-19 | 5 | 2023-05-15 | 2023-05-19 |  | XR | 478 | 17 | 126 | 1 | 1 | 2B/2T |  | KIT CLEAR 5/15 (PHUONG) | SHIPPED 5/19/2023
117766 | 4287.5 | 10 |  | 5 | 2023-05-12 | 2023-05-19 |  | X | 676 | 0 | 144 | 1 | 1 | 2B/2T |  | KIT CLEAR 5/12 | SHIPPED 5/19/2023
117697 | 1587.2 | 10 |  | 5 | 2023-05-12 | 2023-05-19 |  | XR | 55 | 1 | 245 | 1 | 1 | 1B/1T |  | KIT CLEAR 5/12 | SHIPPED 5/19/2023
118035 | 3574 | 5 |  | 2 | 2023-05-17 | 2023-05-19 |  | XR | 215 | 57 | 12 |  |  | 1t |  | KIT CLEAR 5/17 (ERIC) | SHIPPED 5/19/2023
117932 | 7187 | 50 | 2023-05-19 | 5 | 2023-05-12 | 2023-05-19 |  | XR | 593 | 8 | 90 | 0 | 1 | 2T |  | KIT CLEAR 5/12 (ERIC) | SHIPPED 5/19/2023
116458-2BAL | 32.1143 | 1 | 2023-04-13 | 10 | 2023-04-17 | ??? 4/28 |  | X | 290 | 1 | 106 | 1 | 1 | 2B/2T | With change B107934 | KIT CLEAR 4/17 | SHIPPED 5/19/2023
113185 | 6745 | 550 | 2023-05-23 | 20 | 2023-04-27 | 2023-05-25 |  | X | 59 | 0 | 7 | 1 | 1 | 1B/1T |  | KIT CLEAR 4/27 | SHIPPED 5/18/2023
116125 | 4038.5 | 15 | 2023-05-11 | 5 | 2023-05-11 | 2023-05-18 |  | XR | 234 | 62 | 83 | 1 | 1 | 1B/2T |  | KIT CLEAR 5/11 | SHIPPED 5/18/2023
117354-1BAL | 3214.0714 | 53 | 2023-05-23 | 10 | 2023-05-08 | 2023-05-22 |  | X | 139 | 12 | 63 | 0 | 1 | 2T |  | KIT CLEAR 5/8 | SHIPPED 5/17/2023
115854 | 19635 | 25 | 2023-04-14 | 5 | 2023-05-10 | 2023-05-17 |  | X | 1027 | 9 | 169 | 1 | 1 | 2B/2T | Do not de-panel | KIT CLEAR 5/10 | SHIPPED 5/17/2023
117628 | 2800.1 | 30 | 2023-05-16 | 10 | 2023-05-04 | 2023-05-18 |  | XR | 150 | 1 | 40 | 1 | 1 |  |  | KIT CLEAR 5/4 | SHIPPED 5/16/2023
104334 | 3139.88 | 62 | 2023-04-20 | 10 | 2023-05-02 | 2023-05-16 |  | X | 106 | 10 | 43 | 1 | 1 | 1B/1T |  | KIT CLEAR 5/2 | SHIPPED 5/16/2023
117447 | 2310 | 300 | 2023-05-12 | 5 | 2023-05-10 | 2023-05-17 |  | X | 2 | 0 | 2 | 0 | 1 | 1T | No changes B109227 | KIT CLEAR 5/10 | SHIPPED 5/15/2023
113840-1BAL | 2151.6667 | 4 | 2023-01-09 | 3 | 2023-05-12 | 2023-05-17 |  | X | 200 | 11 | 15 | 1 | 1 | 1B/1T |  | KIT CLEAR 5/12 | SHIPPED 5/15/2023
117377 | 2783.2 | 15 | 2023-05-17 | 5 | 2023-05-10 | 2023-05-17 |  | XR | 284 | 40 | 50 |  |  |  |  | KIT CLEAR 5/10 | SHIPPED 5/15/2023
117631 | 2450 | 10 | 2023-05-11 | 10 | 2023-05-02 | 2023-05-16 |  | XR | 407 | 13 | 48 | 1 | 1 |  |  | KIT CLEAR 5/2 | SHIPPED 5/15/2023
117837 | 1969.4 | 4 | 2023-05-12 | 3 | 2023-05-11 | 2023-05-15 |  | X | 753 | 27 | 32 | 1 | 1 | 1B/1T | RONC B115673 | KIT CLEAR 5/11 | SHIPPED 5/15/2023
117374 | 74.3167 | 1 | 2023-05-16 | 10 | 2023-04-28 | ??? 5/12 |  | X | 24 | 19 | 12 | 1 | 0 | 1B |  | KIT CLEAR 4/28 | SHIPPED 5/15/2023
116507 | 2240 | 100 | 2023-05-22 | 10 | 2023-05-03 | 2023-05-17 |  | X | 89 | 7 | 45 | 0 | 1 | 1T | No changes B111571 | KIT CLEAR 5/3 | SHIPPED 5/12
116578 | 1548 | 4 | 2023-05-22 | 10 | 2023-05-02 | 2023-05-16 |  | X | 33 | 43 | 10 | 0 | 1 | 1T | With change B113048 | KIT CLEAR 5/2 | SHIPPED 5/12
116775 | 4064.4 | 60 | 2023-04-18 | 5 | 2023-05-08 | 2023-05-15 |  | X | 150 | 0 | 18 | 0 | 1 | 1T |  | KIT CLEAR 5/8 | SHIPPED 5/12
116048-2BAL | 3429 | 27 | 2023-03-06 | 5 | 2023-05-08 | 2023-05-15 |  | - | 0 | 34 | 0 | 0 | 0 | 0 | Rework B103326 | KIT CLEAR 5/8 | SHIPPED 5/12
117374 | 2155.1833 | 29 | 2023-05-16 | 10 | 2023-04-28 | 2023-05-12 |  | X | 24 | 19 | 12 | 1 | 0 | 1B |  | KIT CLEAR 4/28 | SHIPPED 5/12
117037 | 2417.6 | 30 | 2023-05-10 | 9 | 2023-05-02 | 2023-05-15 |  | X | 167 | 0 | 14 | 1 | 1 | 1B/1T |  | KIT CLEAR 5/2 | SHIPPED 5/11
115642 | 1584.55 | 55 | 2023-05-23 | 10 | 2023-05-01 | 2023-05-15 |  | X | 89 | 13 | 17 | 1 | 1 | 1B/1T |  | KIT CLEAR 5/1 | SHIPPED 5/11
117353 | 5950 | 250 | 2023-05-04 | 20 | 2023-04-14 | 2023-05-12 |  | X | 45 | 10 | 22 | 1 | 1 | 1B/1T | No changes B106348 | KIT CLEAR 4/14 | SHIPPED 5/11
116091-2BAL | 492.72 | 2 | 2023-03-30 | 15 | 2023-05-01 | 2023-05-15 |  | X | 757 | 12 | 66 | 1 | 1 | 1B/2T | No changes B109493 | KIT CLEAR 5/1 | SHIPPED 5/10
117479-1PAR | 550.47 | 143 | 2023-05-11 | 20 | 2023-04-19 | 2023-05-10 |  | X | 23 | 0 | 8 | 0 | 1 | 2T |  | KIT CLEAR 4/19 | SHIPPED 5/10
117354-1PAR | 1030.9286 | 17 | 2023-05-23 | 5 | 2023-05-05 | 2023-05-12 |  | X | 139 | 12 | 63 | 0 | 1 | 2T |  | KIT CLEAR 5/5 | SHIPPED 5/10
115838-1PAR | 28668.09 | 1199 | 2023-04-18 | 20 | 2023-04-11 | 2023-05-09 |  | X | 126 | 4 | 24 | 1 | 1 | 2B/1T | With change B113565 | KIT CLEAR 4/11 | SHIPPED 5/9/2023
117703 | 3198.35 | 59 | 2023-05-01 | 5 | N/C | 2023-05-09 |  | X | 139 | 7 | 48 | 1 | 1 | 1B/1T | With change B114390 | KIT CLEAR 5/2 | SHIPPED 5/9/2023
116107-2 | 6374.9 | 98 | 2023-03-31 | 10 | 2023-04-24 | 2023-05-08 |  | X | 245 | 5 | 91 | 1 | 1 | 1B/2T | No changes from 1st Article | KIT CLEAR 4/24 | SHIPPED 5/8/2023
117299 | 1998.3 | 10 | 2023-05-16 | 10 | 2023-04-24 | 2023-05-08 |  | X | 25 | 16 | 14 | 0 | 1 | 1T |  | KIT CLEAR 4/24 | SHIPPED 5/5/2023
113364 | 2186 | 40 | 2023-05-09 | 15 | 2023-04-14 | 2023-05-05 |  | X | 93 | 4 | 45 | 0 | 1 | 1T |  | KIT CLEAR 4/14 | SHIPPED 5/5/2023
114123-3RD | 9250.24 | 16 | 2022-12-12 | 10 | 2023-04-21 | 2023-05-05 |  | X | 1224 | 0 | 48 | 1 | 1 | 1B/1T | With change 2nd Article | KIT CLEAR 4/21 | SHIPPED 5/5/2023
117601 | 4564.8 | 10 | 2023-05-04 | 5 | 2023-05-01 | 5/5 5/8 |  | X | 966 | 9 | 112 | 1 | 1 | 1B/2T |  | KIT CLEAR 5/1 | SHIPPED 5/5/2023
116708 | 2960.5 | 10 | 2023-04-26 | 5 | 2023-04-28 | 2023-05-05 |  | X | 239 | 60 | 32 | 1 | 1 | 1B/1T | With changes B107054 | KIT CLEAR 4/28 | SHIPPED 5/4/2023
116291 | 2231 | 1 | 2023-04-12 | 5 | 2023-04-25 | 5/4 5/2 |  | X | 74 | 7 | 14 | 0 | 1 | 1T |  | KIT CLEAR 4/25 | SHIPPED 5/4/2023
115498 | 5763 | 100 | 2023-02-15 | 10 | 2023-04-20 | 2023-05-04 |  | X | 230 | 19 | 83 | 1 | 0 | 2B |  | KIT CLEAR 4/20 | SHIPPED 5/4/2023
117663-1BAL | 14506.5625 | 305 | 2023-04-28 | 3 | 2023-05-01 | 2023-05-04 |  | X | 50 | 11 | 22 | 0 | 1 | 2T | With change B116340 | KIT CLEAR 5/4 | SHIPPED 5/4/2023
117101 | 1974.7 | 310 | 2023-04-28 | 10 | 2023-04-20 | 2023-05-04 |  | X | 19 | 2 | 14 | 0 | 1 | 1T | No changes B108946 | KIT CLEAR 4/20 | SHIPPED 5/3/2023
116612 | 6625.1 | 96 97 | 2023-04-24 | 20 | 2023-04-05 | 2023-05-03 |  | X | 370 | 2 | 66 | 1 | 1 | 1B/1T | No changes B112316 | KIT CLEAR 4/5 | SHIPPED 5/2/2023
116639 | 5235 | 5 | 2023-04-18 | 5 | 2023-04-25 | 2023-05-02 |  | X | 730 | 17 | 145 | 1 | 1 | 2B/2T |  | KIT CLEAR 4/25 | SHIPPED 5/2/2023
116048-2BAL | 127 | 1 | 2023-03-06 | 5 | N/C | ??? |  | - | 0 | 34 | 0 | 0 | 0 | 0 | Rework B103326 | NO DOC. | SHIPPED 5/1/2023
116493-2 | 1632 | 8 | 2023-03-21 | 3 | 2023-04-26 | 2023-05-01 |  | X | 3 | 0 | 1 | 1 | 1 | 1B/1T | Hand place - Connector with guide pin only | KIT CLEAR 4/26 | SHIPPED 5/1/2023
117091 | 6320.25 | 5 | 2023-04-13 | 5 | 2023-04-24 | 2023-05-01 |  | X | 1173 | 10 | 169 | 1 | 1 | 2B/3T |  | KIT CLEAR 4/24 | SHIPPED 5/1/2023
117663-1PAR | 3567.1875 | 75 | 2023-04-28 | 3 | N/C | 2023-05-01 |  | X | 50 | 11 | 22 | 0 | 1 | 2T | With change B116340 | 4/25 - SMT CLEAR | SHIPPED 5/1/2023
117663-1PAR | 880 | 20 | 2023-04-28 | 3 | N/C | ??? |  | X | 50 | 11 | 22 | 0 | 1 | 2T | With change B116340 | 4/25 - SMT CLEAR | SHIPPED 4/28/2023
116458-2PAR | 2215.8857 | 69 | 2023-04-13 | 10 | 2023-04-17 | 2023-04-28 |  | X | 290 | 1 | 106 | 1 | 1 | 2B/2T | With change B107934 | KIT CLEAR 4/17 | SHIPPED 4/28/2023
100610-5 | 118585 | 187 | 2021-07-12 | 20 | 2023-03-31 | 2023-04-28 |  | X | 3848 | 7 | 237 | 1 | 1 | 2B/3T | Oklahoma/No changes (final build) | KIT CLEAR 3/31 | SHIPPED 4/28/2023
116432-2BAL | 7307.08 | 2 | 2023-03-02 | 3 | 2023-04-21 | 4/28 4/26 |  | X | 2945 | 77 | 147 | 1 | 1 | 1B/2T | With change | KIT CLEAR 4/20 | SHIPPED 4/27/2023
117102 | 6237.2 | 310 | 2023-04-24 | 5 | 2023-04-19 | 2023-04-27 |  | X | 96 | 3 | 38 | 1 | 1 | 2B/2T | No changes B108947 | KIT CLEAR 4/19 | SHIPPED 4/26/2023
114233-2BAL | 3846.4 | 20 | 2023-03-31 | 5 | 2023-04-20 | 2023-04-27 |  | X | 392 | 2 | 91 | 1 | 1 | 1B/1T |  | KIT CLEAR 4/14 | SHIPPED 4/25/2023
116854 | 2750 | 20 | 2023-04-18 | 5 | 2023-04-20 | 2023-04-27 |  | X | 211 | 3 | 69 | 1 | 1 | 1B/1T |  | KIT CLEAR 4/17 | SHIPPED 4/25/2023
116713 | 6248.8 | 120 | 2023-04-28 | 10 | 2023-04-12 | 2023-04-26 |  | X | 117 | 19 | 58 | 1 | 1 | 1B/1T |  | KIT CLEAR 4/12 | SHIPPED 4/25/2023
117099 | 8229.6 | 5 | 2023-04-14 | 5 | 2023-04-18 | 2023-04-25 |  | X | 702 | 3 | 192 | 1 | 1 | 2B/3T |  | KIT CLEAR 4/18 | SHIPPED 4/25/2023
117356 | 2550.75 | 47 | 2023-04-20 | 10 | 2023-04-18 | 2023-05-02 |  | X | 23 | 18 | 11 | 1 | 1 | 1B/1T | No changes B104338 | KIT CLEAR 4/18 | SHIPPED 4/24/2023
116591 | 1892.7 | 30 | 2023-03-30 | 10 | 2023-04-14 | 2023-04-28 |  | X | 123 | 12 | 45 | 0 | 1 | 1T | No changes B109262 | KIT CLEAR 4/14 | SHIPPED 4/21/2023
113840-1PAR | 1075.8333 | 2 | 2023-01-09 | 3 | 2023-04-19 | 2023-04-20 |  | X | 200 | 11 | 15 | 1 | 1 | 1B/1T |  | KIT CLEAR 4/19 | SHIPPED 4/20/2023
117480 | 3484.25 | 5 | 2023-04-19 | 3 | 2023-04-17 | 2023-04-20 |  | X | 418 | 4 | 79 | 0 | 1 | 2T |  | KIT CLEAR 4/17 | SHIPPED 4/19/2023
117199-2 | 1312.5 | 1 | 2023-04-07 | 3 | 2023-04-13 | 4/19 4/18 |  | X | 149 | 3 | 44 | 0 | 1 | 2T | No changes B110751 | KIT CLEAR 4/18 | SHIPPED 4/19/2023
117199-1 | 1312.5 | 29/30 | 2023-04-07 | 3 | 2023-04-13 | 2023-04-18 |  | X | 149 | 3 | 44 | 0 | 1 | 2T | No changes B110751 | KIT CLEAR 4/18 | SHIPPED 4/18/2023
117166 | 4584 | 10 | 2023-04-13 | 5 | 2023-04-11 | 2023-04-18 |  | X | 691 | 55 | 74 | 1 | 1 | 1B/2T |  | KIT CLEAR 4/18 | SHIPPED 4/17/2023
115998 | 7505 | 500 | 2023-04-17 | 10 | 2023-04-03 | 2023-04-17 |  | X | 7 | 0 | 1 | 1 | 0 | 1B | With change B109867 | KIT CLEAR 4/3 | SHIPPED 4/17/2023
116640 | 2450 | 375 | 2023-04-21 | 15 | 2023-03-27 | 2023-04-17 |  | X | 8 | 0 | 7 | 1 | 1 | 1B/1T |  | KIT CLEAR 3/27 | SHIPPED 4/17/2023
117166 | 916.8 | 2 | 2023-04-13 | 5 | 2023-04-11 | 2023-04-18 |  | X | 691 | 55 | 74 | 1 | 1 | 1B/2T |  | KIT CLEAR 4/18 | SHIPPED 4/14/2023
117148 | 2112.5 | 30 | 2023-04-13 | 3 | 2023-04-11 | 2023-04-14 |  | X | 61 | 17 | 33 | 1 | 1 | 1B/1T |  | KIT CLEAR 4/11 | SHIPPED 4/14/2023
116974 | 9624.6 | 90 | 2023-04-14 | 5 | 2023-04-07 | 2023-04-14 |  | X | 470 | 10 | 113 | 1 | 1 | 2B/2T |  | KIT CLEAR 4/7 | SHIPPED 4/14/2023
116863-2BAL | 26086.4 | 200 | 2023-03-29 | 8 | 2023-04-04 | 2023-04-14 |  | X | 444 | 16 | 62 | 1 | 1 | 1B/2T | No changes B113064 | KIT CLEAR 4/4 | SHIPPED 4/14/2023
117173 | 3401 | 50 | 2023-04-13 | 5 | 2023-04-06 | 2023-04-13 |  | X | 205 | 2 | 53 | 1 | 1 | 1B/1T |  | KIT CLEAR 4/6 | SHIPPED 4/13/2023
116863-1PAR | 6521.6 | 50 | 2023-03-29 | 8 | 2023-04-04 | 2023-04-14 |  | X | 444 | 16 | 62 | 1 | 1 | 1B/2T | No changes B113064 | KIT CLEAR 4/4 | SHIPPED 4/12/2023
117116 | 4722.5 | 10 | 2023-04-13 | 5 | 2023-04-07 | 2023-04-14 |  | X | 528 | 49 | 145 | 1 | 1 | 2B/2T |  | KIT CLEAR 4/7 | SHIPPED 4/12/2023
117150 | 2645.1 | 45 | 2023-04-13 | 5 | 2023-04-06 | 2023-04-13 |  | X | 109 | 13 | 40 | 1 | 1 | 1B/1T |  | KIT CLEAR 4/6 | SHIPPED 4/12/2023
116995 | 4152.25 | 15 | 2023-04-13 | 5 | 2023-04-05 | 2023-04-12 |  | X | 614 | 12 | 65 | 1 | 1 | 1B/1T |  | KIT CLEAR 4/5 | SHIPPED 4/12/2023
100605-7 | 78731.25 | 221 | 2021-09-17 | 20 | 2023-03-08 | 4/12 4/5 |  | X | 2894 | 4 | 205 | 1 | 1 | 2B/2T | Oklahoma/No changes (final build) | KIT CLEAR 3/8 | SHIPPED 4/11/2023
116503 | 3790 | 10 | 2023-04-18 | 15 | 2023-03-23 | 2023-04-13 |  | X | 542 | 57 | 104 | 0 | 1 | 2T |  | KIT CLEAR 3/23 | SHIPPED 4/10/2023
115999 | 11800 | 500 | 2023-03-28 | 10 | 2023-03-21 | 4/10 4/7 4/4 |  | X | 9 | 0 | 5 | 1 | 1 | 1B/1T | No changes B109868 | KIT CLEAR 3/21 | SHIPPED 4/10/2023
114417 | 2024 | 25 | 2023-03-03 | 20 | 2023-03-14 | 2023-04-11 |  | X | 82 | 12 | 33 | 1 | 1 | 1B/1T |  | KIT CLEAR 3/14 | SHIPPED 4/7/2023
116350-1 | 13344.6 | 1 | 2023-03-29 | 5 | 2023-04-04 | 2023-04-07 |  | X | 903 | 72 | 146 | 1 | 1 | 1B/2T |  | KIT CLEAR 4/4 | SHIPPED 4/7/2023
114233-1PAR | 5769.6 | 40 | 2023-03-31 | 5 | 2023-03-31 | 2023-04-07 |  | X | 392 | 2 | 91 | 1 | 1 | 1B/1T |  | KIT CLEAR 3/31 | SHIPPED 4/7/2023
116221 | 1500 | 49 | 2023-04-03 | 5 | 2023-03-31 | 2023-04-07 |  | - |  | 4 |  |  |  |  | PAID RWK | NO DOC. | SHIPPED 4/6/2023
116493-1 | 1140 | 2 | 2023-03-21 | 5 | 2023-04-03 | 2023-04-10 |  | X | 3 | 0 | 1 | 1 | 1 | 1B/1T |  | KIT CLEAR 4/3 | SHIPPED 4/5/2023
116047 | 7532.78 | 3 | 2023-03-02 | 5 | 2023-03-29 | 2023-04-05 |  | XR | 1199 | 9 | 184 | 1 | 1 | 2B/2T |  | KIT CLEAR 3/29 | SHIPPED 4/5/2023
116458-1 | 2248 | 30 | 2023-04-13 | 10 | 2023-03-22 | 2023-04-05 |  | X | 290 | 1 | 106 | 1 | 1 | 2B/2T | With change B107934 | KIT CLEAR 3/22 | SHIPPED 4/5/2023
116984 | 2838 | 4 | 2023-04-04 | 3 | 2023-03-31 | 2023-04-05 |  | X | 186 | 47 | 56 | 0 | 1 | 1T |  | KIT CLEAR 3/31 | SHIPPED 4/5/2023
116877 | 2310 | 250 | 2023-03-27 | 5 | 2023-03-29 | 2023-04-05 |  | X | 14 | 2 | 7 | 1 | 1 | 1B/1T |  | KIT CLEAR 3/30 | SHIPPED 4/5/2023
114946-1PAR2 | 20868.75 | 795 | 2023-02-22 | 20 | 2023-03-08 | 2023-04-05 |  | X | 155 | 3 | 30 | 1 | 1 | 2B/2T |  | KIT CLEAR 3/8 | SHIPPED 4/5/2023
107990 | 5310 | 1000 | 2023-03-29 | 15 | 2023-03-14 | 2023-04-04 |  | X | 29 | 0 | 28 | 1 | 1 | 1B/1T |  | KIT CLEAR 3/14 | SHIPPED 4/4/2023
115701 | 3375 | 50 | 2023-03-28 | 10 | 2023-03-21 | 2023-04-04 |  | X | 150 | 30 | 39 | 0 | 1 | 1T | With change B108135 | KIT CLEAR 3/21 | SHIPPED 4/3/2023
116516 | 6000 | 10 | 2023-03-28 | 10 | 2023-03-20 | 2023-04-03 |  | X | 554 | 2 | 44 | 1 | 1 | 1B/1T |  | KIT CLEAR 3/20 | SHIPPED 4/3/2023
116048-2PAR | 127 | 1 | 2023-03-06 | 5 | 2023-03-24 | 2023-03-31 |  | - | 0 | 34 | 0 | 0 | 0 | 0 | Rework B103326 | NO DOC. | SHIPPED 3/31/2023
112908 | 10586 | 10 | 2022-12-19 | 10 | 2023-03-17 | 2023-03-31 |  | X | 753 | 31 | 104 | 1 | 1 | 1B/2T |  | KIT CLEAR 3/17 | SHIPPED 3/31/2023
116743 | 2715.5 | 2 | 2023-03-30 | 5 | 2023-03-24 | 2023-03-31 |  | X | 386 | 91 | 39 | 1 | 1 | 1B/1T | Pre-bake boards min 48 hours | KIT CLEAR 3/24 | SHIPPED 3/30/2023
116744 | 2715.5 | 2 | 2023-03-23 | 5 | 2023-03-24 | 2023-03-31 |  | X | 386 | 91 | 39 | 1 | 1 | 1B/1T | Pre-bake boards min 48 hours | KIT CLEAR 3/24 | SHIPPED 3/30/2023
115113 | 3650 | 10 | 2023-02-20 | 3 | 2023-03-27 | 2023-03-30 |  | X | 2 | 0 | 2 | 1 | 1 | 1B/1T |  | KIT CLEAR 3/27 | SHIPPED 3/30/2023
116927 | 400 | 2 | 2023-03-28 | 5 | N/C | 2023-03-30 |  | - | [6 empty] | REWORK B101206 | NO DOC. | SHIPPED 3/30/2023
116107-1 | 1238 | 2 | 2023-03-31 | 5 | 2023-03-23 | 2023-03-30 |  | X | 245 | 5 | 91 | 1 | 1 | 1B/2T |  | KIT CLEAR 3/23 | SHIPPED 3/30/2023
117025 | 3840 | 12 | 2023-03-30 | 3 | 2023-03-27 | 2023-03-30 |  | X | 2 | 4 | 1 | 0 | 1 | 1T | No changes B116464 | KIT CLEAR 3/27 | SHIPPED 3/30/2023
116432-1 | 7307.08 | 2 | 2023-03-02 | 3 | 2023-03-24 | 2023-03-30 |  | X | 2945 | 77 | 147 | 1 | 1 | 1B/2T |  | KIT CLEAR 3/24 | SHIPPED 3/30/2023
115913-2 | 5218.56 | 48 | 2023-03-15 | 5 | 2023-03-22 | 2023-03-30 |  | X | 259 | 10 | 65 | 1 | 1 | 1B/1T | With change 1st Article | KIT CLEAR 3/22 | SHIPPED 3/30/2023
116091-1PAR | 1970.88 | 8 | 2023-03-30 | 15 | 2023-03-09 | 2023-03-30 |  | X | 757 | 12 | 66 | 1 | 1 | 1B/2T | No changes B109493 | KIT CLEAR 3/9 | SHIPPED 3/29/2023
116241 | 14505 | 250 | 2023-03-16 | 5 | 2023-03-22 | 2023-03-29 |  | X | 157 | 1 | 50 | 1 | 1 | 1B/2T |  | KIT CLEAR 3/22 | SHIPPED 3/29/2023
115937-RWK | 2450 | 49 | 2023-02-16 | 5 | 2023-03-27 | 2023-03-28 |  | X | 405 | 4 | 104 | 1 | 1 | 1B/1T | PAID RWK | NO DOC. | SHIPPED 3/28/2023
115662 | 6642 | 205 | 2023-03-21 | 5 | 2023-03-21 | 2023-03-28 |  | X | 131 | 5 | 45 | 1 | 1 | 1B/1T |  | KIT CLEARED 3/21 | SHIPPED 3/28/2023
116061 | 1520 | 30 | 2023-03-24 | 10 | 2023-03-15 | 2023-03-29 |  | X | 35 | 25 | 26 | 1 | 1 | 1B/1T | No changes B108919 | KIT CLEAR 3/15 | SHIPPED 3/27/2023
116783 | 3586.5 | 50 | 2023-03-28 | 5 | 2023-03-21 | 2023-03-28 |  | X | 94 | 13 | 29 | 0 | 1 | 1T |  | KIT CLEARED 3/17 | SHIPPED 3/27/2023
116545 | 2327.2 | 24 | 2023-03-28 | 5 | 2023-03-20 | 2023-03-27 |  | X | 141 | 7 | 47 | 1 | 1 | 1B/1T |  | KIT CLEAR 3/20 | SHIPPED 3/27/2023
114820-2 | 675 | 18 | 2023-01-31 | 10 | 2023-03-15 | 2023-03-29 |  | X | 56 | 24 | 26 | 0 | 1 | 1T | No changes 1st Article | KIT CLEAR 3/15 | SHIPPED 3/24/2023
116344 | 3600 | 250 | 2023-03-30 | 5 | 2023-03-20 | 2023-03-27 |  | X | 50 | 0 | 30 | 0 | 1 | 1T |  | KIT CLEAR 3/20 | SHIPPED 3/24/2023
115728 | 3126.45 | 205 | 2023-03-27 | 5 | 2023-03-20 | 2023-03-27 |  | X | 20 | 11 | 9 | 0 | 1 | 1T |  | KIT CLEAR 3/20 | SHIPPED 3/24/2023
116624 | 3279.6 | 4 | 2023-03-13 | 5 | 2023-03-17 | 2023-03-24 |  | X | 282 | 68 | 77 | 0 | 1 | 2T |  | KIT CLEAR 3/17 | SHIPPED 3/24/2023
116391 | 2000 | 20 | 2023-03-06 | 3 | 2023-03-20 | 2023-03-23 |  | X | 174 | 0 | 40 | 1 | 1 | 1B/1T |  | KIT CLEAR 3/20 | SHIPPED 3/23/2023
116605 | 4492.8 | 4 | 2023-03-21 | 3 | 2023-03-21 | 2023-03-24 |  | X | 693 | 5 | 29 | 1 | 1 | 1B/1T |  | KIT CLEAR 3/21 | SHIPPED 3/23/2023
115580 | 2213.8 | 10 | 2023-03-30 | 10 | 2023-03-13 | 2023-03-27 |  | X | 246 | 1 | 59 | 0 | 1 | 1T |  | KIT CLEAR 3/13 | SHIPPED 3/23/2023
116137 | 4240 | 1500 | 2023-03-27 | 5 | 2023-03-17 | 2023-03-24 |  | X | 4 | 0 | 2 | 0 | 1 | 1T | No changes B114452 | KIT CLEARED 3/17 | SHIPPED 3/22/2023
114861 | 8217 | 450 | 2023-02-20 | 5 | 2023-03-16 | 2023-03-23 |  | X | 83 | 0 | 47 | 1 | 1 | 2B/2T | With changes B103335 | KIT CLEAR 3/16 | SHIPPED 3/22/2023
116086-1 | 1096.75 | 10 | 2023-03-23 | 5 | 2023-03-16 | 2023-03-23 |  | X | 250 | 8 | 83 | 0 | 1 | 2T |  | KIT CLEAR 3/16 | SHIPPED 3/22/2023
112967 | 15299 | 200 | 2022-10-24 | 9 | 2022-10-27 | 3/23 11/9/2023 |  | X | 12 | 78 | 7 | 1 | 1 | 1B/1T |  | KIT CLEAR 10/27 | SHIPPED 3/22/2023
115888 | 6670 | 50 | 2023-03-23 | 10 | 2023-03-08 | 2023-03-22 |  | X | 59 | 35 | 28 | 0 | 1 | 1T | With change B112992 | KIT CLEAR 3/8 | SHIPPED 3/22/2023
115929 | 3572.5 | 10 | 2023-02-20 | 5 | 2023-02-27 | 3/21 3/6 |  | X | 563 | 5 | 99 | 1 | 1 | 1B/2T | Hold for new files | KIT CLEAR 3/14 | SHIPPED 3/20/2023
116601 | 3453 | 15 | 2023-03-21 | 5 | 2023-03-13 | 2023-03-20 |  | X | 439 | 0 | 67 | 1 | 1 | 1B/1T |  | KIT CLEAR 3/13 | SHIPPED 3/20/2023
116381 | 2600 | 5 | 2023-03-08 | 5 | 2023-03-13 | 2023-03-20 |  | XR | 482 | 81 | 95 | 0 | 1 |  |  | KIT CLEAR 3/13 | SHIPPED 3/20/2023
107325 | 3014 | 2 | 2023-02-20 | 15 | 2023-02-27 | 2023-03-20 |  | X | 313 | 10 | 131 | 1 | 1 | 1B/2T |  | KIT CLEAR 2/27 | SHIPPED 3/17/2023
116539 | 3575 | 10 | 2023-03-15 | 3 | 2023-03-14 | 2023-03-17 |  | X | 266 | 51 | 77 | 0 | 1 | 2T |  | KIT CLEAR 3/14 | SHIPPED 3/17/2023
115259 | 3572.5 | 25 | 2023-02-13 | 5 | 2023-03-09 | 2023-03-16 |  | X | 315 | 8 | 117 | 1 | 1 | 2B/1T |  | KIT CLEAR 3/9 | SHIPPED 3/17/2023
115476-2 | 2262 | 40 | 2023-02-24 | 10 | 2023-03-03 | 2023-03-17 |  | X | 200 | 3 | 68 | 1 | 1 | 1B/1T | No changes from 1st Article | KIT CLEAR 3/3 | SHIPPED 3/16/2023
116602 | 2382.5 | 5 | 2023-03-17 | 3 | 2023-03-13 | 2023-03-16 |  | X | 489 | 0 | 96 | 1 | 1 | 1B/2T |  | KIT CLEAR 3/13 | SHIPPED 3/16/2023
116268 | 7441.6 | 40 | 2023-03-07 | 5 | 2023-03-09 | 2023-03-16 |  | X | 750 | 5 | 142 | 1 | 1 | 2B/2T |  | KIT CLEAR 3/9 | SHIPPED 3/16/2023
114946-1PAR | 14173.71 | 105 | 2023-02-22 | 20 | 2023-03-08 | 2023-03-16 |  | X | 155 | 3 | 30 | 1 | 1 | 2B/2T | PAID EXPEDITE | KIT CLEAR 3/8 | SHIPPED 3/16/2023
116221 | 2250 | 50 | 2023-03-07 | 10 | 2023-03-02 | 2023-03-16 |  | - | 0 | 31 | 0 | 0 | 0 | 0 | THT only | KIT CLEAR 3/2 | SHIPPED 3/15/2023
116240 | 5388 | 6 | 2023-03-06 | 7 | 2023-03-06 | 2023-03-15 |  | X | 798 | 101 | 162 | 1 | 1 | 1B/2T |  | KIT CLEAR 3/6 | SHIPPED 3/15/2023
115975 | 3537.7 | 115 | 2023-03-13 | 10 | 2023-03-01 | 2023-03-15 |  | X | 86 | 16 | 17 | 1 | 1 | 1B/1T |  | KIT CLEAR 3/2 | SHIPPED 3/15/2023
116340 | 17600 | 400 | 2023-03-08 | 3 | 2023-03-14 | 2023-03-15 |  | X | 50 | 11 | 22 | 0 | 1 | 2T | With change B114404 | KIT CLEAR 3/14 | SHIPPED 3/15/2023
116084-2 | 1980 | 200 | 2023-03-02 | 5 | 2023-03-09 | 2023-03-16 |  | X | 22 | 0 | 10 | 1 | 1 | 1B/1T | No changes 1st Article | KIT CLEAR 3/9 | SHIPPED 3/14/2023
109882-2BAL | 418.0978 | 2 | 2022-08-15 | 5 | 2023-01-25 | 2/17 2/3* |  | X | 650 | 82 | 95 | 0 | 1 | 2T | New gerber/BOM/XY from 1st Article - New program/feeder setup | KIT CLEAR 2/10 | SHIPPED 3/14/2023
113565-2 | 1012.8957 | 720 |  | 5 | 2023-03-07 | 2023-03-14 |  | - | 0 | 1 | 0 | 0 | 0 | 0 | THT ONLY | KIT CLEAR 3/7 | SHIPPED 3/14/2023
116048-1 | 127 | 1 | 2023-03-06 | 5 | 2023-03-06 | 2023-03-13 |  | - | 0 | 34 | 0 | 0 | 0 | 0 | Rework B103326 | KIT CLEAR 3/7 | SHIPPED 3/13/2023
113565-1 | 187.1043 | 133 |  | 5 | 2023-03-06 | 2023-03-13 |  | - | 0 | 1 | 0 | 0 | 0 | 0 | THT ONLY | KIT CLEAR 3/6 | SHIPPED 3/13/2023
115421 | 4754 | 300 | 2023-02-27 | 15 | 2023-02-17 | 3/13H |  | X | 47 | 13 | 24 | 1 | 1 | 1B/1T |  | KIT CLEAR 2/17 | SHIPPED 3/13/2023
116347 | 3000 | 10 | 2023-03-06 | 3 | 2023-03-07 | 2023-03-10 |  | X | 746 | 10 | 53 | 1 | 1 | 1B/1T |  | KIT CLEAR 3/7 | SHIPPED 3/10/2023
116158-2BAL | 7694.8457 | 6 | 2023-02-28 | 5 | 2023-03-07 | 2023-03-10 |  | X | 2069 | 65 | 165 | 1 | 1 | 2B/2T |  | KIT CLEAR 3/7 | SHIPPED 3/10/2023
116474 | 2332.5 | 30 | 2023-03-03 | 3 | 2023-03-07 | 2023-03-10 |  | X | 120 | 14 | 39 | 0 | 1 | 1T |  | KIT CLEAR 3/7 | SHIPPED 3/10/2023
116438 | 4000 | 10 | 2023-03-09 | 3 | 2023-03-07 | 2023-03-10 |  | X | 340 | 43 | 80 | 1 | 1 | 1B/1T |  | KIT CLEAR 3/7 | SHIPPED 3/10/2023
100610-4-2 | 67853.9885 | 107 | 2021-07-12 | 20 | N/C | 3/10 3/8 3/3 2/25H |  | X | 3848 | 7 | 237 | 1 | 1 | 2B/3T | Oklahoma/No changes 3rd Article | KIT CLEAR 12/28 | SHIPPED 3/10/2023
115378 | 2484 | 400 | 2023-03-17 | 10 | 2023-02-24 | 2023-03-10 |  | X | 3 | 0 | 3 | 0 | 1 | 1T | No changes B102423 | KIT CLEAR 2/24 | SHIPPED 3/9/2023
116535 | 2000 | 5 | 2023-03-07 | 3 | 2023-03-06 | 2023-03-09 |  | X | 368 | 3 | 68 | 1 | 1 | 1B/1T |  | KIT CLEAR 3/6 | SHIPPED 3/9/2023
115295 | 2081.25 | 25 | 2023-02-14 | 5 | 2023-03-02 | 2023-03-09 |  | X | 90 | 5 | 49 | 1 | 1 | 1B/1T |  | KIT CLEAR 3/2 | SHIPPED 3/9/2023
116452 | 7567.25 | 15 | 2023-03-10 | 3 | 2023-03-06 | 2023-03-09 |  | X | 57 | 69 | 5 | 1 | 1 | 1B/1T |  | KIT CLEAR 3/6 | SHIPPED 3/9/2023
116158-1PAR | 2996.76 | 1 | 2023-02-28 | 5 | 2023-03-07 | 2023-03-08 |  | X | 2069 | 65 | 165 | 1 | 1 | 2B/2T |  | KIT CLEAR 3/7 | SHIPPED 3/8/2023
115052 | 5206 | 100 |  | 15 | 2023-02-14 | 3/8H |  | X | 157 | 35 | 27 |  |  | 1B 1T |  | KIT CLEAR 2/15 | SHIPPED 3/8/2023
116106 | 6574 | 100 | 2023-03-09 | 10 | 2023-02-22 | 2023-03-08 |  | X | 245 | 34 | 42 | 1 | 1 | 1B/1T | With change B111701 | KIT CLEAR 2/22 | SHIPPED 3/8/2023
114812-6 | 5642 | 50 | 2022-01-10 | 10 | 2022-12-22 | 2/28 2/22 *1/9H | BOT DONE | X | 554 | 16 | 92 | 1 | 1 | 1B/2T | QTY 50 expedited. Can build all 195 at once. | KIT CLEAR 1/20 | SHIPPED 3/7/2023
112356 | 6313 | 380 | 2022-10-24 | 10 | 2023-02-21 | 2023-03-07 |  | X | 71 | 0 | 39 | 1 | 1 | 1B/1T | No changes B110797 | KIT CLEAR 2/21 | SHIPPED 3/7/2023
115825 | 2100 | 70 | 2023-03-08 | 10 | 2023-02-21 | 2023-03-07 |  | - | 0 | 1 | 0 | 0 | 0 | 0 | THT only/No change B110095 | KIT CLEAR 2/21 | SHIPPED 3/7/2023
115661 | 6000 | 20 | 2023-02-10 | 5 | 2023-02-28 | 2023-03-07 |  | X | 703 | 47 | 35 | 0 | 1 | 1T |  | KIT CLEAR 2/28 | SHIPPED 3/7/2023
115913-1 | 2995 | 2 | 2023-03-15 | 5 | 2023-02-27 | 2023-03-06 |  | X | 256 | 10 | 65 | 1 | 1 | 1B/1T |  | KIT CLEAR 2/27 | SHIPPED 3/6/2023
115294 | 3790 | 50 | 2023-02-13 | 5 | 2023-02-28 | 2023-03-06 |  | X | 201 | 8 | 80 | 1 | 1 | 1B/1T |  | KIT CLEAR 2/24 | SHIPPED 3/6/2023
115691 | 3381 | 49 | 2023-02-13 | 10 | 2023-02-07 | 2/24 2/22 |  | - | 0 | 50 | 0 | 0 | 0 |  | THT only | KIT CLEAR 2/7 | SHIPPED 3/6/2023
106348 | 8460 | 400 | 2023-02-24 | 10 | 2023-02-16 | 3/3H |  | X | 45 | 10 | 22 | 1 | 1 | 1B/1T | No changes B101205 | KIT CLEAR 2/10 | SHIPPED 3/6/2023
116464 | 1752 | 4 | 2023-03-01 | 3 | 2023-02-28 | 2023-03-03 |  | X | 2 | 4 | 1 | 0 | 1 | 1T | No changes B115328 | KIT CLEAR 2/28 | SHIPPED 3/3/2023
116136 | 2581 | 5 | 2023-03-09 | 5 | 2023-02-24 | 2023-03-03 |  | X | 484 | 5 | 53 | 1 | 1 | 1B/1T |  | KIT CLEAR 2/24 | SHIPPED 3/3/2023
115908 | 4724 | 50 | 2023-02-01 | 5 | 2023-02-24 | 2023-03-03 |  | X | 308 | 2 | 79 | 1 | 1 | 1B/1T |  | KIT CLEAR 2/24 | SHIPPED 3/3/2023
115822 | 3356 | 7 | 2023-03-02 | 5 | 2023-02-24 | 2023-03-03 |  | X | 136 | 71 | 23 | 0 | 1 | 1T |  | KIT CLEAR 2/24 | SHIPPED 3/3/2023
114906-2 | 86.56 | 1 | 2023-01-19 | 5 | 2023-02-21 | 2023-02-28 |  | X | 183 | 11 | 80 | 1 | 1 | 1B/2T | No changes 1st Article | KIT CLEAR 2/17 | SHIPPED 3/3/2023
115651 | 3499.76 | 32 | 2023-02-14 | 5 | 2023-02-23 | 2023-03-02 |  | X | 332 | 0 | 58 | 1 | 1 | 1B/1T |  | KIT CLEAR 2/23 | SHIPPED 3/2/2023
114305 | 5931.2 | 80 | 2023-02-21 | 10 | 2023-02-15 | 3/2H |  | X | 341 | 11 | 106 | 1 | 1 | 1B/2T | No changes B108431 | KIT CLEAR 2/15 | SHIPPED 3/2/2023
115589 | 10215 | 300 |  | 10 | 2023-02-15 | 3/2H |  | X | 190 | 8 | 84 |  |  | 2T | RONC B109853 | KIT CLEAR 2/15 | SHIPPED 3/2/2023
114812-5 | 2821 | 25 | 2022-01-10 | 10 | 2022-12-22 | 2/28 2/22 *1/9H | BOT DONE | X | 554 | 16 | 92 | 1 | 1 | 1B/2T | QTY 50 expedited. Can build all 195 at once. | KIT CLEAR 1/20 | SHIPPED 3/2/2023
116084-1 | 1850 | 40 | 2023-03-02 | 5 | 2023-02-22 | 2023-03-01 |  | X | 22 | 0 | 10 | 1 | 1 | 1B/1T |  | KIT CLEAR 2/22 | SHIPPED 3/1/2023
116311 | 5469.2 | 4 | 2023-03-01 | 3 | 2023-02-24 | 2023-03-01 |  | X | 858 | 5 | 27 | 1 | 1 | 1B/1T |  | KIT CLEAR 2/24 | SHIPPED 3/1/2023
116156 | 5013.2 | 10 | 2023-02-28 | 3 | 2023-02-24 | 2023-03-01 |  | X | 266 | 38 | 95 | 1 | 1 | 1B/1T |  | KIT CLEAR 2/24 | SHIPPED 3/1/2023
115909 | 4929 | 50 | 2023-02-09 | 5 | 2023-02-22 | 2023-03-01 |  | X | 315 | 9 | 81 | 1 | 1 | 1B/2T |  | KIT CLEAR 2/22 | SHIPPED 3/1/2023
113565-2 | 39.86 | 2 | 2022-12-23 | 20 | 2023-01-17 | 2/17 2/14 |  | X | 127 | 4 | 25 | 1 | 1 | 2B/1T | With change B108218 - Robert | KIT CLEAR 1/17 | SHIPPED 3/1/2023
103336-2BAL | 300.3 | 7 | 2021-09-08 | 10 | 2023-02-10 | 2/27H |  | X | 230 | 2 | 70 | 1 | 1 | 2B/2T | ROWC B98649 | KIT CLEAR 2/10 | SHIPPED 3/1/2023
114906-2 | 4241.44 | 49 | 2023-01-19 | 5 | 2023-02-21 | 2023-02-28 |  | X | 183 | 11 | 80 | 1 | 1 | 1B/2T | No changes 1st Article | KIT CLEAR 2/17 | SHIPPED 2/28/2023
100610-4-1 | 50731.2 | 80 | 2021-07-12 | 20 | N/C | 2/28 2/25H |  | X | 3848 | 7 | 237 | 1 | 1 | 2B/3T | Oklahoma/No changes 3rd Article | KIT CLEAR 12/28 | SHIPPED 2/28/2023
113665-8 | 12612 | 50 | 2022-11-04 | 5 | 2022-10-17 | 2022-02-28 |  | X | 444 | 16 | 62 | 1 | 1 | 1B/2T | No changes B113064 | KIT CLEAR QTY 400 PARTIAL | SHIPPED 2/28/2023
116017 | 7574.96 | 31 | 2023-02-16 | 5 | 2023-02-21 | 2023-02-28 |  | X | 897 | 43 | 110 | 1 | 1 | 1B/2T |  | KIT CLEAR 2/21 | SHIPPED 2/28/2023
103336-2PAR | 6177.6 | 144 | 2021-09-08 | 10 | 2023-02-10 | 2/27H |  | X | 230 | 2 | 70 | 1 | 1 | 2B/2T | ROWC B98649 | KIT CLEAR 2/10 | SHIPPED 2/27/2023
115393 | 2373.6 | 30 | 2023-02-23 | 10 | 2023-02-10 | 2/27H |  | X | 110 | 34 | 41 | 0 | 1 | 1T |  | KIT CLEAR 2/10 | SHIPPED 2/27/2023
115574 | 1999.4 | 450 | 2023-02-23 | 20 | 2023-01-26 | 2/24H |  | X | 188 | 0 | 60 | 1 | 1 | 2B/2T | No changes B101523 | KIT CLEAR 1/26 | SHIPPED 2/24/2023
115362 | 4638.5 | 50 | 2023-02-03 | 5 | 2023-02-16 | 2/24H |  | X | 283 | 17 | 113 | 1 | 1 | 1B/2T |  | KIT CLEAR 2/16 | SHIPPED 2/24/2023
114820-1 | 1328 | 2 | 2023-01-31 | 5 | 2023-02-23 | 2023-03-02 |  | X | 56 | 24 | 26 | 0 | 1 | 1T |  | KIT CLEAR 2/23 | SHIPPED 2/24/2023
115434 | 3196.35 | 3 | 2023-01-26 | 3 | 2023-02-16 | 2/27H |  | X | 234 | 12 | 72 | 1 | 1 | 1B/1T |  | KIT CLEAR 2/17 | SHIPPED 2/23/2023
115493-2 | 5860 | 80 | 2023-02-16 | 5 | 2023-02-15 | 2/23H |  | X | 114 | 20 | 57 | 1 | 1 | 1B 1T | QTY 40 expedited to ship 2/21 (can run all 120 at once) - No changes B114521 | KIT CLEAR 2/15 | SHIPPED 2/23/2023
104338 | 2249.3 | 47 | 2023-02-07 | 10 | 2023-02-09 | 2/24H |  | X | 23 | 18 | 11 | 1 | 1 | 1B/1T |  | KIT CLEAR 2/9 | SHIPPED 2/23/2023
113151-3BAL | 60.02 | 1 | 2022-12-19 | 9 | 2022-12-14 | 2/3 12/28 |  | X | 350 | 6 | 37 | 1 | 1 | 2B/2T | With change B99149 | KIT CLEAR 12/15 | SHIPPED 2/22/2023
115435 | 1485 | 50 | 2023-02-09 | 10 | 2023-02-08 | 2/23H |  | X | 54 | 0 | 40 | 1 | 1 | 1B/1T | No changes B110659 | KIT CLEAR 2/8 | SHIPPED 2/22/2023
114215-2 | 14654.72 | 22 | 2022-12-23 | 5 | 2023-02-13 | 2/21H |  | X | 1304 | 0 | 122 | 1 | 1 | 2B/1T | No changes 1st Article | KIT CLEAR 2/13 | SHIPPED 2/21/2023
114506 | 3591.3 | 10 | 2023-02-08 | 7 | 2023-02-09 | 2/21H |  | X | 643 | 1 | 126 | 1 | 1 | 2B/2T |  | KIT CLEAR 2/8 | SHIPPED 2/21/2023
115493-1 | 5860 | 40 | 2023-02-16 | 5 | 2023-02-15 | 2023-02-21 |  | X | 114 | 20 | 57 | 1 | 1 | 1B 1T | QTY 40 expedited to ship 2/21 (can run all 120 at once) - No changes B114521 | KIT CLEAR 2/15 - PAID EXPEDITE 2/17 | SHIPPED 2/21/2023
115881 | 4920.2 | 4 | 2023-02-17 | 5 | 2023-02-13 | 2/21H |  | X | 990 | 15 | 137 | 1 | 1 | 2B/2T |  | KIT CLEAR 2/13 | SHIPPED 2/21/2023
100605-6 | 78731.25 | 221 | 2021-09-17 | 20 | N/C | 2/21 2/15 |  | X | 2894 | 4 | 205 | 1 | 1 | 2B/2T | Oklahoma/No changes 3rd Article | KIT CLEAR 1/5 | SHIPPED 2/21/2023
116122-RWK |  | 37/50 | 2023-02-22 | 1 | N/C | 2023-02-17 |  | X | 1 | 1 | 1 | 0 | 1 | 1T | PAID RWK | DOC REL 2/10
116121-RWK |  | 40/50 | 2023-02-22 | 1 | N/C | 2023-02-17 |  | X | 1 | 1 | 1 | 0 | 1 | 1T | PAID RWK | DOC REL 2/10
116121 | 9300 | 50 | 2023-02-22 | 1 | N/C | 2023-02-17 |  | X | 1 | 1 | 1 | 0 | 1 | 1T |  | KIT CLEAR 2/15 | SHIPPED 2/17/2023
116122 | 9300 | 50 | 2023-02-22 | 1 | N/C | 2023-02-17 |  | X | 1 | 1 | 1 | 0 | 1 | 1T |  | KIT CLEAR 2/15 | SHIPPED 2/17/2023
115937 | 5431.5 | 50 | 2023-02-16 | 5 | 2023-02-10 | 2023-02-17 |  | X | 405 | 4 | 104 | 1 | 1 | 1B/1T |  | KIT CLEAR 2/10 | SHIPPED 2/17/2023
115735 | 7020 | 250 | 2023-02-15 | 5 | 2023-02-10 | 2023-02-17 |  | X | 117 | 4 | 38 | 1 | 1 | 1B/1T |  | KIT CLEAR 2/10 | SHIPPED 2/17/2023
113565-2 | 20089.44 | 1008 | 2022-12-23 | 20 | 2023-01-17 | 2/17 2/14 |  | X | 127 | 4 | 25 | 1 | 1 | 2B/1T | With change B108218 - Robert | KIT CLEAR 1/17 | SHIPPED 2/17/2023
109882-2PAR | 14633.4222 | 70 | 2022-08-15 | 5 | 2023-01-25 | 2/17 2/3* |  | X | 650 | 82 | 95 | 0 | 1 | 2T | New gerber/BOM/XY from 1st Article - New program/feeder setup | KIT CLEAR 2/10 | SHIPPED 2/17/2023
114812-4 | 641.131 | 5 | 2022-01-10 | 10 | 2022-12-22 | 2/22 *1/9H | BOT DONE | X | 554 | 16 | 92 | 1 | 1 | 1B/2T | QTY 50 expedited. Can build all 195 at once. | KIT CLEAR 1/20 | SHIPPED 2/16/2023
115983 | 4881 | 10 | 2023-02-15 | 3 | 2023-02-14 | 2023-02-17 |  | X | 234 | 75 | 59 | 1 | 1 | 1B/1T |  | KIT CLEAR 2/14 | SHIPPED 2/16/2023
115046 | 4412.8 | 60 |  | 9 | 2023-02-03 | 2023-02-16 |  | X | 304 | 1 | 61 | 1 | 1 | 1B/1T |  | KIT CLEAR 2/3 | SHIPPED 2/16/2023
113997 | 1999.4 | 260 | 2023-02-07 | 10 | 2023-02-03 | 2023-02-17 |  | X | 19 | 2 | 14 | 0 | 1 | 1T | No changes B108946 | KIT CLEAR 2/3 | SHIPPED 2/14/2023
111418 | 2297.88 | 6 | 2022-09-01 | 10 | 2023-02-02 | 2023-02-16 |  | X | 578 | 31 | 68 | 1 | 1 | 1B/1T | With change B104121 | KIT CLEAR 2/2 | SHIPPED 2/14/2023
115375 | 3340 | 400 |  | 5 | 2023-02-07 | 2023-02-14 |  | X | 7 | 0 | 3 |  |  | 1T | RONC B108466 | KIT CLEAR 2/7 | SHIPPED 2/14/2023
115530 | 2022.5 | 125 | 2023-02-03 | 3 | 2023-02-09 | 2023-02-14 |  | X | 5 | 2 | 3 | 0 | 1 | 1T |  | KIT CLEAR 2/9 | SHIPPED 2/13/2023
115874 | 4556 | 200 | 2023-02-15 | 3 | 2023-02-09 | 2023-02-14 |  | X | 34 | 4 | 15 | 0 | 1 | 1T | No changes B114821 | KIT CLEAR 2/9 | SHIPPED 2/13/2023
107474 | 1822 | 20 | 2022-12-21 | 10 | 2023-01-30 | 2023-02-13 |  | X | 33 | 5 | 7 | 1 | 1 | 1B/1T |  | KIT CLEAR 1/30 | SHIPPED 2/13/2023
114812-3 | 2564.524 | 15 | 2022-01-10 | 10 | 2022-12-22 | 2/13 2/15 *1/9H |  | X | 554 | 16 | 92 | 1 | 1 | 1B/2T | QTY 50 expedited. Can build all 195 at once. | PARTIAL CLEAR 12/22 | SHIPPED 2/13/2023
115159 | 3401.5 | 50 | 2023-02-21 | 10 | 2023-01-27 | 2023-02-10 |  | X | 196 | 19 | 57 | 1 | 1 | 1B/1T |  | KIT CLEAR 1/27 | SHIPPED 2/10/2023
115476-1 | 2136 | 10 | 2023-02-24 | 5 | 2023-02-03 | 2023-02-10 |  | X | 200 | 3 | 68 | 1 | 1 | 1B/1T |  | KIT CLEAR 2/3 | SHIPPED 2/10/2023
115487 | 4200 | 350 | 2023-02-15 | 15 | 2023-01-25 | 2023-02-15 |  | - | [6 empty] | REWORK B110198 | NO DOC. | SHIPPED 2/9/2023
115497-2BAL | 1204 | 56 | 2023-02-08 | 5 | 2023-02-07 | 2023-02-14 |  | - | 0 | 1 | 0 | 0 | 0 |  | THT only/No changes B108347 | KIT CLEAR 2/7 | SHIPPED 2/9/2023
115600 | 4218.7 | 2 | 2023-01-24 | 3 | 2023-02-06 | 2023-02-09 |  | X | 838 | 6 | 104 | 1 | 1 | 1B/2T |  | KIT CLEAR 2/6 | SHIPPED 2/9/2023
114958 | 8536.5 | 350 | 2023-02-03 | 15 | 2023-01-18 | 2023-02-08 |  | X | 107 | 5 | 42 | 0 | 2 | 2T | ROWC B104911 | KIT CLEAR 1/18 | SHIPPED 2/8/2023
114307-2 | 5571.06 | 22 | 2022-01-04 | 10 | 2023-01-25 | 2023-02-08 |  | X | 1101 | 0 | 43 | 1 | 1 | 1B/1T | No changes 1st Article | KIT CLEAR 1/25 | SHIPPED 2/8/2023
115522 | 4177.6 | 20 | 2023-02-03 | 5 | 2023-01-31 | 2023-02-07 |  | X | 461 | 26 | 71 | 0 | 1 | 2T |  | KIT CLEAR 1/31 | SHIPPED 2/7/2023
114911 | 2848.8 | 30 | 2023-02-08 | 10 | 2023-01-27 | 2023-02-10 |  | X | 393 | 10 | 65 | 0 | 1 | 2T | No change B107257 | KIT CLEAR 1/27 | SHIPPED 2/7/2023
115497-1 | 408.5 | 19 | 2023-02-08 | 5 | 2023-02-01 | 2023-02-08 |  | - | 0 | 1 | 0 | 0 | 0 |  | THT only/No changes B108347 | KIT CLEAR 2/1 | SHIPPED 2/6/2023
114887 | 2667.6 | 3 | 2023-02-06 | 5 | 2023-01-31 | 2023-02-07 |  | X | 511 | 52 | 57 | 1 | 1 | 1B/1T |  | KIT CLEAR 1/31 | SHIPPED 2/6/2023
113908 | 4760 | 5 | 2023-01-13 | 5 | 2023-01-30 | 2023-02-06 |  | X | 846 | 5 | 185 | 1 | 1 | 2B/2T | New gerber/Program updated 1/11 | KIT CLEAR 1/30 | SHIPPED 2/3/2023
115199 | 550 | 40 | 2023-02-21 | 10 | 2023-01-20 | 2023-02-03 |  | - | [6 empty] | PAID RWK | NO DOC. | SHIPPED 2/3/2023
113151-2PAR | 3901.3 | 65 | 2022-12-19 | 9 | 2022-12-14 | 2/3 12/28 |  | X | 350 | 6 | 37 | 1 | 1 | 2B/2T | With change B99149 | KIT CLEAR 12/15 | SHIPPED 2/3/2023
115422 | 15277.9 | 14 | 2023-02-01 | 5 | 2023-01-26 | 2023-02-02 |  | X | 1443 | 12 | 202 | 1 | 1 | 2B/2T |  | KIT CLEAR 1/26 | SHIPPED 2/2/2023
115380 | 1495 | 10 | 2023-02-08 | 10 | 2023-01-25 | 2023-02-08 |  | X | 26 | 0 | 5 | 0 | 1 | 1T | No change B112985 | KIT CLEAR 1/25 | SHIPPED 2/1/2023
114124-2 | 15226.64 | 22 | 2023-12-23 | 3 | 2023-01-26 | 2023-02-01 |  | X | 1331 | 0 | 101 | 1 | 1 | 1B/1T | No changes 1st Article | KIT CLEAR 1/26 | SHIPPED 2/1/2023
114812-2 | 3726 | 20 | 2022-01-10 | 5 | 2022-12-20 | 1/4 12/28H |  | X | 554 | 16 | 92 | 1 | 1 | 1B/2T | QTY 50 expedited. Can build all 195 at once. | KIT CLEAR 12/20 | SHIPPED 1/31/2023
100606-7 | 50425.7 | 79 | 2021-08-24 | 20 | N/C | 2023-01-31 |  | X | 3734 | 17 | 238 | 1 | 1 | 2B/3T | Oklahoma/No changes 3rd Article | KIT CLEAR 12/19 | SHIPPED 1/31/2023
113565-1 | 26709.7 | 1290 | 2022-12-23 | 20 | N/C | 1/31 1/25 |  | X | 127 | 4 | 25 | 1 | 1 | 2B/1T | With change B108218 - Robert | SHORT 4 ITEMS | SHIPPED 1/31/2023
114813-2 | 99876 | 145 | 2022-01-17 | 10 | 2022-12-21 | 1/6H |  | X | 1117 | 6 | 144 | 1 | 1 | 2B/2T | QTY 50 expedited. Can build all 195 at once. | KIT CLEAR 12/21 | SHIPPED 1/30/2023
115298 | 3958 | 200 | 2023-02-01 | 5 | 2023-01-24 | 2023-01-31 |  | X | 45 | 10 | 39 | 1 | 1 | 1B/1T |  | KIT CLEAR 1/24 | SHIPPED 1/30/2023
113665-7 | 12612 | 100/50 | 2022-11-04 | 5 | 2022-10-17 | 1/31 2/8 |  | X | 444 | 16 | 62 | 1 | 1 | 1B/2T | No changes B113064 | KIT CLEAR QTY 400 PARTIAL | SHIPPED 1/30/2023
115673 | 3369.2 | 4 | 2023-01-30 | 3 | 2023-01-25 | 2023-01-30 |  | X | 753 | 27 | 32 | 1 | 1 | 1B/1T |  | KIT CLEAR 1/25 | SHIPPED 1/30/2023
114955 | 3993.52 | 32 | 2023-02-01 | 10 | 2023-01-17 | 2023-01-31 |  | X | 307 | 5 | 65 | 1 | 1 | 1B/1T |  | KIT CLEAR 1/17 | SHIPPED 1/27/2023
115173 | 4634.8 | 10 | 2023-01-30 | 10 | 2023-01-16 | 2023-01-30 |  | X | 1204 | 23 | 106 | 1 | 1 | 1B/2T |  | DOC REL 1/3 | SHIPPED 1/26/2023
115289 | 3810 | 2 | 2023-01-23 | 5 | 2023-01-23 | 2023-01-30 |  | X | 560 | 44 | 46 | 0 | 1 | 1T |  | KIT CLEAR 1/23 | SHIPPED 1/26/2023
114922 | 6484.75 | 3 | 2023-01-11 | 3 | 2023-01-23 | 2023-01-25 |  | X | 1288 | 11 | 149 | 1 | 1 | 2B/2T |  | KIT CLEAR 1/19* | SHIPPED 1/25/2023
114906-1 | 3428 | 50 | 2023-01-19 | 5 | 2023-01-18 | 2023-01-25 |  | X | 183 | 11 | 80 | 1 | 1 | 1B/2T |  | KIT CLEAR 1/18 | SHIPPED 1/25/2023
115423 | 2033.2 | 140 | 2023-01-23 | 3 | 2023-01-20 | 2023-01-25 |  | X | 8 | 3 | 5 | 0 | 1 | 1T |  | KIT CLEAR 1/20 | SHIPPED 1/24/2023
114874 | 1682.5 | 50 | 2022-01-27 | 15 | 2023-01-03 | 2023-01-24 |  | X | 97 | 16 | 47 | 1 | 1 | 1B/1T | With change B107127 | KIT CLEAR 1/3 | SHIPPED 1/24/2023
110201 | 4192 | 200 | 2022-06-03 | 5 | 2023-01-16 | 2023-01-23 |  | X | 48 | 12 | 22 | 0 | 1 | 1T | New BOM - Program/setup updated 1/16/2023 | KIT CLEAR 1/16 | SHIPPED 1/23/2023
110685 | 9838.5 | 50 | 2022-11-30 | 10 | 2023-01-09 | 2023-01-23 |  | X | 835 | 12 | 134 | 1 | 1 | 2B/2T |  | KIT CLEAR 1/9 | SHIPPED 1/23/2023
100617-4 | 7629.71 | 100 | 2021-08-19 | 20 | 2022-12-22 | 1/20 1/23H* |  | X | 401 | 4 | 54 | 1 | 1 | 1B/1T | No changes 3rd Article (Oklahoma Final Build) | KIT CLEAR 12/22 | SHIPPED 1/20/2023
114123-2PAR | 12379.04 | 22/38 | 2022-12-12 | 10 | N/C | ??? |  | X | 1224 | 0 | 48 | 1 | 1 | 1B/1T |  | DOC REL 1/13 | SHIPPED 1/20/2023
114334-3 | 4982.56 | 836 | 2022-06-17 | 10 | 2022-11-16 | 2023-01-23 |  | X | 35 | 7 | 19 | 0 | 1 | 2T | PAID RWK |  | SHIPPED 1/19/2023
113868 | 4553 | 100 | 2022-01-03 | 15 | 2022-12-30 | 1/20 1/23H* |  | X | 111 | 6 | 50 | 1 | 1 | 1B/1T |  | KIT CLEAR 12/30 | SHIPPED 1/19/2023
104347 | 2237.5 | 85 | 2022-01-19 | 15 | 2023-01-03 | 1/27 1/24 |  | X | 19 | 17 | 10 | 0 | 1 | 1T |  | KIT CLEAR 1/3 -- DUE DATE 1/27 PER EMAIL | SHIPPED 1/19/2023
115328 | 3770 | 8 | 2023-01-16 | 5 | 2023-01-12 | 2023-01-19 |  | X | 2 | 4 | 1 | 0 | 1 | 1T |  | KIT CLEAR 1/12 | SHIPPED 1/18/2023
115240 | 14935 | 700 | 2023-01-18 | 5 | 2023-01-11 | 2023-01-18 |  | X | 88 | 0 | 43 | 1 | 1 | 2B/1T |  | KIT CLEAR 1/11 | SHIPPED 1/18/2023
114734-1 | 7935 | 100 | 2022-12-30 | 10 | 2022-12-27 | 2023-01-19 |  | X | 287 | 46 | 39 | 1 | 1 | 1B/1T | No changes B110779 | KIT CLEAR 1/5 | SHIPPED 1/17/2023
114860-2 | 548 | 23 | 2022-12-29 | 5 | 2023-01-11 | 2023-01-18 |  | X | 227 | 7 | 62 | 1 | 1 | 1B/1T | With change 1st Article | KIT CLEAR 1/11 | SHIPPED 1/16/2023
114791-2BAL | 253.5 | 1 | 2022-08-04 | 5 | 2023-01-05 | 2023-01-16 |  | X | 1033 | 0 | 99 | 1 | 1 | 1B/2T | PAID RWK (HOLD) | NO DOC. | SHIPPED 1/16/2023
114124-1 | 2529 | 2 | 2022-12-23 | 5 | 2023-01-10 | 2023-01-17 |  | X | 1331 | 0 | 101 | 1 | 1 | 1B/1T | New BOM/program/feeders updated 1/10 - With change B108878 | KIT CLEAR 1/10 | SHIPPED 1/16/2023
114215-1 | 2493 | 2 | 2022-12-23 | 5 | 2023-01-11 | 2023-01-18 |  | X | 1304 | 0 | 122 | 1 | 1 | 2B/1T | New BOM/Program feeder updated 1-11-23/With change B108880 | KIT CLEAR 1/11 | SHIPPED 1/13/2023
115013 | 4188.8 | 5 | 2022-01-10 | 5 | 2023-01-09 | 2023-01-16 |  | X | 815 | 16 | 150 | 1 | 1 | 2B/2T | New gerber/Program updated 1/10 | KIT CLEAR 1/9 | SHIPPED 1/13/2023
113665-6 | 12612 | 100/150 | 2022-11-04 | 5 | 2022-10-17 | 2022-01-17 |  | X | 444 | 16 | 62 | 1 | 1 | 1B/2T | No changes B113064 | KIT CLEAR QTY 400 PARTIAL | SHIPPED 1/13/2023
104353 | 2648 | 8 | 2022-01-12 | 10 | 2023-01-03 | 2023-01-17 |  | X | 96 | 43 | 26 | 0 | 1 | 1T |  | KIT CLEAR 1/3 | SHIPPED 1/13/2023
114470 | 3208 | 2 | 2022-12-15 | 5 | 2023-01-10 | 2023-01-17 |  | X | 213 | 84 | 18 | 1 | 1 | 1B/1T |  | KIT CLEAR 1/10 | SHIPPED 1/13/2023
114854 | 2783 | 10 | 2023-01-11 | 5 | 2023-01-10 | 2023-01-17 |  | X | 41 | 49 | 10 | 1 | 1 | 1B/1T |  | KIT CLEAR 1/10 | SHIPPED 1/13/2023
114791-1PAR | 9633 | 39 | 2022-08-04 | 5 | 2023-01-05 | 2023-01-16 |  | X | 1033 | 0 | 99 | 1 | 1 | 1B/2T | PAID RWK | NO DOC. | SHIPPED 1/12/2023
115020 | 3998.5 | 150 | 2022-01-09 | 5 | N/C | 2023-01-13 |  | X | 97 | 0 | 39 | 1 | 1 | 1B/1T |  | KIT CLEAR 12/30 | SHIPPED 1/11/2023
115006 | 2230 | 2 | 2023-01-11 | 2 | 2023-01-10 | 2023-01-12 |  | X | 21 | 8 | 14 | 0 | 1 | 1T |  | KIT CLEAR 1/10 | SHIPPED 1/10/2023
114756 | 5770.5 | 15 | 2022-12-23 | 3 | 2023-01-05 | 2023-01-10 |  | X | 198 | 44 | 50 | 0 | 1 | 1T |  | KIT CLEAR 1/5 | SHIPPED 1/10/2023
115160 | 4162.5 | 125 | 2022-01-04 | 2 | 2023-01-06 | 2023-01-10 |  | X | 60 | 0 | 27 | 1 | 1 | 1B/1T |  | KIT CLEAR 1/6 | SHIPPED 1/10/2023
114712 | 3035.2 | 40 | 2022-01-04 | 10 | 2022-12-27 | 1/11H |  | X | 200 | 21 | 44 | 0 | 1 | 1T |  | KIT CLEAR 12/27 | SHIPPED 1/9/2023
114793 | 3034.5 | 82 | 2023-01-11 | 10 | 2022-12-27 | 1/11H |  | X | 100 | 5 | 38 | 0 | 1 | 1T | With change B110040 | KIT CLEAR 12/27 | SHIPPED 1/9/2023
112596 | 2975 | 20 | 2022-12-22 | 5 | 2023-01-03 | 2023-01-10 |  | X | 145 | 0 | 40 | 1 | 1 | 1B/1T | Do not de-panel!!! | KIT CLEAR 1/3 | SHIPPED 1/9/2023
115144 | 1582 | 200 | 2022-01-10 | 5 | 2022-12-29 | 1/6H |  | X | 7 | 3 | 4 | 0 | 1 | 1T | With change B103726 | KIT CLEAR 12/29 | SHIPPED 1/6/2023
113665-5* | 12612 | 100/250 | 2022-11-04 | 10 | 2022-10-17 | 2022-01-05 |  | X | 444 | 16 | 62 | 1 | 1 | 1B/2T | No changes B113064 | KIT CLEAR QTY 400 PARTIAL | SHIPPED 1/5/2023
113722 | 7506 | 40 | 2022-11-15 | 3 | N/C | ??? |  | X | 305 | 14 | 80 | 1 | 1 | 2B/2T | CANCELLED 1/04 | DOC REL 11/07 | CANCELLED 1/4/2023
114307-1 | 1872 | 2 | 2022-01-04 | 5 | N/C | ??? |  | X | 1101 | 0 | 43 | 1 | 1 | 1B/1T | With change B108879 | DOC REL 12/12 | SHIPPED 1/4/2023
114886-2BAL | 4194.5 | 8 | 2022-12-28 | 5 | 2022-12-23 | 1/3H |  | X | 613 | 53 | 82 | 1 | 1 | 1B/2T |  | KIT CLEAR 12/23 | SHIPPED 1/4/2023
113097 | 7727.6 | 2 | 2022-01-03 | 10 | 2022-12-15 | 12/30H |  | X | 2 | 51 | 1 | 0 | 1 | 1T |  | KIT CLEAR 12/15 | SHIPPED 1/4/2023
114886-1 | 4194.5 | 2 | 2022-12-28 | 5 | 2022-12-23 | 1/3H |  | X | 613 | 53 | 82 | 1 | 1 | 1B/2T |  | KIT CLEAR 12/23 | SHIPPED 1/3/2023
113097 | 7727.6 | 243 | 2022-01-03 | 10 | 2022-12-15 | 12/30H |  | X | 2 | 51 | 1 | 0 | 1 | 1T |  | KIT CLEAR 12/15 | SHIPPED 12/30/22
114101 | 2337 | 300 | 2022-01-11 | 20 | 2022-12-02 | 1/4H |  | X | 23 | 0 | 9 | 0 | 1 | 1T |  | KIT CLEAR 12/2 | SHIPPED 12/30/22
115070 | 3363 | 25 | 2022-12-23 | 3 | 2022-12-27 | 2022-12-30 |  | X | 354 | 0 | 14 | 1 | 1 | 1B/1T | No changes B102179/Note quality issue from previous build | KIT CLEAR 12/27 | SHIPPED 12/30/22
114521-2 | 5192 | 1 | 2022-12-27 | 5 | 2022-12-20 | 12/27H |  | X | 114 | 20 | 57 | 1 | 1 | 1B/1T | No changes ` | KIT CLEAR 12/16 | SHIPPED 12/30/22
114860-1 | 1509.26 | 12 | 2022-12-29 | 5 | 2022-12-21 | 12/29H |  | X | 227 | 9 | 62 | 1 | 1 | 1B/1T |  | KIT CLEAR 12/21 | SHIPPED 12/29
114571 | 1400 | 100 | 2022-11-28 | 5 | 2022-12-21 | 12/29H |  | X | 14 | 0 | 6 | 0 | 1 | 1T | No changes B110259 | KIT CLEAR 12/21 | SHIPPED 12/29
114123-1 | 2325.6 | 2 | 2022-12-12 | 5 | 2022-12-22 | 12/30H |  | X | 1224 | 0 | 48 | 1 | 1 | 1B/1T | With change B108881 | KIT CLEAR 12/22 | SHIPPED 12/29
113151-1 | 3241.08 | 54 | 2022-12-19 | 9 | 2022-12-14 | 2022-12-28 |  | X | 350 | 6 | 37 | 1 | 1 | 2B/2T | With change B99149 | SHORT PCB + 5 ITEMS | SHIPPED 12/28
114521-1 | 5192 | 99/100 | 2022-12-27 | 5 | 2022-12-20 | 12/27H |  | X | 114 | 20 | 57 | 1 | 1 | 1B/1T | No changes ` | KIT CLEAR 12/16 | SHIPPED 12/27
114054-2 | 4000 | 5 |  | 2 | N/C | ??? |  | X | 1297 | 12 | 110 | 1 | 1 | 2B/1T | Need 5 boards Friday 12-9 | DOC REL 12/07 | SHIPPED 12/27
114813-1 | 47893 | 50 | 2022-01-17 | 5 | 2022-12-20 | 12/28H |  | X | 1117 | 6 | 144 | 1 | 1 | 2B/2T | QTY 50 expedited. Can build all 195 at once. | KIT CLEAR 12/20 | SHIPPED 12/23
114814-1 | 5230.3 | 200 | 2022-12-23 | 5 | 2022-12-20 | 12/28H |  | X | 92 | 1 | 42 | 1 | 1 | 1B/2T |  | KIT CLEAR 12/20 | SHIPPED 12/23
114812-1 | 6739 | 30 | 2022-01-10 | 5 | 2022-12-20 | 12/28H |  | X | 554 | 16 | 92 | 1 | 1 | 1B/2T | QTY 50 expedited. Can build all 195 at once. | KIT CLEAR 12/20 | SHIPPED 12/23
114815 | 3661.7 | 130 | 2022-12-23 | 5 | 2022-12-15 | 2022-12-22 |  | X | 92 | 1 | 42 | 1 | 1 | 1B/1T | Uses same PCBs as B114814 | KIT CLEAR 12/15 | SHIPPED 12/22
114404-2 | 13500 | 400 | 2022-12-27 | 10 | 2022-12-02 | 2022-12-22 |  | X | 50 | 11 | 22 | 0 | 1 | 2T | With change B113440 (added hardware) | KIT CLEAR 12/2 | SHIPPED 12/22
114729 | 3426.25 | 5 | 2022-12-21 | 5 | 2022-12-15 | 2022-12-22 |  | X | 618 | 77 | 146 | 1 | 1 | 2B/2T |  | KIT CLEAR 12/15 | SHIPPED 12/22
114735 | 2712 | 50 | 2022-12-28 | 15 | 2022-12-09 | 2022-12-30 |  | X | 173 | 18 | 50 | 1 | 1 | 1B/2T | With change B109885 | KIT CLEAR 12/9 | SHIPPED 12/22
114272 | 16736 | 160 | 2022-12-08 | 5 | 2022-12-14 | 2022-12-21 |  | X | 372 | 2 | 94 | 1 | 1 | 1B/2T |  | KIT CLEAR 12/14 | SHIPPED 12/21
114027 | 5352.04 | 19 | 2022-12-15 | 5 | 2022-12-14 | 2022-12-21 |  | X | 652 | 26 | 125 | 1 | 1 | 1B/2T |  | KIT CLEAR 12/14 | SHIPPED 12/20
114054-2 | 4000 | 5 |  | 2 | N/C | ??? |  | X | 1297 | 12 | 110 | 1 | 1 | 2B/1T | Need 5 boards Friday 12-9 | DOC REL 12/07 | SHIPPED 12/20
113347-2 | 19489.706 | 50 | 2022-12-02 | 1 | 2022-12-13 | 2022-12-14 |  | X | 254 | 21 | 72 | 1 | 1 | 1B/1T | No changes B112096 | KIT CLEAR LESS 1 PC ITEM 40 12/13 | SHIPPED 12/19
114185 | 3693.72 | 28 | 2022-12-15 | 9 | 2022-12-06 | 2022-12-19 |  | X | 462 | 1 | 110 | 1 | 1 | 1B/2T | No changes B114026 | KIT CLEAR 12/6 | SHIPPED 12/19
110198-2 | 1453.5 | 170 | 2022-06-17 | 10 | 2022-12-12 | 2022-12-19 |  | X | 35 | 7 | 19 | 0 | 1 | 2T |  | KIT CLEAR 12/12 | SHIPPED 12/19
113646-2 | 5060 | 4 | 2022-10-26 | 5 | 2022-12-07 | 2022-12-16 |  | X | 691 | 28 | 156 | 1 | 1 | 1B/3T | No changes 1st Article | KIT CLEAR 12/7 (NOT REPORTED) DAY 1 IS 12/12 | SHIPPED 12/19
114332 | 5869 | 100 | 2022-11-30 | 5 | 2022-12-13 | 2022-12-20 |  | X | 239 | 0 | 45 | 0 | 1 | 1T |  | KIT CLEAR 12/13 | SHIPPED 12/16
114821 | 3678 | 120 | 2022-12-15 | 3 | 2022-12-13 | 2022-12-16 |  | X | 34 | 4 | 15 | 0 | 1 | 1T | No change 112849 | KIT CLEAR 12/13 | SHIPPED 12/16
113347-1 | 389.7941 | 1 | 2022-12-02 | 1 | 2022-12-13 | 2022-12-15 |  | X | 254 | 21 | 72 | 1 | 1 | 1B/1T | No changes B112096 | 12/14 - SPLIT QTY 1 OFF (CUST EVAL) | SHIPPED 12/15
113227 | 2135 | 6 | 2022-12-06 | 15 | 2022-11-30 | 2022-12-21 |  | X | 439 | 18 | 83 | 1 | 1 | 1B/2T |  | KIT CLEAR 11/30 | SHIPPED 12/15
104575-3 | 798.8 | 8 | 2021-09-22 | 15 | 2022-12-01 | 2022-12-22 |  | X | 203 | 2 | 63 | 1 | 1 | 1B/2T | No BOM changes 2nd Article - Updated ECO note #8 (Oklahoma Final Build) | KIT CLEAR 12/1 | SHIPPED 12/15
113030 | 6100 | 50 | 2022-11-22 | 20 | 2022-11-14 | 12/14H |  | X | 410 | 0 | 49 | 1 | 1 | 1B/1T | Off hold - program/feeder updated | KIT CLEAR 11/14 | SHIPPED 12/14
114544 | 2862 | 200 | 2022-12-16 | 5 | 2022-12-07 | 2022-12-14 |  | X | 33 | 0 | 13 | 1 | 1 | 1B/1T |  | KIT CLEAR 12/7 | SHIPPED 12/14
114587 | 3562 | 5 | 2022-12-12 | 3 | 2022-12-09 | 2022-12-14 |  | X | 614 | 38 | 77 | 1 | 1 | 1B/1T |  | KIT CLEAR 12/9 | SHIPPED 12/14
110198-1 | 4389 | 180 | 2022-06-17 | 10 | 2022-11-16 | 12/5 12/2H |  | X | 35 | 7 | 19 | 0 | 1 | 2T |  | KIT CLEAR 11/16 12/5 SHORT HEAT SINK PINS | SHIPPED 12/14
114731 | 8784 | 50 | 2022-12-01 | 3 | 2022-12-06 | 2022-12-13 |  | X | 469 | 1 | 11 | 1 | 1 | 1B/1T |  | KIT CLEAR 12/6 | SHIPPED 12/13
114534 | 5081.4 | 60 | 2022-12-14 | 5 | 2022-12-06 | 2022-12-13 |  | X | 231 | 1 | 62 | 1 | 1 | 1B/1T |  | KIT CLEAR 12/6 | SHIPPED 12/13
113048 | 2298 | 4 | 2022-11-16 | 10 | 2022-12-06 | 2022-12-13 |  | X | 33 | 43 | 10 | 0 | 1 | 1T |  | KIT CLEAR 12/6 | SHIPPED 12/13
110416-3 | 1298 | 5 | 2022-06-14 | 5 | 2022-12-06 | 2022-12-13 |  | X | 204 | 3 | 65 | 1 | 1 | 1B/1T | No changes 1st Article | KIT CLEAR 12/6 | SHIPPED 12/12
113835 | 8243 | 100 | 2022-12-13 | 10 | 2022-11-28 | 2022-12-12 |  | X | 178 | 20 | 55 | 1 | 1 | 1B/1T |  | KIT CLEAR 11/28 | SHIPPED 12/12
112874 | 4895.5 | 10 | 2022-10-31 | 10 | 2022-11-21 | 12/12 12/7H |  | X | 959 | 22 | 87 | 1 | 1 | 1B/1T |  | KIT CLEAR 11/21 | SHIPPED 12/12
114334-2 | 2384 | 400/1580 | 2022-11-30 | 10 | N/C | 2022-12-01 |  | X | [6 empty] | PAID RWK | NO DOC. | SHIPPED 12/12
113770 | 4145 | 3 | 2022-11-21 | 5 | 2022-12-05 | 2022-12-12 |  | X | 524 | 102 | 27 | 0 | 1 | 1T |  | KIT CLEAR 12/5 | SHIPPED 12/9
114426 | 3518.25 | 5 | 2022-12-13 | 5 | 2022-12-05 | 2022-12-12 |  | X | 592 | 0 | 119 | 1 | 1 | 1B/2T |  | KIT CLEAR 12/5 | SHIPPED 12/9
114054-1 | 4000 | 5/15 |  | 1 | N/C | 2022-12-09 |  | X | 1297 | 12 | 110 | 1 | 1 | 2B/1T | Need 5 boards Friday 12-9 | DOC REL 12/07
113665-4 | 12612 | 100/350 | 2022-11-04 | 5 | 2022-10-17 | 2022-12-08 |  | X | 444 | 16 | 62 | 1 | 1 | 1B/2T | No changes B113064 | KIT CLEAR QTY 400 PARTIAL | SHIPPED 12/8
111857 | 3534.6 | 20 | 2022-10-17 | 15 | 2022-11-15 | 12/8H |  | X | 375 | 20 | 22 | 1 | 1 | 1B/1T |  | KIT CLEAR 11/15 | SHIPPED 12/8
113153 | 3240.8 | 120 | 2022-11-23 | 10 | 2022-11-22 | 12/8H |  | X | 82 | 9 | 7 | 1 | 1 | 1B/1T |  | KIT CLEAR 11/22 | SHIPPED 12/8
114404-1 | 13500 | 400/800 | 2022-12-27 | 10 | 2022-12-02 | 2022-12-08 |  | X | 50 | 11 | 22 | 0 | 1 | 2T | With change B113440 (added hardware) | KIT CLEAR 12/2 | SHIPPED 12/8
114455 | 6210 | 1950 | 2022-12-06 | 5 | 2022-11-30 | ??? 12/8 |  | X | 7 | 0 | 2 | 0 | 1 | 1T |  | KIT CLEAR 11/30 | SHIPPED 12/8
114454 | 6150 | 2000 | 2022-12-21 | 5 | 2022-11-30 | ??? 12/7 |  | X | 6 | 0 | 6 | 0 | 1 | 2T |  | KIT CLEAR 11/30 | SHIPPED 12/8
114452 | 4990 | 1950 | 2022-12-06 | 5 | 2022-11-29 | ??? 12/6 |  | X | 4 | 0 | 2 | 0 | 1 | 1T |  | KIT CLEAR 11/29 | SHIPPED 12/8
112562 | 9957.5 | 250 | 2022-10-06 | 10 | 2022-11-18 | 2022-12-07 |  | X | 145 | 22 | 42 | 0 | 1 | 1T | With change B109333 | KIT CLEAR 11/18 | SHIPPED 12/7
114184-2 | 7093 | 300 | 2022-11-28 | 5 | 2022-11-29 | 2022-12-06 |  | X | 70 | 0 | 7 | 1 | 0 | 1B |  | KIT CLEAR 11/30 | SHIPPED 12/6
114455 | 6210 | 50/2000 | 2022-12-06 | 5 | 2022-11-30 | 2022-12-08 |  | X | 7 | 0 | 2 | 0 | 1 | 1T |  | KIT CLEAR 11/30 | SHIPPED 12/5
114452 | 4990 | 50/2000 | 2022-12-06 | 5 | 2022-11-29 | 2022-12-06 |  | X | 4 | 0 | 2 | 0 | 1 | 1T |  | KIT CLEAR 11/29 | SHIPPED 12/5
112132-1 | 780 | 2 | 2022-10-03 | 5 | N/C | 2022-11-21 |  | X | 238 | 7 | 64 | 1 | 1 | 1B/1T |  | KIT CLEAR 11/11 (NOT REPORTED) | SHIPPED 12/5
112217-3 | 2603.5 | 41 | 2022-08-31 | 5 | 2022-11-28 | 2022-12-05 |  | X | 1 | 1 | 1 | 0 | 1 | 1T |  | KIT CLEAR 11/28 | SHIPPED 12/5
112218-3 | 2603.5 | 41 | 2022-08-31 | 5 | 2022-11-28 | 2022-12-05 |  | X | 1 | 1 | 1 | 0 | 1 | 1T |  | KIT CLEAR 11/28 | SHIPPED 12/5
113576 | 12216 | 1200 | 2022-11-14 | 20 | 2022-11-02 | 12/2H |  | X | 28 | 2 | 10 | 1 | 0 | 1B | With changes B112810 | KIT CLEAR 11/2 | SHIPPED 12/2
113152 | 2678 | 120 | 2022-11-21 | 9 | 2022-11-16 | 2022-12-02 |  | X | 56 | 7 | 15 | 0 | 1 | 1T |  | KIT CLEAR 11/16 | SHIPPED 12/2
114184-1 | 13104 | 300 | 2022-11-28 | 3 | 2022-11-29 | 2022-12-02 |  | X | 70 | 0 | 7 | 1 | 0 | 1B |  | KIT CLEAR 11/30 | SHIPPED 12/2
105003-2 | 9336 | 30* | 2022-04-25 | 10 | 2022-11-15 | 12/1H |  | X | 92 | 4 | 38 | 1 | 1 | 1B/1T |  | KIT CLEAR 11/15 | SHIPPED 12/1
114057 | 1937.5 | 50 | 2022-12-09 | 10 | 2022-11-15 | 12/1H |  | X | 11 | 3 | 6 | 0 | 1 | 1T | With change B105738 | KIT CLEAR 11/15 | SHIPPED 12/1
114390-2 | 2004.6 | 39 | 2022-11-23 | 5 | 2022-11-22 | 12/1H |  | X | 139 | 15 | 48 | 1 | 1 | 1B/1T |  | KIT CLEAR 11/22 | SHIPPED 12/1
110522 | 8730 | 300 | 2022-12-02 | 15 | 2022-11-07 | 11/30H |  | X | 97 | 0 | 18 | 1 | 1 | 1B/1T | With change B102221 | KIT CLEAR 11/7 | SHIPPED 11/30
111796 | 6022 | 50 | 2022-10-14 | 10 | 2022-11-14 | 11/30H |  | X | 389 | 27 | 80 | 1 | 1 | 1B/1T |  | KIT CLEAR 11/14 | SHIPPED 11/30
111470-2 | 24506.2 | 190 | 2022-08-22 | 10 | N/C | 11/30H* |  | X | 699 | 9 | 151 | 0 | 1 | 3T | With change (2 new ECO notes) - Robert update | KIT CLEAR 11/11 (NOT REPORTED) | SHIPPED 11/30
114351 | 3200 | 500 | 2022-11-30 | 5 | 2022-11-21 | 11/30H |  | X | 1 | 0 | 1 | 0 | 1 | 1T |  | KIT CLEAR 11/21 | SHIPPED 11/30
105003-2 | 9336 | 20/50 | 2022-04-25 | 10 | 2022-11-15 | 12/1H |  | X | 92 | 4 | 38 | 1 | 1 | 1B/1T |  | KIT CLEAR 11/15 | SHIPPED 11/29 (EXPEDITED 20 OF 50)
111751-2 | 49850 | 250 | 2022-09-13 | 20 | 2022-10-27 | 2022-11-29 |  | X | 453 | 139 | 86 | 1 | 1 | 1B/2T | No changes 1st Article | KIT CLEAR 9/30 (NOT REPORTED) | SHIPPED 11/29
113887 | 2110 | 5 | 2022-11-22 | 15 | 2022-11-04 | 11/29H |  | X | 8 | 0 | 1 | 1 | 1 | 1B/1T |  | KIT CLEAR 11/4 | SHIPPED 11/29
109746 | 13240 | 400 | 2022-06-01 | 10 | 2022-11-10 | 11/28H |  | X | 137 | 6 | 68 | 1 | 1 | 2B/2T |  | KIT CLEAR 11/10 | SHIPPED 11/29
114334-1 | 750 | 20 | 2022-11-30 | 2 | N/C | 2022-11-29 |  | X | [6 empty] | PAID RWK | NO DOC. | SHIPPED 11/29
108880 | 9860.5 | 10 | 2022-11-21 | 3 | 2022-11-21 | 11/28H |  | X | 1304 | 7 | 121 | 1 | 1 | 2B/1T |  | KIT CLEAR 11/21 | SHIPPED 11/28
112881-2 | 6152.8 | 4 | 2022-09-27 | 5 | 2022-11-15 | 2022-11-28 |  | X | 706 | 13 | 156 | 1 | 1 | 2B/2T | With change 1st Article | KIT CLEAR 11/15 | SHIPPED 11/28
113975 | 8452.8 | 216 | 2022-11-09 | 15 10 | 2022-11-01 | 11/22 11/28 |  | X | 154 | 8 | 57 | 1 | 1 | 1B/2T | No changes B106111 | KIT CLEAR 11/1 | SHIPPED 11/28
110203-2 | 850.8 | 60 | 2022-06-09 | 9 | 2022-06-10 | 2022-11-23 |  | X | 51 | 4 | 25 | 0 | 1 | 1T |  | KIT CLEAR 6/10 | SHIPPED 11/23
111791 | 3703.04 | 16 | 2022-12-08 | 20 | 2022-10-28 | 11/28H |  | X | 936 | 8 | 48 | 1 | 1 | 1B/1T | With changes B100811 | KIT CLEAR 10/28 | SHIPPED 11/23
114006 | 1495 | 10 | 2022-12-28 | 10 | 2022-11-14 | 11/30H |  | X | 26 | 0 | 5 | 0 | 1 | 1T | No changes B112985 | KIT CLEAR 11/14 | SHIPPED 11/22
114390-1 | 4246 | 20 | 2022-11-23 | 2 | 2022-11-18 | 2022-11-22 |  | X | 139 | 15 | 48 | 1 | 1 | 1B/1T | QTY 20 expedited - Can build all 59 at once | KIT CLEAR 11/18 | SHIPPED 11/22
111695-2 | 10616.3 | 125 | 2022-08-10 | 9 | 2022-11-09 | 2022-11-22 |  | X | 427 | 10 | 124 | 1 | 1 | 2B/2T | With changes - Robert update | KIT CLEAR 11/9 | SHIPPED 11/22
114026 | 3736.7 | 22 | 2022-11-16 | 10 | 2022-11-08 | 2022-11-22 |  | X | 462 | 1 | 110 | 1 | 1 | 1B/2T | No changes B102703 | KIT CLEAR 11/8 | SHIPPED 11/22
113154 | 3111.6 | 120 | 2022-11-21 | 10 | 2022-11-08 | 2022-11-22 |  | X | 35 | 15 | 22 | 0 | 1 | 1T |  | KIT CLEAR 11/8 | SHIPPED 11/21
113426-1 | 18052.65 | 99/100 | 2022-10-26 | 3 | 2022-11-17 | 11/22* |  | X | 254 | 21 | 72 | 1 | 1 | 1B/1T | No changes B112228 | SHORT PCB + 1 ITEM | SHIPPED 11/21
112127-2 | 1757.81 | 43 | 2022-10-03 | 10 | N/C | 2022-11-21 |  | X | 8 | 10 | 7 | 0 | 1 | 1T | No changes 1st Article | DOC REL 11/07 | SHIPPED 11/21
112128-2 | 2247.54 | 38 | 2022-10-03 | 10 | 2022-11-07 | 2022-11-21 |  | X | 0 | 12 | 0 | 0 | 0 | 0 | T/H ONLY | KIT CLEAR 11/7 | SHIPPED 11/21
108879 | 5788.6 | 10 | 2022-11-17 | 5 | 2022-11-11 | 2022-11-18 |  | X | 1101 | 62 | 43 | 1 | 1 | 1B/1T |  | KIT CLEAR 11/11 | SHIPPED 11/18
108878 | 9772 | 9 + 1 | 2022-11-14 | 3 | 2022-11-15 | 2022-11-18 |  | X | 1331 | 7 | 101 | 1 | 1 | 1B/1T |  | KIT CLEAR 11/15 | SHIPPED 11/17
112217-1 | 2896 | 4FA | 2022-08-31 | 5 | 2022-11-11 | 2022-11-18 |  | X | 1 | 1 | 1 | 0 | 1 | 1T |  | KIT CLEAR 11/11 | SHIPPED IN PLACE 11/17 - WRONG FABS FROM AA
112218-1 | 2896 | 4FA | 2022-08-31 | 5 | 2022-11-11 | 2022-11-18 |  | X | 1 | 1 | 1 | 0 | 1 | 1T |  | KIT CLEAR 11/11 | SHIPPED IN PLACE 11/17 - WRONG FABS FROM AA
112217-2 | 1446 | 4FA | 2022-08-31 | 5 | 2022-11-11 | 2022-11-18 |  | X | 1 | 1 | 1 | 0 | 1 | 1T |  | KIT CLEAR 11/11 | SHIPPED 11/17
112218-2 | 1446 | 4FA | 2022-08-31 | 5 | 2022-11-11 | 2022-11-18 |  | X | 1 | 1 | 1 | 0 | 1 | 1T |  | KIT CLEAR 11/11 | SHIPPED 11/17
113292 | 2730.55 | 1 | 2022-09-29 | 3 | 2022-11-15 | 2022-11-18 |  | X | 799 | 6 | 101 | 1 | 1 | 1B/2T |  | KIT CLEAR 11/15 | SHIPPED 11/17
113665-3 | 12612 | 100/450 | 2022-11-04 | 5 | 2022-10-17 | 2022-11-17 |  | X | 444 | 16 | 62 | 1 | 1 | 1B/2T | No changes B113064 | KIT CLEAR QTY 400 PARTIAL | SHIPPED 11/17
112505 | 3108.4 | 35 | 2022-11-15 | 5 | 2022-11-10 | 2022-11-17 |  | X | 164 | 10 | 46 | 1 | 1 | 1B/1T | No changes B108531 | KIT CLEAR 11/10 | SHIPPED 11/17
114073 | 1642.68 | 52 | 2022-11-18 | 5 | 2022-11-09 | 2022-11-16 |  | X | 87 | 1 | 30 | 0 | 1 | 1T |  | KIT CLEAR 11/9 | SHIPPED 11/16
113661 | 3784 | 400 | 2022-11-14 | 10 | 2022-11-02 | 2022-11-16 |  | X | 43 | 0 | 27 | 0 | 1 | 2T | With changes B102579 | KIT CLEAR 11/2 | SHIPPED 11/16
113662 | 4704 | 200 | 2022-11-14 | 10 | 2022-11-01 | 2022-11-15 |  | X | 97 | 7 | 32 | 1 | 1 | 1B/2T | With changes B102582 | KIT CLEAR 11/1 | SHIPPED 11/15
113440-2 | 13500 | 400 | 2022-10-19 | 10 | 2022-11-01 | 2022-11-15 |  | X | 50 | 10 | 22 | 0 | 1 | 2T | No changes B112573 | KIT CLEAR 11/1 | SHIPPED 11/15
111675-2 | 15180 | 25 | 2022-08-05 | 5 | 2022-11-08 | 2022-11-15 |  | X | 577 | 54 | 89 | 1 | 1 | 1B/2T | With changes - Robert update | KIT CLEAR 11/8 | SHIPPED 11/15
112600 | 4061.8 | 10 | 2022-10-07 | 5 | 2022-11-15 | 2022-11-22 |  | X | 678 | 3 | 75 | 1 | 1 | 1B/1T | Do not de-panel | KIT CLEAR 11/15 | SHIPPED 11/15
111560 | 3041.5 | 50 | 2022-10-25 | 9 | 2022-11-02 | 2022-11-15 |  | X | 234 | 0 | 34 | 1 | 1 | 1B/1T |  | KIT CLEAR 11/2 | SHIPPED 11/14
113663 | 4732 | 200 | 2022-11-14 | 10 | 2022-10-31 | 2022-11-14 |  | X | 38 | 14 | 22 | 1 | 0 | 1B | With changes B102583 | KIT CLEAR 10/31 | SHIPPED 11/14
113424 | 3360 | 10 | 2022-11-01 | 10 | 2022-10-31 | 2022-11-14 |  | X | 1 | 82 | 1 | 0 | 1 | 1T |  | KIT CLEAR 10/31 | SHIPPED 11/14
110859-2 | 12888 | 120 | 2022-08-18 | 10 | 2022-10-28 | 2022-11-11 |  | X | 265 | 11 | 43 | 1 | 1 | 1B/2T | No change B109097 | KIT CLEAR 10/28 | SHIPPED 11/11
114025 / 113426 | 12395.8 | *20/100 | 2022-10-26 | *1 | 2022-11-09 | 2022-11-10 |  | X | 254 | 21 | 72 | 1 | 1 | 1B/1T | No changes B112228 | SHORT PCB + 1 ITEM | SHIPPED 11/10
112814 | 3695 | 100 | 2022-10-12 | 10 | 2022-10-28 | 2022-11-11 |  | X | 102 | 7 | 33 | 0 | 1 | 1T |  | KIT CLEAR 10/28 | SHIPPED 11/9
112479 | 2960.5 | 50 | 2022-10-11 | 9 | 2022-10-27 | 2022-11-09 |  | X | 139 | 25 | 32 | 1 | 1 | 1B/1T |  | KIT CLEAR 10/27 | SHIPPED 11/9
113647 | 2842.8 | 48 | 2022-11-02 | 5 | 2022-11-02 | 2022-11-09 |  | X | 118 | 16 | 31 | 1 | 1 | 1B/1T |  | KIT CLEAR 11/2 | SHIPPED 11/9
112722 | 4852 | 20 | 2022-11-01 | 5 | N/C | ??? |  | X | 159 | 62 | 81 | 0 | 1 | 2T |  | SHORT 1 TH ITEM (CONFIRMING 4 ITEMS) | SHIPPED 11/8
111607-2 | 3551.36 | 248 | 2022-10-17 | 10 | 2022-10-27 | 2022-11-10 |  | X | 53 | 4 | 27 | 1 | 1 | 1B/1T |  | KIT CLEAR 10/27 | SHIPPED 11/7
112513 | 1345.5 | 50 | 2022-11-01 | 20 | 2022-10-12 | 2022-11-09 |  | X | 117 | 0 | 32 | 1 | 1 | 1B/1T | No changes B108038 | KIT CLEAR 10/12 | SHIPPED 11/7
114048 | 3870 | 120 | 2022-11-07 | 3 | 2022-11-03 | 2022-11-08 |  | X | 13 | 0 | 6 | 1 | 1 | 1B/1T |  | KIT CLEAR 11/3 | SHIPPED 11/7
113382 | 2310 | 50 | 2022-10-27 | 9 | 2022-10-11 | 2022-11-07 |  | X | 20 | 11 | 11 | 0 | 1 | 1T |  | KIT CLEAR 10/11 | SHIPPED 11/4
113515 | 5085.5 | 10 | 2022-11-04 | 10 | 2022-10-21 | 2022-11-04 |  | X | 801 | 20 | 88 | 1 | 1 | 1B/2T |  | KIT CLEAR 10/21 | SHIPPED 11/4
111683 | 5292 | 100 | 2022-11-07 | 10 | 2022-10-21 | 2022-11-04 |  | X | 167 | 9 | 33 | 0 | 1 | 1T |  | KIT CLEAR 10/21 | SHIPPED 11/4
113665-2 | 12612 | 100/550 | 2022-11-04 | 5 | 2022-10-17 | 2022-11-04 |  | X | 444 | 16 | 62 | 1 | 1 | 1B/2T | No changes B113064 | KIT CLEAR QTY 400 PARTIAL | SHIPPED 11/4
113191 | 5189.9 | 2 | 2022-10-24 | 10 | 2022-10-20 | 11/4 11/3 |  | X | 674 | 23 | 103 | 1 | 1 | 1B/1T |  | KIT CLEAR 10/20 | SHIPPED 11/4
105003 | 2141 | 50 | 2022-04-25 | 10 | 2022-10-19 | 2022-11-01 |  | X | 92 | 4 | 38 | 1 | 1 | 1B/1T |  | 6/21 - SMT CLEAR ONLY | INVOICE ONLY 11/3
113267 | 2652 | 30 | 2022-11-08 | 10 | 2022-10-20 | 2022-11-03 |  | X | 85 | 22 | 26 | 1 | 1 | 1B/1T |  | KIT CLEAR 10/20 | SHIPPED 11/3
113530 | 2692.8 | 60 | 2022-11-07 | 10 | 2022-10-21 | 2022-11-04 |  | X | 114 | 20 | 57 | 1 | 1 | 1B/1T | No changes B112553 | KIT CLEAR 10/21 | SHIPPED 11/3
112710 | 2700 | 10 | 2022-10-14 | 10 | N/C | ??? |  | XR | 385 | 29 | 82 | 1 | 1 | 1B/2T |  | DOC REL 10/12 | SHIPPED 11/3
113166 | 2135 | 415 | 2022-11-02 | 10 | 2022-10-21 | 2022-11-04 |  | X | 3 | 0 | 2 | 0 | 1 | 1T | No changes B113081 | KIT CLEAR 10/21 | SHIPPED 11/1
113167 | 2135 | 415 | 2022-11-02 | 10 | 2022-10-19 | 2022-11-02 |  | X | 3 | 0 | 2 | 0 | 1 | 2T | No changes B113082 | KIT CLEAR 10/19 | SHIPPED 11/1
109791-3 | 546.5 | 50 | 2022-06-01 | 10 | 2022-10-18 | 2022-11-01 |  | X | 49 | 0 | 27 | 1 | 1 | 1B/1T | No changes from 1st Article | KIT CLEAR 10/18 | SHIPPED 11/1
108881 | 8944 | 10 | 2022-11-01 | 3 | 2022-10-27 | 2022-10-31 |  | X | 1224 | 2 | 48 | 1 | 1 | 1B/1T |  | KIT CLEAR 10/27 | SHIPPED 10/31
113823 | 1602.5 | 30 | 2022-10-28 | 5 | 2022-10-24 | 2022-10-31 |  | X | 29 | 0 | 22 | 1 | 1 | 1B/1T |  | KIT CLEAR 10/24 | SHIPPED 10/31
113077-2 | 18784 | 180 | 2022-09-27 | 5 | N/C | 2022-10-31 |  | X | 374 | 54 | 56 | 1 | 1 | 1B/2T | No changes 1st Article | DOC REL 10/17 | SHIPPED 10/31
113454 | 4831.75 | 15 | 2022-10-20 | 5 | 2022-10-24 | 2022-10-31 |  | XR | 393 | 0 | 119 | 1 | 1 | 2B/2T |  | KIT CLEAR 10/24 | SHIPPED 10/31
112216 | 36367.5 | 650 | 2022-11-01 | 20 | N/C | 2022-10-31 |  | X | 373 | 0 | 84 | 1 | 1 | 2B/2T | With change B109536 | DOC REL 9/7 | SHIPPED 10/31
113646-1 | 4248 | 1 | 2022-10-26 | 5 | N/C | ??? |  | X | 691 | 28 | 156 | 1 | 1 | 1B/3T |  | DOC REL 10/13 | SHIPPED 10/28
112229 | 7827.4 | 30 | 2022-10-21 | 3 | 2022-10-25 | 2022-10-28 |  | X | 254 | 21 | 72 | 1 | 1 | 1B/1T | With changes B112096 | KIT CLEAR 10/25 | SHIPPED 10/28
110721-2 | 6707.064 | 166 | 2022-07-11 | 10 | N/C | ??? |  | X | 273 | 2 | 39 | 1 | 1 | 1B/2T | Repeat with change B109847 | DOC REL 6/24 | JOB CANX INVOCE ONLY 10/27
113459 | 30915.5 | 10 | 2022-10-25 | 5 | N/C | 2022-10-27 |  | X | 1462 | 17 | 262 | 1 | 1 | 2B/3T |  | DOC REL 10/06 | SHIPPED 10/27
113636 | 3903.75 | 5 | 2022-10-27 | 5 | 2022-10-21 | 2022-10-28 |  | X | 517 | 43 | 139 | 1 | 1 | 1B/2T |  | KIT CLEAR 10/21 | SHIPPED 10/27
113033 | 4740 | 100 | 2022-10-20 | 9 | 2022-10-13 | 2022-10-26 |  | X | 196 | 9 | 21 | 1 | 1 | 1B/1T |  | KIT CLEAR 10/13 | SHIPPED 10/26
112171 | 3200 | 10 | 2022-10-19 | 5 | 2022-10-18 | 2022-10-26 |  | X | 531 | 6 | 85 | 1 | 1 | 1B/1T | New program ready for bottom - Top side use same program | KIT CLEAR 10/18 | SHIPPED 10/26
113448 | 2500 | 8 | 2022-10-24 | 10 | N/C | ??? |  | X | 558 | 29 | 45 | 1 | 1 | 1B/1T |  | DOC REL 10/11 | SHIPPED 10/26
112877 | 2748 | 100 | 2022-09-27 | 5 | 2022-10-20 | 2022-10-27 |  | X | 42 | 6 | 24 | 0 | 1 | 1T |  | KIT CLEAR 10/20 | SHIPPED 10/26
113311 | 2135 | 3 | 2022-10-18 | 5 | 2022-10-21 | 2022-10-28 |  | X | 519 | 40 | 62 | 1 | 1 | 1B/1T |  | KIT CLEAR 10/21 | SHIPPED 10/26
109349-2 | 1938.48 | 52 | 2022-05-17 | 9 | N/C | 2022-10-25 |  | X | 92 | 15 | 21 | 0 | 1 | 1T |  | SHORT PCB + 1 ITEM | SHIPPED 10/25
112781-2 | 1287 | 95 | 2022-09-20 | 5 | N/C | ??? |  | X | 127 | 4 | 54 | 0 | 1 | 1T | With change 1st Article | SHORT 3 ITEMS | SHIPPED 10/24
113665-1 | 8202 | 50/650 | 2022-11-04 | 5 | 2022-10-17 | 2022-10-24 |  | X | 444 | 16 | 62 | 1 | 1 | 1B/2T | No changes B113064 | KIT CLEAR QTY 400 PARTIAL | SHIPPED 10/24
113057 | 3500 | 6 | 2022-10-17 | 5 | 2022-10-18 | 2022-10-25 |  | X | 542 | 0 | 103 | 1 | 1 | 1B/2T |  | KIT CLEAR 10/18 | SHIPPED 10/21
113502 | 3246.8 | 6 | 2022-10-19 | 5 | 2022-10-19 | 2022-10-26 |  | X | 634 | 9 | 65 | 1 | 1 | 1B/1T |  | KIT CLEAR 10/19 | SHIPPED 10/21
113501 | 3752 | 25 | 2022-10-19 | 5 | 2022-10-18 | 2022-10-25 |  | XR | 241 | 12 | 78 | 0 | 1 | 2T |  | KIT CLEAR 10/18 | SHIPPED 10/21
113179 | 1639.91 | 21 | 2022-10-24 | 9 | 2022-10-07 | 2022-10-20 |  | X | 193 | 3 | 92 | 1 | 1 | 1B/1T |  | KIT CLEAR 10/7 | SHIPPED 10/20
111301 | 4089.5 | 50 | 2022-08-12 | 9 | 2022-10-07 | 2022-10-20 |  | X | 285 | 7 | 105 | 1 | 1 | 1B/2T |  | KIT CLEAR 10/7 | SHIPPED 10/20
112316 | 4218 | 50 | 2022-09-16 | 10 | 2022-10-05 | 2022-10-20 |  | X | 370 | 2 | 66 | 1 | 1 | 1B/1T | With change B111367 | KIT CLEAR 10/6 | SHIPPED 10/20
111850-3 | 4164 | 50 | 2022-09-05 | 10 | 2022-08-25 | 10/20 9/26 10/20 |  | X | 425 | 0 | 97 | 1 | 1 | 2B/2T |  | KIT CLEAR 8/25 | SHIPPED 10/20
112827 | 0 | 20 | 2022-10-07 | 10 | N/C | ??? |  | X | 503 | 52 | 83 | 1 | 1 | 1B/2T |  | KIT CLEAR W/ MULTI SHORT STRIPS - POSS RETURN KIT 10/20 - RETURNED TO AA | SHIPPED 10/20
113277 | 2489 | 2 | 2022-10-21 | 5 | 2022-10-14 | 2022-10-21 |  | X | 96 | 49 | 7 | 1 | 1 | 1T | With change B100732 | KIT CLEAR 10/13 | SHIPPED 10/19
113498 | 3744 | 6 | 2022-10-24 | 5 | 2022-10-14 | 2022-10-21 |  | X | 140 | 2 | 2 | 0 | 1 | 1T |  | KIT CLEAR 10/13 | SHIPPED 10/19
113148 | 1495 | 10 | 2022-10-20 | 10 | 2022-10-07 | 2022-10-21 |  | X | 26 | 0 | 5 | 0 | 1 | 1T | No changes B112985 | KIT CLEAR 10/7 | SHIPPED 10/19
112847 | 1500 | 40 | 2022-10-25 | 15 | N/C | ??? |  | X | 0 | 15 | 0 | 0 | 0 | 0 | THT only | kit clear 9/30 | SHIPPED 10/19
111607-1 | 1948 | 2 | 2022-10-17 | 5 | 2022-10-13 | 2022-10-20 |  | X | 53 | 4 | 27 | 1 | 1 | 1B/1T |  | KIT CLEAR 10/13 | SHIPPED 10/18
106336-2 | 2301.76 | 8 | 2022-01-21 | 15 | 2022-09-28 | 2022-10-19 |  | XR | 747 | 8 | 109 | 1 | 1 | 2B/2T |  | KIT CLEAR 9/28 | SHIPPED 10/18
113270 | 4040 | 3 | 2022-10-03 | 3 | 2022-10-13 | 2022-10-18 |  | X | 499 | 2 | 87 | 1 | 1 | 1B/2T |  | DOC REL 9/29 | SHIPPED 10/18
110275-2 | 4256.1 | 3 | 2022-06-16 | 3 | 2022-10-06 | 2022-10-18 | REJ | X | 888 | 6 | 90 | 1 | 1 | 1B/1T | With change B110167 | KIT CLEAR 10/6 | SHIPPED 10/18
110859-1 | 10740 | 100/220 | 2022-08-18 | 10 | 2022-10-03 | 2022-10-17 |  | X | 265 | 11 | 43 | 1 | 1 | 1B/2T | No change B109097 | PARTIAL KIT CLEAR 10/3 | SHIPPED 10/17
111751-1 | 9500 | 50/300 | 2022-09-13 | 10 | 2022-10-03 | 2022-10-17 |  | X | 453 | 139 | 86 | 1 | 1 | 1B/2T |  | KIT CLEAR 10/3 | SHIPPED 10/17
109219-3 | 649.8 | 60 | 2022-07-08 | 20 | 2022-06-16 | 2022-10-17 |  | X | 45 | 2 | 25 | 0 | 1 | 1T |  | KIT CLEAR 6/16 | SHIPPED 10/17
112771 | 4063.5 | 75 | 2022-10-04 | 5 | 2022-10-07 | 2022-10-14 |  | X | 118 | 2 | 16 | 1 | 1 | 1B/1T |  | KIT CLEAR 10/7 | SHIPPED 10/14
113440-1 | 10950 | 300/400 | 2022-10-19 | 10 | N/C | 10/17* |  | X | 50 | 10 | 22 | 0 | 1 | 2T | No changes B112573 | kit clear 10/6 (NOT REPORTED) | SHIPPED 10/14
105498 | 4124.75 | 5 | 2022-10-10 | 3 | 2022-10-11 | 2022-10-14 |  | X | 853 | 14 | 137 | 1 | 1 | 2B/2T |  | SHORT 19 ITEMS | SHIPPED 10/14
112357/7-2 | 2754.8 | 97 | 2022-10-24 | 10 | N/C | 2022-10-18 |  | X | 71 | 0 | 39 | 1 | 1 | 1B/1T | No changes B110797 | DOC REL 9/6 | SHIPPED 10/13
112357-1 | 8046.4 | 146/243 | 2022-10-24 | 10 | N/C | 9/27* |  | X | 71 | 0 | 39 | 1 | 1 | 1B/1T | No changes B110797 | DOC REL 9/6 | SHIPPED 10/13
112772 | 77.84 | 1 | 2022-10-04 | 5 | 2022-10-05 | ??? |  | X | 135 | 1 | 10 | 1 | 1 | 1B/1T |  | KIT CLEAR 10/5 | SHIPPED 10/13
113037 | 13563.6 | 10 | 2022-10-03 | 3 | 2022-10-10 | 2022-10-13 |  | X | 1126 | 14 | 186 | 1 | 1 | 2B/3T |  | KIT CLEAR 10/10 | SHIPPED 10/13
113394 | 4422.5 | 5 | 2022-10-05 | 3 | 2022-10-10 | 2022-10-13 |  | XR | 464 | 45 | 96 | 1 | 1 | 1B/2T |  | kit clear 10/6 (NOT REPORTED) | SHIPPED 10/13
112992 | 1979.28 | 9 | 2022-10-10 | 10 | 2022-09-29 | 2022-10-13 |  | X | 59 | 35 | 28 | 0 | 1 | 1T | RONC B110745 | KIT CLEAR 9/29 | SHIPPED 10/13
113408 | 8992.5 | 25 | 2022-10-10 | 2 | 2022-10-10 | 2022-10-12 |  | X | 408 | 0 | 109 | 1 | 1 | 2B/1T |  | DOC REL 10/04 | SHIPPED 10/12
112782 | 7039.5 | 3 | 2022-09-28 | 5 | 2022-10-06 | 2022-10-12 | EXP | X | 602 | 34 | 76 | 1 | 1 | 1B/1T |  | DOC REL 10/06 | SHIPPED 10/12
113064 | 6466 | 40 | 2022-09-23 | 3 5 | 2022-10-07 | 2022-10-12 |  | X | 444 | 16 | 62 | 1 | 1 | 1B/2T | No changes B112460 | DOC REL 9/16 | SHIPPED 10/12
112772 | 6560.16 | 74 | 2022-10-04 | 5 | 2022-10-05 | 2022-12-12 |  | X | 135 | 1 | 10 | 1 | 1 | 1B/1T |  | KIT CLEAR 10/5 | SHIPPED 10/12
113077-1 | 2370 | 5 | 2022-09-27 | 5 | 2022-10-04 | 10/12 10/11 |  | X | 374 | 54 | 56 | 1 | 1 | 1B/2T |  | KIT CLEAR 10/4 (10/4 - POWER OUT) | SHIPPED 10/12
110275-1 | 14568.3 | 9 | 2022-06-16 | 3 | 2022-10-06 | 2022-10-11 |  | X | 888 | 6 | 90 | 1 | 1 | 1B/1T | With change B110167 | KIT CLEAR 10/6 | SHIPPED 10/11
113172 | 4139 | 10 | 2022-10-06 | 5 | 2022-10-03 | 10/11 10/10 |  | X | 416 | 72 | 76 | 1 | 1 | 1B/1T |  | KIT CLEAR 10/3 (10/4 - POWER OUT) | SHIPPED 10/11
112598 | 10857.25 | 25 | 2022-09-09 | 5 | 2022-10-04 | 2022-10-11 |  | X | 1023 | 13 | 166 | 1 | 1 | 2B/2T | Do not de-panel | KIT CLEAR 9/29 | SHIPPED 10/11
113081 | 2598 | 160 | 2022-10-07 | 5 | 2022-10-04 | 2022-10-11 |  | X | 3 | 0 | 2 | 0 | 1 | 1T |  | KIT CLEAR 10/4 | SHIPPED 10/10
113082 | 2598 | 160 | 2022-10-10 | 5 | 2022-10-03 | 2022-10-10 |  | X | 3 | 0 | 2 | 0 | 1 | 1T |  | KIT CLEAR 10/3 | SHIPPED 10/10
112553 | 2692.8 | 60 | 2022-10-07 | 10 | 2022-09-26 | 2022-10-10 |  | X | 114 | 20 | 57 | 1 | 1 | 1B/1T | No changes B111909 | KIT CLEAR 9/26 | SHIPPED 10/10
108431 | 5167.64 | 62 | 2022-10-03 | 20 | 2022-09-12 | 2022-10-10 |  | X | 341 | 12 | 106 | 1 | 1 | 1B/2T |  | KIT CLEAR 9/12 | SHIPPED 10/10
112801 | 2640 | 50 | 2022-10-10 | 5 | 2022-10-03 | 2022-10-10 |  | X | 0 | 33 | 0 | 0 | 0 | 0 | THT only | KIT CLEAR 10/3 | SHIPPED 10/10
111675-1 | 6130 | 10 | 2022-08-05 | 3 | 2022-10-03 | 10/10 10/6 |  | X | 583 | 54 | 91 | 1 | 1 | 1B/2T |  | KIT CLEAR 10/3 | SHIPPED 10/7
112443 | 6838.6 | 30 | 2022-10-03 | 5 | 2022-09-30 | 2022-10-07 |  | X | 244 | 66 | 8 | 0 | 1 | 1T |  | KIT CLEAR 9/30 | SHIPPED 10/7
100606-6 | 8297.9 | 13 | 2021-08-24 | 15 | N/C | 2022-10-07 |  | X | 3746 | 5 | 238 | 1 | 1 | 2B/3T |  | 7/18 - BOT SIDE ONLY / 8/24 TOP SIDE | SHIPPED 10/7
110991 | 12990 | 500 | 2022-07-19 | 10 | 2022-09-23 | 2022-10-07 |  | X | 112 | 7 | 41 | 1 | 1 | 1B/1T | No change B108735 | kit clear 9/23 | SHIPPED 10/7
112881-1 | 4124.8 | 1 | 2022-09-27 | 5 | 2022-09-29 | 2022-10-06 |  | X | 707 | 13 | 157 | 1 | 1 | 2B/2T |  | KIT CLEAR 9/29 | SHIPPED 10/6
112128-1 | 780 | 2 | 2022-10-03 | 5 | 2022-09-29 | 2022-10-06 |  | X | 0 | 12 | 0 | 0 | 0 | 0 | THT only | kit clear 9/29 | SHIPPED 10/6
112127-1 | 750 | 2 | 2022-10-03 | 5 | 2022-09-29 | 2022-10-06 |  | X | 8 | 10 | 7 | 0 | 1 | 1T |  | KIT CLEAR 9/29 | SHIPPED 10/6
113150 | 2746 | 25 | 2022-10-07 | 5 | 2022-09-30 | 2022-10-07 |  | X | 198 | 23 | 54 | 0 | 1 | 1T |  | KIT CLEAR 9/30 | SHIPPED 10/5
111754-2 | 1718.5 | 6 | 2022-08-08 | 5 | 2022-09-29 | 2022-10-07 |  | X | 482 | 38 | 65 | 1 | 1 | 1B/1T | With change 1st Article | KIT CLEAR 9/29 | SHIPPED 10/5
108372 | 3857 | 20 | 2022-06-06 | 10 | 2022-09-21 | 2022-10-05 |  | X | 347 | 55 | 93 | 0 | 1 | 2T |  | KIT CLEAR 9/21 | SHIPPED 10/5
107821 | 1754.4 | 34 | 2022-09-26 | 10 | 2022-09-21 | 2022-10-05 |  | X | 31 | 33 | 1 | 1 | 1 | 1B/1T | No change B105244 | KIT CLEAR 9/21 | SHIPPED 10/5
113094 | 7084 | 10 | 2022-09-28 | 5 | 2022-09-27 | 10/5 10/4 |  | XR | 861 | 11 | 133 | 1 | 1 | 2B/2T |  | KIT CLEAR 9/27 (10/4 - POWER OUT) | SHIPPED 10/5
112776-RWK | 900 | 12 |  | 10 | 2022-09-28 | 2022-10-04 | [10 empty] | SHIPPED 10/3
111470-1 | 5921 | 10 | 2022-08-22 | 10 | 2022-09-20 | 2022-10-04 |  | X | 699 | 9 | 151 | 0 | 1 | 3T |  | KIT CLEAR 9/20 QTY 10 | SHIPPED 10/3
112864 | 4471.5 | 50 | 2022-09-23 | 10 | 2022-09-19 | 2022-10-03 |  | X | 300 | 29 | 69 | 1 | 1 | 1B/1T |  | KIT CLEAR 9/19 | SHIPPED 10/3
113279 | 2232 | 150 | 2022-10-04 | 3 | 2022-09-28 | 2022-10-03 |  | X | 0 | 24 | 0 | 0 | 0 | 0 | THT/Press-fit only | KIT CLEAR 9/28 | SHIPPED 9/30
112433 | 6526 | 300 | 2022-09-13 | 4 | 2022-09-26 | 2022-09-30 |  | X | 48 | 0 | 31 | 1 | 1 | 1B/1T |  | KIT CLEAR 9/26 | SHIPPED 9/30
112781-1 | 3797.3 | 5 | 2022-09-20 | 5 | N/C | 9/30* |  | X | 125 | 6 | 52 | 0 | 1 | 1T |  | kit clear 9/30 | SHIPPED 9/30
100606-5 | 55532.1 | 87 | 2021-08-24 | 15 | N/C | 2022-09-30 |  | X | 3746 | 5 | 238 | 1 | 1 | 2B/3T |  | 7/18 - BOT SIDE ONLY / 8/24 TOP SIDE | SHIPPED 9/30
112480 | 3003 | 50 | 2022-09-09 | 5 |  | 9/22 9/29 |  | X | 0 | 100 | 0 | 0 | 0 | 0 | THT only | KIT CLEAR 9/15 | SHIPPED 9/29
112985 | 1495 | 10 | 2022-10-10 | 10 | 2022-09-23 | 2022-10-07 |  | X | 26 | 0 | 5 | 0 | 1 | 1T | No changes B104952 | KIT CLEAR 9/23 | SHIPPED 9/29
107816 | 1555.2 | 3 | 2022-09-12 | 10 | 2022-09-14 | 2022-09-28 |  | X | 792 | 108 | 53 | 1 | 1 | 1B/1T | No changes B104560 | KIT CLEAR 9/14 | SHIPPED 9/28
112810 | 1625 | 125 | 2022-09-15 | 5 | 2022-09-20 | 2022-09-27 |  | X | 28 | 0 | 10 | 1 | 0 | 1B | No changes B111198 | KIT CLEAR 9/20 BUT SHIPPING HOLD | SHIPPED 9/27
112663 | 9050 | 75 | 2022-09-22 | 5 4 | 2022-09-19 | 9/27 9/26 |  | X | 320 | 8 | 90 | 1 | 1 | 1B/1T |  | KIT CLEAR 9/19 | SHIPPED 9/27
113038 | 2092.4 | 40 | 2022-09-23 | 3 | 2022-09-22 | 2022-09-27 |  | X | 67 | 11 | 30 | 1 | 1 | 1B/1T |  | kit clear 9/22 | SHIPPED 9/27
111875 | 625 | 5 |  |  |  | 2022-09-26 |  | X | 28 | 0 | 10 | 1 | 0 | 1B | REWORK PAID | KIT CLEAR 9/20 BUT SHIPPING HOLD | SHIPPED 9/26
112580 | 1572.5 | 250 | 2022-09-19 | 5 | 2022-09-20 | 2022-09-27 |  | X | 4 | 0 | 4 | 1 | 0 | 1B |  | KIT CLEAR 9/20 | SHIPPED 9/26
112228 | 5640 | 20 | 2022-09-07 | 3 | N/C | 2022-09-26 |  | X | 254 | 21 | 72 | 1 | 1 | 1B/1T | No changes B112096 | kit clear 9/21 | SHIPPED 9/26
112809 | 1592 | 200 | 2022-09-22 | 5 | 2022-09-19 | 2022-09-26 |  | X | 17 | 1 | 14 | 0 | 1 | 1T |  | KIT CLEAR 9/19 | SHIPPED 9/26
112758 | 7484.8 | 8 | 2022-09-15 | 5 | 2022-09-19 | 2022-09-26 |  | X | 243 | 142 | 21 | 0 | 1 | 1T |  | KIT CLEAR 9/19 | SHIPPED 9/26
112750-2 | 11226.6 | 405 | 2022-09-22 | 5 | 2022-09-16 | 2022-09-24 |  | X | 54 | 8 | 27 | 1 | 1 | 2B/1T |  | KIT CLEAR 9/16 | SHIPPED 9/24
112096 | 8445.8 | 35 | 2022-08-11 | 3 | N/C | 2022-09-23 |  | X | 254 | 21 | 72 | 1 | 1 | 1B/1T |  | kit clear 9/21 | SHIPPED 9/23
112421 | 2868 | 200 | 2022-09-08 | 10 | 2022-09-09 | 2022-09-23 |  | X | 48 | 4 | 23 | 1 | 1 | 1B/1T | No change B106913 | KIT CLEAR 9/9 | SHIPPED 9/23
112750-1 | 1997.4 | 45 | 2022-09-22 | 5 | 2022-09-16 | 2022-09-23 |  | X | 54 | 8 | 27 | 1 | 1 | 2B/1T |  | KIT CLEAR 9/16 | SHIPPED 9/23
100606-4 | 44681 | 70 | 2021-08-24 | 15 | N/C | 2022-09-23 |  | X | 3746 | 5 | 238 | 1 | 1 | 2B/3T |  | 7/18 - BOT SIDE ONLY / 8/24 TOP SIDE | SHIPPED 9/23
112461 | 5303 | 25 | 2022-09-16 | 5 | 2022-09-16 | 9/22 9/23 |  | X | 381 | 22 | 71 | 1 | 1 | 1B/1T |  | KIT CLEAR 9/16 | SHIPPED 9/22
111850-2 | 4163.5 | 50 | 2022-09-05 | 10 | 2022-08-25 | 2022-09-22 |  | X | 425 | 0 | 97 | 1 | 1 | 2B/2T |  | KIT CLEAR 8/25 | SHIPPED 9/22
111644 | 13344.5 | 50 | 2022-08-04 | 6 10 | 2022-09-13 | 2022-09-21 |  | X | 1033 | 0 | 99 | 1 | 1 | 1B/2T | With change B106969 | KIT CLEAR 9/13 | SHIPPED 9/21
109892 | 1304.1 | 3 | 2022-09-26 | 10 | 2022-09-12 | 2022-09-26 |  | X | 104 | 22 | 23 | 1 | 1 | 1B/1T | No change B107519 | KIT CLEAR 9/12 | SHIPPED 9/21
112502-2 | 547.95 | 3 | 2022-09-12 | 5 | 2022-09-15 | 2022-09-22 |  | XR | 477 | 14 | 118 | 1 | 1 | 1B/2T |  | KIT CLEAR 9/15 BAL | SHIPPED 9/21
111571-2 | 2135 | 50 | 2022-09-07 | 9 | 2022-08-31 | 2022-10-10 |  | X | 89 | 7 | 45 | 0 | 1 | 1T | With change B108042/1st batch of 50 | KIT CLEAR 8/31 | SHIPPED 9/21
112626 | 3874 | 200 | 2022-09-27 | 5 | 2022-09-13 | 2022-09-20 |  | X | 31 | 14 | 3 | 0 | 1 | 1T |  | KIT CLEAR 9/13 | SHIPPED 9/21
111910-2 | 200.8 | 1 | 2022-09-01 | 15 | 2022-08-25 | 9/16H* |  | XR | 353 | 29 | 93 | 1 | 1 | 1B/2T |  | KIT CLEAR 8/25 | SHIPPED 9/19
112029-2 | 11619.4 | 109 | 2022-08-17 | 5 | 2022-09-12 | 2022-09-19 |  | X | 284 | 12 | 91 | 1 | 1 | 1B/2T | No changes 1st Article | KIT CLEAR 9/19 | SHIPPED 9/19
112920 | 5180 | 25 | 2022-09-16 | 3 | 2022-09-14 | 2022-09-19 |  | X | 41 | 14 | 14 | 1 | 1 | 1B/1T | No changes B111746 | kit clear 9/14 | SHIPPED 9/19
112757 | 7866 | 8 | 2022-09-14 | 5 | 2022-09-12 | 2022-09-19 |  | X | 508 | 156 | 34 | 1 | 1 | 1B/1T |  | KIT CLEAR 9/12 | SHIPPED 9/19
112309 | 3672 | 30 | 2022-09-14 | 20 | 2022-08-22 | 2022-09-19 |  | X | 0 | 68 | 0 | 0 | 0 | 0 | THT only/No changes B109946 | KIT CLEAR 8/22 | SHIPPED 9/19
109219-2 | 649.8 | 60 | 2022-07-08 | 20 | 2022-06-16 | 2022-09-19 |  | X | 45 | 2 | 25 | 0 | 1 | 1T |  | KIT CLEAR 6/16 | SHIPPED 9/19
110180 | 4398 | 15 | 2022-09-08 | 10 | 2022-09-01 | 9/16H |  | XR | 284 | 53 | 37 | 1 | 1 | 1B/1T |  | KIT CLEAR 9/1 | SHIPPED 9/19
112502-1 | 8558.05 | 37/40 | 2022-09-12 | 5 | 2022-09-09 | 2022-09-16 |  | XR | 477 | 14 | 118 | 1 | 1 | 1B/2T |  | kit clear 9/15 | SHIPPED 9/16
111910-1 | 3811.2 | 14 | 2022-09-01 | 15 | 2022-08-25 | 9/16H* |  | XR | 353 | 29 | 93 | 1 | 1 | 1B/2T |  | KIT CLEAR 8/25 | SHIPPED 9/16
112759 | 5332 | 8 | 2022-09-14 | 5 | N/C | 9/16* |  | X | 101 | 107 | 22 | 0 | 1 | 1T |  | kit clear 9/9 (INTERNAL) | SHIPPED 9/16
111849 | 12966.5 | 150 | 2022-09-13 | 9 | 2022-09-02 | 9/16H |  | X | 487 | 4 | 95 | 1 | 1 | 2B/2T |  | KIT CLEAR 9/2 | SHIPPED 9/16
112483 | 4284 | 280 |  |  | 2022-08-26 | 9/15H |  | X | 117 | 11 | 52 | 0 | 1 | 2T |  | KIT CLEAR 8/26 | SHIPPED 9/15
112570-2 | 1583.1 | 15 | 2022-09-01 | 3 | 2022-09-12 | 2022-09-15 |  | X | 198 | 16 | 63 | 1 | 1 | 1B/1T |  | KIT CLEAR 9/12 | SHIPPED 9/15
109852 | 6947.5 | 250 | 2022-06-22 | 9 | 2022-09-01 | 9/15H |  | X | 117 | 11 | 52 | 0 | 1 | 2T |  | KIT CLEAR 9/1 | SHIPPED 9/15
111909 | 2692.8 | 60 | 2022-09-09 | 10 | 2022-08-31 | 9/15H |  | X | 114 | 20 | 57 | 1 | 1 | 1B/1T | No change B110848 | KIT CLEAR 8/31 | SHIPPED 9/14
109097-2 | 9785.25 | 75 | 2022-06-03 | 5 | 2022-09-07 | 2022-09-14 |  | X | 265 | 11 | 43 | 1 | 1 | 1B/2T | ROWC B106531 | kit clear 9/7 | SHIPPED 9/14
112492 | 6064.8 | 60 | 2022-09-12 | 5 | 2022-09-02 | 9/15H |  | X | 270 | 0 | 95 | 1 | 1 | 1B/1T |  | KIT CLEAR 9/2 | SHIPPED 9/14
112493 | 3766 | 40 | 2022-09-12 | 5 | 2022-09-02 | 9/15H |  | X | 271 | 0 | 95 | 1 | 1 | 1B/1T |  | KIT CLEAR 9/2 | SHIPPED 9/14
111571-1 | 2135 | 50 | 2022-09-07 | 9 | 2022-08-31 | 9/14H |  | X | 89 | 7 | 45 | 0 | 1 | 1T | With change B108042/1st batch of 50 | KIT CLEAR 8/31 | SHIPPED 9/13
109882-1 | 3528 | 4 | 2022-08-15 | 5 | 2022-09-06 | 2022-09-13 |  | X | 648 | 71 | 93 | 0 | 1 | 2T |  | KIT CLEAR 9/6 | SHIPPED 9/13
112363 | 9301.65 | 3 | 2022-09-02 | 5 | N/C | 9/14* |  | X | 1385 | 14 | 204 | 1 | 1 | 2B/2T |  | kit clear 9/9 | SHIPPED 9/12
111957 | 5402 | 10 | 2022-09-08 | 10 | 2022-08-26 | 9/12H |  | X | 729 | 22 | 117 | 1 | 1 | 1B/2T |  | KIT CLEAR 8/26 | SHIPPED 9/12
107033-2 | 2028.5 | 50 | 2022-05-31 | 20 | 2022-08-18 | 2022-09-15 |  | X | 171 | 14 | 29 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/18 | SHIPPED 9/12
109324-3 | 8378 | 100 | 2022-05-25 | 10 | 2022-08-24 | 2022-09-12 |  | XR | 347 | 9 | 98 | 1 | 1 | 2B/1T | No changes 1st Article | KIT CLEAR 9/2 | SHIPPED 9/9
112156 | 1160 | 50 | 2022-08-19 | 10 | 2022-08-29 | 9/13H |  | X | 69 | 7 | 23 | 0 | 1 | 1T | No changes B108585 | KIT CLEAR 8/29 | SHIPPED 9/9
110178 | 3409 | 20 | 2022-07-08 | 10 | 2022-08-30 | 9/9 9/14H |  | X | 69 | 30 | 24 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/30 | SHIPPED 9/9
111850-1 | 5163.5 | 50 | 2022-09-05 | 10 | 2022-08-25 | 9/9H |  | X | 425 | 0 | 97 | 1 | 1 | 2B/2T |  | KIT CLEAR 8/25 | SHIPPED 9/8
112573 | 12540 | 330 | 2022-08-31 | 3 | 2022-09-02 | 9/8H |  | X | 50 | 10 | 22 | 0 | 1 | 2T | With change B110643 (TZ1 polarity) | kit clear 9/8 | SHIPPED 9/8
109324-2 | 33512 | 400 | 2022-05-25 | 10 | 2022-08-24 | 9/8H |  | XR | 347 | 9 | 98 | 1 | 1 | 2B/1T | No changes 1st Article | KIT CLEAR 9/2 | SHIPPED 9/8
111789 | 3946 | 10 | 2022-08-24 | 3 | 2022-09-01 | 9/7H |  | X | 156 | 0 | 62 | 1 | 1 | 1B/1T |  | KIT CLEAR 9/1 | SHIPPED 9/7
112570-1 | 2777.7 | 5/20 | 2022-09-01 | 3 | 2022-09-01 | 9/7H |  | X | 198 | 16 | 63 | 1 | 1 | 1B/1T |  | KIT CLEAR 9/1 | SHIPPED 9/7
112459 | 3340.99 | 13 | 2022-09-07 | 5 | 2022-08-30 | 9/7H |  | XR | 559 | 3 | 50 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/30 | SHIPPED 9/7
112460 | 11070 | 40 | 2022-08-22 | 2 | 2022-09-07 | 2022-09-09 |  | XR | 444 | 14 | 62 | 1 | 1 | 1B/1T |  | kit clear 9/7 | SHIPPED 9/7
111713 | 2657.5 | 2 | 2022-08-31 | 5 | 2022-08-25 | 2022-09-01 |  | XR | 514 | 102 | 28 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/24 (NOT REPORTED) | SHIPPED 9/1
112442 | 3739 | 100 | 2022-08-29 | 3 | 2022-08-29 | 2022-09-01 |  | XR | 45 | 10 | 39 | 1 | 1 | 1B/1T |  | SMT CLEAR 8/25 KIT CLEAR 8/29 | SHIPPED 9/1
112380 | 2046 | 15 | 2022-08-30 | 5 | 2022-08-25 | 2022-09-01 |  | XR | 38 | 29 | 7 |  |  |  |  | KIT CLEAR 8/25 | SHIPPED 9/1
110268 | 3768.5 | 75 | 2022-08-12 | 10 | 2022-08-17 | 2022-09-01 |  | X | 95 | 13 | 55 | 0 | 1 | 1T |  | KIT CLEAR 8/18 | SHIPPED 9/1
111643-2 | 4486.5 | 15 BAL | 2022-08-19 | 10 | N/C | 2022-08-29 |  | X | 489 | 1 | 165 | 1 | 1 | 2B/2T | With change B107457 | SHORT PCB + 30 ITEMS | SHIPPED 8/31
100606-3 | 54461 | 20 | 2021-08-24 | 15 | N/C | 2022-08-31 |  | X | 3746 | 5 | 238 | 1 | 1 | 2B/3T |  | 7/18 - BOT SIDE ONLY / 8/24 TOP SIDE | SHIPPED 8/31
109942-2 | 1520 | 190 | 2022-05-13 | 5 | 2022-08-24 | 2022-08-31 |  | X | 5 | 4 | 4 | 1 | 1 | 1B/1T | No changes 1st Article | KIT CLEAR 8/24 | SHIPPED 8/31
109333-2 | 4742.5 | 89 | 2022-06-22 | 5 | 2022-08-24 | 2022-08-31 |  | X | 145 | 22 | 42 | 0 | 1 | T | With change 1st Article | KIT CLEAR 8/24 | SHIPPED 8/31
112358 | 2238 | 200 | 2022-08-30 | 10 | 2022-08-18 | 9/1 9/2 |  | X | 32 | 3 | 21 | 1 | 1 | 1B/1T | No changes B108295 | KIT CLEAR 8/18 | SHIPPED 8/30
103558-4 | 1922.44 | 26 | 2021-08-26 | 15 | 2022-08-10 | 2022-08-31 |  | X | 342 | 1 | 93 | 1 | 1 | 2B/2T |  |  | SHIPPED 8/30
112468 | 4054.5 | 50 | 2022-08-24 | 3 | 2022-08-24 | 2022-08-30 |  | XR | 144 | 7 | 47 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/24 | SHIPPED 8/30
109716 | 2037 | 20 | 2022-08-25 | 15 | 2022-08-09 | 2022-08-30 |  | X | 90 | 10 | 55 | 0 | 1 | 1T |  | KIT CLEAR 8/9 | SHIPPED 8/29
110684 | 6930 | 100 | 2022-08-18 | 9 | 2022-08-17 | 2022-08-30 |  | X | 335 | 8 | 53 | 1 | 1 | 1B/1T |  | kit clear 8/17 | SHIPPED 8/29
111643 | 2991 | 10/25 | 2022-08-19 | 10 | N/C | 2022-08-29 |  | X | 489 | 1 | 165 | 1 | 1 | 2B/2T | With change B107457 | SHORT PCB + 30 ITEMS | SHIPPED 8/29
112067 | 3954.6 | 20 | 2022-08-25 | 5 | 2022-08-22 | 2022-08-29 |  | XR | 432 | 1 | 84 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/22 | SHIPPED 8/29
109407 | 3755 | 18 | 2022-08-19 | 10 | 2022-08-15 | 2022-08-29 |  | X | 567 | 6 | 73 | 1 | 1 | 1B/2T |  | KIT CLEAR 8/15 | SHIPPED 8/29
109853 | 7690 | 200 | 2022-06-22 | 9 | 2022-08-16 | 2022-08-29 |  | X | 190 | 6 | 84 | 0 | 1 | 2T |  | KIT CLEAR 8/16 | SHIPPED 8/26
112068 | 6182.4 | 20 | 2022-08-25 | 5 | 2022-08-19 | 2022-08-26 |  | X | 685 | 0 | 126 | 1 | 1 | 2B/1T |  | KIT CLEAR 8/18 - NOT REPORTED | SHIPPED 8/26
110721-1 | 13506.48 | 234/440 | 2022-07-11 | 10 | 2022-08-12 | 2022-08-26 |  | X | 273 | 2 | 39 | 1 | 1 | 1B/2T | Repeat with change B109847 | PARTIAL KIT CLEAR 8/12 | SHIPPED 8/26
110770-2 | 1911.2 | 8 BAL | 2022-07-01 | 5 | 2022-08-10 | 2022-08-17 |  | X | 529 | 9 | 97 | 0 | 1 | 2T |  | KIT CLEAR 7/21 | SHIPPED 8/26
112029-1 | 2596 | 1/110 | 2022-08-17 | 5 | 2022-08-19 | 2022-08-26 |  | X | 284 | 12 | 91 | 1 | 1 | 1B/2T |  |  | SHIPPED 8/25
112227 | 7453 | 20 | 2022-08-19 | 3 | 2022-08-22 | 2022-08-25 |  | X | 561 | 9 | 116 | 1 | 1 | 1B/2T |  | KIT CLEAR 8/22 | SHIPPED 8/25
110113-2 | 4939.35 | 15 | 2022-08-25 | 15 | 2022-07-25 | 2022-08-25 |  | X | 682 | 117 | 57 | 0 | 1 | 2T | RONC B106701 | kit clear 7/25 | SHIPPED 8/25
110203-1 | 1610.8 | 60 | 2022-06-09 | 9 | 2022-06-10 | 2022-08-25 |  | X | 51 | 4 | 25 | 0 | 1 | 1T |  | KIT CLEAR 6/10 | SHIPPED 8/25
107033-1 | 5104.25 | 25 | 2022-05-31 | 20 | 2022-08-18 | 2022-08-25 |  | X | 171 | 14 | 29 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/18 | SHIPPED 8/24
111735 | 7288 | 5 | 2022-08-12 | 3 | 2022-08-19 | 2022-08-24 |  | X | 773 | 27 | 170 | 1 | 1 | 1B/3T |  | KIT CLEAR 8/19 | SHIPPED 8/24
MARVELL |  | 15 |  | 10 | 2022-08-12 | 2022-08-23 |  | X | [8 empty] | SHIPPED 8/24
112235 | 2748.75 | 325 | 2022-08-29 | 5 | 2022-08-18 | 2022-08-25 |  | X | 3 | 0 | 1 | 1 | 0 | 1B |  | KIT CLEAR 8/18 | SHIPPED 8/24
109791-2 | 1420.9 | 80/130 | 2022-06-01 | 10 | N/C | 2022-08-24 |  | X | 49 | 0 | 27 | 1 | 1 | 1B/1T | No changes from 1st Article | SHORT 7 ITEMS | SHIPPED 8/23
111103 | 5271.8 | 18 | 2022-08-11 | 15 | 2022-08-02 | 2022-08-23 |  | X | 467 | 29 | 96 | 1 | 1 | 1B/2T |  | kit clear 8/8 | SHIPPED 8/23
112337 | 1440 | 100 | 2022-08-30 | 5 | 2022-08-18 | 2022-08-25 |  | X | 0 | 24 | 0 | 0 | 0 | 0 | THT/Press-fit only/RONC B109041 | KIT CLEAR 8/18 | SHIPPED 8/23
110896 | 3246 | 300 | 2022-08-22 | 10 | 2022-08-22 | 9/6H |  | X | 32 | 0 | 19 | 0 | 1 | 2T |  | KIT CLEAR 8/22 | SHIPPED 8/22
112406 | 2210 | 200 | 2022-08-23 | 2 | 2022-08-18 | 2022-08-22 |  | X | 4 | 0 | 4 | 1 | 0 | 1B |  | KIT CLEAR 8/18 | SHIPPED 8/22
112148 | 1360 | 40 |  | 10 | 2022-08-08 | 2022-08-22 | [8 empty] | PAID REWORK | KIT CLEAR 8/8 | SHIPPED 8/22
103336-1 | 10682.1 | 249/400 | 2021-09-08 | 10 | 2022-07-28 | 8/19* |  | X | 230 | 2 | 70 | 1 | 1 | 2B/2T | ROWC B98649 | SHORT 5 ITEMS | SHIPPED 8/22
109333 | 0 | 1 |  | 10 | 2022-08-08 | 2022-08-22 | [8 empty] | NC REWORK | KIT CLEAR 8/8
109249-2 | 1250 | 3 | 2022-04-08 | 5 | 2022-08-16 | 2022-08-23 |  | X | 919 | 50 | 110 | 0 | 1 | 2T | No changes from 1st Article | KIT CLEAR 8/16 | SHIPPED 8/19
111199 | 4019 | 5 | 2022-08-10 | 10 | 2022-08-09 | 2022-08-23 |  | X | 480 | 22 | 111 | 1 | 1 | 1B/2T |  | KIT CLEAR 8/9 | SHIPPED 8/19
111818 | 4911.5 | 5 | 2022-08-16 | 10 | 2022-08-09 | 2022-08-23 |  | XR | 644 | 12 | 138 | 1 | 1 | 2B/2T |  | KIT CLEAR 8/9 | SHIPPED 8/19
111657 | 6359.82 | 27 | 2022-08-10 | 5 | 2022-08-10 | 2022-08-17 |  | X | 827 | 37 | 119 | 1 | 1 | 1B/2T |  | KIT CLEAR 8/10 | SHIPPED 8/17
108519 | 3838.6 | 15 | 2022-06-17 | 5 | 2022-08-11 | 2022-08-18 |  | X | 612 | 12 | 127 | 0 | 1 | 2T |  | KIT CLEAR 8/11 | SHIPPED 8/17
111434 | 6159.68 | 96 | 2022-08-16 | 5 | 2022-08-10 | 2022-08-17 |  | X | 252 | 5 | 87 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/10 | SHIPPED 8/17
112050 | 5058 | 20 | 2022-08-15 | 5 | 2022-08-09 | 8/17* |  | X | 345 | 92 | 62 | 1 | 1 | 1B/1T |  | kit clear 8/9 | SHIPPED 8/17
111746 | 2134 | 15 | 2022-07-27 | 2 | 2022-08-11 | 2022-08-16 |  | X | 41 | 14 | 14 | 1 | 1 | 1B/1T | Off hold - kit clear 8/11 | KIT CLEAR 8/11 | SHIPPED 8/16
111368 | 4910 | 2 | 2022-08-18 | 10 | 2022-08-05 | 2022-08-19 |  | X | 1083 | 0 | 215 | 1 | 1 | 2B/2T |  | KIT CLEAR 8/5 | SHIPPED 8/16
109833-2 | 8844.66 | 297 | 2022-06-16 | 15 | 2022-08-04 | 2022-08-25 |  | X | 110 | 12 | 18 | 0 | 1 | 1T | No change 1st Article |  | SHIPPED 8/15
111019 | 2610 | 1 | 2022-08-09 | 3 | 2022-08-09 | 8/12* |  | X | 392 | 154 | 16 | 0 | 1 | 1T |  | KIT CLEAR 8/9 | SHIPPED 8/12
111364 | 2610 | 1 | 2022-08-09 | 3 | 2022-08-09 | 8/12* |  | X | 416 | 189 | 18 | 0 | 1 | 1T |  | KIT CLEAR 8/9 | SHIPPED 8/12
111800 | 6239 | 550 | 2022-08-08 | 5 | 2022-08-05 | 2022-08-12 |  | X | 8 | 6 | 4 | 0 | 1 | 1T |  | KIT CLEAR 8/5 | SHIPPED 8/12
111695-1 | 2060 | 5/130 | 2022-08-12 | 5 | 2022-08-03 | 2022-08-12 |  | X | 423 | 10 | 123 | 1 | 1 | 2B/2T |  | KIT CLEAR 8/3 | SHIPPED 8/12
109004 | 7510 | 150 | 2022-06-30 | 5 | 2022-08-04 | 8/11* |  | X | 184 | 0 | 60 | 1 | 1 | 1B/2T |  | KIT CLEAR 8/4 | SHIPPED 8/11
111349 | 2976.5 | 50 | 2022-08-12 | 5 | 2022-08-04 | 2022-08-11 |  | X | 103 | 24 | 48 | 0 | 1 | 1T |  | KIT CLEAR 8/4 | SHIPPED 8/11
111754-1ST | 1718.5 | 2/8 | 2022-08-08 | 5 | 2022-08-03 | 2022-08-11 |  | X | 482 | 38 | 65 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/3 | SHIPPED 8/11
109324-1ST | 11647 | 100/500 | 2022-05-25 | 5 | 2022-08-03 | 2022-08-10 |  | XR | 347 | 9 | 98 | 1 | 1 | 2B/1T |  | KIT CLEAR 8/3 | SHIPPED 8/10
111198 | 1655 | 125 | 2022-07-21 | 5 | 2022-08-03 | 2022-08-10 |  | X | 28 | 0 | 10 | 1 | 0 | 1B |  | KIT CLEAR 8/3 | SHIPPED 8/10
111757 | 1622.5 | 50 | 2022-08-08 | 5 | 2022-08-03 | 2022-08-10 |  | X | 37 | 9 | 27 | 0 | 1 | 1T |  | KIT CLEAR 8/3 | SHIPPED 8/10
109706-2 | 257.8 | 2 BAL | 2022-06-30 | 10 | 2022-07-28 | ??? |  | X | 410 | 12 | 144 | 1 | 1 | 1B/2T |  | KIT CLEAR 7/28 | SHIPPED 8/9
109706-1 | 4609.2 | 30 | 2022-06-30 | 10 | 2022-07-28 | 2022-08-11 |  | X | 410 | 12 | 144 | 1 | 1 | 1B/2T |  | KIT CLEAR 7/28 | SHIPPED 8/9
110848 | 3039 | 60 | 2022-08-08 | 5 | 2022-08-03 | 2022-08-10 |  | X | 114 | 20 | 57 | 1 | 1 | 1B/1T | No change B109154 | KIT CLEAR 8/3 | SHIPPED 8/9
110691 | 5337.8 | 5 | 2022-07-16 | 10 | 2022-07-27 | 2022-08-10 |  | X | 893 | 57 | 123 | 1 | 1 | 1B/2T |  | kit clear 7/27 | SHIPPED 8/8
109696-2 | 1508.85 | 45 | 2022-05-19 | 5 | 2022-08-02 | 2022-08-09 |  | X | 86 | 11 | 33 | 1 | 1 | 1B/1T | With change 1st Article | KIT CLEAR 8/2 | SHIPPED 8/8
100610-3 | 63451.212 | 22 | 2021-07-12 | 15 | 2022-07-19 | 2022-08-05 |  | X | 3848 | 7 | 237 | 1 | 1 | 2B/3T | With change/1 new ECO note | kit clear 7/19 | SHIPPED 8/5
100605-5 | 10687.63 | 30 | 2021-09-17 | 15 | 2022-06-27 | 2022-08-05 |  | X | 2894 | 4 | 205 | 1 | 1 | 2B/2T | Gerber changed - New program/stencil | KIT CLEAR 6/27 | SHIPPED 8/5
110680-1FA | 2394 | 15 | 2022-07-08 | 5 | 2022-08-01 | 2022-08-08 |  | X | 243 | 7 | 84 | 0 | 1 | 2T |  | KIT CLEAR 8/1 | SHIPPED 8/5
111671 | 1460 | 250 | 2022-08-19 | 9 | 2022-08-02 | 2022-08-15 |  | X | 6 | 0 | 2 | 0 | 1 | 1T | No change B109163 | KIT CLEAR 8/2 | SHIPPED 8/4
109872 | 1107 | 108 | 2022-08-01 | 10 | 2022-07-22 | 2022-08-05 |  | X | 49 | 0 | 19 | 0 | 1 | 1T |  | KIT CLEAR 7/22 | SHIPPED 8/3
111439 | 3475 | 5 | 2022-07-28 | 5 | 2022-07-27 | 2022-08-03 |  | X | 786 | 4 | 83 | 1 | 1 | 1B/2T |  | KIT CLEAR 7/27 | SHIPPED 8/3
111701 | 4173.82 | 42 | 2022-08-03 | 5 | 2022-07-26 | 2022-08-02 |  | X | 245 | 34 | 42 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/26 | SHIPPED 8/2
107934 | 4534.7 | 70 | 2022-06-16 | 20 | 2022-07-05 | 2022-08-02 |  | X | 290 | 1 | 106 | 1 | 1 | 2B/2T | ROWC B100374 | KIT CLEAR 7/5 | SHIPPED 8/2
109830-2 | 13653.97 | 47 | 2022-06-01 | 15 | 2022-07-13 | 2022-08-02 |  | X | 979 | 28 | 144 | 1 | 1 | 2B/1T | With changes | KIT CLEAR 7/12 (7/7) | SHIPPED 8/2
111742 | 1367.5 | 45 | 2022-07-27 | 3 | 2022-07-27 | 2022-08-01 |  | X | 19 | 2 | 15 | 0 | 1 | 1T | With change B109879 | kit clear 7/27 | SHIPPED 8/1
110674 | 5892.72 | 4 | 2022-07-14 | 10 | 2022-07-18 | 2022-08-01 |  | X | 1020 | 42 | 123 | 1 | 1 | 2B/1T |  | KIT CLEAR 7/18 | SHIPPED 8/1
110643-2 | 369.85 | 13 | 2022-06-27 | 5 | 2022-07-19 | 2022-07-26 |  | X | 50 | 10 | 22 | 0 | 1 | 2T |  | kit clear 7/19 | SHIPPED 7/29
110797 | 14418.75 | 250 | 2022-08-01 | 3 | 2022-07-26 | 2022-07-29 |  | X | 71 | 0 | 39 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/26 | SHIPPED 7/29
111175 | 4402.7 | 3 | 2022-08-08 | 5 | 2022-07-22 | 2022-07-29 |  | X | 142 | 41 | 15 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/22 | SHIPPED 7/29
109005 | 4078 | 150 | 2022-06-30 | 10 | 2022-07-15 | 2022-07-29 |  | X | 95 | 0 | 40 | 1 | 1 | 1B/1T | ROWC B107972 | KIT CLEAR 7/7-7/8 7/15 | SHIPPED 7/29
100605-4 | 71250.87 | 200 | 2021-09-17 | 15 | 2022-06-27 | 2022-07-29 |  | X | 2894 | 4 | 205 | 1 | 1 | 2B/2T | Gerber changed - New program/stencil | KIT CLEAR 6/27 | SHIPPED 7/29
109868 | 12132.9 | 610 | 2022-07-05 | 10 | 2022-07-14 | 2022-07-28 |  | X | 9 | 0 | 5 | 1 | 1 | 1B/1T | RONC B106596 | KIT CLEAR 7/14 | SHIPPED 7/29
110770-1 | 4371.8 | 12 | 2022-07-01 | 5 | 2022-07-21 | 2022-07-28 |  | X | 529 | 9 | 97 | 0 | 1 | 2T |  | KIT CLEAR 7/21 | SHIPPED 7/28
108770-2 | 5750 | 500 | 2022-04-26 | 10 | 2022-07-13 | 2022-07-27 |  | X | 70 | 0 | 6 | 1 | 0 | 1B |  | KIT CLEAR 7/13 | SHIPPED 7/27
109165 | 3600 | 1000 | 2022-07-22 | 15 | 2022-07-06 | 2022-07-27 |  | X | 3 | 0 | 3 | 0 | 1 | 1T | RONC B103695 | KIT CLEAR 7/6 | SHIPPED 7/27
111409 | 3630 | 100 | 2022-07-25 | 5 | 2022-07-20 | 2022-07-27 |  | X | 78 | 7 | 25 | 0 | 1 | 1T |  | KIT CLEAR 7/19 | SHIPPED 7/26
111295 | 2133 | 80 | 2022-07-18 | 5 | 2022-07-19 | 2022-07-26 |  | X | 128 | 8 | 49 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/19 | SHIPPED 7/26
110643-2 | 9416.95 | 331 | 2022-06-27 | 5 | 2022-07-19 | 2022-07-26 |  | X | 50 | 10 | 22 | 0 | 1 | 2T |  | kit clear 7/19 | SHIPPED 7/26
109867 | 7405.4 | 610 | 2022-07-05 | 10 | 2022-07-12 | 2022-07-26 |  | X | 7 | 0 | 1 | 1 | 0 | 1B |  | KIT CLEAR 7/12 | SHIPPED 7/25
110779 | 3087.5 | 25 | 2022-06-27 | 15 | 2022-07-01 | 7/25h |  | X | 287 | 46 | 39 | 1 | 1 | 1B/1T |  | smt clear 7/1 | SHIPPED 7/25
108218-3 | 3500 | 200 | 2022-05-16 | 20 | 2022-06-27 | 2022-07-25 |  | X | 127 | 4 | 25 | 1 | 1 | 2B/1T |  | BAL KIT CLEAR 6/27 | SHIPPED 7/25
100616-3 | 1866.64 | 174 | 2021-10-15 | 20 | 2022-06-28 | 2022-07-25 |  | X | 26 | 0 | 7 | 1 | 1 | 1B/1T | Official release Oklahoma - RONC 2nd Article | KIT CLEAR 6/28 | SHIPPED 7/25
111604 | 2000.05 | 64 |  |  |  | 2022-07-22 | [8 empty] | PAID RWK |  | SHIPPED 7/22
110738 | 2113 | 50 | 2022-06-27 | 3 | 2022-07-19 | 2022-07-22 |  | X | 98 | 1 | 49 | 1 | 1 | 1B/1T | RONC B109898 | KIT CLEAR 7/19 | SHIPPED 7/22
110015 | 6500 | 50 | 2022-06-17 | 10 | 2022-07-13 | 2022-07-22 |  | X | 275 | 32 | 38 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/13 | SHIPPED 7/22
111162 | 4792.08 | 2 | 2022-07-21 | 5 | 2022-07-15 | 2022-07-22 |  | X | 2234 | 8 | 32 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/15 | SHIPPED 7/21
104560 | 2898.4 | 4 | 2022-08-18 | 10 | 2022-07-08 | 2022-07-22 |  | X | 789 | 111 | 52 | 1 | 1 | 1B/1T | RONC B98970 | KIT CLEAR 7/8 | SHIPPED 7/21
111105 | 3668.15 | 3 | 2022-07-07 | 3 | 2022-03-18 | 2022-07-21 |  | X | 249 | 42 | 42 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/18 | SHIPPED 7/21
111037 | 11163.2 | 48 | 2022-07-11 | 5 | 2022-07-13 | 2022-07-20 |  | X | 513 | 39 | 80 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/13 | SHIPPED 7/20
110060 | 9011.5 | 10 | 2022-06-23 | 5 | 2022-07-13 | 2022-07-20 |  | X | 819 | 34 | 203 | 1 | 1 | 2B/3T |  | KIT CLEAR 7/13 | SHIPPED 7/20
100617-3 | 5340.797 | 70 | 2021-08-19 | 20 | 2022-06-23 | 2022-07-22 |  | X | 401 | 4 | 54 | 1 | 1 | 1B/1T | Official release Oklahoma - ROWC 2nd Article | KIT CLEAR 6/23 | SHIPPED 7/19
110659 | 3261 | 150 | 2022-06-27 | 5 | 2022-07-13 | 2022-07-20 |  | X | 54 | 0 | 40 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/13 | SHIPPED 7/19
109833-1 | 2801.5 | 3/297 | 2022-06-16 | 5 | 2022-07-14 | 2022-07-21 |  | X | 110 | 12 | 18 | 0 | 1 | 1T |  | KIT CLEAR 7/14 | SHIPPED 7/19
107482-2 | 1250 | 3 | 2022-01-21 | 5 | 2022-07-13 | 2022-07-20 |  | X | 645 | 52 | 108 | 0 | 1 | 2T | No changes from 1st Article | KIT CLEAR 7/8 (NOT REPORTED) | SHIPPED 7/19
107486-2 | 1250 | 3 | 2022-01-26 | 5 | 2022-07-13 | 2022-07-20 |  | X | 573 | 60 | 115 | 0 | 1 | 2T | No changes from 1st Article | KIT CLEAR 7/7 (NOT REPORTED) | SHIPPED 7/18
111367 | 5437.5 | 50 | 2022-07-13 | 5 | 2022-07-12 | 2022-07-19 |  | X | 370 | 2 | 66 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/12 | SHIPPED 7/18
111140 | 6367.6 | 10 | 2022-07-06 | 3 | 2022-07-12 | 2022-07-15 |  | X | 1064 | 80 | 41 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/12 | SHIPPED 7/15
110643-1 | 4135.55 | 119/450 | 2022-06-27 | 5 | 2022-07-08 | 2022-07-15 |  | X | 50 | 10 | 22 | 0 | 1 | 2T |  |  | SHIPPED 7/15
110514 | 4955 | 500 | 2022-07-05 | 5 | 2022-07-05 | 2022-07-18 |  | X | 34 | 0 | 11 | 0 | 1 | 1T |  | KIT CLEAR 6/30 - CAME IN PANEL HAVE TO RUN SINGLE | SHIPPED 7/14
110873 | 2126 | 200 | 2022-07-06 | 5 | 2022-07-07 | 2022-07-14 |  | X | 32 | 7 | 14 | 0 | 1 | 1T |  | KIT CLEAR 7/7 | SHIPPED 7/14
110244 | 5166 | 140 | 2022-07-13 | 5 | 2022-07-07 | 2022-07-14 |  | X | 78 | 9 | 32 | 0 | 1 | 1T |  | KIT CLEAR 7/7 | SHIPPED 7/14
106207 | 4342.5 | 150 | 2021-12-14 | 10 | 2022-06-30 | 7/14h |  | X | 113 | 20 | 41 | 1 | 1 | 1B/1T | ROWC B104539 | KIT CLEAR 6/30 | SHIPPED 7/13
111046 | 4632.1 | 30 | 2022-07-11 | 5 | 2022-07-06 | 2022-07-13 |  | X | 505 | 10 | 91 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/6 | SHIPPED 7/13
110220-2 | 0 | 300 | 2022-06-17 | 10 | 2022-06-16 | 2022-06-30 |  | X | 162 | 1 | 51 | 0 | 1 | 2T |  | KIT CLEAR 6/16 | SHIPPED 7/13
110416-2 | 1998 | 5 | 2022-06-14 | 5 | 2022-07-07 | 2022-07-14 |  | X | 204 | 3 | 65 | 1 | 1 | 1B/1T | With changes | KIT CLEAR 7/7 | SHIPPED 7/12
109333-1 | 1800 | 1 | 2022-06-22 | 5 | 2022-07-06 | 2022-07-13 |  | X | 142 | 22 | 41 | 0 | 1 | 1T |  | KIT CLEAR 7/6 | SHIPPED 7/12
110784 | 3082.8 | 432 | 2022-06-24 | 10 | 2022-06-28 | 7/13h |  | X | 4 | 2 | 3 | 0 | 1 | 1T |  | KIT CLEAR 6/28 | SHIPPED 7/11
110675 | 4211.06 | 46 | 2022-06-15 | 9 | 2022-06-28 | 7/12h |  | X | 288 | 27 | 42 | 1 | 1 | 1B/1T |  | KIT CLEAR 6/28 | SHIPPED 7/11
110743 | 13400 | 159 | 2022-06-24 | 15 | 2022-06-17 | 7/11h |  | X | 363 | 56 | 48 | 1 | 1 | 1B/1T | ROWC B101372 | KIT CLEAR 6/17 | SHIPPED 7/11
109219-1 | 1399.8 | 60 | 2022-07-08 | 20 | 2022-06-16 | 2022-07-10 |  | X | 45 | 2 | 25 | 0 | 1 | 1T |  | KIT CLEAR 6/16 | SHIPPED 7/8
111077 | 1460 | 200 | 2022-07-21 | 9 | 2022-06-28 | 7/12h |  | X | 0 | 3 | 0 | 0 | 0 | 0 | THT only | KIT CLEAR 6/28 | SHIPPED 7/8
110978 | 4654.94 | 11 | 2022-07-06 | 5 | 2022-07-01 | 7/11h |  | X | 601 | 31 | 94 | 1 | 1 | 1B/2T |  | kit clear 7/5 | SHIPPED 7/8
110888 | 6322.8 | 40 | 2022-06-29 | 3 | 2022-07-06 | 2022-07-11 |  | X | 389 | 2 | 81 | 0 | 1 | 2T |  | KIT CLEAR 7/6 | SHIPPED 7/8
110015 | 6340 | 50 | 2022-06-17 | 10 | N/C | ??? |  | X | 275 | 32 | 38 | 1 | 1 | 1B/1T |  | SHORT P7 | SHIP IN PLACE 7/8
104576-3 | 1912 | 10 | 2021-09-16 | 5 | 2022-06-29 | 7/8h |  | X | 750 | 12 | 83 | 1 | 1 | 1B/2T | Official release Oklahoma - RONC 2nd Article | KIT CLEAR 6/29 | SHIPPED 7/7
110220-2 | 9600.7 | 310 | 2022-06-17 | 10 | 2022-06-16 | 2022-06-30 |  | X | 162 | 1 | 51 | 0 | 1 | 2T |  | KIT CLEAR 6/16 | SHIP IN PLACE 7/6
107222 | 3174.18 | 142 | 2022-07-14 | 20 | 2022-06-29 | 2022-07-08 |  | X | 53 | 12 | 12 | 0 | 1 | 1T |  | KIT CLEAR 6/29 | SHIPPED 7/6
109331-2 | 1344.2 | 4 | 2022-05-02 | 3 | 2022-07-05 | 2022-07-07 |  | X | 392 | 7 | 41 | 0 | 1 | 1T | No changes 1st Article but use new set of PCBs - previous had delam issues | KIT CLEAR 7/1 | SHIPPED 7/6
110795 | 3126.4 | 220 | 2022-07-07 | 9 | 2022-06-23 | 7/7h |  | X | 50 | 1 | 31 | 0 | 1 | 1T |  | KIT CLEAR 6/23 | SHIPPED 7/5
108770-1 | 5750 | 500/1000 | 2022-04-26 | 10 | 2022-06-22 | 7/7h |  | X | 70 | 0 | 6 | 1 | 0 | 1B |  | KIT CLEAR 6/22 | SHIPPED 7/5
110794 | 1480.2 | 110 | 2022-07-07 | 9 | 2022-06-20 | 7/5h |  | X | 36 | 1 | 5 | 0 | 1 | 1T |  | KIT CLEAR 6/22 | SHIPPED 7/5
110469 | 5889.32 | 28 | 2022-06-21 | 5 | 2022-06-27 | 7/5h |  | X | 789 | 4 | 81 | 1 | 1 | 1B/1T |  | KIT CLEAR 6/27 | SHIPPED 7/1
100613-3 | 1944.43 | 42 | 2021-08-19 | 20 | 2022-06-14 | 2022-07-12 |  | X | 119 | 4 | 32 | 1 | 1 | 1B/1T | Official release Oklahoma - RONC 2nd Article | KIT CLEAR 6/14 | SHIPPED 7/1
110113-1 | 4939.35 | 15 | 2022-07-01 | 15 | N/C | 2022-07-01 |  | X | 682 | 117 | 57 | 0 | 1 | 2T | RONC B106701 | kit clear 7/25 | SHIPPED 6/30
108135 | 9011.5 | 25 | 2022-06-30 | 10 | 2022-06-17 | 2022-07-01 |  | X | 150 | 30 | 39 | 0 | 1 | 1T |  | KIT CLEAR 6/17 (ALTA) | SHIPPED 6/30
110745 | 1540 | 25 | 2022-07-01 | 9 | 2022-06-17 | 2022-06-30 |  | X | 59 | 35 | 28 | 0 | 1 | 1T |  | KIT CLEAR 6/17 | SHIPPED 6/30
104575-2 | 798.8 | 8 | 2021-09-22 | 10 | 2022-06-14 | 2022-07-07 |  | X | 203 | 2 | 63 | 1 | 1 | 1B/2T | Official release Oklahoma - ROWC 1st Article | KIT CLEAR 6/14 | SHIPPED 6/29
110311 | 2358.75 | 25 | 2022-07-05 | 5 | 2022-06-22 | 2022-06-29 |  | X | 4 | 11 | 3 | 0 | 1 | 1T |  | KIT CLEAR 6/22 | SHIPPED 6/29
110135-2 | 1883.7 | 105 | 2022-05-20 | 5 | 2022-06-22 | 2022-06-29 |  | X | 69 | 0 | 33 | 1 | 1 | 1B/1T | ROWC B108063 | BAL KIT CLEAR 6/22 | SHIPPED 6/29
110511 | 5660 | 500 | 2022-06-20 | 5 | 2022-06-22 | 2022-06-29 |  | X | 29 | 2 | 14 | 0 | 1 | 1T |  | KIT CLEAR 6/22 | SHIPPED 6/29
110195 | 2782.25 | 25 | 2022-06-13 | 9 | 2022-06-16 | 2022-06-29 |  | X | 245 | 22 | 91 | 1 | 1 | 1B/2T |  | KIT CLEAR 6/16 | SHIPPED 6/29
109558-3 | 8874 | 980 | 2022-06-01 | 10 | 2022-06-21 | 7/6h |  | X | 14 | 0 | 6 | 1 | 1 | 1B/1T | No changes from 1st Article | KIT CLEAR 6/21 | SHIPPED 6/29
109558-2 | 4930 | 500/1480 | 2022-06-01 | 10 | 2022-06-15 | 2022-06-29 |  | X | 14 | 0 | 6 | 1 | 1 | 1B/1T | No changes from 1st Article | DOC REL 6/15 | SHIPPED 6/29
110622 | 2909.9 | 7 | 2022-06-15 | 5 | 2022-06-22 | 2022-06-29 |  | X | 473 | 55 | 43 | 0 | 1 | 1T |  | KIT CLEAR 6/22 | SHIPPED 6/28
109361 | 4837 | 100 | 2022-05-23 | 10 | N/C | 2022-06-29 |  | X | 134 | 4 | 73 | 1 | 1 | 1B/2T |  | ALTA kit clear 6/9 | SHIPPED 6/28
110392-2 | 3035.1 | 18 | 2022-05-20 | 5 | 2022-06-17 | 2022-06-29 |  | X | 208 | 39 | 64 | 1 | 1 | 1B/2T |  | KIT CLEAR 6/24 | SHIPPED 6/28
110318 | 2775.25 | 25 | 2022-07-07 | 5 | 2022-06-21 | 2022-06-28 |  | X | 102 | 15 | 26 | 1 | 1 | 1B/1T |  | KIT CLEAR 6/21 | SHIPPED 6/28
104636-3 | 7996 | 200/800 | 2021-05-27 | 20 | N/C | 2022-06-15 |  | X | 148 | 9 | 59 | 1 | 1 | 1B/1T | ROWC B104272 | SHORT PCB + 62 ITEMS | SHIPPED 6/28
110538 | 1581.6 | 240 | 2022-06-29 | 5 | 2022-06-21 | 2022-06-28 |  | X | 9 | 0 | 8 | 0 | 1 | 1T |  | KIT CLEAR 6/21 | SHIPPED 6/27
110695 | 6769.5 | 10 | 2022-06-17 | 3 | 2022-06-22 | 2022-06-27 |  | X | 715 | 0 | 128 | 1 | 1 | 2B/2T |  | SHORT 2 ITEMS | SHIPPED 6/27
110405 | 3794.5 | 5 | 2022-06-13 | 5 | 2022-06-20 | 2022-06-27 |  | X | 835 | 9 | 96 | 1 | 1 | 1B/2T |  | KIT CLEAR 6/20 | SHIPPED 6/27
110751 | 3436.8 | 70 | 2022-06-28 | 5 | 2022-06-20 | 2022-06-27 |  | X | 149 | 3 | 44 | 0 | 1 | 2T | ROWC B97132 | KIT CLEAR 6/20 | SHIPPED 6/27
110540 | 1581.6 | 240 | 2022-06-29 | 5 | 2022-06-20 | 2022-06-27 |  | X | 7 | 0 | 7 | 0 | 1 | 1T |  | KIT CLEAR 6/20 | SHIPPED 6/24
110928 | 1758.45 | 3 | 2022-06-22 | 5 | 2022-06-17 | 2022-06-24 |  | X | 869 | 26 | 101 | 1 | 1 | 1B/2T | ROWC B104156 | KIT CLEAR 6/17 | SHIPPED 6/24
109985 | 4741.4 | 6 | 2022-06-10 | 5 | 2022-06-17 | 2022-06-24 |  | X | 856 | 14 | 58 | 1 | 1 | 1B/1T |  | KIT CLEAR 6/21 (BAKE) | SHIPPED 6/24
110135-1 | 1557.3 | 45/150 | 2022-05-20 | 5 | N/C | ??? |  | X | 69 | 0 | 33 | 1 | 1 | 1B/1T | ROWC B108063 | SHORT 1 ITEM | SHIPPED 6/23
109898-2 | 3515 | 63 | 2022-06-01 | 5 | 2022-06-20 | 6/23* |  | X | 98 | 1 | 49 | 1 | 1 | 1B/1T |  | KIT CLEAR 6/20 - *FABS REJ | SHIPPED 6/23
109695-2 | 1328 | 45 | 2022-05-19 | 5 | 2022-06-16 | 2022-06-23 |  | X | 76 | 11 | 31 | 1 | 1 | 1B/1T | No changes from 1st Article | DOC REL 6/15 | SHIPPED 6/23
108822 | 4185 | 150 | 2022-06-16 | 5 | 2022-06-16 | 2022-06-23 |  | X | 100 | 0 | 7 | 1 | 1 | 1B/1T |  | KIT CLEAR 6/16 | SHIPPED 6/23
109877-3 | 2694 | 60 | 2022-06-02 | 5_10_20 | 2022-05-25 | 2022-06-23 |  | X | 114 | 20 | 57 | 1 | 1 | 1B/1T | RONC B109154 | KIT CLEAR 5/25 | SHIPPED 6/23
110220-1 | 10431.3 | 300/600 | 2022-06-17 | 10 | 2022-06-10 | 2022-06-24 |  | X | 162 | 1 | 51 | 0 | 1 | 2T |  | PARTIAL CLEAR 6/10 | SHIPPED 6/23
109000 | 1572.5 | 150 | 2022-06-16 | 5 | 2022-06-16 | 2022-06-23 |  | X | 5 | 5 | 2 | 0 | 1 | 1T |  | KIT CLEAR 6/16 | SHIPPED 6/23
110614 | 7761.75 | 15 | 2022-06-10 | 3 | 2022-06-20 | 2022-06-23 |  | X | 884 | 18 | 115 | 1 | 1 | 1B/2T |  | KIT CLEAR 6/20 | SHIPPED 6/23
110392-1 | 2923.4 | 12/30 | 2022-05-20 | 5 | 2022-06-17 | 2022-06-22 |  | X | 208 | 39 | 64 | 1 | 1 | 1B/2T |  | KIT CLEAR 6/17 | SHIPPED 6/22
110857 | 4077.64 | 31 | 2022-06-20 | 3 | N/C | 2022-06-17 | 2022-06-22 | X | 110 | 57 | 27 | 0 | 1 | 1T |  | KIT CLEAR 6/17 | SHIPPED 6/22
110733 | 3387.75 | 25 | 2022-06-13 | 5 | 2022-06-15 | 2022-06-22 |  | X | 327 | 31 | 21 | 1 | 1 | 1B/1T |  | KIT CLEAR 6/15 | SHIPPED 6/22
110539 | 1581.6 | 240 | 2022-06-24 | 5 | 2022-06-17 | 2022-06-24 |  | X | 12 | 0 | 9 | 0 | 1 | 1T |  | KIT CLEAR 6/17 | SHIPPED 6/21
110387 | 1650 | 3 | 2022-06-14 | 5 | 2022-06-16 | 2022-06-23 |  | X | 0 | 2 | 0 | 0 | 0 | 0 | THT only | KIT CLEAR 6/16 | SHIPPED 6/21
110487 | 3262.16 | 8 | 2022-06-10 | 3 | 2022-06-16 | 2022-06-21 |  | X | 483 | 38 | 100 | 0 | 1 | 2T |  | KIT CLEAR 6/16 | SHIPPED 6/20
108241 | 2174 | 20 | 2022-04-06 | 10 | 2022-06-07 | 2022-06-21 |  | X | 80 | 62 | 25 | 1 | 0 | 1B |  | KIT CLEAR 6/7 | SHIPPED 6/20
110512 | 4255 | 500 | 2022-06-20 | 5 | 2022-06-14 | 2022-06-21 |  | X | 21 | 2 | 11 | 0 | 1 | 1T |  | KIT CLEAR 6/14 | SHIPPED 6/20
110172-2 | 5815.5 | 15 | 2022-05-20 | 5 | 2022-06-13 | 2022-06-20 |  | X | 1070 | 54 | 87 | 1 | 1 | 1B/2T | ROWC 1st Article | KIT CLEAR 6/13 | SHIPPED 6/17
110186 | 2909.4 | 28 | 2022-06-13 | 10 | 2022-06-03 | 2022-06-17 |  | X | 156 | 26 | 32 | 1 | 1 | 1B/1T |  | KIT CLEAR 6/3 | SHIPPED 6/17
109617-2 | 2715.6 | 60 | 2022-05-30 | 10 | 2022-06-07 | 2022-06-21 |  | X | 183 | 0 | 51 | 1 | 1 | 1B/1T | ROWC 1st Article | KIT CLEAR 6/7 | SHIPPED 6/17
110556 | 3922.26 | 43 | 2022-05-31 | 5 | 2022-06-09 | 2022-06-16 |  | X | 233 | 29 | 67 | 1 | 1 | 1B/1T |  | KIT CLEAR 6/9 | SHIPPED 6/16
110481 | 1500 | 15 | 2022-06-10 | 5 | 2022-06-09 | 2022-06-16 |  | X | 214 | 0 | 56 | 1 | 1 | 1B/1T | AA transfer | KIT CLEAR 6/9 | SHIPPED 6/15
108218-2 | 5250 | 300 | 2022-05-16 | 20 | 2022-05-31 | 2022-06-15 |  | X | 127 | 4 | 25 | 1 | 1 | 2B/1T |  | kit clear 6/27 | SHIPPED 6/15
110214 | 1846 | 142 | 2022-06-07 | 20 | 2022-05-18 | 2022-06-15 |  | X | 0 | 2 | 0 | 0 | 0 | 0 | THT only | KIT CLEAR 5/18 | SHIPPED 6/15
110099 | 4039 | 30 | 2022-06-06 | 5 | 2022-06-06 | 2022-06-13 |  | X | 428 | 0 | 99 | 1 | 1 | 1B/1T |  | kit clear 6/6 | SHIPPED 6/15
110042 | 2000 | 25 | 2022-06-08 | 5 | 2022-06-08 | 2022-06-15 |  | X | 99 | 10 | 45 | 0 | 1 | 1T | AA transfer | KIT CLEAR 6/8 | SHIPPED 6/14
110550 | 3000 | 25 | 2022-06-06 | 4 | 2022-06-09 | 2022-06-15 |  | X | 280 | 10 | 60 | 0 | 1 | 1T | AA transfer | KIT CLEAR 6/9 | SHIPPED 6/14
109830-1 | 2255.95 | 3/47 | 2022-06-01 | 5 | 2022-06-07 | 2022-06-14 |  | X | 979 | 28 | 144 | 1 | 1 | 2B/1T |  | kit clear 6/7 | SHIPPED 6/14
108170 | 2994 | 30 | 2022-03-11 | 10 | 2022-05-31 | 2022-06-13 |  | XR | 259 | 23 | 72 | 1 | 1 | 1B/2T |  | KIT CLEAR 5/31 | SHIPPED 6/14
109006 | 2405 | 150 | 2022-06-16 | 5 | 2022-06-07 | 2022-06-14 |  | X | 30 | 3 | 12 | 1 | 1 | 1B/1T |  | KIT CLEAR 6/7 | SHIPPED 6/13
110416-1 | 2148 | 5 | 2022-06-14 | 5 | 2022-06-06 | 2022-06-13 |  | X | 205 | 3 | 65 | 1 | 1 | 1B/1T |  | KIT CLEAR 6/6 | SHIPPED 6/13
104910-4 | 3910 | 20 | 2022-03-02 | 5 | 2022-06-03 | 2022-06-10 |  | X | 917 | 1 | 167 | 1 | 1 | 2B/2T |  | KIT CLEAR 6/3 | SHIPPED 6/10
110196 | 3125 | 100 | 2022-06-15 | 5 | 2022-06-03 | 2022-06-10 |  | X | 70 | 11 | 34 | 0 | 1 | 1T |  | KIT CLEAR 6/3 | SHIPPED 6/10
109885 | 4387 | 75 | 2022-05-18 | 15 | 2022-05-20 | 2022-06-10 |  | X | 173 | 18 | 50 | 1 | 1 | 1B/2T |  | KIT CLEAR 5/20 | SHIPPED 6/10
110501 | 1750 | 16 | 2022-06-06 | 3 | 2022-06-07 | 2022-06-13 |  | X | 116 | 0 | 45 | 1 | 1 | 1B/1T | AA transfer | KIT CLEAR 6/7 | SHIPPED 6/9
110168 | 2986.7 | 3 | 2022-06-16 | 10 | 2022-06-01 | 2022-06-15 |  | X | 264 | 110 | 8 | 0 | 1 | 1T |  | KIT CLEAR 6/1 | SHIPPED 6/9
109898-1 | 1359.75 | 37/100 | 2022-06-01 | 5 | N/C | 2022-06-09 |  | X | 98 | 1 | 49 | 1 | 1 | 1B/1T |  | SHORT PCB | SHIPPED 6/9
110699 | 1800 | 100 | 2022-06-09 | 3 | 2022-06-06 | 2022-06-09 |  | X | 0 | 24 | 0 | 0 | 0 | 0 | THT/Press-fit only | KIT CLEAR 6/6 | SHIPPED 6/9
109877-2 | 1519.5 | 30 | 2022-06-02 | 5_10_20 | 2022-05-25 | 2022-06-09 |  | X | 114 | 20 | 57 | 1 | 1 | 1B/1T | RONC B109154 | KIT CLEAR 5/25 | SHIPPED 6/9
109579 | 5337.11 | 27 | 2022-05-04 | 5 | 2022-06-01 | 2022-06-09 |  | X | 529 | 41 | 109 | 1 | 1 | 1B/2T |  | SHORT FABS | SHIPPED 6/9
110100 | 2520 | 4 | 2022-06-07 | 10 | 2022-05-26 | 2022-06-10 |  | X | 663 | 27 | 81 | 1 | 1 | 1B/2T |  | KIT CLEAR 5/26 | SHIPPED 6/8
109984 | 4086.8 | 110 | 2022-06-03 | 10 | 2022-05-24 | 2022-06-08 |  | X | 117 | 7 | 45 | 1 | 1 | 2B/1T |  | KIT CLEAR 5/24 | SHIPPED 6/8
109946 | 3876 | 30 | 2022-05-24 | 10 | 2022-05-23 | 2022-06-08 |  | X | 0 | 68 | 0 | 0 | 0 | 0 | THT only | KIT CLEAR 5/23 | SHIPPED 6/8
109791-1 | 2465 | 20 | 2022-06-01 | 10 | N/C | ??? |  | X | 49 | 0 | 27 | 1 | 1 | 1B/1T |  | DOC REL 5/16 | SHIPPED 6/7
110400 | 1459.8 | 115 | 2022-06-24 | 9 | 2022-06-03 | 2022-06-16 |  | X | 7 | 0 | 5 | 1 | 1 | 1B/1T |  | KIT CLEAR 6/3 | SHIPPED 6/7
110019 | 1655 | 13 | [12 empty] | RWK | KIT CLEAR 5/26 | SHIPPED 6/6
110237 | 4678 | 110 | 2022-06-08 | 5 | 2022-05-26 | 2022-06-06 |  | X | 131 | 4 | 51 | 1 | 1 | 1B/1T |  | KIT CLEAR 5/26 | SHIPPED 6/6
109678 | 2906 | 25 | 2022-05-20 | 5 | 2022-05-27 | 2022-06-06 |  | X | 195 | 30 | 69 | 0 | 1 | 2T |  | KIT CLEAR 5/27 | SHIPPED 6/6
109097-1 | 8175.85 | 55/130 | 2022-06-03 | 5 | 2022-05-26 | 2022-06-03 |  | X | 265 | 11 | 43 | 1 | 1 | 1B/2T | ROWC B106531 | kit clear 9/7 | SHIPPED 6/3
109768 | 5482 | 200 | 2022-06-03 | 5 | 2022-05-26 | 2022-06-03 |  | X | 100 | 6 | 50 | 0 | 1 | 2T |  | KIT CLEAR 5/26 | SHIPPED 6/3
110354 | 3492 | 3 | 2022-05-24 | 5 | 2022-05-31 | 2022-06-06 |  | X | 462 | 60 | 53 | 1 | 1 | 1B/1T |  | KIT CLEAR 5/31 | SHIPPED 6/2
110288 | 1129.5 | 45 | 2022-06-08 | 5 | 2022-05-31 | 2022-06-06 |  | X | 24 | Zestron | 11 | 0 | 1 | 1T | ROWC B95097 | KIT CLEAR 5/31 | SHIPPED 6/2
109877-1 | 1692 | 30 | 2022-06-02 | 5_10_20 | 2022-05-25 | 2022-06-02 |  | X | 114 | 20 | 57 | 1 | 1 | 1B/1T | RONC B109154 | KIT CLEAR 5/25 | SHIPPED 6/2
110177 | 2948.6 | 60 | 2022-05-25 | 9 | 2022-05-23 | 2022-06-03 |  | X | 109 | 18 | 61 | 1 | 1 | 1B/1T | ROWC B108553 | KIT CLEAR 5/23 | SHIPPED 6/1
108838 | 4883.73 | 9 | 2022-04-20 | 5 | 2022-06-01 | 2022-06-08 |  | X | 746 | 4 | 52 | 1 | 1 | 1B/1T |  | KIT CLEAR 6/1 | SHIPPED 6/1
109558-1 | 8690 | 20 | 2022-06-01 | 5 | 2022-05-25 | 2022-06-02 |  | X | 14 | 0 | 6 | 1 | 1 | 1B/1T |  | KIT CLEAR 5/25 | SHIPPED 5/31
110040 | 3587 | 100 | 2022-06-01 | 10 | 2022-05-20 | 2022-06-03 |  | X | 100 | 5 | 38 | 0 | 1 | 1T |  | kit clear 5/20 | SHIPPED 5/31
108701 | 2586.5 | 9 | 2022-05-13 | 10 | 2022-05-18 | 2022-06-01 |  | X | 33 | 0 | 20 | 0 | 1 | 1T |  | KIT CLEAR 5/18 | SHIPPED 5/31
108951 | 2140.38 | 138 | 2022-05-23 | 10 | 2022-05-18 | 2022-06-01 |  | X | 55 | 3 | 23 | 1 | 1 | 1B/1T | ROWC B105166 | KIT CLEAR 5/18 | SHIPPED 5/31
108945 | 9516.4 | 32 | 2022-04-01 | 3 | N/C | ??? |  | X | 873 | 1 | 182 | 1 | 1 | 2B/2T |  | kit clear 5/27 | SHIPPED 5/27
104910-3 | 35190 | 180/200 | 2022-03-02 | 5 | N/C | 2022-05-27 |  | X | 917 | 1 | 167 | 1 | 1 | 2B/2T |  | DOC REL 3/7 | SHIPPED 5/27
109331-1 | 2104.3 | 1/5 | 2022-05-02 | 5 | 2022-05-20 | 2022-05-27 |  | X | 392 | 7 | 41 | 0 | 1 | 1T |  | KIT CLEAR 5/20 | SHIPPED 5/27
109349-1 | 3446.19 | 128/180 | 2022-05-17 | 9 | N/C | 2022-05-27 |  | X | 92 | 15 | 21 | 0 | 1 | 1T |  | SHORT PCB + 1 ITEM | SHIPPED 5/27
110172-1 | 3931 | 5/15 | 2022-05-20 | 5 | 2022-05-23 | 5/27* |  | X | 1070 | 54 | 87 | 1 | 1 | 1B/2T |  | kit clear 5/23 | SHIPPED 5/27
109970 | 3515.5 | 25 | 2022-05-24 | 5 | 2022-05-20 | 2022-05-27 |  | X | 304 | 37 | 88 | 1 | 1 | 1B/2T |  | KIT CLEAR 5/20 | SHIPPED 5/26
108218-2 | 7000 | 400 | 2022-05-16 | 20 | N/C | 2022-05-26 |  | X | 127 | 4 | 25 | 1 | 1 | 2B/1T |  | kit clear 6/27 | SHIPPED 5/26
110030 | 3936.1 | 30 | 2022-05-26 | 9 | 2022-05-16 | 2022-05-27 |  | X | 486 | 0 | 90 | 1 | 1 | 1B/1T |  | KIT CLEAR 5/16 | SHIPPED 5/25
109679 | 3392.5 | 25 | 2022-05-13 | 5 | 2022-05-19 | 2022-05-26 |  | X | 270 | 33 | 68 | 1 | 1 | 1B/2T |  | KIT CLEAR 5/19 | SHIPPED 5/25
110022 | 9845.6 | 60 | 2022-05-20 | 15 | 2022-05-05 | 2022-05-26 |  | X | 766 | 38 | 109 | 1 | 1 | 1B/2T |  | KIT CLEAR 5/5 | SHIPPED 5/24
110259 | 2640 | 300 | 2022-05-24 | 5 | 2022-05-18 | 2022-05-25 |  | X | 14 | 0 | 6 | 0 | 1 | 1T |  | KIT CLEAR 5/18 | SHIPPED 5/24
110088 | 750.2 | 44 | 2022-05-27 | 9 | 2022-05-13 | 2022-05-26 |  | X | 1 | 16 | 1 | 0 | 1 | 1T |  | KIT CLEAR 5/13 | SHIPPED 5/23
109617-1 | 2232 | 5 | 2022-05-30 | 5 | 2022-05-18 | 2022-05-25 |  | X | 186 | 0 | 52 | 1 | 1 | 1B/1T |  | DOC REL 5/9 | SHIPPED 5/23
108947 | 1987 | 300 | 2022-05-18 | 10 | 2022-05-11 | 2022-05-25 |  | X | 96 | 3 | 38 | 1 | 1 | 2B/2T |  | KIT CLEAR 5/11 | SHIPPED 5/23
110167 | 4123.75 | 3 | 2022-05-13 | 3 | 2022-05-19 | 2022-05-25 |  | X | 862 | 56 | 89 | 1 | 1 | 1B/1T |  | KIT CLEAR 5/19 | SHIPPED 5/23
106484 | 1700 | 2 | 2022-05-04 | 5 | 2022-05-18 | 2022-05-25 |  | X | 944 | 84 | 59 | 0 | 1 | 2T | ROWC B93995 | KIT CLEAR 5/18 | SHIPPED 5/20
109942-1 | 1780 | 10/190 | 2022-05-13 | 5 | 2022-05-18 | 2022-05-25 |  | X | 5 | 4 | 4 | 1 | 1 | 1B/1T |  | KIT CLEAR 5/18 | SHIPPED 5/20
108252-2 | 1744.82 | 103 | 2022-03-07 | 10 | 2022-05-10 | 2022-05-24 |  | X | 72 | 5 | 30 | 0 | 1 | 1T |  | KIT CLEAR 5/10 | SHIPPED 5/20
108735 | 11375 | 500 | 2022-05-20 | 15 | 2022-04-28 | 2022-05-20 |  | X | 112 | 7 | 41 | 1 | 1 | 1B/1T | ROWC B104930 | KIT CLEAR 4/27 (ALTA) | SHIPPED 5/20
110176 | 3910.75 | 5 | 2022-05-23 | 3 | N/C | ??? |  | X | 725 | 29 | 141 | 1 | 1 | 2B/2T |  | kit clear 5/18 | SHIPPED 5/19
108603-2 | 375 | 10 | 2022-03-16 | 3 | 2022-05-18 | 2022-05-23 |  | XR | 44 | 26 | 31 | 1 | 1 | 1B/1T |  | KIT CLEAR 5/18 | SHIPPED 5/19
109695-1 | 1328 | 5 | 2022-05-19 | 3 | 2022-05-17 | 2022-05-20 |  | X | 76 | 11 | 31 | 1 | 1 | 1B/1T |  | KIT CLEAR 5/17 | SHIPPED 5/19
109696-1 | 1338 | 5 | 2022-05-19 | 3 | 2022-05-17 | 2022-05-20 |  | X | 85 | 11 | 33 | 1 | 1 | 1B/1T |  | KIT CLEAR 5/17 | SHIPPED 5/19
109536-2 | 5553 | 150 | 2022-05-12 | 5 | 2022-05-10 | 2022-05-18 |  | X | 373 | 0 | 83 | 1 | 1 | 2B/2T |  | KIT CLEAR 5/10 | SHIPPED 5/18
110095 | 3800 | 100 | 2022-05-23 | 3 | 2022-05-16 | 2022-05-19 |  | X | 0 | 1 | 0 | 0 | 0 | 0 | THT only, RONC B106693 | KIT CLEAR 5/16 | SHIPPED 5/18
109847-4 | 12121.2 | 210 | 2022-05-12 | 140 | 2022-05-04 | 2022-05-18 |  | X | 275 | 1 | 41 | 1 | 1 | 1B/2T |  | KIT CLEAR 5/4 | SHIPPED 5/18
109847-3 | 9235.2 | 160 | 2022-05-12 | 140 | 2022-05-04 | 2022-05-18 |  | X | 275 | 1 | 41 | 1 | 1 | 1B/2T |  | KIT CLEAR 5/4 | SHIPPED 5/17
109054 | 2447.5 | 1 | 2022-04-20 | 5 | 2022-05-11 | 2022-05-18 |  | X | 477 | 94 | 24 | 0 | 1 | 1B/1T |  | KIT CLEAR 5/11 | SHIPPED 5/17
109419-2 | 3133.35 | 11 | 2022-04-20 | 5 | 2022-05-10 | 2022-05-17 |  | X | 924 | 3 | 165 | 1 | 1 | 2B/2T |  | KIT CLEAR 5/10 | SHIPPED 5/17
109536-1 | 5553 | 150/300 | 2022-05-12 | I | 2022-05-10 | 2022-05-17 |  | X | 373 | 0 | 83 | 1 | 1 | 2B/2T |  | KIT CLEAR 5/10 | SHIPPED 5/17
109527 | 5526 | 50 | 2022-05-13 | 3 | 2022-05-11 | 2022-05-16 |  | X | 247 | 0 | 88 | 1 | 1 | 1B/1T |  | KIT CLEAR 5/11 | SHIPPED 5/16
108218-1 | 2050 | 100/1000 | 2022-05-16 | 20 | N/C | 2022-05-16 |  | X | 127 | 4 | 25 | 1 | 1 | 2B/1T |  | kit clear 6/27 | SHIPPED 5/16
109941 | 3924 | 2 | 2022-05-13 | 5 | 2022-05-09 | 2022-05-16 |  | X | 2335 | 9 | 32 | 1 | 1 | 1B/1T |  | KIT CLEAR 5/6 | SHIPPED 5/16
108737 | 1560 | 12 | 2022-04-15 | 9 | 2022-05-10 | 2022-05-23 |  | X | 95 | 28 | 31 | 1 | 1 | 1B/1T |  | KIT CLEAR 5/10 | SHIPPED 5/13
108907-3 | 1764 | 21 | 2022-03-30 | 5 | 2022-05-10 | 2022-05-17 |  | X | 0 | 70 | 0 | 0 | 0 | 0 | THT only | KIT CLEAR 5/10 | SHIPPED 5/13
109689 | 2525 | 20 | 2022-05-16 | 5 | 2022-05-06 | 2022-05-13 |  | X | 110 | 55 | 27 | 0 | 1 | 1T |  | KIT CLEAR 5/6 | SHIPPED 5/13
108472-2 | 2746.2 | 138 | 2022-04-01 | 10 | 2022-04-29 | 2022-05-13 |  | X | 102 | 4 | 49 | 1 | 1 | 1B/1T |  | KIT CLEAR 4/29 | SHIPPED 5/13
109694 | 4060.5 | 10 | 2022-05-09 | 5 | 2022-05-05 | 2022-05-12 |  | X | 709 | 39 | 143 | 1 | 1 | 1B/2T |  | KIT CLEAR 5/5 | SHIPPED 5/12
109774 | 18101 | 100 | 2022-05-04 | 5 | 2022-05-05 | 2022-05-12 |  | X | 819 | 45 | 63 | 1 | 1 | 2B/1T | ROWC B106208 | KIT CLEAR 5/5 | SHIPPED 5/12
109493 | 4795.2 | 15 | 2022-05-11 | 5 | 2022-05-05 | 2022-05-12 |  | X | 756 | 12 | 66 | 1 | 1 | 1B/2T |  | KIT CLEAR 5/5 | SHIPPED 5/11
109427 | 3270 | 10 | 2022-04-14 | 5 | 2022-05-04 | 2022-05-11 |  | X | 51 | 2 | 31 | 1 | 1 | 1B/1T |  | KIT CLEAR 5/4 | SHIPPED 5/11
109578-4 | 3814.93 | 230 | 2022-04-29 | 5 | 2022-04-27 | 2022-05-04 |  | X | 46 | 4 | 27 | 0 | 1 | 2T |  | KIT CLEAR 4/27 | SHIPPED 5/11
109419-1 | 3531 | 3/14 | 2022-04-20 | 3 | 2022-05-09 | 2022-05-12 |  | X | 924 | 3 | 165 | 1 | 1 | 2B/2T |  | KIT CLEAR 5/9 | SHIPPED 5/11
108749 | 10924 | 400 | 2022-05-26 | 25 | 2022-04-12 | 2022-05-17 |  | X | 103 | 0 | 50 | 1 | 1 | 1B/2T | RONC B104974 | KIT CLEAR 4/12 | SHIPPED 5/11
109720 | 2888.8 | 4 | 2022-05-05 | 3 | 2022-05-06 | 2022-05-11 |  | X | 534 | 15 | 102 | 1 | 1 | 1B/2T |  | kit clear 5/6 | SHIPPED 5/11
109250 | 2700 | 75 | 2022-04-27 | 5 | 2022-05-04 | 2022-05-11 |  | X | 84 | 0 | 23 | 1 | 1 | 1B/1T |  | KIT CLEAR 5/4 | SHIPPED 5/10
109629-1 | 1825.15 | 2 | 2022-05-04 | 5 | N/C | 2022-05-12 |  | X | 496 | 47 | 80 | 1 | 1 | 1B/1T |  | DOC REL 4/18 | SHIPPED 5/10
109688 | 1987 | 20 | 2022-05-16 | 5 | 2022-05-03 | 2022-05-10 |  | X | 65 | 30 | 17 | 0 | 1 | 1T |  | KIT CLEAR 5/3 | SHIPPED 5/10
109847-2 | 1154.4 | 20 | 2022-05-12 | 140 | 2022-05-04 | 2022-05-18 |  | X | 275 | 1 | 41 | 1 | 1 | 1B/2T |  | KIT CLEAR 5/4 | SHIPPED 5/9
104910-2 | 0 | 9 | 2022-03-02 | 5 | N/C | ??? | HOLD | X | 917 | 1 | 167 | 1 | 1 | 2B/2T |  | DOC REL 3/7 | SHIPPED 5/9
108909-3 | 1413.02 | 2 | 2022-04-26 | 2 | 2022-05-03 | 2022-05-10 |  | X | 1032 | 36 | 96 | 1 | 1 | 1B/2T | 5/4 - BOT DELAM | KIT CLEAR 5/3 | SHIPPED 5/9
108909-2 | 2119.53 | 3 | 2022-04-26 | 2 | 2022-05-03 | 2022-05-09 |  | X | 1032 | 36 | 96 | 1 | 1 | 1B/2T | 5/4 - BOT DELAM | KIT CLEAR 5/3 | SHIPPED 5/9
108909-1 | 3969.53 | 3 | 2022-04-26 | 2 | 2022-05-03 | 2022-05-05 | HOLD | X | 1032 | 36 | 96 | 1 | 1 | 1B/2T | 5/4 - BOT DELAM | KIT CLEAR 5/3 | SHIPPED 5/6
104910-1 | 9000 | 11/20 | 2022-03-02 | 5 | N/C | ??? | HOLD | X | 917 | 1 | 167 | 1 | 1 | 2B/2T |  | DOC REL 3/7 | SHIPPED 5/6
109578-3 | 1161.07 | 70 | 2022-04-29 | 5 | 2022-04-27 | 2022-05-04 |  | X | 46 | 4 | 27 | 0 | 1 | 2T |  | KIT CLEAR 4/27 | SHIPPED 5/6
108725 | 3081.5 | 10 | 2022-04-27 | 5 | 2022-05-02 | 2022-05-09 |  | X | 516 | 31 | 105 | 1 | 1 | 1B/2T |  | KIT CLEAR 5/2 | SHIPPED 5/6
109189 | 1977 | 25 | 2022-04-07 | 5 | 2022-04-29 | 2022-05-06 |  | X | 100 | 22 | 45 | 1 | 1 | 1B/1T |  | KIT CLEAR 4/29 | SHIPPED 5/6
109340 | 8464.6 | 10 | 2022-04-28 | 5 | 2022-04-28 | 2022-05-06 |  | X | 1056 | 49 | 148 | 1 | 1 | 1B/2T |  | KIT CLEAR 4/28 | SHIPPED 5/6
109578-2 | 1244 | 100 | 2022-04-29 | 5 | 2022-04-27 | 2022-05-04 |  | X | 46 | 4 | 27 | 0 | 1 | 2T |  | KIT CLEAR 4/27 | SHIPPED 5/5
109847-1 | 2109 | 10/400 | 2022-05-12 | 3 | N/C | 2022-05-09 |  | X | 275 | 1 | 41 | 1 | 1 | 1B/2T |  | KIT CLEAR 5/4 | SHIPPED 5/5
108974 | 5389.2 | 160 | 2022-05-20 | 20 | 2022-04-21 | 2022-05-19 |  | X | 173 | 0 | 101 | 0 | 1 | 2T |  | KIT CLEAR 4/21 | SHIPPED 5/5
109578-1 | 1244 | 100 | 2022-04-29 | 5 | 2022-04-27 | 2022-05-04 |  | X | 46 | 4 | 27 | 0 | 1 | 2T |  | KIT CLEAR 4/27 | SHIPPED 5/4
109529 | 3028.06 | 33 | 2022-05-04 | 5 | 2022-04-27 | 2022-05-04 |  | X | 215 | 25 | 66 | 1 | 1 | 1B/2T |  | KIT CLEAR 4/27 | SHIPPED 5/4
108039 | 1955.5 | 5 | 2022-05-06 | 10 | 2022-04-20 | 2022-05-04 |  | X | 160 | 40 | 41 | 1 | 1 | 1B/1T |  | KIT CLEAR 4/20 | SHIPPED 5/3
109612 | 2808 | 24 | 2022-05-04 | 3 | 2022-04-28 | 2022-05-03 |  | X | 26 | 0 | 6 | 0 | 1 | 1T | RONC B104952 | KIT CLEAR 4/28 | SHIPPED 5/3
108988 | 1974 | 4 | 2022-05-16 | 15 | 2022-04-20 | 2022-05-11 |  | X | 251 | 12 | 39 | 1 | 1 | 1B/1T |  | KIT CLEAR 4/20 | SHIPPED 5/3
107215-2ND | 1620 | 4 | 2022-04-04 | 3 | 2022-05-02 | 2022-05-05 |  | X | 0 | 27 | 0 | 0 | 0 | 0 | THT assembly only | KIT CLEAR 5/2 | SHIPPED 5/3
109262 | 1415.7 | 22 | 2022-05-03 | 10 | N/C | ??? |  | X | 123 | 12 | 45 | 0 | 1 | 1T | ROWC B105905 | SHORT PCB + 1 ITEM | SHIPPED 5/3
108734 | 4960 | 500 | 2022-05-12 | 15 | 2022-04-22 | 2022-05-13 |  | X | 53 | 0 | 19 | 0 | 1 | 1T |  | KIT CLEAR 4/22 | SHIPPED 5/3
109555 | 5279.8 | 5 | 2022-04-29 | 3 | N/C | ??? |  | X | 783 | 71 | 128 | 1 | 1 | 2B/2T |  | kit clear 4/29 | SHIPPED 5/2
109879 | 2800 | 50 | 2022-04-28 | 2 | 2022-04-28 | 2022-05-02 |  | X | 19 | 2 | 15 | 0 | 1 | 1T |  | KIT CLEAR 4/29 | SHIPPED 5/2
108472-1 | 1688.8 | 12/150 | 2022-04-01 | 10 | N/C | 2022-05-02 |  | X | 102 | 4 | 49 | 1 | 1 | 1B/1T |  | kit clear 4/29 | SHIPPED 5/2
106389 | 1810 | 25 | 2022-02-02 | 15 | 2022-04-15 | 2022-05-06 |  | X | 66 | 22 | 21 | 1 | 1 | 1B/1T |  | KIT CLEAR 4/15 | SHIPPED 4/29
108907-2 | 1764 | 21 | 2022-03-30 | 5 | N/C | ??? |  | X | 0 | 70 | 0 | 0 | 0 | 0 | THT only | kit clear 5/10 | SHIPPED 4/29
109154-4 | 987.8 | 28 | 2022-04-13 | 5 | 2022-04-27 | 2022-05-11 |  | X | 114 | 20 | 57 | 1 | 1 | 2T | Can build all 100 at once/ROWC B107898 2nd Article | KIT CLEAR 4/27 | SHIPPED 4/29
109154-3 | 1257.2 | 22 | 2022-04-13 | 5 | 2022-04-27 | 2022-04-29 |  | X | 114 | 20 | 57 | 1 | 1 | 2T | Can build all 100 at once/ROWC B107898 2nd Article | KIT CLEAR 4/27 | SHIPPED 4/29
109186 | 1988 | 25 | 2022-04-07 | 5 | 2022-04-22 | 2022-04-29 | BOT DONE | X | 109 | 22 | 38 | 1 | 1 | 1B/1T | RONC B103315 | KIT CLEAR 4/22 | SHIPPED 4/29
107236-2 | 1073.53 | 31 | 2022-03-10 | 20 | 2022-04-13 | 2022-04-29 |  | X | 131 | 15 | 11 | 0 | 1 | 1T | ROWC B103984 | SHORT 5 ITEMS (1 SMT) | SHIPPED 4/28
108976 | 3737.2 | 40 | 2022-04-06 | 5 | 2022-04-21 | 2022-04-28 |  | X | 227 | 28 | 83 | 0 | 1 | 2T |  | KIT CLEAR 4/21 | SHIPPED 4/28
108946 | 2934.4 | 380 | 2022-04-21 | 5 | 2022-04-21 | 2022-04-28 |  | X | 19 | 2 | 14 | 0 | 1 | 1T |  | KIT CLEAR 4/21 | SHIPPED 4/28
109003 | 2875 | 150 | 2022-04-21 | 5 | 2022-04-20 | 2022-04-29 |  | X | 2 | 0 | 1 | 1 | 0 | 1B |  | KIT CLEAR 4/20 | SHIPPED 4/28
108875 | 1500 | 10 | 2022-04-14 | 10 | 2022-04-20 | 2022-04-29 |  | X | 416 | 0 | 102 | 0 | 1 | 2T |  | DOC REL 3/28 | SHIPPED 4/27
109007 | 1826 | 5 | 2022-04-20 | 5 | 2022-04-20 | 2022-04-27 |  | X | 746 | 4 | 52 | 1 | 1 | 1B/1T |  | KIT CLEAR 4/20 | SHIPPED 4/27
107329-2 | 3833.6 | 8 | 2022-03-28 | 9 | 2022-04-25 | 2022-05-06 | SHORT | X | 388 | 0 | 4 | 1 | 1 | 1B/1T |  | DOC REL 3/15 | SHIPPED 4/27
107257-2ND | 1900 | 29 | 2022-01-07 | 5 | 2022-04-19 | 2022-04-26 |  | XR | 393 | 10 | 65 | 0 | 1 | 2T |  | KIT CLEAR 4/19 | SHIPPED 4/26
109524 | 2043 | 100 | 2022-04-27 | 3 | 2022-04-22 | 2022-04-27 |  | X | 21 | 1 | 14 | 1 | 1 | 1B/1T |  | KIT CLEAR 4/22 | SHIPPED 4/26
103326 | 4400.1 | 30 | 2021-09-10 | 15 | 2022-04-14 | 2022-04-29 |  | X | 624 | 25 | 77 | 1 | 1 | 1B/1T | ROWC B98717 (Robert) | KIT CLEAR 4/14 | SHIPPED 4/26
109425 | 1942.5 | 50 | 2022-04-19 | 10 | 2022-04-11 | 2022-04-25 |  | X | 54 | 9 | 23 | 1 | 1 | 1B/1T |  | KIT CLEAR 4/11 | SHIPPED 4/25
109154-2 | 1818 | 20 | 2022-04-13 | 5 | 2022-04-18 | 2022-04-25 |  | X | 114 | 20 | 57 | 1 | 1 | 2T | Can build all 100 at once/ROWC B107898 2nd Article | SHORT 9 ITEMS | SHIPPED 4/25
109227 | 3130 | 540 | 2022-04-27 | 10 | 2022-04-20 | 2022-05-04 |  | X | 2 | 0 | 2 | 0 | 1 | 1T |  | KIT CLEAR 4/20 | SHIPPED 4/25
109385 | 2566.4 | 40 | 2022-05-04 | 9 | 2022-04-18 | 2022-04-29 |  | X | 138 | 0 | 10 | 1 | 1 | 1B/1T |  | KIT CLEAR 4/18 | SHIPPED 4/25
109631 | 3616.9 | 22 | 2022-04-21 | 5 | 2022-04-18 | 2022-04-25 |  | X | 382 | 0 | 69 | 0 | 1 | 2T |  | DOC REL 4/14 | SHIPPED 4/22
108782 | 3820.5 | 50 | 2022-04-15 | 10 | 2022-04-08 | 2022-04-22 |  | X | 266 | 13 | 53 | 1 | 1 | 1B/1T |  | KIT CLEAR 4/8 | SHIPPED 4/22
109231 | 6214.4 | 16 | 2022-04-13 | 5 | 2022-04-18 | 2022-04-25 |  | X | 686 | 1 | 125 | 1 | 1 | 2B/1T |  | KIT CLEAR 4/18 | SHIPPED 4/21
107546-2ND | 2874.2 | 17 | 2022-01-18 | 5 | 2022-04-15 | 2022-04-22 |  | X | 328 | 11 | 47 | 1 | 1 | 1B/1T |  | KIT CLEAR 4/15 | SHIPPED 4/21
108919 | 2189 | 55 | 2022-04-11 | 9 | 2022-04-13 | 2022-04-20 |  | X | 35 | 25 | 26 | 1 | 1 | 1B/1T | RONC B106808 | kit clear 4/14 | SHIPPED 4/20
109154-1 | 3934.5 | 30 | 2022-04-13 | 5 | 2022-04-18 | 2022-04-20 |  | X | 114 | 20 | 57 | 1 | 1 | 2T | Can build all 100 at once/ROWC B107898 2nd Article | KIT CLEAR 4/18 | SHIPPED 4/20
109163 | 1461.75 | 775 | 2022-04-21 | 9 | 2022-04-11 | 2022-04-22 |  | X | 6 | 0 | 2 | 0 | 1 | 1T |  | KIT CLEAR 4/11 | SHIPPED 4/19
107329-1 | 3833.6 | 32/40 | 2022-03-28 | 9 | 2022-04-15 | 2022-04-27 |  | X | 388 | 0 | 4 | 1 | 1 | 1B/1T |  | KIT CLEAR FOR PARTIAL 4/15 | SHIPPED 4/19
108556 | 2725 | 100 | 2022-03-22 | 5 | 2022-04-13 | 2022-04-20 |  | X | 49 | 11 | 13 | 0 | 1 | 1T |  | KIT CLEAR 4/13 | SHIPPED 4/19
109386-2 | 10365.58 | 302 | 2022-04-08 | 2 | N/C | 2022-04-18 |  | X | 95 | 0 | 38 | 0 | 1 | 2T | QTY 150 ASAP | KIT CLEAR 4/14 | SHIPPED 4/18
108531 | 3383 | 50 | 2022-04-01 | 9 | 2022-04-06 | 2022-04-19 |  | X | 167 | 7 | 47 | 1 | 1 | 1B/1T |  | KIT CLEAR 4/6 | SHIPPED 4/18
105892-2 | 5524.5 | 3 | 2021-12-15 | 3 | 2022-04-15 | 2022-04-21 |  | X | 1780 | 385 | 88 | 1 | 1 | 2B/2T | ROWC 1st Article | KIT CLEAR 4/15 | SHIPPED 4/18
109244 | 4844.5 | 3 | 2022-04-07 | 3 | 2022-04-13 | 2022-04-18 |  | X | 507 | 75 | 50 | 1 | 1 | 1B/1T |  | KIT CLEAR 4/13 | SHIPPED 4/15
100605-2 | 7125 | 20/100 | 2021-09-17 | 15 | 2022-03-11 | 2022-04-15 |  | X | 2894 | 4 | 205 | 1 | 1 | 2B/2T | Gerber changed - New program/stencil | KIT CLEAR 3/11 | SHIPPED 4/15
109386-1 | 1690.42 | 48/302 | 2022-04-08 | 2 | N/C | 2022-04-15 |  | X | 95 | 0 | 38 | 0 | 1 | 2T | QTY 150 ASAP | KIT CLEAR 4/14 | SHIPPED 4/15
109183 | 1972.25 | 15 | 2022-04-04 | 5 | 2022-04-07 | 2022-04-14 |  | X | 126 | 3 | 24 | 1 | 1 | 1B/1T |  | KIT CLEAR 4/7 | SHIPPED 4/14
109309 | 3991.68 | 72 | 2022-04-05 | 5 | 2022-04-08 | 2022-04-15 |  | X | 177 | 9 | 59 | 1 | 1 | 1B/1T | RONC B106782 | KIT CLEAR 4/8 | SHIPPED 4/14
108941 | 4646.25 | 25 | 2022-04-18 | 10 | N/C | 4/15* |  | X | 3 | 3 | 1 | 1 | 0 | 1B | RONC B107450 | KIT CLEAR 4/1 | SHIPPED 4/13
108942 | 4399.5 | 25 | 2022-04-18 | 10 | N/C | 4/15* |  | X | 2 | 2 | 1 | 1 | 0 | 1B | RONC B107449 | KIT CLEAR 4/1 | SHIPPED 4/13
109344 | 6326 | 100 | 2022-04-05 | 2 | 2022-04-12 | 2022-04-14 |  | X | 92 | 20 | 30 | 1 | 1 | 1B/1T |  | KIT CLEAR 4/12 | SHIPPED 4/13
107257-1FA | 1900 | 1/30 | 2022-01-07 | 5 | 2022-04-07 | 2022-04-14 |  | XR | 393 | 10 | 65 | 0 | 1 | 2T |  | KIT CLEAR 4/7 | SHIPPED 4/13
108585 | 1520 | 40 | 2022-03-21 | 9 | 2022-04-01 | 2022-04-14 |  | X | 69 | 7 | 23 | 0 | 1 | 1T |  | kit clear 4/4 | SHIPPED 4/12
109249-1 | 3163 | 4/10 | 2022-04-08 | 5 | 2022-04-06 | 2022-04-13 |  | X | 919 | 50 | 110 | 0 | 1 | 1B/1T |  | KIT CLEAR 4/6 | SHIPPED 4/12
108910 | 3408.8 | 8 | 2022-04-05 | 2 | 2022-04-08 | 2022-04-12 |  | X | 267 | 6 | 57 | 1 | 1 | 1B/1T |  | KIT CLEAR 4/8 | SHIPPED 4/12
109307 | 4613 | 10 | 2022-04-11 | 3 | 2022-04-06 | 2022-04-11 |  | X | 645 | 42 | 62 | 1 | 1 | 1B/1T |  | KIT CLEAR 4/6 | SHIPPED 4/11
109306 | 5032.8 | 72 | 2022-04-05 | 5 | 2022-04-04 | 2022-04-11 |  | X | 257 | 13 | 34 | 0 | 1 | 1T | RONC B107159 | KIT CLEAR 4/4 | SHIPPED 4/11
108042 | 2500 | 100 | 2022-04-05 | 7 | 2022-03-31 | 2022-04-11 |  | X | 89 | 7 | 45 | 0 | 1 | 1T |  | KIT CLEAR 3/31 | SHIPPED 4/11
104885-2 | 1500 | 11 | 2021-11-02 | 10 | 2022-03-29 | 2022-04-11 | SHORT | X | 624 | 25 | 77 | 1 | 1 | 2B/2T | ROWC 1st Article | KIT CLEAR 3/29 | SHIPPED 4/11
107895-2 | 1945.97 | 13 | 2022-03-18 | 15 |  | ??? | SHORT | X | 882 | 10 | 57 | 1 | 1 | 1B/1T |  |  | SHIPPED 4/8
107895-1 | 2896.28 | 12/25 | 2022-03-18 | 15 | 2022-03-17 | 2022-04-08 |  | X | 882 | 10 | 57 | 1 | 1 | 1B/1T |  | KIT CLEAR 3/17 | SHIPPED 4/8
109173 | 7663 | 10 | 2022-04-11 | 3 | 2022-04-06 | 2022-04-11 |  | X | 1 | 1 | 1 | 1 | 0 | 1B | ROWC B105555 | KIT CLEAR 4/6 | SHIPPED 4/8
109174 | 7362 | 10 | 2022-04-04 | 3 | 2022-04-06 | 2022-04-11 |  | X | 2 | 0 | 1 | 1 | 1 | 1B/1T | RONC B107455 | KIT CLEAR 4/6 | SHIPPED 4/8
109381 | 258.82 | 16 |  |  |  | 2022-04-08 | [5 empty] | 1 |  |  | PAID RWK | smt clear 3/31 | SHIPPED 4/8
108335 | 1500 | 4 | 2022-04-18 | 10 | N/C | ??? |  | XR | 471 | 14 | 86 | 1 | 1 | 1B/2T |  | kit clear 4/7 | SHIPPED 4/7
107546-1FA | 1350 | 18/35 | 2022-01-18 | 5 | 2022-04-01 | 2022-04-08 |  | X | 328 | 11 | 47 | 1 | 1 | 1B/1T |  | KIT CLEAR 4/1 | SHIPPED 4/7
108859 | 3457 | 10 | 2022-03-22 | 5 | 2022-04-01 | 2022-04-07 |  | XR | 576 | 26 | 106 | 0 | 1 | 2T |  | DOC REL 3/21 | SHIPPED 4/7
108514 | 3054 | 100 | 2022-03-22 | 5 | 2022-03-30 | 2022-04-07 |  | X | 75 | 0 | 28 | 1 | 1 | 1B/1T |  | KIT CLEAR 3/30 | SHIPPED 4/7
100606-2 | 57447 | 90 | 2021-08-24 | 15 | 2022-03-07 | 2022-04-07 |  | X | 3746 | 5 | 238 | 1 | 1 | 2B/3T | Gerber changed - New program/stencil | KIT CLEAR 3/7 | SHIPPED 4/7
109020 | 862.5 | 150 | 2022-04-11 | 5 | 2022-04-04 | 2022-04-11 |  | X | 7 | 0 | 7 | 1 | 1 | 1B/1T |  | KIT CLEAR 4/4 | SHIPPED 4/7
109021 | 1572.5 | 150 | 2022-04-11 | 5 | 2022-04-04 | 2022-04-11 |  | X | 4 | 0 | 4 | 1 | 1 | 1B/1T |  | KIT CLEAR 4/4 | SHIPPED 4/7
108145 | 120.97 | 1 | 2022-03-02 | 3 | 2022-03-25 | 2022-03-30 |  | XR | 215 | 25 | 75 | 0 | 1 | 2T |  | kit clear 3/24 | SHIPPED 4/6
108380-2 | 5083.89 | 43 | 2022-03-18 | 5 | 2022-03-29 | 2022-04-05 |  | X | 599 | 8 | 122 | 1 | 1 | 1B/2T |  | PARTIAL KIT CLEAR 3/22 | SHIPPED 4/6
108937 | 2509.5 | 15 | 2022-04-18 | 10 | 2022-04-01 | 2022-04-15 |  | X | 1 | 1 | 1 | 1 | 0 | 1B | RONC B105652 | KIT CLEAR 4/1 | SHIPPED 4/6
108938 | 6250 | 25 | 2022-04-18 | 10 | 2022-04-01 | 2022-04-15 |  | X | 2 | 0 | 1 | 1 | 1 | 1B/1T | RONC B107455 | KIT CLEAR 4/1 | SHIPPED 4/6
109226 | 1800 | 220 | 2022-04-12 | 5 | 2022-04-01 | 2022-04-08 |  | X | 4 | 0 | 2 | 0 | 1 | 1T |  | KIT CLEAR 4/1 | SHIPPED 4/6
107215-1 | 1188 | 1FA/5 | 2022-04-04 | 5 | 2022-03-30 | 2022-04-04 |  | X | 0 | 27 | 0 | 0 | 0 | 0 | THT assembly only | KIT CLEAR 3/30 | SHIPPED 4/4
108907 | 1932 | 23/65 | 2022-03-30 | 5 | N/C | ??? |  | X | 0 | 70 | 0 | 0 | 0 | 0 | THT only | kit clear 5/10 | SHIPPED 4/4
108639-1 | 3301.06 | 24FA/40 | 2022-04-01 | 5 | 2022-03-28 | 2022-04-04 |  | X | 263 | 0 | 82 | 1 | 1 | 1B/1T |  | KIT CLEAR 3/28 | SHIPPED 4/4
109213 | 6000 | 20 | 2022-04-04 | 1 | N/C |  |  | X | 235 | 7 | 79 | 1 | 1 | 1B/2T |  | kit clear 4/1 | SHIPPED 4/4
106595 | 3178 | 200 | 2022-03-01 | 10 | 2022-02-21 | 2022-04-04 |  | X | 7 | 0 | 1 | 1 | 0 | 1B |  | KIT CLEAR 3/21 | SHIPPED 4/1
108392 | 2791.25 | 5 | 2022-04-04 | 5 | 2022-03-25 | 2022-04-01 |  | X | 835 | 9 | 94 | 1 | 1 | 1B/2T |  | KIT CLEAR 3/25 | SHIPPED 4/1
107937-2 | 945.776 | 122 | 2022-02-25 | 5 | 2022-03-25 | 2022-04-01 |  | X | 2 | 0 | 2 | 1 | 0 | 1B |  | KIT CLEAR 3/25 | SHIPPED 3/31
108603-1 | 2092.5 | 35 | 2022-03-16 | 3 | 2022-03-28 | 2022-03-31 |  | XR | 44 | 26 | 31 | 1 | 1 | 1B/1T |  | KIT CLEAR 3/28 | SHIPPED 3/31
108877 | 12490.5 | 10 | 2022-03-28 | 3 | 2022-03-28 | 2022-03-31 | FAB | X | 630 | 203 | 38 | 0 | 1 | 1T |  | KIT CLEAR 3/28 | SHIPPED 3/31
108784 | 1489.52 | 108 | 2022-03-28 | 9 | 2022-03-18 | 2022-03-31 |  | X | 41 | 0 | 18 | 0 | 1 | 1T |  | KIT CLEAR 3/18 | SHIPPED 3/31
109058 | 1150 | 10 | 2022-03-31 | 5 | 2022-03-23 | 2022-03-30 |  | X | 223 | 0 | 48 | 0 | 1 | 1T |  | KIT CLEAR 3/22 | SHIPPED 3/30
108786 | 5492.16 | 6 | 2022-03-14 | 5 | 2022-03-23 | 2022-03-30 |  | X | 1274 | 102 | 79 | 1 | 1 | 1B/2T |  | KIT CLEAR 3/23 | SHIPPED 3/30
108145 | 4717.83 | 40 | 2022-03-02 | 3 | 2022-03-25 | 2022-03-30 |  | XR | 215 | 25 | 75 | 0 | 1 | 2T |  | kit clear 3/24 | SHIPPED 3/30
108380-1 | 5643.36 | 32/75 | 2022-03-18 | 5 | 2022-03-22 | 2022-03-30 |  | X | 599 | 8 | 122 | 1 | 1 | 1B/2T |  | PARTIAL KIT CLEAR 3/22 | SHIPPED 3/30
108252-1 | 2490.18 | 147 | 2022-03-07 | 10 | 2022-03-15 | 2022-03-29 |  | X | 72 | 5 | 30 | 0 | 1 | 1T |  | kit clear 5/10 | SHIPPED 3/30
104894 | 650 | 95 | [12 empty] | PAID RWK | KIT CLEAR 3/23 | SHIPPED 3/29
107891 | 7710 | 90 | 2022-03-11 | 10 | 2022-03-23 | 2022-04-06 |  | XR | 314 | 4 | 112 | 1 | 1 | 2B/2T |  | KIT CLEAR 3/23 | SHIPPED 3/29
106450 | 4084.24 | 36 | 2021-12-07 | 5 | 2022-03-22 | 2022-03-29 |  | X | 309 | 9 | 118 | 1 | 1 | 1B/2T |  | KIT CLEAR 3/22 | SHIPPED 3/29
109118 | 1781.9 | 130 | 2022-03-25 | 5 | 2022-03-22 | 2022-03-29 |  | X | 13 | 1 | 3 | 0 | 1 | 1T |  | KIT CLEAR 3/22 | SHIPPED 3/29
108317 | 2900.2 | 2 | 2022-03-03 | 5 | 2022-03-28 | 2022-04-04 |  | X | 1420 | 98 | 82 | 1 | 1 | 1B/2T |  | KIT CLEAR 3/28 | SHIPPED 3/28
107972-2 | 1650 | 6 | 2022-03-01 | 1 | 2022-03-24 | 2022-03-28 |  | X | 95 | 0 | 40 | 1 | 1 | 1B/1T |  | KIT CLEAR 3/25 | SHIPPED 3/28
108874 | 4881.25 | 25 | 2022-03-18 | 3 | 2022-03-23 | 2022-03-28 |  | XR | 367 | 6 | 107 | 1 | 1 | 2B/2T |  | KIT CLEAR 3/23 | SHIPPED 3/28
104008 | 2491.83 | 27 | 2022-03-18 | 10 | 2022-03-15 | 2022-03-29 |  | X | 402 | 15 | 57 | 1 | 1 | 1B/1T | RONC B99888 | KIT CLEAR 3/15 | SHIPPED 3/25
107274 | 7372.5 | 50 | 2022-03-16 | 5 | N/C | 3/25* |  | X | 550 | 54 | 135 | 0 | 1 | 2T |  | kit clear 3/24 | SHIPPED 3/25
108420-2 | 458.85 | 133 | 2022-03-14 | 5 | 2022-03-21 | 2022-03-28 |  | X | 1 | 1 | 1 | 0 | 1 | 1T |  | KIT CLEAR 3/21 | SHIPPED 3/25
108348 | 4705.6 | 45 | 2022-03-16 | 3 | 2022-03-22 | 2022-03-25 |  | XR | 220 | 3 | 71 | 1 | 1 | 1B/1T |  | KIT CLEAR 3/22 | SHIPPED 3/25
108876 | 2394 | 25 | 2022-03-18 | 3 2 | 2022-03-22 | 2022-03-24 |  | X | 82 | 8 | 41 | 1 | 1 | 1B/1T |  | KIT CLEAR 3/22 | SHIPPED 3/24
108358 | 4850 | 20 | 2022-03-22 | 3 | 2022-03-21 | 2022-03-24 |  | X | 379 | 1 | 150 | 1 | 1 | 2B/1T |  | KIT CLEAR 3/21 | SHIPPED 3/24
109041 | 1910 | 50 | 2022-03-23 | 3 | 2022-03-21 | 2022-03-24 |  | X | 24 | 0 | 1 | 0 | 0 | 0 | No XY but 1 pin contact spring only - press-fit per customer | KIT CLEAR 3/21 | SHIPPED 3/24
107347 | 2522.5 | 5 | 2022-03-23 | 5 | 2022-03-18 | 2022-03-28 |  | X | 334 | 22 | 84 | 1 | 1 | 1B/1T |  | KIT CLEAR 3/18 | SHIPPED 3/24
104009 | 2704.05 | 27 | 2022-03-18 | 10 | 2022-03-14 | 2022-03-28 |  | X | 402 | 15 | 57 | 1 | 1 | 1B/1T | RONC B99890 | KIT CLEAR 3/14 | SHIPPED 3/24
108689 | 3029.75 | 15 | 2022-03-24 | 5 | 2022-03-17 | 2022-03-24 |  | X | 426 | 41 | 54 | 1 | 1 | 1B/1T |  | KIT CLEAR 3/17 | SHIPPED 3/23
108038 | 1696.5 | 50 | 2022-03-23 | 5 | 2022-03-17 | 2022-03-24 |  | X | 117 | 0 | 32 | 1 | 1 | 1B/1T | ROWC B105264 | KIT CLEAR 3/17 | SHIPPED 3/23
106596-2 | 4050 | 180 | 2022-03-03 | 10 | 2022-03-16 | 2022-03-31 |  | X | 9 | 0 | 5 | 1 | 1 | 1B/1T |  | KIT CLEAR 3/16 | SHIPPED 3/23
106994 | 2604 | 2 | 2022-03-23 | 10 | 2022-03-15 | 2022-03-29 |  | XR | 1220 | 40 | 14 | 1 | 1 | 1B/1T |  | KIT CLEAR 3/15 | SHIPPED 3/22
106531 | 12360 | 80 | 2022-03-04 | 5 | 2022-03-15 | 2022-03-23 |  | X | 265 | 11 | 43 | 1 | 1 | 1B/2T | RONC B106039 | KIT CLEAR 3/15 | SHIPPED 3/22
108347-1 | 1350 | 22/75 | 2022-03-16 | 10 | 2022-03-11 | 2022-03-25 |  | X | 0 | 1 | 0 | 0 | 0 | 0 | THT only/RONC B104412 | kit clear 3/18 | SHIPPED 3/22
108347-2 | 1350 | 53 | 2022-03-16 | 10 | 2022-03-11 | 2022-04-01 |  | X | 0 | 1 | 0 | 0 | 0 | 0 | THT only/RONC B104412 | kit clear 3/18 | SHIPPED 3/22
108758 | 1642.5 | 25 | 2022-03-24 | 5 | 2022-03-16 | 2022-03-23 |  | X | 57 | 41 | 18 | 0 | 1 | 1T |  | KIT CLEAR 3/16 | SHIPPED 3/22
107565 | 1600.1 | 1 | 2022-03-15 | 5 | 2022-03-15 | 2022-03-22 |  | XR | 822 | 22 | 118 | 1 | 1 | 1B/2T |  | KIT CLEAR 3/15 | SHIPPED 3/22
106693 | 1610 | 46 | 2022-02-15 | 5 | 2022-02-18 | 2022-02-25 |  | X | 0 | 1 | 0 | 0 | 0 | 0 | THT only/RONC B103309 | KIT CEAR 3/18 | SHIPPED 3/21
108471 | 4100.06 | 17 | 2022-03-17 | 6 | 2022-03-14 | 2022-03-22 |  | XR | 496 | 1 | 161 | 1 | 1 | 1B/3T |  | KIT CEAR 3/14 | SHIPPED 3/21
107719 | 1599.6 | 30 | 2022-03-09 | 10 | N/C | ??? |  | X | 106 | 38 | 38 | 0 | 1 | 1T | ROWC B97395 | 3/10 RECV WRONG C14 | SHIPPED 3/18
107972-1 | 3925 | 9/15 | 2022-03-01 | 1 | 2022-03-10 | 2022-03-18 |  | X | 95 | 0 | 40 | 1 | 1 | 1B/1T |  | KIT CLEAR 3/10 | SHIPPED 3/18
108332-2 | 1260 | 130 | 2022-03-03 | 5 | 2022-03-14 | 2022-03-21 |  | X | 0 | 5 | 0 | 0 | 0 | 0 | THT only - 2ND ART | KIT CLEAR 3/14 | SHIPPED 3/18
107894 | 4294.5 | 25 | 2022-03-18 | 15 | 2022-03-08 | 2022-03-29 |  | X | 781 | 2 | 19 | 1 | 1 | 1B/1T |  | KIT CLEAR 3/8 | SHIPPED 3/18
108866 | 499.8 | 1 | [12 empty] | PAID RWK |  | SHIPPED 3/17
107457 | 8520.97 | 36 | 2022-02-01 | 5 | 2022-03-14 | 2022-03-21 |  | X | 489 | 1 | 165 | 1 | 1 | 2B/2T | ROWC B104372 3rd Article | KIT CLEAR 3/14 | SHIPPED 3/17
108553 | 862.5 | 25 | 2022-03-07 | 5 | 2022-03-11 | 2022-03-18 |  | X | 109 | 18 | 61 | 1 | 1 | 1B/1T | RONC B105822 | KIT CLEAR 3/11 | SHIPPED 3/17
104576-2 | 1912 | 4 | 2021-09-16 | 5 | 2022-03-08 | 2022-03-17 |  | X | 750 | 12 | 83 | 1 | 1 | 1B/2T | Gerber changed - New program/stencil | KIT CLEAR 3/8 | SHIPPED 3/17
104573-2 | 5903.64 | 4 | 2021-09-22 | 15 | 2022-03-01 | 2022-03-22 |  | X | 4093 | 5 | 237 | 1 | 1 | 2B/3T | Gerber changed - New program/stencil | KIT CLEAR 3/1 | SHIPPED 3/17
106324 | 41390.4 | 3504 | 2022-01-03 | 10 | 2022-03-04 | 2022-03-18 |  | X | 25 | 0 | 16 | 1 | 1 | 1B/1T | ROWC B96743 | DOC REL 11/24 | SHIPPED 3/17
108655-2 | 0 | 9 | 2022-03-03 | 5 | N/C |  |  | X | 326 | 124 | 43 | 1 | 1 | 1B/1T | ROWC B107703 | JOB CANCELLED | MOVED TO SNA
108771 | 1080 | 90 | 2022-03-09 | 5 | N/C |  |  | NEED | [7 empty] | NO DOC. | SHIPPED 3/16
108681 | 3219 | 100 | 2022-03-24 | 5 | 2022-03-09 | 2022-03-16 |  | X | 45 | 35 | 7 | 0 | 1 | 1T |  | KIT CLEAR 3/9 | SHIPPED 3/16
108526-1 | 912.75 | 15FA | 2022-03-10 | 3 | 2022-03-17 | 2022-03-17 | NR | XR | 216 | 7 | 87 | 1 | 1 | 2B/1T |  | DOC REL 3/3 | SHIPPED 3/16
107457 | 6154.03 | 26 | 2022-02-01 | 3 | 2022-03-14 | 2022-03-17 |  | X | 489 | 1 | 165 | 1 | 1 | 2B/2T | ROWC B104372 3rd Article | KIT CLEAR 3/14 | SHIPPED 3/16
108420-1 | 1113.65 | 117/250 | 2022-03-14 | 5 | N/C | ??? |  | X | 1 | 1 | 1 | 0 | 1 | 1T |  | DOC REL 2/18 | SHIPPED 3/15
108655-1 | 3473.65 | 1 | 2022-03-03 | 5 | N/C | ??? |  | X | 326 | 124 | 43 | 1 | 1 | 1B/1T | ROWC B107703 | DOC REL 3/3 | SHIPPED 3/15
107730-1 | 4525 | 50 | 2022-03-02 | 5 | 2022-03-09 | 2022-03-16 |  | X | 268 | 2 | 38 | 1 | 1 | 1B/1T |  | KIT CLEAR 3/3 BUT FAB ISSUE | SHIPPED 3/15
108481 | 2648 | 15 | 2022-03-15 | 10 | 2022-03-04 | 2022-03-18 |  | X | 74 | 2 | 22 | 1 | 1 | 1B/1T |  | KT CLEAR 3/4 | SHIPPED 3/14
107438 | 426.6 | 2 | 2022-02-14 | 10 | N/C | ??? |  | X | 481 | 50 | 78 | 1 | 1 | 1B/2T | ROWC B101152 | SHORT 17 ITEMS | SHIPPED 3/14
104014 | 8700 | 20 | 2022-01-26 | 10 | 2022-02-28 | 2022-03-14 |  | X | 1022 | 12 | 165 | 1 | 1 | 2B/2T |  | KIT CLEAR 2/28 | SHIPPED 3/14
107346-2 | 2625.75 | 15 | 2022-06-01 | 10 | 2022-02-07 | 2022-06-01 |  | X | 682 | 117 | 57 | 0 | 1 | 2T | ROWC B104254 | KIT CLEAR 2/7 | SHIPPED 3/14
106008-2 | 4655.18 | 86 | 2021-12-07 | 20 | 2022-02-25 | 2022-03-25 |  | X | 248 | 17 | 53 | 1 | 1 | 1B/1T | SHIP QTY 4FA/BAL SPLIT SHIPMENT | KIT CLEAR 2/25 | SHIPPED 3/14
108641 | 2230 | 5FA | 2022-03-11 | 3 | 2022-03-09 | 2022-03-14 |  | X | 196 | 34 | 62 | 0 | 1 | 1T |  | KIT CLEAR 3/9 | SHIPPED 3/11
108466 | 1560 | 150 | 2022-03-15 | 5 | 2022-03-07 | 2022-03-14 |  | X | 7 | 0 | 3 | 0 | 1 | 1T |  | KIT CLEAR 3/7 | SHIPPED 3/11
106828 | 4191.5 | 7 | 2022-02-23 | 5 | 2022-02-25 | 2022-03-04 |  | X | 888 | 6 | 90 | 1 | 1 | 1B/1T |  | KIT CLEAR 2/25 | SHIPPED 3/11
108526-1 | 1204.25 | 5 | 2022-03-10 | 3 | N/C | ??? | NR | XR | 216 | 7 | 87 | 1 | 1 | 2B/1T |  | DOC REL 3/3 | SHIPPED 3/11
108412 | 3999.6 | 20 | 2022-03-11 | 15 | 2022-02-28 | 2022-03-21 |  | X | 572 | 0 | 131 | 1 | 1 | 2B/2T | ROWC B107226 | KIT CLEAR 2/28 | SHIPPED 3/10
106596 | 450 | 20/200 | 2022-03-03 | 10 | 2022-02-25 | 2022-03-11 |  | X | 9 | 0 | 5 | 1 | 1 | 1B/1T |  | kit clear 3/16 | SHIPPED 3/10
108049 | 7500 | 400 | 2022-02-28 | 5 | 2022-03-03 | 2022-03-10 |  | X | 114 | 0 | 53 | 1 | 1 | 1B/1T | ROWC B96963 | KIT CLEAR 3/3 | SHIPPED 3/10
107937-1 | 3783.11 | 320/400 | 2022-02-25 | 5 | 2022-03-04 | 2022-03-11 |  | X | 2 | 0 | 2 | 1 | 0 | 1B |  | kit clear 3/25 | SHIPPED 3/10
108332-1 | 850 | 20 | 2022-03-03 | 3 | 2022-03-04 | 2022-03-09 |  | X | 0 | 5 | 0 | 0 | 0 | 0 | THT only - 1ST ART | KIT CLEAR 3/4 | SHIPPED 3/9
104574-2 | 1100.04 | 8 | 2021-09-16 | 15 | 2022-02-22 | 2022-03-08 |  | X | 64 | 32 | 8 | 1 | 1 | 1B/1T | Gerber changed - New program/stencil | KIT CLEAR 2/23 | SHIPPED 3/9
108048 | 3599 | 100 | 2022-03-07 | 5 | 2022-03-03 | 2022-03-10 |  | X | 108 | 0 | 51 | 1 | 1 | 1B/1T | ROWC B96963 | KIT CLEAR 3/3 | SHIPPED 3/9
105219 | 3999.84 | 24 | 2022-01-06 | 15 | N/C | 3/11* |  | XR | 872 | 80 | 99 | 1 | 1 | 1B/2T |  | kit clear 3/3 | SHIPPED 3/9
108046 | 3241.2 | 2 | 2022-02-16 | 5 | 2022-03-02 | 2022-03-09 |  | X | 1504 | 109 | 79 | 1 | 1 | 1B/2T |  | KIT CLEAR 3/2 | SHIPPED 3/8
100610-2 | 2536.6 | 10/22 | 2021-07-12 | 15 | 2022-02-17 | 2022-03-11 |  | X | 3848 | 7 | 237 | 1 | 1 | 2B/3T | Gerber changed - New program/stencil | KIT CLEAR 2/17 | SHIPPED 3/8
107236 | 2389.47 | 69 | 2022-03-10 | 20 | N/C | ??? |  | X | 131 | 15 | 11 | 0 | 1 | 1T | ROWC B103984 | SHORT 5 ITEMS (1 SMT) | SHIPPED 3/8
108558 | 999.1 | 10 | 2022-03-14 | 10 | 2022-02-28 | 2022-03-09 |  | X | 40 | 47 | 1 | 0 | 1 | 1T | RONC B106717 | KIT CLEAR 2/28 | SHIPPED 3/7
107345 | 6264 | 15 | 2022-02-23 | 3 | 2022-03-03 | 2022-03-08 |  | X | 795 | 24 | 99 | 1 | 1 | 1B/2T | ROWC B107108 | DOC REL 2/7 | SHIPPED 3/7
108212 | 5130 | 10 | 2022-02-16 | 3 | 2022-03-01 | 2022-03-04 |  | X | 795 | 24 | 99 | 1 | 1 | 2B/2T | ROWC B107108 | KIT CLEAR 3/1 | SHIPPED 3/5
107174-2 | 5363.6 | 11 | 2022-01-20 | 5 | 2022-02-25 | 2022-03-04 |  | XR | 1607 | 11 | 48 | 1 | 1 |  |  | KIT CLEAR 2/25 | SHIPPED 3/5
106693 | 140 | 4/50 | 2022-02-15 | 5 | 2022-02-11 | 2022-02-18 |  | X | 0 | 1 | 0 | 0 | 0 | 0 | THT only/RONC B103309 | kit clear 3/18 | SHIPPED 3/4
107492 | 3445.75 | 205 | 2022-03-02 | 5 | 2022-02-24 | 2022-03-03 |  | X | 24 | 11 | 15 | 1 | 1 | 1B/1T |  | KIT CLEAR 2/24 | SHIPPED 3/3
108225 | 5745 | 500 | 2022-02-10 | 3 | 2022-02-28 | 2022-03-03 |  | X | 36 | 0 | 22 | 0 | 1 | 2T | ROWC B105783 | KIT CLEAR 2/28 | SHIPPED 3/2
108063 | 3992 | 120 | 2022-02-14 | 3 | 2022-02-28 | 2022-03-03 |  | X | 69 | 0 | 33 | 1 | 1 | 1B/1T |  | KIT CLEAR 2/28 | SHIPPED 3/2
107346-1 | 3025.75 | 15 | 2022-03-01 | 10 | 2022-02-07 | 2022-03-01 |  | X | 682 | 117 | 57 | 0 | 1 | 2T | ROWC B104254 | KIT CLEAR 2/7 | SHIPPED 3/1
100616-2 | 1866.64 | 32 | 2021-10-15 | 10 | 2022-02-23 | 2022-03-12 |  | X | 26 | 0 | 7 | 1 | 1 | 1B/1T | ROWC 1st Article (use PCB rev 1.B.1) | KIT CLEAR 2/23 | SHIPPED 3/1
106037 | 6150 | 200 | 2021-11-16 | 10 | N/C | 2022-02-24 |  | X | 46 | 2 | 28 | 1 | 1 | 1B/1T | DON’T HAVE TO DEPANEL | SHORT 1 ITEM | SHIPPED 2/28
107898-2 | 6463.8 | 95 | 2022-02-11 | 2 | 2022-02-24 | 2022-02-28 |  | X | 114 | 20 | 57 | 1 | 1 | 1B/1T |  | DOC REL 2/7 | SHIPPED 2/28
106336-1 | 2275.44 | 2 | 2022-01-21 | 15 | 1900-01-05 | ??? |  | XR | 747 | 8 | 109 | 1 | 1 | 2B/2T |  | SHORT 12 ITEMS | SHIPPED 2/28
107705 | 2462.96 | 996 | 2022-02-17 | 9 | 2022-02-23 | 2022-03-05 |  | X | 9 | 0 | 6 | 1 | 1 | 1B/1T |  | KIT CLEAR 2/23 | SHIPPED 2/25
107438 | 1066.5 | 5 | 2022-02-14 | 10 | N/C | ??? |  | X | 481 | 50 | 78 | 1 | 1 | 1B/2T | ROWC B101152 | SHORT 17 ITEMS | SHIPPED 2/24
104911-2 | 5909.85 | 345 | 2021-12-27 | 20 | 2022-02-17 | 2022-03-17 |  | X | 106 | 5 | 41 | 0 | 1 | 1T | RONC 1st Article | SHORT 1 ITEM | SHIPPED 2/24
106009-2 | 3686.68 | 106 | 2022-01-07 | 20 | 2022-02-03 | 2022-03-03 |  | X | 185 | 3 | 62 | 0 | 1 | 2T | SHIP QTY 4FA/BAL SPLIT SHIPMENT | kit clear | SHIPPED 2/23
107918 | 5168 | 6 | 2022-02-15 | 5 | N/C | 3/1* |  | X | 13 | 1 | 7 | 0 | 1 | 1T |  | KIT CLEAR 2/23 | SHIPPED 2/23
108295 | 2430 | 200 | 2022-02-17 | 5 | 2022-02-17 | 2022-02-25 |  | X | 32 | 3 | 21 | 1 | 1 | 1B/1T | RONC B107590 | KIT CLEAR 2/17 | SHIPPED 2/23
105709 | 4320.2 | 12 | 2021-11-09 | 5 | 2022-02-16 | 2022-02-24 |  | X | 861 | 17 | 144 | 1 | 1 | 2B/1T |  | KIT CLEAR 2/16 | SHIPPED 2/22
108093 | 4105 | 25 | 2022-02-14 | 3 | 2022-02-15 | 2022-02-18 |  | X | 176 | 70 | 44 | 0 | 1 | 1T |  | kit clear 2/15 | SHIPPED 2/18
107616 | 2984.5 | 50 | 2022-01-25 | 10 | 2022-02-17 | 2022-03-03 |  | X | 112 | 62 | 27 | 0 | 1 | 1T |  | kit clear 2/17 | SHIPPED 2/18
100606-2 | 6341.5 | 10/100 | 2021-08-24 | 15 | N/C | 2022-02-18 |  | X | 3746 | 5 | 238 | 1 | 1 | 2B/3T | Gerber changed - New program/stencil | DOC REL 1/12 | SHIPPED 2/18
106667 | 2687.5 | 5 | 2022-01-03 | 10 | N/C | ??? |  | X | 178 | 62 | 22 | 1 | 1 | 1B/1T |  | kit clear 2/16 | SHIPPED 2/17
107898-1 | 1900 | 5 | 2022-02-11 | 2 | N/C | ??? |  | X | 114 | 20 | 57 | 1 | 1 | 1B/1T |  | DOC REL 2/7 | SHIPPED 2/16
107726 | 1400 | 200 | 2022-02-10 | 5 | 2022-02-10 | 2022-02-17 |  | X | 0 | 7 | 0 | 0 | 0 | 0 | THT only | KIT CLEAR 2/10 | SHIPPED 2/16
106090 | 3244 | 200 | 2021-11-16 | 5 | 2022-02-10 | 2022-02-17 |  | X | 45 | 3 | 27 | 1 | 1 | 1B/1T | DON’T HAVE TO DEPANEL | KIT CLEAR 2/10 | SHIPPED 2/16
107903 | 2400 | 7 | [14 empty] | SHIPPED 2/15
107451 | 9449 | 50 | 2022-02-08 | 5 | 2022-02-10 | 2022-02-17 |  | X | 863 | 1 | 180 | 1 | 1 | 2B/2T |  | KIT CLEAR 2/10 | SHIPPED 2/15
107799 | 2570 | 10 | 2022-02-21 | 10 | 2022-02-09 | 2022-02-23 |  | X | 8 | 90 | 6 | 1 | 1 | 1B/1T |  | KIT CLEAR 2/9 | SHIPPED 2/15
107632 | 80 | 1 | 2022-02-10 | 5 | N/C | 2022-02-11 |  | X | [6 empty] | REWORK | NO DOC. | SHIPPED 2/14
106708 | 1838 | 12 | 2022-01-03 | 10 | N/C | 2/2* |  | X | 34 | 50 | 13 | 0 | 1 | 1T |  | SHORT 6 ITEMS | SHIPPED 2/14
108173 | 1500 | 96 | 2022-02-10 | 5 | N/C | 2022-02-11 |  | X | [6 empty] | REWORK | NO DOC. | SHIPPED 2/11
107632 | 7200 | 91 | 2022-02-10 | 5 | N/C | 2022-02-11 |  | X | [6 empty] | REWORK | NO DOC. | SHIPPED 2/11
107714 | 2816.72 | 1028 | 2022-02-17 | 10 | 2022-01-31 | 2022-02-14 |  | X | 8 | 2 | 3 | 1 | 1 | 1B/1T | RONC B96769 | KIT CLEAR 1/31 | SHIPPED 2/11
100605-2 | 7125 | 20/140 | 2021-09-17 | 15 | N/C | ??? |  | X | 2894 | 4 | 205 | 1 | 1 | 2B/2T | Gerber changed - New program/stencil | kit clear 3/17 | SHIPPED 2/10
107632 | 8000 | 100 | 2022-02-10 | 5 | N/C | 2022-02-10 |  | NEED | [6 empty] | REWORK | NO DOC. | SHIPPED 2/10
107538 | 2750 | 5 | 2022-02-21 | 10 | 2022-02-07 | 2022-02-21 |  | X | 26 | 0 | 5 | 0 | 1 | 1T | RONC B104952 | KIT CLEAR 2/7 | SHIPPED 2/8
104636-2 | 7996 | 200/1000 | 2021-02-28 | 20 | 2022-01-31 | 2022-02-14 |  | X | 148 | 9 | 59 | 1 | 1 | 1B/1T | ROWC B104272 | KIT CLEAR 1/31 | SHIPPED 2/7
106017 | 5752.32 | 96 | 2022-01-07 | 20 | 2022-01-24 | 2022-02-21 |  | X | 354 | 4 | 80 | 0 | 1 | 2T | SHIP QTY 4FA/BAL SPLIT SHIPMENT | KIT CLEAR 12/27 | SHIPPED 2/4
106421 | 2679.8 | 4 | 2021-12-30 | 5 | 2022-01-31 | 2022-02-07 |  | XR | 478 | 76 | 94 | 1 | 1 |  |  | kit clear 1/31 | SHIPPED 2/4
107590 | 1715.5 | 10 | 2022-01-18 | 5 | 2022-01-31 | 2022-02-07 |  | X | 32 | 3 | 21 | 1 | 1 | 1B/1T |  | KIT CLEAR 1/31 | SHIPPED 2/3
106701 | 2625.15 | 15 | 2022-01-10 | 10 | N/C | ??? |  | X | 682 | 117 | 57 | 0 | 1 | 2T | DO NOT SHIP BEFORE 1/3/22 - ROWC B104254 | kit clear 2/3 | SHIPPED 2/3
104911 | 1847 | 5FA/350 | 2021-12-27 | 5/20 | 2022-02-02 | 2022-02-09 |  | X | 106 | 5 | 41 | 0 | 1 | 1T | ROWC B100607 | kit clear 2/17 | SHIPPED 2/3
107413 | 2486.8 | 20 | 2022-01-26 | 10 | 2022-01-20 | 2022-02-03 |  | X | 184 | 35 | 24 | 0 | 1 | 1T |  | KIT CLEAR 1/20 | SHIPPED 2/2
107452 | 10962 | 35 | 2022-02-01 | 10 | N/C | 2022-02-10 |  | X | 522 | 0 | 123 | 1 | 1 | 2B/2T | ROWC B105552 | DOC REL 1/4 | SHIPPED 2/2
106891 | 8001 | 50 | 2022-01-11 | 3 | 2022-01-27 | 2022-02-01 |  | X | 184 | 68 | 70 | 0 | 1 | 2T |  | KIT CLEAR 1/27 | SHIPPED 2/1
107486 | 2475 | 4FA/10 | 2022-01-26 | 5 | N/C | ??? |  | XR | 573 | 60 | 115 | 0 | 1 |  |  | kit clear 1/31 | SHIPPED 2/1
107630 | 1721 | 255 | 2022-02-07 | 10 | 2022-01-25 | 2022-02-08 |  | X | 6 | 0 | 2 | 0 | 1 | 1T |  | KIT CLEAR 1/25 | SHIPPED 2/1
107456 | 986 | 20 | 2022-01-31 | 10 | 2022-01-25 | 2022-02-08 |  | X | 17 | 0 | 7 | 0 | 1 | 1T | RONC B105655 | KIT CLEAR 1/25 | SHIPPED 1/31
107608 | 3431 | 50 | 2022-02-08 | 9 | 2022-01-19 | 2022-02-01 |  | X | 157 | 15 | 51 | 1 | 1 | 1B/1T | ROWC B102137 | KIT CLEAR 1/19 | SHIPPED 1/31
107516 | 8920.45 | 55 | 2022-01-31 | 4 | 2022-01-25 | 2022-01-31 |  | XR | 675 | 6 | 78 | 1 | 1 |  |  | KIT CLEAR 1/25 | SHIPPED 1/31
107912-2 | 2500 | 100 | 2022-01-28 | 2 | 2022-01-28 | 2022-02-02 |  | X | 0 | 4 | 0 | 0 | 0 |  | PAID REWORK | SHORT 1 PART | SHIPPED 1/31
106826 | 1928.3 | 55 | 2021-12-20 | 5 | 2022-01-24 | 2022-01-31 |  | X | 83 | 12 | 37 | 1 | 1 | 1B/1T | ROWC B101434 | KIT CLEAR 1/24 | SHIPPED 1/28
107912-1 | 1500 | 60/160 | 2022-01-28 | 2 | 2022-01-28 | 2022-02-02 |  | X | 0 | 4 | 0 | 0 | 0 |  | PAID REWORK | SHORT 1 PART | SHIPPED 1/28
107607 | 1652.5 | 25 | 2022-01-31 | 5 | 2022-01-24 | 2022-01-31 |  | X | 59 | 38 | 19 | 1 | 1 | 1B/1T |  | KIT CLEAR 1/24 | SHIPPED 1/28
107383 | 2344 | 400 | 2022-01-07 | 10 | 2022-01-17 | 2022-01-31 |  | X | 7 | 4 | 6 | 0 | 1 | 1T |  | KIT CLEAR 1/17 | SHIPPED 1/27
107519 | 2352 | 5 | 2022-01-26 | 5 | 2022-01-25 | 2022-01-31 |  | XR | 104 | 22 | 23 | 1 | 1 |  |  | KIT CLEAR 1/25 | SHIPPED 1/27
107104 | 3049.9 | 14 | 2022-01-24 | 5 | 2022-01-21 | 2022-01-28 |  | X | 511 | 5 | 56 | 0 | 1 | 1T | ROWC B105575 | KIT CLEAR 1/21 | SHIPPED 1/27
107450 | 5677.5 | 50 | 2022-02-04 | 10 | 2022-01-19 | 2022-02-02 |  | X | 3 | 3 | 1 | 1 | 0 | 1B | RONC B105332 | KIT CLEAR 1/19 | SHIPPED 1/26
107449 | 5000 | 50 | 2022-02-04 | 10 | 2022-01-19 | 2022-02-02 |  | X | 2 | 2 | 1 | 1 | 0 | 1B | RONC B105331 | KIT CLEAR 1/19 | SHIPPED 1/26
107454 | 7150 | 50 | 2022-02-04 | 10 | 2022-01-19 | 2022-02-02 |  | X | 1 | 1 | 1 | 1 | 0 | 1B | ROWC B105555 | KIT CLEAR 1/19 | SHIPPED 1/26
107786 | 4075 | 10 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-26 |  | X | 95 | 0 | 26 | 0 | 1 | 1T |  | KIT CLEAR 1/25 | SHIPPED 1/26
107470 | 5230 | 50 | 2022-02-21 | 5 | 2022-01-19 | 2022-01-26 |  | XR | 370 | 9 | 98 | 1 | 1 |  |  | KIT CLEAR 1/19 | SHIPPED 1/26
107348 | 1600 | 25 | 2022-02-10 | 10 | 2022-01-21 | 2022-02-04 |  | X | 2 | 0 | 2 | 1 | 1 | 1B/1T |  | KIT CLEAR 1/21 | SHIPPED 1/25
107482 | 2414 | 4FA/10 | 2022-01-21 | 5 | 2022-01-20 | 2022-01-27 |  | XR | 645 | 52 | 108 | 0 | 1 |  |  | KIT CLEAR 1/20 | SHIPPED 1/25
107081 | 3360.5 | 2 | 2021-12-27 | 5 | 2022-01-18 | 2022-01-25 |  | XR | 637 | 28 | 69 | 0 | 1 |  |  | KIT CLEAR 1/18 | SHIPPED 1/25
107174-1 | 3000 | 1 | 2022-01-20 | 5 | 2022-01-18 | 2022-01-25 |  | XR | 1607 | 11 | 48 | 1 | 1 |  |  | KIT CLEAR 1/18 | SHIPPED 1/25
107491 | 4988 | 100 | 2022-01-12 | 5 | 2022-01-17 | 2022-01-24 |  | X | 135 | 7 | 47 | 1 | 1 | 1B/2T | ROWC B100251 | KIT CLEAR 1/17 | SHIPPED 1/24
103611 | 5472 | 38 | 2021-08-12 | 5 | 2022-01-21 | 2022-01-28 |  | X | 370 | 4 | 93 | 1 | 1 | 1B/2T | ROWC B97071 | kit clear 1/21 | SHIPPED 1/24
107127 | 2485 | 50 | 2021-01-28 | 9 | 2022-01-14 | 2022-01-27 |  | X | 97 | 16 | 47 | 1 | 1 | 1B/1T |  | KIT CLEAR 1/14 | SHIPPED 1/24
107455 | 7900 | 50 | 2022-02-04 | 10 | 2022-01-19 | 2022-02-02 |  | X | 2 | 0 | 1 | 1 | 1 | 1B/1T | RONC B105554 | KIT CLEAR 1/19 | SHIPPED 1/24
107665 | 36000 | [13 empty] | OKLA FEEDERS |  | SHIPPED 1/21
107445 | 3264.4 | 15 | 2022-01-17 | 5 | 2022-01-17 | 2022-01-24 |  | XR | 432 | 6 | 100 | 1 | 1 |  |  | KIT CLEAR 1/17 | SHIPPED 1/21
106403-2 | 1114 | 15 | 2021-12-02 | 5 | 2022-01-18 | 2022-01-25 |  | X | 32 | 8 | 18 | 1 | 1 | 1B/1T | ROWC 1st Article | SHORT 1 (THT) ITEM/SMT CLEAR | SHIPPED 1/21
106479 | 4958.8 | 10 | 2021-12-14 | 5 | 2022-01-13 | 2022-01-20 |  | XR | 640 | 28 | 169 | 1 | 1 | 2B/2T |  | kit clear 1/14 | SHIPPED 1/21
106658 | 7130 | 1000 | 2022-02-02 | 15 | 2022-01-11 | 2022-02-01 |  | X | 35 | 2 | 22 | 0 | 1 | 2T |  | KIT CLEAR 1/11 | SHIPPED 1/21
106012 | 3640.8 | 90 | 2022-01-07 | 20 | N/C | 1/15* |  | X | 179 | 4 | 53 | 1 | 1 | 1B/1T | SPLIT SHIPMENT | kit clear 1/20 | SHIPPED 1/20
106839 2nd | 9983.25 | 27 | 2021-12-16 | 5 | 2022-01-14 | 2022-01-20 |  | X | 1306 | 45 | 207 | 1 | 1 | 1B/3T | ROWC 1st Article | KIT CLEAR 1/14 | SHIPPED 1/20
107412 | 6293.5 | 25 | 2022-01-14 | 3 | 2022-01-17 | 2022-01-20 |  | X | 591 | 1 | 88 | 1 | 1 | 2B/1T |  | DOC REL 1/4 | SHIPPED 1/20
100613 2nd | 370.368 | 8 | 2021-08-19 | 15 | 2022-01-14 | 2022-01-28 |  | X | 119 | 4 | 32 | 1 | 1 | 1B/1T | Gerber changed - New program/stencil | KIT CLEAR 1/14 | SHIPPED 1/19
100617 2nd | 2441.51 | 32 | 2021-08-19 | 15 | 2022-01-14 | 2022-01-28 |  | X | 401 | 4 | 54 | 1 | 1 | 1B/1T | Gerber changed - New program/stencil | KIT CLEAR 1/13 | SHIPPED 1/19
107332 | 1532.33 | 150 | 2022-02-04 | 10 | 2022-01-17 | 2022-01-28 |  | X | 16 | 0 | 2 | 1 | 1 |  |  | KIT CLEAR 1/17 | SHIPPED 1/18
104885 | 1500 | 3/14 | 2021-11-02 | 10 | 2022-01-05 | 2022-01-19 |  | X | 624 | 25 | 77 | 1 | 1 | 2B/2T | ROWC B103326 | kit clear 1/5 | SHIPPED 1/18
105709 | 3245.8 | 8 | 2021-11-09 | 5 | N/C | 2022-01-18 |  | X | 861 | 17 | 144 | 1 | 1 | 2B/1T |  | SHORT 13 ITEMS | SHIPPED 1/18
106023 | 4984 | 20 | 2021-12-15 | 5 | 2022-01-17 | 2022-01-24 |  | X | 678 | 3 | 75 | 1 | 1 | 1B/1T |  | KIT CLEAR 1/17 | SHIPPED 1/17
107232 | 2984.4 | 105 | 2022-01-10 | 10 | 2022-01-07 | 2022-01-21 |  | X | 92 | 4 | 41 | 0 | 1 | 1T |  | KIT CLEAR 1/7 | SHIPPED 1/17
106011 | 2832 | 300 | 2022-01-07 | 20 | 2021-12-27 | 2021-01-15 |  | X | 21 | 1 | 9 | 0 | 1 | 1T | SPLIT SHIPMENT | KIT CLEAR 12/27 | SHIPPED 1/14
104636-1 | 4967 | 100/1100 | 2021-11-29 | 20 | N/C | ??? |  | X | 148 | 9 | 59 | 1 | 1 | 1B/1T | ROWC B104272 | SHORT PCB + 62 ITEMS | SHIPPED 1/14
106016 | 2836.2 | 90 | 2022-01-07 | 20 | 2021-12-27 | 2021-01-15 |  | X | 90 | 0 | 33 | 0 | 1 | 1T | SPLIT SHIPMENT | KIT CLEAR 12/27 | SHIPPED 1/14
106324 | 25209.6 | 2496/6000 | 2022-01-03 | 10 | N/C | ??? |  | X | 25 | 0 | 16 | 1 | 1 | 1B/1T | ROWC B96743 | kit clear 3/4 | SHIPPED 1/14
106808 | 2595 | 50 | 2021-12-22 | 3 | N/C | ??? |  | XR | 35 | 25 | 26 | 1 | 1 | 1B/1T | Ray | kit clear 1/12 | SHIPPED 1/13
105892-1 | 4585 | 1FA/4 | 2021-12-15 | 5/3* | 2022-01-10 | 2022-01-17 |  | X | 1780 | 385 | 88 | 1 | 1 | 1B/1T |  | 1FA kit clear 1/10 | SHIPPED 1/13
106008 | 1799.8 | 4FA/90 | 2021-12-07 | 20 | N/C | ??? |  | X | 248 | 17 | 53 | 1 | 1 | 1B/1T | SHIP QTY 4FA/BAL SPLIT SHIPMENT | DOC REL 11/15 | SHIPPED 1/12
106872 | 1637.84 | 28 | 2021-01-12 | 10 | 2022-01-10 | 2022-01-24 |  | X | 29 | 13 | 8 | 0 | 1 | 1T |  | KIT CLEAR 1/10 | SHIPPED 1/12
107108 | 2888.15 | 3 | 2021-12-27 | 3 | 2022-01-12 | 2022-01-14 |  | X | 795 | 24 | 99 | 1 | 1 | 1B/2T |  | KIT CLEAR 1/12 | SHIPPED 1/12
106900 | 2532.4 | 4 | 2022-01-12 | 10 | 2022-01-06 | 2022-01-20 |  | XR | 819 | 21 | 104 | 1 | 1 | 1B/2T | Ray | KIT CLEAR 1/6 | SHIPPED 1/11
107260 | 3410.88 | 33 | 2022-01-19 | 10 | N/C | ??? |  | X | 304 | 0 | 85 | 1 | 1 | 1B/2T | ROWC B103030 | kit clear 1/6 | SHIPPED 1/11
107259 | 3116.1 | 30 | 2022-01-05 | 10 | N/C | ??? |  | X | 298 | 3 | 84 | 1 | 1 | 1B/2T | ROWC B103035 | kit clear 1/6 | SHIPPED 1/11
106756 | 3426.51 | 207 | 2021-12-23 | 9 | 2022-01-03 | 2022-01-14 |  | X | 38 | 11 | 18 | 0 | 1 | 1T |  | KIT CLEAR 1/3 | SHIPPED 1/10
107261 | 2515 | 20 | 2022-01-06 | 10 | N/C | ??? |  | X | 297 | 0 | 83 | 1 | 1 | 1B/2T | ROWC B107259 (same PCB) | kit clear 1/7 | SHIPPED 1/10
107265 | 2291 | 100 | 2022-01-06 | 10 | N/C | 1/17* |  | X | 57 | 2 | 29 | 1 | 1 | 1B/1T |  | KIT CLEAR 1/3 | SHIPPED 1/7
107226 | 2769 | 4 | 2022-01-10 | 5 | N/C | ??? |  | XR | 572 | 0 | 131 | 1 | 1 | 2B/2T | FAVOR | kit clear 1/6 | SHIPPED 1/7
106797 | 3091.3 | 10 | 2022-01-13 | 10 | 2021-12-30 | 2021-01-14 |  | X | 647 | 14 | 131 | 1 | 1 | 2B/2T |  | KIT CLEAR 12/30 | SHIPPED 1/6
107027 | 5652.75 | 15 | 2021-12-17 | 3 | 2021-12-14 | 2021-12-17 |  | X | 452 | 0 | 146 | 1 | 1 | 1B/2T |  | KIT CLEAR 12/14 | SHIPPED 1/6
107399 | 1815 | 100 | 2022-01-07 | 5 | 2022-01-03 | 2022-01-10 |  | X | 33 | 0 | 15 | 1 | 1 |  | RONC B96441 | KIT CLEAR 1/10 | SHIPPED 1/5
104894 | 1566.47 | 42 | 2021-10-18 | 15 | N/C | ??? |  | X | 131 | 7 | 32 | 1 | 1 | 1B/1T | QTY 53 SHIPPED 11/16 | kit clear 1/4 | SHIPPED 1/5
105929 | 2385 | 100 | 2021-12-01 | 15 | 2022-01-05 | 2022-01-11 |  | X | 99 | 12 | 37 | 0 | 1 | 2T | ROWC B103338 | kit clear 1/5 | SHIPPED 1/5
106940 | 3054 | 60 | 2022-01-12 | 5 | 2021-12-28 | 2021-01-05 |  | X | 93 | 12 | 27 | 1 | 1 | 1B/1T |  | KIT CLEAR 12/28 | SHIPPED 1/4
106009 | 1765.2 | 4/110 | 2022-01-07 | 20 | 2021-12-27 | 2021-01-15 |  | X | 185 | 3 | 62 | 0 | 1 | 2T | SHIP QTY 4FA/BAL SPLIT SHIPMENT | kit clear | SHIPPED 1/4
106969 | 4969 | 10 | 2021-12-28 | 10 | 2021-12-23 | 2021-01-10 |  | X | 1034 | 0 | 100 | 1 | 1 | 1B/2T |  | KIT CLEAR 12/27 | SHIPPED 1/4
106017 | 1899 | 4/100 | 2022-01-07 | 20 | 2021-12-27 | 2021-01-15 |  | X | 354 | 4 | 80 | 0 | 1 | 2T | SHIP QTY 4FA/BAL SPLIT SHIPMENT | KIT CLEAR 12/27 | SHIPPED 1/3
100607 | 500 | 85 | [12 empty] | PAID REWORK | KIT CLEASR 11/29 | SHIPPED 1/3
106972 | 2905 | 2 | 2021-12-28 | 10 | 2021-12-22 | 2021-01-07 |  | X | 321 | 39 | 61 | 0 | 1 | 1T |  | KIT CLEAR 12/22 | SHIPPED 1/3
107247 | 2881.2 | 8 | 2021-12-29 | 3 | 2021-12-28 | 2021-01-03 |  | X | 129 | 17 | 47 | 1 | 1 | 1B/1T |  | KIT CLEAR 12/28 | SHIPPED 12/30
106200 | 3753.2 | 20 | 2021-11-11 | 3 | N/C | ??? |  | X | 180 | 14 | 38 | 0 | 1 | 1T |  | kit clear 12/30 | SHIPPED 12/30
106794 | 1886.75 | 25 | 2021-12-28 | 5 | 2021-12-22 | 2021-12-30 |  | X | 432 | 10 | 79 | 1 | 1 | 1B/1T |  | kit clear 12/22 | SHIPPED 12/30
106126 | 3760 | 50 | 2021-12-27 | 5 | 2021-12-22 | 2021-12-30 |  | X | 61 | 12 | 37 | 1 | 1 | 1B/1T |  | kit clear 12/22 | SHIPPED 12/30
106882 | 5017.5 | 2 | 2021-12-17 | 5 | 2021-12-22 | 2021-12-30 |  | X | 1263 | 92 | 96 | 0 | 1 | 2T |  | KIT CLEAR 12/22 | SHIPPED 12/30
106964 | 2122.6 | 20 | 2021-12-14 | 3 | 2021-12-28 | 2021-01-03 |  | X | 135 | 1 | 35 | 1 | 1 | 1B/1T |  | KIT CLEAR 12/28 | SHIPPED 12/29
107054 | 2258.05 | 3 | 2022-01-05 | 5 | 2021-12-27 | 12/30* |  | X | 239 | 60 | 32 | 1 | 1 | 1B/1T |  | kit clear 12/27 | SHIPPED 12/29
106772 2nd | 2060.16 | 29 | 2021-12-07 | 5 | 2021-12-22 | 2021-12-30 |  | X | 181 | 24 | 41 | 0 | 1 | 1T | ROWC 1st Article | 2ND ART KIT CLEAR 12/22 | SHIPPED 12/29
104636-1 | 4967 | 100/1200 | 2021-11-29 | 20 | N/C | 2021-12-28 |  | X | 148 | 9 | 59 | 1 | 1 | 1B/1T | ROWC B104272 | kit clear 1/11 | SHIPPED 12/29
106776 2nd | 2060.16 | 29 | 2021-12-07 | 5 | 2021-12-22 | 2021-12-30 |  | X | 181 | 24 | 41 | 0 | 1 | 1T | ROWC 1st Article | 2ND ART KIT CLEAR 12/22 | SHIPPED 12/28
106580 | 4617 | 20 | 2021-12-21 | 5 | 2021-12-22 | 2021-12-30 |  | X | 674 | 11 | 84 | 1 | 1 | 1B/2T |  | KIT CLEAR 12/22 | SHIPPED 12/28
107024 | 3687 | 10 | 2021-12-17 | 5 | 2021-12-22 | 2021-12-29 |  | X | 466 | 5 | 128 | 1 | 1 | 2B/1T |  | KIT CLEAR 12/21 | SHIPPED 12/28
106839 | 4438.78 | 3FA/30 | 2021-12-16 | 5 | 2021-12-20 | 2021-12-28 |  | X | 1306 | 44 | 205 | 1 | 1 | 1B/3T |  | KIT CLEAR 12/20 | SHIPPED 12/27
106785 | 3597.7 | 5 | 2021-12-07 | 5 | 2021-12-17 | 2021-12-27 |  | X | 1405 | 11 | 93 | 1 | 1 | 1B/2T |  | KIT CLEAR 12/17 | SHIPPED 12/27
106784 | 2350 | 5 | 2021-12-17 | 5 | 2021-12-27 | 2021-12-30 |  | X | 327 | 8 | 105 | 1 | 1 | 2B/2T | ROWC B104955 | KIT CLEAR 12/27 | SHIPPED 12/27
105483 | 1732.5 | 30 | 2022-01-06 | 15 | 2021-12-27 | 2021-12-30 |  | X | 0 | 74 | 0 | 0 | 0 | 0 | THT only | KIT CLEAR 12/27 | SHIPPED 12/27
107087 | 450 | 6 |  | 3 | 2021-12-21 | 2021-12-23 | [8 empty] | REWORK 97453 | kit clear 12/17 | SHIPPED 12/23
107402 | 240 | 3 |  | 3 | 2021-12-21 | 2021-12-23 | [8 empty] | REWORK PMS | kit clear 12/17 | SHIPPED 12/23
107159 | 3034.16 | 28 | 2021-12-20 | 5 | 2021-12-17 | 2021-12-27 |  | X | 257 | 13 | 34 | 0 | 1 | 1T |  | kit clear 12/17 | SHIPPED 12/23
106039 | 14150 | 100 | 2021-12-06 | 5 | 2021-12-16 | 2021-12-23 |  | X | 265 | 11 | 43 | 1 | 1 | 1B/2T | ROWC B102764 | KIT CLEAR 12/17 | SHIPPED 12/23
106622 | 5008.5 | 50 | 2021-12-16 | 5 | 2021-12-17 | 2021-12-27 |  | X | 344 | 11 | 79 | 1 | 1 | 1B/2T |  | kit clear 12/17 | SHIPPED 12/22
104378 | 1540.15 | 5 | 2021-08-12 | 5 | 2021-12-17 | 2021-12-27 |  | X | 673 | 24 | 70 | 1 | 1 | 1B/1T |  |  | SHIPPED 12/22
105929 | 3577.5 | 150 | 2021-12-01 | 15 | N/C | 2021-12-22 |  | X | 99 | 12 | 37 | 0 | 1 | 2T | ROWC B103338 | SHORT 1 ITEM | SHIPPED 12/22
106584 | 3418.74 | 27 | 2021-12-02 | 5 | 2021-12-17 | 2021-12-27 |  | X | 487 | 0 | 89 | 1 | 1 | 1B/1T |  | KIT CLEAR 12/17 | SHIPPED 12/21
107206 | 2538 | 200 | 2021-12-23 | 3 | 2021-12-17 | 2021-12-22 |  | X | 8 | 0 | 3 | 1 | 1 | 1B/1T |  | KIT CLEAR 12/17 | SHIPPED 12/21
106913 | 1448 | 300 | 2021-12-16 | 10 | 2021-12-13 | 2021-12-28 |  | X | 48 | 4 | 23 | 1 | 1 | 1B/1T |  | KIT CLEAR 12/13 | SHIPPED 12/20
106325 | 14180 | 1000 | 2021-12-09 | 10 | 2021-12-09 | 2021-12-23 |  | X | 25 | 0 | 16 | 1 | 1 | 1B/2T | RONC B96744 | KIT CLEAR 12/9 | SHIPPED 12/20
106325 | 14180 | 1000 | 2021-12-09 | 10 | 2021-12-09 | 2021-12-23 |  | X | 25 | 0 | 16 | 1 | 1 | 1B/2T | RONC B96744 | KIT CLEAR 12/9 | SHIPPED 12/17
106836 | 2745.95 | 5 | 2021-11-29 | 5 | 2021-12-13 | 2021-12-20 |  | X | 504 | 31 | 104 | 1 | 1 | 1B/2T |  | kit clear 12/13 | SHIPPED 12/17
106614 | 3738.5 | 10 | 2021-12-13 | 5 | 2021-12-10 | 2021-12-17 |  | X | 609 | 20 | 145 | 1 | 1 | 1B/2T |  | KIT CLEAR 12/10 | SHIPPED 12/17
105008 | 2997 | 20 | 1902-10-17 | 10 | 2021-11-24 | 2021-12-13 |  | X | 389 | 18 | 53 | 1 | 1 | 1B/2T |  | KIT CLEAR 11/24 | SHIPPED 12/17
105640 | 2080.17 | 37 | 2021-10-19 | 10 | 2021-11-17 | 2021-12-03 |  | X | 72 | 72 | 3 | 0 | 1 | 1T |  | KIT CLEAR 11/17 | SHIPPED 12/17
103015 | 3303.75 | 5 | 2021-11-05 | 15 | 2021-11-23 | 2021-12-16 |  | X | 1048 | 5 | 148 | 1 | 1 | 2B/2T |  | KIT CLEAR 11/23 | SHIPPED 12/16
104302 | 5277.6 | 240 | 2021-09-29 | 20 | 2021-12-02 | 2021-12-30 |  | X | 118 | 1 | 55 | 1 | 1 | 1B/1T |  | KIT CLEAR 12/2 | SHIPPED 12/16
107141 | 2000 | 25 | 2021-12-01 | 5 | 2021-11-22 | 2021-12-01 |  | X | [6 empty] | PAID REWORK | KIT CLEAR 11/22 | SHIPPED 12/15
106616 | 1640.5 | 10 | 2021-12-27 | 10 | 2021-12-06 | 2021-12-20 |  | X | 1 | 20 | 1 | 0 | 1 | 1T |  | KIT CLEAR 12/7 | SHIPPED 12/15
106764 | 3375 | 20 | 2021-12-06 | 3 | 2021-12-13 | 2021-12-16 |  | X | 201 | 21 | 61 | 1 | 1 | 1B/1T |  | KIT CLEAR 12/13 | SHIPPED 12/15
105088 | 698 | 100 | 2021-10-15 | 10 | 2021-10-01 | 2021-12-22 |  | X | 37 | 0 | 15 | 1 | 1 | 1B/2T | SPLIT SHIPMENT BAL | KIT CLEAR 10/1 | SHIPPED 12/15
106717 | 999.5 | 10 | 2021-12-22 | 10 | 2021-12-02 | 2021-12-16 |  | X | 40 | 47 | 1 | 0 | 1 | 1T | RONC B106341 | KIT CLEAR 12/2 | SHIPPED 12/15
105082 | 2393.5 | 10 | 2021-12-06 | 5 | 2021-12-08 | 2021-12-15 |  | X | 295 | 64 | 82 | 0 | 1 | 2T |  | KIT CLEAR 12/8 | SHIPPED 12/15
106367 | 1998.5 | 5 | 2021-12-21 | 10 | 2021-12-01 | 2021-12-15 |  | X | 67 | 45 | 4 | 0 | 1 | 1T |  | KIT CLEAR 12/1 | SHIPPED 12/15
106095 | 1846 | 3 | 2021-12-13 | 15 | 2021-11-23 | 2021-12-16 |  | X | 92 | 50 | 15 | 1 | 1 | 1B/1T |  | KIT CLEAR 11/23 | SHIPPED 12/14
106710 | 3377.5 | 30 | 2021-12-07 | 5 | 2021-12-07 | 2021-12-14 |  | X | 239 | 7 | 91 | 1 | 1 | 1B/2T |  | kit clear 12/7 | SHIPPED 12/14
105880 | 1542 | 24 | 2021-12-15 | 5 | 2021-12-04 | 2021-12-14 |  | X | 90 | 0 | 3 | 0 | 1 | 1B/1T |  | KIT CLEAR 12/7 | SHIPPED 12/14
104586 | 251.72 | 58 | 2021-10-08 | 10 | 2021-09-28 | 2021-10-15 |  | X | 3 | 2 | 3 | 1 | 1 | 1B/1T |  | KIT CLEAR 9/28 | SHIPPED 12/13
106403 | 1114 | 5FA/20 | 2021-12-02 | 5 | 2021-12-09 | 2021-12-16 |  | X | 32 | 8 | 18 | 1 | 1 | 1B/1T |  | KIT CLEAR 12/9 | SHIPPED 12/13
105166 | 1346.25 | 75 | 2021-12-13 | 10 | 2021-11-29 | 2021-12-13 |  | X | 56 | 3 | 24 | 1 | 1 | 1B/1T | RONC B96867 | KIT CLEAR 11/29 | SHIPPED 12/13
106772 | 2071.5 | 1FA/30 | 2021-12-07 | 5 | 2021-12-06 | 2021-12-13 |  | X | 189 | 24 | 41 | 0 | 1 | 1T |  | KIT FA CLEAR 12/6 | SHIPPED 12/13
106776 | 2071.5 | 1FA/30 | 2021-12-07 | 5 | 2021-12-06 | 2021-12-13 |  | X | 189 | 24 | 41 | 0 | 1 | 1T | ROWC B106772 | KIT FA CLEAR 12/6 | SHIPPED 12/13
106458 | 2926.94 | 14 | 2021-12-06 | 10,5 | 2021-12-06 | 2021-12-13 |  | X | 338 | 45 | 76 | 1 | 1 | 1B/1T |  | KIT CLEAR 12/6 | SHIPPED 12/13
106805 | 2237.5 | 10 | 2021-12-13 | 3 | 2021-12-08 | 2021-12-13 |  | X | 26 | 28 | 13 | 1 | 0 | 1B |  | KIT CLEAR 12/8 | SHIPPED 12/13
105783 | 6485 | 500 | 2021-11-01 | 3 | 2021-12-07 | 2021-12-10 |  | X | 36 | 0 | 22 | 0 | 1 | 2T |  | KIT CLEAR 12/7 | SHIPPED 12/10
104539 | 1570 | 30 | 2022-01-20 | 20 | 2021-11-24 | 2021-12-10 |  | X | 113 | 20 | 41 | 1 | 1 | 1B/1T | ROWC B97023 | KIT CLEAR 11/24 | SHIPPED 12/10
106140 | 3871.3 | 10 | 2021-11-24 | 5 | N/C | 2021-12-09 |  | X | 1323 | 34 | 204 | 1 | 1 | 2B/2T | ROWC B99292 | KIT CLEAR 12/2 | SHIPPED 12/10
106410 | 3418.4 | 20 | 2021-11-30 | 5 | 2021-12-02 | 2021-12-09 |  | X | 374 | 0 | 150 | 1 | 1 | 2B/2T |  | KIT CLEAR 12/2 | SHIPPED 12/9
106544 | 2829.25 | 5 | 2021-12-01 | 3 | 2021-12-06 | 2021-12-09 |  | X | 728 | 19 | 125 | 1 | 1 | 1B/2T |  | KIT CLEAR 12/6 | SHIPPED 12/9
106219 | 1996.75 | 20 | 2021-11-22 | 5 | 2021-12-02 | 2021-12-09 |  | X | 256 | 14 | 46 | 1 | 1 | 1B/1T |  | KIT CLEAR 11/15 | SHIPPED 12/9
106140 | 13549.67 | 35 | 2021-11-24 | 5 | N/C | 2021-12-09 |  | X | 1323 | 34 | 204 | 1 | 1 | 2B/2T | ROWC B99292 | KIT CLEAR 12/2 | SHIPPED 12/9
105881 | 594.6 | 2 | 2021-11-29 | 15 | 2021-11-11 | 2021-12-06 |  | X | 251 | 76 | 57 | 1 | 1 | 1B/1T |  | KIT CLEAR 11/11 | SHIPPED 12/9
106532 | 3027.9 | 6 | 2021-11-22 | 3 | 2021-12-03 | 2021-12-08 |  | X | 641 | 18 | 72 | 1 | 1 | 1B/1T | 12/8 - SHIELD DNF | KIT CLEAR 12/3 | SHIPPED 12/8
105305 | 2020 | 100 | 2021-12-10 | 3 | 2021-12-03 | 2021-12-08 |  | X | 6 | 2 | 2 | 0 | 1 | 1T |  | KIT CLEAR 12/3 | SHIPPED 12/8
104509 | 15750 | 600 | 2021-10-04 | 20 | 2021-11-08 | 2021-12-08 |  | X | 150 | 2 | 49 | 0 | 1 | 2T | ROWC B103603 | SHORT 2 ITEMS | SHIPPED 12/8
106777 | 500.4 | 121 | 2021-12-03 | 3 | 2021-12-06 | 2021-12-09 |  | X | [6 empty] | REWORK | NO DOC. | SHIPPED 12/7
105972 | 1260 | 8 | 2021-11-26 | 10 | 2021-11-18 | 2021-12-06 |  | X | 0 | 35 | 0 | 0 | 0 | 0 | TH only | KIT CLEAR 11/18 | SHIPPED 12/7
106782 | 2589.84 | 28 | 2021-12-01 | 5 | 2021-11-30 | 2021-12-07 |  | X | 177 | 9 | 59 | 1 | 1 | 1B/1T |  | KIT CLEAR 11/30 | SHIPPED 12/7
106711 | 3905.5 | 30 | 2021-12-07 | 5 | 2021-11-30 | 2021-12-07 |  | X | 245 | 34 | 42 | 1 | 1 | 1B/1T |  | KIT CLEAR 11/30 | SHIPPED 12/7
104662 | 3690 | 90 | 2021-09-01 | 5 | 2021-11-30 | 2021-12-07 |  | X | 167 | 1 | 56 | 1 | 1 | 1B/1T |  | 2ND ARTICLE RELEASED 11/30 | SHIPPED 12/7
106145 | 1963.75 | 5 | 2021-12-02 | 10 | 2021-11-19 | 2021-12-07 |  | X | 94 | 91 | 10 | 0 | 1 | 1T |  | KIT CLEAR 11/19 | SHIPPED 12/6
106584 | 2265 | 3FA/30 | 2021-12-02 | 5 | 2021-11-29 | 2021-12-06 |  | X | 487 | 0 | 89 | 1 | 1 | 1B/1T |  | KIT CLEAR 11/30 | SHIPPED 12/6
105944 | 4734 | 50 | 2021-12-06 | 15 | 2021-11-12 | 2021-12-06 |  | X | 47 | 67 | 15 | 1 | 1 | 1B/1T | RONC B104923 | SHORT 1 ITEM | SHIPPED 12/6
105881 | 2378.4 | 8 | 2021-11-29 | 15 | 2021-11-11 | 2021-12-06 |  | X | 251 | 76 | 57 | 1 | 1 | 1B/1T |  | KIT CLEAR 11/11 | SHIPPED 12/6
106121 | 2444 | 20 | 2021-11-29 | 3 | 2021-11-29 | 2021-12-03 |  | X | 400 | 16 | 70 | 1 | 1 | 1B/1T |  | KIT CLEAR 11/29 | SHIPPED 12/3
106502 | 2540 | 2 | 2021-11-19 | 5 | 2021-11-24 | 2021-12-03 |  | X | 561 | 46 | 54 | 1 | 1 | 1B/1T |  | KIT CLEAR 11/24 | SHIPPED 12/3
104421 | 4365 | 450 | 2021-11-16 | 15 | 2021-11-10 | 2021-12-03 |  | X | 53 | 1 | 28 | 0 | 1 | 2T |  | KIT CLEAR 11/16 | SHIPPED 12/3
104931 2nd | 6952 | 22 | 2021-09-07 | 5 | 2021-11-22 | 2021-12-02 |  | X | 1214 | 14 | 115 | 1 | 1 | 2B/2T | ROWC 1st Article | KIT CLEAR 11/22 | SHIPPED 12/2
106455 | 1786 | 80 | 2021-11-30 | 5 | 2021-11-22 | 2021-12-02 |  | X | 18 | 4 | 9 | 1 | 1 | 1B/1T |  | KIT CLEAR 11/22 | SHIPPED 12/2
106260 | 3426.5 | 210 | 2021-11-17 | 9 | 2021-11-17 | 2021-12-02 |  | X | 64 | 1 | 38 | 1 | 1 | 1B/1T |  | KIT CLEAR 11/17 | SHIPPED 12/2
106524 | 2525 | 650 | 2021-12-02 | 5 | 2021-11-23 | 2021-12-03 |  | X | 2 | 0 | 2 | 0 | 1 | 1T | RONC B103819 | KIT CLEAR 11/23 | SHIPPED 12/2
101761 2nd Article | 2511.6 | 150 | 2021-06-21 | 5 | 2021-11-22 | 2021-12-02 |  | X | 146 | 27 | 66 | 1 | 1 | 2B/2T | RONC 1st Article | KIT CLEAR 11/22 | SHIPPED 12/2
106598 | 2985.36 | 8 | 2021-12-02 | 5 | 2021-11-19 | 2021-11-30 |  | X | 795 | 1 | 35 | 1 | 1 | 1B/1T | SHIPPING HOLD | KIT CLEAR 11/19 | SHIPPED 12/1
106689 | 8970 | 104 | 2021-12-01 | 5 | 2021-11-22 | 2021-12-01 |  | X | [6 empty] | PAID REWORK | KIT CLEAR 11/22 | SHIPPED 12/1
106343 | 5149 | 50 | 2021-11-18 | 10 | 2021-11-15 | 2021-12-01 |  | X | 441 | 0 | 118 | 1 | 1 | 2B/2T | ROWC B98944 | KIT CLEAR 11/15 | SHIPPED 12/1
106384 | 3214.12 | 6 | 2021-11-24 | 5 | 2021-11-22 | 2021-12-02 |  | X | 1017 | 3 | 64 | 1 | 1 | 1B/1T |  | KIT CLEAR 11/22 | SHIPPED 12/1
105088 | 1047 | 150 | 2021-10-15 | 10 | 2021-10-01 | 2021-11-22 |  | X | 37 | 0 | 15 | 1 | 1 | 1B/2T | ROWC B103760 | KIT CLEAR 10/1 | SHIPPED 11/30
106534 | 2621 | 6 | 2021-12-01 | 5 | 2021-11-22 | 2021-12-02 |  | X | 493 | 8 | 52 | 1 | 1 | 1B/1T |  | KIT CLEAR 11/22 | SHIPPED 11/30
105187 | 3137.46 | 12 | 2021-10-07 | 5 | 2021-09-28 | 10/5* |  | X | 422 | 74 | 80 | 1 | 1 |  | SHIPPING HOLD | SHORT PCB + 1 ITEM | SHIPPED 11/30
106341 | 1064.5 | 10 | 2021-12-09 | 10 | 2021-11-15 | 2021-12-01 |  | X | 40 | 47 | 1 | 0 | 1 | 1T |  | KIT CLEAR 11/15 | SHIPPED 11/30
106093 | 5412.5 | 25 | 2021-11-15 | 5 | 2021-11-18 | 2021-11-30 |  | X | 863 | 1 | 182 | 1 | 1 | 2B/2T | ROWC B104907 | KIT CLEAR 11/18 | SHIPPED 11/30
100607 | 3043.3 | 85 | 2021-10-19 | 20 | N/C | 2021-12-07 |  | X | 106 | 5 | 40 | 0 | 1 | 1T |  | KIT CLEASR 11/29 | SHIPPED 11/30
104794 | 3833.5 | 10 | 2021-11-02 | 5 | 2021-11-17 | 2021-11-23 |  | X | 662 | 42 | 134 | 0 | 1 | 2T |  | KIT CLEAR 11/23 | SHIPPED 11/29
106663 | 4899 | 50 | 2021-12-02 | 2 | 2021-11-23 | 2021-11-30 |  | X | 185 | 0 | 60 | 1 | 1 | 1B/1T |  | KIT CLEAR 11/23 | SHIPPED 11/29
105090 | 1795 | 3 | 2021-11-08 | 15 | 2021-11-09 | 2021-11-30 |  | X | 239 | 11 | 39 | 1 | 1 | 1B/1T |  | KIT CLEAR 11/9 | SHIPPED 11/29
106662 | 2220 | 50 | 2021-12-01 | 2 | 2021-11-23 | 2021-11-29 |  | X | 17 | 3 | 10 | 0 | 1 | 1T |  | KIT CLEAR 11/23 | SHIPPED 11/29
105917 | 11856.5 | 50 | 2021-11-02 | 3 | 2021-11-19 | 2021-11-29 |  | X | 728 | 0 | 51 | 1 | 1 | 1B/2T | Facebook | KIT CLEAR 11/19 | SHIPPED 11/29
99731 | 2466.75 | 275 | 2021-11-16 | 10 | 2021-11-11 | 2021-11-29 |  | X | 39 | 0 | 21 | 1 | 1 | 1B/1T | ROWC B94947 | KIT CLEAR 11/11 | SHIPPED 11/29
93544 | 0 | 0 | 2021-03-19 | 20 | 2021-03-15 | 2021-04-16 |  | X | 239 | 1 | 95 | 1 | 1 |  | RMA FINAL | RMA FINAL | SHIPPED 11/23
106219 | 1996.75 | 5FA/25 | 2021-11-22 | 5 | 2021-11-16 | 2021-11-23 |  | X | 256 | 14 | 46 | 1 | 1 | 1B/1T |  | KIT CLEAR 11/15 | SHIPPED 11/23
106087 | 1750 | 250 | 2021-11-24 | 10 | 2021-11-08 | 2021-11-23 |  | X | 5 | 3 | 4 | 0 | 1 | 1T | RONC B105080 | KIT CLEAR 11/9 | SHIPPED 11/23
104974 | 8034 | 200 | 2021-11-18 | 20 | 2021-10-26 | 2021-11-23 |  | X | 103 | 0 | 50 | 1 | 1 | 1B/2T | RONC B102107 | KIT CLEAR 10/26 | SHIPPED 11/22
106440 | 6034 | 10 | 2021-11-16 | 3 | 2021-11-17 | 2021-11-22 |  | X | 829 | 68 | 115 | 0 | 1 | 2T |  | SHORT 3 ITEMS | SHIPPED 11/22
104737 | 4376.55 | 5 | 2021-09-22 | 5 | N/C | ??? |  | X | 1407 | 81 | 171 | 1 | 1 | 1B/3T |  | KIT CLEAR 11/19 | SHIPPED 11/19
105951 | 3372.6 | 70 | 2021-11-15 | 10 | 2021-11-08 | 2021-11-22 |  | X | 183 | 0 | 34 | 1 | 1 | 1B/1T |  | KIT CLEAR 11/8
105947 | 5097.96 | 4 | 2021-10-29 | 5 | 2021-11-15 | 2021-11-22 |  | X | 1265 | 93 | 142 | 1 | 1 | 1B/2T |  | KIT CLEAR 11/15 | SHIPPED 11/19
106233 | 1102.5 | 25 | 2021-11-12 | 5 | 2021-11-15 | 2021-11-22 |  | X | 126 | 0 | 54 | 1 | 1 | 1B/1T | RONC B105653 | KIT CLEAR 11/15 | SHIPPED 11/19
105575 | 4156 | 20 | 2021-11-16 | 5 | 2021-11-15 | 2021-11-22 |  | X | 511 | 5 | 56 | 0 | 1 | 1T |  | KIT CLEAR 11/15 | SHIPPED 11/18
105914 | 6146.5 | 75 | 2021-11-01 | 10 | 2021-11-10 | 2021-11-22 |  | X | 287 | 45 | 39 | 1 | 1 | 1B/1T | ROWC B98877 | KIT CLEAR 11/10 | SHIPPED 11/18
105915 | 3983 | 75 | 2021-11-01 | 10 | 2021-11-08 | 2021-11-22 |  | X | 173 | 18 | 50 | 1 | 1 | 1B/1T | ROWC B98881 | KIT CLEAR 11/8 | SHIPPED 11/18
104894 | 1976.73 | 53/95 | 2021-10-18 | 15 | N/C | 11/19* |  | X | 131 | 7 | 32 | 1 | 1 | 1B/1T |  | kit clear 1/4 | SHIPPED 11/16
105291 | 2804.5 | 15 | 2021-10-19 | 10 | 2021-11-03 | 2021-11-17 |  | X | 446 | 41 | 33 | 1 | 1 | 1B/1T |  | KIT CLEAR 11/3 | SHIPPED 11/16
103558 | 6284.9 | 85 | 2021-08-26 | 15 | 2021-11-09 | 2021-12-03 |  | X | 342 | 1 | 93 | 1 | 1 | 2B/2T |  | QTY 85 CLEAR 11/9 | SHIPPED 11/15
104586 | 251.72 | 58 | 2021-10-08 | 10 | 2021-09-28 | 2021-10-15 |  | X | 3 | 2 | 3 | 1 | 1 | 1B/1T |  | KIT CLEAR 9/28 | SHIPPED 11/15
106057 | 1996.9 | 190 | 2021-10-22 | 10 | N/C | 2021-11-15 |  | X | 34 | 3 | 22 | 1 | 1 | 1B/1T | SS/Excel in kit box | WTG FOR PART CONFIRM | SHIPPED 11/15
105807 | 2027.68 | 58 | 2021-11-10 | 10 | N/C | 2021-11-16 |  | X | 178 | 0 | 34 | 1 | 1 | 1B/2T | ROWC B100387 | PAID EXPEDITE | SHIPPED 11/15
106208 | 8530.4 | 40 | 2021-11-08 | 5 | N/C | 2021-11-16 |  | X | 819 | 45 | 63 | 1 | 1 | 2B/1T |  | KIT CLEAR 11/8 | SHIPPED 11/12
104419 | 4582.5 | 450 | 2021-10-18 | 15 | 2021-10-26 | 2021-11-15 |  | X | 60 | 1 | 30 | 1 | 1 | 1B/1T |  | KIT CLEAR 10/27 | SHIPPED 11/12
105652 | 3075 | 50 | 2021-11-11 | 2 | N/C | ??? |  | X | 1 | 1 | 1 | 1 | 0 | 1B |  | KIT CLEAR 11/11 | SHIPPED 11/12
105234 | 2793 | 10 | 2021-10-22 | 5 | 2021-11-08 | 2021-11-15 |  | X | 529 | 18 | 70 | 0 | 1 | 2T |  | KIT CLEAR 11/8 | SHIPPED 11/11
105807 | 2971.6 | 85/143 | 2021-11-10 | 10 | N/C | 2021-11-11 |  | X | 178 | 0 | 34 | 1 | 1 | 1B/2T | ROWC B100387 | PAID EXPEDITE | SHIPPED 11/11
106084 | 4072 | 12 | 2021-11-02 | 2 | 2021-11-09 | 2021-11-11 |  | X | 335 | 1 | 85 | 1 | 1 | 1B/1T |  | KIT CLEAR 11/9 | SHIPPED 11/11
106107 | 0 | 64 |  |  |  | 2021-11-11 |  | X | 109 | 18 | 61 | 1 | 1 | 1B/1T | NO CHARGE RWK | KIT CLEAR 10/29 | SHIPPED 11/10
106413 | 4634.16 | 102 | 2021-11-04 | 5 | N/C | 2021-11-10 |  | X | 154 | 8 | 57 | 1 | 1 | 1B/2T |  | KIT CLEAR 11/3 | SHIPPED 11/10
105822 | 2273.9 | 35 | 2021-10-28 | 9 | 2021-10-29 | 2021-11-11 |  | X | 109 | 18 | 61 | 1 | 1 | 1B/1T | RONC B103365 | KIT CLEAR 10/29 | SHIPPED 11/10
106111 | 4634.16 | 102 | 2021-11-04 | 5 | N/C | 2021-11-10 |  | X | 154 | 8 | 57 | 1 | 1 | 1B/2T |  | KIT CLEAR 11/3 | SHIPPED 11/10
106241 | 690 | 10 FA | 2021-11-05 | 5 | 2021-11-03 | 11/10* |  | X | [6 empty] | REWORK ONLY | KIT CLEAR 11/3 | SHIPPED 11/10
105937 | 5684.75 | 25 | 2021-10-20 | 3 | 2021-11-04 | 2021-11-09 |  | X | 466 | 0 | 83 | 1 | 1 |  |  | KIT CLEAR 11/4 | SHIPPED 11/9
106112 | 4654.73 | 103 | 2021-11-04 | 5 | 2021-11-03 | 2021-11-09 |  | X | 134 | 18 | 47 | 0 | 1 | 2T |  | KIT CLEAR 11/3 | SHIPPED 11/9
105928 | 2685 | 250 | 2021-11-15 | 10 | 2021-11-01 | 2021-11-15 |  | X | 24 | 6 | 9 | 0 | 1 | 1T | RONC B103909 | 2ND ARTICLE CLEAR 11/1 | SHIPPED 11/8
105669 | 3498 | 10 | 2021-10-29 | 5 | 2021-11-03 | 2021-11-10 |  | X | 639 | 9 | 126 | 1 | 1 | 2B/2T | Update - Same BOM/GERBER change only | KIT CLEAR 11/3 | SHIPPED 11/8
105905 | 1415.7 | 22 | 2021-11-12 | 10 | 2021-10-29 | 2021-11-12 |  | X | 123 | 12 | 45 | 0 | 1 | 1T | ROWC B100316 | KIT CLEAR 10/29 | SHIPPED 11/8
105716 | 3586.5 | 50 | 2021-10-08 | 5 | 2021-11-01 | 2021-11-08 |  | X | 307 | 1 | 80 | 1 | 1 | 2B/2T | RONC B99931 | KIT CLEAR 11/1 | SHIPPED 11/8
105244 | 1988 | 24 | 2021-11-04 | 5 | 2021-11-03 | 2021-11-10 |  | X | 31 | 33 | 1 | 1 | 1 | 1B/1T |  | KIT CLEAR 11/3 | SHIPPED 11/5
103877 2nd | 2221 | 6 | 2021-08-19 | 10 | 2021-10-27 | 2021-11-10 |  | X | 297 | 4 | 162 | 1 | 1 | 1B/2T | ROWC 1st Article | KIT CLEAR 10/27 | SHIPPED 11/5
105264 | 2578.5 | 50 | 2021-11-30 | 5 | 2021-10-29 | 2021-11-05 |  | X | 117 | 0 | 32 | 1 | 1 | 1B/1T |  | KIT CLEAR 10/29 | SHIPPED 11/5
105552 | 4176 | 10 | 2021-10-27 | 10 | 2021-10-22 | 2021-11-05 |  | X | 522 | 0 | 124 | 1 | 1 | 2B/2T | ROWC B104504 | KIT CLEAR 10/22 | SHIPPED 11/5
105111 | 6788.5 | 350 | 2021-10-05 | 10 | 2021-10-22 | 2021-11-05 |  | X | 104 | 0 | 58 | 0 | 1 | 2T |  | KIT CLEAR 10/22 | SHIPPED 11/5
104432 | 132 | 22 | 2021-09-14 | 10 | 2021-10-27 | 2021-11-10 |  | X | 34 | 0 | 11 | 0 | 1 | 1T |  | SHORT PCB | SHIPPED 11/4
105655 | 1470 | 25 | 2021-10-28 | 10 | 2021-10-22 | 2021-11-05 |  | X | 17 | 0 | 7 | 0 | 1 | 1T |  | KIT CLEAR 10/22 | SHIPPED 11/4
103558 | 2513.96 | 34 | 2021-08-26 | 15 | N/C | 2021-11-05 |  | X | 342 | 1 | 93 | 1 | 1 | 2B/2T | QTY 30/175 SHIP 8/19 | SHORT 1 ITEM | SHIPPED 11/4
106107 | 3679.2 | 70 | 2021-11-04 | 3 | 2021-11-01 | 2021-11-04 |  | X | 46 | 1 | 27 | 1 | 1 | 1B/1T |  | KIT CLEAR 11/1 | SHIPPED 11/4
105795 | 3853 | 20 | 2021-10-13 | 3 | 2021-11-01 | 2021-11-04 |  | X | 297 | 15 | 36 | 1 | 1 | 1B/1T |  | KIT CLEAR 11/1 | SHIPPED 11/4
105016 | 14278.4 | 132 | 2021-10-14 | 5 | 2021-10-27 | 2021-11-03 |  | X | 20 | 1 | 14 | 1 | 1 | 1B/1T | ROWC B102540 | KIT CLEAR 10/27 | SHIPPED 11/3
105080 | 1212.75 | 147 | 2021-09-20 | 5 | 2021-10-13 | 2021-11-03 |  | X | 5 | 3 | 4 | 0 | 1 | 1T | SS/Excel in kit box | SHORT 1 ITEM | SHIPPED 11/3
105016 | 14278.4 | 132 | 2021-10-14 | 5 | 2021-10-27 | 2021-11-03 |  | X | 20 | 1 | 14 | 1 | 1 | 1B/1T | ROWC B102540 | KIT CLEAR 10/27 | SHIPPED 11/3
105208 | 5146 | 200 | 2021-10-20 | 9 | 2021-10-21 | 2021-11-03 |  | X | 113 | 4 | 48 | 0 | 1 | 2T |  | KIT CLEAR 10/21 | SHIPPED 11/3
104515 | 8353.88 | 31 | 2021-10-07 | 15 | 2021-10-01 | 2021-11-02 |  | X | 766 | 37 | 109 | 1 | 1 | 1B/2T | ROWC B98233 | KIT CLEAR 10/12 | SHIPPED 11/2
105535 | 2769 | 13 | 2021-10-29 | 5 | N/C | 2021-11-02 |  | X | 547 | 28 | 131 | 1 | 1 | 2B/2T | SS/Excel in kit box | KIT CLEAR 10/26 | SHIPPED 11/2
105653 | 1570 | 25 | 2021-10-29 | 10 | 2021-11-19 | 2021-11-02 |  | X | 126 | 0 | 54 | 1 | 1 | 1B/1T |  | KIT CLEAR 10/19 | SHIPPED 11/2
105883 | 1460 | 60 | 2021-10-25 | 10 | 2021-10-19 | 2021-11-02 |  | X | 0 | 10 | 0 | 0 | 0 | 0 | TH only | KIT CLEAR 10/19 | SHIPPED 11/2
105079 | 1312.5 | 7 | 2021-10-08 | 10 | 2021-10-18 | 2021-11-02 |  | X | 609 | 2 | 107 | 0 | 1 |  | EXPEDITE TO 11/3 | KIT CLEAR 10/20 | SHIPPED 11/2
105618 | 2850 | 6FA | 2021-10-21 | 3 | 2021-10-27 | 2021-11-01 |  | X | 432 | 9 | 57 | 1 | 1 | 1B/1T |  | SHORT 3 ITEMS | SHIPPED 11/1
104923 | 4449.96 | 47 | 2021-10-12 | 15 | 2021-10-18 | 2021-11-01 |  | X | 47 | 67 | 15 | 1 | 1 | 1B/1T | ROWC B101729 | KIT CLEAR 10/9 | SHIPPED 11/1
106057 | 1862.5 | 10FA/200 | 2021-10-22 | 3 | N/C | 2021-11-02 |  | X | 34 | 3 | 22 | 1 | 1 | 1B/1T | SS/Excel in kit box | WTG FOR PART CONFIRM | SHIPPED 10/28
104952 | 2971 | 9 | 2021-10-06 | 5 | N/C | 2021-10-28 |  | X | 26 | 0 | 5 | 0 | 1 | 1T | 1 DAY TURN FAVOR | KIT CLEAR 10/27 | SHIPPED 10/28
105477 | 11046 | 50 | 2021-10-07 | 10 | N/C | ??? |  | X | 1052 | 0 | 218 | 1 | 1 | 2B/3T | RONC B98626 | KIT CLEAR 10/6 | SHIPPED 10/28
105145 | 3501 | 300 | 2021-10-19 | 10 | 2021-10-15 | 2021-10-29 |  | X | 47 | 3 | 20 | 0 | 1 | 1T | RONC B95042 | KIT CLEAR 10/15 | SHIPPED 10/28
105584 | 1123.2 | 30 | 2021-10-14 | 5 | 2021-10-14 | 2021-10-29 |  | X | 220 | 19 | 47 | 0 | 1 | 1T |  | KIT CLEAR 10/25 | SHIPPED 10/28
100606 | 5106.4 | 7FA | 2021-08-24 | 10 | 2021-10-15 | 2021-10-29 |  | X | 3696 | 7 | 238 | 1 | 1 | 2B/3T |  | SHORT PCB + 10 ITEMS | SHIPPED 10/28
104957 | 1296 | 42 | 2021-10-11 | 10 | N/C | 2021-10-29 |  | X | 100 | 62 | 11 | 0 | 1 | 1T | ROWC B95996 | KIT CLEAR 9/23 | SHIPPED 10/28
105241 | 3267.5 | 50 | 2021-10-19 | 5 | N/C | 2021-10-28 |  | X | 145 | 22 | 38 | 0 | 1 | 1T | EXPEDITE | SHORT 4 ITEMS | SHIPPED 10/27
105404 | 199.31 | 1 | 2021-10-20 | 5 | N/C | 2021-10-26 |  | X | 582 | 12 | 75 | 1 | 1 | 1B/1T | ROWC B98805 | KIT CLEAR 10/19 | SHIPPED 10/27
104420 | 2592 | 450 | 2021-10-21 | 15 | 2021-10-07 | 2021-10-28 |  | X | 10 | 4 | 9 | 1 | 1 | 1B/1T |  | KIT CLEAR 10/7 | SHIPPED 10/27
105376 | 7411.5 | 15 | 2021-10-06 | 10 | 2021-10-14 | 2021-10-28 |  | X | 0 | 158 | 0 | 0 | 0 | 0 | TH only | KIT CLEAR 10/14 | SHIPPED 10/27
105738 | 1680.5 | 150 | 2021-10-29 | 10 | 2021-10-15 | 2021-10-29 |  | X | 11 | 3 | 6 | 0 | 1 | 1T |  | KIT CLEAR 10/15 | SHIPPED 10/26
105555 | 2000 | 10 | 2021-11-03 | 10 | 2021-10-15 | 2021-10-29 |  | X | 1 | 0 | 1 | 1 | 0 | 1B |  | KIT CLEAR 10/15 | SHIPPED 10/26
105554 | 2000 | 10 | 2021-11-03 | 10 | 2021-10-15 | 2021-10-29 |  | X | 2 | 0 | 1 | 1 | 1 | 1B/1T |  | KIT CLEAR 10/15 | SHIPPED 10/26
105388 | 4758.9 | 30 | 2021-10-15 | 5 | 2021-10-20 | 2021-10-27 |  | X | 514 | 11 | 122 | 1 | 1 |  |  | KIT CLEAR 10/20 | SHIPPED 10/26
103335 | 6776 | 400 | 2021-09-08 | 10 | 2021-10-13 | 2021-10-27 |  | X | 83 | 0 | 47 | 1 | 1 | 2B/2T |  | KIT CLEAR 10/13 | SHIPPED 10/26
103255 | 5655.8 | 15 | 2021-10-21 | 10 | 2021-10-08 | 2021-10-28 |  | X | X | 130 | 7 | 0 | 1 | 1T | SS/Excel in kit box | KIT CLEAR 10/8 | SHIPPED 10/26
105404 | 3786.89 | 20 | 2021-10-20 | 5 | N/C | 2021-10-26 |  | X | 582 | 12 | 75 | 1 | 1 | 1B/1T | ROWC B98805 | KIT CLEAR 10/19 | SHIPPED 10/26
105661 | 4016.75 | 13 | 2021-10-06 | 3 | 2021-10-19 | 2021-10-22 |  | X | 341 | 21 | 51 | 1 | 1 | 1B/1T |  | KIT CLEAR 10/19 | SHIPPED 10/26
105648 | 4242.5 | 25 | 10/111 | 5 | N/C | 2021-10-25 |  | X | 416 | 6 | 145 | 1 | 1 | 1B/2T |  | KIT CLEAR 10/20 | SHIPPED 10/25
105799 | 3295.4 | 4 | 2021-10-13 | 5 | 2021-10-18 | 2021-10-25 |  | X | 623 | 42 | 129 | 1 | 1 | 1B/2T | SS/Excel in kit box | KIT CLEAR 10/18 | SHIPPED 10/25
104372 | 12867.4 | 140 | 2021-08-24 | 10 | 2021-10-12 | 2021-10-25 |  | X | 489 | 1 | 165 | 1 | 1 | 2B/2T | ROWC 2nd Article | SHORT PCB + 13 ITEMS | SHIPPED 10/25
105593 | 4680 | 120 | 2021-10-15 | 3 | N/C |  |  | X | [6 empty] | REWORK | NO DOC. | SHIPPED 10/22
105283 | 591.3 | 270 | 2021-10-21 | 5 | 2021-10-15 | 2021-10-22 |  | X | 2 | 0 | 2 | 0 | 1 | 1T | RONC B103819 | KIT CLEAR 10/15 | SHIPPED 10/22
104615 | 2886 | 39 | 2021-09-21 | 5 | N/C | 10/21* |  | X | 267 | 11 | 75 | 1 | 1 | 1B/2T | SS/Excel in kit box | KIT CLEAR 9/22 | SHIPPED 10/22
104618 2nd | 4455.36 | 39 | 2021-09-16 | 10 | 2021-10-15 | 2021-10-22 |  | X | 544 | 13 | 95 | 1 | 1 | 1B/1T | ROWC 1st Article | KIT CLEAR 10/15 | SHIPPED 10/22
104372 | 4995.5 | 50 | 2021-08-24 | 10 | 2021-10-12 | 2021-10-25 |  | X | 489 | 1 | 165 | 1 | 1 | 2B/2T | ROWC 2nd Article | SHORT PCB + 13 ITEMS | SHIPPED 10/21
105546 | 1582 | 200 | 2021-10-21 | 5 | 2021-10-14 | 2021-10-21 |  | X | 14 | 2 | 11 | 0 | 1 | 1T |  | KIT CLEAR 10/14 | SHIPPED 10/21
104266 | 1889.5 | 5 | 2021-10-15 | 5 | 2021-10-14 | 2021-10-21 |  | X | 155 | 26 | 36 | 1 | 1 | 1B/1T |  | KIT CLEAR 10/14 | SHIPPED 10/21
104925 | 2038.32 | 23 | 2021-10-13 | 15 | 2021-09-30 | 2021-10-21 |  | X | 161 | 31 | 8 | 1 | 1 | 1B/1T | SS/Excel in kit box | KIT CLEAR 9/30 | SHIPPED 10/21
105331 | 1400 | 25 | 2021-10-20 | 10 | N/C | 10/25* |  | X | 2 | 2 | 1 | 1 | 0 | 1B | ROWC B103488 | KIT CLEAR 10/13 | SHIPPED 10/20
105332 | 1642.5 | 25 | 2021-10-20 | 10 | N/C | 10/25* |  | X | 3 | 3 | 1 | 1 | 0 | 1B | ROWC B103489 | KIT CLEAR 10/13 | SHIPPED 10/20
105787 | 4156.8 | 20 | 2021-10-14 | 3 | N/C | 10/20* |  | X | 282 | 19 | 77 | 1 | 1 | 2B/1T |  | KIT CLEAR 10/15 | SHIPPED 10/20
105641 | 3028 | 10 | 2021-10-15 | 5 | 2021-10-13 | 2021-10-20 |  | X | 349 | 53 | 83 | 1 | 1 | 1B/2T |  | KIT CLEAR 10/13 | SHIPPED 10/20
105377 | 7091.25 | 15 | 2021-10-06 | 10 | 2021-10-06 | 2021-10-20 |  | X | 0 | 154 | 0 | 0 | 0 | 0 | TH only | KIT CLEAR 10/6 | SHIPPED 10/20
105242 | 2358 | 200 | 2021-10-27 | 15 | 2021-10-06 | 2021-10-27 |  | X | 37 | 2 | 18 | 0 | 1 | 1T | RONC B94543 | KIT CLEAR 10/6 | SHIPPED 10/19
100616 | 0 | 4FA/210 | 2021-10-15 | 10 | 2021-10-06 | 2021-10-20 |  | X | 26 | 0 | 7 | 1 | 1 | 1B/1T |  | SHORT 1 ITEM | SHIPPED 10/19
105374 | 1610 | 5 | 2021-10-06 | 10 | 2021-10-06 | 2021-10-20 |  | X | 0 | 90 | 0 | 0 | 0 | 0 | TH only | KIT CLEAR 10/6 | SHIPPED 10/19
105375 | 5535.75 | 15 | 2021-10-07 | 10 | 2021-10-06 | 2021-10-20 |  | X | 0 | 121 | 0 | 0 | 0 | 0 | TH only | KIT CLEAR 10/6 | SHIPPED 10/19
105769 | 3050.4 | 12 | 2021-10-18 | 3 | 2021-10-14 | 2021-10-19 |  | X | 121 | 27 | 51 | 1 | 1 | 1B/1T | SS/Excel in kit box | KIT CLEAR 10/14 | SHIPPED 10/18
105373 | 9272 | 20 | 2021-10-04 | 10 | 2021-10-04 | 2021-10-18 |  | X | 0 | 151 | 0 | 0 | 0 | 0 | TH only | KIT CLEAR 10/4 | SHIPPED 10/18
105599 | 3732.6 | 20 | 2021-10-13 | 5 | 2021-10-08 | 2021-10-15 |  | X | 450 | 1 | 97 | 1 | 1 | 1B/1T | SS/Excel in kit box | KIT CLEAR 10/8 | SHIPPED 10/15
102813 | 4016 | 25 | 2021-09-08 | 5 | 2021-10-08 | 2021-10-15 |  | X | 410 | 21 | 78 | 1 | 1 | 1B/1T |  | KIT CLEAR 10/8 | SHIPPED 10/15
100610 | 2536.6 | 4FA | 2021-07-12 | 5 |  | 2021-10-15 |  | X | 3800 | 7 | 244 | 1 | 1 | 2B/3T |  | FA KIT CLEAR 10/4 - SHORT PCB + 2 ITEMS | SHIPPED 10/15
105088 | 1787 | 150 | 2021-10-15 | 10 | 2021-10-01 | 2021-10-15 |  | X | 37 | 0 | 15 | 1 | 1 | 1B/2T | ROWC B103760 | KIT CLEAR 10/1 | SHIPPED 10/15
104931 | 5552.8 | 10/22 | 2021-09-07 | 5 | 2021-10-07 | 2021-10-14 |  | X | 1235 | 14 | 114 | 1 | 1 | 2B/2T |  | 10FA CLEAR - BAL SHORT FAB + 1 ITEM | SHIPPED 10/14
104586 | 251.72 | 173 | 2021-10-08 | 10 | 2021-09-28 | 2021-10-15 |  | X | 3 | 2 | 3 | 1 | 1 | 1B/1T |  | KIT CLEAR 9/28 | SHIPPED 10/14
104859 | 2352 | 50 | 2021-10-15 | 10 | 2021-09-30 | 2021-10-14 |  | X | 106 | 7 | 36 | 0 | 1 | 1T |  | KIT CLEAR 9/30 | SHIPPED 10/14
104573 | 2951.82 | 2FA/4FA/16 | 2021-09-22 | 10 | 2021-09-30 | 2021-10-14 |  | X | 4053 | 5 | 237 | 1 | 1 | 2B/3T |  | KIT CLEAR 9/30 | SHIPPED 10/14
105062 | 3824.7 | 10 | 2021-10-05 | 5 | 2021-10-06 | 2021-10-13 |  | X | 894 | 20 | 106 | 1 | 1 |  |  | KIT CLEAR 10/6 | SHIPPED 10/13
105662 | 2375.65 | 13 | 2021-10-06 | 3 | 2021-10-08 | 2021-10-13 |  | X | 126 | 16 | 56 | 0 | 1 | 1T |  | KIT CLEAR 10/8 | SHIPPED 10/13
104302 | 2269.5 | 10FA/250 | 2021-09-29 | 5 | 2021-10-07 | 2021-10-14 |  | X | 118 | 1 | 55 | 1 | 1 | 1B/1T |  | KIT CLEAR 12/2 | SHIPPED 10/13
104957 | 1428.6 | 50 | 2021-10-11 | 10 | N/C | 2021-10-07 |  | X | 100 | 62 | 11 | 0 | 1 | 1T | ROWC B95996 | KIT CLEAR 9/23 | SHIPPED 10/13
105178 | 1873.2 | 64 | 2021-10-01 | 5 | 2021-10-05 | 2021-10-12 |  | X | 48 | 6 | 20 | 1 | 1 | 1B/1T |  | KIT CLEAR 10/4 | SHIPPED 10/12
105434 | 3132 | 30 | 2021-10-15 | 5 | 2021-10-06 | 2021-10-13 |  | X | 398 | 16 | 99 | 1 | 1 |  |  | KIT CLEAR 10/6 | SHIPPED 10/12
105496 | 1941.9 | 5 | 2021-10-08 | 5 | 2021-10-06 | 2021-10-13 |  | X | 73 | 50 | 20 | 0 | 1 | 1T |  | KIT CLEAR 10/6 | SHIPPED 10/12
105816 | 2018 | 150 | 2021-10-14 | 3 | 2021-10-11 | 2021-10-14 |  | X | 19 | 0 | 15 | 0 | 1 | 1T | SS/Excel in kit box | KIT CLEAR 10/11 | SHIPPED 10/12
104957 | 1428.57 | 50 | 2021-10-11 | 10 | N/C | 2021-10-07 |  | X | 100 | 62 | 11 | 0 | 1 | 1T | ROWC B95996 | KIT CLEAR 9/23 | SHIPPED 10/11
104907 | 5434.75 | 25 | 2021-10-07 | 10 | 2021-09-28 | 2021-10-12 |  | X | 863 | 1 | 182 | 1 | 1 | 2B/2T | SS/Excel in kit box | KIT CLEAR 9/28 | SHIPPED 10/11
104922 | 3631.5 | 50 | 2021-09-17 | 5 | 14/4 | 2021-10-11 |  | X | 307 | 13 | 82 | 1 | 1 | 1B/2T | RONC B100286 | KIT CLEAR 10/4 | SHIPPED 10/11
100605 | 2850 | 8FA/16FA/800 | 2021-09-17 | 7/10/20 | N/C | ??? |  | X | 2881 | 4 | 204 | 1 | 1 | 2B/2T | SS/Excel in kit box | 8FA KIT CLEAR - THE REST SHORT PCB + 5 ITEMS | SHIPPED 10/11
104957 | 2857.14 | 100 | 2021-10-11 | 10 | N/C | 2021-10-07 |  | X | 100 | 62 | 11 | 0 | 1 | 1T | ROWC B95996 | KIT CLEAR 9/23 | SHIPPED 10/8
104521 | 3559.4 | 180 | 2021-10-08 | 15 | 2021-09-28 | 2021-10-19 |  | X | 79 | 2 | 36 | 1 | 1 | 1B/2T |  | KIT CLEAR 9/28 | SHIPPED 10/8
100481 | 1980 | 4 | 2021-09-27 | 10 | N/C | ??? |  | X | 820 | 58 | 73 | 1 | 1 | 1B/2T | ROWC B92410 (Robert) | KIT CLEAR 10/8 | SHIPPED 10/8
105042 | 1725 | 10 |  |  | 2021-09-23 | 2021-10-07 |  | X |  | 180 | [6 empty] | SHIPPED 10/8
105318 | 2731 | 60 |  |  | 2021-09-23 | 2021-10-07 |  | X |  | 248 | [6 empty] | SHIPPED 10/8
103180 | 1672.95 | 19 | 2021-09-01 | 10 | 2021-09-29 | 2021-10-13 |  | X | 226 | 27 | 7 | 0 | 1 | 1T |  | KIT CLEAR 9/16 | SHIPPED 10/7
104722 | 4868 | 200 | 2021-10-04 | 15 | 2021-09-24 | 2021-10-15 |  | X | 89 | 2 | 43 | 1 | 1 | 1B/2T |  | KIT CLEAR 9/24 | SHIPPED 10/6
104372 3rd | 3216.85 | 35 | 2021-08-24 | 10 | N/C | 10/6* |  | X | 489 | 1 | 165 | 1 | 1 | 2B/2T | ROWC 2nd Article | SHORT PCB + 13 ITEMS | SHIPPED 10/6
105270 | 1490 | 25 | 2021-10-05 | 10 | 2021-09-29 | 2021-10-13 |  | X | 18 | 18 | 11 | 0 | 1 | 1T |  | KIT CLEAR 9/29 | SHIPPED 10/6
104419 | 0 | 20FA | 2021-10-18 | 3 | N/C | 2021-10-05 |  | X | 60 | 1 | 30 | 1 | 1 | 1B/1T | SS/Excel in kit box | KIT CLEAR 10/1 | SHIPPED 10/6
105303 | 4818 | 200 | 2021-09-29 | 3 | N/C | 10/1* |  | X | 56 | 3 | 25 | 1 | 1 | 1B/1T |  | KIT CLEAR 10/1 | SHIPPED 10/6
104957 | 1428.6 | 50 | 2021-10-11 | 10 | N/C | 2021-10-07 |  | X | 100 | 62 | 11 | 0 | 1 | 1T | ROWC B95996 | KIT CLEAR 9/23 | SHIPPED 10/5
104372 3rd | 459.55 | 5/250 | 2021-08-24 | 10 | N/C | 10/6* |  | X | 489 | 1 | 165 | 1 | 1 | 2B/2T | ROWC 2nd Article | SHORT PCB + 4 ITEMS | SHIPPED 10/5
105250 | 1013.08 | 62 | 2021-09-27 | 3 | 2021-09-24 | ??? |  | X | 26 | 2 | 14 | 1 | 1 | 1B/1T | SS/Excel in kit box | KIT CLEAR 9/24 | SHIPPED 10/5
105029 | 3472 | 15 | 2021-10-04 | 3 | 2021-09-30 | 2021-10-05 |  | X | 53 | 36 | 18 | 1 | 1 | 1B/1T |  | KIT CLEAR 9/30 | SHIPPED 10/4
104522 | 1066.89 | 11 | 2021-09-27 | 15 | 2021-09-23 | 2021-10-08 |  | X | 234 | 36 | 58 | 1 | 1 | 2B/2T | SS/Excel in kit box | SHORT 5 ITEMS | SHIPPED 10/4
104575 | 2050 | 4FA/20 | 2021-09-22 | 10 | N/C | ??? |  | X | 203 | 1 | 64 | 1 | 1 | 1B/2T |  | SHORT 1 ITEM | SHIPPED 10/4
104574 | 1100.04 | 2FA/10 | 2021-09-16 | 10 | 2021-09-24 | 2021-10-05 |  | X | 64 | 32 | 8 | 1 | 1 | 1B/1T |  | KIT CLEAR 10/20 | SHIPPED 9/30
105319 | 992.5 | 35 |  |  | 2021-09-23 | 2021-10-07 |  | X |  | 35 | [5 empty] | KIT CLEAR 10/1 | SHIPPED 9/30
103695 | 3600 | 1000 | 2021-10-07 | 15 | 2021-09-21 | 2021-10-12 |  | X | 3 | 0 | 3 | 0 | 1 | 1T | RONC B101820 | KIT CLEAR 9/14 | SHIPPED 9/30
105201 | 2417.1 | 30 | 2021-10-07 | 10 | 2021-09-24 | 2021-10-08 |  | X | 175 | 17 | 23 | 0 | 1 | 1T | SS/Excel in kit box | KIT CLEAR 9/24 | SHIPPED 9/30
104576 | 1912 | 2FA/16 | 2021-09-16 | 5 | N/C | ??? |  | X | 710 | 12 | 85 | 1 | 1 | 1B/2T |  | SHORT 1 ITEM | SHIPPED 9/29
105250 | 1029.42 | 63 | 2021-09-27 | 3 | 2021-09-24 | 2021-09-29 |  | X | 26 | 2 | 14 | 1 | 1 | 1B/1T | SS/Excel in kit box | KIT CLEAR 9/24 | SHIPPED 9/29
104221 | 1418.62 | 50 | 2021-09-24 | 5 | 2021-09-28 | 2021-10-05 |  | X | 29 | 4 | 9 | 1 | 0 | 1T |  | SMT CLEAR, SHORT 1 TH ITEM | SHIPPED 9/29
103895 | 2558.9 | 35 | 2021-09-28 | 10 | N/C | ??? |  | X | 166 | 10 | 74 | 1 | 1 | 2B/1T | SS/Excel in kit box | KIT CLEAR 9/28 | SHIPPED 9/29
104308 | 7487.5 | 50 | 2021-08-13 | 5 | 2021-09-22 | 2021-09-29 |  | X | 589 | 19 | 96 | 1 | 1 | 1B/2T |  | KIT CLEAR 9/22 | SHIPPED 9/28
104930 | 3776.4 | 120 | 2021-10-04 | 10 | 2021-09-16 | 2021-09-30 |  | X | 112 | 7 | 41 | 1 | 1 | 1B/1T |  | KIT CLEAR 9/16 | SHIPPED 9/27
105253 | 2202 | 10 | 2021-09-27 | 3 | 2021-09-22 | 2021-09-27 |  | X | 112 | 62 | 47 | 0 | 1 | 1T | SS/Excel in kit box | KIT CLEAR 9/22 | SHIPPED 9/27
105170 | 5805.1 | 35 | 2021-09-20 | 3 | N/C | 2021-09-24 |  | X | 513 | 0 | 117 | 1 | 1 | 2B/2T |  | KIT CLEAR 9/23 | SHIPPED 9/24
105020 | 2940 | 84 |  |  |  | 2021-09-27 | [8 empty] | PAID RWK |  | SHIPPED 9/24
104121 | 4455 | 20 | 2021-08-27 | 10 | 2021-09-22 | 2021-09-29 |  | X | 575 | 34 | 67 | 1 | 1 | 1B/1T |  | KIT CLEAR 9/22 | SHIPPED 9/23
104475 | 7050.2 | 16 | 2021-08-27 | 5 | N/C | 2021-09-23 |  | X | 1738 | 7 | 107 | 1 | 1 | 2B/2T |  | SHORT 10 ITEMS | SHIPPED 9/23
104605 | 1920.75 | 25 | 2021-09-14 | 5 | 2021-09-16 | 2021-09-23 |  | X | 229 | 20 | 83 | 0 | 1 | 2T | ROWC B98026 | KIT CLEAR 9/16 | SHIPPED 9/23
105170 | 1919.3 | 5 | 2021-09-20 | 3 | N/C | 2021-09-23 |  | X | 513 | 0 | 117 | 1 | 1 | 2B/2T |  | SHORT 1 ITEM | SHIPPED 9/23
105039 | 3210 | 4000 | 2021-09-17 | 10 | 2021-09-09 | 2021-09-23 |  | X | 3 | 0 | 3 | 1 | 1 | 1B/1T |  | KIT CLEAR 9/9 | SHIPPED 9/23
105080 | 1627.25 | 3FA/150 | 2021-09-20 | 5 | 2021-09-14 | 2021-09-21 |  | X | 5 | 3 | 4 | 0 | 1 | 1T | SS/Excel in kit box | KIT CLEAR 10/27 | SHIPPED 9/23
104919 | 2420.5 | 3 | 2021-09-21 | 5 | 2021-09-20 | 2021-09-27 |  | X | 700 | 101 | 7 | 1 | 0 | 1B |  | KIT CLEAR 9/20 | SHIPPED 9/22
105117 | 900 | 3 | 2021-09-09 | 3 | N/C | 2021-09-22 |  | X | 357 | 20 | 107 | 1 | 1 | 1B/2T |  | KIT CLEAR 9/21 | SHIPPED 9/22
103628 | 4133.3336 | 8 | [12 empty] | BARE FLEX |  | SHIPPED 9/22
102224 | 6645.2 | 160 | 2021-08-17 | 10 | N/C | 8/20* |  | X | 146 | 5 | 65 | 1 | 1 | 1B/2T |  | KIT CLEAR 9/21 | SHIPPED 9/22
104618 | 2392.76 | 3FA/42 | 2021-09-16 | 5/10 | 2021-09-16 | 2021-09-23 |  | X | 546 | 12 | 95 | 1 | 1 | 1B/1T | SS/Excel in kit box | KIT CLEAR 9/22 | SHIPPED 9/22
104615 | 4027.5 | 3FA/42 | 2021-09-21 | 5 | N/C | 9/20* |  | X | 267 | 11 | 75 | 1 | 1 | 1B/2T | SS/Excel in kit box | KIT CLEAR 9/22 | SHIPPED 9/22
104766 | 1050 | 2 | 2021-09-20 | 5 | 2021-09-15 | 2021-09-22 |  | X | 613 | 9 | 128 | 1 | 1 | 1B/2T | SS/Excel in kit box | KIT CLEAR 9/15 | SHIPPED 9/21
102530 | 3200 | 10 | 2021-09-16 | 5 | 2021-09-16 | 2021-09-22 |  | X | 243 | 9 | 72 | 1 | 1 | 1B/1T | SS/Excel in kit box | KIT CLEAR 9/17 | SHIPPED 9/21
104372 2nd Article | 0 | 2/250 | 2021-08-24 | 3 | N/C | 2021-09-21 |  | X | 526 | 1 | 167 | 1 | 1 | 2B/2T | SS/Excel in kit box |  | SHIPPED 9/21
104432 | 1480 | 125 | 2021-09-14 | 10 | N/C | 9/20* |  | X | 34 | 0 | 11 | 0 | 1 | 1T |  | KIT CLEAR 10/27 | SHIPPED 9/20
99596 | 1125 | 283 | 2021-09-03 | 20 | 2021-08-04 | 2021-09-01 |  | X | 6 | 0 | 6 | 0 | 1 | 1T |  | KIT CLEAR 8/4 | SHIPPED 9/20
99600 | 2625 | 283 | 2021-07-14 | 10 | 2021-08-09 | 2021-08-23 |  | X | 43 | 1 | 20 | 1 | 1 | 1B/2T | Updated 8/5 for alternate parts |  | SHIPPED 9/20
104968 | 1572 | 200 | 2021-09-21 | 5 | 2021-09-15 | 2021-09-22 |  | X | 1 | 2 | 1 | 0 | 1 | 1T |  | KIT CLEAR 9/15 | SHIPPED 9/17
103180 | 1837.5 | 1FA/20 | 2021-09-01 | 5/10 | 2021-09-16 | 2021-09-23 |  | X | 226 | 27 | 7 | 0 | 1 | 1T |  | KIT CLEAR 9/16 | SHIPPED 9/17
100617 | 610 | 8FA/202 | 2021-08-19 | 5 | 2021-09-14 | 2021-09-21 |  | X | 376 | 3 | 54 | 1 | 1 | 1B/1T |  | kit clear 1/13 | SHIPPED 9/17
100613 | 185.2 | 4FA/50 | 2021-08-19 | 5 | 2021-09-14 | 2021-09-21 |  | X | 142 | 4 | 39 | 1 | 1 | 1B/1T |  | kit clear 6/14 | SHIPPED 9/17
103363 | 2674.47 | 354 | 2021-07-26 | 10 | N/C | ??? |  | X | 17 | 5 | 11 | 0 | 1 | 2T |  | SMT CLEAR - SHORT 2 (TH) ITEMS | SHIPPED 9/16
99600 | 2625 | 200 | 2021-07-14 | 10 | 2021-08-09 | 2021-08-23 |  | X | 43 | 1 | 20 | 1 | 1 | 1B/2T | Updated 8/5 for alternate parts |  | SHIPPED 9/16
99596 | 1125 | 200 | 2021-09-03 | 20 | 2021-08-04 | 2021-09-01 |  | X | 6 | 0 | 6 | 0 | 1 | 1T |  | KIT CLEAR 8/4 | SHIPPED 9/16
100619 | 1930 | 800 | 2021-08-10 | 20 | 2021-09-02 | 2021-10-04 |  | X | 2 | 0 | 2 | 0 | 1 | 1T |  | DOC REL 7/13 | SHIPPED 9/15
105138 | 2267.4 | 12 | 2021-09-13 | 3 | N/C | 9/15* |  | X | 268 | 37 | 66 | 1 | 1 | 1B/1T | SS/Excel in kit box | KIT CLEAR 9/10 | SHIPPED 9/15
104717 | 5968.7 | 3 | 2021-09-13 | 3 | N/C | 2021-09-15 |  | X | 1572 | 6 | 189 | 1 | 1 | 1B/3T | SS/Excel in kit box | 2 ITEMS NEEDS VERF. | SHIPPED 9/15
104777 | 3721.5 | 25 | 2021-09-01 | 3 | N/C | 2021-09-15 |  | X | 241 | 2 | 75 | 1 | 1 | 1B/1T |  | KIT CLEAR 9/13 | SHIPPED 9/15
104955 | 1200 | 5 | 2021-09-15 | 4 | N/C | 2021-09-15 |  | X | 328 | 8 | 107 | 1 | 1 | 1B/1T | SS/Excel in kit box | KIT CLEAR 9/13 | SHIPPED 9/15
105112 | 1813.78 | 15 | 9/16* | 2 | N/C | ??? |  | X | 81 | 0 | 43 | 1 | 1 | 1B/1T | SS/Excel in kit box | SHORT PCB | SHIPPED 9/15
103377 2nd Article | 5532.6 | 60 | 2021-07-13 | 10 | N/C | 2021-09-20 |  | X | 341 | 8 | 70 | 1 | 1 | 1B/1T | RONC 1st Article | KIT CLEAR 9/3 | SHIPPED 9/13
104662 | 1936.2 | 10FA/100 | 2021-09-01 | 5 | 2021-09-07 | 2021-09-14 |  | X | 167 | 1 | 56 | 1 | 1 | 1B/1T |  | KIT CLEAR 9/13 | SHIPPED 9/13
104781 | 2122.6 | 10 | 2021-10-04 | 20 | N/C | 10/4* |  | X | 237 | 56 | 29 | 1 | 1 | 1B/1T |  | KIT CLEAR 9/7 | SHIPPED 9/10
105020 | 2030 | 58 | [12 empty] | PAID RWK |  | SHIPPED 9/10
104704 | 3588.75 | 5 | 2021-08-26 | 5 | N/C | ??? |  | X | 790 | 8 | 127 | 1 | 1 | 1B/2T |  | KIT CLEAR 9/3 | SHIPPED 9/10
104648 | 1460 | 300 | 2021-09-15 | 10 | 2021-09-01 | 2021-09-16 |  | X | 0 | 4 | 0 | 0 | 0 | 0 | TH only | KIT CLEAR 9/1 | SHIPPED 9/8
102356 | 438.4 | 27 | 2021-06-15 | 5 | N/C | ??? |  | X | 516 | 1 | 95 | 1 | 1 | 1B/2T | SHIPPED 4 FA 7/12 | SHORT FABS | SHIPPED 9/7
104504 | 8221.5 | 25 | 2021-09-09 | 10 | 2021-12-09 | 2021-12-23 |  | X | 522 | 0 | 124 | 1 | 1 | 2B/2T | ROWC B102745 | kit clear 12/9 | SHIPPED 9/3
104300 | 12310 | 1500 | 2021-09-20 | 15 | 2021-08-23 | 2021-09-14 | #VALUE! | X | 21 | 3 | 17 | 0 | 1 | 2T |  | KIT CLEAR 8/23 | SHIPPED 9/3
104189 | 3223 | 5 | 2021-08-19 | 3 | N/C | ??? |  | X | 673 | 55 | 128 | 1 | 1 | 1B/2T |  | KIT CLEAR 9/2 | SHIPPED 9/3
104254 | 1750 | 10 | 2021-09-15 | 15 | N/C | ??? |  | X | 682 | 117 | 57 | 0 | 1 | 2T | ROWC B103418 | KIT CLEAR 9/2 | SHIPPED 9/3
104582 | 3010.15 | 5 | 2021-09-02 | 5 | 2021-08-30 | 2021-09-07 |  | X | 877 | 0 | 133 | 1 | 1 | 2B/2T | SS/Excel in kit box | KIT CLEAR 8/30 | SHIPPED 9/3
102493 | 4365 | 5 | 2021-07-02 | 5 | N/C | ??? |  | X | 865 | 8 | 172 | 1 | 1 | 2B/2T | ROWC B95703 | KIt CLEAR 9/2 | SHIPPED 9/2
104703 | 1582 | 200 | 2021-09-07 | 5 | 2021-08-27 | 2021-09-03 |  | X | 13 | 0 | 8 | 1 | 1 | 1B/1T |  |  | SHIPPED 9/2
103435 | 521.95 | 1 | 2021-08-26 | 10 | N/C | ??? |  | X | 256 | 80 | 5 | 1 | 1 | 1B/1T |  | SHORT PCB | SHIPPED 9/2
104371 | 1069.2 | 55 | 2021-09-14 | 5 | 2021-08-25 | 2021-09-01 |  | X | 13 | 6 | 12 | 1 | 1 | 1B/1T | ROWC B103512 | KIT CLEAR 8/25 | SHIPPED 9/1
104649 | 1480 | 50 | 2021-09-15 | 10 | 2021-08-30 | 2021-09-14 |  | X | 12 | 23 | 3 | 0 | 1 | 1T |  | KIT CLEAR 8/30 | SHIPPED 9/1
103416 | 2657.51 | 3 | 2021-07-30 | 7 | 2021-08-26 | 2021-09-07 |  | X | 1166 | 0 | 67 | 1 | 1 | 1B/1T |  |  | SHIPPED 8/31
104272 | 4499.2 | 76 | 2021-08-26 | 10 | 2021-08-23 | 2021-09-07 |  | X | 148 | 9 | 59 | 1 | 1 | 1B/1T | ROWC B103881 (Robert) | KIT CLEAR 8/23 | SHIPPED 8/31
104253 | 6348 | 200 | 2021-08-13 | 5 | N/C | ??? |  | X | 129 | 0 | 54 | 0 | 1 | 2T | ROWC B100569 | KIT CLEAR 8/25 | SHIPPED 8/31
104705 | 1572 | 200 | 2021-09-01 | 5 | 2021-08-24 | 2021-08-31 |  | X | 0 | 3 | 0 | 0 | 0 | 0 | TH only | KIT CLEAR 8/24 | SHIPPED 8/30
103489 | 2707.5 | 30 | 2021-07-19 | 5 | N/C | 2021-08-30 |  | X | 3 | 0 | 1 | 1 | 0 | 1B | ONE DAY TURN | SHORT PCB | SHIPPED 8/30
101525 | 3484.64 | 68 | 2021-09-03 | 20 | 2021-08-11 | 2021-09-09 |  | X | 94 | 0 | 49 | 1 | 1 | 1B/1T |  |  | SHIPPED 8/30
102333 | 6853.7 | 30 | 2021-05-24 | 5 | N/C | ??? |  | X | 861 | 11 | 148 | 1 | 1 | 2B/2T | 7/20 - AOI | KIT CLEAR 9/9 | SHIPPED 8/30
104211 | 4498.56 | 99 | 2021-08-18 | 5 | 2021-08-23 | 2021-08-31 |  | X | 175 | 9 | 49 | 0 | 1 | 1T | SHIPPED 1 PC FA 8/18 |  | SHIPPED 8/30
104778 | 1582.5 | 50 | 2021-08-31 | 3 | 2021-08-26 | 2021-08-31 |  | X | 21 | 3 | 17 | 0 | 1 | 2T | ROWC B104300 (Robert) |  | SHIPPED 8/30
104341 | 3808.9 | 70 | 2021-08-19 | 5 | 2021-08-23 | 2021-08-30 |  | X | 166 | 9 | 48 | 1 | 1 | 1B/1T |  |  | SHIPPED 8/27
101523 | 19494.25 | 415 | 2021-09-02 | 20 | 2021-08-11 | 2021-09-09 |  | X | 188 | 0 | 60 | 1 | 1 | 2B/2T |  |  | SHIPPED 8/27
103819 | 1574 | 300 | 2021-08-02 | 5 | 2021-08-23 | 2021-08-30 |  | X | 2 | 0 | 2 | 0 | 1 | 1T |  | KIT CLEAR 8/23 | SHIPPED 8/27
103877 | 2221 | 2FA/15 | 2021-08-19 | 3 | N/C | 8/26* |  | X | 297 | 4 | 162 | 1 | 1 | 1B/2T |  | KI CLEAR 8/23 | SHIPPED 8/26
103489 | 902.5 | 10 | 2021-07-19 | 5 | N/C | 2021-08-19 |  | X | 3 | 0 | 1 | 1 | 0 | 1B |  | SHORT PCB | SHIPPED 8/25
102940 | 3041.9 | 6 | 2021-08-19 | 10 | N/C | 9/8* |  | X | 177 | 48 | 42 | 1 | 1 | 1B/1T |  | SHORT 1 ITEM | SHIPPED 8/25
104412 | 1350 | 75 | 2021-09-06 | 10 | 2021-08-24 | 2021-09-08 |  | X | 0 | 1 | 0 | 0 | 0 | 0 | TH only | KIT CLEAR 8/24 | SHIPPED 8/25
103697 | 1008 | 3 | 2021-09-02 | 10 | 2021-08-19 | 2021-09-02 |  | X | 24 | 5 | 8 | 0 | 1 | 1T |  | KIT CLEAR 8/19 | SHIPPED 8/25
104444 | 2068.4 | 20 | 2021-08-26 | 5 | N/C | ??? |  | X | 121 | 27 | 52 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/24 | SHIPPED 8/25
103435 | 1565.85 | 3 | 2021-08-26 | 10 | N/C | ??? |  | X | 256 | 80 | 5 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/31 | SHIPPED 8/25
103605 | 3756.99 | 11 | 2021-08-23 | 10 | 2021-08-24 | 2021-09-07 |  | X | 341 | 31 | 110 | 0 | 1 | 2T |  | KIT CLEAR 8/24 | SHIPPED 8/24
103012 | 2427.75 | 249 | 2021-07-13 | 3 | 2021-08-12 | 2021-08-26 |  | X | 14 | 5 | 13 | 1 | 1 | 1B/1T |  |  | SHIPPED 8/24
103946 | 2463 | 3 | 2021-09-02 | 10 | 2021-08-18 | 2021-09-01 |  | X | 98 | 50 | 9 | 1 | 1 | 1B/1T |  |  | SHIPPED 8/24
104372 | 2675 | 2FA/252 | 2021-08-24 | 3 | N/C | ??? |  | X | 526 | 1 | 167 | 1 | 1 | 2B/2T |  | SHORT PCB + 7 ITEMS | SHIPPED 8/24
99600 | 5.25 | 1 | 2021-07-14 | 10 | 2021-08-09 | 2021-08-23 |  | X | 43 | 1 | 20 | 1 | 1 | 1B/2T | Updated 8/5 for alternate parts |  | SHIPPED 8/24
99596 | 1125 | 500 | 2021-09-03 | 20 | 2021-08-04 | 2021-09-01 |  | X | 6 | 0 | 6 | 0 | 1 | 1T |  | KIT CLEAR 8/4 | SHIPPED 8/24
102526 | 5677 | 50 | 2021-06-25 | 5 | 2021-08-16 | 2021-08-23 |  | X | 426 | 5 | 86 | 0 | 1 | 2T |  |  | SHIPPED 8/23
103881 | 4550 | 30 | 2021-08-05 | 3 | 2021-08-17 | 2021-08-20 |  | X | 148 | 9 | 59 | 1 | 1 | 1B/1T |  |  | SHIPPED 8/20
104100 | 2150 | 200 | 2021-09-07 | 15 | 2021-08-16 | 2021-09-07 |  | X | 2 | 0 | 2 | 0 | 1 | 1T |  | KIT CLEAR 8/16 | SHIPPED 8/20
103488 | 3050 | 40 | 2021-07-15 | 5 | N/C | 2021-08-19 |  | X | 2 | 0 | 1 | 1 | 0 | 1B |  | SHORT PCB | SHIPPED 8/19
104211 | 2122.5 | 1FA/100 | 2021-08-18 | 5 | 2021-08-16 | 2021-08-23 |  | X | 175 | 9 | 49 | 0 | 1 | 1T |  |  | SHIPPED 8/18
103984 | 1996.5 | 50 | 2021-08-09 | 10 | 2021-08-16 | 2021-08-30 |  | X | 131 | 13 | 11 | 0 | 1 | 1T | RONC B103542 | KIT CLEAR 8/16 | SHIPPED 8/18
103558 | 2466.86 | 30/175 | 2021-08-26 | 15 | N/C | 2021-08-20 |  | X | 342 | 1 | 93 | 1 | 1 | 2B/2T | *30 PCS CLEAR 8/16 | SHORT 1 ITEM | SHIPPED 8/18
103742 | 2298.5 | 2FA/15 | 2021-08-16 | 5 | 2021-08-13 | 2021-08-20 |  | X | 542 | 28 | 131 | 1 | 1 | 2B/2T |  |  | SHIPPED 8/18
104337 | 2304 | 20 | 2021-08-16 | 5 | 2021-08-13 | 2021-08-20 |  | X | 0 | 30 | 0 | 0 | 0 | 0 | TH only | KIT CLEAR | SHIPPED 8/18
104378 | 2343.75 | 1FA/6 | 2021-08-12 | 5 | N/C | 2021-08-19 |  | X | 673 | 24 | 70 | 1 | 1 | 1B/1T |  |  | SHIPPED 8/18
104335 | 2304 | 20 | 2021-08-16 | 5 | 2021-08-12 | 2021-08-19 |  | X | 0 | 42 | 0 | 0 | 0 | 0 | TH only | KIT CLEAR | SHIPPED 8/17
103554 | 4556.5 | 5 | 2021-07-30 | 5 | 2021-08-09 | 2021-08-18 |  | X | 1529 | 4 | 146 | 1 | 1 | 1B/2T | *BGA REMOVED FROM ANOTHER BOARD |  | SHIPPED 8/17
103780 | 3391.25 | 5 | 2021-07-27 | 5 | 2021-08-10 | 2021-08-17 |  | X | 848 | 14 | 109 | 1 | 1 | 1B/2T |  |  | SHIPPED 8/17
104330 | 1801.5 | 15 | 2021-08-24 | 5 | N/C | ??? |  | X | 16 | 6 | 11 | 1 | 0 | 1B |  | KIT CLEAR 8/16 | SHIPPED 8/16
103309 | 1250 | 50 | 2021-08-23 | 15 | N/C | 2021-08-23 |  | X | 0 | 1 | 0 | 0 | 0 | 0 | TH only | KIT CLEAR 8/2 | SHIPPED 8/16
104181 | 5849.7 | 30 | 2021-08-05 | 5 | 2021-08-10 | 2021-08-17 |  | X | 758 | 0 | 59 | 1 | 1 | 2B/1T |  |  | SHIPPED 8/16
103983 | 1181.25 | 25 | 2021-09-10 | 5 | 2021-08-09 | 2021-08-16 |  | X | 0 | 21 | 0 | 0 | 0 | 0 | TH only/ROWC B103546 | KIT CLEAR | SHIPPED 8/16
103760 | 2672 | 200 | 2021-08-10 | 5 | 2021-08-11 | 2021-08-18 |  | X | 37 | 0 | 15 | 1 | 1 | 1B/2T |  | SHORT U2/BOT SIDE | SHIPPED 8/13
104245 | 2358.5 | 3 | 2021-08-10 | 3 | 2021-08-11 | 2021-08-16 |  | X | 21 | 75 | 8 | 1 | 1 | 1B/1T |  | SHORT 1 ITEM | SHIPPED 8/13
103908 | 2700 | 200 | 2021-08-16 | 10 | N/C | 2021-08-16 |  | X | 23 | 6 | 9 | 0 | 1 | 1T |  | KIT CLEAR 8/3 | SHIPPED 8/13
103754 | 7692.84 | 53 | 2021-08-10 | 5 | N/C | 2021-08-13 |  | X | 450 | 0 | 95 | 1 | 1 | 2B/1T |  | KIT CLEAR 8/6 | SHIPPED 8/13
103557 | 4381.6 | 10 | 2021-07-27 | 10 | 2021-08-05 | 2021-08-19 |  | X | 1110 | 3 | 101 | 1 | 1 | 1B/2T |  | KIT CLEAR 8/5 | SHIPPED 8/12
103546 | 1050 | 25 | 2021-08-17 | 15 | N/C | 8/17* |  | X | 0 | 21 | 0 | 0 | 0 | 0 | TH only |  | SHIPPED 8/12
103822 | 3392.8 | 4 | 2021-08-06 | 5 | 2021-08-02 | 2021-08-09 |  | X | 605 | 65 | 139 | 1 | 1 | 2B/2T |  | SHORT 1 ITEM | SHIPPED 8/12
103962 | 3898.6 | 60 | 2021-08-03 | 5 | 2021-08-04 | 2021-08-11 |  | X | 168 | 25 | 33 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/4 | SHIPPED 8/11
103581 | 3211.6 | 30 | 2021-07-21 | 5 | 2021-08-04 | 2021-08-11 |  | X | 241 | 27 | 50 | 1 | 1 | 1B/1T |  | KIT CLEAR 8/5 | SHIPPED 8/11
103274 | 4000 | 6 | 2021-07-08 | 5 | 2021-08-11 | 2021-08-18 |  | X | 603 | 2 | 131 | 1 | 1 | 1B/2T |  | SHORT 1 ITEM | SHIPPED 8/11
103690 | 2541.75 | 5 | 2021-08-10 | 5 | N/C | ??? |  | X | 410 | 57 | 90 | 1 | 1 | 2B/1T |  | SHORT 2 ITEMS | SHIPPED 8/11
104145 | 3149 | 50 | 2021-08-09 | 5 | 2021-08-10 | 2021-08-16 |  | X | 184 | 0 | 89 | 1 | 1 | 1B/2T | ROWC B103728 - SS/Excel in kit box | SHORT 5 ITEMS | SHIPPED 8/10
103365 | 2491.95 | 35 | 2021-07-08 | 5 | N/C | ??? |  | X | 109 | 18 | 61 | 1 | 1 | 1B/1T | ROWC B99925 | KIT CLEAR 8/6 | SHIPPED 8/10
103843 | 1571 | 525 | 2021-08-06 | 5 | N/C | 2021-08-10 |  | X | 6 | 0 | 2 | 0 | 1 | 1T |  | KIT CLEAR 8/3 | SHIPPED 8/9
103338 | 5750 | 200 | 2021-08-12 | 10 | 2021-07-30 | 2021-08-13 |  | X | 99 | 12 | 37 | 0 | 1 | 2T |  | KIT CLEAR 7/30 | SHIPPED 8/9
103310 | 2100 | 75 | 2021-08-16 | 10 | N/C | 2021-08-16 |  | X | 155 | 1 | 50 | 0 | 1 | 2T |  | KIT CLEAR 8/3 | SHIPPED 8/9
103728 | 3145 | 50 | 2021-07-21 | 5 | N/C | 2021-08-10 |  | X | 184 | 0 | 89 | 1 | 1 | 1B/2T |  | KIT CLEAR 8/4 - 2 ITEMS NEED ATTR. | SHIPPED 8/9
103441 | 4014.4 | 20 | 2021-07-29 | 5 | 2021-08-02 | 2021-08-09 |  | X | 449 | 28 | 114 | 1 | 1 | 1B/2T | 7/26 - BOT SIDE DONE | KIT CLEAR 8/2 | SHIPPED 8/9
103542 | 2582 | 33 | 8/17* | 15 | 2021-07-27 | 2021-08-17 |  | X | 131 | 13 | 11 | 0 | 1 | 1T | *33 PLATING ISSUE |  | SHIPPED 8/6
104116 | 5170 | 400 | 2021-08-05 | 3 | 2021-08-03 | 2021-08-06 |  | X | 19 | 0 | 17 | 0 | 1 | 2T |  | KIT CLEAR 8/3 | SHIPPED 8/6
103603 | 5568.5 | 150 | 2021-07-23 | 5 | 2021-08-04 | 2021-08-11 |  | X | 150 | 2 | 49 | 0 | 1 | 2T |  | KIT CLEAR 8/4 | SHIPPED 8/5
104156 | 3513.6 | 4 | 2021-08-09 | 3 | N/C | 2021-08-06 |  | X | 869 | 26 | 101 | 1 | 1 | 1B/2T | SS/Excel in kit box | KIT CLEAR 8/3 | SHIPPED 8/5
103909 | 2940 | 200 | 2021-08-16 | 10 | 2021-07-30 | 2021-08-13 |  | X | 24 | 0 | 6 | 0 | 1 | 1T |  | KIT CLEAR 7/30 | SHIPPED 8/4
103512 | 1593 | 100 | 2021-08-05 | 5 | 2021-07-30 | 2021-08-04 |  | X | 13 | 6 | 12 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/28 | SHIPPED 8/4
102284 | 3470 | 1000 | 2021-06-16 | 10 | 2021-07-21 | 2021-08-04 |  | X | 4 | 4 | 3 | 0 | 1 | 1T | ROWC B96986 | KIT CLEAR 7/21 | SHIPPED 8/4
104185 | 660 | 20 | 2021-08-03 | 3 | 2021-08-04 |  |  | X | [6 empty] | REWORK | NO DOC. | SHIPPED 8/4
103559 | 4488 | 100 | 2021-08-04 | 10 | 2021-07-27 | 2021-08-10 |  | X | 374 | 0 | 81 | 1 | 1 | 2B/2T | ROWC B100172 | KIT CLEAR 7/27 | SHIPPED 8/3
102806 | 5850 | 1000 | 2021-07-26 | 15 | 2021-07-15 | 2021-08-05 |  | X | 29 | 1 | 19 | 0 | 1 | 1T | 7/20 - BACK | SHORT 1 ITEM | SHIPPED 8/3
103755 | 3460 | 100 | 2021-08-02 | 3 | 2021-07-29 | 2021-08-03 |  | X | 24 | 5 | 12 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/29 | SHIPPED 8/2
103726 | 1582.5 | 150 | 2021-08-03 | 5 | 2021-07-27 | 2021-08-03 |  | X | 7 | 3 | 4 | 0 | 1 | 1T |  | KIT CLEAR 7/30 | SHIPPED 8/2
103509 | 3635 | 100 | 2021-08-05 | 5 | 2021-07-27 | 2021-08-03 |  | X | 102 | 7 | 34 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/27 | SHIPPED 8/2
103727 | 6303 | 20 | 2021-07-28 | 5 | 2021-07-28 | 2021-08-04 |  | X | 830 | 26 | 105 | 0 | 1 | 2T | SS/Excel in kit box | KIT CLEAR 7/28 | SHIPPED 7/30
101909 | 7349.39 | 47 | 2021-05-17 | 5 | 2021-07-23 | 2021-07-30 |  | X | 531 | 0 | 29 | 1 | 1 | 1B/1T | 7/21 - 2ND ART REL | KIT CLEAR 7/23 | SHIPPED 7/30
103418 | 1750 | 10 | 2021-08-02 | 10 | 2021-07-26 | 2021-08-09 |  | X | 682 | 117 | 57 | 0 | 1 | 2T | ROWC B99062 | KIT CLEAR 7/26 | SHIPPED 7/29
102914 | 4820 | 100 | 2021-07-19 | 5 | 2021-07-23 | 2021-07-30 |  | X | 116 | 7 | 60 | 1 | 1 | 1B/2T |  | KIT CLEAR 7/23 | SHIPPED 7/29
103345 | 4276 | 5 | 2021-08-12 | 10 | 2021-07-22 | 2021-08-05 |  | X | 879 | 1 | 35 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/22 | SHIPPED 7/28
102725 | 21592 | 797 | 2021-06-29 | 15 | 2021-07-15 | 2021-08-05 |  | X | 122 | 1 | 48 | 1 | 1 | 2B/2T | 7/20 - AOI | *SHORT U3 | SHIPPED 7/28
103539 | 5262.6 | 130 | 2021-07-23 | 5 | 2021-07-27 | 2021-08-03 |  | X | 179 | 0 | 55 | 1 | 1 | 2B/2T |  | KIT CLEAR: 7/27 | SHIPPED 7/28
102550 | 2654 | 50 | 2021-07-21 | 10 | 2021-07-20 | 2021-08-03 |  | X | 225 | 17 | 53 | 1 | 1 | 1B/1T | 7/20 - AOI | SHORT 3 ITEMS | SHIPPED 7/26
103019 | 3932 | 4 | 2021-07-09 | 5 | 2021-07-19 | 2021-07-26 |  | X | 615 | 113 | 147 | 1 | 1 | 2B/2T | 7/20 - AOI | KIT CLEAR 7/19 | SHIPPED 7/26
103276 | 1510 | 50 | 2021-08-03 | 10 | 2021-07-20 | 2021-08-03 |  | X | 44 | 18 | 16 | 0 | 1 | 1T | 7/21 - AOI | KIT CLEAR 7/20 | SHIPPED 7/22
103417 | 1770.3 | 8 | 2021-07-19 | 5 | 2021-07-16 | 2021-07-23 |  | X | 0 | 281 | 0 | 0 | 0 | 0 | TH only | KIT CLEAR 7/16 | SHIPPED 7/21
103593 | 1503 | 12 | [14 empty] | SHIPPED 7/20
103315 | 2480 | 25 | 2021-07-13 | 10 | N/C | ??? |  | X | 109 | 22 | 38 | 1 | 1 | 1B/1T | 7/16 - AOI | KIT CLEAR 7/20 | SHIPPED 7/20
103297 | 7387.2 | 110 | 2021-07-09 | 5 | 2021-07-15 | 2021-07-22 |  | X | 201 | 8 | 70 | 0 | 1 | 2T |  |  | SHIPPED 7/20
103295 | 5968.8 | 4 | 2021-07-14 | 5 | 2021-07-15 | 2021-07-22 |  | X | 1423 | 18 | 234 | 1 | 1 | 2B/3T | 7/16 - BACK |  | SHIPPED 7/19
102471 | 2917.5 | 15 | 2021-07-26 | 10 | N/C | 2021-07-28 |  | X | 548 | 0 | 46 | 1 | 1 | 1B/1T | 7/16 - AOI | KIT CLEAR BUT NEED ATTRITION FOR 10 ITEMS 7/14 | SHIPPED 7/19
103497 | 3185 | 20 | 2021-07-15 | 5 | 2021-07-12 | 2021-07-19 |  | X | 344 | 48 | 75 | 1 | 1 | 1B/1T |  |  | SHIPPED 7/16
103124 | 2791.5 | 10 | 2021-07-28 | 10 | 2021-07-13 | 2021-07-27 |  | X | 279 | 37 | 64 | 1 | 1 | 1B/1T | 7/15 - BACK |  | SHIPPED 7/16
103363 | 347.53 | 46/400 | 2021-07-26 | 10 | N/C | ??? |  | X | 17 | 5 | 11 | 0 | 1 | 2T |  | KIT CLEAR 9/15 | SHIPPED 7/16
101761 | 2511.6 | 70/220 | 2021-06-21 | 5 | N/C | 7/16* |  | X | 146 | 27 | 66 | 1 | 1 | 2B/2T | FSU | SHORT U23
103214 | 2032.2 | 12 | 2021-07-19 | 5 | 2021-07-12 | 2021-07-19 |  | X | 102 | 12 | 7 | 0 | 1 | 1T
103028 | 3932.4 | 16 | 2021-07-08 | 5 | 2021-07-12 | 2021-07-19 |  | X | 288 | 38 | 98 | 1 | 1 | 1B/2T | 6/30 - BOT SIDE | KIT CLEAR 7/12
103173 | 8890.2 | 12 | 2021-06-30 | 3 | N/C | ??? |  | X | 905 | 53 | 165 | 1 | 1 | 1B/3T | 6/30 - BOT DONE | KIT CLEAR 7/6 | *RUN BOT SIDE ONLY
98989 | 2504.96 | 28 | 2021-01-25 | 10 | 2021-07-09 | 2021-07-23 |  | X | 18 | 36 | 6 | 0 | 1 | 1T |  |  | SHIPPED 7/15
102725 | 1650 | 3/800 | 2021-06-29 | 5 | N/C | ??? |  | X | 122 | 1 | 48 | 1 | 1 | 2B/2T | 6/24 - BOT SIDE | *SHORT U3 | SHIPPED 7/15
102764 | 22650 | 200 | 2021-06-22 | 5 | N/C | 7/15* |  | X | 265 | 4 | 43 | 1 | 1 | 1B/2T | FSU | KIT CLEAR 7/9 | SHIPPED 7/14
102270 | 3977.5 | 5 | 2021-06-10 | 5 | 2021-07-07 | 2021-07-14 |  | X | 314 | 50 | 66 | 1 | 1 | 1B/1T | RTR | KIT CLEAR 7/7 | SHIPPED 7/12
103468 | 2400 | 24 | 2021-07-08 | 3 | 2021-07-08 | 2021-07-13 |  | X | 93 | 5 | 39 | 0 | 1 | 1T | 7/9 - TOP SIDE |  | SHIPPED 7/12
103057 | 5200.5 | 25 | 2021-06-21 | 2 | 2021-07-08 | 2021-07-12 |  | X | 488 | 1 | 135 | 1 | 1 | 1B/2T | 7/8 - AOI | SHORT PCB (ETA 6/17) + 1 ITEM | SHIPPED 7/12
102356 | 438.4 | 4/31 | 2021-06-15 | 3 | 2021-07-07 | 2021-07-12 |  | X | 516 | 1 | 95 | 1 | 1 | 1B/2T | 7/9 - BOT SIDE |  | SHIPPED 7/12
103377 | 2243.36 | 12/60 | 2021-07-13 | 5 | 2021-07-06 | 2021-07-13 |  | X | 341 | 8 | 70 | 1 | 1 | 1B/1T | 7/8 - AOI | SHORT PCB + 1 ITEM | SHIPPED 7/9
102107-2 | 6084 | 90 | 2021-05-26 | 5 | 2021-07-06 | 2021-07-13 |  | X | 103 | 0 | 50 | 1 | 1 | 1B/2T | 7/8 - AOI |  | SHIPPED 7/9
103012 | 1581 | 1/250 | 2021-07-13 | 3 | 2021-07-07 | 2021-07-12 |  | X | 14 | 5 | 13 | 1 | 1 | 1B/1T |  |  | SHIPPED 7/8
102921 | 2434 | 100 | 2021-07-12 | 10 | 2021-06-30 | 2021-07-14 |  | X | 51 | 8 | 26 | 0 | 1 | 1T | 6/30 - TOP SIDE |  | SHIPPED 7/8
103224 | 2646.5 | 50 | 2021-07-02 | 10 | 2021-06-29 | 2021-07-13 |  | X | 125 | 17 | 6 | 0 | 1 | 1T | 6/30 - AOI |  | SHIPPED 7/8
100351 | 3011.5 | 1 | 2021-05-13 | 10 | N/C | 2021-07-07 |  | X | 93 | 156 | 26 | 1 | 1 | 1B/1T |  | KIT CLEAR 7/6 | SHIPPED 7/8
103096 | 4826.25 | 5 | 2021-06-23 | 2 | N/C |  |  | X | 466 | 43 | 100 | 1 | 1 | 1B/2T |  | KIT CLEAR 7/6 | SHIPPED 7/6
103056 | 2687.2 | 80 | 2021-07-13 | 10 | N/C | 2021-07-08 |  | X | 58 | 19 | 26 | 0 | 1 | 1T | FSU | KIT CLEAR 6/30 | SHIPPED 7/7
102745 | 6788 | 18 | 2021-06-24 | 5 | 2021-06-30 | 2021-07-08 |  | X | 522 | 0 | 124 | 1 | 1 | 2B/2T |  |  | SHIPPED 7/7
102778 | 8709.6 | 60 | 2021-06-11 | 10 | 2021-06-24 | 2021-07-08 |  | X | 642 | 42 | 83 | 1 | 1 | 2B/2T | 6/24 - TOP SIDE | KIT CLEAR 6/25 | SHIPPED 7/7
100989 | 5266 | 18 | 2021-06-23 | 5 | 2021-06-29 | 2021-07-06 |  | X | 939 | 0 | 106 | 1 | 1 | 1B/2T | 6/29 - AOI |  | SHIPPED 7/6
101909 | 2702.5 | 3 (FA) | 2021-05-17 | 5 | 2021-05-28 | 2021-06-05 |  | X | 531 | 0 | 29 | 1 | 1 | 1B/1T | 6/29 - AOI |  | SHIPPED 7/2
103105 | 3051.93 | 21 | 2021-06-25 | 3 | N/C |  |  | X | 157 | 26 | 30 | 0 | 1 | 1T | 6/25 - SHORT | FAV | SHIPPED 7/1
103000 | 4302 | 28 | 2021-06-29 | 3 | 2021-06-30 | 2021-07-01 |  | X | 134 | 26 | 46 | 1 | 1 | 1B/1T | 6/30 - BACK | FAV | SHIPPED 7/1
93544 | 36396.48 | 1600 | 2021-03-19 | 20 | 2021-03-15 | 2021-04-16 |  | X | 239 | 1 | 95 | 1 | 1 |  | 3/19 - TOP SIDE |  | SHIPPED 7/1
103154 | 4455 | 10 | 2021-06-25 | 1 | N/C | 2021-06-25 |  | X | 99 | 31 | 32 | 0 | 1 | 1T | 6/25 - BACK | FAV | SHIPPED 6/28
103105 | 581.32 | 4/25 | 2021-06-25 | 3 | N/C |  |  | X | 157 | 26 | 30 | 0 | 1 | 1T | FACEBOOK/ROYAL | FAV | SHIPPED 6/25
103035 | 2000 | 15 | 2021-06-18 | 5 | 2021-06-22 | 2021-06-29 |  | X | 297 | 4 | 83 | 1 | 1 | 1B/2T | 6/22 - TOP SIDE |  | SHIPPED 6/25
103030 | 4500 | 50 | 2021-06-25 | 5 | 2021-06-22 | 2021-06-29 |  | X | 302 | 2 | 83 | 1 | 1 | 1B/2T | 6/22 BOT SIDE |  | SHIPPED 6/25
103033 | 2000 | 15 | 2021-06-18 | 5 | 2021-06-21 | 2021-06-28 |  | X | 303 | 1 | 84 | 1 | 1 | 1B/2T | 6/21 - AOI |  | SHIPPED 6/25
102703 | 3372.5 | 10 | 2021-06-28 | 10 | 2021-06-22 | 2021-06-29 |  | X | 462 | 1 | 113 | 1 | 1 | 1B/2T |  |  | SHIPPED 6/23
102999 | 3561.2 | 20 | 2021-06-23 | 3 | 2021-06-21 | 2021-06-24 |  | X | 237 | 2 | 50 | 1 | 1 | 1B/1T | SHORT FAB 6DUE 6/21
102745 | 400 | 2/20 | 2021-06-24 | 5 | 2021-06-17 | 2021-06-24 |  | X | 522 | 0 | 124 | 1 | 1 | 2B/2T | 6/17 - AOI
102836 | 4350 | 37 |  | 10 | 2021-06-17 | 2021-06-24 |  | X | [6 empty] | 6/22 - REMOVE & RBL | *REPORTS TO B102778
101729 | 157.14 | 1 | 2021-05-18 | 10 | 2021-06-08 | 2021-06-22 |  | X | 47 | 67 | 15 | 1 | 1 | 1B/1T | 6/9 - AOI |  | DAMAGED PART
101729 | 2985.66 | 19 | 2021-05-18 | 10 | 2021-06-08 | 2021-06-22 |  | X | 47 | 67 | 15 | 1 | 1 | 1B/1T | 6/9 - AOI |  | SHIPPED 6/22
102542 | 11008.75 | 25 | 2021-06-22 | 10 | 2021-06-10 | 6/22* |  | X | 1151 | 0 | 162 | 1 | 1 | 2B/2T | 6/10 - AOI | KIT CLEAR | SHIPPED 6/22
101319 | 2983.75 | 5 | 2021-06-11 | 10 | 2021-06-14 | 2021-06-28 |  | X | 16 | 3 | 15 | 1 | 1 | 1B/1T |  | SHORT PCB | SHIPPED 6/21
103057 | 2673 | 5FA/30 | 2021-06-21 | 2 | N/C | 6/21* |  | X | 488 | 1 | 135 | 1 | 1 | 1B/2T | 6/18 - AOI | SHORT PCB (ETA 6/17) + 1 ITEM | SHIPPED 6/21
102205 | 7063.75 | 25 | 2021-05-24 | 5 | 2021-06-14 | 2021-06-18 |  | X | 669 | 0 | 139 | 1 | 1 | 2B/2T | *DO NOT LOSE ITEM 97/ALSO USED ON B102542 | FAV | SHIPPED 6/18
102614 | 3000 | 10 | 2021-06-18 | 10 | 2021-06-09 | 6/22* |  | X | 469 | 42 | 90 | 1 | 1 | 2B/1T | 6/9 - AOI |  | SHIPPED 6/18
102583 | 2569 | 100 | 2021-06-11 | 10 | 2021-06-04 | 2021-06-18 |  | X | 42 | 16 | 25 | 1 | 0 | 1B | 6/10 - AOI |  | SHIPPED 6/18
102478 | 5485.76 | 32 | 2021-06-15 | 2 | 2021-06-15 | 2021-06-17 |  | X | 220 | 43 | 63 | 1 | 1 | 1B/2T |  |  | SHIPPED 6/17
102582 | 3142 | 100 | 2021-06-11 | 10 | 2021-06-03 | 2021-06-17 |  | X | 97 | 8 | 32 | 1 | 1 | 1B/2T | 6/9 - AOI |  | SHIPPED 6/16
100996 | 1084.48 | 12 | 2021-05-03 | 10 | 2021-06-01 | 2021-06-15 |  | X | 372 | 0 | 94 | 1 | 1 | 2B/2T | 6/4 - AOI | FAV | 5/18 - RAN QTY 63
102528 | 8350.8 | 40 | 2021-06-14 | 5 | 2021-06-09 | 2021-06-16 |  | X | 895 | 5 | 72 | 1 | 1 | 2B/2T | 6/10 - AOI |  | SHIPPED 6/14
102579 | 2680 | 200 | 2021-06-11 | 10 | 2021-06-03 | 2021-06-17 |  | X | 43 | 0 | 27 | 0 | 1 | 2T |  |  | SHIPPED 6/14
102490 | 4010 | 10 | 2021-06-09 | 10 | 2021-06-02 | 2021-06-16 |  | X | 681 | 19 | 154 | 1 | 1 | 1B/3T | FSU |  | SHIPPED 6/14
101820 | 2155 | 500 | 2021-05-20 | 10 | 2021-06-01 | 2021-06-15 |  | X | 3 | 0 | 3 | 0 | 1 | 1T | 6/3 - BACK |  | SHIPPED 6/14
102383 | 3467.5 | 10 | 2021-06-14 | 5 | N/C | 6/15* |  | X | 206 | 3 | 73 | 1 | 1 | 1B/1T | 6/9 - AOI | SHORT 1 ITEM | SHIPPED 6/11
100889 | 1460.72 | 192 | 2021-06-14 | 10 | 2021-05-27 | 2021-06-14 |  | X | 0 | 2 | 0 | 0 | 0 | 0 | TH assembly |  | SHIPPED 6/11
101889 | 4654 | 8 | 2021-06-14 | 10 | 2021-05-27 | 2021-06-14 |  | X | 251 | 139 | 13 | 1 | 1 | 1B/1T | 6/2 - AOI |  | SHIPPED 6/9
102660 | 6386 | 40 | 2021-06-07 | 3 | 2021-06-07 | 2021-06-10 |  | X | 113 | 10 | 33 | 1 | 1 | 1B/1T |  |  | SHIPPED 6/9
99075 | 3905 | 20 | 2021-04-28 | 5 | 2021-06-02 | 2021-06-09 |  | X | 596 | 12 | 75 | 1 | 1 | 1B/2T | 6/4 - TOP SIDE |  | SHIPPED 6/9
102485 | 5989 | 100 | 2021-05-20 | 5 | 2021-06-02 | 2021-06-09 |  | X | 223 | 14 | 50 | 0 | 1 | 2T | 6/4 - TOP SIDE |  | SHIPPED 6/9
102455 | 1479.84 | 52 | 2021-06-11 | 10 | 2021-05-25 | 2021-06-09 |  | X | 0 | 23 | 0 | 0 | 0 | 0 | TH assembly |  | SHIPPED 6/8
102009 | 4742.25 | 1 | 2021-05-07 | 5 | 2021-06-01 | 2021-06-08 |  | X | 1551 | 148 | 57 | 0 | 1 | 1T | 6/2 - AOI |  | SHIPPED 6/8
100327 | 2989 | 98 | 2021-05-13 | 10 | 2021-05-25 | 2021-06-09 |  | X | 59 | 10 | 34 | 1 | 1 | 1B/1T | 6/2 - BACK |  | SHIPPED 6/7
102029 | 5989.6 | 6 | 2021-05-06 | 5 | 2021-06-01 | 2021-06-08 |  | X | 1149 | 91 | 99 | 1 | 1 | 1B/2T | 6/2 - AOI |  | SHIPPED 6/7
102743 | 2062.4 | 40 | 2021-06-04 | 3 | 2021-06-02 | 2021-06-07 |  | X | 31 | 9 | 15 | 0 | 1 | 1T |  |  | SHIPPED 6/7
102626 | 2449.5 | 110 | 2021-06-04 | 5 | 2021-05-28 | 2021-06-07 |  | X | 38 | 6 | 21 | 0 | 1 | 1T | 6/2 - AOI |  | SHIPPED 6/7
102600 | 1200 | 3/30 | 2021-05-28 | 3 | 2021-06-02 | 2021-06-07 |  | X | 357 | 8 | 68 | 1 | 1 | 1B/1T | 6/3 - TOP SIDE | MIS | SHIPPED 6/4
101731 | 1764 | 42 | 2021-05-20 | 5 | 2021-05-28 | 2021-06-07 |  | X | 66 | 26 | 20 | 1 | 1 | 1B/1T | 6/2 - AOI |  | SHIPPED 6/4
102540 | 16545 | 70+70 | 2021-06-01 | 3 | 2021-06-01 | 2021-06-04 |  | X | 20 | 3 | 14 | 1 | 1 | 1B/1T | DLC/SST VERSION |  | SHIPPED 6/4
102523 | 2374.4 | 20 | 2021-06-04 | 5 | 2021-05-27 | 2021-06-04 |  | X | 236 | 40 | 67 | 1 | 1 | 1B/1T |  |  | SHIPPED 6/3
102650 | 4802.5 | 15 | 2021-06-07 | 4 | 2021-05-28 | 2021-06-04 |  | X | 120 | 27 | 52 | 1 | 1 | 1B/1T |  |  | SHIPPED 6/3
102206 | 7611.95 | 23 | 2021-05-17 | 5 | 2021-05-27 | 2021-06-04 |  | X | 776 | 15 | 114 | 1 | 1 | 2B/2T | FAVOR SHIP 6/3 | FAV | SHIPPED 6/3
102107 | 2960 | 10/90 | 2021-05-26 | 5 | 2021-05-24 | 2021-06-02 |  | X | 103 | 0 | 50 | 1 | 1 | 1B/2T | 5/26 - AOI |  | SHIPPED 6/2
102418 | 10080 | 14 | 2021-05-21 | 3 | N/C | 2021-06-02 |  | X | 565 | 1 | 128 | 1 | 1 | 2B/2T | 5/21 - AOI | SHORT 1 ITEM | SHIPPED 6/2
102179 | 8918 | 100 | 2021-05-17 | 10 | 2021-05-19 | 2021-06-03 |  | X | 354 | 0 | 14 | 1 | 1 | 2B/2T |  |  | SHIPPED 6/2
102045 | 5506 | 25 | 2021-05-18 | 5 | 2021-05-21 | 2021-06-03 |  | X | 272 | 81 | 25 | 0 | 1 | 2T | 5/21 - 10 FABS REJECTED |  | SHIPPED 6/2
102221 | 14511.2 | 680 | 2021-06-02 | 15 | 2021-05-12 | 2021-06-02 |  | X | 97 | 0 | 18 | 1 | 1 | 1B/1T | 5/24 - TOP SIDE |  | SHIPPED 6/2
102600 | 1200 | 2/33 | 2021-05-28 | 3 | 2021-05-26 | 2021-06-01 |  | X | 357 | 8 | 68 | 1 | 1 | 1B/1T | 5/26 - BOT SIDE |  | SHIPPED 6/2
101152 | 840 | 6 | 2021-05-19 | 10 | 2021-05-20 | 2021-06-03 |  | X | 487 | 50 | 81 | 1 | 1 |  |  |  | SHIPPED 6/1
101664 | 47750 | 4775 | 2021-05-19 | 7 | N/C | HOLD |  | X | 1 | 3 | 1 | 1 | 0 | 1B | 5/11 - BOT SIDE | SHORT 1 ITEM | SHIPPED 5/28
100811 | 3139.6 | 6 | 2021-05-27 | 10 | 2021-05-18 | 2021-06-02 |  | X | 936 | 8 | 48 | 1 | 1 | 1B/1T | 5/26 - AOI |  | SHIPPED 5/28
102474 | 16545 | 140 | 2021-06-01 | 3 | 2021-05-25 | 2021-05-28 |  | X | 20 | 3 | 14 | 1 | 1 | 1B/1T | 5/26 - BOT SIDE DONE |  | SHIPPED 5/28
102271 | 110.84 | 6 | 2021-05-25 | 3 | 2021-05-21 | 5/26* | HOLD | X | 13 | 0 | 3 | 0 | 1 | 1T |  | KIT CLEAR | SHIPPED 5/28
102271 | 1921.16 | 104/110 | 2021-05-25 | 3 | 2021-05-21 | 2021-05-28 |  | X | 13 | 0 | 3 | 0 | 1 | 1T |  | SHORT 6 FABS | SHIPPED 5/28
102114 | 11364.5 | 85 | 2021-05-27 | 20 | 2021-05-11 | 2021-05-28 |  | X | 562 | 18 | 120 | 1 | 1 | 2B/2T | 5/24 - BACK |  | SHIPPED 5/27
102418 | 5040 | 7 | 2021-05-21 | 3 | N/C | 2021-05-24 |  | X | 565 | 1 | 128 | 1 | 1 | 2B/2T | 5/21 - AOI | SHORT 1 ITEM | SHIPPED 5/26
102158 | 2938 | 16 | 2021-05-28 | 10 | 2021-05-17 | 2021-06-01 |  | X | 3 | 0 | 3 | 0 | 1 | 1T |  |  | SHIPPED 5/26
102213 | 3412.3 | 39 | 2021-05-17 | 5 | 2021-05-19 | 2021-05-26 |  | X | 95 | 21 | 34 | 1 | 1 | 1B/1T | 5/24 - BACK |  | SHIPPED 5/26
102423 | 700 | 100 | 2021-06-02 | 5 | 2021-05-20 | 2021-05-27 |  | X | 3 | 0 | 3 | 0 | 1 | 1T | ROWC B100834 |  | SHIPPED 5/26
102362 | 5787.5 | 10 | 2021-05-20 | 3 | 2021-05-20 | 2021-05-25 |  | X | 354 | 40 | 84 | 0 | 1 | 2T | 5/21 - BOT SIDE |  | SHIPPED 5/25
102418 | 2880 | 4 | 2021-05-21 | 3 | N/C | 2021-05-24 |  | X | 565 | 1 | 128 | 1 | 1 | 2B/2T | 5/21 - AOI | SHORT 1 ITEM
101888 | 4090 | 50 | 2021-06-02 | 15 | 2021-05-06 | 2021-05-27 |  | X | 44 | 0 | 24 | 1 | 1 | 1B/1T | 5/10 - AOI |  | SHIPPED 5/24
102417 | 7180 | 25 | 2021-05-24 | 3 | N/C | 2021-05-24 |  | X | 119 | 0 | 26 | 1 | 1 | 1B/1T | 5/21 - BOT SIDE | SHORT PCB | SHIPPED 5/24
102422 | 2902.59 | 17 | 2021-05-20 | 3 | 2021-05-19 | 2021-05-24 |  | X | 500 | 0 | 138 | 1 | 1 | 1B/2T | 5/21 - TOP SIDE |  | SHIPPED 5/24
102422 | 1707.41 | 10 | 2021-05-20 | 3 | 2021-05-19 | 2021-05-24 |  | X | 500 | 0 | 138 | 1 | 1 | 1B/2T | FAVOR | FAV | SHIPPED 5/21
102147 | 4180 | 50 | 2021-05-17 | 5 | 2021-05-14 | 2021-05-21 |  | X | 217 | 5 | 19 | 1 | 1 | 1B/1T | 5/18 - AOI |  | SHIPPED 5/21
102415 | 9450 | 25 | 2021-05-21 | 3 | 2021-05-19 | 2021-05-21 |  | X | 174 | 0 | 13 | 0 | 1 | 1T | FAVOR | FAV | SHIPPED 5/21
101664 | 35708.75 | 1225 | 2021-05-19 | 7 | N/C | 2021-05-18 | HOLD | X | 1 | 3 | 1 | 1 | 0 | 1B | 5/11 - BOT SIDE | SHORT 1 ITEM | SHIPPED 5/21
102464 | 3600 | 15 | 2021-05-20 | 2 | 2021-05-21 | 2021-05-24 |  | X | 39 | 0 | 23 | 1 | 1 | 1B/1T | 5/21 - AOI | SHORT 1 ITEM | SHIPPED 5/21
101645 | 3403.69 | 15 | 2021-04-22 | 5 | 2021-05-14 | 2021-05-21 |  | X | 436 | 60 | 118 | 1 | 1 |  | 5/17 - AOI |  | SHIPPED 5/20
102130 | 3334.8 | 120 | 2021-05-17 | 10 | 2021-05-10 | 2021-05-24 |  | X | 105 | 0 | 58 | 0 | 1 | 2T |  |  | SHIPPED 5/20
102137 | 2629 | 30 | 2021-05-18 | 5 | 2021-05-13 | 2021-05-20 |  | X | 157 | 15 | 50 | 1 | 1 | 1B/1T | 5/17 - AOI |  | SHIPPED 5/20
100488 | 562.3 | 1 | 2021-04-16 | 5 | 2021-05-12 | 5/19* |  | X | 635 | 20 | 135 | 1 | 1 | 2B/2T | 5/13 - TOP SIDE |  | SHIPPED 5/20
100996 | 5693.52 | 63/75 | 2021-05-03 | 10 | N/C | 5/17* |  | X | 372 | 0 | 94 | 1 | 1 | 2B/2T | FAVOR | FAV | SHIPPED 5/19
101434 | 1753 | 50 | 2021-05-04 | 5 | 2021-05-12 | 2021-05-19 |  | X | 83 | 12 | 37 | 1 | 1 | 1B/1T | RONC B97063 |  | SHIPPED 5/19
101731 | 1338 | 2/42 | 2021-05-20 | 5 | 2021-05-12 | 5/19* |  | X | 66 | 26 | 20 | 1 | 1 | 1B/1T |  | KIT CLEAR | SHIPPED 5/19
100488 | 2811.45 | 5 | 2021-04-16 | 5 | 2021-05-12 | 5/19* |  | X | 635 | 20 | 135 | 1 | 1 | 2B/2T | 5/13 - TOP SIDE |  | SHIPPED 5/19
99082 | 14435.72 | 13 | 2021-03-04 | 5 | N/C | 5/19* |  | X | 2661 | 175 | 303 | 1 | 1 | 2B/5T | 5/11 - AOI |  | SHIPPED 5/19
101434 | 1753 | 50 | 2021-05-04 | 5 | 2021-05-12 | 2021-05-19 |  | X | 83 | 12 | 37 | 1 | 1 | 1B/1T | RONC B97063 |  | SHIPPED 5/19
100488 | 2249.2 | 4 | 2021-04-16 | 5 | 2021-05-12 | 5/19* |  | X | 635 | 20 | 135 | 1 | 1 | 2B/2T | 5/13 - TOP SIDE |  | SHIPPED 5/19
99082 | 14435.72 | 13 | 2021-03-04 | 5 | N/C | 5/19* |  | X | 2661 | 175 | 303 | 1 | 1 | 2B/5T | 5/11 - AOI |  | SHIPPED 5/19
100786 | 2222 | 20FA/150 | 2021-04-01 | 5 | 2021-05-11 | 2021-05-18 |  | X | 174 | 0 | 52 | 1 | 1 | 2B/2T | 5/12 - TOP SIDE |  | SHIPPED 5/18
96986 | 1407.6 | 510 | 2020-12-15 | 10 | 2021-05-04 | 2021-05-18 |  | X | 4 | 4 | 3 | 0 | 1 |  | 12/9 - HOLD BAL 510 | 1 SIDE | SHIPPED 5/18
102133 | 2769.9 | 30 | 2021-05-13 | 5 | 2021-05-11 | 2021-05-18 |  | X | 165 | 7 | 64 | 1 | 1 |  | 5/11 - AOI |  | SHIPPED 5/18
101350 | 5089 | 6 | 2021-04-22 | 5 | 2021-05-10 | 2021-05-17 |  | X | 650 | 5 | 192 | 1 | 1 | 2B/3T | 5/11 - AOI |  | SHIPPED 5/17
101399 | 3450 | 1000 | 2021-05-27 | 20 | 2021-04-23 | 2021-05-21 |  | X | 7 | 0 | 6 | 0 | 1 | 1T | 5/3 - BACK |  | SHIPPED 5/17
101205 | 1739.25 | 45 | 2021-05-13 | 10 | 2021-05-04 | 2021-05-17 |  | X | 45 | 10 | 22 | 1 | 1 | 1B/1T | 5/7 - AOI |  | SHIPPED 5/14
102041 | 3902.5 | 10 | 2021-05-10 | 3 | 2021-05-13 | 2021-05-14 |  | X | 113 | 1 | 30 | 1 | 1 | 1B/1T | 1 DAY FAVOR | FAV | SHIPPED 5/14
101941 | 3759.5 | 10 | 2021-05-11 | 5 | 2021-05-06 | 2021-05-13 |  | X | 421 | 36 | 101 | 1 | 1 |  | 5/7 - AOI | KIT CLEAR W/ DNI | SHIPPED 5/13
102141 | 3902.5 | 30 | 2021-05-13 | 5 | 2021-05-06 | 2021-05-13 |  | X | 16 | 13 | 4 | 0 | 1 | 1T | 5/7 - BACK |  | SHIPPED 5/13
101547 | 3842 | 200 | 2021-05-03 | 5 | 2021-05-06 | 2021-05-13 |  | X | 71 | 0 | 7 | 1 | 0 | 2B | 5/7 - AOI |  | SHIPPED 5/13
100116 | 2235 | 10 | 2021-05-11 | 15 | 2021-04-23 | 5/14* |  | X | 55 | 9 | 27 | 0 | 1 | 1T | 5/6 - BACK |  | SHIPPED 5/12
101921 | 252.163 | 7 | 2021-05-06 | 5 | 2021-05-07 | 2021-05-12 |  | X | 122 | 1 | 48 | 1 | 1 | 2B/2T | 5/7 - AOI |  | SHIPPED 5/12
101921 | 6844.45 | 190 | 2021-05-06 | 5 | N/C | 2021-05-12 |  | X | 122 | 1 | 48 | 1 | 1 | 2B/2T | SHORT 7 FABS |  | SHIPPED 5/12
99075 | 5105 | 5FA/25 | 2021-04-28 | 7 | 2021-05-03 | 2021-05-12 |  | X | 597 | 12 | 76 | 1 | 1 | 1B/2T | 5/6 - AOI |  | SHIPPED 5/12
101835 | 1850 | 200 | 2021-05-12 | 5 | 2021-05-05 | 2021-05-11 |  | X | 28 | 0 | 14 | 0 | 1 | 1T | 5/7 - AOI |  | SHIPPED 5/11
102085 | 2737.5 | 5 | 2021-05-11 | 5 | 2021-05-05 | 2021-05-11 |  | X | 55 | 63 | 7 | 0 | 1 | 1T | 5/6 - BACK |  | SHIPPED 5/11
100327 | 61 | 2/100 | 2021-05-13 | 5 | 2021-05-03 | 2021-05-10 |  | X | 58 | 11 | 33 | 1 | 1 | 1B/1T | 5/5 - BACK |  | SHIPPED - 5/10
101774 | 3869.8 | 16 | 2021-05-06 | 5 | 2021-05-03 | 2021-05-10 |  | X | 473 | 0 | 114 | 1 | 1 | 1B/2T | 5/7 - BACK |  | SHIPPED - 5/10
100330 | 7137.95 | 185 | 2021-03-03 | 5 | 2021-04-30 | 2021-05-10 |  | X | 145 | 5 | 69 | 1 | 1 | 2B/2T | 5/7 - BACK |  | SHIPPED - 5/10
102032 | 3733.25 | 3 | 2021-05-03 | 3 | 2021-05-05 | 2021-05-10 |  | X | 238 | 47 | 58 | 1 | 1 | 1B/1T | 5/6 - AOI |  | SHIPPED - 5/10
101836 | 1582 | 200 | 2021-05-12 | 5 | 2021-05-04 | 2021-05-10 |  | X | 11 | 1 | 9 | 1 | 1 | 1B/1T |  |  | SHIPPED - 5/10
101023 | 3394.72 | 336 | 2021-04-20 | 7 | N/C | 2021-05-13 |  | X | 25 | 0 | 16 | 1 | 1 | 1B/2T | 5/7 - BACK | SHORT 1 ITEM (TH) | SHIPPED - 5/10
102235 | 12210 | 5 | 2021-05-06 | 2 | 2021-05-07 | 2021-05-08 |  | X | 264 | 111 | 122 | 0 | 1 | 2T | 5/7 - BACK | FAV | SHIPPED 5/7
100158 | 2404.8 | 8 | 2021-04-28 | 10 | 2021-04-23 | 2021-05-07 |  | X | 0 | 281 | 0 | 0 | 0 |  | TH only |  | SHIPPED 5/7
101577 | 2685 | 5 | 2021-05-10 | 5 | 2021-04-29 | 2021-05-06 |  | X | 56 | 44 | 29 | 0 | 1 | 1T |  | SMT CLEAR ONLY | SHIPPED 5/6
101050 | 1400.67 | 34 | 2021-03-29 | 10 | 2021-04-22 | 2021-05-06 |  | X | 0 | 20 | 0 | 0 | 0 | 0 | TH only. |  | SHIPPED 5/6
-00038 |  | 10 |  |  |  | 2021-05-05 |  | X | [6 empty] | 4/30 - TOP SIDE |  | SHIPPED 5/6
102066 | 6167.8 | 10 | 2021-05-04 | 3 | 2021-05-03 | 2021-05-06 |  | X | 730 | 19 | 116 | 1 | 1 | 1B/2T |  | FAV | SHIPPED 5/5
102099 | 4692.5 | 6 | 2021-05-04 | 3 | 2021-04-30 | 2021-05-05 |  | X | 305 | 15 | 78 | 0 | 1 | 2T |  |  | SHIPPED 5/5
101512 | 945 | 300 | 2021-04-29 | 5 | 2021-04-22 | 2021-04-29 | ASAP | X | 6 | 0 | 2 | 0 | 1 | 1T | 4/27 - BACK |  | SHIPPED 5/5
101476 | 5678 | 2 | 2021-04-22 | 5 | 2021-04-23 | 2021-05-04 |  | X | 1676 | 129 | 192 | 1 | 1 | 2B/2T | 4/29 - AOI |  | SHIPPED 5/4
101133 | 4608 | 200 | 2021-04-13 | 10 | 2021-04-20 | 2021-05-04 |  | X | 138 | 11 | 44 | 0 | 1 | 2T | ROWC B99471 |  | SHIPPED 5/4
-00037 |  | 10 |  |  |  | 2021-05-04 |  | X | [6 empty] | 4/30 - TOP SIDE |  | SHIPPED 5/4
101406 | 8442.75 | 25 | 2021-04-12 | 3 for qty 5 - 10 for balance | 2021-04-23 | 2021-05-04 |  | X | 812 | 2 | 104 | 1 | 1 | 2B/2T | QTY 5 SHIPPED 4/28 |  | SHIPPED 5/3
100741 | 1736 | 6 | 2021-04-13 | 7 | 2021-04-20 | 2021-04-29 |  | X | 301 | 13 | 93 | 1 | 1 | 1B/2T | WTG CUST ANSWR |  | SHIPPED 5/3
100387 | 2631.42 | 66 | 2021-03-04 | 5 | 2021-04-26 | 2021-05-03 |  | X | 178 | 0 | 34 | 1 | 1 |  | SHIPPED 4/7 QTY 24 |  | SHIPPED 5/3
99939 | 8816 | 1856 | 2021-03-30 | 10 | 2021-04-19 | 2021-04-22 | ??? | X | 27 | 2 | 26 | 0 | 1 |  | 4/12 - BACK |  | SHIPPED 5/1
101000 | 3362.5 | 125 | 2021-04-19 | 10 | 2021-04-16 | 2021-04-30 |  | X | 86 | 17 | 26 | 0 | 1 | 1T | ROWC B96328 |  | SHIPPED 4/30
95674 | 3558 | 216 |  | 5 | 2021-04-23 | 2021-04-30 |  | X | 6 | 0 | 6 | 0 | 1 | 1T | 3rd article |  | SHIPPED 4/30
100735 | 243.3846 | 1 | 2021-04-13 | 7 | 2021-04-21 | 2021-04-30 |  | X | 338 | 14 | 112 | 1 | 1 | 1B/2T | 4/29 - CAGE ISSUE |  | SHIPPED 4/30
101372 | 7250 | 100 | 2021-04-19 | 15 | 2021-04-07 | 2021-04-29 |  | X | 363 | 56 | 48 | 1 | 1 | 1B/1T | 4/26 - AOI/BACK |  | SHIPPED 4/29
101512 | 630 | 200 | 2021-04-29 | 5 | 2021-04-22 | 2021-04-29 |  | X | 6 | 0 | 2 | 0 | 1 | 1T | 4/27 - BACK |  | SHIPPED 4/29
100734 | 3087 | 8 | 2021-04-13 | 7 | 2021-04-20 | 2021-04-29 |  | X | 493 | 14 | 125 | 1 | 1 | 1B/2T | 4/27 - TOP SIDE |  | SHIPPED 4/29
101431 | 4146.25 | 15 | 2021-04-23 | 5 | 2021-04-22 | 2021-04-29 |  | X | 270 | 23 | 92 | 1 | 1 | 1B/1T | 4/27 - BOT SIDE |  | SHIPPED 4/29
98962 | 3321.4 | 60 | 2020-01-15 | 10 | 2021-04-15 | 2021-04-29 |  | X | 145 | 4 | 70 | 1 | 1 |  | ROWC B98648 |  | SHIPPED 4/29
100735 | 2920.6153 | 12 | 2021-04-13 | 7 | 2021-04-21 | 2021-04-29 |  | X | 338 | 14 | 112 | 1 | 1 | 1B/2T | Setup/Excel in kit box |  | SHIPPED 4/29
101620 | 1787.5 | 65 |  | 3 |  | 2021-04-30 | [8 empty] | 4/27 - BACK |  | SHIPPED 4/28
101495 | 13632 | 85 | 2021-04-23 | 3 | 2021-04-23 | 2021-04-28 |  | X | 335 | 50 | 63 | 1 | 1 | 1B/2T | 4/26 - AOI |  | SHIPPED 4/28
101645 | 3508.75 | 5/20 | 2021-04-22 | 5 | 2021-04-26 | 4/28* | 2021-04-29 | X | 438 | 60 | 119 | 1 | 1 | 1B/2T | 4/26 - AOI |  | SHIPPED 4/28
101253 | 3547 | 9 | 2021-04-16 | 5 | 2021-04-21 | 2021-04-28 |  | X | 100 | 46 | 8 | 1 | 1 | 1B/1T |  |  | SHIPPED 4/28
101406 | 11181.3 | 30 | 2021-04-12 | 3 for qty 5 - 10 for balance | 2021-04-23 | 2021-04-28 |  | X | 812 | 2 | 104 | 1 | 1 | 2B/2T | 4/26 - AOI |  | SHIPPED 4/28
101449 | 1500 | 50 | 2021-04-27 | 10 | 2021-04-13 | 2021-04-27 |  | X | 45 | 11 | 15 | 1 | 1 | 1B/1T |  |  | SHIPPED 4/27
100858 | 3475 | 15 | 2021-03-24 | 10 | 2021-04-13 | 2021-04-27 |  | X | 312 | 26 | 50 | 0 | 1 |  |  |  | SHIPPED 4/27
101128 | 3515.6 | 4 | 2021-04-02 | 5 | 2021-04-20 | 2021-04-27 |  | X | 882 | 23 | 147 | 1 | 1 | 1B/2T | 4/21 - TOP SIDE |  | SHIPPED 4/27
100732 | 2947 | 3 | 2021-04-09 | 5 | 2021-04-20 | 2021-04-27 |  | X | 96 | 49 | 7 | 1 | 1 | 1B/1T | 4/23 - BACK |  | SHIPPED 4/27
101023 | 38396.465 | 3800 | 2021-04-20 | 7 | 2021-05-06 | 2021-04-23 |  | X | 25 | 0 | 16 | 1 | 1 | 1B/2T | 4/19 - BOT SIDE DONE | SHORT 1 ITEM (TH) | SHIPPED 4/26
101691 | 1648 | 3 | 2021-04-21 | 5 | 2021-04-19 | 2021-04-26 |  | X | 498 | 0 | 139 | 1 | 1 | 1B/2T | RTR |  | SHIPPED 4/26
101529 | 17486 | 240 | 2021-04-20 | 3 | 2021-04-21 | 2021-04-26 |  | X | 20 | 3 | 14 | 1 | 1 | 1B/1T | ROWC B99621 |  | SHIPPED 4/26
100636 | 10936 | 21 | 2021-03-23 | 3 | 2021-03-24 | 2021-04-26 |  | X | 864 | 1 | 180 | 1 | 1 | 2B/2T | 4/21 - BOT SIDE |  | SHIPPED 4/26
101785 | 1572 | 200 | 2021-04-26 | 5 | 2021-04-21 | 4/26* | 2021-04-23 | X | 3 | 0 | 3 | 0 | 1 | 1T | 4/21 - BACK |  | SHIPPED 4/23
101499 | 4741.6 | 10 | 2021-04-23 | 10 | 2021-04-09 | 2021-04-23 |  | X | 1015 | 0 | 117 | 1 | 1 |  | 4/20 - AOI |  | SHIPPED 4/23
99939 | 2992.25 | 630 | 2021-03-30 | 10 | 2021-04-19 | 2021-04-22 |  | X | 27 | 2 | 26 | 0 | 1 |  | 4/12 - BACK |  | SHIPPED 4/22
101810 | 8500 | 10 | 2021-04-30 | 2 | 2021-04-21 | 2021-04-26 |  | X | 502 | 0 | 124 | 1 | 1 | 2B/1T |  | KIT CLEAR | SHIPPED 4/22
101176 | 3173.25 | 25 | 2021-04-15 | 5 | 2021-04-15 | 2021-04-22 |  | X | 209 | 55 | 50 | 0 | 1 | 1T | 4/19 - AOI |  | SHIPPED 4/22
101668 | 4138.7 | 20 | 2021-04-21 | 3 | 2021-04-20 | 2021-04-22 |  | X | 134 | 26 | 47 | 1 | 1 | 1B/1T | 4/20 - AOI |  | SHIPPED 4/22
101349 | 5949 | 180 | 2021-04-27 | 5 | 2021-04-15 | 2021-04-22 | 2021-04-20 | X | 20 | 3 | 14 | 1 | 1 | 1B/1T | 4/19 - BACK |  | SHIPPED 4/21
100382 | 1930.5 | 25 | 2021-04-19 | 10 | 2021-04-07 | 2021-04-21 |  | X | 136 | 24 | 30 | 1 | 1 |  | 4/19 - AOI |  | SHIPPED 4/21
100315 | 4960 | 130 | 2021-04-05 | 5 | 2021-04-13 | 2021-04-20 |  | X | 154 | 7 | 54 | 1 | 1 | 2B/2T | 4/16 - AOI |  | SHIPPED 4/20
101068 | 4151.5 | 50 | 2021-04-06 | 5 | 2021-04-12 | 2021-04-19 |  | X | 256 | 12 | 68 | 1 | 1 | 1B/2T | 4/16 - AOI |  | SHIPPED 4/19
100723 | 2778 | 12 | 2021-04-12 | 7 | 2021-04-08 | 2021-04-19 |  | X | 296 | 6 | 77 | 1 | 1 | 1B/1T | 4/14 - AOI |  | SHIPPED 4/19
101323 | 11550 | 275 | 2021-04-14 | 5 | N/C | 4/15* |  | X | 22 | 1 | 15 | 1 | 1 | 1B/1T | 4/13 - 1725 COMP | SHORT 518 ELECTRODES ONLY | SHIPPED 4/19
101530 | 7370 | 100 | 2021-04-20 | 5 | 2021-04-12 | 2021-04-19 |  | X | 335 | 0 | 72 | 1 | 1 | 2B/2T | 4/13 - AOI |  | SHIPPED 4/19
93544 | 22747.8 | 1000 | 2021-03-19 | 20 | 2021-03-15 | 2021-04-12 |  | X | 239 | 1 | 95 | 1 | 1 |  | 3/19 - TOP SIDE |  | SHIPPED 4/17
100201 | 12910.5 | 95 | 2021-04-14 | 10 | 2021-04-02 | 2021-04-16 |  | X | 562 | 18 | 120 | 1 | 1 | 2B/2T | 4/14 - AOI |  | SHIPPED 4/16
100813 | 4091.13 | 57 | 2021-04-16 | 10 | 2021-04-05 | 4/16* |  | X | 166 | 11 | 39 | 1 | 1 | 1B/1T | 4/14 - AOI |  | SHIPPED 4/16
101024 | 28360 | 2000 | 2021-03-30 | 7 | 2021-04-07 | 2021-04-16 |  | X | 25 | 0 | 16 | 1 | 1 | 1B/2T | 4/9 - TOP SIDE DONE |  | SHIPPED 4/16
101530 | 3685 | 50 | 2021-04-20 | 5 | 2021-04-12 | 2021-04-19 |  | X | 335 | 0 | 72 | 1 | 1 | 2B/2T | 4/13 - AOI |  | SHIPPED 4/14
101323 | 72450 | 1725 | 2021-04-14 | 5 | N/C | 4/15* |  | X | 22 | 1 | 15 | 1 | 1 | 1B/1T | 4/13 - 1725 COMP | SHORT 518 ELECTRODES ONLY | SHIPPED 4/14
100593 | 3616 | 70 | 2021-04-12 | 10 | 2021-03-31 | 2021-04-14 |  | X | 304 | 15 | 79 | 1 | 1 | 2B/2T | 4/12 - AOI |  | SHIPPED 4/14
100892 | 1250 | 5 | 2021-04-21 | 10 | 2021-03-31 | 2021-04-14 |  | X | 0 | 112 | 0 | 0 | 0 | 0 | TH only |  | SHIPPED 4/14
100361 | 6200 | 125 | 2021-03-30 | 10 | 2021-04-01 | 2021-04-15 |  | X | 190 | 14 | 43 | 0 | 1 | 2T | 4/9 - AOI |  | SHIPPED 4/13
100754 | 4219.1 | 155 | 2021-03-31 | 10 | 2021-04-01 | 2021-04-15 |  | X | 157 | 7 | 40 | 0 | 1 | 2T | 4/9 - AOI |  | SHIPPED 4/13
101353 | 2090 | 115 | 2021-04-07 | 3 | 2021-04-06 | 2021-04-09 |  | X | 24 | 0 | 16 | 1 | 1 | 1B/1T | 4/6 - BOT SIDE |  | SHIPPED 4/12
101092 | 2101 | 10 | 2021-04-06 | 10 | 2021-03-29 | 2021-04-12 |  | X | 210 | 53 | 43 | 1 | 1 | 1B/1T | 4/8 - BACK |  | SHIPPED 4/12
99933 | 1847.5 | 2 | 2021-03-30 | 10 | N/C |  | 2021-04-06 | X | 219 | 39 | 33 | 1 | 1 | 1B/1T | 4/1 - AOI | SHORT 2 ITEMS | SHIPPED 4/12
98561 | 4338.6 | 28 | 2021-03-08 | 10 | 2021-03-29 | 2021-04-13 |  | X | 613 | 2 | 204 | 1 | 1 | 3 | 4/8 - TOP SIDE |  | SHIPPED 4/12
93544 | 22747.8 | 1000 | 2021-03-19 | 20 | 2021-03-15 | 2021-04-09 |  | X | 239 | 1 | 95 | 1 | 1 |  | 3/19 - TOP SIDE |  | SHIPPED 4/10
101083 | 3047.5 | 25 | 2021-03-12 | 5 | 2021-04-02 | 2021-04-09 |  | X | 203 | 22 | 58 | 1 | 1 | 1B/1T | 4/7 - BACK |  | SHIPPED 4/9
99292 | 5042.9 | 10 | 2021-03-30 | 10 | 2021-03-26 | 2021-04-09 |  | X | 1345 | 39 | 217 | 1 | 1 | 2B/2T | 4/6 - AOI |  | SHIPPED 4/9
97190 | 254.38 | 1 | 2020-11-09 | 10 | 2020-10-30 | 2020-11-13 | 2020-12-16 | X | 883 | 7 | 181 |  |  |  | LINE SHORT | 2 SIDE | SHIPPED 4/8
101252 | 5388 | 10 | 2021-03-31 | 3 | 2021-04-05 | 4/8* |  | X | 751 | 29 | 152 | 1 | 1 | 1B/2T | 4/5 - AOI |  | SHIPPED 4/8
101217 | 1358 | 3/200 | 2021-03-31 | 5 | 2021-04-01 | 2021-04-08 |  | X | 122 | 1 | 48 | 1 | 1 |  | 4/5 - AOI |  | SHIPPED 4/8
101175 | 2130 | 8 | 2021-04-01 | 5 | 2021-03-26 | 2021-04-09 |  | X | 69 | 0 | 3 | 0 | 1 | 1T | 4/2 - BACK |  | SHIPPED 4/8
101066 | 3618.25 | 1 | 2021-04-02 | 5 | 2021-04-01 | 2021-04-08 |  | X | 1398 | 91 | 99 | 0 | 1 | 2T | 4/6 - AOI | SHORT 1 ITEM | SHIPPED 4/8
97453 | 258.65 | 1 | 2021-03-26 | 10 | 2021-03-23 | 2021-04-06 | L/S | X | 935 | 38 | 133 | 1 | 1 | 2B/2T | 4/2 - AOI |  | SHIPPED 4/8
100564 | 11847.7 | 30 | 2021-03-31 | 20 | 2021-03-10 | 2021-04-07 |  | X | 113 | 0 | 44 | 1 | 1 | 1B/1T | 4/2 - AOI |  | SHIPPED 4/7
100387 | 2155.58 | 34/100 | 2021-03-04 | 5 | 2021-04-26 | 2021-05-03 |  | X | 178 | 0 | 34 | 1 | 1 |  | 4/2 - AOI |  | SHIPPED 4/7
100791 | 2394.5 | 5 | 2021-04-08 | 5 | 2021-03-31 | 2021-04-07 |  | X | 473 | 1 | 114 | 1 | 1 | 1B/2T | 4/2 - AOI |  | SHIPPED 4/7
99936 | 3049.95 | 3 | 2021-03-30 | 10 | 2021-03-26 | 4/9* | 2021-04-05 | X | 1400 | 128 | 120 | 1 | 1 | 1B/2T | 3/31 - AOI |  | SHIPPED 4/7
100471 | 8.25 | 2 | 2021-03-26 | 20 | 2021-03-08 | 2021-04-05 | L/S | X | 9 | 1 | 4 | 0 | 1 | 1T | *SHIP FEDEX ALTA ACCT |  | SHIPPED 4/7
99935 | 3519.3 | 5 | 2021-03-30 | 10 | 2021-03-30 | 2021-04-13 | 2021-04-06 | X | 1189 | 139 | 105 | 1 | 1 | 1B/2T | 4/1 - AOI |  | SHIPPED 4/6
99174 | 1470 | 375 | 2021-04-08 | 15 | 2021-03-16 | 2021-04-06 |  | X | 11 | 0 | 8 | 0 | 1 |  | 4/2 - BACK |  | SHIPPED 4/6
97453 | 7242.055 | 28 | 2021-03-26 | 10 | 2021-03-23 | 2021-04-06 |  | X | 935 | 38 | 133 | 1 | 1 | 2B/2T | 4/2 - AOI |  | SHIPPED 4/6
100471 | 1641.75 | 398 | 2021-03-26 | 20 | 2021-03-08 | 2021-04-05 | 2021-04-06 | X | 9 | 1 | 4 | 0 | 1 | 1T | *SHIP FEDEX ALTA ACCT |  | SHIPPED 4/6
100172 | 48 | 1 | 2021-03-22 | 5 | 2021-03-26 | 2021-04-02 |  | X | 374 | 0 | 81 | 1 | 1 |  | 4/2 - LINE SHORT |  | SHIPPED 4/5
99932 | 2385.2 | 5 | 2021-03-30 | 10 | 2021-03-24 | 2021-04-09 | 2021-04-05 | X | 648 | 121 | 70 | 1 | 1 | 1B/2T | 3/31 - AOI |  | SHIPPED 4/5
100630 | 24074.4 | 380/500 | 2021-03-16 | 3 | N/C | 2021-04-05 |  | X | 22 | 1 | 15 | 1 | 1 | 1B/1T | 4/1 - QA/BAKE |  | SHIPPED 4/5 - Closed short at 380
100172 | 4752 | 99 | 2021-03-22 | 5 | 2021-03-26 | 2021-04-02 |  | X | 374 | 0 | 81 | 1 | 1 |  | 3/30 - AOI |  | SHIPPED 4/2
93544 | 22747.8 | 1000 | 2021-03-19 | 20 | 2021-03-15 | 2021-04-02 |  | X | 239 | 1 | 95 | 1 | 1 |  | 3/26 BACK |  | SHIPPED 4/2
101003 | 3502.5 | 5 | 2021-03-19 | 5 | 2021-03-26 | 2021-04-02 |  | X | 71 | 0 | 39 | 1 | 1 | 1B/1T | 3/31 - AOI |  | SHIPPED 4/1
97132 | 11428.625 | 325 | 2021-03-23 | 5 | 2021-03-25 | 2021-04-01 |  | X | 149 | 3 | 44 | 0 | 1 | 2T | 3/26 - AOI |  | SHIPPED 4/1
100374 | 4769.75 | 75 | 2021-04-01 | 10 | 2021-03-17 | 2021-03-31 |  | X | 292 | 1 | 109 | 1 | 1 | 2B/2T | 3/30 - AOI |  | SHIPPED 3/31
101082 | 2042.5 | 25 | 2021-03-26 | 5 | 2021-03-24 | 2021-03-31 |  | X | 44 | 22 | 21 | 1 | 1 | 1B/1T | 3/29 - AOI |  | SHIPPED 3/31
100383 | 2746.5 | 110 | 2021-04-01 | 5 | 2021-03-23 | 2021-03-30 |  | X | 58 | 0 | 25 | 1 | 1 | 1B/1T | 3/29 - AOI |  | SHIPPED 3/30
97130 | 2260 | 1/400 | 2021-03-22 | 5 | 2021-03-22 | 2021-03-29 |  | X | 0 | 1 | 0 | 0 | 0 | 0 | 1 PC FA SHIPPED 3/24 |  | SHIPPED 3/29
100636 | 3854 | 4/25 | 2021-03-23 | 3 | 2021-03-24 | 2021-03-31 |  | X | 864 | 1 | 180 | 1 | 1 | 2B/2T | 3/26 - AOI |  | SHIPPED 3/29
97132 | 2637.38 | 75 | 2021-03-23 | 5 | 2021-03-25 | 2021-03-29 |  | X | 149 | 3 | 44 | 0 | 1 | 2T | 3/26 - AOI |  | SHIPPED 3/29
99621 | 2208 | 100 | 2021-03-19 | 20 | 2021-02-18 | 2021-03-29 |  | X | 22 | 1 | 15 | 1 | 1 |  | 2/19 - TOP SIDE |  | SHIPPED 3/29
99082 | 5249.82 | 2/15 | 2021-03-04 | 5 | 2021-03-22 | 2021-03-29 |  | X | 2676 | 175 | 305 | 1 | 1 | 2B/5T | 3/26 - AOI |  | SHIPPED 3/27
93544 | 4113.739 | 5 | 2021-03-19 | 20 | 2021-03-15 | 2021-04-02 |  | X | 239 | 1 | 95 | 1 | 1 |  | 3/26 BACK |  | SHIPPED 3/29
100081 | 5213.4 | 20 | 2021-02-22 | 5 | 2021-03-19 | 2021-03-26 |  | X | 952 | 6 | 171 | 1 | 1 | 2B/2T | 3/24 - AOI |  | SHIPPED 3/26
100236 | 2311 | 100 | 2021-03-23 | 5 | 2021-03-19 | 2021-03-26 |  | X | 23 | 6 | 10 | 1 | 1 | 1B/1T | 3/26 - BACK |  | SHIPPED 3/26
100803 | 2678 | 6 | 2021-03-24 | 5 | 2021-03-25 | 3/26* |  | X | 91 | 126 | 19 | 0 | 1 | 1T | 3/23 - BACK |  | SHIPPED 3/26
98384 | 6842 | 100 | 2020-01-04 | 5 | 2021-03-16 | 2021-03-23 |  | X | 304 | 15 | 79 | 1 | 1 |  | 3/22 - AOI |  | SHIPPED 3/24
100856 | 228.1 | 1 | 2021-03-15 | 3 | 2021-03-15 | 2021-03-18 |  | X | 217 | 29 | 31 | 1 | 1 | 1B/1T | 3/16 - BACK |  | SHIPPED 3/24
101073 | 123.9 | 1 | 2021-03-24 | 3 | 2021-03-22 | 2021-03-25 |  | X | 169 | 0 | 33 | 1 | 1 | 1B/1T | 3/24 - BACK |  | SHIPPED 3/24
100316 | 2469.14 | 22 | 2021-03-31 | 3 | 2021-03-19 | 2021-03-24 |  | X | 123 | 12 | 45 | 0 | 1 | 1T | 3/22 - AOI |  | SHIPPED 3/24
98384 | 10263 | 150 | 2020-01-04 | 5 | 2021-03-16 | 2021-03-23 |  | X | 304 | 15 | 79 | 1 | 1 |  | 3/22 - AOI |  | SHIPPED 3/23
100065 | 3564.25 | 5 | 2021-03-11 | 5 | 2021-03-16 | 2021-03-23 |  | X | 1486 | 35 | 178 | 1 | 1 | 2B/3T | 3/22 - AOI |  | SHIPPED 3/23
101073 | 2984.6 | 14 | 2021-03-19 | 3 | 2021-03-18 | 2021-03-23 |  | X | 2 | 0 | 1 | 1 | 0 | 1B |  |  | SHIPPED 3/22
101085 | 3453.34 | 15 | 2021-03-19 | 3 | 2021-03-18 | 2021-03-23 |  | X | 2 | 0 | 1 | 1 | 0 | 1B |  |  | SHIPPED 3/22
100876 | 5183.4 | 60 | 2021-03-19 | 5 | 2021-03-15 | 2021-03-22 |  | X | 335 | 0 | 72 | 1 | 1 | 2B/2T | 3/19 - AOI |  | SHIPPED 3/22
100154 | 2386 | 110 | 2021-03-09 | 10 | 2021-03-08 | 2021-03-22 |  | X | 146 | 27 | 65 | 1 | 1 |  | 3/15 - BACK |  | SHIPPED 3/22
99994 | 6601.2 | 20 | 2021-03-01 | 10 | N/C | 2021-03-22 |  | X | 829 | 0 | 106 | 1 | 1 | 2B/2T | 3/19 - AOI |  | SHIPPED 3/22
99988 | 6509.25 | 20 | 2021-03-01 | 10 | 2021-03-08 | 2021-03-22 |  | X | 833 | 0 | 78 | 1 | 1 | 1B/2T | 3/19 - AOI |  | SHIPPED 3/22
99993 | 7479.3 | 20 | 2021-03-01 | 10 | 2021-03-08 | 2021-03-22 |  | X | 986 | 0 | 92 | 1 | 1 | 2B/2T | 3/18 - AOI |  | SHIPPED 3/22
99995 | 6509.25 | 20 | 2021-03-01 | 10 | 2021-03-08 | 2021-03-22 |  | X | 314 | 0 | 44 | 1 | 1 | 1B/1T | 3/17 - AOI |  | SHIPPED 3/22
100834 | 2270 | 450 | 2021-03-23 | 5 | 2021-03-15 | 2021-03-22 |  | X | 3 | 0 | 3 | 0 | 1 | 1T | 3/20 - TOP SIDE |  | SHIPPED 3/22
94714 | 389.6 | 180 | 2020-07-06 | 20 | 2021-01-19 | 2020-08-24 |  | X | 6 | 0 | 6 | 0 | 1 |  | 8/24 - KIT CLEAR | 1 SIDE | SHIPPED 3/20
100325 | 29.19 | 1 | 2021-03-09 | 5 | 2021-03-11 | 2021-03-19 |  | X | 75 | 11 | 25 | 1 | 1 |  | 3/16 - BACK |  | SHIPPED 3/19
100810-REV1 | 5090.75 | 15 | 2021-03-17 | 1 | 2021-03-18 | 2021-03-19 |  | X | 288 | 1 | 98 | 1 | 1 | 2B/1T | 3/19 - AOI |  | SHIPPED 3/19
100364 | 4029 | 15 | 2021-03-16 | 5 | 2021-03-11 | 2021-03-19 |  | X | 389 | 16 | 97 | 1 | 1 | 2B/2T | 3/16 - AOI |  | SHIPPED 3/19
101084 | 3700 | 15 | 2021-03-19 | 3 | 2021-03-16 | 2021-03-19 |  | X | 2 | 0 | 1 | 1 | 0 | 1B | 3/18 - BACK |  | SHIPPED 3/19
100100 | 4222.5 | 125 | 2021-03-15 | 10 | 2021-03-08 | 2021-03-22 |  | X | 157 | 7 | 40 | 0 | 1 |  | 3/18 - BACK |  | SHIPPED 3/19
100317 | 2093.6 | 22 | 2021-03-24 | 5 | 2021-03-15 | 2021-03-18 |  | X | 108 | 23 | 45 | 0 | 1 | 1T | 3/17 - BACK |  | SHIPPED 3/18
99351 | 12312.5 | 300 | 2020-02-15 | 10 | 2021-03-11 | 2021-03-18 |  | X | 207 | 0 | 31 | 1 | 1 |  | 3/17 - BACK |  | SHIPPED 3/18
100325 | 3707.6 | 127 | 2021-03-09 | 5 | 2021-03-11 | 2021-03-18 |  | X | 75 | 11 | 25 | 1 | 1 |  | 3/16 - BACK |  | SHIPPED 3/18
100856 | 2052.9 | 9 | 2021-03-15 | 3 | 2021-03-15 | 2021-03-18 |  | X | 217 | 29 | 31 | 1 | 1 | 1B/1T | 3/16 - BACK |  | SHIPPED 3/18
100569 | 6176 | 200 | 2021-03-08 | 5 | 2021-03-10 | 2021-03-18 |  | X | 125 | 0 | 54 | 0 | 1 | 2T | 3/15 - BACK |  | SHIPPED 3/17
100891 | 2042.48 | 26 | 2021-03-15 | 3 | 2021-03-15 | 2021-03-18 |  | X | 0 | 23 | 0 | 0 | 0 | 0 | TH only. |  | SHIPPED 3/17
99911 | 2165 | 15 | 2021-02-18 | 5 | 2021-03-11 | 2021-03-18 |  | X | 952 | 6 | 171 | 1 | 1 | 2 | 3/15 - BACK |  | SHIPPED 3/17
100245 | 1965.15 | 3 | 2021-03-03 | 5 | 2021-03-02 | 2021-03-09 |  | X | 886 | 13 | 116 | 1 | 1 | 2 | 3/3 - AOI |  | SHIPPED 3/16
100345 | 9281.25 | 495 | 2021-03-09 | 5 | 2021-03-10 | 2021-03-16 |  | X | 114 | 0 | 53 | 1 | 1 |  | 3/12 - AOI/BACK |  | SHIPPED 3/16
100066 | 3997.25 | 25 | 2021-03-15 | 15 | 2021-03-01 | 2021-03-17 |  | X | 504 | 71 | 46 | 1 | 1 |  | 3/12 - BACK |  | SHIPPED 3/16
100939 | 1697.25 | 3 | 2021-03-12 | 3 | 2021-03-12 | 3/17* |  | X | 108 | 23 | 45 | 0 | 1 | 1T | 3/12 - RTR |  | SHIPPED 3/16
100550 | 1500 | 75 | 2021-03-19 | 5 | 2021-03-12 | 2021-03-19 |  | X | 0 | 1 | 0 | 0 | 0 |  | 3/12 - BACK |  | SHIPPED 3/15
99152 | 24.86 | 1 | 2021-02-26 | 10 | 2021-02-23 | 2021-03-09 |  | X | 35 | 15 | 22 | 0 | 1 |  | SHIP 3/11 |  | SHIPPED 3/15
100449 | 7104.05 | 15 | 2021-03-11 | 3 | 2021-03-10 | 2021-03-15 |  | X | 823 | 8 | 176 | 1 | 1 | 1B/3T | 3/12 - BACK |  | SHIPPED 3/15
99743 | 2034 | 100 | 2021-03-16 | 10 | 2021-03-01 | 2021-03-15 |  | X | 2 | 0 | 1 | 0 | 1 |  | 3/13 - TOP SIDE |  | SHIPPED 3/15
99621 | 41952 | 1900 | 2021-03-19 | 20 | 2021-02-18 | 2021-03-12 |  | X | 22 | 1 | 15 | 1 | 1 |  | 2/19 - TOP SIDE |  | 3/1 - 1050 COMPLETE
100516 | 3646.8 | 16 | 2021-03-22 | 10 | 2021-03-03 | 2021-03-17 |  | X | 54 | 78 | 1 | 1 | 0 |  | 3/10 - BACK |  | SHIPPED 3/12
99152 | 2461.14 | 99 | 2021-02-26 | 10 | 2021-02-23 | 2021-03-09 |  | X | 35 | 15 | 22 | 0 | 1 |  | SHIP 3/11 |  | SHIPPED 3/11
100549 | 3150 | 100 | 2021-03-12 | 5 | 2021-03-05 | 2021-03-12 |  | X | 2 | 0 | 2 | 1 | 1 |  | SHIPPED 3/11 |  | SHIPPED 3/11
100561 | 1500 | 75 | 2021-03-12 | 5 | 2021-03-08 | 2021-03-15 |  | X | 0 | 1 | 0 | 0 | 0 |  | SHIPPED 3/11 |  | SHIPPED 3/11
99151 | 2923 | 65 | 2021-02-26 | 10 | 2021-02-23 | 3/9* |  | X | 82 | 9 | 7 | 1 | 1 |  | SHIPPED 3/11 |  | SHIPPED 3/11
93217 | 2223.6 | 24/25 | 2020-12-15 | 10 | 2021-02-25 | 2021-03-11 |  | X | 323 | 13 | 71 | 0 | 2 |  | SHIP 3/10 | 1 SIDE | SHIPPED 3/10
100309 | 1582.4 | 160 | 2021-03-11 | 5 | 2021-03-08 | 2021-03-15 |  | X | 9 | 0 | 9 | 0 | 1 |  | SHIP 3/10 |  | SHIPPED 3/10
97571 | 2590.58 | 2 | 2021-02-17 | 5 | 2021-03-03 | 2021-03-10 |  | X | 128 | 114 | 27 | 1 | 1 |  | SHIP 3/10 |  | SHIPPED 3/10
100487 | 3061.84 | 36 | 2021-03-08 | 5 | 2021-03-03 | 2021-03-10 |  | X | 228 | 8 | 53 | 1 | 1 |  | 3/8 - BACK |  | SHIPPED 3/10
98561 | 2386.5 | 2/30 | 2021-03-08 | 10 | 2021-03-09 | 2021-03-15 |  | X | 613 | 2 | 204 | 1 | 1 | 3 | 3/8 - BACK |  | SHIPPED 3/10
100149 | 2773.4 | 20 | 2021-03-08 | 10 | 2021-02-26 | 2021-03-11 |  | X | 284 | 53 | 36 | 1 | 1 |  | 3/3 - AOI |  | SHIPPED 3/8
99149 | 7036 | 100 | 2021-02-26 | 10 | 2021-02-25 | 3/9* |  | X | 350 | 6 | 38 | 1 | 1 |  | 3/8 - BACK |  | SHIPPED 3/8
100245 | 655.05 | 1 | 2021-03-03 | 5 | 2021-03-02 | 2021-03-09 |  | X | 886 | 13 | 116 | 1 | 1 | 2 | 3/3 - AOI |  | SHIPPED 3/8
100286 | 3595.5 | 50 | 2021-02-19 | 5 | 2021-03-01 | 2021-03-08 |  | X | 307 | 9 | 82 | 1 | 1 |  | 3/3 - AOI |  | SHIPPED 3/5
99621 | 22080 | 1000 | 2021-03-19 | 20 | 2021-02-18 | 2021-03-12 |  | X | 22 | 1 | 15 | 1 | 1 |  | 2/19 - TOP SIDE |  | SHIPPED 3/5
98612 | 1440 | 60 | 2020-12-28 | 10 | 2021-01-28 | 2020-12-31 | *** | X | 115 | 18 | 37 |  |  |  | 12/28 - BACK |  | SHIPPED 3/4
100342 | 2394.23 | 47 | 2021-03-03 | 10 | 2021-02-24 | 2021-03-10 |  | X | 5 | 0 | 4 | 1 | 1 |  | 3/3 - BACK |  | SHIPPED 3/4
99151 | 353 | 35 | 2021-02-26 | 10 | 2021-02-23 | 3/9* |  | X | 82 | 9 | 7 | 1 | 1 |  | 3/3 - AOI |  | SHIPPED 3/4
99941 | 2500 | 6 | 2021-02-23 | 7 | 2021-02-24 | 2021-03-05 |  | X | 808 | 21 | 106 | 1 | 1 | 2 | SHIPPED 3/4 |  | SHIPPED 3/4
100407 | 3132.25 | 25 | 2021-03-03 | 5 | 2021-02-24 | 2021-03-03 |  | X | 243 | 35 | 44 | 1 | 1 |  | 3/1 - AOI |  | SHIPPED 3/3
97452 | 4249.5 | 30 | 2021-02-12 | 10 | 2021-02-22 | 3/4* |  | X | 296 | 70 | 60 | 1 | 1 |  | 2/25 - BACK |  | SHIPPED 3/3
100189 | 3392 | 100 | 2021-03-03 | 10 | 2021-02-17 | 2021-03-03 |  | X | 107 | 12 | 30 | 0 | 1 |  | 2/23 - AOI |  | SHIPPED 3/2
99892 | 4491.7 | 30 | 2021-02-24 | 5 | 2021-02-24 | 3/2* |  | X | 425 | 38 | 102 | 1 | 1 | 2 | 3/1 - BACK |  | SHIPPED 3/2
99911 | 2165 | 5/20 | 2021-02-18 | 5 | 2021-02-24 | 2021-03-02 |  | X | 952 | 6 | 171 | 1 | 1 | 2 | 3/1 - BACK |  | SHIPPED 3/2
99895 | 1622.5 | 50 | 2021-02-23 | 5 | 2021-03-01 | 2/23* |  | X | 331 | 24 | 118 | 1 | 1 |  | 2/18 - BOT SIDE | KIT CLEAR | SHIPPED 3/2
100244 | 2737 | 5 | 2021-02-19 | 5 | 2021-02-24 | 2021-03-03 |  | X | 443 | 38 | 97 | 1 | 1 |  | 3/1 - AOI |  | SHIPPED 3/2
100288 | 2530.8 | 12 | 2021-02-22 | 3 | 2021-03-01 | 3/1* |  | X | 276 | 34 | 71 | 0 | 1 |  | 2/25 - AOI |  | SHIPPED 3/1
99486 | 1537.75 | 11 |  | 5 | 2021-02-22 | 2021-03-01 |  | X | 386 | 31 | 89 | 1 | 1 |  | 2/25 - BACK |  | SHIPPED 3/1
100108 | 2230.4 | 360 | 2021-03-04 | 5 | 2021-02-24 | 2021-03-03 |  | X | 3 | 0 | 3 | 1 | 1 |  | 2/25 - BACK |  | SHIPPED 2/26
100175 | 5041.6 | 120 | 2021-02-23 | 5 | 2021-02-26 | 3/1* |  | X | 113 | 22 | 34 | 0 | 1 |  | 2/25 - BACK |  | SHIPPED 2/26
99788 | 6817.5 | 250 | 2021-03-01 | 10 | 2021-02-12 | 2021-03-01 |  | X | 103 | 4 | 46 | 1 | 1 |  | 2/24 - AOI |  | SHIPPED 2/26
100133 | 2867.3 | 53/75 | 2021-02-19 | 3 | 2021-02-19 | 2021-02-24 |  | X | 83 | 9 | 36 | 1 | 1 |  | 2/24 - SHIP |  | SHIPPED 2/24
99150 | 2455 | 100 | 2021-02-26 | 10 | 2021-02-10 | 2021-02-24 |  | X | 56 | 7 | 15 | 0 | 1 |  | 2/24 - BACK |  | SHIPPED 2/24
98847 | 59859 | 2500 |  |  | 2021-02-05 | 2021-02-26 |  | X | 20 | 3 | 14 | 1 | 1 |  | 2/24 - SHIP |  | SHIPPED 2/24
99603 | 206.15 | 5 | 2021-02-18 | 10 | 2021-02-03 | 2021-02-18 |  | X | 196 | 9 | 21 | 1 | 1 |  | 2/11 - AOI |  | SHIPPED 2/24
100131 | 4057.5 | 25 | 2021-02-22 | 5 | 2021-02-16 | 2021-02-23 |  | X | 260 | 7 | 92 | 1 | 1 |  | 2/22 - BACK |  | SHIPPED 2/23
100251 | 3814 | 45 | 2021-02-24 | 3 | 2021-02-18 | 2021-02-23 |  | X | 135 | 7 | 47 | 1 | 1 |  | 2/22 - BACK |  | SHIPPED 2/23
99598 | 545 | 100 | 2021-02-24 | 10 | 2021-02-08 | 2021-02-23 |  | X | 9 | 4 | 5 | 0 | 1 |  | 2/17 - AOI |  | SHIPPED 2/23
98717 | 9064.6 | 70 | 2020-02-08 | 15 | 2021-02-01 | 2021-02-22 |  | X | 626 | 23 | 78 | 1 | 1 |  | 2/17 - AOI |  | SHIPPED 2/23
98700 | 2645.87 | 3 | 2020-12-08 | 2 | 2021-02-22 | 2021-02-24 |  | X | 160 | 49 | 47 | 1 | 1 |  | 2/22 - AOI/BACK |  | ***2 DAY TURN***
100017 | 3933.5 | 53/100 |  |  | 2021-02-19 | 2021-02-23 |  | X | [6 empty] | 2/22 - BACK |  | SHIPPED 2/22
94714 | 876.6 | 180 | 2020-07-06 | 20 | 2021-01-19 | 2020-08-24 |  | X | 6 | 0 | 6 | 0 | 1 |  |  | 1 SIDE | SHIPPED 2/22
99529 | 3908.3 | 11 | 2021-02-19 | 5 | 2021-02-15 | 2021-02-22 |  | X | 346 | 63 | 61 | 0 | 1 |  | 2/16 - AOI |  | SHIPPED 2/22
99597 | 400 | 200 | 2021-02-24 | 10 | 2021-02-08 | 2021-02-22 |  | X | 0 | 3 | 0 | 0 | 0 |  | 2/8 - BACK |  | SHIPPED 2/22
98497 | 3120.2 | 100 | 2021-02-19 | 15 | 2021-01-29 | 2021-02-19 |  | X | 116 | 6 | 28 | 0 | 1 |  | 2/16 - BACK |  | SHIPPED 2/19
99888 | 3141.29 | 27 | 2021-02-12 | 10 | 2021-02-05 | 2021-02-19 |  | X | 402 | 15 | 57 | 1 | 1 |  | 2/16 - BACK |  | SHIPPED 2/19
99887 | 5201.39 | 27 | 2021-02-09 | 10 | 2021-02-05 | 2021-02-19 |  | X | 822 | 22 | 117 | 1 | 1 |  | 2/17 - BACK |  | SHIPPED 2/19
99603 | 7009.1 | 175 | 2021-02-18 | 10 | 2021-02-03 | 2021-02-18 |  | X | 196 | 9 | 21 | 1 | 1 |  | 2/11 - AOI |  | SHIPPED 2/18
100133 | 1190.2 | 22/75 | 2021-02-19 | 3 | 2021-02-22 | 2/19* |  | X | 83 | 9 | 36 | 1 | 1 |  | 2/17 - BOT QTY 22 | *SHOULD CLEAR 2/16 | SHIPPED 2/17
100061 | 5581.25 | 25 | 2021-02-17 | 5 | 2021-02-12 | 2021-02-17 |  | X | 796 | 27 | 103 | 0 | 1 |  | 2/12 - AOI |  | SHIPPED 2/17
99890 | 3347.57 | 27 | 2021-02-12 | 10 | 2021-02-01 | 2021-02-16 |  | X | 402 | 15 | 57 | 1 | 1 |  | 2/11 - BACK | 1 ITEM NEEDS VRF. | SHIPPED 2/16
100174 | 3448.5 | 150 | 2021-02-16 | 3 | 2021-02-11 | 2021-02-16 |  | X | 7 | 0 | 4 | 1 | 1 |  | 2/15 - STICKER |  | SHIPPED 2/16
99925 | 2270.4 | 35 | 2021-02-11 | 10 | 2021-02-05 | 2/16* |  | X | 108 | 18 | 59 | 1 | 1 |  | 2/10 - AOI |  | SHIPPED 2/16
99352 | 11941.53 | 105 | 2020-01-27 | 7 | N/C | 2021-02-16 |  | X | 649 | 3 | 111 | 1 | 1 |  | 2/8 - AOI/BACK |  | SHIPPED 2/16
100212 | 1770 | 6 | 2021-02-11 | 1 | N/C | 2021-02-10 |  | X | 39 | 0 | 23 | 1 | 1 |  | SHIPPED QTY 4 2/10 |  | SHIPPED 2/15
99931 | 4537 | 50 | 2021-02-04 | 5 | 2021-02-05 | 2021-02-12 |  | X | 307 | 1 | 80 | 1 | 1 |  | 2/10 - BACK |  | SHIPPED 2/12
99786 | 2090 | 200 | 2021-02-02 | 3 | 2021-02-09 | 2021-02-12 |  | X | 24 | 0 | 16 | 1 | 1 |  | 2/10 - AOI |  | SHIPPED 2/11
94715 | 439.56 | 198 |  |  |  | 2021-02-12 | [8 empty] | 2/11 - TOP SIDE |  | SHIPPED 2/11
100212 | 1180 | 4 | 2021-02-11 | 1 | N/C | 2021-02-10 |  | X | 39 | 0 | 23 | 1 | 1 |  |  |  | ***SAME DAY TURN***
99713 | 2105.4 | 2 | 2021-02-04 | 5 | 2021-02-03 | 2021-02-10 |  | X | 748 | 6 | 92 | 0 | 1 |  | 2/8 - AOI |  | SHIPPED 2/10
99352 | 13647.6 | 120 | 2020-01-27 | 7 | 2021-02-09 | 2021-02-10 |  | X | 649 | 3 | 111 | 1 | 1 |  | 2/8 - AOI/BACK |  | SHIPPED 2/10
99712 | 1711.25 | 3 | 2021-02-08 | 5 | 2021-02-05 | 2021-02-12 |  | X | 168 | 53 | 32 | 0 | 1 |  | 2/8 - AOI |  | SHIPPED 2/9
99741 | 1854 | 100 | 2021-02-08 | 5 | 2021-02-02 | 2021-02-09 |  | X | 103 | 0 | 48 | 1 | 1 |  | 2/8 - AOI/BACK |  | SHIPPED 2/9
99585 | 2480 | 50 | 2021-01-28 | 5 | 2021-02-01 | 2021-02-08 |  | X | 21 | 3 | 15 | 1 | 1 |  | 2/5 - BACK |  | SHIPPED 2/8
99584 | 3429.6 | 130 | 2021-02-04 | 5 | 2021-02-01 | 2021-02-08 |  | X | 21 | 3 | 14 | 1 | 1 |  | 2/5 - BACK |  | SHIPPED 2/8
99807 | 2718.3 | 10 | 2021-02-09 | 5 | 2021-02-01 | 2021-02-08 |  | X | 471 | 46 | 103 | 0 | 1 |  | 2/3 - BACK |  | SHIPPED 2/5
99410 | 1592 | 200 | 2021-01-28 | 5 | 2021-02-04 | 1/27* |  | X | 15 | 1 | 15 | 1 | 1 |  | 1/22 - BACK |  | SHIPPED 2/4
97454 | 7483.85 | 19 | 2021-02-11 | 10 | 2021-01-26 | 2021-02-09 |  | X | 777 | 66 | 86 | 1 | 1 |  | 2/3 - AOI |  | SHIPPED 2/4
99226 | 5181.6 | 410 | 2021-02-08 | 10 | 2021-01-25 | 2021-02-08 |  | X | 61 | 0 | 33 | 1 | 1 |  | 2/1 - BACK |  | SHIPPED 2/3
99805 | 2282.4 | 40 | 2021-02-05 | 5 | 2021-01-29 | 2021-02-05 |  | X | 168 | 9 | 37 | 1 | 1 |  | 2/1 - BACK |  | SHIPPED 2/2
99746 | 2072.8 | 60 | 2021-02-05 | 3 | 2021-01-29 | 2021-02-03 |  | X | 44 | 13 | 23 | 0 | 1 |  | 2/1 - BACK |  | SHIPPED 2/2
98847 | 4434 | 200/3000 | 2021-03-05 | 3 | N/C | 1/28* |  | X | 20 | 3 | 14 | 1 | 1 |  | 1/27 - BOT SIDE |  | SHIPPED 2/2
99017 | 82.66 | 1 | 2020-01-12 | 15 | 2021-01-13 | 2021-02-03 |  | X | 204 | 17 | 87 | 0 | 1 |  | 2/1 SHIP 49 |  | SHIPPED 2/1
99017 | 4050.34 | 50 | 2020-01-12 | 15 | 2021-01-13 | 2021-02-03 |  | X | 204 | 17 | 87 | 0 | 1 |  | 1/29 - QA |  | SHIPPED 2/1
98279 | 920.51 | 7 |  | 3 | N/C | 2021-02-01 |  | X | 202 | 61 | 97 | 1 | 1 |  | 1/29 - BOT SIDE |  | SHIPPED 2/1
99740 | 3580 | 100 | 2021-02-01 | 3 | 2021-01-27 | 2021-02-01 |  | X | 7 | 1 | 4 | 1 | 1 |  | 1/29 - BACK |  | SHIPPED 2/1
99639 | 750 | 35 | 2021-01-29 | 10 | 2021-01-21 | 2021-02-04 |  | X | 45 | 10 | 22 | 1 | 1 |  | RONC B97316. Same program/setup |  | SHIPPED 1/29
94714 | 0 | 248 | [14 empty] | SHIPPED 1/29
99470 | 2000 | 20 | 2021-02-02 | 5 | 2021-01-26 | 2021-02-02 |  | X | 298 | 1 | 68 | 0 | 1 |  | 1/27 - TOP SIDE |  | SHIPPED 1/29
99183 | 4354 | 40 | 2021-02-05 | 10 | 2021-01-20 | 2/2* |  | X | 378 | 25 | 105 | 0 | 1 |  | 1/26 - TOP SIDE |  | SHIPPED 1/29
99471 | 2304 | 100 | 2021-02-08 | 10 | 2021-01-25 | 2021-02-02 |  | X | 138 | 11 | 44 | 0 | 1 |  | 1/27 - BACK |  | SHIPPED 1/29
94714 | 0 | 287 | [12 empty] | RMA |  | SHIPPED 1/28
98847 | 6651 | 300/3000 | 2021-03-05 | 3 | 2021-02-11 | 1/28* |  | X | 20 | 3 | 14 | 1 | 1 |  | 1/27 - BOT SIDE |  | SHIPPED 1/27
94715 | 0 | 338 | [12 empty] | RMA |  | SHIPPED 1/27
98881 | 3589.5 | 50 | 2020-01-12 | 15 | 2021-01-12 | 2021-02-02 |  | X | 177 | 18 | 50 | 1 | 1 |  | 1/26 - AOI |  | SHIPPED 1/27
99034 | 5951 | 100 | 2021-01-25 | 10 | 2021-01-20 | 2021-01-27 |  | X | 227 | 1 | 103 | 1 | 1 |  | 1/26 - BACK | 2 SIDE | SHIPPED 1/27
94714 | 0 | [13 empty] | RMA |  | SHIPPED 1/26
94715 | 0 | [13 empty] | RMA |  | SHIPPED 1/26
98520 | 3947.2 | 24 | 2020-12-03 | 5 | 2021-01-21 | 2021-01-28 |  | X | 633 | 2 | 28 | 1 | 1 |  | 1/25 - BACK | 1 SIDE | SHIPPED 1/26
99295 | 3414.5 | 25 | 2021-01-29 | 5 | 2021-01-21 | 2021-01-28 |  | X | 351 | 21 | 35 | 0 | 1 |  | 1/25 - BACK |  | SHIPPED 1/26
98964 | 3549.6 | 60 | 2020-01-29 | 10 | 2021-01-15 | 2021-01-29 |  | X | 230 | 2 | 70 | 1 | 1 |  | 1/22 - AOI/BACK |  | SHIPPED 1/25
99332 | 3916.8 | 40 | 2021-01-25 | 3 | 2021-01-21 | 1/26* |  | X | 150 | 15 | 50 | 0 | 1 |  | 1/22 - BACK |  | SHIPPED 1/25
98877 | 4609 | 50 | 2020-01-12 | 15 | 2021-01-14 | 2021-02-04 |  | X | 333 | 45 | 39 | 1 | 1 |  | 1/21 - BACK |  | SHIPPED 1/22
98884 | 5505 | 50 | 2020-01-12 | 15 | 2021-01-07 | 2021-01-28 |  | X | 427 | 35 | 62 | 1 | 1 |  | 1/19 - BACK |  | SHIPPED 1/22
98970 | 3516.4 | 4 | 2020-01-21 | 10 | 2021-01-08 | 1/22* |  | X | 794 | 106 | 55 | 1 | 1 |  | 1/18 - BACK SHORT U3 |  | SHIPPED 1/22
98017 | 1520 | 30 | 2020-01-14 | 10 | 2021-01-14 | 2021-01-28 |  | X | 43 | 28 | 19 | 1 | 1 |  | 1/19 - AOI/BACK |  | SHIPPED 1/21
99435 | 3568.4 | 10 | 2021-01-19 | 3 | 2021-01-20 | 1/21* |  | X | 537 | 1 | 170 | 1 | 1 |  | 1/18 - PRE SET UP |  | SHIPPED 1/21
99436 | 3520.25 | 275 | 2021-01-25 | 5 | 2021-01-15 | 2021-01-22 |  | X | 45 | 0 | 9 | 1 | 1 |  | 1/19 - AOI/BACK |  | SHIPPED 1/20
98805 | 9091.8 | 70 | 2020-01-07 | 5 | 2021-01-13 | 1/20* |  | X | 582 | 12 | 76 | 1 | 1 |  | 1/14 - BACK |  | SHIPPED 1/20
99317 | 2451.92 | 14 | 2020-01-18 | 5 | 2021-01-12 | 2021-01-19 |  | X | 209 | 50 | 63 | 1 | 1 |  | 1/14 - BACK |  | SHIPPED 1/18
99486 | 2363 | 15/4 FA | 2021-01-19 | 5 | 2021-01-14 | 2021-01-21 |  | X | 386 | 31 | 88 | 1 | 1 |  | 1/18 - BACK |  | SHIPPED 1/18
98973 | 1470 | 200 | 2021-01-19 | 10 | 2021-01-13 | 2021-01-27 |  | X | 20 | 1 | 6 | 1 | 1 |  | 1/14 - BACK |  | SHIPPED 1/18
99294 | 2220 | 85 | 2020-01-27 | 20 | 2021-01-04 | 2021-02-01 | 1/18* | X | 41 | 4 | 18 | 0 | 1 |  | 1/12 - AOI |  | SHIPPED 1/14
98650 | 3745.5 | 175 | 2020-01-11 | 5 | 2021-01-08 | 2021-01-15 |  | X | 103 | 0 | 47 | 1 | 1 |  | 1/14 - QA |  | SHIPPED 1/14
99451 | 1044 | 18 |  |  |  | 2021-01-13 |  |  | 0 | 17 |  |  |  |  | R&R REWORK |  | SHIPPED 1/14
99336 | 2545 | 20 | 2020-01-15 | 10 | 2021-01-07 | 2021-01-21 |  | X | 104 | 28 | 23 | 0 | 1 |  | 1/12 - AOI |  | SHIPPED 1/13
99062 | 1750 | 10 | 2020-01-21 | 10 | 2021-01-05 | 2021-01-19 |  | X | 682 | 117 | 57 | 0 | 1 |  | 1/14 - BCK |  | SHIPPED 1/12
99161 | 2667 | 50 | 2020-01-20 | 10 | 2021-01-08 | 2021-01-22 |  | X | 2 | 0 | 2 | 0 | 1 |  |  |  | SHIPPED 1/12
97316 | 1510 | 60 | 2020-12-16 | 10 | 2020-12-31 | 2020-01-14 |  | X | 46 | 9 | 32 | 1 | 1 |  | 1/7 - AOI | 2 SIDE | SHIPPED 1/12
98649 | 8670 | 175 | 2020-01-04 | 5 | 2021-01-05 | 2021-01-12 |  | X | 247 | 2 | 70 | 1 | 1 |  | 1/11 - AOI | 2 SIDE | SHIPPED 1/12
98911 | 1433.04 | 3 | 2020-01-14 | 10 | 2021-01-11 | 1/14* |  | X | 356 | 31 | 59 | 1 | 1 |  | 1/7 - BACK | 2 SIDE | SHIPPED 1/11
94215 | 52.15 | 1 | 2020-12-21 | 10 | 2020-12-23 | 2020-01-08 |  | X | 184 | 10 | 34 | 0 | 1 |  | 1/5 - AOI | 1 SIDE | SHIPPED 1/11
98367-Rev1 | 5507 | 100 | 2020-12-21 |  | 2020-12-28 | 1/8* | 2020-01-12 | X | 216 | 13 | 37 | 2 | 0 |  | SHORT 1 PART | 1 SIDE | SHIPPED 1/8
98799 | 6057.2 | 40 | 2020-01-12 | 5 | N/C | 1/7* |  | X | 593 | 9 | 36 | 0 | 1 |  | 12/30 - SMT CLEAR ONLY | 1 SIDE | SHIPPED 1/8
94215 | 3650.85 | 71 | 2020-12-21 | 10 | 2020-12-23 | 2020-01-08 |  | X | 184 | 10 | 34 | 0 | 1 |  | 1/5 - AOI | 1 SIDE | SHIPPED 1/8
97861 | 6016.3 | 45 | 2020-01-07 | 10 | 2020-12-23 | 2020-01-08 |  | X | 562 | 18 | 120 | 2 | 2 |  | 1/7 - BACK | 2 SIDE | SHIPPED 1/7
97196 | 3238.6 | 150 | 2020-11-19 | 10 | 2020-11-23 | 2020-12-09 | 2020-01-07 | X | 113 | 4 | 48 | 0 | 2 |  | 1/4 - AOI | 1 SIDE | SHIPPED 1/7
98774 | 3441 | 300 | 2020-01-07 | 10 | 2020-12-21 | 2020-01-06 |  | X | 46 | 1 | 17 |  |  |  | 12/31 - AOI |  | SHIPPED - 1/6
99127 | 11546.28 | 34 | 2020-01-04 | 5 | N/C | 2020-01-05 | 2020-01-06 | X | 1626 | 65 | 67 | 1 | 2 |  | 12/31 - AOI | 2 SIDE | SHIPPED - 1/6
97455 | 4821.5 | 13 | 2020-01-08 | 10 | 2020-12-22 | 2020-01-07 |  | X | 371 | 87 | 52 | 1 | 1 |  | 1/4 - AOI/BACK | 2 SIDE | SHIPPED - 1/6
97539 | 1460 | 200 | 2020-11-25 | 10 | 2020-12-21 | 2020-01-06 |  | X | 8 | 1 | 5 | 0 | 1 |  | 12/31 - BACK | 1 SIDE | SHIPPED 1/5
97160 | 19350 | 10 | 2020-12-28 | 5 | 2021-12-29 | 2020-01-05 |  | X | 2968 | 38 | 131 | 2 | 3 |  | 12/31 - BACK | 2 SIDE | SHIPPED 1/5
98958 | 4480 | 25/30 | 2020-12-24 | 10 | 2020-12-22 | 2020-01-04 |  | X | 624 | 3 | 126 | 2 | 2 |  | 12/31 - BACK | 2 SIDE | SHIPPED 1/4
99129 | 2150 | 100 | 2020-01-07 | 5 | N/C | 2020-01-05 |  | X | 2 | 0 | 2 |  | HL |  | 12/31 - BACK | 1 SIDE | SHIPPED 1/4
96986 | 2072.4 | 290 | 2020-12-15 | 10 | N/C | 2020-12-21 |  | X | 4 | 4 | 3 |  |  |  | 12/10 - BACK |  | SHIPPED 1/4
99033 | 1810 | 2 | 2020-12-30 | 5 | 2020-12-24 | 2020-01-04 |  | X | 2 | 40 | 1 |  |  |  | 12/24 - BACK |  | SHIPPED 1/4
94714 | 1095.75 | 225 |  |  | 2020-12-28 | 2020-12-31 |  | X | 6 | 0 | 6 |  |  |  | 12/30 - TOP SIDE | 1 SIDE | SHIPPED 12/31
98648 | 5765 | 175 | 2020-12-23 | 5 | 2020-12-17 | 2020-12-24 | 2020-12-31 | X | 145 | 4 | 69 |  |  |  | 12/29 - AOI |  | SHIPPED 12/31
94715 | 1498.5 | 675 |  |  | 2020-12-28 | 2020-12-31 |  | X | 6 | 0 | 6 |  |  |  | 12/30 - BACK | 1 SIDE | SHIPPED 12/31
98944 | 6296.5 | 50 | 2020-12-30 | 10 | 2020-12-17 | 2020-01-04 |  | X | 554 | 0 | 36 |  |  |  | 12/29 - AOI |  | SHIPPED 12/31
98958 | 896 | 5/30 | 2020-12-24 | 5 | 2020-12-22 | 2021-12-30 |  | X | 624 | 3 | 126 | 2 | 2 |  | 12/31 - BACK | 2 SIDE | SHIPPED 12/30
98191 | 1950 | 350 | 2020-12-15 | 20 | 2020-12-03 | 2020-12-30 |  | X | 88 | 0 | 32 |  |  |  | 12/28 - NEED AOI |  | SHIPPED 12/30
98152 | 4499.95 | 45 | 2020-12-17 | 10 | 2020-12-14 | 2020-12-29 |  | X | 390 | 7 | 118 |  |  |  | 12/28 - NEED AOI |  | SHIPPED 12/29
96705 | 3625 | 10 |  |  | 2020-12-21 | 2020-12-29 |  | X | 929 | 7 | 152 |  |  |  | 12/24 - BACK |  | SHIPPED 12/29
98155 | 4642 | 225 | 2020-12-18 | 10 | 2020-12-14 | 2020-12-29 |  | X | 93 | 1 | 49 |  |  |  | 12/24 - BACK |  | SHIPPED 12/28
97471 | 1748.4 | 15 | 2020-10-22 | 5 | 2020-10-22 | 2020-10-29 |  | X | 230 | 18 | 84 |  |  |  | BAL - SHORTAGE 12/28 | 1 SIDE | SHIPPED 12/28
98449 | 1615.4 | 10 | 2020-12-10 | 5 | 2020-12-18 | 2020-12-28 |  | X | 301 | 13 | 64 |  |  |  | 12/22 - BACK |  | SHIPPED 12/24
98782 | 7591 | 50 | 2020-12-17 | 5 | 2020-12-18 | 2020-12-28 | 2020-12-24 | X | 647 | 3 | 111 |  |  |  | 12/24 - BACK |  | SHIPPED 12/24
98578 | 6844.4 | 7 | 2020-12-09 | 3 | N/C | 2020-12-21 | 2020-12-24 | X | 1602 | 21 | 251 |  |  |  | 12/22 - BACK |  | SHIPPED 12/24
98265 | 4116.7 | 15 | 2020-12-15 | 5 | 2020-12-17 | 2020-12-24 |  | X | 1238 | 26 | 57 | 1 | 1 |  | 12/22 - AOI/BACK |  | SHIPPED 12/23
98626 | 11546 | 50 | 2020-12-15 | 10 | N/C | 2020-12-28 |  | X | 1053 | 0 | 219 | 2 | 3 |  | 12/22 - BACK |  | SHIPPED 12/23
98801 | 3589.5 | 30 | 2020-12-21 | 5 | 2020-12-15 | 2020-12-22 |  | X | 324 | 18 | 71 | 0 | 2 |  | 12/17 - AOI/BACK | 1 SIDE | SHIPPED 12/21
98192 | 1950 | 350 | 2020-12-15 | 20 | 2020-12-01 | 2020-12-29 |  | X | 65 | 0 | 19 |  |  |  | 12/16 - AOI |  | SHIPPED 12/18
96986 | 2072.4 | 200 | 2020-12-15 | 10 | N/C | 2020-12-17 |  | X | 5 | 4 | 6 |  |  |  | 12/10 - BACK |  | SHIPPED 12/17
98269 | 5124.8 | 40 | 2020-12-16 | 3 |  | 2020-12-16 |  | X | 390 | 5 | 127 | 2 | 2 |  | 12/15 - TOP SIDE |  | SHIPPED 12/16
97190 | 20095.63 | 79 | 2020-11-09 | 10 | 2020-10-30 | 2020-11-13 | 2020-12-16 | X | 924 | 7 | 187 | 2 | 3 |  | 12/14 - AOI/BACK | 2 SIDE | SHIPPED 12/16
98407 | 3707.2 | 80 | 2020-12-15 | 10 | 2020-11-30 | 2020-12-14 |  | X | 202 | 0 | 35 | 1 | 1 |  | 12/11 - BACK |  | SHIPPED 12/14
93217 | 2514.98 | 1/25 | 2020-12-15 | 10 | 2020-12-07 | 2020-12-14 |  | X | 323 | 13 | 71 | 0 | 2 |  | 12/11 - BACK | 1 SIDE | SHIPPED 12/14
98067 | 6521.6 | 11 | 2020-11-24 | 5 | 2020-12-07 | 2020-12-14 |  | X | 1500 | 23 | 260 | 2 | 3 |  | 12/14 - AOI/BACK | 2 SIDE | SHIPPED 12/14
98233 | 6891 | 25 | 2020-12-08 | 15 | 2020-11-24 | 2020-12-14 |  | X | 785 | 36 | 131 | 1 | 2 |  | 12/11 - BACK |  | SHIPPED 12/14
98026 | 3318.85 | 45 | 2020-12-09 | 10 | N/C | 2020-12-14 |  | X | 240 | 15 | 95 |  |  |  | 12/10 - QA |  | SHIPPED 12/11
96768 | 5156 | 50 | 2020-12-09 | 10 | 2020-11-23 | 2020-12-09 | 2020-12-11 | X | 414 | 34 | 74 | 1 | 1 |  | 12/10 - AOI |  | SHIPPED 12/11
97196 | 2159.09 | 100 | 2020-11-19 | 10 | 2020-11-23 | 2020-12-09 |  | X | 114 | 4 | 52 | 0 | 2 |  | 12/1 - TOP SIDE | 1 SIDE | SHIPPED 12/10
97196 | 6477.28 | 300 | 2020-11-19 | 10 | 2020-11-23 | 2020-12-09 |  | X | 114 | 4 | 52 | 0 | 2 |  | 12/1 - TOP SIDE | 1 SIDE | SHIPPED 12/10
97963 | 4397.8 | 32 | 2020-11-19 | 5 | 2020-11-13 | 2020-12-09 |  | X | 357 | 1 | 98 | 2 | 2 |  | 12/8 - BOT SIDE |  | SHIPPED 12/9
98089 | 3465.6 | 8 | 2020-12-08 | 3 | 2020-12-03 | 2020-12-08 |  | X | 700 | 24 | 167 | 1 | 2 |  | 12/7 - TOP SIDE | 2 SIDE | SHIPPED 12/9
98420 | 5166.9 | 90 | 2020-12-08 | 5 | 2020-12-01 | 2020-12-08 |  | X | 336 | 0 | 73 | 2 | 2 |  | 12/7 - TOP SIDE | 2 SIDE | SHIPPED 12/9
97188 | 702 | 20/500 | 2020-11-23 | 10 | 2020-11-23 | 2020-12-02 |  | X | 52 | 1 | 29 | 0 | 1 |  | 12/1 - TOP SIDE |  | SHIPPED 12/8 CREDIT HOLD
97187 | 730 | 20/500 | 2020-11-30 | 5 | 2020-11-30 | 2020-12-02 |  | X | 60 | 2 | 32 | 1 | 1 |  | 12/1 - BACK | 2 SIDE | SHIPPED 12/8 CREDIT HOLD
98537 | 4820.75 | 25 | 2020-12-07 | 3 | 2020-12-04 | 2020-12-07 | X | NEED | 354 | 21 | 131 | 2 | 1 |  | KIT CLEAR |  | SHIPPED 12/7
96769 | 1800 | 450 | 2020-12-09 | 10 | 2020-11-20 | 2020-12-04 |  | X | 8 | 2 | 4 | 1 | 1 |  | 12/1 - BACK |  | SHIPPED 12/3
98415 | 18735 | 300 | 2020-12-03 | 3 | 2020-11-30 | 2020-12-03 |  | X | 20 | 3 | 16 |  |  |  | 11/30 - BOT DONE | 2 SIDE | SHIPPED 12/3
98112 | 3933 | 100 | 2020-12-02 | 5 | 2020-11-23 | 2020-12-02 |  | X | 163 | 0 | 48 | 1 | 1 |  | 11/30 - AOI |  | SHIPPED 12/2
97993 | 3947.2 | 240 | 2020-11-24 | 5 | 2020-11-23 | 2020-12-02 |  | X | 60 | 0 | 27 |  |  |  | 12/1 - BACK |  | SHIPPED 12/2
95129 | 7500 | 190 |  | 10 | 2020-11-16 | 2020-11-30 | 2020-12-02 | X | 299 | 4 | 87 |  |  |  | 11/30 - BACK/AOI
97933 | 2731.2 | 16 | 2020-12-01 | 5 | 2020-11-20 | 2020-12-01 |  | X | [6 empty] | 11/30 - BACK |  | SHIPPED 11/30
97925 | 3860.25 | 5 | 2020-12-01 | 5 | 2020-11-19 | 2020-11-26 | 2020-11-25 | X | [6 empty] | 11/24 - AOI |  | SHIPPED 11/25
98269 | 2358.5 | 10/50 | 2020-11-30 | 3 | 2020-11-23 | 2020-11-30 |  | X | [6 empty] | 11/24 - RTR |  | SHIPPED 11/25
97888 | 2729 | 50 | 2020-12-01 | 10 | 2020-11-10 | 2020-11-24 |  | X | [6 empty] | 11/24 - AOI |  | SHIPPED 11/24
98110 | 1540 | 30 | 2020-11-23 | 5 | 2020-11-18 | 2020-11-25 |  | X | [6 empty] | NEED FIXTURE |  | SHIPPED 11/23
98279 | 2587.3 | 3/10 | 2020-11-23 | 3 | 2020-11-16 | 2020-11-23 |  | X | [8 empty] | SHIPPED 11/20
98178 | 1615.4 | 10 | 2020-11-20 | 5 | 2020-11-13 | 2020-11-20 |  | X | [8 empty] | SHIPPED 11/20
94714 | 0 | 140 | 2020-07-06 | 20 | N/C | 2020-08-24 |  | X | X | [5 empty] | 8/24 - SHORT FAB | 1 SIDE | SHIPPED 11/20
94715 | 0 | 122 | 2020-07-02 | 3 | N/C |  | 2020-09-04 | X | X | [5 empty] | 9/2 - SHORT FAB | 1 SIDE | SHIPPED 11/20
98299 | 3046 | 25 | 2020-11-18 | 3 | 2020-11-16 | 2020-11-19 |  | X | [6 empty] | 11/18 - BACK |  | SHIPPED 11/19
97395 | 2387.1 | 30 | 2020-11-20 | 10 | 2020-11-05 | 2020-11-19 |  | X | [6 empty] | 11/18 - BACK | 1 SIDE | SHIPPED 11/19
98042 | 2274.4 | 20 | 2020-11-18 | 5 | 2020-11-12 | 2020-11-19 |  | X | [6 empty] | 11/18 - BACK |  | SHIPPED 11/19
97666 | 9611.8 | 12 | 2020-11-18 | 10 | 2020-11-03 | 2020-11-19 | 2020-11-10 | X | [6 empty] | 11/11 - BACK |  | SHIPPED 11/19
97913 | 1965 | 10 | 2020-11-25 | 10 | 2020-11-05 | 2020-11-19 |  | X | [6 empty] | 11/17 - BACK | 1 SIDE | SHIPPED 11/18
97333 | 1225 | 3 | 2020-12-02 | 15 | 2020-10-28 | 2020-11-18 |  | X |  | S | NA |  |  |  | 11/17 - AOI/BACK | 2 SIDE | SHIPPED 11/18
97963 | 4397.8 | 18/50 | 2020-11-19 | 5 | 2020-11-13 | 2020-11-18 |  | X | [6 empty] | 11/16 - BOT SIDE |  | SHIPPED 11/18
97950 | 6059 | 300 | 2020-11-16 | 5 | N/C | 2020-11-17 |  | X | [6 empty] | 11/17 - BACK | 1 SIDE | SHIPPED 11/17
97620 | 2484 | 25 | 2020-11-18 | 10 | 2020-11-03 | 2020-11-17 |  | X | [6 empty] | 11/17 - AOI/BACK | 2 SIDE | SHIPPED 11/17
95589 | 2383 | 10 | 2020-11-10 | 10 | 2020-10-30 | 2020-11-18 |  | X | [6 empty] | 11/13 - BACK |  | SHIPPED 11/17
95674 | 1355.2 | 160 |  | 5 | 2020-11-12 | 2020-11-19 |  | X | [6 empty] | 11/17 - BACK |  | SHIPPED 11/17
97878 | 1573 | 100 | 2020-11-16 | 5 | 2020-11-09 | 2020-11-16 |  | X | [6 empty] | ALL PTH/NO SMT |  | SHIPPED 11/16
94979 | 3064.32 | 3 | 2020-07-13 | 5 | 2020-11-09 | 2020-11-16 |  | X | NEED | [5 empty] | 11/12 - BACK | 2 SIDE | SHIPPED 11/16
98047 | 4850 | 300 | 2020-11-16 | 3 | 2020-11-12 | 2020-11-16 |  | X | [6 empty] | 11/13 - BACK |  | SHIPPED 11/16
98122 | 1443.08 | 86 |  |  |  | 2020-11-11 | 2020-11-12 | [7 empty] | 11/4 - BACK |  | SHIPPED 11/13
98123 | 1375.44 | 88 |  |  |  | 2020-11-11 | 2020-11-12 | [7 empty] | 11/4 - BACK |  | SHIPPED 11/13
96410 | 1807.25 | 25 | 2020-10-05 | 15 | 2020-10-19 | 2020-11-09 |  | X | NEED | S | Y |  |  |  | 11/6 - HOLD SHORT | 1 SIDE | SHIPPED 11/12
98160 | 5032 | 6 | 2020-11-12 | 5 | 2020-11-06 | 2020-11-13 |  | X | [6 empty] | 11/12 - BACK | 2 SIDE | SHIPPED 11/12
98122 | 1678 | 100 |  |  |  | 2020-11-11 | 2020-11-12 | [7 empty] | 11/4 - BACK |  | SHIPPED 11/12
98123 | 1563 | 100 |  |  |  | 2020-11-11 | 2020-11-12 | [7 empty] | 11/4 - BACK |  | SHIPPED 11/12
98122 | 1678 | 100 |  |  |  | 2020-11-11 | 2020-11-12 | [7 empty] | 11/4 - BACK |  | SHIPPED 11/11
98123 | 1563 | 100 |  |  |  | 2020-11-11 | 2020-11-12 | [7 empty] | 11/4 - BACK |  | SHIPPED 11/11
96705 | 1812.51 | 5/20 | 2020-09-23 | 5 | 2020-11-04 | 2020-11-06 | 2020-11-11 | X | X |  | Y |  |  |  | 11/9 - AOI | 2 SIDE | SHIPPED 11/11
97987 | 3086 | 2 | 2020-11-11 | 3 | 2020-11-09 | 2020-11-12 |  | X | [6 empty] | 11/11 - AOI/BACK | 2 SIDE | SHIPPED 11/11
830-37-2 | 5000 | 8 |  | 3 | [10 empty] | * 3 DAY TURN * | 2 SIDE | SHIPPED 11/10
95996-2 | 4380 | 146 | 2020-09-28 | 10 | 2020-10-28 | 2020-11-11 |  | X | X | S | NA |  |  |  | 11/4 - BACK | 1 SIDE | SHIPPED 11/10
97510 | 6620 | 100 | 2020-11-09 | 10 | 2020-10-27 | 2020-11-10 |  | X |  | S | NA |  |  |  | 11/9 - TOP SIDE | 2 SIDE | SHIPPED 11/10
96718 | 3960 | 110 | 2020-10-09 | 10 | 2020-10-22 | 2020-11-05 | 2020-11-10 | X | NEED | P | NA |  |  |  | 11/5 - TOP SIDE | 1 SIDE | SHIPPED 11/9
97815 | 2872 | 18 | 2020-11-12 | 5 | 2020-11-02 | 2020-11-09 |  | X | [6 empty] | 11/4 - RTR |  | SHIPPED 11/9
97805 | 13182 | 880 | 2020-10-29 | 5 | 2020-11-02 | 2020-11-09 |  | X |  |  | Y |  |  |  | 11/4 - BOT SIDE DONE | 2 SIDE | SHIPPED 11/9
97804 | 34980 | 2640 | 2020-11-03 | 5 | 2020-11-02 | 2020-11-09 |  | X |  |  | Y |  |  |  | 11/4 - BOT SIDE DONE | 2 SIDE | SHIPPED 11/9
830-37-1 | 6000 | 16 |  |  | ? | 2020-11-06 | [8 empty] | 11/4 -AOI | 2 SIDE | SHIPPED 11/6
SCI098K |  | 20 | [5 empty] | X | X | [5 empty] | 9/11 - BACK | 2 SIDE | SHIPPED 11/5
LOR |  | 45 | [12 empty] | 10/9 - AOI | 1 SIDE | SHIPPED 11/5
97802 | 3409 | 6 | 2020-11-06 | 5 | 2020-10-29 | 2020-11-05 |  | X | [6 empty] | 11/4 -AOI |  | SHIPPED 11/5
96693 | 3958.3 | 15 |  | 5 | 2020-10-28 | 2020-11-04 |  | X |  | S | NA |  |  |  | 11/4 - BACK | 2 SIDE | SHIPPED 11/4
92711 | 9675 | 180 | 2020-10-26 | 15 | N/C | 2020-11-02 |  | X |  | P | NA |  |  |  | 11/3 - BACK | 2 SIDE | SHIPPED 11/3
97028 | 0 | 3 |  |  |  | 2020-11-02 |  | X | X | S | NA |  |  |  | 11/3 - BACK | 1 SIDE | SHIPPED 11/3
96742 | 2067.6 | 6 | 2020-11-02 | 10 | 2020-10-21 | 2020-11-04 |  | X | NEED | S | NA |  |  |  | 11/3 - BACK | 2 SIDE | SHIPPED 11/3
92711 | 1075 | 20 | 2020-10-26 | 15 | N/C | 2020-11-02 |  | X |  | P | NA |  |  |  | 11/3 - BACK | 2 SIDE | SHIPPED 11/2
96659 | 2034.4 | 20 | 2020-09-15 | 10 | 2020-10-19 | 2020-11-02 |  | X | NEED | S | Y |  |  |  | 10/28 - FEEDER S/U | 2 SIDE | SHIPPED 11/2
96882 | 2094.7 | 30 | 2020-10-27 | 10 | 2020-10-16 | 2020-10-30 |  | X | NEED | S | Y |  |  |  | 10/29 - AOI | 2 SIDE | SHIPPED 10/30
95666 | 3818.6 | 6 | 2020-10-30 | 5 | 2020-10-22 | 2020-10-29 | 2020-10-30 | X | X | S | NA |  |  |  | 10/29 - BACK | 2 SIDE | SHIPPED 10/30
96717 | 1860 | 100 | 2020-10-08 | 10 | 2020-10-19 | 2020-10-30 | 2020-10-29 | X | X | P | NA |  |  |  | 10/28 - AOI | 2 SIDE | SHIPPED 10/29
97646 | 2139 | 10 | 2020-10-30 | 5 | 2020-10-22 | 2020-10-29 |  | X | X | S | NA |  |  |  | 10/28 - BOT SIDE | 2 SIDE | SHIPPED 10/29
97795 | 3866 | 25 | 2020-10-28 | 3 | 2020-10-26 | 2020-10-29 |  | X | X | S | NA |  |  |  | 10/28 - BOT SIDE | 1 SIDE | SHIPPED 10/29
SST-T83 |  | 4 | [14 empty] | SHIPPED 10/28
97471 | 1165.6 | 10 | 2020-10-22 | 5 | 2020-10-22 | 2020-10-29 |  | X | X | [5 empty] | 10/28 - BACK Q10/15 | 1 SIDE | SHIPPED 10/28
97213 | 1520 | 50 | 2020-10-29 | 10 | 2020-10-14 | 2020-10-28 |  | X | X |  | Y |  |  |  | 10/28 - BACK | 2 SIDE | SHIPPED 10/28
97609 | 3160 | 30 | 2020-10-27 | 5 | 2020-10-21 | 2020-10-28 |  | X | NEED | [5 empty] | 10/26 - BACK |  | SHIPPED 10/27
97610 | 3807.4 | 60 | 2020-10-27 | 5 | 2020-10-20 | 2020-10-27 |  | X | [6 empty] | 10/26 - BACK |  | SHIPPED 10/27
97023 | 90 | 5 | 2020-10-30 | 20 | 2020-09-28 | 2020-10-26 |  | X | [6 empty] | 10/26 - BACK |  | SHIPPED 10/27
97023 | 1710 | 95 | 2020-10-30 | 20 | 2020-09-28 | 2020-10-26 |  | X | [6 empty] | 10/26 - BACK |  | SHIPPED 10/26
97221 | 32.55 | 1 | 2020-10-20 | 10 | 2020-10-08 | 2020-10-22 |  | X | X |  | NA |  |  |  | 10/21 - AOI | 2 SIDE | SHORT 1 PART
96778 | 3756.25 | 25 | 2020-10-22 | 15 | 2020-10-05 | 2020-10-26 |  | X | X |  | NA |  |  |  | pics warpage | 2 SIDE | SAME AS B96450
97632 | 2362.8 | 8 | 2020-10-22 | 3 | N/C | 2020-10-23 |  | X | X | [5 empty] | 10/21 - TOP SIDE |  | * 2 DAY TURN
97339 | 3847.75 | 5 | 2020-10-16 | 5 | 2020-10-16 | 2020-10-23 |  | X | X |  | NA |  |  |  | 10/20 - RTR |  | SHIPPED 10/22
97217 | 2818.4 | 120 | 2020-10-23 | 5 | 2020-10-15 | 2020-10-22 |  | X | X |  | Y |  |  |  | 10/21 - BOT SIDE | 2 SIDE | SHIPPED 10/22
97221 | 4199 | 129 | 2020-10-20 | 10 | 2020-10-08 | 2020-10-22 |  | X | X |  | NA |  |  |  | 10/21 - AOI | 2 SIDE | SHIPPED 10/22
96835 | 3124.25 | 25 | 2020-10-20 | 5 | 2020-10-14 | 2020-10-21 |  | X | X |  | NA |  |  |  | 10/21 - NEED TOOL |  | SHIPPED 10/22
97046 | 2289.6 | 3 | 2020-10-22 | 5 | 2020-10-15 | 2020-10-22 |  | X | X |  | NA |  |  |  | 10/21 - BACK | 2 SIDE | SHIPPED 10/21
96826 | 1525 | 30 | 2020-09-24 | 3 | 2020-10-19 | 2020-10-22 |  | X | X |  | NA |  |  |  | 10/20 - BACK |  | SHIPPED 10/21
97259 | 2102.4 | 110 | 2020-10-20 | 5 | 2020-10-15 | 2020-10-22 |  | X | X |  | Y |  |  |  | 10/20 - AOI | 2 SIDE | SHIPPED 10/21
95692 | 181.7 | 1 | 2020-08-21 | 10 | 2020-10-02 | 2020-10-16 |  | X | X |  | NA |  |  |  | 10/17 - BACK | 2 SIDE | SHIPPED 10/20
94210 | 3850 | 250 | 2020-07-08 | 20 | 2020-09-22 | 2020-10-20 | 2020-10-16 | X | X |  | NA |  |  |  | 9/29 - BOT DONE | 2 SIDE | SHIPPED 10/20
97097 | 2751 | 25 | 2020-10-07 | 5 | 2020-10-13 | 2020-10-20 |  | X | X |  | YES |  |  |  | 10/19 - RTR |  | SHIPPED 10/20
97204 | 2880.7 | 5 | 2020-10-16 | 5 | 2020-10-13 | 2020-10-20 |  | X | X |  | NA |  |  |  | 10/19 - TOP SIDE |  | SHIPPED 10/20
97218 | 870 | 50 | 2020-10-20 | 5 | 2020-10-12 | 2020-10-19 | 2020-10-20 | X | X |  | NA |  |  |  | 10/19 - AOI | 2 SIDE | SHIPPED 10/20
97199 | 388.97 | 1 | 2020-10-09 | 5 | 2020-10-08 | 2020-10-15 | 2020-10-20 | X | NEED | [5 empty] | 10/19 - AOI | 2 SIDE | SHIPPED 10/20
97139 | 2326.29 | 30 | 2020-10-06 | 10 | 2020-10-05 | 2020-10-16 | 2020-10-20 | X | NEED |  | NA |  |  |  | 10/19 - BACK | 1 SIDE | SHIPPED 10/20
96493 | 3790 | 200 | 2020-10-20 | 10 | 2020-10-05 | 2020-10-19 |  | X | X |  | NA |  |  |  | 10/19 - TOP SIDE | 2 SIDE | SHIPPED 10/19
97218 | 1740 | 80 | 2020-10-20 | 5 | 2020-10-12 | 2020-10-19 |  | X | X |  | NA |  |  |  | 10/19 - AOI | 2 SIDE | SHIPPED 10/19
97199 | 3500.73 | 9 | 2020-10-09 | 5 | 2020-10-08 | 2020-10-15 | 2020-10-19 | X | NEED | [5 empty] | 10/19 - AOI | 2 SIDE | SHIPPED 10/19
97139 | 8529.71 | 110 | 2020-10-06 | 10 | 2020-10-05 | 2020-10-16 | 2020-10-19 | X | NEED |  | NA |  |  |  | 10/19 - BACK | 1 SIDE | SHIPPED 10/19
95692 | 9085 | 49 | 2020-08-21 | 10 | 2020-10-02 | 2020-10-16 |  | X | X |  | NA |  |  |  | 10/16 - BOT SIDE | 2 SIDE | SHIPPED 10/17
97050 | 1428.5 | 2/10 | 2020-10-09 | 5 | 2020-10-07 | 2020-10-14 | 2020-10-16 | X | NEED |  | Y |  |  |  | 10/16 - TOP SIDE | 2 SIDE | SHIPPED 10/16
94714 | 987 | 188 |  |  |  | 2020-10-16 |  | X | X |  | NA |  |  |  | 10/16 - TOP SIDE | 1 SIDE | SHIPPED 10/16
96755 | 2779 | 36 |  |  | 2020-10-09 | 2020-10-16 |  | X | NEED |  | NA |  |  |  | CHK CHANGES |  | SHIPPED 10/16
96630 | 6439 | 42 |  | 10 | 2020-10-02 | 2020-10-16 |  | X | X |  | NA |  |  |  | FA APPROVED | 2 SIDE | SHIPPED 10/16
97062 | 2323 | 100 | 2020-10-08 | 10 | 2020-10-01 | 2020-10-15 |  | X | X |  | NA |  |  |  | 10/15 - TOP SIDE | 2 SIDE | SHIPPED 10/15
96971 | 6642 | 50 | 2020-10-01 | 3 | 2020-10-12 | 2020-10-15 |  | X | X |  | NA |  |  |  | 10/15 - AOI | 2 SIDE | SHIPPED 10/15
97024 | 2262 | 26 | 2020-10-19 | 10 | 2020-10-01 | 2020-10-15 |  | X | X | [5 empty] | 10/9 - BACK NO AOI | 2 SIDE | SHIPPED 10/15
97025 | 3096.25 | 6 | 2020-10-05 | 10 | 2020-10-01 | 2020-10-15 |  | X | X | [5 empty] | 10/9 - BACK NO AOI | 2 SIDE | SHIPPED 10/15
97466 | 3006 | 5 | 2020-10-15 | 3 | 2020-10-12 | 2020-10-15 |  | X | X |  | NA |  |  |  | 10/13 - FEEDER S/U | 2 SIDE | SHIPPED 10/15
96450 | 2028 | 10 | 2020-09-23 | 5 | 2020-10-09 | 2020-10-16 | 2020-10-15 | X | NEED |  | NA |  |  |  | PULL IN | 2 SIDE | SHIPPED 10/15
96963 | 5000 | 240 | 2020-10-13 | 5 | 2020-10-07 | 2020-10-14 | 2020-10-15 | X | X |  | Y |  |  |  | 10/14 - AOI | 2 SIDE | SHIPPED 10/15
97001 | 676.31 | 3 | 2020-10-08 | 5 | 2020-10-07 | 2020-10-14 | 2020-10-15 | X | X |  | NA |  |  |  | 10/13 - AOI | 2 SIDE | SHIPPED 10/15
96823 | 545.9 | 1 | 2020-10-02 | 5 | 2020-10-05 | 2020-10-12 | 2020-10-15 | X | X |  | NA |  |  |  | SHIPPED 9 10/14 | 2 SIDE | SHIPPED 10/15
96551 | 1540 | 25 | 2020-09-28 | 10 | 2020-09-29 | 2020-10-13 | 2020-10-16 | X | X | [5 empty] | 10/7 - BACK | 2 SIDE | SHIPPED 10/15
97063 | 2100 | 44 | 2020-10-15 | 5 | 2020-10-07 | 2020-10-14 |  | X | X |  | Y |  |  |  | 10/13 - TOP SIDE | 2 SIDE | SHIPPED 10/14
97001 | 2254 | 7 | 2020-10-08 | 5 | 2020-10-07 | 2020-10-14 |  | X | X |  | NA |  |  |  | 10/13 - AOI | 2 SIDE | SHIPPED 10/14
96823 | 5459 | 9 | 2020-10-02 | 5 | 2020-10-05 | 2020-10-12 | 2020-10-14 | X | X |  | NA |  |  |  | 10/13 - AOI | 2 SIDE | SHIPPED 10/14
96613 | 3506 | 25 | 2020-10-06 | 5 | 2020-10-07 | 2020-10-14 |  | X | X |  | NA |  |  |  | 10/13 - BACK | 2 SIDE | SHIPPED 10/14
96858 | 8036 | 100 | 2020-10-13 | 10 | 2020-09-30 | 2020-10-14 |  | X | X |  | NA |  |  |  | 10/8 - BACK | 2 SIDE | SHIPPED 10/14
95180 | 2517.5 | 25 | 2020-10-12 | 5 | 2020-10-06 | 2020-10-13 |  | X | X |  | NA |  |  |  | 10/9 - AOI | 1 SIDE | SHIPPED 10/13
96855 | 1615.4 | 10 | 2020-10-12 | 5 | 2020-10-06 | 2020-10-13 |  | X | X |  | NA |  |  |  | 10/9 - AOI | 2 SIDE | SHIPPED 10/13
96896 | 5331 | 250 | 2020-10-13 | 10 | 2020-09-29 | 2020-10-14 |  | X | X |  | Y |  |  |  | 10/8 - AOI | 2 SIDE | SHIPPED 10/13
96705 | 1812.51 | 5/20 | 2020-09-23 | 5 | 2020-10-05 | 2020-10-12 |  | X | X |  | Y |  |  |  | 10/9 - BACK NO AOI | 2 SIDE | SHIPPED 10/12
96624 | 10861 | 80 |  |  | 2020-10-05 | 2020-10-12 |  | X | X |  | NA |  |  |  | 10/7 - BACK | 1 SIDE | SHIPPED 10/12
96787 | 1400 | 10 |  |  |  | 2020-10-12 |  | X | X |  | NA |  |  |  | 10/7 - BACK |  | SHIPPED 10/12
97223 | 3992.5 | 250 | 2020-10-12 | 4 | 2020-10-05 | 2020-10-09 |  | X | X |  | ? |  |  |  | 10/7 - BACK | 2 SIDE | SHIPPED 10/9
95548 | 3441 | 100 | 2020-09-17 | 10 | 2020-09-15 | 2020-09-29 | 2020-10-09 | X | X |  | NA |  |  |  | 9/25 - BACK | 1 SIDE | SHIPPED 10/9
10285(DK) |  | 50 | [5 empty] | X | X | [5 empty] | 10/3 - TOP SIDE | 2 SIDE | SHIPPED 10/8
SCI139 |  | 30 | [5 empty] | X | X | [5 empty] | 9/8 - BACK | 2 SIDE | SHIPPED 10/8
SCI0141 |  | 15 | [5 empty] | X | X | [5 empty] | 9/15 - BACK | 2 SIDE | SHIPPED 10/8
96807 | 8385 | 150 | 2020-10-08 | 10 | 2020-09-24 | 2020-10-08 |  | X | X |  | ? |  |  |  | 10/6 - AOI | 2 SIDE | SHIPPED 10/8
SLEEP |  | 5 | [5 empty] | X | X | [6 empty] | 1 SIDE | SHIPPED 10/7
96863 | 6964.85 | 19 |  | 3 | 2020-10-02 | 2020-10-07 |  | X | X |  | ? |  |  |  | 10/3 - BACK | 2 SIDE | SHIP 10/7 - 3 DAY TURN
97133 | 9449 | 300 | 2020-10-05 | 5 | 2020-09-30 | 2020-10-07 | 2020-10-01 | X | X |  | NA |  |  |  | 10/2 - BACK | 1 SIDE | SHIP 10/7-CANT BE LATE
97126 | 6286.2 | 30 | 2020-09-30 | 5 | 2020-09-28 | 2020-10-07 |  | X | X |  | NA |  |  |  | 10/2 - BACK | 2 SIDE | SHIP 10/7
97061 | 3304.3 | 200 | 2020-10-12 | 10 | 2020-09-23 | 2020-10-07 | 2020-10-05 | X | X |  | NA |  |  |  | 10/1 - BACK | 2 SIDE | SHIP 10/7
95933 | 2112.5 | 10 | 2020-09-29 | 10 | 2020-09-21 | 2020-10-05 | 2020-10-06 | X | X |  | NA |  |  |  | WRONG DATE 10/8 | 2 SIDE | SHIPPED 10/6
96782 | 2347.6 | 35 | 2020-09-10 | 5 | 2020-09-15 | 2020-09-22 |  | X | X |  | NA |  |  |  | 9/16 - HOLD RWK | 2 SIDE | SHIPPED 10/6
96321 | 9250 | 1000 | 2020-09-24 | 15 | 2020-09-15 | 2020-10-06 | 2020-09-30 | X | X |  | Y |  |  |  | 9/16 - BACK | 2 SIDE | SHIPPED 10/6
SCI0141 |  | 50 | [5 empty] | X | X | [5 empty] | 9/15 - BACK | 2 SIDE | SHIPPED 10/5
SST-T13 |  | 50 | [5 empty] | X | X | [5 empty] | 9/21 - TOP SIDE (50) | 2 SIDE | SHIPPED 10/5
97071 | 2843.68 | 30 | 2020-10-05 | 5 | 2020-09-29 | 2020-10-06 | 2020-10-05 | X | X |  | NA |  |  |  | 10/2 - AOI | 2 SIDE | SHIPPED 10/5
96316 | 2205 | 100 | 2020-10-07 | 15 | 2020-09-17 | 2020-10-08 | 2020-10-05 | X | X |  | NA |  |  |  | 10/1 - BACK | 1 SIDE | SHIPPED 10/5
96906 | 1486.8 | 5 | 2020-09-29 | 5 | 2020-09-28 | 2020-10-05 | 2020-10-02 | X | X |  | NA |  |  |  | 10/1 - BACK | 2 SIDE | SHIPPED 10/5
96060 | 1200 | 10 | 2020-09-30 | 10 | DF | 2020-10-05 | 2020-09-30 | X | X |  | NA |  |  |  | 9/29 - BACK | 1 SIDE | SHIPPED 10/5
96777 | 4515 | 29 | 2020-10-01 | 5 | 2020-09-25 | 2020-10-02 |  | X | X |  | NA |  |  |  | 10/1 - BACK | 1 SIDE | SHIPPED 10/5
96883 | 5073.5 | 50 | 2020-10-02 | 5 | 2020-09-28 | 2020-10-05 | 2020-10-01 | X | X |  | Y |  |  |  | 10/1 - AOI | 2 SIDE | SHIPPED 10/2
96116 | 16370 | 1000 | 2020-09-24 | 15 | 2020-09-14 | 2020-10-05 | 2020-09-30 | X | X |  | NA |  |  |  | 9/18 - BACK | 2 SIDE | SHIPPED 10/2
SLEEP |  | 5 | [5 empty] | X | X | [5 empty] | 9/29 - TOP SIDE | 2 SIDE | SHIPPED 10/1
97119 | 3291.45 | 15 | 2020-10-01 | 3 | 2020-09-28 | 2020-10-01 |  | X | X |  | NA |  |  |  | 9/29 - BACK | 1 SIDE | SHIPPED 10/1
96328 | 3912.5 | 125 | 2020-09-15 | 10 | 2020-09-18 | 2020-10-02 | 2020-09-30 | X | X |  | NA |  |  |  | 9/25 - BACK | 1 SIDE | SHIPPED 10/1
96898 | 1671.75 | 250 | 2020-10-13 | 10 | 2020-09-29 | 2020-10-13 | 2020-09-30 | X | X |  | ? |  |  |  | 9/29 - BACK | 2 SIDE | SHIPPED 10/1
SCI0141 |  | 20 | [5 empty] | X | X | [6 empty] | 2 SIDE | SHIPPED 9/30
SST-T13 |  | 30 | [5 empty] | X | X | [6 empty] | 2 SIDE | SHIPPED 9/30
96898 |  | 50 | 2020-10-13 | 10 | 2020-09-29 | 2020-10-13 | 2020-09-30 | X | X | [6 empty] | 2 SIDE | SHIPPED 9/30
96896 |  | 50 | 2020-10-13 | 10 | 2020-09-29 | 2020-10-13 | 2020-09-30 | X | X | [6 empty] | 2 SIDE | SHIPPED 9/30
SCI0141 |  | 20 | [5 empty] | X | X | [6 empty] | 2 SIDE | SHIPPED - 9/29
SCI139 |  | 30 | [5 empty] | X | X | [6 empty] | 2 SIDE | SHIPPED - 9/29
ROYAL |  | 60 |  |  |  |  | 2020-09-29 | X | X | [6 empty] | 2 SIDE | SHIPPED - 9/29
96354 |  | 80 | 2020-10-01 | 10 | 2020-09-16 | 2020-09-30 |  | X | X | [6 empty] | 2 SIDE | SHIPPED - 9/29
97028 |  | 8 | 2020-09-25 | 5 | 2020-09-24 | 2020-10-01 |  | X | X | [6 empty] | 1 SIDE | SHIPPED - 9/29
96682 |  | 10 | 2020-10-05 | 10 | 2020-09-18 | 2020-10-02 | 2020-09-30 | X | X | [6 empty] | 2 SIDE | SHIPPED - 9/29
PINK |  | 1 | [14 empty] | SHIPPED 9/28
PINK |  | 1 | [14 empty] | SHIPPED 9/28
96661 |  | 100 | 2020-09-30 | 10 | 2020-09-16 | 2020-09-30 |  | X | X | [6 empty] | 1 SIDE | SHIPPED 9/28
96744 |  | 880 | 2020-09-11 | 5 | 2020-09-21 | 2020-09-28 |  | X | X |  | Y |  |  |  |  | 2 SIDE | SHIPPED 9/28
96743 |  | 2640 | 2020-09-16 | 5 | 2020-09-21 | 2020-09-28 |  | X | X |  | Y |  |  |  |  | 2 SIDE | SHIPPED 9/28
SCI139 |  | 20 | [5 empty] | X | X | [6 empty] | 2 SIDE | SHIPPED 9/25
SCI0141 |  | 20 | [5 empty] | X | X | [6 empty] | 2 SIDE | SHIPPED 9/25
SST-T13 |  | 20 | [5 empty] | X | X | [6 empty] | 2 SIDE | SHIPPED 9/25
COMBO |  | 3 | [5 empty] | X | X | [6 empty] | 2 SIDE | SHIPPED 9/24
96693 |  | 2/15 | 2020-09-28 | 5 | 2020-09-21 | 2020-09-25 |  | X | X | [7 empty] | SHIPPED 9/24
96637 |  | 50 | 2020-09-18 | 5 | 2020-09-18 | 2020-09-25 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 9/24
95308 |  | 80 | 2020-07-22 | 5 | 2020-09-08 | 2020-09-17 | 2020-09-24 | X | X | [6 empty] | 1 SIDE | SHIPPED 9/24
COMBO |  | 5 | [5 empty] | X | X | [6 empty] | 2 SIDE | SHIPPED 9/23
SCI139 |  | 30 | [5 empty] | X | X | [6 empty] | 2 SIDE | SHIPPED 9/23
96373 |  | 100 | 2020-09-17 | 15 | 2020-09-10 | 2020-10-01 | 2020-09-28 | X | X | [6 empty] | 2 SIDE | SHIPPED 9/23
96721 |  | 2/20 | 2020-09-21 | 5 | 2020-09-21 | 2020-09-28 | 2020-09-24 | X | X | [6 empty] | 2 SIDE | SHIPPED 9/23
96867 |  | 108 | 2020-09-22 | 10 | 2020-09-14 | 2020-09-28 |  | X | X | [6 empty] | 2 SIDE | SHIP 9/23
95300 |  | 1/3 | 2020-09-02 | 5 | 2020-09-19 | 2020-09-25 | 2020-09-23 | X | X |  | Y |  |  |  |  | 2 SIDE | SHIP 9/23
SCI0141 |  | 40 | [5 empty] | X | X | [6 empty] | 2 SIDE | NEED 170 BY 9/30, 100 BY 10/2
SCI098K |  | 20 | [5 empty] | X | X | [6 empty] | 2 SIDE | SHIPPED 9/22
96557 |  | 2 | 2020-09-08 | 2 | 2020-09-21 | 2020-09-23 |  | X | X | [6 empty] | 2 SIDE | SHIP BY 9/23
96863 |  | 2/21 | 2020-09-22 | 3 | 2020-09-18 | 2020-09-23 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 9/21
96959 |  | 10 | 2020-09-22 | 3 | 2020-09-18 | 2020-09-23 |  | X | X | [6 empty] | 1 SIDE | SHIPPED 9/21
96827 |  | 30 | 2020-09-24 | 3 | 2020-09-17 | 2020-09-22 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 9/21
94979 |  | 2 |  | 5 | 2020-09-15 | 2020-09-22 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 9/21
97015 |  | 28 | 2020-09-24 | 3 | 2020-09-18 | 2020-09-23 |  | X | X | [6 empty] | 1 SIDE | SHIPPED 9/19
97030 |  | 10 | 2020-09-21 | 3 | 2020-09-17 | 2020-09-22 |  | X | X | [6 empty] | 1 SIDE | SHIPPED 9/19 PICK UP???
SCI139 |  | 60 | [5 empty] | X | X | [6 empty] | 2 SIDE | SHIP 100 BY 9/18
SCI0141 |  | 30 | [5 empty] | X | X | [6 empty] | 2 SIDE | SHIP 100 BY 9/25
96414 |  | 75 | 2020-09-02 | 10 | 2020-09-17 | 2020-10-01 |  | X | X | [6 empty] | 1 SIDE | SHIPPED 9/18
95390 |  | 15 | 2020-08-21 | 15 | 2020-08-25 |  | 2020-09-21 | X | X | [6 empty] | 2 SIDE | SHIPPED 9/18
94445 |  | 250 | 2020-10-01 | 10 | 2020-09-15 | 2020-09-29 | 2020-09-24 | X | X | [6 empty] | 1 SIDE | SHIPPED 9/18
96624 |  | 20 | 2020-09-18 | 3 | 2020-09-16 | 2020-09-22 | 2020-09-21 | X | X | [6 empty] | 2 SIDE | SHIPPED 9/18
95462 |  | 30 | 2020-08-17 | 10 | 2020-09-10 | 2020-09-24 | 2020-09-22 | X | X | [6 empty] | 2 SIDE | SHIP 9/17
93997 |  | 1 | 2020-09-17 | 5 | 2020-09-11 | 2020-09-18 |  | X | X | [6 empty] | 1 SIDE | SHIP 9/17
96643 |  | 6 | 2020-09-16 | 5 | 2020-09-11 | 2020-09-18 | 2020-09-16 | X | X | [6 empty] | 2 SIDE | SHIP 9/17
MOJAVE | [15 empty] | PINK | SHIPPED 9/17
800-06182 | [15 empty] | PINK | SHIPPED 9/17
800-06152 | [15 empty] | PINK | SHIPPED 9/17
800-06151 | [15 empty] | PINK | SHIPPED 9/17
800-06159 | [15 empty] | PINK | SHIPPED 9/17
SCI098K |  | 50 | [5 empty] | X | X | [6 empty] | 2 SIDE | SHIPPED 9/16
96292 |  | 20 | 2020-09-16 | 10 | 2020-09-16 | 2020-09-30 | 2020-09-22 | X | X | [6 empty] | 2 SIDE | SHIPPED 9/16
95957 |  | 200 | 2020-09-21 | 5 | 2020-09-14 | 2020-09-21 |  | X | X | [6 empty] | 1 SIDE | SHIPPED 9/16
LOR |  | 16 | [5 empty] | X | X | [6 empty] | 2 SIDE | SHIPPED 9/15
EV20100 |  | 40 | [5 empty] | X | X | [6 empty] | 1 SIDE | SHIPPED 9/15
EV42607 |  | 50 | [5 empty] | X | X | [6 empty] | 1 SIDE | SHIPPED 9/15
96433 |  | 6 | 2020-09-16 | 5 | 2020-09-11 | 2020-09-18 | 2020-09-16 | X | X | [6 empty] | 2 SIDE | SHIPPED 9/15
96606 |  | 15 | 2020-09-16 | 5 | 2020-09-10 | 2020-09-17 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 9/15
96605 |  | 14 | 2020-09-16 | 5 | 2020-09-09 | 2020-09-16 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 9/15
95996-1 |  | 54 | 2020-09-28 | 10 | N/C |  | 2020-09-17 | X | X | [6 empty] | 1 SIDE | SHIPPED 9/15
96510 |  | 5 | 2020-09-17 | 2 | 2020-09-14 | 2020-09-16 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 9/15
96755 |  | 4 | 2020-09-17 | 3 | 2020-09-10 | 2020-09-15 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 9/14 - FA - * 3 DAY *
SCI098K |  | 50 | [5 empty] | X | X | [6 empty] | 2 SIDE | SHIPPED 9/14
95918 |  | 5 | 2020-08-19 | 5 | 2020-09-08 | 2020-09-15 |  | X | X | [6 empty] | 1 SIDE | SHIPPED 9/11
95823 |  | 65 | 2020-09-18 | 10 | 2020-09-03 | 2020-09-17 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 9/11
96630 |  | 8 | 2020-09-11 | 3 | 2020-09-09 | 2020-09-14 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 9/11
95600-2 |  | 50 | 2020-09-14 | 10 | 2020-09-03 | 2020-09-17 |  | X | X | [6 empty] | 1 SIDE | SHIPPED 9/11
95600-1 |  | 50 | 2020-09-14 | 10 | 2020-09-03 | 2020-09-17 |  | X | X | [6 empty] | 1 SIDE | SHIPPED 9/11
SCI139 |  | 70 | [5 empty] | X | X | [6 empty] | 2 SIDE | SHIPPED 9/11
4444EUB |  | 50 | [5 empty] | X | X | [6 empty] | 1 SIDE | SHIPPED 9/10
SCI139 |  | 30 | [5 empty] | X | X | [6 empty] | 2 SIDE | SHIPPED 9/9
96063 |  | 20 | 2020-09-24 | 15 | 2020-09-03 | 2020-09-25 | 2020-09-11 | X | X | [6 empty] | 1 SIDE | SHIPPED 9/9
96393 |  | 200 | 2020-09-09 | 5 | 2020-09-02 | 2020-09-09 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 9/9
96441 |  | 150 | 2020-09-17 | 20 | 2020-08-28 | 2020-09-25 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 9/8
SCI244 |  | 50 | [5 empty] | X | X | [6 empty] | 2 SIDE | SHIPPED 9/4
KAT |  | 5 |  |  |  |  | 2020-09-04 | X | X | [6 empty] | 2 SIDE | SHIPPED 9/4
96280 |  | 90 | 2020-09-02 | 3 | 2020-09-02 | 2020-09-08 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 9/4
96049 |  | 50 | 2020-08-21 | 10 | 2020-08-25 | 2020-09-08 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 9/4
95836 |  | 12 | 2020-08-31 | 10 | 2020-08-20 | 2020-09-04 | 2020-09-04 | X | X | [6 empty] | 2 SIDE | SHIPPED 9/4
SCI244 |  | 25 | [5 empty] | X | X | [6 empty] | 2 SIDE | SHIPPED 9/3
96568 |  | 10 | 2020-09-02 | 5 | 2020-08-31 | 2020-09-07 | 2020-09-04 | X | X | [6 empty] | 2 SIDE | SHIPPED 9/3
96356 |  | 17 | 2020-09-01 | 5 | 2020-08-31 | 2020-09-07 | 2020-09-04 | X | X | [6 empty] | 2 SIDE | SHIPPED 9/3
94715 |  | 84 | 2020-07-02 | 3 | 2020-08-31 |  | 2020-09-04 | X | X | [6 empty] | 1 SIDE | SHIPPED 9/3
94714 |  | 54 | 2020-07-06 | 20 | N/C | 2020-08-24 |  | X | X | [5 empty] | 8/24 - REJECTED | 1 SIDE | FINGER PRINT
SCI244 |  | 25 | [5 empty] | X | X | [6 empty] | 2 SIDE | SHIPPED 9/2
96235 |  | 3 | 2020-08-25 | 5 | 2020-08-24 | 2020-08-31 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 8/31
95703 |  | 4 | 2020-09-01 | 10 | 2020-08-19 | 2020-09-02 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 8/31
95688 |  | 4 | 2020-08-21 | 3 | 2020-08-21 | 2020-08-26 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 8/31
95680 |  | 30 | 2020-07-24 | 10 | 2020-08-07 | 2020-08-21 | 2020-08-25 | X | X | [6 empty] | 2 SIDE | SHIPPED 8/31
95351 |  | 5 | 2020-08-12 | 3 | 2020-08-27 | 2020-09-01 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 8/28
95580 |  | 60 | 2020-08-06 | 5 | 2020-08-20 | 2020-08-28 |  | X | X | [6 empty] | 1 SIDE | SHIPPED 8/28
95768 |  | 50 | 2020-07-31 | 5 | 2020-08-21 | 2020-08-28 |  | X | X | [6 empty] | 1 SIDE | SHIPPED 8/28
95294 |  | 501 | 2020-07-22 | 10 | 2020-08-17 | 2020-08-31 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 8/27
94987 |  | 3 | 2020-07-24 | 10 | 2020-08-14 | 2020-08-28 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 8/27
96284 |  | 100 | 2020-08-28 | 5 | 2020-08-20 | 2020-08-27 |  | X | X | [6 empty] | 1 SIDE | SHIPPED 8/27
96364 |  | 8 | 2020-08-24 | 2 | 2020-08-26 | 2020-08-28 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 8/27
94489 |  | 3 | 2020-07-23 | 5 | 2020-08-21 | 2020-08-28 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 8/27
95761 |  | 30 | 2020-08-27 | 10 | 2020-08-12 | 2020-08-26 |  | X | X | [6 empty] | 1 SIDE | SHIPPED 8/26
95210 |  | 5 | 2020-08-27 | 10 |  | 2020-08-26 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 8/26
95294 |  | 499 | 2020-07-22 | 10 | 2020-08-17 | 2020-08-31 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 8/36
94254 |  | 13 | 2020-06-23 | 5 | 2020-08-11 | 2020-08-18 | 2020-08-24 | X | X | [6 empty] | 2 SIDE | SHIPPED QTY 9 8/24 - BAL 8/25
SCI-U0141C |  | 50 |  |  |  | 2020-08-14 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 8/25
92637 |  | 50 | 2020-06-11 | 5 |  | 2020-08-19 |  | X | 0 | 37 | 21 |  |  |  | 8/13 - BACK | 2 SIDE | SHIPPED 8/24
94714 |  | 96 | 2020-07-06 | 20 | N/C | 2020-08-24 |  | X | X | [6 empty] | 1 SIDE | SHIPPED QTY 96 - 8/24
94860 |  | 50 | 2020-07-17 | 5 | 2020-08-12 | 2020-08-20 | 2020-08-21 | X | X | [6 empty] | 2 SIDE | SHIPPED 10 8/20, BAL 8/21
94689 |  | 70 | 2020-08-14 | 3 | 2020-08-17 | 2020-08-20 | 2020-08-21 | X | X | [6 empty] | 2 SIDE | SHIPPED 8/21
94860 |  | 10 | 2020-07-17 | 5 | 2020-08-12 | 2020-08-20 | 2020-08-21 | X | X | [6 empty] | 2 SIDE | SHIPPED 8/20
95286 |  | 1836 | 2020-07-09 | 5 | 2020-08-06 | 2020-08-20 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 8/20
95287 |  | 612 | 2020-07-09 | 5 | 2020-08-06 | 2020-08-20 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 8/20
95820 |  | 30 | 2020-08-11 | 5 | 2020-08-12 | 2020-08-19 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 8/20
96172 |  | 10 | 2020-08-18 | 3 | 2020-08-17 | 2020-08-20 |  | X | X | [6 empty] | 1 SIDE | SHIPPED 8/20
95983 |  | 10 | 2020-08-03 | 5 | 2020-08-11 | 2020-08-18 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 8/19
94441 |  | 50 | 2020-07-16 | 10 | 2020-08-04 | 2020-08-18 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 8/19
95943 |  | 48 | 2020-08-17 | 5 | 2020-08-11 | 2020-08-18 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 8/19
95303 |  | 12 | 2020-08-05 | 10 | 2020-08-04 | 2020-08-18 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 8/19
95322 |  | 4 | 2020-07-21 | 5 | 2020-08-10 | 2020-08-17 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 8/18
95072 |  | 1 | 2020-08-11 | 7 | 2020-08-07 | 2020-08-18 |  | X | X | [5 empty] | 1 PC FA | 2 SIDE | SHIPPED 8/18
93689 |  | 100 | 2020-06-24 | 20 | 2020-07-31 | 2020-08-17 |  | X | X | [6 empty] | 1 SIDE | SHIPPED 8/18
95932 |  | 3 | 2020-08-17 | 5 | 2020-08-10 | 2020-08-17 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 8/17
94741 |  | 70 | 2020-06-18 | 5 | 2020-08-07 | 2020-08-14 |  | X | X | [6 empty] | 1 SIDE | SHIPPED 8/15
95726 |  | 30 | 2020-08-12 | 3 | 2020-08-11 | 2020-08-14 |  | X | X | [6 empty] | 1 SIDE | SHIPPED 8/14
95181 |  | 12 | 2020-07-10 | 10 | 2020-08-03 | 2020-08-14 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 8/14
92718 |  | 20 | 2020-07-16 | 5 | 2020-08-06 | 2020-08-13 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 8/13
95825 |  | 50 | 2020-08-10 | 3 | 2020-08-11 | 2020-08-14 |  | X | X | [6 empty] | 1 SIDE | SHIPPED 8/13
95308 |  | 20 | 2020-07-22 | 5 | 2020-08-04 | 2020-08-11 |  | X | X | [6 empty] | 1 SIDE | SHIPPED 8/12
95723 |  | 30 | 2020-07-28 | 5 | 2020-08-06 | 2020-08-13 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 8/12
95286 |  | 1500 | 2020-07-09 | 5 | 2020-08-06 | 2020-08-13 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 8/12
95287 |  | 500 | 2020-07-09 | 5 | 2020-08-06 | 2020-08-13 |  | X | X | [6 empty] | 2 SIDE | SHIPPED 8/12