## PROG PRI
| JOB | DAY TURN | LINES | THT | REQUEST DATE | PROGRAMMER | PROG STATUS | NEED BY / PROG NOTES | NOTES | REPEAT / NEW
| SSB-NWS1-1.A.1 | 10 | 103 | 7 | 2026-04-20 | NATION | requested | 2026-05-11 | 5/11 - PCB ETA | NEW
| 135458 | 10 | 120 | 1 | 2026-02-18 | NATION | requested |  | 2/27 PCB HERE, SHORT 4 ITEMS NO ETA | NEW
| 137656 | 20 | 99 | 3 | 2026-04-02 | NATION | requested |  | 4/2 PCB HERE, SHORT MANY SMT NO ETA | NEW
| 137818 | 5 | 52 | 2 | 2026-04-21 | ROBERT/NATION | DONE | 24-Apr (need to run 137819 1st) Made new program to run at the same time as 137819 | 4/24 - PCB ETA | ROWC 137819 (NATION)
| 139369 | 5 | 22 | 2 | 2026-04-21 | NATION | DONE | 2026-04-24 | 4/24 - PCB ETA | NEW
| 137819 | 5 | 54 | 2 | 2026-04-15 | NATION | DONE | 2026-04-23 | 4/24 - PCB ETA | NEW
| 136890 | 10 | 94 | 14 | 2026-04-06 | NATION | DONE | 2026-04-21 | 4/21 - SMT CLEAR, short THT M1, due 4/22 | NEW
| 139228 | 5 | 19 | 10 | 2026-04-08 | NATION | DONE | 2026-04-21 | 4/21 - KIT CLEAR (SHIP DATE 4/28) | NEW
| 136891 | 10 | 7 | 49 | 2026-04-09 | NATION | DONE | 2026-04-20 |  | NEW
| 138434 | 5 | 23 | 0 | 2026-04-10 | ROBERT/RAY | DONE | 2026-04-24 | 4/10 - PCB HERE - SHORT SMT U1, NO ETA | RONC (PHUONG)
| 139058 | 5 | 100 | 12 | 2026-04-16 | ROBERT/RAY | DONE | 2026-04-28 |  | RONC (PHUONG)
| 139297 | 5 | 5 |  | 2026-04-14 | ROBERT/RAY | DONE | 2026-04-24 |  | RONC (PHUONG)
| 139331 | 10 | 6 | 1 | 2026-04-10 | ROBERT/RAY | DONE | 2026-04-23 | 4/23 - PCB DUE | RONC (PHUONG)
| 139188 | 10 | 14 | 0 | 2026-04-07 | ROBERT/RAY | DONE | 2026-04-13 | 4/13 - KIT CLEAR (SHIP DATE 4/27) | RONC (PHUONG)
| 138910 | 5 | 117 | 28 | 2026-04-14 | NATION | DONE | 2026-04-20 |  | NEW
| 139142 | 5 | 13 | 28 | 2026-04-17 | ROBERT/NATION | DONE | 2026-04-21 |  | ROWC (NATION)
| 138771 | 5 | 147 | 1 | 2026-03-23 | NATION | DONE | 2026-04-20 | KIT CLEAR 4/17 (SHIP DATE 4/24) SHORT PCB NO ETA | NEW
| 139404 | 5 | 19 | 1 | 2026-04-10 | ROBERT/RAY | DONE | 2026-04-13 | 4/13 - KIT CLEAR (SHIP DATE 4/17) | RONC
| 138942 | 15 | 35 | 11 | 2026-04-14 | NATION | DONE | 2026-04-15 | SMT start 4/16 at the latest | NEW
| 137911 | 10 | 126 | 17 | 2026-04-02 | NATION | DONE | 2026-04-15 | 4/15 - UPDATED BOM 4/13 - KIT CLEAR (SHIP DATE 4/27) 4/8 - PCB DUE | NEW
| 139353 | 5 | 49 | 3 |  | NATION | DONE |  | KIT BOX/PCBs HERE | NEW
| 137296 | 10 | 14 | 40 | 2026-04-02 | NATION | DONE | 2026-04-13 | 4/13 - KIT CLEAR (SHIP DATE 4/27) 4/15 - PCB DUE | NEW
1 | 138409-2nd | 5 | 34 | 5 | 2026-04-13 | ROBERT/RAY | DONE | 2026-04-13 | 4/13 - KIT CLEAR (SHIP DATE 4/20) | ROWC
2 | 139238 | 5 | 69 | 38 | 2026-04-08 | NATION | DONE | 2026-04-13 | 4/13 - KIT CLEAR (SHIP DATE 4/17) 4/10 - PCB DUE | NEW
4 | 136887 | 10 | 2 | 16 | 2026-04-03 | NATION | DONE | 2026-04-13 | 4/10 - PCB DUE KIT CLEAR (SHIP DATE 4/24) | NEW
1 | 139309 | 3 | 26 | 0 | 2026-04-08 | NATION | DONE | 2026-04-13 | 4/14 - PCB DUE 4/10 - PCB DUE, SHORT SMT U1, NO ETA | NEW
1 | 139117 | 10 | 29 | 35 | 2026-04-08 | ROBERT/RAY | DONE | 2026-04-10 |  | RONC
4 | 139039 | 10 | 102 | 174 | 2026-04-07 | ROBERT/RAY | DONE | 2026-04-14 |  | ROWC
5 | 139306 | 15 | 63 | 16 | 2026-04-06 | ROBERT/RAY | DONE | 2026-04-16 |  | ROWC
2 | 138927 | 5 | 49 | 31 | 2026-04-08 | NATION | DONE | 2026-04-08 | 4/9 - PCB DUE, SHORT THT C9, NO ETA | NEW
3 | 138383 | 15 | 44 | 10 | 2026-04-03 | ROBERT/RAY | DONE | 2026-04-14 |  | ROWC
1 | 139104 | 5 | 23 | 14 | 2026-04-08 | ROBERT/RAY | DONE | 2026-04-08 |  | ROWC
1 | 138936 | 5 | 70 | 77 | 2026-03-31 | NATION | DONE | 2026-04-08 | 4/8 - SMT CLEAR, SHORT THT U7, NO ETA SHORT PCB NO ETA | NEW
1 | 136888 | 10 | 59 | 8 | 2026-04-06 | NATION | DONE | 2026-04-08 | 4/10 - PCB DUE | NEW
1 | 138436 | 5 | 13 | 1 | 2026-04-07 | ROBERT/RAY | DONE | 2026-04-07 | KIT CLEAR | RONC
2 | 139073 | 5 | 68 | 3 | 2026-04-07 | ROBERT/RAY | DONE | 2026-04-07 |  | ROWC
1 | 138057 | 10 | 119 | 14 | 2026-03-17 | NATION | DONE | 2026-04-07 | PCBs here | NEW
2 | 137912 | 10 | 77 | 11 | 2026-03-26 | NATION | DONE | 2026-04-08 | 4/7 - PCB DUE | NEW
1 | 136881 | 10 | 23 | 8 | 2026-03-31 | NATION | DONE | 2026-04-03 | 4/3 - KIT CLEAR (SHIP DATE 4/16) 4/6 - PCB DUE | NEW
2 | 137655 | 20 | 54 | 7 | 2026-04-01 | NATION | DONE | 2026-04-03 | 4/3 - PCB DUE RECEIVED - short BGA U7 (top side - no skip) due 4/7 | NEW
3 | 138799 | 5 | 73 | 7 | 2026-04-02 | NATION | DONE | 2026-04-06 | 4/7 - PCB DUE | NEW
1 | 139107 | 10 | 40 | 0 | 2026-03-26 | ROBERT/RAY | DONE | 2026-04-03 |  | RONC
2 | 139055 | 10 | 33 | 7 | 2026-03-31 | ROBERT/RAY | DONE | 2026-04-06 |  | RONC
3 | 138753 | 5 | 115 | 1 |  | LINH | DONE | 2026-04-06 |  | NEW
1 | 137118 | 5 | 22 | 14 | 2026-04-02 | NATION | DONE | 2026-04-02 | 4/2 PCB HERE, SHORT 1 SMT (D1 - CAN SKIP) NO ETA | NEW
2 | 138826 | 15 | 33 | 6 | 2026-03-25 | NATION | DONE | 2026-04-03 | 4/3 - PCB DUE | NEW
2 | 138577 | 10 | 9 | 34 | 2026-03-31 | ROBERT/RAY | DONE | 2026-04-02 |  | ROWC
3 | 138738 | 5 | 149 | 2 | 2026-03-26 | ROBERT/RAY | DONE | 2026-04-03 |  | ROWC
3 | FPGA-SJTAG1_REV.1.C.2 | EXPEDITE | 2 | 0 | 2026-04-01 | ROBERT/RAY | done | 2026-04-01 |  | RONC
1 | 138916 | 15 | 59 | 9 | 2026-03-24 | NATION | DONE | APR 2 4/3/2026 | 4/1 - KIT CLEAR (SHIP DATE 4/10) 4/3 - PCB DUE | NEW
2 | 138935 | 5 | 40 | 14 | 2026-03-24 | NATION | DONE | 2026-04-02 | 4/3 - PCB DUE | NEW
2 | 138258 | 5 | 51 | 6 | 2026-03-31 | ROBERT/RAY | DONE | 2026-04-01 |  | ROWC
1 | 138930 | 5 | 43 | 1 | 2026-04-01 | ROBERT/RAY | DONE | 2026-04-01 |  | RONC
1 | 137694 | 15 | 91 | 9 | 2026-03-20 | NATION | DONE | 2026-05-31 |  | NEW
1 | 139106 | 5 | 16 | 1 | 2026-03-27 | ROBERT/RAY | done | 2026-04-01 |  | RONC
3 | 138417 | 5 | 38 | 0 | 2026-03-24 | ROBERT/RAY | done | 2026-03-30 |  | ROWC
2 | 138734 | 10 | 100 | 12 | 2026-03-24 | LINH | DONE | 2026-03-30 | KIT CLEAR | NEW
1 | 138988 | 10 | 10 | 2 | 2026-03-27 | ROBERT/RAY | DONE | 2026-03-30 | KIT CLEAR | RONC
1 | 138968 | 5 | 133 | 1 |  | NATION | DONE |  | KIT BOX HERE - CUSTOMER REQUEST 5 BOARDS SOONER IF POSSIBLE | NEW
| 138752 | 5 | 137 | 1 | 2026-03-26 | NATION | DONE |  | 3/18 3/23 - PCB HERE, SHORT 5 ITEMS NO ETA | NEW
| 138741 | 10 | 7 | 1 |  | NATION | DONE | 2026-03-27 | 3/26 - KIT CLEAR (SHIP DATE 4/09) | NEW
1 | 138410 | 5 | 105 | 21 | 2026-03-16 | NATION/LINH | DONE | 2026-03-25 | 3/25 - PCB ETA | NEW
2 | 138934 | 5 | 63 | 46 | 2026-03-24 | LINH | DONE | 2026-03-27 |  | NEW
3 | 138874 | 3 | 47 | 32 | 2026-03-23 | LINH | DONE | 2026-03-27 |  | NEW
2 | 138425 | 5 | 8 | 0 | 2026-03-23 | NATION/ROBERT | DONE | march 23 3/25/2026 |  | ROWC
3 | 138420 | 10 | 14 | 0 | 2026-03-23 | NATION/ROBERT | DONE | march 23 3/25/2026 |  | ROWC
4 | 138415 | 5 | 88 | 0 | 2026-03-23 | NATION/ROBERT | DONE | march 23 3/25/2026 |  | ROWC
1 | 138801 | 5 | 116 | 18 | 2026-03-23 | NATION/RAY | DONE | 2026-03-23 |  | ROWC
| 138733 | 10 | 106 | 6 | 2026-03-20 | LINH | DONE | 2026-03-25 |  | NEW
| 137410 | 5 | 78 | 6 | 2026-03-23 | NATION | DONE | 2026-03-25 |  | NEW
| 137409 | 5 | 79 | 12 | 2026-03-24 | NATION | DONE | 2026-03-25 |  | NEW
| 138631 | 5 | 45 | 0 | 2026-03-23 | LINH |  | 2026-03-23 |  | NEW
| 138414 | 5 | 35 | 2 | 2026-03-17 | NATION | DONE | 2026-03-24 | 3/24 - PCB ETA | NEW
| OCTO-FPGA | 10 | 209 | 2 | 2026-03-23 | NATION | DONE | 2026-03-25 |  | ROWC
| 138430 | 5 | 2 | 0 | 2026-03-23 | NATION/ROBERT | DONE |  |  | ROWC
| 138424 | 10 | 7 | 1 | 2026-03-23 | NATION/ROBERT | DONE | 2026-03-23 |  | ROWC
| 138413 | 5 | 16 | 0 | 2026-03-23 | NATION/RAY | DONE | 2026-03-23 |  | ROWC
| 137864 | 5 | 78 | 1 | 2026-03-20 | NATION | DONE | 2026-03-20 | 3/20 - KIT CLEAR (SHIP DATE 3/27) | NEW
| 138245 | 5 | 66 | 37 | 2026-03-19 | NATION | DONE |  | 3/19 - KIT CLEAR (SHIP DATE 3/26) | NEW
| 138392 | 3 | 127 | 13 | 2026-03-13 | NATION | DONE | 2026-03-18 | 3/19 - PCB ETA | NEW
| 138563 | 10 | 23 | 12 | 2026-03-13 | NATION | DONE | 2026-03-18 | 3/18 - KIT CLEAR (SHIP DATE 3/27) | NEW
| 138137 | 10 | 66 | 25 |  | NATION | DONE | 2026-03-17 | 3/17 - PCB ETA | NEW
| 138409 | 3 | 33 | 6 | 2026-03-16 | NATION | DONE | 2026-03-18 | 3/17 - PCB HERE, SHORT 2 ITEMS | NEW
| 137848 | 10 | 147 | 26 | 2026-03-05 | NATION | DONE | 2026-03-13 | 3/16 - KIT CLEAR (SHIP DATE 3/25) 3/13 - PCB ETA | NEW
| 138291 | 5 | 185 | 33 | 2026-03-02 | NATION | DONE | 2026-03-14 | 3/4 - PCB HERE, SHORT 10 ITEMS NO ETA | NEW
| 138643 | 5 | 26 | 0 |  | NATION | DONE | 2026-03-11 |  | NEW
| 138271 | 15 | 6 | 1 | 2026-03-05 | NATION | DONE | 2026-03-10 | 3/9 - KIT CLEAR (SHIP DATE 3/30) | NEW
| 138677 | 1 | 1 | 33 |  | NATION | DONE |  | 3/6 - MATERIAL HERE | NEW
| 138506 | 3 | 29 | 35 |  | NATION | DONE |  | 3/6 - MATERIAL HERE/PCB HERE | ROWC
| 135989 | 5 | 166 | 26 | 2026-03-06 | NATION | DONE |  | 3/9 - PCB ETA | NEW
| 138200 | 10 | 220 | 19 | 2026-02-23 | NATION | DONE | 2026-03-06 | 3/6 - PCB DUE | NEW
| 137770 | 10 | 30 | 88 | 2026-03-05 | NATION | DONE | 2026-03-05 |  | NEW
| 137845 | 10 | 183 | 37 | 2026-03-04 | NATION | DONE |  | 3/5 - PCB DUE | NEW
| 138241 | 10 | 5 | 0 | 2026-03-04 | NATION | DONE | 2026-03-05 | 3/4 - KIT CLEAR (SHIP DATE 03/13) | NEW
| 138324 | 5 | 121 | 37 | 2026-03-04 | NATION | DONE | 2026-03-05 |  | NEW
| 138578 | 5 | 166 | 12 | 2026-03-03 | NATION/ROBERT | DONE | 2026-03-06 | 3/9 - PCB DUE | ROWC
| 138609 | 3 | 188 | 28 |  | NATION | DONE |  |  | RONC
| 138246 | 5 | 139 | 17 |  | NATION | DONE |  | 3/3 3/5 - PCB DUE | NEW
| 135988 | 5 | 103 | 39 | 2026-02-23 | NATION | DONE | 2026-09-26 | SHORT PCB + 3 ITEMS NO ETA | NEW
| 138020 | 10 | 70 | 17 | 2026-02-23 | NATION | DONE | 2026-02-26 | 2/26 - PCB DUE | NEW
| QUAD-H1-TEST4-1.A.1 | 1 | 36 | 2 | 2026-02-24 | NATION | DONE | 2026-02-25 | PCB'S DUE 2/26 | NEW
| 138013 | 10 | 104 | 25 | 2026-02-23 | NATION | DONE | 2026-09-24 | 2/26 - PCB DUE 2/19 - SHORT PCB + 2 ITEMS START DAY 1 OR EARLIER - A LOT OF EXTRA PROCESS FOR BACK END | NEW
| 136828 | 10 | 63 | 24 |  | NATION | DONE |  | 2/19 - PCB HERE/WAITING FOR MATERIAL | NEW
| 138284 | 1 | 99 | 11 |  | NATION | DONE |  | 2/23 - PCB DUE | NEW
| 131541 | 5 | 1 | 0 |  | NATION | DONE |  |  | NEW
| 131540 | 5 | 1 | 0 |  | NATION | DONE |  |  | NEW
| 137725 | 10 | 3 | 3 |  | NATION | DONE |  | 2/26 - PCB DUE | NEW
| 138131 | 5 | 2 | 0 |  | NATION | DONE |  | 2/20 - PCB DUE | NEW
| 138337 | 5 |  |  |  | NATION | DONE |  | 2/25 PCB DUE | RONC
| 137749 | 1 | 6 | 32 | 2026-02-17 | NATION | DONE | 2026-02-17 | KIT BOX HERE | NEW
| 137778 | 5 | 38 | 8 | 2026-02-06 | NATION | DONE | 2026-02-17 | 2/16 - KIT CLEAR... 2/17* (2/16 is a holiday) - PCB DUE | NEW
| 138082 | 5 | 12 | 0 | 2026-02-12 | NATION | DONE | 2026-02-17 | 2/16 - KIT CLEAR... 2/17* (2/16 is a holiday) - PCB DUE | NEW
| 137225 | 3 | 132 | 7 | 2026-02-06 | NATION | DONE | 2026-02-12 | 2/17 - PCB DUE | NEW
| 137795 | 5 | 35 | 0 | 2026-02-06 | NATION | DONE |  | 2/13 - KIT CLEAR (SHIP DATE 2/23) 2/18 - PCB DUE | NEW
| 137874 | 10 | 1 | 1 | 2026-02-10 | NATION | DONE | 2026-02-13 | 2/12 - KIT CLEAR (SHIP DATE 2/24) 2/17* (2/16 is a holiday) - PCB DUE | NEW
| 137829 | 10 | 120 | 20 | 2026-02-06 | NATION | DONE | 2026-02-13 | 2/12 - KIT CLEAR (SHIP DATE 2/24) 2/17 - PCB DUE | NEW
| 137748 | 1 | 2 | 78 |  | NATION/RAY | DONE |  | SHORT PCB NO ETA | ROWC
| 136545 | 10 | 89 | 15 | 2026-02-11 | NATION/ROBERT | DONE | 2026-02-17 | REMAKE | NEW
| 138065 | 5 | 11 | 7 |  | NATION | DONE |  | 2/12 - PCB DUE | NEW
| 137944 | 10 | 65 | 12 |  | NATION | DONE |  | 2/18 - KIT CLEAR (SHIP DATE 2/27) | NEW
| 137377 | 10 | 2 | 0 |  | NATION | DONE |  | 2/18 - KIT CLEAR (SHIP DATE 3/26) | NEW
| 137872 | 5 | 6 | 2 | 2026-02-10 | NATION | DONE |  | 2/17 - SMT CLEAR | NEW
| 137873 | 5 | 2 | 0 | 2026-02-10 | NATION | DONE |  | 2/13 - PCB DUE | NEW

## UNREL
SHIPPED | PCB NOTES | KIT NOTES | SCHEDULING NOTES | FEEDER S/U | LINE 1 | LINE 2 | LINE 3 | JOB | QTY | SHIP DATE | PROG | STENCIL | MFG NOTES | BOTTOM | TOP | AOI | SMT LINES | SMT PLCMNTS | MACH | T/H | T/H EXT | SHIP METHOD | CUST | SALES P | HISTORY | DOC REL | KIT REL | CODE
|  |  |  | FSU |  |  |  | 114025 RONC 113426 | 20 |  |  |  | *** 1 DAY TURN *** ICs & PCBs REQ BAKING BEFORE RUN |  |  |  | 72 | 254 | 1B 1T | 22 | 440 | FEDEX P |  |  |  | SHORT PCB + 2 ITEMS |  | 12395.8
|  |  |  | FSU |  |  |  | 121433 REWORK 118749 | 6 | [11 empty] | 0 | FEDEX GRD | Thermon Heating Systems, Inc |  |  | NO DOC. |  | 2340
|  |  |  | FSU |  |  |  | 114124-3 | 16 | [11 empty] | 0 |  |  |  |  | NO DOC. |  | 11073.92
|  |  |  | FSU |  |  |  | 114307-3 | 16 | [11 empty] | 0 |  |  |  |  | NO DOC. |  | 9622.74
|  |  |  | FSU |  |  |  | 118993-2 | 30 |  |  |  | JOB CLOSED (10/17) PARTS MOVE TO B121521 | [7 empty] | 0 | UPS RED |  |  |  | NO DOC. |  | 2172
|  |  |  | FSU |  |  |  | 119432-3 | 10 | [11 empty] | 0 | FEDEX P | Phoenix Contact, Inc. |  |  | NO DOC. |  | 9997
|  |  |  | FSU |  |  |  | 119788-2 | 105 | [11 empty] | 0 | FEDEX P | Industrialex Manufacturing |  |  | NO DOC. |  | 4984.35
|  |  |  | FSU |  |  |  | 120465-2 | 90 | [11 empty] | 0 | FEDEX P | Industrialex Manufacturing |  |  | NO DOC. |  | 4257
|  |  |  | FSU |  |  |  | 120633-1 REWORK 116048 | 2 | [11 empty] | 0 | FEDEX GRD | HRL Laboratories |  |  | NO DOC. |  | 1812
|  |  |  | FSU |  |  |  | 120633-2 REWORK 116048 | 10 | [11 empty] | 0 | FEDEX GRD | HRL Laboratories |  |  | NO DOC. |  | 1023
|  |  |  | FSU |  |  |  | 121339 | 109 |  | X |  | THT Assembly Only DEPANEL MECH ASSY REQ - SEE DWG NOTES 13 & 14 LABEL PER ECO #5 TRIM LEADS 0.030 MAX PER ECO #6 INCLUDE S/N'S ON CofC |  |  |  | 0 | 0 | 0 | 44 | 4796 | FEDEX P | Boeing - Argon ST |  |  | DOC REL 11/30 |  | 1469.92
|  |  |  | FSU |  |  |  | 122309 REWORK 118686 | 91 | [11 empty] | 0 | UPS 2ND DAY | Graph-Tech USA, LLC |  |  | NO DOC. |  | 2548
|  |  |  | FSU |  |  |  | 121807 REWORK 111657 | 1 | [11 empty] | 0 | UPS 3DAY | Coastal Designs, LLC |  |  | NO DOC. |  | 400
|  |  |  | FSU |  |  |  | 123871-2 | 10 |  | X |  | 2nd Article Cancelled 11-07-2024 | [7 empty] | 0 | FEDEX P | Design Solutions Inc. |  |  | NO DOC. |  | 2298
|  |  |  | FSU |  |  |  | 124685 NEW | 25 |  | NL |  | Component lead extension to be 0.140" max PER ECO #2 SPECIAL LABEL FORMAT REQ PER ECO #6 *READ - DEPANEL PER ECO #1 |  |  |  | 57 | 218 | 1T | 29 | 725 | FEDEX P | Friedrich Air Conditioning LLC |  |  | DOC REL 3/27 |  | 2970.5
|  |  |  | FSU |  |  |  | 121281-2 | 3 |  | X |  | 2nd Article Cancelled 11-13-2024 | [7 empty] | 0 | UPS RED | Nottingham Spirk Design Associates, Inc. |  |  | NO DOC. |  | 5818.71
|  |  |  | FSU |  |  |  | 126277 NEW | 6 |  | NL | [5 empty] | 80 | 473 | 1B 1T | 9 | 54 | FEDEX P | Plexus Engineering Solutions |  |  | DOC REL 7/9 |  | 2000
|  |  |  | FSU |  |  |  | 126891 NEW | 3 |  | - |  | Cancelled 1-20-2025 *** DoD DO-C9 RATING *** on hold |  |  |  | 119 | 839 | - | 55 | 165 | FEDEX P | Scientific Research Corporation |  |  | DOC REL 7/17 |  | 5122.8
|  |  |  | FSU |  |  |  | 123007 ROWC 110511 | 162 |  | NL | [5 empty] | 13 | 28 | 1T | 2 | 324 | FEDEX P | Biomeme, Inc. |  |  | DOC REL 7/3 |  | 2901.02
|  |  |  | FSU |  |  |  | 123154 | 50 |  |  |  | Cancelled 08-22-2024 | [7 empty] | 0 | FEDEX P | TEST COACH |  |  | NO DOC. |  | 6736.5
|  |  |  | FSU |  |  |  | 127818 REWORK 126223 | 14 | [11 empty] | 0 | FEDEX P | L3 |  |  | NO DOC. |  | 1855
|  |  |  | FSU |  |  |  | 127434 | 6 |  |  |  | SNA BUILD - DISREGARD | [7 empty] | 0 | FEDE 2 DAY | Honeywell International Inc | MM |  | NO DOC. |  | 6773.28
|  |  |  | FSU |  |  |  | 127433 | 6 |  |  |  | SNA BUILD - DISREGARD | [7 empty] | 0 | FEDE 2 DAY | Honeywell International Inc | MM |  | NO DOC. |  | 7674.32
|  |  |  | FSU |  |  |  | 128713 | 250 | 10D | - |  | CANCELLED 2-10-2025 | [7 empty] | 0 | UPS GRD | Cogmedix, Inc. | JP |  | NO DOC. |  | 7985
|  |  |  | FSU |  |  |  | 125299 | 105 | 5D | [10 empty] | 0 | FEDEX P | Amazon | CV |  | NO DOC. |  | 1882.5
|  |  |  | FSU |  |  |  | 129215 | 110 | 5D | [10 empty] | 0 | FEDEX P | X-Microwave - A Quantic Company | PF |  | NO DOC. |  | 20144.7
| 12/4/24 - cancelled | 12/4/24 - cancelled |  | FSU |  |  |  | 129382 | 30 | 5D | [10 empty] | 0 | FEDEX P | Allocortech, Inc. | LA |  | NO DOC. |  | 10800
| 2/14/25 CANCELLED | 2/14/25 CANCELLED |  | FSU |  |  |  | 130070-2nd | 295 | 10D |  |  | CLASS 3 LEAD FREE WASH PROCESS "BT1, M5, M25, M3, U33" AFTER WASH *** PAID REWORK - SEE REWORK INSTRUCTIONS - PRD.WI.0612- VectorNav Soldering MK6 R2 (Vendor) & PRD.WI.0622_Mk6.3_NewADSchipSelectMod__DRAFT FAIR REQ XRAY & SAVE IMAGES DEPANEL & SAND PER ECO NOTE 3 LIST SERIAL NUMBERS ON CofC QR CODE REQ ON ESD BAG PER ASSY DRAWING ESD STICKER ON ESD BAG | [7 empty] | 0 | FEDEX P | Industrialex Manufacturing | PF | #50 exact given! | NO DOC. |  | 43304
[8 empty] | 114812-7 RONC 1ST | 50 |  |  | X | BAKE BOARDS BEFORE SHIPPING CLASS 3 DEPANEL |  |  |  | 16 | 554 | 92 | 16 | 800 | UPS RED | Precision Graphics Inc |  |  | DOC REL 10/16 |  | 5642
|  |  |  | FSU |  |  |  | 135789 | 20 | 5D |  |  | *** 9/24 - cancelledL | [7 empty] | 0 | FEDEX 2DAY | Anduril Maritime Quincy, MA | PF |  | NO DOC. |  | 12747.6 |  | x
|  |  |  | FSU |  |  |  | 130041 | 30 | 3D |  |  | Cancelled 01-02-2025 | [7 empty] | 0 | UPS GRD | Cogmedix, Inc. | JP |  | NO DOC. |  | 0 |  | x
|  |  |  | FSU |  |  |  | 131024 | 10 | 3D |  |  | 3/11 - cancelled | [7 empty] | 0 | FEDEX P | Philips Medizin Systeme Boeblingen GmbH | MM |  | NO DOC. |  | 3560 |  | x
|  |  |  | FSU |  |  |  | 130785 | 35 | 10D |  |  | *** 100% INSP REQ - BOARDS MUST BE PERFECT!!! | [7 empty] | 0 | FEDEX P | Integrated Consultants | LA |  | NO DOC. |  | 53742.15 |  | x
|  |  |  | FSU |  |  |  | 131546-BAL (AS9100-ITAR-CUI) | 45 | 10D | X | [5 empty] | 0 | 0 | 0 | 66 | 2970 | FEDEX P | Test Coach | PF |  | NO DOC. |  | 7430.4 | alta stand complete | x
|  |  |  | FSU |  |  |  | 132749 | 3 | 5D | [10 empty] | 0 | FEDEX GRD | CACI | LA |  | NO DOC. |  | 9989.1 |  | x
|  |  |  | FSU |  |  |  | 132312-2nd 2BAL RONC 1st Article | 440 | 20D | NL |  | *** QUALITY ALERT!!! - CHECK ALL LED'S - CUST FOUND LEDS NOT WORKING DUE TO SHORTS @ "U18 & U24" AS9102 FAIR REQUIRED DO NOT SKIP AOI MAKE SURE BOARDS ARE FREE AND CLEAN OF FLUX & DEBRIS |  |  |  | 23 | 319 | 1T | 0 | 0 | UPS RED | Cogmedix, Inc. | PF | REMINDER EMAIL ABOUT REFLOW - white board change reflow | DOC REL 6/24 |  | 27815.1667 | 2550 EXPEDITE FEE FOR PARTIAL | x
|  |  |  | FSU |  |  |  | 132314-2nd 2BAL RONC 1st Article | 660 | 20D | NL |  | *** QUALITY ALERT!!! - CHECK ALL LED'S - CUST FOUND LEDS NOT WORKING DUE TO SHORTS @ "U18 & U24" AS9102 FAIR REQUIRED "D1x64" CHECK POLARITY PER ECO #2 DO NOT SKIP AOI DEPANEL & SAND ADD SER #S TO CofC ADD REV TO THE PCB |  |  |  | 22 | 419 | 2T | 0 | 0 | UPS RED | Cogmedix, Inc. | PF | REMINDER EMAIL ABOUT REFLOW - white board change reflow | DOC REL 6/24 |  | 48182.4 | 2250 EXPEDITE FEE FOR PARTIAL | x
|  |  |  | FSU |  |  |  | 132891-BAL | 3 | 10D | X |  | 2ND ARTICLE CANCELLED 07-02-2025 | [7 empty] | 0 | FEDEX GRD | Diversified Supply | AJ | return label if last of B132847 & B132891 | NO DOC. |  | 2610.9 | complete ECO label w/customer labels | x
|  |  |  | FSU |  |  |  | QUAD-H1-RFCH2-1.B.2 (PLATED 2 CAVITY) NEW | 4 | 10D | NL | x |  |  |  |  | 119 | 1095 | 1B 2T | 7 | 28 |  |  |  | kick off review prior to SMT setup - PREBAKE 24 HOURS | DOC REL 6/4 |  |  |  | x
|  |  |  | FSU |  |  |  | 132716 | 25 | 10D | [10 empty] | 0 | FEDEX P | Baron Weather, Inc. | AJ |  | NO DOC. |  | 2993.75 |  | x
|  | CLOSED SHORT (7/22/2025) |  | FSU |  |  |  | 133925-BAL | 320 | 5D | X |  | CLOSED SHORT (7/22/2025) | [7 empty] | 0 | UPS RED | Reprieve Cardiovascular, Inc. | PF |  | NO DOC. |  | 7008 |  | x
|  |  |  | FSU |  |  |  | 134392 | 50 | 10D | [10 empty] | 0 | FEDEX P | HunterLab | LA |  | NO DOC. |  | 5508 |  | x
|  |  |  | FSU |  |  |  | 134207 NEW (canx 1/6/26) | 45 | 10D | NL |  | LEAD PROCESS DO NOT SKIP AOI XRAY & SAVE IMAGES *** MIN T/H FILL 75% CLEAN ALL FLUX AFTER ASSY |  |  |  | 48 | 547 | 1B 1T | 2 | 90 | FEDEX P | Washington University in St Louis | PF |  | DOC REL 9/3 |  | 8347.6 |  | x
|  |  |  | FSU |  |  |  | 135468 | 15 | 10D | [10 empty] | 0 | FEDEX P | Frencken America Inc. | MM |  | NO DOC. |  | 7355 |  | x
|  |  |  | FSU |  |  |  | 134905 | 191 | 10D | [10 empty] | 0 | FEDEX P | TMC / Technical Manufacturing Corp. | PF |  | NO DOC. |  | 11265.18 |  | x
|  |  |  | FSU |  |  |  | 135349 | 5 | 5D | [10 empty] | 0 | FEDEX P | Nextern Inc. | PF |  | NO DOC. |  | 6515 |  | x
|  |  |  | FSU |  |  |  | 135382 | 10 | 5D |  |  | Cancelled 10-02-2025 | [7 empty] | 0 | FEDEX P | Summit Interconnect Orange | LA |  | NO DOC. |  | 2730 |  | x
|  |  |  | FSU |  |  |  | 135817-BAL | 20 | ??? 3D | X |  | 10/29/2025 - BAL QTY 20 closing short | [7 empty] | 0 | FEDEX P | Nordson Corporation | AJ |  | NO DOC. |  | 8976 |  | x
|  |  |  | FSU |  |  |  | 135818-BAL | 70 | 10D | [10 empty] | 0 | FEDEX P | Hoverfly Technologies Inc | AJ |  | NO DOC. |  | 18728.5 | printed alta | x
|  |  |  | FSU |  |  |  | 136501 NEW | 50 | 5D | X |  | DEPANEL & SAND Cancelled 11-04-2025 |  |  |  | 52 | 199 |  | 5 | 250 | FEDEX P1 | Phenix Fiber Optics | MM |  | DOC REL 10/31 |  | 6091 |  | x
|  |  |  | FSU |  |  |  | 136748 | 44 | 5D | [10 empty] | 0 | FEDEX P1 | Technical Manufacturing Corp | PF |  | NO DOC. |  | 1540 |  | x
|  |  |  | FSU |  |  |  | 136778 REWORK | 73 | 10D | X |  | Cancelled 11-25-2025 | [7 empty] | 0 | FEDEX P1 | Solo Pace | PF |  | NO DOC. |  | 549.69 |  | x
|  |  |  | FSU |  |  |  | 136998-BAL | 12 | 5D | X |  | 2nd Article Cancelled 01-30-2026 Transfer remaining boards/material to B137830 | [7 empty] | 0 | UPS RED | NextPhase Medical Devices | PF |  | NO DOC. |  | 7394.4 | folder | x
|  |  |  | FSU |  |  |  | 137367-BAL | 55 | ??? 3D | X |  | 2nd Article cancelled 02-17-2026 Transfer material to B138284 and mark any left over PCBs as DNU (gerber changed). | [7 empty] | 0 | FEDEX P1 | Nordson Corporation | AJ |  | NO DOC. |  | 16624.3 | folder | x
|  |  |  | FSU |  |  |  | 135902-BAL | 45 | 5D | [10 empty] | 0 | FEDEX P1 | Hoverfly Technologies, Inc. | AJ |  | NO DOC. |  | 10465.4893 |  | x
| 2/11 - -2 QTY 2284 3/6 -3 QTY 2284 3/23 -4 QTY 2284 4/6 |  | 2/11 - RUN PARTIALS OF QTY 2284 | FSU |  |  |  | 131540-2PAR | 2284 | 10D |  |  | bal qty remain: 4568 *** P/N: 74663125R - FOLLOW MFG RECOMMENDED SOLDER PROFILE - CONFIRM W/ ROBERT CLASS 3 | [7 empty] | 0 | FEDEX 2DAY | Leidos | MM |  | NO DOC. |  | 22399.5 |  | x
| 2/11 - -2 QTY 2284 3/6 -3 QTY 2284 3/23 -4 QTY 2284 4/6 |  | 2/11 - RUN PARTIALS OF QTY 2284 | FSU |  |  |  | 131540-3PAR | 2284 | 10D |  |  | bal qty remain: 2284 *** P/N: 74663125R - FOLLOW MFG RECOMMENDED SOLDER PROFILE - CONFIRM W/ ROBERT CLASS 3 | [7 empty] | 0 | FEDEX 2DAY | Leidos | MM |  | NO DOC. |  | 22399.5 |  | x
| 2/11 - -2 QTY 2284 3/6 -3 QTY 2284 3/23 -4 QTY 2284 4/6 |  | 2/11 - RUN PARTIALS OF QTY 2284 | FSU |  |  |  | 131540-4BAL | 2284 | 10D |  |  | *** P/N: 74663125R - FOLLOW MFG RECOMMENDED SOLDER PROFILE - CONFIRM W/ ROBERT | [7 empty] | 0 | FEDEX 2DAY | Leidos | MM |  | NO DOC. |  | 22399.5 |  | x
| 2/12 - -2 QTY 2284 3/6 -3 QTY 2284 3/20 -4 QTY 2284 4/7 |  |  | FSU |  |  |  | 131541-2PAR | 2284 | 5D |  | x | bal qty remain: 4568 *** P/N: 74663125R - FOLLOW MFG RECOMMENDED SOLDER PROFILE - CONFIRM W/ ROBERT | [7 empty] | 0 | FEDEX 2DAY | Leidos | MM |  | NO DOC. |  | 46511.5 |  | x
| 2/12 - -2 QTY 2284 3/6 -3 QTY 2284 3/20 -4 QTY 2284 4/7 |  |  | FSU |  |  |  | 131541-3PAR | 2284 | 5D |  |  | bal qty remain: 2284 | [7 empty] | 0 | FEDEX 2DAY | Leidos | MM |  | NO DOC. |  | 46511.5 |  | x
| 2/12 - -2 QTY 2284 3/6 -3 QTY 2284 3/20 -4 QTY 2284 4/7 |  |  | FSU |  |  |  | 131541-4BAL | 2284 | 5D | [10 empty] | 0 | FEDEX 2DAY | Leidos | MM |  | NO DOC. |  | 46511.5 |  | x
|  |  |  | FSU |  |  |  | 137694-BAL | 200 | 15D |  | x | [8 empty] | 0 | FEDEX P1 | Access Sensor Technologies | CV |  | NO DOC. |  | 16696 |  | x
|  |  | 4/10 - confirm stencil okay (Trinh) | FSU |  |  |  | 138057-BAL | 90 | 20D |  | x | [8 empty] | 0 | FEDEX GRD | Colorado State University | CV | #1 pins | NO DOC. |  | 7559.5 |  | x
|  |  | 4/13 - job has to use reflow line 3 (Robert) setup and prep early | FSU |  |  | LINE 3 OVEN | 138444-BAL | 125 | ??? 3D | NL |  | * 3/26 - INCR QTY BY 10 (FROM FA) |  |  |  | 156 | 626 | 2B 2T | 13 | 1625 | FEDEX P1 | Hoverfly Technologies, Inc. | AJ |  | NO DOC. |  | 56253.4 |  | x
|  |  |  | FSU |  |  |  | 138908 | 5 | 5D | [10 empty] | 0 | FEDEX P1 | OXOS Medical, Inc. | PF |  | NO DOC. |  | 250 |  | x
|  |  |  | FSU |  |  |  | 138924 | 15 | 5D | [10 empty] | 0 | FEDEX P1 | Solo Pace | PF |  | NO DOC. |  | 250 |  | x
|  |  |  | FSU |  |  |  | 139092 | 100 | 10D |  |  | DEPANEL | [7 empty] | 0 | UPS RED | Nova Tech | PF |  | NO DOC. |  | 1870 |  | x
|  |  |  | FSU |  |  |  | 139309-BAL | 210 | ??? 3D |  | x | [8 empty] | 0 | FEDEX P1 | Hoverfly Technologies Inc | AJ |  | NO DOC. |  | 9870 | folder | x
|  |  |  | FSU |  |  |  | 138539 | 150 | 15D | [10 empty] | 0 | UPS RED | Benchmark Electronics | LA |  | NO DOC. |  | 4586 |  | x
|  |  |  | FSU |  |  |  | 138540 | 150 | 10D | [10 empty] | 0 | UPS RED | Benchmark Electronics | LA |  | NO DOC. |  | 3762.5 |  | x
|  |  |  | FSU |  |  |  | 139270 | 8 | 20D | [10 empty] | 0 | UPS BLUE 2 DAY | Government Contracting Specialists, Inc. | MM |  | NO DOC. |  | 5800 |  | x
|  |  |  | FSU |  |  |  | 138538 | 150 | 10D | [10 empty] | 0 | UPS Ground | Benchmark Electronics | LA |  | NO DOC. |  | 4372.5 |  | x
|  |  |  | FSU |  |  |  | 138542 | 30 | 10D | [10 empty] | 0 | UPS Ground | Benchmark Electronics | LA |  | NO DOC. |  | 2370 |  | x
|  |  |  | FSU |  |  |  | 138537 | 150 | 10D | [10 empty] | 0 | UPS Ground | Benchmark Electronics | LA |  | NO DOC. |  | 4272 |  | x
|  |  |  | FSU |  |  |  | 137096 | 10 | 10D | [10 empty] | 0 | FEDEX P1 | HRL Laboratories | LA |  | NO DOC. |  | 3306.7 |  | x
|  |  |  | FSU |  |  |  | 139429 NEW | 10 | 10D |  |  | *** SMT HEAT SINK REQ - PLACE HEAT SINK BEFORE REFLOW - SEE ECO NOTE 3 "SW1" AFTER WASH * 26 ADDTIONAL PARTS AFTER REFLOW PER ECO NOTE 6 "L5, L7, L9" VERY LARGE PARTS, MAY HAVE REFLOW/SOLDER ISSUES - ONLY REFLOW ONE TO CHECK IF PROFILE NEED ADJUSTMENTS "F1" LEAD FORMING REQUIRED DEPANEL & SAND |  |  |  | 133 | 483 |  | 40 | 400 | FEDEX P1 | Monaco Enterprises, Inc. | MM | see email (thomas) | DOC REL 4/23 |  | 8683.5 |  | x
|  |  |  | FSU |  |  |  | 136877 | 3 | 10D | [10 empty] | 0 | FEDEX P1 | Diversified Supply | AJ |  | NO DOC. |  | 7214.25 |  | x
|  |  |  | FSU |  |  |  | 136882 | 4 | 10D | [10 empty] | 0 | FEDEX P1 | Diversified Supply | AJ |  | NO DOC. |  | 3804 |  | x
|  |  |  | FSU |  |  |  | 136880 | 3 | 10D | [10 empty] | 0 | FEDEX P1 | Diversified Supply | AJ |  | NO DOC. |  | 3304.5 |  | x
|  |  |  | FSU |  |  |  | 136883 | 2 | 10D | [10 empty] | 0 | FEDEX P1 | Diversified Supply | AJ |  | NO DOC. |  | 2385 |  | x
|  |  |  | FSU |  |  |  | 139547 RONC 137272 | 250 | 5D | NL |  | ok to use J1 right angle LEAD PROCESS DEPANEL |  |  |  | 8 | 15 | 1T | 5 | 1250 | FEDEX P1 | Avtron Power Solutions | TM |  | DOC REL 4/22 |  | 5440 |  | x | uploaded
|  |  |  | FSU |  |  |  | 139628 NEW | 320 | 10D |  |  | RUN ALL AT ONCE IF CLEAR SHUNTS REQ PER ECO DEANEL 1st Shipment May 20: 40 2nd in June 10: 80 3rd in July 10: 80 4th in August 10: 40 5th in September 10: 40 6th in October 10: 40 |  |  |  | 2 | 2 | 1T | 7 | 2240 | FEDEX GRD | LongPath Technologies | CV |  | DOC REL 4/23 |  |  |  | x
|  |  |  | FSU |  |  |  | 139684 RONC 131018 | 180 | 10D | NL |  | *** NEED TO MAKE WE SEND PARTS PACKING SLIPS TO CUSTOMER PER ECO NOTE 2 CLASS 3 LEAD WASH TAG BTD or DNI & NOTE IN PAPERWORK |  |  |  | 22 | 45 | 1B 1T | 10 | 1800 | UPOS ORANGE 3DAY | Coastal Designs, LLC | TM |  | DOC REL 4/23 |  | 6021 |  | x
|  |  |  | FSU |  |  |  | 139540 | 30 | 5D | [10 empty] | 0 | FEDEX P1 | Neocis, Inc | AJ |  | NO DOC. |  | 3250 |  | x
|  |  |  | FSU |  |  |  | 139260 | 40 | 5D |  |  | do not ship early | [7 empty] | 0 | UPS RED 10:30 AM FEDEX P1 | QT Imaging Inc. | LA |  | NO DOC. |  | 5504 |  | x
|  |  |  | FSU |  |  |  | 139114 | 50 | 5D | [10 empty] | 0 | FEDEX P1 | Rogue Signal Processing Corporation | LA |  | NO DOC. |  | 8708 |  | x
|  |  |  | FSU |  |  |  | 139335 | 25 | 5D | [10 empty] | 0 | FEDEX P1 | Allocortech, Inc. | LA |  | NO DOC. |  | 7932.75 |  | x
|  |  |  | FSU |  |  |  | 139388 | 32 | 10D | [10 empty] | 0 | FEDEX P1 | Technical Manufacturing Corp | PF |  | NO DOC. |  | 2675.2 |  | x
|  |  |  | FSU |  |  |  | 139531-FA | 14 | 10D | [10 empty] | 0 | UPS GRD | Amphenol Aerospace | CV |  | NO DOC. |  | 4365 |  | x
|  |  |  | FSU |  |  |  | 139531-BAL | 73 | 10D | [10 empty] | 0 | UPS GRD | Amphenol Aerospace | CV |  | NO DOC. |  | 2956.5 |  | x
|  |  |  | FSU |  |  |  | 139736 | 9 | 5D | [10 empty] | 0 | FEDEX P1 | Solo Pace | PF |  | NO DOC. |  | 135 |  | x
|  |  |  | FSU |  |  |  | 139686 | 85 | 10D | [10 empty] | 0 | UPS GRD | Churchill Navigation dba Shotover Systems Inc | CV |  | NO DOC. |  | 6935.15 |  | x
|  |  |  | FSU |  |  |  | 138932 | 50 | 3D | [10 empty] | 0 | FEDEX P1 | Wabtec | AJ |  | NO DOC. |  | 7134 |  | x
|  |  |  | FSU |  |  |  | 138933 | 50 | 3D | [10 empty] | 0 | FEDEX P1 | Wabtec | AJ |  | NO DOC. |  | 5410 |  | x
|  |  |  | FSU |  |  |  | 139648 | 15 | 5D | [10 empty] | 0 | FEDEX 2DAY | CACI | LV |  | NO DOC. |  | 2664.9 |  | x
|  |  |  | FSU |  |  |  | 137405 | 7 | 5D | [10 empty] | 0 | FEDEX P1 | Scientific Research Corporation | AJ |  | NO DOC. |  | 17097.18 |  | x
|  |  |  | FSU |  |  |  | 137961 | 7 | 5D | [10 empty] | 0 | FEDEX P1 | Scientific Research Corporation | AJ |  | NO DOC. |  | 16874 |  | x
|  |  |  | FSU |  |  |  | 138929 | 50 | 3D | [10 empty] | 0 | FEDEX P1 | Wabtec | AJ |  | NO DOC. |  | 4567.5 |  | x
|  |  |  | FSU |  |  |  | 138931 | 50 | 3D | [10 empty] | 0 | FEDEX P1 | Wabtec | AJ |  | NO DOC. |  | 5956 |  | x
|  |  |  | FSU | [16 empty] | 0 |  |  |  |  | NO DOC. |  |  |  | x
|  |  |  | FSU | [16 empty] | 0 |  |  |  |  | NO DOC. |  |  |  | x
|  |  |  | FSU | [16 empty] | 0 |  |  |  |  | NO DOC. |  |  |  | x
Note on N66: Eric Silverio: RFQ NOTES: RWK B132705/ INSTRUCTIONS ARE TO FIX INSUFFICIENT SOLDER JOINTS OR POOR SOLDERING QUALITY ON COMPONENTS L6 AND/OR U40 LED TO AN INTERMITTENT 3.3V POWER RAIL ISSUE, CAUSING POWER INTERRUPTIONS DURING THE PROGRAMMING STEP.
Note on N67: Eric Silverio: RFQ NOTES - Rework B134516
Note on N68: Eric Silverio: BUILD NOTES RONC B130060
Note on N69: Eric Silverio: BUILD NOTES - NO COATING/NO SHIELD CANs/THT IS EDGE CONN
Note on AA69: Tad Kasai: ECO APPVD - DWG NOTES CONF
Note on N72: Eric Silverio: BUILD NOTES -RONC B125215/T/H including 1 heatsink
Note on N73: Lan: 1, Per PO date 4/15, Keep kit at Alta. Do not return. 2, Quote added AS9102 FAIR, PO not mentioned FAIR.
Note on N77: Eric Silverio: BUILD NOTES - +REMOVE CLASS 3 - SUPER HOT1/ROWC B131120 BUT NEW TO US/CLASS 3/DEPANELIZE/MECH ARE 1 HEATSINK, 4 STANTOFFS, 7 PEM NUTS AND 6 SHUNTS
Note on N78: Eric Silverio: BUILD NOTES - CLASS 3/BEND PIN 8 FIBER OPTICs TO FIT ONTO BOARDS, PLACE INSULATOR TO PREVENT SHORT, 8 FIBER OPTICs PARTS COMES WITH 32 WASHERES, 16 SCREWs/
Note on N79: Eric Silverio: BUILD NOTES - CLASS 3/ MECH ARE 2 BRACKETs, 2 SCREWs & 2 WASHERs
Note on N80: Eric Silverio: BUILD NOTES - CLASS 3/ MECH ARE 12 THREAD GUIDEs & 4 SCREWs
Note on N81: Eric Silverio: BUILD NOTES -CLASS 3/MECH ARE 2 BRACKETs, 2 SCREWs & 2 WASHER
Note on N82: Eric Silverio: BUILD NOTES - De-panel /Use Rev02 BOM/NO DWG.
Note on AA82: Tad Kasai: 4/15 - ECO APPVD - NO DWG NOTES
Note on N83: Eric Silverio: BUILD NOTES - NO DWG/MECH ARE 2 SHUNTs
Note on AA83: Tad Kasai: 4/15 - ECO APPVD - NO DWG NOTES
Note on N84: Eric Silverio: BUILD NOTES -RONC B131018/ CLASS 3
Note on AA84: Tad Kasai: 4/15 - ECO APPVD - NO DWG NOTES
Note on N85: Eric Silverio: BUILD NOTES - TH ONLY
Note on N86: Eric Silverio: build notes - ADD QTY & LT/RONC B130670/RONC B125478/RONC B134439
Note on W86: Tad Kasai: 4/22/26 - changed by customer - email 1:00pm
Note on N87: Eric Silverio: BUILD NOTES - NEW BOM /NO DWG / MECH IS SHUNT
Note on N89: Eric Silverio: BUILD NOTES - THT ONLY/CUT 2 MOUNTING LEADS OF SW1/CUT PIN Q1,Q2 & C2 FLUSHED ONTO BOARDS TO ENSURE THEY ARE NOT CONTACT TO METAL OF SW1.
Note on N90: Eric Silverio: BUILD NOTES HOT/FA/CLASS 3/COATING/MECH ARE 4 THREAD STANDOFFs, 6 SCREWs/ TORQUE SETTING REQUIRE/ALL HARDWAREs NEED TO BE LIQUID STAKED (DP-190 GRAY EPOXY/LOCTITE 242 OR EQUIPVALENT) /TRIM LEADs J2 & J3
Note on N91: Eric Silverio: BUILD NOTES HOT/FA/CLASS 3/COATING/MECH ARE 4 THREAD STANDOFFs, 6 SCREWs/ TORQUE SETTING REQUIRE/ALL HARDWAREs NEED TO BE LIQUID STAKED (DP-190 GRAY EPOXY/LOCTITE 242 OR EQUIPVALENT) /TRIM LEADs J2 & J3
Note on N93: Eric Silverio: BUILD NOTES - RONC OF B135722/RONC B131993 /RONC B129427
Note on N94: Eric Silverio: BUILD NOTES - RONC B136286
Note on N95: Eric Silverio: BUILD NOTES - RONC B136231
Note on N96: Eric Silverio: BUILD NOTES - RONC B133257 / Required Manufacturer Tests/10 edge CONN
Note on N97: Eric Silverio: BUILD NOTES - NEW FILES/ NO DWG/ P1 and P2 have to be riveted to the board with supplied rivets
Note on N98: Eric Silverio: BUILD FILES - HOT/NEW FILES/CLASS 3/NO DWG BUT BUILD INSTR/CUSTOMER SEND ALL PARTS W/PRETINNED LEAD/P1 and P2 HAVE RIVETS COUNT AS MECH/Underfill U1, U0301, U0401, U0901, U1001, U1202 with Zymet CN-1431.
Note on N99: Eric Silverio: BUILD NOTES RONC B135061
Note on N100: Eric Silverio: BUILD NOTES - RONC B136233

## SHIPPED (AA)
SHIPPED | PCB NOTES | KIT NOTES | SCHEDULING NOTES | FEEDER S/U | LINE 1 | LINE 2 | LINE 3 | JOB | QTY | SHIP DATE | PROG | STENCIL | MFG NOTES | BOTTOM | TOP | AOI | SMT LINES | SMT PLCMNTS | MACH | T/H | T/H EXT | SHIP METHOD | CUSTOMER | SALES P | KIT RELEASE / NOTE | DOC REL | KIT REL | CODE | LABEL | BOM INSPECT | ECO / BUILD NOTES | DRAWING | PROCESS | PREV RUN | BOM COMPARE / PHOTOS | THOMAS XTRA WORK | panel | pcb inspected
| clear 4/8 | 4/22 - kit clear 4/21 - short SMT D1 due 4/22 4/8 - short SMT D1 (maybe skippable), no ETA | 4/24 - OFF HOLD 4/23 - ON HOLD D1,D3 LED color issue | RTR | 1 |  |  | 139104 ROWC 137118 (ITAR) | 46 | 04/29 5D | RL | x | SPECIFIC LABEL REQ PER ECO NOTE 1 depanel |  | 4/23 - 9:00 |  | 22 | 42 | 1T | 14 | 644 | FEDEX P1 | Specialty Coating Systems, Inc. | LV |  | NO DOC. | 4/8 | 3670.8 | eco | x | reviewed | none | R C | reviewed | p/n change uploaded | #19 THT TO SMT? | 2 | 2026-04-09

## SHIP TODAY
2026-05-01
Column1 | DATE | Column3 | QTY | MFG NOTES | SHIP METHOD | CUSTOMER | SCHEDULE NOTES
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
04/29 | 04/29 | 139104 | 46 | SPECIFIC LABEL REQ PER ECO NOTE 1 depanel | FEDEX P1 | Specialty Coating Systems, Inc. | 4/24 - OFF HOLD 4/23 - ON HOLD D1,D3 LED color issue
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
DATE
#VALUE!

## HOLIDAYS
Date | Holiday
2026-01-01 | NEW YEAR
2026-02-16 | PRESIDENT'S DAY
2026-05-25 | MEMORIAL DAY
2026-07-04 | INDEPENDENCE DAY
2026-09-07 | LABOR DAY
2026-11-26 | THANKSGIVING DAY
2026-11-27 | THANKSGIVING FRIDAY
2026-12-25 | CHRISTMAS DAY
2027-01-01 | NEW YEAR

## Sheet1
139117 | 25 | 2026-04-22
136861 | 28 | 2026-04-23
139353 | 24 | 2026-04-23
138771 | 24 | 2026-04-24
138936 | 48 | 2026-04-24
139055 | 50 | 2026-04-24
137296 | 6 | 2026-04-27
139188 | 480 | 2026-04-27
137911 | 8 | 2026-04-27
137845 | 4 | 2026-04-27
138910 | 80 | 2026-04-27
138577 | 14 | 2026-04-28
138843 | 8 | 2026-04-28
139228 | 30 | 2026-04-28
139142 | 6 | 2026-04-29
139104 | 46 | 2026-04-29